## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
bb282afd-6a3d-4d9d-b14e-275b5cba33cf | checklist | M3RNAR-FUL-QAC-ITP-001 - Clearing & Grubbing Rev3 | itp | M3RNAR-FUL-QAC-ITP-001 - Clearing & Grubbing
a214731b-afae-4a40-8d18-82e96cb1b42d | section | Preliminary Works
2be3816d-64c8-4bd2-a45a-abad029333fd | checkpoint | 1.1 Check for correct documentation
bfad8f2d-f9dc-51f5-ab29-49c8fcb91f24 | note | FREQUENCY: Prior to commencing any activity
ebac9d66-9dac-5f95-8646-ea5cb6d699ad | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
992b539f-7c72-53f5-aa27-27ecc5b43aa0 | note | — using the correct and complete set of drawings
5b224209-24cb-5591-82e0-99ed22dd240e | note | — all drawings are the latest revision
665b60e4-510c-57f5-8f8b-a2b10f9cc106 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2de65081-8ba8-57b8-8700-27429ef46add | note | INSPECTION/TEST METHOD: Visual inspection
0ede915e-7b81-586c-b916-77f2309f79d9 | note | RECORD OF CONFORMITY: This ITP signed
4f0e95fa-00ce-5f3d-a403-f00a556646c2 | note | HP*
8763d41d-3372-5389-9224-17caaea9d081 | note | RESPONSIBILITY: Site Engineer / Site Foreman
dce070ef-4bc1-5316-8d95-fbd6f2d20381 | textbox | Date Completed:
ed37c0c3-ce23-4b99-85d1-e8fd985e3864 | checkpoint | 1.2 Implementation of all measures and controls
886d5d28-47ac-5bcc-baac-a9b247433036 | note | FREQUENCY: Prior to commencing any activity
a6e80e9e-7096-5c18-a6c9-b292651de34e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP,CSEMP, ERA, QMP, CHMP, SWMS, Hume Council Permit No: P25490
2f216446-ae9b-5f93-9e9b-3178673ec94a | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, CSEMP, ERA, QMP, CHMP, SWMS, Permit No: P25490
4a2b5c06-0094-537f-b7b2-ead203860012 | note | INSPECTION/TEST METHOD: Visual Inspection
629b2045-10ee-56dc-b30a-b2ce84da0e4c | note | RECORD OF CONFORMITY: This ITP signed
4fd55c40-b5d1-57bd-8657-d5c40426ccfc | note | HP*
d8b39b02-4482-5579-b289-6b151c791b34 | note | RESPONSIBILITY: Site Engineer / Site Foreman
38256f38-3878-5c61-b591-6ad296a1ddd6 | textbox | Date Completed:
5f5ba76c-e1d6-4f6d-becf-18392bdd5671 | checkpoint | 1.3 Flora & Fauna
2c2fce49-158c-51e0-9f5d-f54de7c65ee2 | note | FREQUENCY: Prior to commencing clearing
1cc13276-5078-5e85-b8d5-0a13cb736e21 | note | ACCEPTANCE CRITERIA: A qualified ecologist and/or botanist has examined trees to be removed and/or any fallen logs affected by works and provided written clearance for removal; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
b1b842a6-1ce5-5aa6-9b69-19dd5619a71e | note | REFERENCE DOCUMENTS: CEMP, ECP
549b37e0-3edc-59f6-b149-f7e1b7e979a5 | note | INSPECTION/TEST METHOD: Visual Inspection
f4265bd7-4866-54a8-b0eb-0650e3547380 | note | RECORD OF CONFORMITY: This ITP Signed off
660ce12c-5da0-5d86-a527-f2010d071323 | note | IP
e5e530a6-0152-591a-93e6-66998622ff48 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2162cc08-a0e7-5cfc-ae33-2efb98366f2e | textbox | Date Completed:
32bb349f-ae3a-4fb3-9f48-ba10b2502b98 | checkpoint | 1.4 Permit to distrurb flora & fauna
3a9348fc-48a4-572a-ae8d-5dc0a2f04535 | note | FREQUENCY: Prior to commencing clearing
8bc057a4-7d38-58b0-b56c-090c7e6e51a0 | note | ACCEPTANCE CRITERIA: Obtain Part 13 Permit & PP010l permit from APAM prior to tree removal. Obtain all other permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
6166808e-17e6-5845-86d1-ba3dadc878c9 | note | REFERENCE DOCUMENTS: CEMP, ECP
b3f946a7-35fd-5087-9ce8-909628520871 | note | INSPECTION/TEST METHOD: Visual Inspection
3699a046-6e35-5794-88d6-f9ddc4f81071 | note | RECORD OF CONFORMITY: This ITP Signed off
c4e65120-9d8d-57e4-a853-ed95e6ab4432 | note | IP
2a0202a5-386d-57d5-9a19-9039105bcf0d | note | RESPONSIBILITY: Project Engineer
b0e7493a-11f0-5b36-9b50-ce6ce3c805e6 | textbox | Date Completed:
da9b778e-9664-4987-a086-fc947d84377b | section | Clear & Grub
d7dd641b-b24e-4eb2-896e-1e8f49a57913 | checkpoint | 2.1 Lot start date
2deb3f2e-63cd-5f90-993a-9924ad7c9f92 | note | FREQUENCY: Prior to commencing clearing
c87e5ed6-17d6-5be3-a857-17a3014a5f8a | note | ACCEPTANCE CRITERIA: Insert lot start date:
d0787f6b-a8db-5a5d-98a4-e0c87c87ff95 | note | REFERENCE DOCUMENTS: N/A
b4d3b98b-76ff-52ed-86f7-4479c6af40b1 | note | INSPECTION/TEST METHOD: Visual Inspection
fdb8ac03-f3e1-518e-820f-1fe5e213ad76 | note | RECORD OF CONFORMITY: This ITP Signed off
0061cf39-cd39-58ed-bdef-25defc51d7b9 | note | IP
a231ecb1-7c90-5aa8-9a42-378000278813 | note | RESPONSIBILITY: Site Engineer
bb747131-9633-5a3e-8836-c600d01a283a | textbox | Date Completed:
876cdc10-6fdc-4c26-9668-a75045d2e91c | checkpoint | 2.2 Define work area
7b251e53-4454-50ea-af3b-a2d9f25023e4 | note | FREQUENCY: Prior to commencing clearing
20af4d80-1c7b-51dc-a945-48e1701dcaf8 | note | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
64272677-66e2-5a5c-9233-398fadb952bc | note | REFERENCE DOCUMENTS: 201.03
4440b195-f9b6-5183-8a09-f12ab0ac5358 | note | INSPECTION/TEST METHOD: Inspect
6f2da720-647a-58d0-ba88-cc8e98343d24 | note | RECORD OF CONFORMITY: This ITP Signed off
30f52e48-633a-5596-97ce-c914773616a5 | note | WP
364dc1e6-a95e-51cc-9aaf-8eb77c86bece | note | RESPONSIBILITY: Project Engineer/ Superintendent
2e46afb5-f69c-54bb-99d3-9a7355bf36d8 | textbox | Date Completed:
cb7cdbf2-9856-4549-b802-70c8fa6f85af | checkpoint | 2.3 Identify No-go Zones
fa78e7eb-d379-59ab-b4a2-28f1184c4728 | note | FREQUENCY: Prior to commencing clearing
a5e3ac4c-54c2-5d83-a03c-0abeaff2b27a | note | ACCEPTANCE CRITERIA: Existing vegetation and native fauna habitat identified in the Contract to be retained, shall be identified as ‘No-Go Zones’ and protected by temporary fencing, consisting of, as a minimum, star pickets,wire support and parawebbing. Signage shall be erected outside the limit of the of the vegetation or the habitat site.
1db53eb0-2c86-5a2d-a742-90a96650062e | note | REFERENCE DOCUMENTS: Drawings 201.10
ef5bd3ab-975a-5473-a1bc-9e24f62ff66d | note | INSPECTION/TEST METHOD: Visual Inspection
9b721465-c1be-5418-b83b-7df59d112028 | note | RECORD OF CONFORMITY: This ITP Signed off
799b8c73-431f-5358-9337-2943c3721ea9 | note | WP
bd058e7d-2a39-5530-8973-14e48dab41f8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e5809d6d-5572-58a6-a8ac-3364e0df6085 | textbox | Date Completed:
d59d3843-ea33-43ed-9476-41fac2107434 | checkpoint | 2.4 Clear felling distances of trees are adequate.
0d6b458d-0dfd-5f9f-8355-d61d515fe0f0 | note | FREQUENCY: Prior to commencing clearing
75b889ff-3acf-5fd5-89e4-f6d42ace9f1b | note | ACCEPTANCE CRITERIA: Ensure the clear distances are adequate and signage is inplace as planned. Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared.
2b141222-303b-56bc-b519-3c1654e6d319 | note | REFERENCE DOCUMENTS: 201.04
895337e2-e57c-552e-bcd6-0bc8576771db | note | INSPECTION/TEST METHOD: Visual Inspection
e65c42d9-b75c-5183-bfc1-ca71b6fa7577 | note | RECORD OF CONFORMITY: This ITP Signed off
49447031-0abf-5c7b-8c08-30e074f879a8 | note | IP
f78e226c-8bc9-5fb1-8a56-1d870ee98789 | note | RESPONSIBILITY: Site Engineer / Site Foreman
200dd0b3-258d-50e4-aa82-fa662a3204f9 | textbox | Date Completed:
ee450135-37d2-4aa6-a14e-1bf71d431ed6 | checkpoint | 2.5 Clear and grub trees and vegetation
7b6494b4-0d5a-5910-81e2-8e9024d4ff46 | note | FREQUENCY: After clearing
7a96bb54-b3ea-5242-b245-16b64f6658eb | note | ACCEPTANCE CRITERIA: Vegetation in areas of site excavation have been cleared and grubbed to at least 0.3m below subgrade, all other vegetation and obstructions cleared to natural surface level
f742a3ae-e908-5e3a-8bf3-ca63742cef4d | note | ○ Tree branches extending over the carriageway shall be trimmed to provide minimum clearance of 6m above the carriageway surface.
23266e2b-b116-5272-9952-6a800ffb14a9 | note | REFERENCE DOCUMENTS: 201.04, 201.05, 201.06
881f17c3-c271-5bc4-b436-18a56b755bf7 | note | INSPECTION/TEST METHOD: Visual Inspection
da35e5ca-b5da-5878-9683-fca569993dff | note | RECORD OF CONFORMITY: This ITP Signed off
652435e9-891b-5423-bfda-2514befe47c3 | note | IP
5bd26f33-e0db-5cd2-aeb2-6e4db7782737 | note | RESPONSIBILITY: Site Engineer / Site Foreman
9797abee-eb63-5ea3-855e-b098329813c9 | textbox | Date Completed:
e8ac9bcd-d947-4777-b3db-15f37df36dd2 | checkpoint | 2.6 Backfill holes
0b624365-2176-5ac3-bdd7-aade4ed0e935 | note | FREQUENCY: After clearing
97227525-00cb-5f56-80d1-4dbd9ab5ef97 | note | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material to the sorrounding material and compacted to the same degree to the sorrounding material.
9d75a38b-572a-58e4-b4ab-5b30a3f14a5f | note | REFERENCE DOCUMENTS: 201.05
7e4e7df9-b324-5b7e-b581-3a389052783a | note | INSPECTION/TEST METHOD: Visual Inspection
3889e4e9-3c4f-57c3-a788-500dc8fee799 | note | RECORD OF CONFORMITY: This ITP Signed off
3e82f9d5-1c22-59fd-b6be-1870bd780e08 | note | IP
b083a212-ab3c-5b61-8aa7-7daf5a4f530e | note | RESPONSIBILITY: Site Engineer / Site Foreman
e49ae1c4-cb50-53c6-9048-c828797ac9ce | textbox | Date Completed:
f8a10da3-0053-43e1-a803-c7b46aa7a618 | checkpoint | 2.7 Dispose of Trees and vegetation
f0be0b75-c001-554d-aba4-d889ae112e3e | note | FREQUENCY: After clearing
e74241d8-a3eb-50b3-9421-3399a9fd8aab | note | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works or otherwise transported to the APAM mulch laydown area.
798bb3de-fff5-59a3-9da7-92ac39456343 | note | REFERENCE DOCUMENTS: 201.07
d23298b6-84d6-5919-a37a-d2c5dc9b6608 | note | INSPECTION/TEST METHOD: Visual Inspection
035c4f2d-713e-518a-a858-eb619ddba3fc | note | RECORD OF CONFORMITY: This ITP Signed off
ce21826f-876a-527c-87f7-f9fa087ca134 | note | IP
a40ec71e-7941-53ac-8d91-7743490f5211 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ef51d6c0-566e-5303-8d02-666c0e9362a9 | textbox | Date Completed:
842e6029-5391-40bd-8fdd-88bde1c6792f | checkpoint | 2.8 Dispose of concrete, bituminous and other recyclable materials.
45c35763-b4e5-5331-9cdf-554c19cfeae4 | note | FREQUENCY: After clearing
02c92466-98ca-5285-95c9-48a61c65147e | note | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials shall be sent to APAM site recycling facilities.
122d6aeb-25e1-50d0-9434-d6830ff2916a | note | REFERENCE DOCUMENTS: 201.07
6b51c0ca-4c29-5f27-be34-690f3421c16f | note | INSPECTION/TEST METHOD: Visual Inspection
fa57d00a-9e32-5d07-b495-3a0824580436 | note | RECORD OF CONFORMITY: This ITP Signed off
72a6236a-9de9-59d1-ad8a-1c945e5af69e | note | IP
a87061dc-79b4-5ad6-8068-4a0ead4dea21 | note | RESPONSIBILITY: Site Engineer / Site Foreman
fa90fc35-0f1d-5eae-9301-c3d57feae26f | textbox | Date Completed:
e20e0530-e52b-49a3-be8a-421e43b257c8 | checkpoint | Final Inspection
b3a5a6ff-de31-5bcf-a3d3-c5da2c4a37f8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e1bf9b22-3b05-50e7-9b84-26381c13d95d | textbox | Print Name:
049ebaf8-35cd-544f-824f-0d3b27756623 | textbox | Position:
4a0a3ef2-da3c-5aa2-b615-7abdb64dc07f | textbox | Date:
2ab76cca-3028-4388-9867-4b70893fd7a1 | checklist | M3RNAR-FUL-QAC-ITP-002 - Profiling Rev2 | itp | M3RNAR-FUL-QAC-ITP-002 - Profiling
7c564eb5-428c-4b47-ac99-6b0f570f24b8 | section | Preliminary Works
f0fdb406-b648-4b6c-82bf-b5345076d80d | checkpoint | 1.1 Check for correct documentation
8b221e86-aeb5-5365-a859-e079f9c14ea0 | note | FREQUENCY: Prior to commencing any activity
326317df-55b4-5207-bd7a-52e6d05ae56e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2c6fc690-b776-54d3-9df5-40229ee148b0 | note | — using the correct and complete set of drawings
b53b8dd6-0993-58be-972d-d0f369cb80d0 | note | — all drawings are the latest revision
9f30ed2e-aafe-5f84-81c8-2ad6899a4afe | note | REFERENCE DOCUMENTS: Drawings and drawing registers
be6076d0-a32d-5281-b6fd-4aa17d9210e6 | note | INSPECTION/TEST METHOD: Visual inspection
e0e237f2-bc60-5def-8b65-26d18caff9f0 | note | RECORD OF CONFORMITY: This ITP signed
53963d3b-4216-55f3-8244-bb1fc04bc5ca | note | HP*
73efb018-c978-58ad-8287-05b58be96ae2 | note | RESPONSIBILITY: Fulton Hogan Engineer
179a6954-bdf5-57ab-af0d-b9bcdc64162c | textbox | Date Completed:
d01985d1-01dc-4d55-b432-4bfc95f1a1f5 | checkpoint | 1.2 Implementation of all measures and controls
cb4a5a79-ba6a-53e6-a55f-055002645ba7 | note | FREQUENCY: Prior to commencing any activity
65c6b780-055a-5bb5-9b55-e0ea614e6c29 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
e9ac1f68-f78c-5cf2-8245-aae5d56abc42 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
d061ab02-6953-58c8-91b1-a29a68b6e2aa | note | INSPECTION/TEST METHOD: Visual Inspection
e10dbf78-863d-50e5-945a-47c1c053d76c | note | RECORD OF CONFORMITY: This ITP signed
1d00c9ee-6355-5ab3-aa66-1dfe683773b6 | note | HP*
b4f46c4a-c70f-58b8-83db-0202feeab04c | note | RESPONSIBILITY: Fulton Hogan Engineer
178c1e7a-f88c-5f9c-88de-4a61b9355d94 | textbox | Date Completed:
c85a3515-4bb1-4bce-ae4e-c5fba87ee115 | section | Construction Works
36d032b3-1474-4141-b21a-bbce88e98722 | checkpoint | 2.1 Profiling Works
0f3cb7d5-5fb4-5dea-8a78-a26f65a847a0 | note | FREQUENCY: Each lot
06fb653d-f64c-5ae3-bc35-e602a8848dd6 | note | ACCEPTANCE CRITERIA: Cold planing shall be carried out in a manner such that a uniform surface is present on a plane parallel with the ultimate finished surface of the pavement
e655c620-f890-539e-a75a-734847de4874 | note | REFERENCE DOCUMENTS: 402.02
4ac17800-cd84-5938-b064-571ffe3e3d72 | note | INSPECTION/TEST METHOD: Visual Inspection
64458dfa-b1d8-500f-a8ef-f6ca4e08235f | note | RECORD OF CONFORMITY: This ITP signed
6056e4c6-c02d-51e0-a957-fc9e6462809c | note | WP
e0f6ca32-e9d5-56dc-b63c-4edda0f35d66 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
dc22e034-d2a0-5f60-9fd1-6ba27dfb935a | textbox | Date Completed:
6626201c-79bb-4df9-918d-f1ff6739e4a2 | checkpoint | 2.2 Depth check
05ab4b19-d19b-5d73-ad7b-9f2ac3574549 | note | FREQUENCY: Each lot
1bf3698d-710d-554e-bd9c-a1b8e3d4d115 | note | ACCEPTANCE CRITERIA: Average depth of pavement to be removed shall be 40mm ensuring that all Wearing Course is removed. After planing, no point on the planed surface shall be positioned more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
4e51f3e4-4910-5dff-bc15-1807c4cb6ebb | note | REFERENCE DOCUMENTS: 402.02
782fc417-c69d-536c-9bf0-8a3957deb529 | note | INSPECTION/TEST METHOD: Visual Inspection
6f63463a-253b-56e6-a0a2-a44725c69bf2 | note | RECORD OF CONFORMITY: This ITP signed
cfe4b75e-c14a-58d8-a166-767ea175a5df | note | WP
a300585e-282f-5b99-88ac-2b35a79501ec | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
7d33fd6d-5a55-5e77-b3c7-6b346310ed52 | textbox | Date Completed:
3d72f5db-337a-4dfd-94de-f59766f63f35 | checkpoint | 2.3 Temporary ramping (longitudinal)
80bb8695-3e33-50d1-8083-0ca7e94ad34d | note | FREQUENCY: Longitudinal edges
087a29e8-f960-5b58-acc5-5964fbf09329 | note | ACCEPTANCE CRITERIA: Any exposed longitudinal edges within the trafficked area shall be ramped down at a slope no steeper than 5 horizontal to 1 vertical.
e1f4d873-40ed-55c6-9e49-531df19c715b | note | REFERENCE DOCUMENTS: 402.05
f90b69e5-b17f-51cc-88ae-2a2161b943e2 | note | INSPECTION/TEST METHOD: Verify
23c4a75f-abe7-50fd-8762-60e8d6c8b45f | note | RECORD OF CONFORMITY: This ITP signed
2e3b31da-c316-5439-9560-eb9102b9d71a | note | WP
005a792b-28cd-5d3b-969f-a20d94d10de1 | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
95665777-79e8-5f28-a8fa-3019b75f8e9f | textbox | Date Completed:
e27c519b-11e6-41c2-815b-1ebcf3eb106c | checkpoint | 2.4 Temporary ramping (transverse)
c4413e22-7f84-51e3-a1dd-eef31df0f93a | note | FREQUENCY: Transverse Edges
ed3b2326-05fa-5540-b4ae-2b60d8a47c91 | note | ACCEPTANCE CRITERIA: Temporary ramping shall not be steeper than 20 horizontal to 1 vertical for traffic speeds of more than 75 km/h or 10 horizontal to 1 vertical for traffic speeds of 75 km/h or less
8e9a1352-773c-52ca-892e-63c4a85fbe31 | note | REFERENCE DOCUMENTS: 402.05
63167a34-46e0-50a0-afd0-82416c74fea5 | note | INSPECTION/TEST METHOD: Verify
b4acf9ab-0d26-58a6-9ef1-f161fa398fe5 | note | RECORD OF CONFORMITY: This ITP signed
6e088eb7-8849-5f38-bfa1-d10cfb349e6b | note | WP
e2603761-fb73-5a89-92cf-e456a31d401c | note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman/ subcontractor
c97c6bbb-5e6a-52e2-83dc-848be1a4e9da | textbox | Date Completed:
9eb6e98c-db04-41ff-bec6-41f952ebebd1 | checkpoint | Final Inspection
1830f0ea-dde6-5ab3-bc38-601f5c7de05d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b48eb2df-9b44-579d-a4e5-47064e894ee1 | textbox | Print Name:
dd0f7734-db70-531b-9d0d-3c664bc6c619 | textbox | Position:
94f19ee9-e506-5c66-b765-2ae2038f83ff | textbox | Date:
8586ff73-2223-4289-8146-7155b38369f2 | checklist | M3RNAR-FUL-QAC-ITP-003 - Subgrade Preparation Rev2 | itp | M3RNAR-FUL-QAC-ITP-003 - Subgrade Preparation
089b8f91-f3b2-4c09-904b-ab534048e616 | section | Preliminary Works
8d127e47-b2d1-4d06-9a44-3ba86ca9662b | checkpoint | 1.1 Check for correct documentation
26b510f7-a088-5b23-af40-baa959a3491e | note | FREQUENCY: Prior to commencing any activity
3eb71a3d-9e86-57fc-8a48-d598827563cb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
1e08e24e-2687-5a95-b24a-5696f6f21e9d | note | — using the correct and complete set of drawings
19cfac67-2e8b-5c28-9f78-6b1b1e5b1f9d | note | — all drawings are the latest revision
a19416f5-dfa1-5cb8-af61-33ba695ef180 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f398eaad-37ed-51f0-94fd-2e21d2570a04 | note | INSPECTION/TEST METHOD: Visual inspection
6bcf515d-31d3-5883-9f77-4f1d028555ad | note | RECORD OF CONFORMITY: This ITP signed off
9c88a1f2-0880-581f-b3ae-1f9e5802a8b7 | note | HP*
1293e837-c924-543a-848f-9b4cac0a39b1 | note | RESPONSIBILITY: Site Engineer / Site Foreman
93cd52cc-da5a-5a5f-8393-8ad6b27e6fe0 | textbox | Date Completed:
50c1fcee-00bd-43d1-a53b-ac36180ad8c0 | checkpoint | 1.2 Implementation of all measures and controls
31d87f98-727a-5d5b-8fce-47f8bcaa2513 | note | FREQUENCY: Prior to commencing any activity
3f76c7ee-f81f-5451-a374-f95b0771baec | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
4ccaba3f-6e44-5b92-a2bd-d9cafdbc524b | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
59f5d145-82fd-52bc-a0cc-670d6727bcbb | note | INSPECTION/TEST METHOD: Visual Inspection
95c2f847-6d77-520e-a4a3-da063a83c8f0 | note | RECORD OF CONFORMITY: This ITP signed off
86d17c1a-f226-520f-b553-4d31fe0896ae | note | HP*
3f97985f-7d36-5fd5-af35-e99877cf376e | note | RESPONSIBILITY: Site Engineer / Site Foreman
0de93f06-5a75-50c7-bb17-1b88acb8b035 | textbox | Date Completed:
b15e446e-3fa7-4674-a189-0d5d9b653429 | section | Construction Works
a01e4b68-1b3d-42ec-9ae8-74ba472d0120 | checkpoint | 2.1 Survey Set-Out
b9a2eaa5-8e6d-58df-9857-55d70b2bf5be | note | FREQUENCY: Prior to commencement of excavation
17bd33b1-831a-5360-91b3-d61f4c48d050 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
3f0e3b55-154a-5cc7-8899-8efa35aa37e4 | note | REFERENCE DOCUMENTS: Drawings, Work Procedure
88c3f842-1df9-56df-be89-1452662002e8 | note | INSPECTION/TEST METHOD: Verify
ceafa681-e109-570b-86c5-7066fc8a5a27 | note | RECORD OF CONFORMITY: This ITP signed
4f03a84e-ef25-58f8-874f-8917701de956 | note | IP
48e753b4-426c-58da-86ae-24dbfab05bad | note | RESPONSIBILITY: Site Engineer/ Surveyor
ae8dcef9-82df-5ade-9fed-7607bf1d7ee0 | textbox | Date Completed:
4bcbd115-9cc8-428b-b65a-a4391c82df81 | checkpoint | 2.2 Excavation Permit
e337884f-6287-5f84-be1b-ff58e24ee6e0 | note | FREQUENCY: Each lot
544df1ef-730e-5f99-8f27-077779ecee0a | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
c5f5eb11-6035-5d51-bb7c-579d7d41e2c6 | note | ○ Plant and equipment shall be appropriate for the task.
e0c0f621-7230-5369-a597-1915b077c57b | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
5e43d818-24ad-5dda-be3d-261660f62197 | note | REFERENCE DOCUMENTS: Excavation permit
224f456f-cc31-5e1a-a1a7-ccd38b2219a5 | note | INSPECTION/TEST METHOD: Verify
bd76fcd5-ba51-5b0d-80ba-e679d752712b | note | RECORD OF CONFORMITY: This ITP Signed Off
feb52c29-970c-5a93-b927-c09be065499a | note | HP*
6539569a-98f6-5f4c-8473-3575d46174ae | note | RESPONSIBILITY: Site Engineer
567d38be-77b9-59bc-ab02-448eea4b9955 | textbox | Date Completed:
ed1628d8-09cd-4f00-b841-b31ca677865e | checkpoint | 2.3 Subgrade Material Properties
72d5bde8-ee6c-551d-a8af-6ae331de29d8 | note | FREQUENCY: Each Lot
27c26a0d-1896-5f5d-af5c-219777802d8e | note | ACCEPTANCE CRITERIA: Material at cut floor level to have CBR > 2% as per drawing 12001.
40df684f-fd16-532a-8360-64a35890ae2a | note | REFERENCE DOCUMENTS: Drawings
9c7e915d-7481-58ed-aa87-03350eafb0b9 | note | INSPECTION/TEST METHOD: Test Point
daaf65d1-089e-51a0-80c7-b93be643262a | note | RECORD OF CONFORMITY: Test Reports
a63b1926-d3cc-57b2-98e8-e04d51196343 | note | TP
1022d239-07f8-50ca-be0c-754f9683d479 | note | RESPONSIBILITY: Site Engineer
362b9b30-c819-52c0-ab6e-c74ed4073e6a | textbox | Date Completed:
4dd8111a-8559-4707-add7-bb3ed61bb15c | checkpoint | 2.4 Inspection of Subgrade Material
2fadd18e-165e-52c6-bbfa-aafba2cba60e | note | FREQUENCY: Each lot
cc5695ec-831c-5fab-b5ff-29e4446296bf | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on suitability in accordance with 204.04.
19f7dd31-7983-54d7-b336-fd7ca5dcf35e | note | REFERENCE DOCUMENTS: 204.06 (c)
617a69f6-77fb-54c8-afb0-ac64108c493d | note | INSPECTION/TEST METHOD: Verify
b4da6779-11b6-53ba-8d61-755e74113c0b | note | RECORD OF CONFORMITY: This ITP Signed Off
9d76ac4e-f5f6-552f-aeb1-7e744032483f | note | HP
953836e7-2065-5c7d-9f55-a267e18a2d5b | note | RESPONSIBILITY: Site Engineer/ Superintendent
46e3bcd0-5838-50d9-a706-49895f494b59 | textbox | Date Completed:
6c88ca2b-13d4-4f5b-bde9-af9755387937 | signoff | AUTHORITY HOLDPOINT
0494b240-d0d7-43fb-9711-a10dbb65d829 | checkpoint | 2.5 Unsuitable Material
6241b8cc-72ee-5b6b-9a84-9db8997a2f38 | note | FREQUENCY: Each Lot
41083bcf-89d1-5979-99df-cc728baa1722 | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
9cdae208-c057-58d3-a4ab-51cbce093547 | note | REFERENCE DOCUMENTS: 204.07 (d)
2d37f1f6-67fa-500a-8de7-9bef39053f96 | note | INSPECTION/TEST METHOD: Visual Inspection
da48a485-6aac-5aeb-b3ac-b98c9afdabef | note | RECORD OF CONFORMITY: This ITP Signed Off
12791cfa-ccb6-57a1-b6f9-985646c9de70 | note | HP
1ada6fb6-76a7-549f-a42b-5a83212b2076 | note | RESPONSIBILITY: Site Engineer/ Superintendent
10fdb6c6-894f-58a0-b0eb-d61ed4bbc4d7 | textbox | Date Completed:
93914b6a-8b4e-4628-b194-9a3794eab5ee | signoff | AUTHORITY HOLDPOINT
95b0bcaf-7ef3-43fd-bb7c-ebb8f1ee8fb8 | checkpoint | 2.6 Groundwater
7ff797f0-3015-5598-bb64-ed0a35aa710f | note | FREQUENCY: Each Lot
57e08b5c-a4d6-5886-8884-ec879409b939 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
6fc7ff38-249f-574a-b3b6-87ccee686bf4 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
a37abecf-8e7f-5a95-8d26-2c3becd5934d | note | REFERENCE DOCUMENTS: 204.06 (h)
9e0b628c-e694-5479-ab7b-9285d13f1974 | note | INSPECTION/TEST METHOD: Visual inspection
56a5ab67-b6e4-5290-bce1-43e17c7f1451 | note | RECORD OF CONFORMITY: This ITP signed off
808d623e-0550-589a-a62d-4b54d38cd1b8 | note | HP
ba9198bf-20f7-5c16-a7e0-07f020899c9b | note | RESPONSIBILITY: Site Engineer/ Superintendent
ad13c44f-aa4a-56a2-87ed-ead1a8e84e16 | textbox | Date Completed:
f594870f-5e04-4ec8-b742-6d24b65f123c | signoff | AUTHORITY HOLDPOINT
f3be9f33-c1aa-4c6e-91c1-70687dbe9c73 | checkpoint | 2.7 Trimming and Level conformity (Scale B for NAR)
23a7aa19-4709-507b-973e-e56549921552 | note | FREQUENCY: Each Lot
a65e16bf-472b-568b-9490-04fe6896bde7 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
7ac10013-5af3-5bcc-99f4-09906ada5ef5 | note | ○ Level tolerances:
bd322a80-a62b-524c-a087-22f210df602e | note | — Range x = +5, -25mm
06849171-bbf6-516a-a99a-d9836ef62d07 | note | — Max S = 15 mm
4e69c017-d3f7-593c-bc5b-db349ed5fd0b | note | — 40 measurements per lot (Scale B)
4c04f906-37b8-5bfb-9018-a4e4a1a02829 | note | REFERENCE DOCUMENTS: 204.03(g)
d6d9c350-9f3f-5820-9765-59cb77bebedd | note | INSPECTION/TEST METHOD: Survey Report
7b25423b-4ae0-5798-8f3a-deef1ff05895 | note | RECORD OF CONFORMITY: Survey Record
f4f94089-00bd-5933-aedb-0a3ae51c60d5 | note | SCP
6590dd49-e140-53f8-94ce-d652adfa644b | note | RESPONSIBILITY: Site Engineer/ Surveyor
1031a5b9-82ac-5595-b9d4-a7c13eae56c2 | textbox | Date Completed:
5d3612df-5147-4088-8a65-ad5418f529ad | checkpoint | 2.8 Trimming and Level conformity (Scale A for Sunbury Rd)
ef058ec2-ae07-57f8-ad5d-c129b334bb38 | note | FREQUENCY: Each Lot
3b0ae413-0e68-5b85-a19b-527417a4cc73 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Random level assessments shall not be undertaken in lots not exceeding 4000 m2.
b624431b-fdf5-55e2-9c19-519b5f04a132 | note | ○ Level tolerances:
5c4c58cf-c382-5314-a373-b26d69c5ac79 | note | — Range x = +5, -15mm
8e6c5057-4d4b-51a7-a945-406e08c941c4 | note | — Max S = 12 mm
adf93c09-f073-54c9-887f-2ae9a3cf8801 | note | — 80 measurements per lot (Scale A)
541fcf69-2396-5ea2-a6f9-716703071d23 | note | REFERENCE DOCUMENTS: 204.03(g)
a6729fe1-b962-5dd6-bc3a-671b2bba972f | note | INSPECTION/TEST METHOD: Survey Report
1ffab1d1-65fd-5cf1-8091-c50a07998962 | note | RECORD OF CONFORMITY: Survey Record
8b65e1d9-469a-5fa0-acc2-7a023c244f50 | note | SCP
b6a81cd9-f589-5dfe-ae2b-612a3fd5798a | note | RESPONSIBILITY: Site Engineer/ Surveyor
23a96e7b-3638-527f-ac4f-00c940957a1c | textbox | Date Completed:
f3f380bc-05be-424f-aab0-ca40b26a3b41 | section | Testing
17422c76-7acd-4e30-b768-3400ce5ba2fc | checkpoint | 3.1 Proof Rolling
82ec44cb-7f24-553b-88f0-2a32493caa4f | note | FREQUENCY: Each Lot
311a1c8b-2826-54ec-b2ff-fb81f2844348 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the Department of Transports Standard Specification
3361f676-d991-5fdc-9a82-e30cdd32faf5 | note | REFERENCE DOCUMENTS: Section 173
7ce2aaab-df16-5984-98ca-c5dfd6f087c7 | note | INSPECTION/TEST METHOD: Visual Inspection
094a200a-d89b-5005-8295-e1c9aca9bcf4 | note | RECORD OF CONFORMITY: This ITP signed off
66bc200a-5d99-55f6-b6fc-c27c38afb8c3 | note | HP*, WP
270b9e17-0ea0-5398-87a9-33a6b66261ef | note | RESPONSIBILITY: Site Engineer/ Superintendent
ce961e9a-4ec6-5228-b13c-2cb5c874e1aa | textbox | Date Completed:
0e862a24-f6d5-4f12-9514-f1ffee27d9d7 | checkpoint | 3.2 Minimum Testing
1b7d7fc8-8ba0-5fd8-9ca8-7c590b32e949 | note | FREQUENCY: Each Lot
caf37915-8ac3-5d00-a902-06580b8706c4 | note | ACCEPTANCE CRITERIA: Testing of every lot shall continue until three consecutive lots of like material and work have achieved the specified requirements in the first test. After satisfying this requirement and establishing a compaction procedure to the satisfaction of the Superintendent, the Contractor may seek the Superintendent’s agreement to reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
d17b101c-78f3-565a-b7b3-4f428595e261 | note | REFERENCE DOCUMENTS: 204.14 c
f90e2236-40ae-5c5a-bef3-c7d321046fcd | note | INSPECTION/TEST METHOD: Test Point
5fc80db4-50fd-506f-aec7-03bd65aae4ff | note | RECORD OF CONFORMITY: This ITP signed off
e049ec78-2c42-59d2-ba2e-21d192b2d1fa | note | HP*, WP
c0e76c45-77a4-5136-a449-51e9b3f1e171 | note | RESPONSIBILITY: Site Engineer/ Superintendent
969cd907-8d56-5903-a72c-015f2265c52b | textbox | Date Completed:
208ece3f-5316-41e5-8eae-03a9721c96ff | checkpoint | 3.3 Compaction Testing (Scale B for NAR)
3e23a22d-af80-536a-b188-b321b18102dc | note | FREQUENCY: Each Lot
c579bbbe-55ed-5871-9578-d01e107247a3 | note | ACCEPTANCE CRITERIA: All Type A Material = minimum compaction 98% MDD
c766baad-b306-54f6-85ec-e6f6091cd334 | note | ○ Ripped and re-compacted material below Cut Floor Level = minimum compaction 98% MDD.
44a26ac1-ab3b-52e3-9b3a-5596cbb76e76 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 95% MDD.
4dcb303f-365a-5baf-bf33-d84cff17ba9d | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 95% MDD.
0503c650-656c-52cc-86f6-f4f6f0a13f17 | note | REFERENCE DOCUMENTS: Table 204.131
c63ac011-939a-5d6c-be3e-a2f4ea6348f8 | note | INSPECTION/TEST METHOD: Test Point
0f871114-5302-54c0-b0d7-092dc2a12c93 | note | RECORD OF CONFORMITY: Test Records, Lot Register
18e04ddb-cc7b-5082-895a-0a963ab221f1 | note | TP
7dcf50fc-5e0d-5f02-90f5-ec60cdea9ca2 | note | RESPONSIBILITY: Site Engineer
1a3274b7-c2bf-5e3d-8b57-795d0adc6885 | textbox | Date Completed:
4b462e85-512e-4282-98ff-89629ccba916 | checkpoint | 3.4 Compaction Testing (Scale A for Sunbury Rd)
e4adf77f-cc4e-5dab-aea8-fd614d73e67c | note | FREQUENCY: Each Lot
f4086586-e0bb-59d5-806a-108d783126ad | note | ACCEPTANCE CRITERIA: All Type A Material = minimum compaction 99% MDD
00fd27e5-3bd5-5b34-99d4-f527a81c67db | note | ○ Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
e1a9cbf3-d409-5463-8a08-df60eb8f2008 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 97% MDD.
6398f895-6624-5a06-b6da-53a5bb4bed50 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
d28c57e8-5fd0-55ad-b148-cff4a3fcd347 | note | REFERENCE DOCUMENTS: Table 204.131
d86547a2-d447-527a-8451-4fb53b757680 | note | INSPECTION/TEST METHOD: Test Point
11ac1543-b604-5cbf-b980-df23afcb4ea5 | note | RECORD OF CONFORMITY: Test Records, Lot Register
2627fe08-0e34-5c30-b4d4-e207c1a2508b | note | TP
bbf0738e-ba8d-5a96-a62d-f0494c076766 | note | RESPONSIBILITY: Site Engineer
f89c8ea3-1a2b-5189-9dde-07c27696f628 | textbox | Date Completed:
dc7e436d-708a-44cf-8a83-35f49c2182dd | checkpoint | 3.5 Compaction Testing (Small Lots)
77e9e015-359d-51dd-b1e9-04f1df8119b0 | note | FREQUENCY: Each Lot
654cd89f-670b-5566-87c9-6a800e5ac004 | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% MDD.
b5f76313-5fff-53c4-b610-c7b5d302098b | note | REFERENCE DOCUMENTS: 173.04 d
721b35e5-81b1-56c2-bb87-5e032a0266d4 | note | INSPECTION/TEST METHOD: Test Point
89ad0980-16e3-568d-8d70-ccc8676b2113 | note | RECORD OF CONFORMITY: Test Records, Lot Register
6c05e9f0-82b9-546c-b466-92a262e94183 | note | TP
4658579f-3597-5ab1-997e-337ee80f2bf5 | note | RESPONSIBILITY: Site Engineer
119daf5c-6c0f-53f8-b601-63d65045c5c8 | textbox | Date Completed:
90d6143e-4704-488e-b9dd-7088c46ab82d | checkpoint | Final Inspection
37ce39e4-1c1f-5f8e-9c7a-10b72354f5d5 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
cd0ecf58-aa04-58aa-a7c5-7f5711b027c5 | textbox | Print Name:
857504fa-e1d7-5f4a-84f0-7a9c631c3d7b | textbox | Position:
4a2d35a0-5de9-5c02-80bd-ddfed06bceb4 | textbox | Date:
d4bea301-9aac-4c35-91ec-2de918867faa | checklist | M3RNAR-FUL-QAC-ITP-004 - Type A Fill Placement Rev2 | itp | M3RNAR-FUL-QAC-ITP-004 - Type A Fill Placement
58a29781-bcd7-444a-afff-f9f14ec2a12f | section | Preliminary Works
fea0da8e-b91c-43af-9b9d-5bd69c8b968c | checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
31fe509e-1a2f-581b-a553-492d5b6c62ff | note | FREQUENCY: Prior to commencing
1ee736a7-59fe-5154-96a7-97427f855325 | note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
c020fd98-b75c-5104-8d82-79eaaeee56a2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e2471537-50fd-5add-a4a7-d596b95a915d | note | INSPECTION/TEST METHOD: Visual Inspection
89aa5844-06ec-5711-911f-0a4be50e170e | note | RECORD OF CONFORMITY: This ITP Signed Off
60aabaa2-35de-5b83-8f0f-58580b912e25 | note | HP*
5351b92c-1032-57fb-af68-973ddec0571d | note | RESPONSIBILITY: Site Engineer / Site Foreman
55d54fc5-c428-5f21-ae22-6bf2276b7e0f | textbox | Date Completed:
e2a15924-6bca-4ef1-9080-d60ebdb10677 | checkpoint | 1.2 Implementation of all measures and controls
a29812d8-bc01-53ee-8ac7-bf8e1c57d91c | note | FREQUENCY: Prior to Placement/ Each Lot
c39732ac-3588-56c2-9d40-d76df03812af | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
fa7e7cbf-b2d2-5ce2-851d-eb9054147a10 | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
1c38563d-5c41-5efb-bc77-c74c48445463 | note | INSPECTION/TEST METHOD: Visual Inspection
a9d9d64e-4266-5d1f-a701-c82b2d0d6019 | note | RECORD OF CONFORMITY: This ITP Signed Off
dbe9940a-f55d-56b9-82dc-76a2a7287111 | note | HP*
45cb8b2a-dd3f-5c0d-a342-94080523e45d | note | RESPONSIBILITY: Site Engineer / Site Foreman
d85ec5e1-842a-57b0-aef8-7e5db2cdf308 | textbox | Date Completed:
70af7960-8b08-4d7f-ad49-ce4abbca2b77 | checkpoint | 1.3 Material Approval
24984c17-a08c-5080-b70a-a2ebc1d6c76a | note | FREQUENCY: Prior to Placement
7499ece9-b2e3-5bde-abe5-eb2d7b87764e | note | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
ff8cf66f-bf7f-513c-872d-03d954535e14 | note | ○ Assigned CBR to be greater than 10%, swell is to equal or less than 1.5%, unless approved as expansive.
49368fba-103a-53ed-b5dc-41b726a8f116 | note | ○ Permeability of less than 5X10^-9 for capping and verge material
df9c0483-f894-5c1b-94b5-faa9b4b29fb9 | note | REFERENCE DOCUMENTS: Table 204.041
bbdcbf37-f578-5d2d-b45e-d4d6b4def1b8 | note | INSPECTION/TEST METHOD: Verfiy
d4f07519-8614-5fc3-ab5c-25b59363bc37 | note | RECORD OF CONFORMITY: Aconex Acceptance
bbc975c8-1fb4-5ca1-b889-56ce1374bd6d | note | HP*
4c9388ac-4755-5f6a-bdcc-5e5a5e53c8f0 | note | RESPONSIBILITY: Site Engineer
299bf3e2-4e13-537b-9352-cf07f2e756b7 | textbox | Date Completed:
ab9f7193-af18-460c-960c-c6a838185c4a | checkpoint | 1.4 Verify Material
ea72e1e0-a0c6-5461-9945-9e0c3e60e6c4 | note | FREQUENCY: Prior to Placement
809f9007-03a7-519d-9d3c-542db49ff55c | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent
1a9f23a2-2dc7-5331-b413-1cb84dca194f | note | REFERENCE DOCUMENTS: Cl. 204.04(b)
46a8be2e-05d1-5587-bf28-6e69f824e63b | note | INSPECTION/TEST METHOD: Site Inspection
e14d2a8a-b09b-55fa-9774-33ccd03695b3 | note | RECORD OF CONFORMITY: Test Record (If silt is proposed for Type A material)
782e3bc4-ed0a-5c02-ba1b-c4697efa713b | note | HP
86d102b6-c8c4-51f8-9be0-da695ebd1e9d | note | RESPONSIBILITY: Site Engineer & Superintendent
5dde7066-6145-5a16-949b-9b2be5c08fb9 | textbox | Date Completed:
6869c936-7e7b-40a4-9941-d69b2b77db24 | signoff | AUTHORITY HOLDPOINT
6dcfb71a-6e73-419b-ab49-38def6c76de6 | checkpoint | 1.5 Excavation Permit
4109dc6b-df70-5f05-b498-33697f04c3b3 | note | FREQUENCY: Each lot
26887a04-ff25-50e0-8b24-3d3fb9f10bfb | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
274afa7c-9d0f-57eb-89fb-f5767949917a | note | ○ Plant and equipment shall be appropriate for the task.
7bfaa336-3699-5378-a844-9e814ef801b9 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
1b8e8bc2-1373-58c9-b012-4f457b3c8743 | note | REFERENCE DOCUMENTS: Excavation permit
dc3a34d1-e49d-5fcc-8a52-42f823eed383 | note | INSPECTION/TEST METHOD: Verify
42ccb0ed-3a56-5e3c-b1eb-0c87ca1744aa | note | RECORD OF CONFORMITY: This ITP Signed Off
208f5150-8e12-5ce8-974a-88d350e05233 | note | HP*
57ad671e-35ca-58ec-8db0-05bfe293cf34 | note | RESPONSIBILITY: Site Engineer
d9cad0ef-1465-522e-887d-6471fd592b7a | textbox | Date Completed:
d3e1cee3-f757-42b1-bdf5-64f5dcbe2d19 | section | Construction Works
a3a37c57-3b57-4b07-afaf-727d20cf51a9 | checkpoint | 2.1 Survey set-out
728f6b34-5961-5fd0-8583-1d2ba3543cc2 | note | FREQUENCY: Prior to Commencing Excavation
a9b3eb51-2a92-5867-90d7-a6ebdd6acf70 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
ef8a124c-c01a-512e-8720-0657ae97190d | note | REFERENCE DOCUMENTS: Latest IFC Drawings
9446f988-17e8-5440-a3d4-bb41a326119d | note | INSPECTION/TEST METHOD: Site Inspection
0af1d29e-1980-58ae-aa53-8588138e7567 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
6a6c7bc3-782a-5b4a-babf-a0083902fef3 | note | SCP
32206e76-f4b9-5145-a480-c0e9192a49e0 | note | RESPONSIBILITY: Site Engineer/ Surveyor
5914ae62-cf4f-5099-b511-4ab634ebf4e6 | textbox | Date Completed:
d120dbae-5b21-428f-9f17-aae06fd44852 | checkpoint | 2.2 Inspection of fill area
12995ca8-0439-505d-8829-1a2892520f87 | note | FREQUENCY: Each lot
c5afea50-00f9-5c4b-b2da-3e99cd9e3f28 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
aeb772c2-d119-5e25-be2b-3e10be9ac2b2 | note | REFERENCE DOCUMENTS: 204.10 (b)
49ea8698-eabe-5181-a715-2ccac4cca02d | note | INSPECTION/TEST METHOD: Visual Inspection
a83f5d89-3c2e-50ba-88cf-8527052e9c42 | note | RECORD OF CONFORMITY: This ITP Signed Off
3dc827c1-cca0-5d0c-93aa-6cc91247c45e | note | HP
86e7fb9f-aed7-57b2-b1f6-0fbc78c8070c | note | RESPONSIBILITY: Site Engineer / Superintendent
e5b3129d-e2b6-5a8d-a7dd-dd05cb7b6dc6 | textbox | Date Completed:
73e8179c-ec4d-44c3-989d-9609a168264e | signoff | AUTHORITY HOLDPOINT
a311d07d-09c4-48eb-91ca-70acf58bc740 | checkpoint | 2.3 Layer Thickness
9c77d705-3d33-50e7-89ba-dd9ecba39e54 | note | FREQUENCY: During Excavation
1c41ae85-0c25-5fdf-8573-8c445a8bf43e | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
8882efdc-076f-5d36-ab8f-c43f358d0b5f | note | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.10(d)(ii)
fb70e390-e516-504f-b812-49a5e27adaad | note | INSPECTION/TEST METHOD: Visual Inspection
2e93e9b3-8aeb-504b-ae24-b467d4d48648 | note | RECORD OF CONFORMITY: This ITP Signed Off
c22534aa-65dd-53af-9472-2de15eab9fb2 | note | IP
bac57a5a-2897-5e7e-b3bb-4908d8bbc1df | note | RESPONSIBILITY: Site Engineer
00beef15-d787-5b45-99ef-53d78449ecc3 | textbox | Date Completed:
20127021-4772-492d-a3ab-0409b1cec106 | checkpoint | 2.4 Maximum Lot Size
33dfeac6-6d26-5196-bd0b-961844b04e26 | note | FREQUENCY: During Excavation
d4ff94d3-e140-51ed-9209-2cab39bb1e5a | note | ACCEPTANCE CRITERIA: Lot size for testing is to be one day's production or 5,000m2, whichever is lesser.
2676cae8-a05c-5b7d-90f3-303c037bc33c | note | REFERENCE DOCUMENTS: DTPs Spec. Table 204.142
f729f7a8-1f48-5b84-be23-0e1cc1351a90 | note | INSPECTION/TEST METHOD: Visual Inspection
843b3da0-4e1c-5a88-8b1d-fd5f1c439638 | note | RECORD OF CONFORMITY: This ITP Signed Off
4ad89ea4-6f62-5547-ba9b-cc8d86701bc2 | note | IP
0d794cfd-2a26-52b6-ae42-7ece6ce392ca | note | RESPONSIBILITY: Site Engineer
b365c878-7ccc-5f21-ba6a-00cfc8b75e59 | textbox | Date Completed:
cabfbd7f-c60b-44ea-8e92-bf9baa089e61 | checkpoint | 2.6 Proof Roll
7196b750-49ff-5d05-8182-a4a05841a11f | note | FREQUENCY: Prior to placement
01a0092c-48e2-5dd3-bab9-e31b9b62489d | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the Department of Transports Standard Specification
5020159a-2489-5b3a-8013-ac4c6e7f5381 | note | REFERENCE DOCUMENTS: 173.03, 204.12, 204.10 (b)
abf9dd7e-aa51-5c30-a8aa-1fe60228cf50 | note | INSPECTION/TEST METHOD: Visual Inspection
c138b763-2838-5cfa-a79f-90b1f32a05b8 | note | RECORD OF CONFORMITY: This ITP Signed Off
9e82f59a-71c5-559a-a196-9eddc1625b70 | note | WP
31343745-852d-51f6-a510-07332bbe9b3f | note | RESPONSIBILITY: Site Foreman/ Superintendent
5343a6b3-5227-50e7-9709-0027c64dc649 | textbox | Date Completed:
d05c4d8a-fb1e-4050-be78-06bb70320933 | checkpoint | 2.5 Type A Placement
5c0990a2-72f0-51e1-b24e-621cfebe60c6 | note | FREQUENCY: Prior to Placement/ Each Lot
2b4c257a-94a2-5c0c-b8d5-7b0b0593ebe2 | note | ACCEPTANCE CRITERIA: Top of fill must be shaped and compacted to minimise damage due to wet weather
f06afb17-c45d-512a-850c-8c88a5c52fa6 | note | ○ Any rocky material present must be uniform throughout the layer
ef0f1961-0347-5ba3-a931-8c49227f5a58 | note | ○ Each layer shall be kept generally parallel to the surface of subgrade
c5dfff55-3765-5a32-94aa-aa0a7004a547 | note | REFERENCE DOCUMENTS: 204.10 (d) (i). 204.10 (d) (ii).
0047bf6f-c181-517e-9020-d1743146764e | note | INSPECTION/TEST METHOD: Visual Inspection
a9a14c2c-62b1-53da-bc63-26ccbbd6bc77 | note | RECORD OF CONFORMITY: This ITP Signed Off
27fe913a-82eb-5b02-bda8-4d9bfbdfd713 | note | IP
c3155f59-c452-5dad-8a02-bc62c7b2a5a9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
02484693-91a1-53ec-88e3-c0d48166787f | textbox | Date Completed:
aea3ee44-2cf0-49a5-969d-8800f2e668fe | section | Testing
2ab173cd-c13d-4901-a83c-8df75d9d1595 | checkpoint | 3.1 Reduced Test Frequency
11fb06d6-0fc4-58c3-a435-3de1d225ad4b | note | FREQUENCY: Each lot
1db3dc3a-8b52-57ed-a56c-2ede18a7b5d0 | note | ACCEPTANCE CRITERIA: Initial Testing requirements shall satisfy the full requirements as detailed in the specification. Once three consecutive lots have achieved specified requirement, Superintendent can agree to reduce frequency of testing of subsequent lots to the reduced testing frequency specified in Table 204.141. Reduced frequency resets if one lot fails.
5e93b2ce-9864-517c-8dbe-e784d25ef7e4 | note | REFERENCE DOCUMENTS: DTPs Spec. Table 204.131
881bfb92-6bf0-5020-9c26-773b2397b0f4 | note | INSPECTION/TEST METHOD: Test Record
623c3033-9537-505b-b247-43d036d7eb12 | note | RECORD OF CONFORMITY: Test Records
e9bdcb45-47a8-59bc-ac1b-34d647174d86 | note | AP
5d6b457b-4bee-54e2-82c7-ff35958b5f22 | note | RESPONSIBILITY: Project Engineer
c4ee6157-7dbe-518d-9557-1f82c646fe09 | textbox | Date Completed:
98ae4049-b3af-48af-b448-45b3f4406fcd | checkpoint | 3.2 Compaction Testing (Scale B for NAR)
38ff4c32-33c0-5921-88c7-aff564c11955 | note | FREQUENCY: Each Lot
9035fa35-726d-5559-ba7f-3e9ed661e64f | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 98% Characteristic Value of Density Ratio (Scale B).
bd9271f1-5f85-5387-b034-cd0b57fcafb1 | note | REFERENCE DOCUMENTS: DTPs Spec. Table 204.131
ed004e0b-8871-541e-ab3e-cc1ea30dac55 | note | INSPECTION/TEST METHOD: Verify
b431d439-eb60-5406-8a34-0a03d55673c2 | note | RECORD OF CONFORMITY: Compaction Test Records
76fed848-9405-56ff-a4d5-e41ce6b953b3 | note | TP
45359c29-3041-5ce3-ae5a-a79c9df24fe8 | note | RESPONSIBILITY: Site Engineer
4bb1a373-cc52-5683-bde1-8d1bb098917c | textbox | Date Completed:
a5792ec5-064a-4f38-a1b7-c8000ddbb581 | checkpoint | 3.3 Compaction Testing (Scale A for Sunbury Rd)
e36faa78-31ea-5b33-8333-ffc807b30ae5 | note | FREQUENCY: Each Lot
c5db987f-6b71-5e8f-91e2-95fb2bca7b39 | note | ACCEPTANCE CRITERIA: Type A material should be compacted to 99% Characteristic Value of Density Ratio (Scale A).
0d42804f-d2c3-5e64-b21c-61fa18f1fad9 | note | REFERENCE DOCUMENTS: DTPs Spec. Table 204.131
99587d71-3d80-5645-a03e-ddaf7f5e6366 | note | INSPECTION/TEST METHOD: Verify
c8e20b2b-ab42-54f5-8b34-68fa19f9032a | note | RECORD OF CONFORMITY: Compaction Test Records
396f6761-76c3-519b-abee-98921f5a4283 | note | TP
b180a337-f91f-5d55-af18-6a818a39ab0b | note | RESPONSIBILITY: Site Engineer
88851a13-7b82-599a-9889-849fe5d32330 | textbox | Date Completed:
a064dcc1-655e-42d3-b443-76fe7b6b1e33 | checkpoint | 3.4 Compaction Testing (Small Lots)
4fe5f3d8-c39f-5e1d-ba80-d97ee0da6c00 | note | FREQUENCY: Each Lot
2fcfbc18-4630-5125-b731-b76a2d7ef97e | note | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% SDD.
55f7a1f5-4ff0-5faf-8ae6-9d57f98c38b6 | note | REFERENCE DOCUMENTS: 173.04 d
a5c9b5c4-d22c-5919-8838-27fc84c69378 | note | INSPECTION/TEST METHOD: Test Point
280039e1-10b1-581e-9197-c5b2cca2f864 | note | RECORD OF CONFORMITY: Test Records, Lot Register
f36383da-fc9d-5536-8845-19ddf459cbaa | note | TP
3ae62901-d741-5e34-b8b0-2d33ff807c43 | note | RESPONSIBILITY: Site Engineer
979c84c6-907c-593b-bdd8-d327ef805492 | textbox | Date Completed:
883c4ab9-943a-4492-9d2e-7f821a92af1c | checkpoint | 3.5 Maximum Particle Size
ab340f23-401c-525b-8c91-825efc8dceb7 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
6aa8a968-ddc3-52fa-9c24-b407a3c19a8a | note | ACCEPTANCE CRITERIA: Material is to be graded such that 100% passes through a 75mm sieve, 40-80% passes through 4.75mm and 10-40% passes 0.075
f713d804-4808-5c82-adf6-8ca89e7e7d59 | note | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
951ce811-970b-57f6-b1f4-2ca71de0c893 | note | INSPECTION/TEST METHOD: Verify
9a1cad14-f4bb-5ac3-9842-f82c111bd669 | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
e3000f65-5a41-5d70-a3eb-b34b4598c72d | note | TP
1dd6c863-469a-5f11-a3ea-0e05ce6bf440 | note | RESPONSIBILITY: Site Engineer
f14aac5b-21f5-5319-9ed4-3b2294353874 | textbox | Date Completed:
1e98d3d0-177e-4bf2-b818-95fd9872e775 | checkpoint | 3.6 CBR/Swell
27888b10-e8bb-57e5-8720-dcc5ec175473 | note | FREQUENCY: First lot only
3ed2b2b3-6ff3-5bbe-b5c1-c15db59da676 | note | ACCEPTANCE CRITERIA: CBR: ≥ 6%, Swell: ≤ 1.5% (Verge material less than 1.0%).
8ffdddaf-0c5c-5d0a-8ec7-cb406b99bbf4 | note | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(i) Table 204.141, Table 204.041
c762d70f-6883-5701-9fab-be37c531b4f1 | note | INSPECTION/TEST METHOD: Verify
6b88f731-50aa-51f9-8bfa-9cd8c1618378 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
16816174-c276-584d-8e67-92f67db9429a | note | TP
2f72c1eb-9596-5784-8514-d329a83d7e81 | note | RESPONSIBILITY: Site Engineer
f429886f-b7a1-5ed3-aa6e-18774bcdee30 | textbox | Date Completed:
6e427c2e-d385-4856-972f-746946a5da54 | checkpoint | 3.7 Atterberg Limit Tests
d2e3323a-3077-51d7-8477-08aad843f117 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
a1425600-39b4-540a-8ed8-352d06e920cc | note | ACCEPTANCE CRITERIA: PI between 6 and 25, PI x % passing through 0.425 to be less than 1000
38f70a51-95e7-5c75-b2ad-852a797d0055 | note | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
9cdb2dea-6220-53ab-8f7a-28408c5962cf | note | INSPECTION/TEST METHOD: Verify
d414774a-30fc-57a2-b897-d4ca0fdfe604 | note | RECORD OF CONFORMITY: PI Test Records
40bb236b-2fe0-5fa2-afe0-2710a999a35c | note | TP
7d4e309a-274f-5bfa-8d25-210b44ef9962 | note | RESPONSIBILITY: Site Engineer
0ad9cc59-6e08-540c-a36b-7e1d57253e0c | textbox | Date Completed:
cc6c4f0c-acca-469f-b5a2-28d5cdbdde3b | checkpoint | 3.8 Permeability
aa11ed1b-7946-50cf-91c0-d867fa30c1d7 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
ec9d37d6-efdc-5ddb-b51f-c92a7d8cfbae | note | ACCEPTANCE CRITERIA: Permeability of less than 5X10^-9 for capping and verge material
ca2c40e4-e4ec-5f5c-b7c6-dc80a6b72d6c | note | REFERENCE DOCUMENTS: DTPs Spec. Cl. 204.14(a)(ii) Table 204.141, Table 204.041
5fc88367-d6cf-5ead-b0d5-bacf203be9f2 | note | INSPECTION/TEST METHOD: Verify
04620f5d-1c40-5d3d-9bb7-4bd92dcd4511 | note | RECORD OF CONFORMITY: Permeability Test Records
0af00140-a241-5c77-a2a3-f9fdfa8ea731 | note | TP
e30848ea-3bbb-5d33-8425-ef102b24bb8c | note | RESPONSIBILITY: Site Engineer
fbdde6a4-8750-5cf7-9010-777dab9e56a5 | textbox | Date Completed:
f82fa9ff-bd39-4946-9a3f-064f96a06dc2 | checkpoint | 3.9 Material Property Testing (Scale B for NAR)
736e7d88-d818-5f3d-9e2a-8f383647af4e | note | FREQUENCY: Each lot, unless reduced frequency has been approved
a87b645b-3220-5cf0-ba57-cbaf08471e0f | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
b38b8c2c-9df4-5ae3-b851-86b8b04b8764 | note | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
d26b72ae-10c7-5bdc-82cc-b4f93ec659fa | note | INSPECTION/TEST METHOD: Verify
7f754f92-9e4b-50dd-8340-b80a01b6a137 | note | RECORD OF CONFORMITY: NATA test report
bafaeeb0-9d8f-5f9e-925a-fbed11945dca | note | TP
be3857a3-6df5-5d7d-8d74-7fa01716cdac | note | RESPONSIBILITY: Site Engineer
b603addd-3c36-5f8c-8db6-4649aa5e2bb8 | textbox | Date Completed:
25a61f44-97ca-4188-ae34-6afabad4d92a | checkpoint | 3.10 Material Property Testing (Scale A for Sunbury Rd)
3f4100dd-8815-5f90-b54a-753b57a9a021 | note | FREQUENCY: Each lot, unless reduced frequency has been approved
cd9d1ed5-c9a3-5773-801e-6c07389fdba1 | note | ACCEPTANCE CRITERIA: Obtain production testing ITP from the supplier. Materials shall be tested to show compliance with the requirements of Clause 204.04.
baf43f0e-bd13-5eb2-bc21-89dab942e1e1 | note | REFERENCE DOCUMENTS: Cl 204.04 Cl204.14
6fe19eea-17bd-5e40-b9c2-371b7809aa70 | note | INSPECTION/TEST METHOD: Verify
2791cb4c-0d28-57da-9990-dfabb60b4a79 | note | RECORD OF CONFORMITY: NATA test report
152e408b-bacb-5771-8b3a-99f653d77301 | note | TP
9b26b085-7ec6-570f-bee4-7f24eb250ba9 | note | RESPONSIBILITY: Site Engineer
e41fa106-bd46-5f40-b835-e4f0e1d8ea48 | textbox | Date Completed:
42289af3-de34-4ddf-9307-5cb699ddd21a | checkpoint | 3.11 Survey Conformance (Scale B for NAR)
dca6d907-54e8-516c-a58d-1621d8944715 | note | FREQUENCY: Each lot
811214bd-9ce6-5a28-b9ca-d256caec0b7b | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
ee8aa387-2d9e-5d6f-b6b9-d23f4f4015ce | note | ○ Scale B:
e1ac3b9f-f054-52fd-bfee-2fe12ebb5083 | note | — Range x = +5,-25
1996862f-8211-5221-b50b-3aa6b753c2a1 | note | — Max S = 15mm
f3979355-7dc4-521c-956b-3b8049273780 | note | — 40 measurements per lot
cbe27888-4596-52e2-a446-2b8e12d3f212 | note | REFERENCE DOCUMENTS: 204.03
f1f59a56-739f-57ac-9cc5-e67d2d407671 | note | INSPECTION/TEST METHOD: Survey conformance point
e8934a16-2891-5deb-a761-1c4de10e364e | note | RECORD OF CONFORMITY: Survey report, Lot Register
06b383c9-f051-5e47-856c-b8e80fb2a9d8 | note | WP, SCP
818b536f-c392-573a-b353-ee75d6d27b84 | note | RESPONSIBILITY: Site Engineer & Surveyor
5ae26f3a-0541-51e6-9f6d-bca49b48af77 | textbox | Date Completed:
75d56609-e699-4db0-a7df-add99e22a6fe | checkpoint | 3.12 Survey Conformance (Scale A for Sunbury Rd)
0cf11fee-b5c7-5a5c-9527-295fd670f3c2 | note | FREQUENCY: Each lot
a064cf1c-afb8-57d4-94a6-5275c3a0f9ef | note | ACCEPTANCE CRITERIA: The number of measurements and the tolerances of the mean and standard deviation from the theoretical surface level must comply with Table 204.031
7192259d-2b75-5030-95b4-98581311900a | note | ○ Scale A:
634fde76-c25c-51e1-a77b-d904cb58530c | note | — Range x = +5,-15
bfc5659b-c00a-5b3e-b4d8-08feb822ad1a | note | — Max S = 12mm
02d4f767-c0bf-52d6-aa37-ab9a1a75ab07 | note | — 80 measurements per lot
2ce5e7eb-ef21-5a07-8794-25301dd38d25 | note | REFERENCE DOCUMENTS: 204.03
edca5891-0abf-57de-bada-4ec2d0fab43c | note | INSPECTION/TEST METHOD: Survey conformance point
8f9e5870-b90d-5cb9-9c27-810362d6637d | note | RECORD OF CONFORMITY: Survey report, Lot Register
a3adb41e-3ce2-5a3a-92f0-df6543797b7a | note | WP, SCP
120a77de-93ad-5f5a-a041-2f0f629570d3 | note | RESPONSIBILITY: Site Engineer & Surveyor
96bb84dd-3648-5bed-9ef4-e36d5884f10e | textbox | Date Completed:
f4a69e07-8c9e-4d43-946d-f23f454cc420 | checkpoint | Final Inspection
fa333777-c1a3-5ff5-9bb5-b22213bbb0d2 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4c187dcc-0dc7-5e2e-8b92-be8040abe170 | textbox | Print Name:
428758f6-29e2-579b-8a19-7f134507891a | textbox | Position:
6d024fea-5d4a-536d-972f-52337f2bc3bf | textbox | Date: