## ITP-006
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [8 empty] | Document # M3RNAR-FUL-QAC-ITP-0006
[12 empty] | Revision : 2 | Date : 08/09/25
Client: |  | APAM |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Northern Access Road |  | Class 3 Crushed Rock Subbase |  | Name: Kamal Nour Hussain |  | Name: |  |  | Name: Damon Bromwich
Job No: |  | 7436000 |  | Specifications: Section 173 , 304, 204, VR Code of Practice RC 500.02 as outlined in M3R-BECA-001-SPC-00001[C04]
|  |  |  | Structure / Component: Pavement |  | Signed : | #VALUE! | Signed : |  |  | Signed :
|  |  |  | Location: NAR & Sunbury Road |  | Date : 08/09/2025 |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [6 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - Using the correct and complete set of drawings - All drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Material Mix Design |  | Prior to commencing any activity | Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175 | Cl 812.04 RC 500.02 | Document Review | Mix Design VicRoads Approval | HP* | Site Engineer | N/A |  | N/A
1.3 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual Inspection | This ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Transverse Joints |  | Check prior to placing material | Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres | Project Specifications Cl.304 | Visual Inspection | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2.2 | Longitudinal Joints |  | Check prior to placing material | Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane. | Project Specifications Cl.304 | Visual Inspection | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2.3 | Lot Size |  | Check prior to placing material | A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser. | . Project Specifications Cl.304 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Layer Thickness |  | Each Lot | The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material. | Project Specifications Cl.304 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.5 | Proof Rolling |  | Proof Roll each layer | No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03. | Project Specifications Cl.304 | Visual inspection | This ITP signed off | HP/ WP | Site Engineer & Superintendent |  |  | N/A
3 | Testing Requirements
3.1 | Determine Testing Scale & Initial Testing Frequency |  | Prior to Testing | The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified. Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course. | Project Specifications Cl.304 | Document Review/ Site Inspection | Signed ITP | AP | Project Engineer | N/A |  | N/A
3.2 | Compaction Testing (Scale B for NAR) |  | Every Lot Every second lot (reduced frequency) | Minimum Characteristic Density Ratio (CDR) of not less than 97%, using Modified compaction effort. | Project Specifications Cl.304 | Test point | This ITP signed off; Test reports | TP | Site Engineer | N/A |  | N/A
3.3 | Compaction Testing (Scale A for Sunbury Rd) |  | Every Lot Every second lot (reduced frequency) | Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort. | Project Specifications Cl.304 | Test point | This ITP signed off; Test reports | TP | Site Engineer | N/A |  | N/A
3.4 | Compaction Testing (Small Lots) |  | Each Lot | Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort. | Project Specifications Cl.304 | Test Point | Test Records Lot Register | TP | Site Engineer | N/A |  | N/A
3.5 | Material Grading - Post Compaction (Class 2 & 3 Only) |  | First Lot Only | Post compaction material grading results must comply with the following: Class 4 - N/A Class 3 - As per Table 304.101 - VR Spec. 304.10 Class 2 - As per Table 304.101 - VR Spec. 304.10 | Project Specifications Cl.304 | Test point | This ITP signed off; Test reports | TP | Site Engineer | N/A |  | N/A
3.6 | Plasticity Index - Post Compaction (Class 2 & 3 Only) |  | First Lot Only | Post compaction PI results must comply with the following: Class 4 - N/A Class 3 - 0 to 10 Class 2 - 0 to 6 | Project Specifications Cl.304 | Test point | This ITP signed off; Test reports | TP | Site Engineer | N/A |  | N/A
3.7 | Survey Conformance (Scale B for NAR) |  | Each lot | Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits: Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances: Range x = +8, -16mm Max S = 15 mm 40 measurements per lot (Minimum) | Project Specifications Cl.304 | Survey | This ITP signed off; Survey Report | SCP | Site Engineer/ Surveyor | N/A |  | N/A
3.8 | Survey Conformance (Scale A for Sunbury Rd) |  | Each lot | Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits: Shape: no point deviation > 8mm from 3m straight edge in any direction Surface level tolerances: Range x = +6, -10mm Max S = 10 mm 80 measurements per lot (Minimum) | Project Specifications Cl.304 | Survey | This ITP signed off; Survey Report | SCP | Site Engineer/ Surveyor | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on L16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This will need to be tested regardless of Silt?

## Sheet1
Cost Code | Cost Code Description | Unit | Original Quantity | Quantity At Completion | Budget Rate | Original Budget Total | Quantity To Date | To Date Rate | Actual To Date (ACWP) | Quantity To Complete | To Complete Rate | Estimate To Complete | Budgeted Quantity | Estimate At Completion Rate | Estimate At Completion (EAC) | Delta EAC | Delta VAC
01.* | Supervision & Management |  | 0 | 0 | 0 | 1240420 | 0 | 0 | 61416 | 0 | 0 | 1190700 | 0 | 0 | 1252116 | -71743 | 71743
1.01 | SUP - Project Manager | Month | 17 | 17 | 12911.353 | 219493 | 1 | 16000 | 16000 | 8 | 16000 | 128000 | 9 | 16000 | 144000 | -32000 | 31999
1.02 | SUP - Project Engineer | Month | 17 | 17 | 20827.529 | 354068 | 1 | 14000 | 14000 | 16 | 13000 | 208000 | 17 | 13058.824 | 222000 | -52000 | 52000
1.03 | SUP - Site Engineer | Month | 14 | 14 | 21430.143 | 300022 | 0 | 0 | 2224 | 16 | 8000 | 128000 | 16 | 8139 | 130224 | -32000 | 32000
1.04 | SUP - Foreman | Month | 18 | 18 | 17172.944 | 309113 | 0 | 0 | 0 | 7 | 20571.429 | 144000 | 7 | 20571.429 | 144000 | -16000 | 16000
1.05 | SUP - Leading/Hand/Site Management | Month | 1 | 1 | 0 | 0 | 2 | 12460.5 | 24921 | 6 | 13000 | 78000 | 8 | 12865.125 | 102921 | 7321 | -7321
1.06 | SUP - HSEQ Officer | Item | 1 | 1 | 36870 | 36870 | 0 | 0 | 0 | 8 | 12000 | 96000 | 8 | 12000 | 96000 | 16000 | -16000
1.07 | SUP - Staff Expenses | Item | 1 | 1 | 20854 | 20854 | 0 | 0 | 4271 | 1 | 408700 | 408700 | 1 | 412971 | 412971 | 36936 | -36936
02.* | Site Facilities |  | 0 | 0 | 0 | 502046 | 0 | 0 | 98585 | 0 | 0 | 171398 | 0 | 0 | 269983 | 33868 | -33869
2.01 | SITE FAC - Compound/Site Demob | Weeks | 52 | 52 | 200 | 10400 | 0 | 0 | 0 | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 0 | 0
2.02 | SITE FAC - Building Hire | Weeks | 52 | 52 | 2071.385 | 107712 | 18 | 615.611 | 11081 | 38 | 678.947 | 25800 | 56 | 658.589 | 36881 | 11081 | -11081
2.03 | SITE FAC - Services - water, electricity, sewer | Weeks | 52 | 52 | 2474.692 | 128684 | 0 | 0 | 15215 | 1 | 5000 | 5000 | 1 | 20215 | 20215 | 0 | 0
2.04 | SITE FAC - Toilet Pumpouts | Weeks | 52 | 52 | 500 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.05 | SITE FAC - Test & Tag | Weeks | 52 | 52 | 146.654 | 7626 | 18 | 204.111 | 3674 | 38 | 173.105 | 6578 | 56 | 183.071 | 10252 | 2141 | -2141
2.06 | SITE FAC - Waste Bins | Weeks | 52 | 52 | 335 | 17420 | 13 | 471.538 | 6130 | 38 | 458.421 | 17420 | 51 | 461.765 | 23550 | 6130 | -6130
2.07 | SITE FAC - Site Running Costs | Weeks | 52 | 52 | 1846.904 | 96039 | 18 | 1863.278 | 33539 | 38 | 1857.895 | 70600 | 56 | 1859.625 | 104139 | 9969 | -9970
2.08 | SITE FAC - Site Fencing | lm | 500 | 500 | 20.23 | 10115 | 0 | 0 | 4855 | 900 | 4.444 | 4000 | 900 | 9.839 | 8855 | 4277 | -4277
2.09 | SITE FAC - Compound Setup | Item | 1 | 1 | 65091 | 65091 | 1 | 24091 | 24091 | 0 | 0 | 0 | 1 | 24091 | 24091 | 270 | -270
2.1 | SITE FAC - Compound Demob | Item | 1 | 1 | 32959 | 32959 | 0 | 0 | 0 | 1 | 17000 | 17000 | 1 | 17000 | 17000 | 0 | 0
03.* | Site Costs |  | 0 | 0 | 0 | 531388 | 0 | 0 | 235763 | 0 | 0 | 367282 | 0 | 0 | 603045 | 161485 | -161486
3.01 | SITE COST - Cleaner | mhrs | 2813 | 2813 | 50 | 140650 | 31 | 253.677 | 7864 | 117 | 220 | 25740 | 148 | 227.054 | 33604 | -660 | 660
3.02 | SITE COST - Small Tools | Item | 1 | 1 | 59599 | 59599 | 18 | 2197.444 | 39554 | 38 | 913.737 | 34722 | 56 | 1326.357 | 74276 | 15596 | -15596
3.03 | SITE COST - Temporary Lighting | Shift | 420 | 420 | 140 | 58800 | 0.4 | 61465 | 24586 | 0.6 | 60666.667 | 36400 | 1 | 60986 | 60986 | 1166 | -1166
3.04 | SITE COST - Street Sweeper | Hrs | 873 | 873 | 105 | 91665 | 13 | 759.615 | 9875 | 38 | 505.263 | 19200 | 51 | 570.098 | 29075 | 8180 | -8180
3.05 | SITE COST - Plant Mob Small | EaWay | 52 | 52 | 300 | 15600 | 0 | 0 | 2400 | 50 | 312 | 15600 | 50 | 360 | 18000 | 0 | 0
3.06 | SITE COST - Plant Mob Large | EaWay | 40 | 40 | 700 | 28000 | 0 | 0 | 800 | 65 | 430.769 | 28000 | 65 | 443.077 | 28800 | 0 | 0
3.07 | SITE COST - Site Maintenance | Item | 1 | 1 | 85597 | 85597 | 18 | 2001.389 | 36025 | 38 | 2000 | 76000 | 56 | 2000.446 | 112025 | -1456 | 1456
3.08 | SITE COST - Plant Hire Costs | Weeks | 59 | 59 | 872.492 | 51477 | 0 | 0 | 110553 | 0 | 0 | 131620 | 0 | 0 | 242173 | 134553 | -134553
3.09 | SITE COST - Wet Weather |  | 0 | 0 | 0 | 0 | 0 | 0 | 4106 | 0 | 0 | 0 | 0 | 0 | 4106 | 4106 | -4106
04.* | Survey |  | 0 | 0 | 0 | 256413 | 0 | 0 | 47493 | 0 | 0 | 113300 | 0 | 0 | 160793 | 8787 | -8787
4.01 | SURV - 1 Man Survey Crew | Hours | 2000 | 2000 | 102.85 | 205700 | 473 | 100.408 | 47493 | 0 | 0 | 108300 | 473 | 329.372 | 155793 | 8787 | -8787
4.02 | SURV - Base Station | Month | 12 | 12 | 2667.75 | 32013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.03 | SURV - Survey Consumables | Weeks | 37 | 37 | 505.405 | 18700 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0
05.* | Environmental |  | 0 | 0 | 0 | 292045 | 0 | 0 | 89000 | 0 | 0 | 51168 | 0 | 0 | 140168 | 5809 | -5809
5.01 | ENV - Environmental | Item | 1 | 1 | 292045 | 292045 | 13 | 6846.154 | 89000 | 43 | 1189.953 | 51168 | 56 | 2503 | 140168 | 5809 | -5809
06.* | Design Costs |  | 0 | 0 | 0 | 1190246 | 0 | 0 | 955675 | 0 | 0 | 205512 | 0 | 0 | 1161187 | -249 | 249
6.01 | DESIGN - SMEC Subcontract | Item | 1 | 1 | 834817 | 834817 | 0 | 0 | 805736 | 1 | 63545 | 63545 | 1 | 869281 | 869281 | 0 | 0
6.02 | DESIGN - SMEC Construction Phase | Item | 1 | 1 | 64267 | 64267 | 0 | 0 | 0 | 0 | 0 | 64267 | 0 | 0 | 64267 | 0 | 0
6.03 | DESIGN - Cox Architecture | Item | 1 | 1 | 60000 | 60000 | 0 | 0 | 42990 | 0 | 0 | 17000 | 0 | 0 | 59990 | 0 | 0
6.04 | DESIGN - Proof Eng | Item | 1 | 1 | 60000 | 60000 | 0 | 0 | 69412 | 0 | 0 | 20000 | 0 | 0 | 89412 | 0 | 0
6.05 | DESIGN - Powerplant (Street Lighting) | Item | 1 | 1 | 105518 | 105518 | 0 | 0 | 15785 | 0 | 0 | 10000 | 0 | 0 | 25785 | 0 | 0
6.06 | DESIGN - Capire (Stakeholder Consultant) | Item | 1 | 1 | 62404 | 62404 | 0 | 0 | 20512 | 0 | 0 | 28000 | 0 | 0 | 48512 | -989 | 989
6.07 | DESIGN - Temporary Works | Item | 1 | 1 | 3240 | 3240 | 0 | 0 | 1240 | 0 | 0 | 2700 | 0 | 0 | 3940 | 740 | -740
07.* | Tender Costs |  | 0 | 0 | 0 | 171600 | 0 | 0 | 177324 | 0 | 0 | 0 | 0 | 0 | 177324 | 0 | 0
7.01 | TENDER - Tender Costs eg SMEC, Cox, printing, CGE, Power Plant | Item | 1 | 1 | 171600 | 171600 | 0 | 0 | 177324 | 0 | 0 | 0 | 0 | 0 | 177324 | 0 | 0
08.* | Management System Audits |  | 0 | 0 | 0 | 31200 | 0 | 0 | 6979 | 0 | 0 | 25400 | 0 | 0 | 32379 | 0 | 0
8.01 | SQE - Audits | Item | 1 | 1 | 31200 | 31200 | 0 | 0 | 6979 | 0 | 0 | 25400 | 0 | 0 | 32379 | 0 | 0
10.* | Project Manager's Contingency |  | 0 | 0 | 0 | 93808 | 0 | 0 | 0 | 0 | 0 | 786400 | 0 | 0 | 786400 | -528627 | 528627
10.01 | PM - Contingency | Item | 1 | 1 | 93808 | 93808 | 0 | 0 | 0 | 0 | 0 | 786400 | 0 | 0 | 786400 | -528627 | 528627
22.* | Traffic Management - Barrier Hire |  | 0 | 0 | 0 | 212888 | 0 | 0 | 68533 | 0 | 0 | 120000 | 0 | 0 | 188533 | 1971 | -1971
22.01 | TRAF - Barrier Installation/Removal - Cranes, Trucking, Labour | Item | 1 | 1 | 212888 | 212888 | 0 | 0 | 48128 | 0 | 0 | 120000 | 0 | 0 | 168128 | 451 | -451
22.02 | TRAF - Barriers - Installation Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 20405 | 0 | 0 | 0 | 0 | 0 | 20405 | 1520 | -1520
23.* | Traffic Management - Personnel |  | 0 | 0 | 0 | 395800 | 0 | 0 | 102821 | 0 | 0 | 240210 | 0 | 0 | 343031 | 62483 | -62483
23.01 | TRAF - Traffic Crews | Item | 1 | 1 | 395800 | 395800 | 3 | 34273.667 | 102821 | 8 | 30026.25 | 240210 | 11 | 31184.636 | 343031 | 62483 | -62483
24.* | Bridge Closure Traffic Management |  | 0 | 0 | 0 | 172670 | 0 | 0 | 0 | 0 | 0 | 132590 | 0 | 0 | 132590 | 0 | 0
24.01 | TRAF - Bridge Closures | Item | 1 | 1 | 172670 | 172670 | 0 | 0 | 0 | 0 | 0 | 132590 | 0 | 0 | 132590 | 0 | 0
25.* | Traffic Management Consultants |  | 0 | 0 | 0 | 86900 | 0 | 0 | 45910 | 0 | 0 | 30780 | 0 | 0 | 76690 | -560 | 560
25.01 | TRAF -Trafficworks | Item | 1 | 1 | 64000 | 64000 | 0 | 0 | 42550 | 0 | 0 | 20000 | 0 | 0 | 62550 | 0 | 0
25.02 | TRAF - Road Safety Audits | Item | 1 | 1 | 22900 | 22900 | 0 | 0 | 3360 | 0 | 0 | 10780 | 0 | 0 | 14140 | -560 | 560
27.* | Traffic Management - Temporary Linemarking & Signage |  | 0 | 0 | 0 | 72080 | 0 | 0 | 43464 | 0 | 0 | 32959 | 0 | 0 | 76423 | 0 | 0
27.01 | TRAF - Temporary Signs | Item | 1 | 1 | 0 | 0 | 0 | 0 | 38478 | 0 | 0 | 0 | 0 | 0 | 38478 | 0 | 0
27.02 | TRAF - Temporary Lines | Item | 1 | 1 | 72080 | 72080 | 0 | 0 | 4986 | 0 | 0 | 32959 | 0 | 0 | 37945 | 0 | 0
28.* | Temporary Pavement |  | 0 | 0 | 0 | 52365 | 0 | 0 | 15197 | 0 | 0 | 40000 | 0 | 0 | 55197 | 2574 | -2574
28.01 | Temp Road Pavement | sm | 200 | 200 | 18.08 | 3616 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 16410 | -16410
28.02 | Temp Footpaths during Construction (Concrete pavement) - 150mm Thick 32 MPa broom finish F82 with 40mm cover | sm | 1070 | 1070 | 45.56 | 48749 | 0 | 0 | 11039 | 0 | 0 | 20000 | 0 | 0 | 31039 | -13836 | 13836
28.03 | Temp Footpaths during Construction (Concrete pavement) - Crushed Rock Pad - Park | sm | 1 | 1 | 0 | 0 | 0 | 0 | 4158 | 0 | 0 | 0 | 0 | 0 | 4158 | 0 | 0
30.* | Job ready startup costs |  | 0 | 0 | 0 | 35472 | 0 | 0 | 5836 | 0 | 0 | 10591 | 0 | 0 | 16427 | 0 | 0
30.01 | Job ready startup costs - Inductions, medicals, | Item | 1 | 1 | 10045 | 10045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.02 | Job ready startup costs - Labour costs | mhr | 132 | 132 | 73.379 | 9686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30.03 | Job ready startup costs - PPE | Week | 72 | 72 | 218.625 | 15741 | 0 | 0 | 5836 | 0 | 0 | 10591 | 0 | 0 | 16427 | 0 | 0
31.* | Defects Maintenance Allowances |  | 0 | 0 | 0 | 101922 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
31.01 | Defects Maintenance Allowances | Item | 1 | 1 | 101922 | 101922 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
40.* | SHARED USE PATH BRIDGE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41.* | Earthworks to Bridge Approach |  | 0 | 0 | 0 | 89013 | 0 | 0 | 52166 | 0 | 0 | 47660 | 0 | 0 | 99826 | 15673 | -15673
41.01 | SUP - Bridge Approaches - supply and place Fill | ccm | 2713 | 2713 | 32.81 | 89013 | 0 | 0 | 52166 | 0 | 0 | 47660 | 0 | 0 | 99826 | 15673 | -15673
42.* | Structural Element Excavations & Backfill |  | 0 | 0 | 0 | 49942 | 0 | 0 | 0 | 0 | 0 | 49942 | 0 | 0 | 49942 | 0 | 1
42.01 | SUP - Excavate & backfill - River Span Pier Pilecaps | M3 | 298 | 298 | 82.779 | 24668 | 0 | 0 | 0 | 0 | 0 | 24668 | 0 | 0 | 24668 | 0 | 0
42.02 | SUP - Beaching - East Abutment | M2 | 132 | 132 | 118.538 | 15647 | 0 | 0 | 0 | 0 | 0 | 15647 | 0 | 0 | 15647 | 0 | 0
42.03 | SUP - Contamination - off site disposal | bcm | 47 | 47 | 204.83 | 9627 | 0 | 0 | 0 | 0 | 0 | 9627 | 0 | 0 | 9627 | 0 | 0
43.* | Piling |  | 0 | 0 | 0 | 395489 | 0 | 0 | 1175 | 0 | 0 | 334208 | 0 | 0 | 335383 | 0 | -1
43.01 | SUP - Piling Subbie | cm | 120 | 120 | 2844.008 | 341281 | 0 | 0 | 1175 | 0 | 0 | 300000 | 0 | 0 | 301175 | 0 | 0
43.02 | SUP - Piling - FH Costs | cm | 120 | 120 | 184.808 | 22177 | 0 | 0 | 0 | 0 | 0 | 22177 | 0 | 0 | 22177 | 0 | 0
43.03 | SUP - Piling - Extra Over ASS | LS | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43.04 | SUP - Rock Anchors For Cantilever Crosshead | Ea | 2 | 2 | 10000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43.05 | SUP - Piling - contaminated spoil disposal | bcm | 121 | 121 | 99.43 | 12031 | 0 | 0 | 0 | 0 | 0 | 12031 | 0 | 0 | 12031 | 0 | 0
44.* | Structural Steelwork |  | 0 | 0 | 0 | 1324253 | 0 | 0 | 428085 | 0 | 0 | 1553217 | 0 | 0 | 1981302 | 55000 | -55000
44.01 | SUP - Structural Girder Bridge - supply, paint, & deliver | Tonne | 226 | 226 | 4703.699 | 1063036 | 0 | 0 | 428085 | 0 | 0 | 1292000 | 0 | 0 | 1720085 | 55000 | -55000
44.02 | SUP - Structural Girder Bridge - Assemble & Install | Tonne | 226.6 | 226.6 | 1152.767 | 261217 | 0 | 0 | 0 | 1 | 261217 | 261217 | 1 | 261217 | 261217 | 0 | 0
45.* | Precast Concrete |  | 0 | 0 | 0 | 397089 | 0 | 0 | 22294 | 0 | 0 | 420360 | 0 | 0 | 442654 | 0 | -1
45.01 | SUP - Precast Floor Panels - supply & deliver | sm | 760 | 760 | 278.817 | 211901 | 0 | 0 | 10000 | 0 | 0 | 255000 | 0 | 0 | 265000 | 0 | 1
45.02 | SUP - Precast Floor Panels - installation | sm | 760 | 760 | 63.289 | 48100 | 0 | 0 | 0 | 0 | 0 | 48100 | 0 | 0 | 48100 | 0 | 0
45.03 | SUP - Permastruct Decking | Ea | 4 | 4 | 31000 | 124000 | 0 | 0 | 12294 | 0 | 0 | 117260 | 0 | 0 | 129554 | 0 | 0
45.04 | SUP - Super T Beams - install | Ea | 4 | 4 | 3272 | 13088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46.* | Insitu Concrete Works |  | 0 | 0 | 0 | 448395 | 0 | 0 | 0 | 0 | 0 | 398707 | 0 | 0 | 398707 | -45222 | 45221
46.01 | SUP - In Situ Conc Subbie | cm | 560.3 | 560.3 | 501.315 | 280887 | 0 | 0 | 0 | 0 | 0 | 260000 | 0 | 0 | 260000 | -20887 | 20887
46.02 | SUP - Concrete F15 & F20 - supply only | cm | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2144 | 0 | 0 | 2144 | 0 | 0
46.03 | SUP - Concrete VR 32 MPa - supply only | cm | 21 | 21 | 135.286 | 2841 | 0 | 0 | 0 | 0 | 0 | 2841 | 0 | 0 | 2841 | 0 | 0
46.04 | SUP - Concrete VR 40 MPa - supply only | cm | 275 | 241 | 165.203 | 39814 | 0 | 0 | 0 | 241 | 147.332 | 35507 | 241 | 147.332 | 35507 | 0 | 0
46.05 | SUP - Concrete - testing | cm | 296 | 241 | 24.494 | 5903 | 0 | 0 | 0 | 241 | 14.938 | 3600 | 241 | 14.938 | 3600 | 0 | 0
46.06 | SUP - Reinforcement - supply & deliver | Tonne | 46.4 | 46.4 | 1272.737 | 59055 | 0 | 0 | 0 | 0 | 0 | 59055 | 0 | 0 | 59055 | 0 | 0
46.07 | SUP - Bearings - Supply & deliver | Ea | 16 | 16 | 2054.5 | 32872 | 0 | 0 | 0 | 8 | 4445 | 35560 | 8 | 4445 | 35560 | 2688 | -2688
46.08 | SUP - Bearings - install only | Ea | 16 | 16 | 1688.938 | 27023 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | -27023 | 27023
47.* | Miscellaneous Elements (metalwork, ballustrading, conduits, & line markings) |  | 0 | 0 | 0 | 157750 | 0 | 0 | 6783 | 0 | 0 | 176470 | 0 | 0 | 183253 | 506 | -505
47.01 | SUP - Metalwork - Joint Between Precast Floor Panels | lm | 250 | 250 | 21.548 | 5387 | 0 | 0 | 0 | 290 | 18.576 | 5387 | 290 | 18.576 | 5387 | 0 | 0
47.02 | SUP - Metalwork (Expansion Joints) to both the Steel & Super Tee spans | lm | 19.2 | 19.2 | 1000 | 19200 | 0 | 0 | 0 | 9 | 2133.333 | 19200 | 9 | 2133.333 | 19200 | 0 | 0
47.03 | SUP - Gutter, Kickplate Install | lm | 310 | 310 | 213.913 | 66313 | 0 | 0 | 6783 | 310 | 140.106 | 43433 | 310 | 161.987 | 50216 | 506 | -506
47.04 | SUP - SS Handrail | lm | 84 | 84 | 700 | 58800 | 0 | 0 | 0 | 310 | 189.677 | 58800 | 310 | 189.677 | 58800 | 0 | 0
47.05 | SUP - Line Marking | Item | 1 | 1 | 1500 | 1500 | 0 | 0 | 0 | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 0 | 0
47.06 | SUP - Conduits - supply & install | lm | 310 | 310 | 21.129 | 6550 | 0 | 0 | 0 | 620 | 15.565 | 9650 | 620 | 15.565 | 9650 | 0 | 0
47.07 | SUP - Off Structure Fencing | lm | 0 | 192.5 | 0 | 0 | 0 | 0 | 0 | 192.5 | 200 | 38500 | 192.5 | 200 | 38500 | 0 | 0
48.01 | SUP - Painting | sm | 476 | 200 | 41.615 | 8323 | 0 | 0 | 0 | 200 | 25 | 5000 | 200 | 25 | 5000 | 0 | 0
50* | ROADWORKS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51.* | RW - Demolition, Clearing & Grubbing |  | 0 | 0 | 0 | 170771 | 0 | 0 | 34278 | 0 | 0 | 119986 | 0 | 0 | 154265 | 9274 | -9274
51.01 | RW - Demolition - clear trees, relocate palm trees | Item | 1 | 1 | 59596 | 59596 | 0 | 0 | 20773 | 0 | 0 | 5000 | 0 | 0 | 25773 | 9273 | -9273
51.02 | RW -Demolition - Concrete Kerbs | m | 3894 | 2400 | 33.912 | 81389 | 300 | 27.033 | 8110 | 1800 | 25.667 | 46200 | 2100 | 25.862 | 54310 | 0 | 0
51.03 | RW -Demolition - asphalt pavements | sm | 1800 | 1800 | 12.127 | 21829 | 0 | 0 | 0 | 0 | 0 | 21829 | 0 | 0 | 21829 | 0 | 0
51.04 | RW - Demolition - remove bluestones | sm | 187 | 187 | 31.941 | 5973 | 90 | 59.944 | 5395 | 0 | 0 | 5973 | 90 | 126.322 | 11369 | 1 | -1
51.05 | RW -Demolition - remove Signs | Each | 2 | 2 | 992 | 1984 | 0 | 0 | 0 | 2 | 992 | 1984 | 2 | 992 | 1984 | 0 | 0
51.06 | RW - Remove Existing Concrete Slabs | m2 | 1839 | 1300 | 0 | 0 | 0 | 0 | 0 | 1300 | 30 | 39000 | 1300 | 30 | 39000 | 0 | 0
52.* | RW -Cart & Dispose Contaminated Soil |  | 0 | 0 | 0 | 412925 | 0 | 0 | 126214 | 0 | 0 | 299520 | 0 | 0 | 425734 | -5315 | 5315
52.01 | RW - Contaminated soils - cart & dispose | Tonne | 6640 | 6640 | 96.505 | 640796 | 1158 | 108.993 | 126214 | 3000 | 99.84 | 299520 | 4158 | 102.389 | 425734 | -5315 | 5315
52.02 | RW - Contaminated soils - Reuse In Ped Bridge Approach | ccm | -1000 | -1000 | 227.871 | -227871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53.* | RW - Cart & Dispose Clean Material |  | 0 | 0 | 0 | 0 | 0 | 0 | 8707 | 0 | 0 | 12000 | 0 | 0 | 20707 | 707 | -707
53.01 | RW - Pavements - Cart & Dispose Clean Material |  | 0 | 0 | 0 | 0 | 0 | 0 | 8097 | 2000 | 6 | 12000 | 2000 | 10.049 | 20097 | 97 | -97
53.02 | RW -Pavements - Clean material - Cart for Re Use On Site |  | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 610 | 610 | -610
54* | RW - Excavation for Pavements |  | 0 | 0 | 0 | 137372 | 0 | 0 | 64946 | 0 | 0 | 82223 | 0 | 0 | 147169 | 1689 | -1689
54.01 | RW - Excavation for Pavements incl beneath kerbs | bcm | 4459 | 4459 | 27.703 | 123526 | 0 | 0 | 54821 | 3900 | 19.288 | 75223 | 3900 | 33.345 | 130044 | 16 | -16
54.02 | RW - Subgrade Preparation - both Cut & Fill locations | sm | 7994 | 7994 | 1.732 | 13846 | 0 | 0 | 10125 | 0 | 0 | 7000 | 0 | 0 | 17125 | 1673 | -1673
55.* | RW - Fill - supply & placePlacement |  | 0 | 0 | 0 | 19008 | 0 | 0 | 0 | 0 | 0 | 19008 | 0 | 0 | 19008 | 0 | 1
55.01 | RW - Fill - import supply & deliver | ccm | 300 | 300 | 23.66 | 7098 | 0 | 0 | 0 | 0 | 0 | 7098 | 0 | 0 | 7098 | 0 | 0
55.02 | RW - Fill - place only | ccm | 531 | 531 | 22.429 | 11910 | 0 | 0 | 0 | 0 | 0 | 11910 | 0 | 0 | 11910 | 0 | 0
56.* | RW - Topsoil - strip & replace |  | 0 | 0 | 0 | 25187 | 0 | 0 | 0 | 0 | 0 | 25187 | 0 | 0 | 25187 | 0 | 0
56.01 | RW - Topsoil - load from on-site stockpile & place only | sm | 144 | 144 | 44.924 | 6469 | 0 | 0 | 0 | 0 | 0 | 6469 | 0 | 0 | 6469 | 0 | 0
56.02 | RW - Topsoil - strip | sm | 2532 | 2532 | 7.393 | 18718 | 0 | 0 | 0 | 1000 | 18.718 | 18718 | 1000 | 18.718 | 18718 | 0 | 0
57.* | RW - Subsoil drainage - Sand Backfill |  | 0 | 0 | 0 | 201127 | 0 | 0 | 5464 | 0 | 0 | 79912 | 0 | 0 | 85376 | -1985 | 1984
57.01 | RW - Material Supply - Fabric, Pipe, & backfill materials | lm | 3725 | 1494 | 14.454 | 21595 | 1494 | 3.657 | 5464 | 0 | 0 | 0 | 1494 | 3.657 | 5464 | -1985 | 1985
57.02 | RW - Excavate, lay pipe, install quarry, & install pipe & pits etc | lm | 3725 | 1494 | 28.631 | 42774 | 0 | 0 | 0 | 1494 | 19 | 28386 | 1494 | 19 | 28386 | 0 | 0
57.03 | RW - Quarry - supply & deliver | lm | 2734 | 816 | 46.315 | 37793 | 0 | 0 | 0 | 816 | 4.534 | 3700 | 816 | 4.534 | 3700 | 0 | 0
57.04 | RW - Concrete - supply & deliver | lm | 991 | 678 | 31.186 | 21144 | 0 | 0 | 0 | 678 | 13.608 | 9226 | 678 | 13.608 | 9226 | 0 | 0
57.05 | RW - Contamination | Tonne | 806 | 400 | 194.553 | 77821 | 0 | 0 | 0 | 1494 | 25.837 | 38600 | 1494 | 25.837 | 38600 | 0 | 0
58.* | RW - Subsoil drainage - Pits & Flushouts |  | 0 | 0 | 0 | 1352 | 0 | 0 | 1387 | 0 | 0 | 9076 | 0 | 0 | 10463 | -2137 | 2137
58.01 | RW - Pits & flushouts - supply & install | Each | 14 | 20 | 67.6 | 1352 | 0 | 0 | 1387 | 22 | 412.545 | 9076 | 22 | 475.591 | 10463 | -2137 | 2137
59* | RW - Stormwater Drainage (RCPs only) |  | 0 | 0 | 0 | 167324 | 0 | 0 | 26130 | 0 | 0 | 162782 | 0 | 0 | 188912 | 25204 | -25203
59.01 | RW - Pipe - supply & deliver only (all sizes) | lm | 296 | 258 | 99.783 | 25744 | 0 | 0 | 1892 | 258 | 114.911 | 29647 | 258 | 122.244 | 31539 | -1090 | 1090
59.02 | RW - Pipes - quarry supply only | lm | 296 | 258 | 108.267 | 27933 | 0 | 0 | 556 | 258 | 108.267 | 27933 | 258 | 110.422 | 28489 | 556 | -556
59.03 | RW - Pipes - excavate, lay pies, & backfill (install components only) | lm | 296 | 258 | 187.213 | 48301 | 70 | 207.971 | 14558 | 188 | 212 | 39856 | 258 | 210.907 | 54414 | 16614 | -16614
59.04 | RW - Contamination - Cat "C" |  | 0 | 0 | 0 | 65346 | 70 | 130.343 | 9124 | 188 | 347.585 | 65346 | 258 | 288.643 | 74470 | 9124 | -9124
60.* | RW - Stormwater Drainage (Box culverts only) |  | 0 | 0 | 0 | 206461 | 0 | 0 | 198407 | 0 | 0 | 177682 | 0 | 0 | 376089 | 93720 | -93720
60.01 | RW - Box culverts - supply & deliver only (all sizes) | lm | 307.8 | 541 | 204.298 | 110525 | 315 | 342.949 | 108029 | 251.5 | 221.976 | 55827 | 566.5 | 289.243 | 163856 | 71647 | -71648
60.02 | RW - Box culverts - quarry supply only | lm | 307.8 | 541 | 13.771 | 7450 | 315 | 38.086 | 11997 | 251 | 29.681 | 7450 | 566 | 34.359 | 19447 | 3184 | -3184
60.03 | RW - Box culverts - excavate, lay pies, & backfill (install components only) | lm | 307.8 | 541 | 99.277 | 53709 | 315 | 217.651 | 68560 | 251 | 250 | 62750 | 566 | 231.996 | 131310 | 17100 | -17100
60.04 | RW - Contamination (Cat "C") |  | 0 | 0 | 0 | 34777 | 315 | 31.178 | 9821 | 251 | 205.797 | 51655 | 566 | 108.615 | 61476 | 1789 | -1789
61.* | RW - Stormwater Drainage (Pits) |  | 0 | 0 | 0 | 81121 | 0 | 0 | 26550 | 0 | 0 | 155064 | 0 | 0 | 181614 | 1985 | -1986
61.01 | RW - SW Drain - Pits - Construct New | Each | 27 | 47 | 1010.17 | 47478 | 0 | 0 | 26550 | 41 | 2853.659 | 117000 | 41 | 3501.22 | 143550 | 1985 | -1985
61.02 | RW - SW Drain - Pits - Modify | Each | 27 | 10 | 1557.9 | 15579 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0
61.03 | RW - Contamination | Tonne | 71 | 71 | 97.056 | 6891 | 0 | 0 | 0 | 71 | 97.056 | 6891 | 71 | 97.056 | 6891 | 0 | 0
61.04 | RW - Connections to existing | Item | 1 | 1 | 11173 | 11173 | 0 | 0 | 0 | 0 | 0 | 11173 | 0 | 0 | 11173 | 0 | 0
62.* | RW - Stormwater drainage - Miscellaneous |  | 0 | 0 | 0 | 2517 | 0 | 0 | 720 | 0 | 0 | 14900 | 0 | 0 | 15620 | 720 | -720
62.01 | RW - Drainage (existing) - demolish | Item | 1 | 1 | 2517 | 2517 | 0 | 0 | 720 | 0 | 0 | 14900 | 0 | 0 | 15620 | 720 | -720
63.* | RW - Pavements Ex Apshalt |  | 0 | 0 | 0 | 180456 | 0 | 0 | 12071 | 0 | 0 | 86655 | 0 | 0 | 98726 | 15033 | -15032
63.01 | RW - Pavements CTCR Supply | sm | 3615 | 1355 | 38.755 | 52513 | 0 | 0 | 720 | 1355 | 8.806 | 11932 | 1355 | 9.337 | 12652 | 720 | -720
63.02 | RW - Pavements Crushed Rock Supply | sm | 6064 | 5557 | 10.265 | 57041 | 595 | 11.313 | 6731 | 4962 | 6.6 | 32749 | 5557 | 7.105 | 39480 | 9693 | -9692
63.03 | RW - Pavements CTCR Place | sm | 3616 | 1355 | 33.677 | 45632 | 0 | 0 | 0 | 1355 | 6.777 | 9183 | 1355 | 6.777 | 9183 | 0 | 0
63.04 | RW - Pavements Crushed Rock Place | sm | 6064 | 5557 | 4.547 | 25270 | 1140 | 4.053 | 4620 | 4417 | 7.424 | 32791 | 5557 | 6.732 | 37411 | 4620 | -4620
64.* | RW - Concrete Infills, concrete driveways, bluestone driveways |  | 0 | 0 | 0 | 140853 | 0 | 0 | 0 | 0 | 0 | 104946 | 0 | 0 | 104946 | 0 | 1
64.01 | RW - Conc Infills - Crushed Rock - Supply Only | sm | 1503 | 899 | 16.768 | 15074 | 0 | 0 | 0 | 899 | 5.204 | 4678 | 899 | 5.204 | 4678 | 0 | 0
64.02 | RW - Conc Infills- Crushed Rock - Place Only | sm | 1503 | 899 | 25.284 | 22730 | 0 | 0 | 0 | 899 | 9 | 8091 | 899 | 9 | 8091 | 0 | 0
64.03 | RW - Conc Infills - Concrete - Supply Only | sm | 1503 | 899 | 40.929 | 36795 | 0 | 0 | 0 | 899 | 20.79 | 18690 | 899 | 20.79 | 18690 | 0 | 0
64.04 | RW - Conc Infills - Concrete - Place Only | sm | 1503 | 899 | 64.103 | 57629 | 0 | 0 | 0 | 899 | 25 | 22475 | 899 | 25 | 22475 | 0 | 0
64.05 | RW - Conc Infill - Reo Supply | sm | 0 | 899 | 0 | 0 | 0 | 0 | 0 | 899 | 5.069 | 4557 | 899 | 5.069 | 4557 | 0 | 0
64.06 | RW - Driveways - Crushed Rock - Supply Only | sm | 75 | 617 | 0 | 0 | 0 | 0 | 0 | 616 | 3.047 | 1877 | 616 | 3.047 | 1877 | 0 | 0
64.07 | RW - Driveway - Crushed Rock - Place Only | sm | 75 | 616 | 14.002 | 8625 | 0 | 0 | 0 | 616 | 9 | 5544 | 616 | 9 | 5544 | 0 | 0
64.08 | RW - Driveways - Concrete - Supply Only | sm | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 616 | 26.399 | 16262 | 616 | 26.399 | 16262 | 0 | 0
64.09 | RW - Driveways - Concrete - Place Only | sm | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 616 | 30 | 18480 | 616 | 30 | 18480 | 0 | 0
64.1 | RW - Driveways - Reo Supply | sm | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 616 | 6.968 | 4292 | 616 | 6.968 | 4292 | 0 | 0
65.* | Kerb & Channel |  | 0 | 0 | 0 | 177832 | 0 | 0 | 6898 | 0 | 0 | 158470 | 0 | 0 | 165367 | 15261 | -15261
65.01 | RW - Kerb & Channel - Concrete Supply | lm | 2542 | 2788 | 18.314 | 51059 | 0 | 0 | 1584 | 2788 | 19.473 | 54292 | 2788 | 20.042 | 55876 | 1584 | -1584
65.02 | RW - Kerb & Channel - Lay - Include Kerb Bed | lm | 2542 | 2788 | 45.471 | 126773 | 0 | 0 | 5314 | 2788 | 37.367 | 104178 | 2788 | 39.272 | 109491 | 13677 | -13677
66.* | Asphalt |  | 0 | 0 | 0 | 1437851 | 0 | 0 | 0 | 0 | 0 | 1461586 | 0 | 0 | 1461586 | 0 | -1
66.01 | RW - ASPH - Pavement Type 1 (Inc TJ to Rego & Existing) | sm | 10502 | 1355 | 246.165 | 333553 | 0 | 0 | 0 | 1355 | 246.165 | 333553 | 1355 | 246.165 | 333553 | 0 | 0
66.02 | RW - ASPH - Pavement Type 2 (Inc TJ to Rego,Existing) | sm | 27823 | 4357 | 160.388 | 698811 | 0 | 0 | 0 | 4357 | 160.388 | 698811 | 4357 | 160.388 | 698811 | 0 | 0
66.03 | RW - ASPH - Pavement Type 3 (Inc TJ to Rego,Existing) | sm | 4501 | 883 | 115.571 | 102049 | 0 | 0 | 0 | 883 | 115.571 | 102049 | 883 | 115.571 | 102049 | 0 | 0
66.04 | RW - ASPH - Pavement Type 4 (Inc TJ to Rego,) | sm | 189 | 317 | 13.372 | 4239 | 0 | 0 | 0 | 317 | 88.246 | 27974 | 317 | 88.246 | 27974 | 0 | 0
66.05 | RW - ASPH - Pavement Type Rego and Overlay | sm | 13181 | 13181 | 14.683 | 193543 | 0 | 0 | 0 | 13181 | 14.683 | 193543 | 13181 | 14.683 | 193543 | 0 | 0
66.06 | RW - ASPH - Pavement Type Shepherd Bridge | sm | 3333 | 3333 | 14.683 | 48940 | 0 | 0 | 0 | 3333 | 14.683 | 48940 | 3333 | 14.683 | 48940 | 0 | 0
66.07 | RW - ASPH - Pavement - Profiling | cm | 886 | 886 | 64.014 | 56716 | 0 | 0 | 0 | 886 | 64.014 | 56716 | 886 | 64.014 | 56716 | 0 | 0
66.08 | RW - ASPH - Pavement - Kerb Patching | lm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67.* | Signs & Linemarking |  | 0 | 0 | 0 | 78695 | 0 | 0 | 0 | 0 | 0 | 78695 | 0 | 0 | 78695 | 0 | 0
67.01 | RW - LINEMARK - Pavement Markings – Final | Item | 1 | 1 | 32370 | 32370 | 0 | 0 | 0 | 1 | 32370 | 32370 | 1 | 32370 | 32370 | 0 | 0
67.02 | RW - SIGN - Existing Sign Relocations | Each | 18 | 18 | 510.944 | 9197 | 0 | 0 | 0 | 1 | 9197 | 9197 | 1 | 9197 | 9197 | 0 | 0
67.03 | RW - SIGN New Signs - Supply & Install | Item | 1 | 1 | 37128 | 37128 | 0 | 0 | 0 | 1 | 37128 | 37128 | 1 | 37128 | 37128 | 0 | 0
68.* | Shotcrete Wall North East Abutment |  | 0 | 0 | 0 | 102455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.01 | RW - WALL - Shotcrete Supply | sm | 150 | 150 | 23.807 | 3571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.02 | RW - WALL - Shotcrete Spray | sm | 150 | 150 | 193.307 | 28996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.03 | RW - WALL - Supply & Install Soil Nails | Ea | 84 | 84 | 629.286 | 52860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68.04 | RW - WALL - Miscellaneous | sm | 150 | 150 | 113.52 | 17028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.* | Off Structure Barriers |  | 0 | 0 | 0 | 744299 | 0 | 0 | 17650 | 0 | 0 | 485490 | 0 | 0 | 503140 | 3390 | -3390
69.01 | RW - OSB - Supply of Medium Containment Barriers inc Transition + Shop Drawings | lm | 172 | 154 | 1076.494 | 165780 | 0 | 0 | 17650 | 154 | 1004.026 | 154620 | 154 | 1118.636 | 172270 | -9610 | 9610
69.02 | RW - OSB - Supply of Regular Containment Barriers | lm | 122 | 72 | 1579.111 | 113696 | 0 | 0 | 0 | 1 | 68520 | 68520 | 1 | 68520 | 68520 | 0 | 0
69.03 | RW - OSB - Install Medium Containment | lm | 172 | 154 | 151.429 | 23320 | 0 | 0 | 0 | 154 | 151.429 | 23320 | 154 | 151.429 | 23320 | 0 | 0
69.04 | RW - OSB - Install Regular Containment | lm | 122 | 72 | 237.514 | 17101 | 0 | 0 | 0 | 72 | 237.514 | 17101 | 72 | 237.514 | 17101 | 0 | 0
69.06 | RW - OSB - Strip Footing Conc Supply | cm | 264 | 264 | 173.125 | 45705 | 0 | 0 | 0 | 220 | 192.777 | 42411 | 220 | 192.777 | 42411 | 0 | 0
69.07 | RW - OSB - Strip Footing Reo Supply | Tonne | 42 | 42 | 1269.643 | 53325 | 0 | 0 | 0 | 26.44 | 1200 | 31728 | 26.44 | 1200 | 31728 | 0 | 0
69.08 | RW- OSB - Strip Footing Concrete Subbie | cm | 264 | 264 | 449.962 | 118790 | 0 | 0 | 0 | 0 | 0 | 118790 | 0 | 0 | 118790 | 0 | 0
69.1 | RW - OSB - Supply and Install Medium Containment Railing | lm | 172 | 172 | 651.453 | 112050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.11 | RW - OSB - Supply and Install Regular Containment Railing | lm | 122 | 122 | 446.984 | 54532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.12 | RW - OSB - End Posts | Ea | 4 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69.13 | RW - OSB - Crash Cushion | Ea | 2 | 2 | 10000 | 20000 | 0 | 0 | 0 | 2 | 14500 | 29000 | 2 | 14500 | 29000 | 13000 | -13000
70.* | Sign Gantry |  | 0 | 0 | 0 | 72666 | 0 | 0 | 0 | 0 | 0 | 98009 | 0 | 0 | 98009 | 0 | 0
70.01 | RW - GANT - Manufacture & Deliv Gantry | Tonne | 13.5 | 13.5 | 4680.963 | 63193 | 0 | 0 | 0 | 0 | 0 | 83536 | 0 | 0 | 83536 | 0 | 0
70.02 | RW - GANT - Install Gantry | Tonne | 13.5 | 13.5 | 534.222 | 7212 | 0 | 0 | 0 | 0 | 0 | 7212 | 0 | 0 | 7212 | 0 | 0
70.03 | RW - GANT - Bridge Connections | Each | 4 | 4 | 565.25 | 2261 | 0 | 0 | 0 | 0 | 0 | 7261 | 0 | 0 | 7261 | 0 | 0
71.* | Traffic Signals |  | 0 | 0 | 0 | 472297 | 0 | 0 | 0 | 0 | 0 | 472297 | 0 | 0 | 472297 | 0 | -1
71.01 | RW - SIG - Traffic Signal Conduits - Supply | lm | 1441 | 1441 | 14.478 | 20863 | 0 | 0 | 0 | 0 | 0 | 20863 | 0 | 0 | 20863 | 0 | 0
71.02 | RW - SIG - Traffic Signal Pits - Supply |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71.03 | RW - SIGN - Crushed Rock Supply | lm | 946 | 946 | 2.504 | 2369 | 0 | 0 | 0 | 0 | 0 | 2369 | 0 | 0 | 2369 | 0 | 0
71.04 | RW - SIG - Excavate, Lay, Backfill | lm | 946 | 946 | 29.841 | 28230 | 0 | 0 | 0 | 0 | 0 | 28230 | 0 | 0 | 28230 | 0 | 0
71.05 | RW - SIG - UG Boring | lm | 495 | 495 | 157.903 | 78162 | 0 | 0 | 0 | 0 | 0 | 78162 | 0 | 0 | 78162 | 0 | 0
71.06 | RW - SIG - UG Boring Evap Pond | Item | 1 | 1 | 4973 | 4973 | 0 | 0 | 0 | 0 | 0 | 4973 | 0 | 0 | 4973 | 0 | 0
71.07 | RW - SIG - Traffic Signalling Subcontract | Item | 1 | 1 | 273000 | 273000 | 0 | 0 | 0 | 0 | 0 | 273000 | 0 | 0 | 273000 | 0 | 0
71.08 | RW - SIG - Dispose of Contam to Tip | Tonne | 670 | 670 | 96.567 | 64700 | 0 | 0 | 0 | 0 | 0 | 64700 | 0 | 0 | 64700 | 0 | 0
72.* | Landscaping |  | 0 | 0 | 0 | 11153 | 0 | 0 | 1295 | 0 | 0 | 41472 | 0 | 0 | 42767 | 0 | 0
72.01 | RW - LAND - Topsoil Seeding | sm | 1153 | 1153 | 1 | 1153 | 0 | 0 | 0 | 0 | 0 | 11472 | 0 | 0 | 11472 | 0 | 0
72.02 | RW - LAND - Landscaping Subbie | Item | 1 | 1 | 10000 | 10000 | 0 | 0 | 1295 | 0 | 0 | 30000 | 0 | 0 | 31295 | 0 | 0
73.* | Overheight Detection System |  | 0 | 0 | 0 | 38556 | 0 | 0 | 0 | 0 | 0 | 38556 | 0 | 0 | 38556 | 0 | 0
73.01 | RW - OHD - Relocate existing pole, convert existing VMS to STREAMS and install new control cabinet:, install new POS or extend power from existing supply; supply and install new sensors:; | Item | 1 | 1 | 28024 | 28024 | 0 | 0 | 0 | 0 | 0 | 28024 | 0 | 0 | 28024 | 0 | 0
73.02 | RW - OHD - Civils e.g. cabinet foundation, pole foundation, & minor conduiting | Item | 1 | 1 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 9000 | 0 | 0
73.03 | RW - OHD - Contamination - disposal of "Cat" C material | Tonne | 15.75 | 15.75 | 97.27 | 1532 | 0 | 0 | 0 | 0 | 0 | 1532 | 0 | 0 | 1532 | 0 | 0
74.* | Street Lighting |  | 0 | 0 | 0 | 369845 | 0 | 0 | 0 | 0 | 0 | 418661 | 0 | 0 | 418661 | 0 | 0
74.01 | RW - LIGHT - Street Lighting (Conduits) - supply & deliver | lm | 855 | 855 | 18.255 | 15608 | 0 | 0 | 0 | 0 | 0 | 15608 | 0 | 0 | 15608 | 0 | 0
74.02 | RW - LIGHT - Street Lighting (Pits) - supply & deliver |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74.03 | RW - LIGHT Street Lighting (quarry products) - supply & deliver | lm | 520 | 520 | 4.95 | 2574 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 2574 | 0 | 0
74.04 | RW - LIGHT - Street Lighting (open cut civils) - excavate, lay conduits, backfill | lm | 520 | 520 | 60.581 | 31502 | 0 | 0 | 0 | 0 | 0 | 31502 | 0 | 0 | 31502 | 0 | 0
74.05 | RW - LIGHT - Street Lighting (boring) - thrust pits, bore, install conduits, & grout annulus (if required) | lm | 335 | 335 | 90.991 | 30482 | 0 | 0 | 0 | 0 | 0 | 30482 | 0 | 0 | 30482 | 0 | 0
74.06 | RW - LIGHT - Street Lighting - poles, lanterns, cabling, terminations, Point of Supply connections etc | Item | 1 | 1 | 258000 | 258000 | 0 | 0 | 0 | 0 | 0 | 306816 | 0 | 0 | 306816 | 0 | 0
74.07 | RW - LIGHT Contamination - cart & dispose to tip | Tonne | 328 | 328 | 96.582 | 31679 | 0 | 0 | 0 | 0 | 0 | 31679 | 0 | 0 | 31679 | 0 | 0
75.* | ITS Counter |  | 0 | 0 | 0 | 50080 | 0 | 0 | 0 | 0 | 0 | 10080 | 0 | 0 | 10080 | 0 | 0
75.01 | RW - ITS - ITS Counter (CamLex Electrical Signalling & Lighting price to relocate) including relocation of traffic loops, pit, & control cabinet | Item | 1 | 1 | 50080 | 50080 | 0 | 0 | 0 | 0 | 0 | 10080 | 0 | 0 | 10080 | 0 | 0
76.* | Footpaths |  | 0 | 0 | 0 | 175769 | 0 | 0 | 0 | 0 | 0 | 89791 | 0 | 0 | 89791 | 0 | 0
76.01 | RW - FOOTPATH - Footpaths (crushed rock) - supply & deliver | sm | 1929 | 1274 | 12.601 | 16054 | 0 | 0 | 0 | 1274 | 6.381 | 8130 | 1274 | 6.381 | 8130 | 0 | 0
76.02 | RW - FOOTPATH - Footpaths (crushed rock) - place | sm | 1929 | 1274 | 20.142 | 25661 | 0 | 0 | 0 | 1274 | 9 | 11466 | 1274 | 9 | 11466 | 0 | 0
76.03 | RW - FOOTPATH - Footpaths (concrete) - supply & deliver | sm | 1929 | 1274 | 33.223 | 42326 | 0 | 0 | 0 | 1274 | 24.957 | 31795 | 1274 | 24.957 | 31795 | 0 | 0
76.04 | RW - FOOTPATH - Footpaths (concrete) - place concrete, edge forms etc | sm | 1929 | 1274 | 61.401 | 78225 | 0 | 0 | 0 | 1274 | 25 | 31850 | 1274 | 25 | 31850 | 0 | 0
76.05 | RW - FOOTPATH - Reinforcement - supply only | sm | 1929 | 1274 | 10.599 | 13503 | 0 | 0 | 0 | 1274 | 5.141 | 6550 | 1274 | 5.141 | 6550 | 0 | 0
7B25P4 | AusNet Gas -TP Relocation | EA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80.* | SHEPHERD BRIDGE STRUCTURE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81.* | SB - Access Provisions |  | 0 | 0 | 0 | 378185 | 0 | 0 | 60797 | 0 | 0 | 240638 | 0 | 0 | 301435 | 363 | -362
81.01 | SB - ACCESS - Temp Services | Item | 1 | 1 | 26650 | 26650 | 0 | 0 | 665 | 1 | 26650 | 26650 | 1 | 27315 | 27315 | 0 | 0
81.02 | SB - ACCESS - Extra Access Costs/Deck Repairs | Item | 1 | 1 | 65291 | 65291 | 0.1 | 38930 | 3893 | 0.9 | 33333.333 | 30000 | 1 | 33893 | 33893 | 0 | 0
81.03 | SB - ACCESS CIG - Widening/Transverse | Item | 1 | 1 | 286244 | 286244 | 0.233 | 241369.099 | 56239 | 0.793 | 232015.132 | 183988 | 1.026 | 234139.376 | 240227 | 363 | -362
82.* | Marine Traffic Management |  | 0 | 0 | 0 | 176156 | 0 | 0 | 15941 | 0 | 0 | 176156 | 0 | 0 | 192097 | 3044 | -3044
82.01 | SB - MARINE - Marine Traffic Management | Item | 1 | 1 | 176156 | 176156 | 0 | 0 | 15941 | 0 | 0 | 176156 | 0 | 0 | 192097 | 3044 | -3044
83.* | Hinge Joint Modifications - Demolition |  | 0 | 0 | 0 | 114186 | 0 | 0 | 0 | 0 | 0 | 114186 | 0 | 0 | 114186 | 0 | 1
83.01 | SB - HINGE - Demolition - Concrete Deck & bend back the existing reinforcement bars | cm | 13 | 13 | 7701.923 | 100125 | 0 | 0 | 0 | 0 | 0 | 100125 | 0 | 0 | 100125 | 0 | 0
83.02 | SB - HINGE - Existing steel girders - prepare girder & bend back the existing reinforcement bars | Item | 1 | 1 | 14061 | 14061 | 0 | 0 | 0 | 0 | 0 | 14061 | 0 | 0 | 14061 | 0 | 0
84.* | Hinge Joint Modifications - Steelwork |  | 0 | 0 | 0 | 138771 | 0 | 0 | 0 | 0 | 0 | 93087 | 0 | 0 | 93087 | 0 | 1
84.01 | SB - HINGE - Steel plate (new) - supply, protective coat, & deliver | Tonne | 2.14 | 2.14 | 3129.907 | 6698 | 0 | 0 | 0 | 0 | 0 | 6698 | 0 | 0 | 6698 | 0 | 0
84.02 | SB - HINGE - Structural Bolts - supply & deliver | Each | 855 | 855 | 5.325 | 4553 | 0 | 0 | 0 | 0 | 0 | 4553 | 0 | 0 | 4553 | 0 | 0
84.03 | SB - HINGE - Steel Road Plates (temporary) - supply and install | sm | 101 | 101 | 452.317 | 45684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84.04 | SB - HINGE - Steel plate (new) - install only | Each | 135 | 135 | 606.193 | 81836 | 0 | 0 | 0 | 0 | 0 | 81836 | 0 | 0 | 81836 | 0 | 0
85.* | Hinge Joint Modifications - Concrete Works |  | 0 | 0 | 0 | 68078 | 0 | 0 | 0 | 0 | 0 | 91517 | 0 | 0 | 91517 | 23439 | -23438
85.01 | SB - HINGE - Concrete - supply, deliver, & test | cm | 12.8 | 12.8 | 179.453 | 2297 | 0 | 0 | 0 | 0 | 0 | 2297 | 0 | 0 | 2297 | 0 | 0
85.02 | SB - HINGE - Reinforcement - supply & fix | Tonne | 4.2 | 4.2 | 2266.429 | 9519 | 0 | 0 | 0 | 0 | 0 | 9519 | 0 | 0 | 9519 | 0 | 0
85.03 | SB - HINGE - Formwork - supply & install | cm | 12.8 | 12.8 | 2764.766 | 35389 | 0 | 0 | 0 | 0 | 0 | 58828 | 0 | 0 | 58828 | 23439 | -23439
85.04 | SB - HINGE - Plant Openings | Shift | 2 | 2 | 3198 | 6396 | 0 | 0 | 0 | 0 | 0 | 6396 | 0 | 0 | 6396 | 0 | 0
85.05 | SB - HINGE - Place Concrete | cm | 12.8 | 12.8 | 393.828 | 5041 | 0 | 0 | 0 | 0 | 0 | 5041 | 0 | 0 | 5041 | 0 | 0
85.06 | SB - HINGE - Waterproof Membrane | sm | 90.3 | 90.3 | 104.496 | 9436 | 0 | 0 | 0 | 0 | 0 | 9436 | 0 | 0 | 9436 | 0 | 0
86.* | Strengthening Works |  | 0 | 0 | 0 | 493423 | 0 | 0 | 3600 | 0 | 0 | 666796 | 0 | 0 | 670396 | 1373 | -1373
86.01 | SB - PIER - CT Stress Bars to River Piers | Each | 16 | 16 | 1933.875 | 30942 | 0 | 0 | 0 | 1 | 72315 | 72315 | 1 | 72315 | 72315 | 1373 | -1373
86.02 | SB - CARBON - Carbon Fibre Strengthening | Item | 1 | 1 | 425728 | 425728 | 0 | 0 | 3600 | 1 | 557728 | 557728 | 1 | 561328 | 561328 | 0 | 0
86.03 | SB - ANCHORAGE - Steel Anchorage Strengthening | Item | 1 | 1 | 36753 | 36753 | 0 | 0 | 0 | 1 | 36753 | 36753 | 1 | 36753 | 36753 | 0 | 0
87.* | Rigid Frame Strengthening |  | 0 | 0 | 0 | 113797 | 0 | 0 | 0 | 0 | 0 | 113797 | 0 | 0 | 113797 | 0 | 0
87.01 | SB - RIGID FRAME - Rigid Frame Strengthening (demolition, coring, water proofing, reinforcement supply & place, & concrete supply & place) | Item | 1 | 1 | 113797 | 113797 | 0 | 0 | 0 | 1 | 113797 | 113797 | 1 | 113797 | 113797 | 0 | 0
88.* | Waterproofing to Abutments |  | 0 | 0 | 0 | 10070 | 0 | 0 | 0 | 0 | 0 | 10070 | 0 | 0 | 10070 | 0 | 0
88.01 | SB - ABUT - Abutment Waterproofing | Item | 1 | 1 | 10070 | 10070 | 0 | 0 | 0 | 1 | 10070 | 10070 | 1 | 10070 | 10070 | 0 | 0
89.* | Bridge Widening - Demolition |  | 0 | 0 | 0 | 592346 | 0 | 0 | 260308 | 0 | 0 | 431867 | 0 | 0 | 692175 | 234171 | -234171
89.01 | SB - WIDEN - Demolition - Internal Concrete Nibs | cm | 542 | 800 | 691.11 | 552888 | 160 | 239.838 | 38374 | 640 | 150 | 96000 | 800 | 167.968 | 134374 | 800 | -800
89.02 | SB - WIDEN - Demolition - Precast Slab/Bitumen/Stab Sand | sm | 1120 | 1120 | 6.659 | 7458 | 430 | 25.309 | 10883 | 550 | 18.182 | 10000 | 980 | 21.309 | 20883 | 3278 | -3278
89.03 | SB - WIDEN - Demolition - Remove Steel Railing | lm | 320 | 320 | 100 | 32000 | 160 | 32.95 | 5272 | 160 | 51.594 | 8255 | 320 | 42.272 | 13527 | 480 | -480
89.04 | SB - WIDEN - Demolition Concrete Edge Beam | LM | 320 | 320 | 0 | 0 | 0 | 0 | 69212 | 320 | 375 | 120000 | 320 | 591.288 | 189212 | 134737 | -134737
89.05 | SB - WIDEN - Demolition - Remove Curtain Wall | m | 148 | 0 | 0 | 0 | 0.5 | 32272 | 16136 | 0.5 | 29240 | 14620 | 1 | 30756 | 30756 | 1988 | -1988
89.06 | SB - WIDEN - Demolition - Waterblasting | M3 | 26 | 26 | 0 | 0 | 0 | 0 | 107507 | 26 | 4807.692 | 125000 | 26 | 8942.577 | 232507 | 90652 | -90652
89.07 | SB - WIDEN - Demolition - Drill and Supply Epoxy Starter Bars | EA | 2140 | 2140 | 0 | 0 | 0 | 0 | 12924 | 2140 | 27.099 | 57992 | 2140 | 33.138 | 70916 | 2236 | -2236
90.* | Bridge Widening - In Situ Concrete Works |  | 0 | 0 | 0 | 298764 | 0 | 0 | 192070 | 0 | 0 | 280076 | 0 | 0 | 472146 | 108371 | -108371
90.01 | SB - WIDEN - Bridge Widening (In Situ Concrete Works) - formwork (supply & place), concrete (place only), scabbling | sm | 480 | 480 | 545.219 | 261705 | 0 | 0 | 182604 | 0 | 0 | 218006 | 0 | 0 | 400610 | 98905 | -98905
90.02 | SB - WIDEN - Bridge Widening (In Situ Concrete Works) - Reinforcement & Bolts - Supply | Tonne | 480 | 29.3 | 861.843 | 25252 | 3.67 | 1953.134 | 7168 | 22.33 | 1708.912 | 38160 | 26 | 1743.385 | 45328 | 7168 | -7168
90.03 | SB - WIDEN - Bridge Widening (In Situ Concrete Works) - Concrete Supply & test | m3 | 480 | 90 | 131.189 | 11807 | 7.6 | 302.368 | 2298 | -7.6 | -3146.053 | 23910 | 0 | 0 | 26208 | 2298 | -2298
92.* | Bridge Widening - Parapets |  | 0 | 0 | 0 | 373412 | 0 | 0 | 126540 | 0 | 0 | 203766 | 0 | 0 | 330306 | 5041 | -5041
92.01 | SB - WIDEN - Parapets - supply & deliver | lm | 320 | 320 | 784.363 | 250996 | 0.577 | 219306.759 | 126540 | 0.423 | 219260.047 | 92747 | 1 | 219287 | 219287 | 5041 | -5041
92.02 | SB - WIDEN - Parapets - install | lm | 320 | 320 | 189.022 | 60487 | 0 | 0 | 0 | 320 | 189.022 | 60487 | 320 | 189.022 | 60487 | 0 | 0
92.03 | SB - WIDEN - Stich Pour - concrete supply | lm | 320 | 320 | 10.209 | 3267 | 0 | 0 | 0 | 0 | 0 | 4691 | 0 | 0 | 4691 | 0 | 0
92.04 | SB - WIDEN - Stich Pour - reinforcement - supply & fix | lm | 320 | 320 | 8.394 | 2686 | 0 | 0 | 0 | 0 | 0 | 2458 | 0 | 0 | 2458 | 0 | 0
92.05 | SB - WIDEN - Stich Pour - place concrete | lm | 320 | 320 | 135.572 | 43383 | 0 | 0 | 0 | 0 | 0 | 43383 | 0 | 0 | 43383 | 0 | 0
92.06 | SB - WIDEN - Painting | lm | 320 | 320 | 39.353 | 12593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93.* | Bridge Widening - Steel Railing |  | 0 | 0 | 0 | 208446 | 0 | 0 | 0 | 0 | 0 | 255000 | 0 | 0 | 255000 | 0 | 0
93.01 | SB - WIDEN - Bridge Widening - Steel Railing - Supply & Install | lm | 320 | 320 | 651.394 | 208446 | 0 | 0 | 0 | 0 | 0 | 255000 | 0 | 0 | 255000 | 0 | 0
94.* | Bridge Widening - Expansion Joint |  | 0 | 0 | 0 | 326287 | 0 | 0 | 0 | 0 | 0 | 281385 | 0 | 0 | 281385 | -44902 | 44902
94.01 | SB -EJ - Bridge Widening - Expansion Joint (Existing) - Demolition | Item | 1 | 1 | 44902 | 44902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44902 | 44902
94.02 | SB - EJ - Bridge Widening - Expansion Joint (New) - supply & install | lm | 204 | 204 | 1379.338 | 281385 | 0 | 0 | 0 | 0 | 0 | 281385 | 0 | 0 | 281385 | 0 | 0
95.* | Schedule 3A - Shepherds Bridge over-height detection system |  | 0 | 0 | 0 | 152328 | 0 | 0 | 0 | 0 | 0 | 99380 | 0 | 0 | 99380 | 0 | 1
95.01 | RW - OHD - New VMS sign including cabling, terminations etc | Item | 1 | 1 | 87894 | 87894 | 0 | 0 | 0 | 0 | 0 | 87894 | 0 | 0 | 87894 | 0 | 0
95.02 | RW - OHD - Cantilever pole - supply & install | Item | 1 | 1 | 52948 | 52948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95.03 | RW - OHD - Civils eg cabinet foundation, pole foundation, & minor conduiting | Item | 1 | 1 | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | 7000 | 0 | 0
95.04 | RW - OHD - Contamination - disposal of Cat "C" | Tonne | 677 | 677 | 6.626 | 4486 | 0 | 0 | 0 | 0 | 0 | 4486 | 0 | 0 | 4486 | 0 | 0
P1 | Provisional - Daywork | Item | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P3 | Provisional - Testing of Earthwork & Pavement Materials | Item | 1 | 1 | 0 | 0 | 0 | 0 | 3119 | 0 | 0 | 0 | 0 | 0 | 3119 | 3119 | -3119
P4 | Utilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P4.01 | Provisional - Utlities | Item | 1 | 1 | 81870 | 81870 | 0.791 | 584006.321 | 461949 | 0.21 | 1458028.571 | 306186 | 1.001 | 767367.632 | 768135 | 0 | 0
P4.02 | Provisional - Utilities - Water Main Footpath |  | 1 | 1 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 44089 | 0 | 0 | 44889 | 0 | 0
P4.03 | Provisional Utilities - FH HV Works | LS | 0 | 0 | 0 | 0 | 0 | 0 | 14328 | 0 | 0 | 0 | 0 | 0 | 14328 | 1016 | -1016
P5 | Provisional - Concrete Crack Repair | Item | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P6 | Provisional - Asphalt Pavement Repair | sm | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P7 | Provisional - Asphalt Regulation | Tonne | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
{_Misallocation} | Misallocations |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ungrouped |  |  | 0 | 0 | 0 | 17313604 | 0 | 0 | 4134668 | 0 | 0 | 14633894 | 0 | 0 | 18768562 | 194338 | -194337