## ITP-007
|  |  | Inspection and Test Plan - Installation of Fencing | [7 empty] | Document # M3RNAR-FUL-QAC-ITP-0007
[11 empty] | Revision : 2 | Date : 08/09/25
Client: |  | APAM |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Northern Access Road |  | Installation of Fencing |  | Name: Kamal Nour Hussain |  | Name: |  |  | Name: Damon Bromwich
Job No: |  | 7436000 |  | Specifications: Section 707 as outlined in M3R-BECA-001-SPC-00001[C04]
|  |  |  | Structure / Component: Fencing |  | Signed : | #VALUE! | Signed : |  |  | Signed :
|  |  |  | Location: NAR & Sunbury Road |  | Date : 08/09/2025 |  | Date : |  |  | Date :
Lot No: |  |  | Lot Title: |  |  |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used. | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified . | EMP, Site induction, | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
1.3 | Exacavation Permit Issued |  | Prior to commencing work | Current Excavation Permit (GPP) signed and specific for the area where works will be executed. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
1.4 | Traffic Management (When required) |  | Prior to Commencing Work | Approved Traffic Management Plans and Permits: TMP and MoA. | TMP, MoA | Document review & Site inspection | Approved TMP & MOA | AP | Site Engineer | N/A |  | N/A
1.5 | Material Conformance |  | Prior to commencing | The Contractor shall submit for review by the Superintendent prior to the proposed use of fencing materials, gates and connections to existing fencing, a signed certificate including relevant test reports demonstrating the compliance of the materials and components required for the construction of each type of fencing, gates and connections to existing fencing, comply with the requirements of this specifications. | 707.03 | Document Review | Certificate of Conformance Relevant Standard Drawings | AP | Site Engineer / Project Engineer | N/A |  | N/A
2 | Construction
2.1 | Site preparation |  | Each Lot | All logs, stumps, saplings and undergrowth within 1 m of the fence line and all tress which will interfere with the proper construction of the fence shall be removed and disposed of. Any high points which interfere with the placing of wire or wire netting shall be cut down to provide the clearance shown on the detailed drawings, and any low spots shall be filled with surplus earth from holes and trimming | 707.04 | Site Inspection | Photos | IP | Site Engineer | N/A |  | N/A
2.2 | Fencing Set Out |  | Each Lot | Surveyor to set out fenceline as per drawings and set out posts as per drawings if required. Cadastral Boundary Surveyor when in related to property boundarys, Right of Ways, and Titles. | Drawings | Site Inspection | Drawings/ Survey Set Out | IP | Site Engineer / Surveyor | N/A |  | N/A
2.3 | Install Fence |  | Each Lot | Install fence as per VicRoads Sec 707.04 | 707.04 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3 | Conformance
3.1 | Asbuilt Survey |  | After installation | Construction Tolerances: the verticle tolerance on the height of the fencing shall be ± 20mm from the design line. ( b ) the longtitudinal line tolerance for the fencing shall be ± 20mm in plan view; and ( c ) the tolerance on the verticality of fencing shall be 1 in 50. | 707.08 Asbuilts Survey Report | Document Review/ Site Inspection | Asbuilt Survey | SCP | Site Engineer/ Surveyor / Survey Manager |  |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent