## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | M3RNAR-FUL-QAC-ITP-006 - Class 3 Crushed Rock Subbase | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-006 - Class 3 Crushed Rock Subbase Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — Using the correct and complete set of drawings
label | — All drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Material Mix Design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
label | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.3 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.3 Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | REFERENCE DOCUMENTS: . Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Layer Thickness
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.5 Proof Rolling
label | FREQUENCY: Proof Roll each layer
label | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP/ WP
label | RESPONSIBILITY: Site Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Testing Requirements
checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
label | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | AP
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
checkpoint | 3.2 Compaction Testing (Scale B for NAR)
label | FREQUENCY: Every Lot
label | ○ Every second lot (reduced frequency)
label | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 97%, using Modified compaction effort.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.3 Compaction Testing (Scale A for Sunbury Rd)
label | FREQUENCY: Every Lot
label | ○ Every second lot (reduced frequency)
label | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.4 Compaction Testing (Small Lots)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area.
label | ○ Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.5 Material Grading - Post Compaction (Class 2 & 3 Only)
label | FREQUENCY: First Lot Only
label | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
label | ○ Class 4 - N/A
label | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
label | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.6 Plasticity Index - Post Compaction (Class 2 & 3 Only)
label | FREQUENCY: First Lot Only
label | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
label | ○ Class 4 - N/A
label | ○ Class 3 - 0 to 10
label | ○ Class 2 - 0 to 6
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.7 Survey Conformance (Scale B for NAR)
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
label | ○ Surface level tolerances:
label | — Range x = +8, -16mm
label | — Max S = 15 mm
label | — 40 measurements per lot (Minimum)
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: This ITP signed off; Survey Report
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 3.8 Survey Conformance (Scale A for Sunbury Rd)
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
label | ○ Surface level tolerances:
label | — Range x = +6, -10mm
label | — Max S = 10 mm
label | — 80 measurements per lot (Minimum)
label | REFERENCE DOCUMENTS: Project Specifications Cl.304
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: This ITP signed off; Survey Report
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | M3RNAR-FUL-QAC-ITP-007 - Fencing | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-007 - Fencing Rev2
section | Preliminary Works
checkpoint | 1.1 Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used.
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified .
label | REFERENCE DOCUMENTS: EMP, Site induction,
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.3 Exacavation Permit Issued
label | FREQUENCY: Prior to commencing work
label | ACCEPTANCE CRITERIA: Current Excavation Permit (GPP) signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Excavation Permit #
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Traffic Management (When required)
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Approved Traffic Management Plans and Permits: TMP and MoA.
label | REFERENCE DOCUMENTS: TMP, MoA
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Approved TMP & MOA
label | AP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.5 Material Conformance
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: The Contractor shall submit for review by the Superintendent prior to the proposed use of fencing materials, gates and connections to existing fencing, a signed certificate including relevant test reports demonstrating the compliance of the materials and components required for the construction of each type of fencing, gates and connections to existing fencing, comply with the requirements of this specifications.
label | REFERENCE DOCUMENTS: 707.03
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Certificate of Conformance, Relevant Standard Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Project Engineer
textbox | Date Completed:
section | Construction
checkpoint | 2.1 Site preparation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All logs, stumps, saplings and undergrowth within 1 m of the fence line and all tress which will interfere with the proper construction of the fence shall be removed and disposed of. Any high points which interfere with the placing of wire or wire netting shall be cut down to provide the clearance shown on the detailed drawings, and any low spots shall be filled with surplus earth from holes and trimming
label | REFERENCE DOCUMENTS: 707.04
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Photos
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Fencing Set Out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surveyor to set out fenceline as per drawings and set out posts as per drawings if required.
label | ○ Cadastral Boundary Surveyor when in related to property boundarys, Right of Ways, and Titles.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Drawings/ Survey Set Out
label | IP
label | RESPONSIBILITY: Site Engineer / Surveyor
textbox | Date Completed:
checkpoint | 2.3 Install Fence
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Install fence as per VicRoads Sec 707.04
label | REFERENCE DOCUMENTS: 707.04
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Conformance
checkpoint | 3.1 Asbuilt Survey
label | FREQUENCY: After installation
label | ACCEPTANCE CRITERIA: Construction Tolerances:
label | ○ the verticle tolerance on the height of the fencing shall be ± 20mm from the design line.
label | ( b ) the longtitudinal line tolerance for the fencing shall be ± 20mm in plan view; and
label | ( c ) the tolerance on the verticality of fencing shall be 1 in 50.
label | REFERENCE DOCUMENTS: 707.08 Asbuilts Survey Report
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Asbuilt Survey
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor / Survey Manager
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | M3RNAR-FUL-QAC-ITP-008 - Stormwater Drainage | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-008 - Stormwater Drainage Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — All drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Precast Materials acceptance
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
label | REFERENCE DOCUMENTS: Cl. 701.05e
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Precast Pipe & Culvert Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
label | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058
label | REFERENCE DOCUMENTS: Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.5 Precast Drainage Pit Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
label | REFERENCE DOCUMENTS: Cl.610, Cl. 705.04, AS5100
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.6 Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
label | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.7 Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
label | REFERENCE DOCUMENTS: 701.09(d), 701.091
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.8 Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Set out drainage
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Excacation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.151, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.4 Excacation (pits)
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
label | REFERENCE DOCUMENTS: 705.05b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: 701.20, 701.20a
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.7 Place pipes & precast pits
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.8 Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.9 Sealing - for joining culvert sections and pipe penetrations in pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
label | REFERENCE DOCUMENTS: 610.32, 701.17c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.10 Survey of laid pipe or pit
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Survey Conformance Point
label | RECORD OF CONFORMITY: ITP Signed
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 2.11 Haunching & compaction of bedding material
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
label | ○ Loose layer thickness <=150mm
label | ○ Compacted to refusal using hand held mechanical equipment.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.16, 701.20
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.12 Place & compact backfill material over pipes
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.19, 701.20
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.13 Place & compact backfill material around pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
label | ○ Compacted to refusal using hand held mechanical equipment.
label | REFERENCE DOCUMENTS: 705.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.14 Backfilling with cement stabilised sand
label | FREQUENCY: Each culvert
label | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | REFERENCE DOCUMENTS: Cl. 701.19(a)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Superintendent approval, ITP signed
label | AP
label | RESPONSIBILITY: Project Engineer / Superintendent
textbox | Date Completed:
checkpoint | 2.15 Install step irons
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: For pits > 1m deep.
label | REFERENCE DOCUMENTS: 705.12
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
label | REFERENCE DOCUMENTS: Standard drawing SD 1002
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.17 Place pit covers
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
label | REFERENCE DOCUMENTS: 705.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.18 Repairs to damaged pipes and box culverts
label | FREQUENCY: Each damaged pipe or culvert
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31a
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Testing Requirements
checkpoint | 3.1 Compaction and moisture content of backfill & bedding material
label | FREQUENCY: at least 20% of all lots
label | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 97% using standard compactive effort.
label | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: 701.20a, 701.20b
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.2 CCTV inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: 701.3
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: CCTV Report
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 Flushing of pipes
label | FREQUENCY: Each line
label | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
label | REFERENCE DOCUMENTS: 701.28
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | M3RNAR-FUL-QAC-ITP-009 - Line Marking | itp |  |  |  |  | M3RNAR-FUL-QAC-ITP-009 - Line Marking Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — All drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Position of Markings
label | FREQUENCY: Prior to application
label | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | ○ Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
label | REFERENCE DOCUMENTS: Traffic Engineering Manual Volume 2 Drawings
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Materials
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
label | REFERENCE DOCUMENTS: 712.A04(c), 721.A05(c)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 General Markings
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
label | ○ All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
label | REFERENCE DOCUMENTS: 712.D01(c), 721.D01
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 3.1 Tolerances
label | FREQUENCY: Each marking
label | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
label | (i) Distance between centreline of marking and set out marks <30mm
label | (ii) Width of completed paint markings <15mm
label | (iii) Length of completed stripes and blocks 0 to +10% of specified length
label | REFERENCE DOCUMENTS: Table 712.A101, 721.A101
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.2 As-Built
label | FREQUENCY: Post Completion
label | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings, Survey Records
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed off
label | SCP
label | RESPONSIBILITY: Project Engineer /Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: