## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b6415681-638d-4993-836a-5a429a4eb398 | checklist | ITP-001 - Localised Expansion Joint Repair Rev0 | itp | ITP-001 - Localised Expansion Joint Repair
834a388f-c77b-4a9d-b59e-87f2b7098a98 | section | 1 – EXPANSION JOINT REPAIR
06847e1e-9992-49a4-8f71-a72cd45c1545 | checkpoint | 1.1 - Preparation & Admin; Safe Work method statements
45eb6338-43cb-5286-8a6f-b6689efb7dd9 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: HP: Documents listed below shall be provided at least 14 days prior to the commencement of works. No works shall commence until Fulton Hogan has approved the submitted documents.
71b4b530-3f70-5ae9-8848-10862db075d7 | note | ○ The Contractor shall provide FH with an exhaustive list ofpersonnel that will be undertaking or facilitating the works at least 7 days prior to any such person being on site.
723b266f-5114-50ef-836d-62118db68aba | note | ○ Where additional personnel are required to undertake the works, the Contractor shall provide FH with additional personnel names and employers to allow for auditing.
08a08c57-50db-5617-a82c-903c65a575bf | note | ○ The Contractor shall submit the SWMS, and contract vehicle and mobile Pre-acceptance checklist.
64f38002-f885-5760-9468-510d725f01c6 | note | ACCEPTANCE CRITERIA: Documents submitted and Approved
c3f1dc48-ad60-569a-a8c3-1573d70a5d4d | note | ○ Crew Signed SWMS
3af378f3-750e-5389-b647-7a341df82e3c | note | ○ Signed ITP
aa208c36-d6d2-5f8d-86e8-42194f743f86 | note | VERIFYING DOCUMENT: SWMS, Vehicle and Mobile Pre-Acceptance Check List, Induction ID VicRoads 177, VicRoads 160, VicRoads 168
87b29dd9-3c63-5279-a697-4681455d70c8 | note | KEY: HP MS R
d9e613de-195f-5faf-bec6-d24d47ad5530 | note | REP: PM PE SE S
af1c9938-627f-5ca6-9430-0eaaf5b8b33d | date | Date Completed:
136a5544-6729-47d1-b3ee-9c133dd3f06a | signoff | AUTHORITY HOLDPOINT
16f90aeb-d773-42c4-a7ff-17d1189ebab2 | checkpoint | 1.2 - Quality Management (ITP'S)
54c684c2-db34-5618-b3fc-d5dd61fc8f22 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: HP: The Contractor shall submit proposed ITP’s to FH at least 14 days prior to their use.
dd03b081-ae84-50c3-855f-bf6a5aa991f1 | note | ○ The Contractor shall remain responsible for all Quality Assurance requirements as per VicRoads Section 160, inclusive of the submission of ITPs and completion of documentation.
4c6b6f79-60b9-5f6e-b0ca-e31b32a521c3 | note | ○ ITP includes all the Hold points required for each stage of the project.
829f0005-f56c-5ded-968c-542675fe6272 | note | ACCEPTANCE CRITERIA: ITPs submitted and approved
4d71fc14-6a0d-50cd-a352-57599ca4ba58 | note | VERIFYING DOCUMENT: Contract Conditions and Specifications
26cdbab0-0b07-5b22-a3c7-e5d22877c869 | note | KEY: HP R
09f6d4c1-99a6-5adf-9782-bdebd11d3ef9 | note | REP: PM PE SE S
9806e795-7109-554f-9baa-1755a2d61ad3 | date | Date Completed:
c926d7fa-54b2-4c77-8a65-1c908043d691 | signoff | AUTHORITY HOLDPOINT
ce00b9c5-5540-44a3-83cc-723b9dea71dd | checkpoint | 1.3 - Surface Preparation – Remove Bridge Joint Area
9e1874bc-a6b0-50fc-a927-85f3cf3fddd5 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: Silspec 900 PNS must be applied to clean, dry and sound surfaces for effective bond.
446ea660-883c-54fd-b887-e23edac1a51d | note | ○ Existing nosing material to be sawcut to depth of 40mm.
cb683499-58ec-5c44-bce6-2368e2d81b9b | note | ○ All unsound material must be removed by handheld jack hammer or similar means.
51d89617-d6d0-5304-b1b8-5ac6aca84896 | note | ○ All loose material must be removed by brushing, vacuuming or blowing.
b3e4122e-b41b-5aef-8ac6-2d92d28a310c | note | ACCEPTANCE CRITERIA: Depth of cutting existing nosing material – 40mm
10851667-9cfb-58bc-80fd-144b25e8ab23 | note | ○ Signed ITP
730aa7fc-c9fb-57b5-864f-725701d61f97 | note | VERIFYING DOCUMENT: VicRoads 660.04, VicRoads 689.08 Manufacture Specifications
ee00bb23-ac10-5fe7-b869-e1867ad34fe9 | note | KEY: V
1fd5f267-b4ef-5f68-8ce0-621a8779f1d0 | note | REP: PM SE S
aea3d8d7-57f3-50f0-91f9-d4ba7d980c0c | date | Date Completed:
60835f0f-482d-42f4-89c6-2e4a7a328210 | checkpoint | 1.4 - Surface Preparation – Preparing the Bridge Joint Area
6ef8795f-9842-529c-a3fc-eb1f57ec73c2 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: Grit blast the blockout so that all residue from the asphalt, and any other “old” or loose material is removed.
84c44e83-f901-525e-9fb1-23d10db1a4dc | note | ○ Grit blast any exposed reinforcement to provide a clean surface.
5ecb61d5-14f1-5e0f-8b35-7b03f88db554 | note | ○ After grit blasting thoroughly sweep area and blow out the blockout so that there are no loose particles or dust left in the blockout that could prevent adhesion of the Silspec material.
0a67d2ad-0b49-5d10-85b7-8c4bf147c451 | note | ○ Whilst the Silspec can tolerate some moisture it is preferable to have the blockout as dry as possible – blow dry the surface to remove moisture.
f71c6a19-635c-56a0-bab0-5381308d6768 | note | ACCEPTANCE CRITERIA: Signed ITP
6e8f0623-fb4f-59c4-b012-c14431fa6a1b | note | VERIFYING DOCUMENT: Megapoxy P1 Manufacture Specifications
422cb499-4497-559a-ba3e-9aab7c1627e2 | note | KEY: V
c352ef01-be23-5aaf-8752-a7960450ff68 | note | REP: PM SE S
8217975f-ccee-533e-b429-693de28024ae | date | Date Completed:
9564cbae-a1e0-4924-8073-f8a8a88475f6 | checkpoint | 1.5 - Install Foam (Formwork) to Create Joint
86b3e90d-9821-5dc5-b21b-5e5f15591b0b | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: Place formwork in the middle of the blockout to form the expansion joint gap to the desired expansion joint gap width.
fe2ec3ad-3e36-5abe-a260-52cf3938a734 | note | ○ The upper surfaces of the joint shall be parallel with the longitudinal grade and cross- fall of the completed road or footpath surface.
9f3c30ee-2601-575f-8f7c-187cfbbc465e | note | ACCEPTANCE CRITERIA: Signed ITP
4da97f6b-c8c7-5a3e-8410-76c2b935457d | note | VERIFYING DOCUMENT: VicRoads 660.04 Manufacture Specifications
7b018c71-b85f-5de1-b3f1-33f1fdfd4bf3 | note | KEY: V
ddef143c-2e12-555d-9683-c4590a205867 | note | REP: PM SE S
acce6436-8536-5f3a-ae13-36c05fcb572d | date | Date Completed:
3341b62e-8bac-426d-a8b1-80121414005e | checkpoint | 1.6 - Adhesion of Exposed Reinforcement to Silspec & Protection from Corrosion
5ba419bd-6e8c-56b6-bb49-3e82451aa636 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: If Reinforcement is exposed after jack hammering, the following procedure will be carried out,
01958d6f-56e4-5d09-955f-938b3e6387e7 | note | ○ MEGAPOXY P1 will be used for protection of reinforcing steel.
a97fc49c-fd0c-537f-b766-93bde5b8bfd9 | note | ○ Part “A” and Part “B” are thoroughly mixed before use with correct mixing ratio (1:1)
c816c56c-27a0-5260-97fe-08e127ad91a3 | note | ○ Applied to exposed Reinforcement using a paint brush before placing Silpsec
42e563d2-0401-52de-b233-6510b7480f0e | note | ACCEPTANCE CRITERIA: Inspection by Supervisor of prepared surface
7622e0ef-2455-595c-8b31-b08a2a97e639 | note | VERIFYING DOCUMENT: Megapoxy P1 TDS
478ed628-96f6-5ac5-b72f-5efd730787aa | note | KEY: V
cbfa3b10-8f30-5e26-b015-62a8a5ce02b0 | note | REP: PM SE S
4249d20f-b2dd-5a01-b522-5f9895d6d1ab | date | Date Completed:
7922ad15-d900-4c48-ac20-28cc1a4155a4 | checkpoint | 1.7 - Mix and Install Silspec
9a97a999-b718-51ab-a955-acbff8516a6c | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: The expansion joint shall be installed in accordance with the supplier’s recommended procedure.
3972c049-6e4d-53ce-b7ea-e6bacf8e1b51 | note | — Silspec 900 PNS must be thoroughly combined prior to use in a separate container.
6da8042d-1281-50c1-8449-59da8e8ac237 | note | — Mechanical mixing, using a heavy-duty low speed drill motor with paint-type paddle stirrers is recommended. Mixing time should not be less than 3 minutes.
eea99599-e537-5ea1-86e0-3ece275733f8 | note | — The blended batch must be applied to the surface in 5-10 min. Once spread out, working time will be approximately 1/2 hour.
f329b8de-e421-5a9f-a09a-d9d66945c875 | note | — In cold weather, it is recommended that liquid and aggregate to be stored in a heated area until just prior to use.
7dbc837c-d478-5faa-859d-f02adab993d5 | note | Installation Tolerances
3ce32a3c-1de3-5a19-ab51-21e9cd436d40 | note | ○ The following tolerances shall apply to joint installation:
0e26c59a-3ac8-5df8-a281-00db6cf67921 | note | — joint gap  3 mm
1c825284-7a79-5030-98f8-3cf72ff14129 | note | — deviation from plan alignment 5 mm maximum over the total length of the joint
4dcfcee6-f3d4-578a-b265-e7fcb965c553 | note | — the top surface of the joint shall be level with the adjacent road surface with a tolerance of 0 to 2 mm when measured with a 2.5 m straight edge at 90º to the joint.
d4b673f8-743d-519d-9400-4164a112c4ee | note | ○ HP: After concreting and prior to installation of the joint seal, the vertical face of the concrete under the full length of the joint shall be inspected for the presence of voids and other imperfections. If the joint or any of its component parts is damaged during construction, the Contractor shall repair the damage to the satisfaction of the Superintendent
79e03fa2-b417-5f42-844e-8303aead1f09 | note | ACCEPTANCE CRITERIA: Joint gap tolerance ± 3 mm
06aae5f0-2653-51cf-93c5-e814cb080532 | note | ○ 150mm Minimum width of XJS Nosing when asphalt adjacent
3badbc70-558c-56aa-8aee-cdceba4afab0 | note | ○ 100mm Minimum width of XJS Nosing when concrete adjacent
e7abf2e0-ecd7-5bc7-8e65-91726b0775fe | note | ○ Signed ITP
29babec7-b401-5c89-b5b6-7c765fa87aaf | note | VERIFYING DOCUMENT: VicRoads 660.04, VicRoads 660.05 Manufacture Specifications
42b3f765-34ed-5409-81e0-60812df56d38 | note | KEY: HP V
595dbf26-750b-59b4-9702-845f6768d0fe | note | REP: PM SE S
2422bc20-bfa6-5ff0-ac72-40b272209ae7 | date | Date Completed:
cfc4be1a-98d9-4974-90ab-cc626e12add8 | signoff | AUTHORITY HOLDPOINT
52794ba5-1eba-421c-87ab-bfe670202974 | checkpoint | 1.8 - Curing Silspec
c51d155e-3d23-5fbb-9fd7-632d3429ccd5 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: Indirect heating system to be installed as per the attached drawing.
bd93bf12-4630-5973-8fe2-650054600063 | note | ○ Heating to be monitored and maintained during entire repair process (as practicable).
35111690-42c2-5a09-a351-6e46958c2573 | note | ○ The arrangement shouldn’t be removed until curing period of grout is achieved (As practical within the time frame)
c8ab830e-561d-54e1-9a3b-7886b02f68eb | note | ○ Higher temperatures will shorten the cure while lower temperatures will lengthen the cure time.
d9f4d79a-6c19-5d7c-bf1a-4cff0c6fd3fc | note | ○ Temperature monitored using a Thermometer.
e3a07d75-cd82-510b-9c40-a42519f64bfb | note | ACCEPTANCE CRITERIA: 20°C for 3-4 hours (as practicable)
29189d14-4cb0-5f3c-ab00-2c8b5fc0b4bd | note | ○ Signed ITP
85163f86-21c3-548f-aa5e-72ef6e34f738 | note | VERIFYING DOCUMENT: Contract Conditions and Specifications, Manufacture Specifications
50661570-8772-59d8-8244-84b31f4d60e5 | note | KEY: V
2ac56d6d-066a-50f3-a4ec-5c3d2fa49741 | note | REP: PM SE S
f16db5b9-c389-5875-903c-a7bdcbd24904 | date | Date Completed:
c9b0966c-7736-47eb-8eed-25a74bea9b15 | checkpoint | 1.9 - Chamfer Requirements
e975b2ef-6207-5b7d-919e-10521e2a1e39 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: The edges of the gap should be ground (using an angle grinder) to form a 5mm x 5mm chamfer.
1d344656-4d3a-5ba0-b97f-38d71ac3e356 | note | ACCEPTANCE CRITERIA: Signed ITP
538282c0-3b74-522e-9b1e-df1cb8bb1892 | note | VERIFYING DOCUMENT: Manufacture Specifications
e2dc30cb-cdb8-52c7-906e-b2273dfadf8a | note | KEY: V
aafffc14-a5c1-5663-98fc-55a1d6cca776 | note | REP: PM SE S
71edda46-9851-5fa0-ad0f-c0012245e213 | date | Date Completed:
bcb8035e-35a4-4fd2-905e-800a61de3ca0 | checkpoint | 1.10 - Primer Application
0e11856f-6d7c-5588-aeb5-a834bf5e4c04 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: Paint the Dow Corning P5200 primer on the sides of the gap using a small paint brush.
2cfdf4ab-d678-5ccc-a1f8-98e0230aab7f | note | ○ The primer will only take a few minutes to dry.
00c71476-5309-59d3-ab10-b95d7d6c20e7 | note | ACCEPTANCE CRITERIA: Signed ITP
7129062a-f5b8-5bae-ac4f-f4a162938b06 | note | VERIFYING DOCUMENT: Manufacture Specifications
2ec0474c-abcf-5c7b-82d1-8b2dcea161a5 | note | KEY: V
50540431-ff58-5fde-a83f-7dd53b6fefd7 | note | REP: PM SE S
793ca9b9-b5cb-51f5-a1c9-6083e367f96a | date | Date Completed:
e19ff54b-0122-47a4-a010-df424726496d | checkpoint | 1.11 - Install Backing Rod and Silicone Seal (Joint Seal)
afed0224-347a-53e5-806a-364d868229c2 | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: The joint surfaces must be thoroughly dry and clean.
3a09753a-6ba5-51b6-825d-dd118eb3b4c1 | note | ○ Remove all laitance, curing compounds, form release agents, loose materials and any contaminating foreign matter from joint faces.
574664e5-b2c7-5ae6-9b0a-d08fc3f367a7 | note | ○ Depending on the joint configuration, place with pressure fit, backing rod into the joint to support internal back of the sealant.
8f95d095-155b-574b-a7cd-ac76beacde9f | note | ○ Road seal is applied from 600 ml sausages or bulk containers into the joints using a suitablesealant gun.
f0a02883-c272-5686-93a7-b4af3422243d | note | ○ The Road seal does not require any tooling and the road can be opened to traffic soon after pouring and pack up.
e16920aa-06c0-534a-8e49-f564df5b6aae | note | ACCEPTANCE CRITERIA: Backing rod to be pressure fit 25mm below the surface of joint.
d47cba60-6dda-585f-8bcb-7757247c3bdd | note | ○ Silicone Seal minimum 12 mm below pavement surface.
271315ce-35aa-5924-bab7-ca3de166ce30 | note | ○ Signed ITP
ff44a3e1-f815-5e4f-84e1-5b701ebbaa4e | note | VERIFYING DOCUMENT: VicRoads 660.04, VicRoads 660.05 Manufacture Specifications
4fdddb7a-4d1e-505d-9e3b-64eea1f066cd | note | KEY: V
7de6ea0c-dbc1-5849-a03b-9316f831a172 | note | REP: PM SE S
3f050140-a0b2-5fac-9dd7-839f54f37a22 | date | Date Completed:
2d23f8c1-b523-4755-a12d-11757b6edac6 | checkpoint | 1.12 - Sign off Upon Completion
b35b1602-2439-566f-90fd-d348f209d25b | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: HP: Client Representative (FH) to sign off upon completion of works.
02469666-fb79-53fb-b144-d990db3438e8 | note | ACCEPTANCE CRITERIA: Signed ITP
e6d961c6-889b-51f8-a948-9a8e8b1b9ac8 | note | VERIFYING DOCUMENT: Contract Conditions and Specifications
128ff375-1793-517b-a11c-d2461c2134fc | note | KEY: HP
4cc1b1de-cc50-5eed-8468-49292f6f4638 | note | REP: PM SE S
94618092-ad3b-5a12-a22b-e9071f4dddc2 | date | Date Completed:
5a865954-dfb9-4e1a-925e-0fb951f904d8 | signoff | AUTHORITY HOLDPOINT
9706a0f0-0258-4633-a8ba-9163c98b23ab | section | 2 - EXPANSION JOINT REPAIR (PROVISIONAL ITEM)
7a500f95-b478-4846-ac8d-c57ccc9d6939 | checkpoint | 2.1 - Concrete Spalling works under the Expansion Joint (If present & Method agreed by the Client) Mix and install
f637d59c-e853-5eaf-bebb-084bfa9dcbde | note | INSPECTION POINT: QUALITY CONTROL ACTIVITY: The joint surfaces must be thoroughly dry and clean. Be sure repair area is not less than 5 mm deep.
b282a8a4-45ea-5955-a333-e41d8dc1be74 | note | ○ Remove all laitance, curing compounds, form release agents, loose materials and any contaminating foreign matter from joint faces.
5d9cc011-64b8-5059-a20e-38e31f8d9eb7 | note | ○ Mechanically mix in an appropriately sized mortar mixer. Wet down all tools and mixer to be used.
649db27d-84d4-53d4-9cdf-0a39bcf2bbb5 | note | ○ Start with 2.1 liters of water added to the mixing vessel. Add 1 bag of SikaQuick®- 2500 while continuing to mix. Add up to another 0.3 liters of water to achieve desired consistency. Do not over water.
a6d714a3-abb5-5bee-bf40-b6c1cece1ade | note | ○ Overall Water used for mixing should be within 2.1 – 2.4 Liters per 20 Kg Bag
22d52ba5-95ba-5e54-aa4f-7eebe27fbf2e | note | ○ The prepared mortar must be scrubbed into the substrate. Be sure to fill all pores and voids. force materials against the edge of the repair, working towards the center. After filling the repair, screed of excess.
d5f2c3f7-e9af-518f-b201-87cb1660667f | note | ○ Allow concrete to set to desired stiffness, then finish.
10e539e3-bc31-5aad-bed1-b3433ae4f7cc | note | ○ Open to Foot traffic in 45 Mins. (at 23 degrees Celsius)
4788ea76-c369-50e9-9a42-058fd80b07ce | note | ○ Open to Vehicle Traffic in 1 Hour (at 23 degree Celsius)
68856234-ce0c-5a69-b1b5-8ebd78c1e16e | note | ACCEPTANCE CRITERIA: Mortar Thickness is Min 5mm and Maximum 150mm.
52a307f5-ddf8-5ede-ab31-3395b84fbc51 | note | ○ Mixing, placing and finishing should not exceed 15 Minutes Maximum.
b9838242-b196-5b14-a289-7e7070259fcc | note | ○ Curing Temperature 23°C for 30 mins – 1 hour (as practicable)
be5486e1-fd8f-5d94-8c33-dfbdefe34e72 | note | ○ Manufacturer Specification.
dd7be2e7-58a0-5d99-8812-f2da3bfef4f7 | note | ○ Inspection by Supervisor of prepared surface
ee644305-6249-5d7f-b59a-545ce1c8e0a1 | note | ○ Signed ITP
8e527e67-90dd-5f6d-93f7-f45a0ca8695f | note | VERIFYING DOCUMENT: VicRoads 660.04 Manufacture Specifications
56137589-0780-5018-bbec-9d6c57193aca | note | KEY: V
08c51ceb-5587-51e6-a63e-6de9740f693e | note | REP: PM SE S
fde1a657-8563-5f94-a18e-2a98dd4487de | date | Date Completed:
c37410f4-857b-49a7-9947-547c693cbe51 | checkpoint | Final Inspection
803d3ca7-f378-513b-950d-4171e5862006 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a5e9eae1-28b3-530f-bdd2-a4411c8e473f | textbox | Print Name:
18d09ce1-cb0f-5d7d-8c31-dac2ce9bf88c | textbox | Position:
d6897e4c-041d-562e-b968-67bfc02c74e5 | date | Date:
249f5dda-68e7-480b-bf7b-3cfaf722430a | checklist | ITP-010 - Preliminary & Civil Works - Tallarook Rev1 | itp | ITP-010 - Preliminary & Civil Works - Tallarook
ca8370eb-42ea-4dab-81ca-b274711eb60d | section | 1 - Preliminary Works
1a46a150-ef80-485b-be46-3970ff3a91a0 | checkpoint | 1.1 - Submission of Project Management Documentation
d4dedb5e-67e6-5429-b231-bb4ce46b16a4 | note | FREQUENCY: 2 weeks prior to commencement
96266570-b151-516e-baa2-cb214eb6a4f5 | note | ACCEPTANCE CRITERIA: Receival of all relevant documentation including HSMP/OHS/QMP/TMPEMP/Procedures
bda14116-cdf3-51f7-86df-a4e56d4295f6 | note | REFERENCE DOCUMENTS: Cl 160.A4 Cl 176.A3
ed11191d-0fc4-56d0-aeae-1d84a5134012 | note | INSPECTION/TEST METHOD: ITP Signed
5baa7464-777a-5528-917c-f0cea51d55df | note | RECORD OF CONFORMITY: Completed ITP
cfa9fff4-c354-5064-b675-80eba9ec4809 | note | HP
6b9d3a6f-c429-5250-9ee6-be078854c786 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
9dc54742-5f08-5dad-ac70-592a41b4a34a | date | Date Completed:
7b87f5da-1eaf-4919-8964-43be2ee7077a | signoff | AUTHORITY HOLDPOINT
1eb50727-ed7c-4b2a-86ef-0264f425a62c | checkpoint | 1.2 - Site confirmation and vegetation removal
62c4d42c-2a9b-54ed-885f-d6d16391c516 | note | FREQUENCY: Prior to commencement
d9f66d90-3c95-52cb-9862-6bb65a9a5ae8 | note | ACCEPTANCE CRITERIA: Joint site inspection to determine agreed scope of work including extent of drainage / vegetation work
77017ae2-ace1-58ec-bde3-1651088dcaa0 | note | REFERENCE DOCUMENTS: Cl 176.I1, Cl 100.5, Cl 100.10
9188f238-d39f-5b1c-bfd0-02d302a0012f | note | INSPECTION/TEST METHOD: ITP Signed
52cf22d2-656b-5b44-8d37-8a70abb943d9 | note | RECORD OF CONFORMITY: Completed ITP
cd65d4cf-c8fe-527e-a9eb-cea6d44d85ee | note | HP
d207c217-8b19-5fb9-865b-f83b450666bb | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
506b2367-3632-59fc-90c0-f93924fced62 | date | Date Completed:
6d427e5b-dbb7-48de-9270-1240af4e06b0 | signoff | AUTHORITY HOLDPOINT
71d938d7-9c8a-42de-9939-c89f4eba253a | checkpoint | 1.3 - Placement of VMS boards
1bac93b3-9266-5f36-a5ef-a7470982a306 | note | FREQUENCY: 2 weeks prior to commencement
dfc00f1d-8fbf-5f50-a2f3-6d1f9929be1c | note | ACCEPTANCE CRITERIA: Approval of installation location for VMS boards
541142c0-9d2b-5bc9-bf25-c605501eb157 | note | REFERENCE DOCUMENTS: Cl 100.11
f620f1c4-5afb-5ba7-a133-6142031bb1c5 | note | INSPECTION/TEST METHOD: ITP Signed
9cc139ca-04ba-551c-a445-0feb4be193ea | note | RECORD OF CONFORMITY: Completed ITP
e2d9fdfe-b340-54a3-b20b-d85b7aa8d70f | note | HP
0f071828-3605-527b-8681-f6f487ab1b3f | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
8475ce5e-5b42-50ec-a6a5-3c278d95387a | date | Date Completed:
f5ac70f0-61f4-4e19-aede-ad11d9bdbc05 | signoff | AUTHORITY HOLDPOINT
62ae4655-0cc5-460c-9e96-e69b15a80385 | checkpoint | 1.4 - Service location
c032c619-113d-57b2-aaa7-7768814726a9 | note | FREQUENCY: Prior to commencement
ad2ac770-3560-5397-a12d-78eb6c631868 | note | ACCEPTANCE CRITERIA: All services marked out and located on site
8dfc3dc2-21cc-5f76-9a38-2ebf7efa0808 | note | REFERENCE DOCUMENTS: Cl 100.13
8141d658-fb8b-576d-8f09-75286ae64671 | note | INSPECTION/TEST METHOD: ITP Signed
a135b8c3-a31f-57b7-a3f3-11723cabd1e5 | note | RECORD OF CONFORMITY: Completed ITP
008498a1-62fd-5eb4-911f-81e9edb9c747 | note | HP
6a2ef366-a637-5145-b2ff-f1976afd7951 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
be2584a0-4ece-52a0-a303-2802aea28d6f | date | Date Completed:
852b8a12-a638-4019-b13f-e89f28710f3f | signoff | AUTHORITY HOLDPOINT
767420c1-82df-4d4e-b2d9-3e01d0ff77c0 | checkpoint | 1.5 - Product approval
74cb427f-01f1-5e36-acae-737ba19c53d5 | note | FREQUENCY: Prior to commencing works
16e1c942-49e1-5146-b0e5-dde471c47c6b | note | ACCEPTANCE CRITERIA: Approval of products / materials
a23d2ac9-73f6-5cc6-a05f-85024eeb7767 | note | REFERENCE DOCUMENTS: Sec 663
4aceeac4-7430-578d-b259-e2a0dc9cd484 | note | INSPECTION/TEST METHOD: ITP Signed
44661014-dadd-5c5e-be0b-948883559476 | note | RECORD OF CONFORMITY: Completed ITP
85e7fa50-7770-519c-ac5c-14c2ad1cac54 | note | HP
7885c47e-eaa7-5e1b-b86a-2f33f2893ad1 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
49379379-5efd-5b59-9d44-c05ccc63453d | date | Date Completed:
a5c99a0c-3951-41d8-bc88-4319ce06c522 | signoff | AUTHORITY HOLDPOINT
3d7867cb-c4ed-4b6d-a077-6f492c2a227e | checkpoint | 1.6 - Methodology and works sequence approved
8335d076-34bd-5838-baa8-5558c83b5bfb | note | FREQUENCY: Prior to commencing works
6a6dd5d2-5db0-5db4-9b94-93f1cd209746 | note | ACCEPTANCE CRITERIA: Approval of methodology and works sequence
591751a5-62b2-5df4-9432-9d130cf37565 | note | REFERENCE DOCUMENTS: Sec 660
63ac924c-9635-54c4-98ed-987814c70366 | note | INSPECTION/TEST METHOD: ITP Signed
9d80b06e-613d-5fda-a972-a63d1b233590 | note | RECORD OF CONFORMITY: Completed ITP
7b80bf51-eec8-550b-a556-e8ed575a2819 | note | HP
d40014e4-2b26-58aa-b330-e17113d86594 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
dff94f27-4d40-5afd-9b72-9896edeed59e | date | Date Completed:
73a30eaa-ff90-496b-889c-18a8e86a85b3 | signoff | AUTHORITY HOLDPOINT
76243fa7-6d7d-4d8b-aa01-f2a11d97c502 | section | 2 - Civil Works
a1015b71-423b-4e03-a185-85d520f0d55d | checkpoint | 2.1 - Vegetation and verge removal
0e87bbdf-4c25-5f76-b12f-5c3abe099245 | note | FREQUENCY: Prior to asphalting
5ec614fb-0a8e-57ed-b5d5-40c803c466cd | note | ACCEPTANCE CRITERIA: All approved vegetation and verge stripping works completed
d35aeb94-ac4c-5f31-8abd-efd65c262cda | note | REFERENCE DOCUMENTS: Cl 100.1, Cl 204.03
5900b302-60d8-53ca-8b32-92b3dba09ca0 | note | INSPECTION/TEST METHOD: Inspection
d430c381-d1d2-5426-8c78-0bdbda7067a2 | note | RECORD OF CONFORMITY: Completed ITP
e11815f2-049e-5f73-8be5-2e33e6089c36 | note | IP
868a9397-1660-5d2a-8b95-2aa007d2d3c3 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
e1f9052f-bdae-5b70-9954-d217945129ef | date | Date Completed:
bad400dd-492e-4a8f-8737-c10df0a9b044 | checkpoint | 2.2 - If applicable, acceptance from Professional Engineer on bridge deck repairs in accordance with 'AST 5340 Cementitious Patch Repair of Concrete'
0017d280-e7b5-5321-975d-7cbb6b1cf731 | note | ACCEPTANCE CRITERIA: Signoff required from a professional consultant in accordance with AST 5340
c4dfcca7-d976-52ba-a646-d0d4fe4698cc | date | Date Completed:
4fb36df5-220a-491e-a42a-bfb65935d231 | checkpoint | 2.3 - Drain clearing
b3e68f7b-48f8-5de5-9a7a-971a6b56cf3d | note | FREQUENCY: Prior to asphalting
cdf4b93c-294e-5031-979e-0f7cdb14dd4e | note | ACCEPTANCE CRITERIA: Drain cleared and reshaped appropriately
9eb398bb-7862-5f4a-94e2-610ce957678c | note | REFERENCE DOCUMENTS: Cl 100.1, Cl 700.1
f911990d-e630-5abb-a5ce-4386f5b2d9f8 | note | INSPECTION/TEST METHOD: Inspection
c499feda-166e-5c59-8e3d-6e14af4063ef | note | RECORD OF CONFORMITY: Completed ITP
40aac4d5-d488-5c06-a3d6-d6d7fa7d60a9 | note | IP
f842f3dc-199a-558c-b8ca-5dfb16659fef | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
a8a88867-4749-598d-b4ce-f6bec8651300 | date | Date Completed:
77a481b7-d484-4f2d-ac9a-c1538dd57a47 | section | 2 - Expansion Joint Demolition & Installation
13d833bb-e7ca-4387-b977-d289fa3d55b6 | checkpoint | 2.1 - Saw cutting and removal of existing nosing
2e648f0f-5215-5d76-b6db-95c8df4cb092 | note | FREQUENCY: Prior to new nosing installation
a53fba8f-c18d-5bbc-b1b4-598d1817a69b | note | ACCEPTANCE CRITERIA: Sawcutting of all existing asphalt completed and all loose material removed from existing recess and a clear base and sides present to pour new nosing. Sand / grit blasting recommended
f79de941-addb-5ad8-a115-a91eda56d88a | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
f1db3ece-d9d5-5e5f-9c53-3269c7e77c26 | note | INSPECTION/TEST METHOD: Inspection
c2af18a2-eef7-5246-908e-9ef742fd0193 | note | RECORD OF CONFORMITY: Completed ITP
051f6090-4cda-59b9-b51d-24046366a55e | note | HP*
c2d29187-e0c2-5750-bd59-83d77f57fed8 | note | RESPONSIBILITY: Project Engineer / Foreman
d8eb276e-74dd-5a3e-83ff-831b3808d9a7 | date | Date Completed:
e6f7ba91-e116-4ad3-b97f-51ec7b87efce | checkpoint | 2.2 - Preparation and pouring of nosing
7d0e90cf-85c3-5153-bb19-3bc76849b583 | note | FREQUENCY: After sawcutting / demolition works completion
e3c5e5df-0bdd-5cc9-903b-8ca5904c8216 | note | ACCEPTANCE CRITERIA: Once the recess is clear of debris, insert styrofoam gap former, mix and pour the nosing polymer as per manufactuers specification
a9d6fe64-5904-5abf-8aef-cc864e0a7e53 | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
64de54af-dfd2-5856-8c90-83477c6e6cf5 | note | INSPECTION/TEST METHOD: Approval Correspondance
6b6a5bda-dc70-5896-ba0a-618f6c401f0b | note | RECORD OF CONFORMITY: Completed ITP
86b0a42e-3c36-5665-a3f2-d27a4905380d | note | IP
fae0c2c9-dd1a-55f4-813e-686345e90c0a | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
f3173d02-0f41-5ee5-b83c-eb76662e6d82 | date | Date Completed:
4fa1eb77-5ff5-4e9e-9728-25fe9685a71c | checkpoint | 2.3 - Preparation for joint seal
8f55e734-1178-5edb-8387-40b1a93d20c0 | note | FREQUENCY: After nosing has been poured and set
93164fc4-01a5-5a91-8675-486889e3cfe3 | note | ACCEPTANCE CRITERIA: Once the polymer has cured, styrofoam filler can be removed. 5mm x 5mm chamfer to be cut into edges of nosing. Undertake further grit blasting, prime the surface and install backing rod
14cf11cd-c0d5-56e3-bd77-35f891596ab4 | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
4813d71c-6114-5523-8a24-8f820f12a6e8 | note | INSPECTION/TEST METHOD: Approval Correspondance
052ea710-d627-5840-b28c-d9df67167e63 | note | RECORD OF CONFORMITY: Completed ITP
10778258-520d-536f-af7e-ea14ba9f6357 | note | IP
4c3b8038-8eea-5f18-b212-a6aed8e5ad43 | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
ccb4616b-84be-55a3-9d1f-c48c8f105bb0 | date | Date Completed:
42121e75-35c1-42cd-9d5d-f2a096a0dc9c | checkpoint | 2.4 - Pouring of silicone sealant
bc4f2ff8-f0ae-5be4-b0d9-2eb5d0d229c1 | note | FREQUENCY: After backing rod has been inserted
d594d745-0049-54dd-944a-6cb34b63384d | note | ACCEPTANCE CRITERIA: Mix and install approved sealant as per manufactuers specification, ensuring a 12mm recess below pavement level
de01b78e-0807-501c-a1b7-ecc18a7c00fa | note | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
f420d20a-bed2-592e-8e34-f6ce19f07782 | note | INSPECTION/TEST METHOD: Approval Correspondance
0377bfdd-da64-5544-b89d-0f574fb198d5 | note | RECORD OF CONFORMITY: Completed ITP
be38635a-e03b-587b-856a-236e9ca0a190 | note | IP
5271dac2-3cc8-5cf1-9d76-b5d1230a746e | note | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
f32581ea-61e4-5bb0-9216-d93827030a5b | date | Date Completed:
23bebd54-3b09-47e2-9aa1-9f5750a625ad | checkpoint | Final Inspection
235baed7-8d19-515a-94ed-3ac365bbfb14 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f50028a3-fd95-5b59-b600-49512e886094 | textbox | Print Name:
31fa033c-3a0d-507c-8ef9-9c37e7087d44 | textbox | Position:
dc010fcd-9cfd-5314-975a-f2b42fc8ad2d | date | Date: