## ITP-001 Open Cut
|  |  | Inspection and Test Plan - Hot Mix Asphalt Placement | [7 empty] | Document # ASP- ITP -001
[11 empty] | Revision : 1 | Date : 16/04/2024
Client: | DTP |  | Construction Process: | Hot Mix Asphalt Placement |  |  | Prepared by: |  | Reviewed by : |  | Approved by :
Project: | Hume Freeway, Tallarook | [5 empty] | Name: William Power |  | Name: | Paul Jeffery | Name:
Contract: | DOT 39515 |  | Specifications: | VicRoads Sections 407 Hot Mix Asphalt (2022); Section 404- Stone Mastic Asphalt (2018); Section 417- Open Grade Asphalt (2018) and AS2150 (2020) Hot Mix Asphalt – A Guide to Good Practice |  |  | Surfacing Engineer |  | Fulton Hogan |  | Client | DTP
Date: | / /
Lot No: |  |  | Location: | Hume Freeway
Carriageway: |  | Chainage: |  | Layer (circle) : SC WC IC1 IC2 BC |  | Asphalt Type and Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
No. |  |  | Frequency | Acceptance Criteria |  | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Fulton Hogan Industries | Client | Date | Comments
1 | Preliminary Works
1.1 | Mix Design approval / Tack Coat Approval |  | Prior to commencing paving | Mix design to be used must be registered and current by DTP as 'General'. The Contractor shall submit the details of the trackless tack coat or tack coat application system proposed to be used in the works. |  | 407.09 / 404.05 Mix Design Registration RC500.01 407.08 | Approval Correspondance | Completed ITP | HP | Superintendent | N/A
1.2 | Site Inspection and Base Condition |  | Prior to commencing paving | Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials. |  | 407.17 AS2150 10.1 AS2150 10.3 | Visual Inspection | Completed ITP | IP | Asphalt Supervisor |  | N/A
1.3 | Ambient Conditions for Placing |  | Prior to commencing paving | The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs Where the above temperatures cannot be achieved, asphalt must be laid under the "Cold Weather Management Plan" |  | 407.17 | Infrared Thermometer | Completed ITP | IP | Asphalt Supervisor |  | N/A
1.4 | Ambient Conditions for Placing / Cold Weather Placement Management Plan |  | Prior to commencing paving | Monitoring frequency of pavement temperature, asphalt temperature at discharge into paver and mat temperature after initial rolling. Asphalt delivery – planning to avoid delays and use of the quickest route to the site, enough trucks to allow continuous paving and avoiding trucks waiting for lengthy periods. Paving – determination of paving width and speed to match roller capacity, measurement of mix temperature prior to discharge, use of material transfer vehicles where practical and a process to cease works where pavement temperatures fall below the minimum requirement. Compaction - modified rolling procedures, additional rollers for surfacing mixes, use of joint compaction devices, monitoring of compaction and mat temperature during laying. |  | 407.17 | Infrared Thermometer | Cold Weather Field Sheet | HP | Superintendent | N/A
1.5 | Planning of Joints / Cold Planing |  | Prior to commencing paving | Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines Asphalt joints against a granular pavement shall not be offset between layers but shall form a vertical flush joint. Exposed granular pavement material shall be watered, re compacted. Before commencement of each day's work, all temporary transverse ramping shall be removed using a 2m profiler or skid steer with profiling head attachment & by cutting back along a straight line to expose a vertical face of fully compacted asphalt at the specified layer depth. |  | 407.21 402.04 402.05 | Measure and mark out runs by tape measure or survey | Completed ITP | WP | Asphalt Supervisor |  | N/A
1.5 | Tack Coat |  | Prior to Commencing paving | Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15 to 0.30 L/m2 of CRS60 of residual bitumen (except for joints and chases where rates shall be doubled). Tack coat must be allowed to fully break / cure . NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces. Where asphalt is to be spread over a clean, un-trafficked, freshly laid asphalt, or over a clean primed surface, or on a granular material where the overall asphalt depth is 150mm or greater the Contractor may omit the tack coat. Photographical evidence must be obtained (with an identifiable landmark) |  | 407.19 AS2150 11 | Spray area and inspect | Completed ITP Photograph | IP | Asphalt Foreman
2 | Photos
3 | Asphalt Placement works
3.1 | Commencement of Placing |  | Prior to Commencing paving | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority. |  | 407.23 404.13 | Visual Inspection | Completed ITP | HP | Superintendent | N/A
3.2 | Delivery of Mix |  | Each lot | Check correct mix design has been supplied, as per pavement design. |  | Pavement Design Details 407.20 | Check asphalt delivery docket | Completed ITP | IP | Asphalt Foreman |  | N/A
3.21 | Delivery of Mix |  | Each load | Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. |  | 404.13, 407.11 Table 407.111 407.20 (a) | Visual Inspection & Delivery Docket | Completed ITP | WP | Asphalt Foreman |  | N/A
3.3 | Traceability |  | Each lot | Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer |  | Fulton Hogan Quality Plan | Measure and Record on Daily Lot Record | Completed ITP | IP | Fulton Hogan Foreman/ Engineer |  | N/A
3.4 | Layer Thickness and Level Control |  | Regularly during paving | Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications |  | Pavement Design Details 407.25(a),(b) | Dips using ruler or dip stick | Completed ITP | WP | Asphalt Foreman |  | N/A
3.5 | Paver Stoppages |  | If paver stops | The Contractor shall conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised. A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C |  | 407.25 (c) | Thermometer | Completed ITP | WP | Asphalt Foreman |  | N/A
3.6 | Compaction |  | During paving / rolling | Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement. Vibratory rolling shall not be used to compact asphalt on bridge decks. SMA-H Vibratory rollers may be used for a maximum of two passes only. Use of vibration shall be discontinued immediately if any breakdown of surface aggregate occurs. Pneumatic tyred rollers shall not be used. |  | 404.14 407.26 | Visual Inspection | Completed ITP | WP | Asphalt Foreman |  | N/A
3.7 | Surface Finish |  | During paving and after final roll | The finished surface of asphalt shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks |  | 407.25 © 407.29 | Visual Inspection | Completed ITP | WP | Asphalt Foreman |  | N/A
3.8 | Kerb and Channel |  | During paving and after final roll | The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified |  | 407.29 (a)(ii) | Visual Inspection & Measurement | Completed ITP | WP | Asphalt Foreman |  | N/A
3.9 | Trafficking pavement after placment |  | After final roll | For Stone Mastic Asphalt, this must be 40°C |  | 404.14 | Visual Inspection & Thermometert | Completed ITP | HP | Superintendent | N/A
4 | Testing
4.1 | Compaction Testing (Dense Graded Apshalt) |  | Per Lot | Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits: >50mm layer depth = 96.0% <50mm layer depth = 95.0% SMA-H - <50mm layer depth 96.0% or more (6 tests) Additional Test must be undertaken on the longitudinal joints for wearing courses Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0% Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis |  | 404.14 Table 404.141 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure Table 407.271 | Nuclear Density Test, DGA Compaction Procedure | Completed ITP, Compaction rerports | TP | Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer |  | N/A
4.2 | Level Conformance |  | Each Lot | The minimum number of level measurements per Lot for Scale A: 80 tests per Lot The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.293 Scale A: +/- 5mm Range, +/- 8mm standard deviation |  | Table 407.292 407.29 | Survey Results | Completed ITP, Survey Conformance Results | WP | Surveyor |  | N/A
4.3 | Ride Quality |  | Within 3 months of applying surfacing | Individual lane Roughness value and Mean Lane Roughness Value less than those limits specified |  | VicRoads Section 180; Table 3040.021 | VicRoads Section 180 | Ride Test Report ARRB | TP | Fulton Hogan |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  |  | Signature:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Superintendent or Client |  |  | SCP Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SC Surfacing Course WC Wearing Course IC1 Intermediate Course 1 IC2 Intermediate Course 2 BC Base Course
Thermometer
Tack Coat