## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 - Hotmix Asphalt - Tallarook | itp |  |  |  |  | ITP-001 - Hotmix Asphalt - Tallarook Rev2
section | 1 – Preliminary Works
checkpoint | 1.1 - Mix Design approval / Tack Coat Approval
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Mix design to be used must be registered and current by DTP as 'General'.
label | ○ The Contractor shall submit the details of the trackless tack coat or tack coat application system proposed to be used in the works.
label | REFERENCE DOCUMENTS: 407.09 / 404.05, Mix Design Registration RC500.01, 407.08
label | INSPECTION / TEST METHOD: Approval Correspondance
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.17, AS2150 10.1 AS2150 10.3
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Asphalt Supervisor
date | Date Completed:
checkpoint | 1.3 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Cold Weather Management Plan"
label | REFERENCE DOCUMENTS: 407.17
label | INSPECTION / TEST METHOD: Infrared Thermometer
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing / Cold Weather Placement Management Plan
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Monitoring frequency of pavement temperature, asphalt temperature at discharge into paver and mat temperature after initial rolling.
label | ○ Asphalt delivery – planning to avoid delays and use of the quickest route to the site, enough trucks to allow continuous paving and avoiding trucks waiting for lengthy periods.
label | ○ Paving – determination of paving width and speed to match roller capacity, measurement of mix temperature prior to discharge, use of material transfer vehicles where practical and a process to cease works where pavement temperatures fall below the minimum requirement.
label | ○ Compaction - modified rolling procedures, additional rollers for surfacing mixes, use of joint compaction devices, monitoring of compaction and mat temperature during laying.
label | REFERENCE DOCUMENTS: 407.17
label | INSPECTION / TEST METHOD: Infrared Thermometer
label | RECORD OF CONFORMITY: Cold Weather Field Sheet
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Planning of Joints / Cold Planing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints for the final Wearing Course are located on lane lines
label | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines
label | ○ Asphalt joints against a granular pavement shall not be offset between layers but shall form a vertical flush joint.
label | ○ Exposed granular pavement material shall be watered, re compacted.
label | ○ Before commencement of each day's work, all temporary transverse ramping shall be removed using a 2m profiler or skid steer with profiling head attachment & by cutting back along a straight line to expose a vertical face of fully compacted asphalt at the specified layer depth.
label | REFERENCE DOCUMENTS: 407.21, 402.04, 402.05
label | INSPECTION / TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Supervisor
date | Date Completed:
checkpoint | 1.5 - Tack Coat
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15 to 0.30 L/m2 of CRS60 of residual bitumen (except for joints and chases where rates shall be doubled). Tack coat must be allowed to fully break / cure .
label | ○ NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces.
label | ○ Where asphalt is to be spread over a clean, un-trafficked, freshly laid asphalt, or over a clean primed surface, or on a granular material where the overall asphalt depth is 150mm or greater the Contractor may omit the tack coat.
label | ○ Photographical evidence must be obtained (with an identifiable landmark)
label | REFERENCE DOCUMENTS: 407.19, AS2150 11
label | INSPECTION / TEST METHOD: Spray area and inspect
label | RECORD OF CONFORMITY: Completed ITP, Photograph
label | IP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
section | 2 – Photos
checkpoint-no-status | Thermometer
checkpoint-no-status | Tack Coat
section | 3 – Asphalt Placement works
checkpoint | 3.1 - Commencement of Placing
label | FREQUENCY: Prior to Commencing paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
label | REFERENCE DOCUMENTS: 407.23, 404.13
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Delivery of Mix
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design.
label | REFERENCE DOCUMENTS: Pavement Design Details 407.20
label | INSPECTION / TEST METHOD: Check asphalt delivery docket
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.21 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 404.13, 407.11 Table 407.111, 407.20 (a)
label | INSPECTION / TEST METHOD: Visual Inspection & Delivery Docket
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.3 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION / TEST METHOD: Measure and Record on Daily Lot Record
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan Foreman/ Engineer
date | Date Completed:
checkpoint | 3.4 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b)
label | INSPECTION / TEST METHOD: Dips using ruler or dip stick
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.5 - Paver Stoppages
label | FREQUENCY: If paver stops
label | ACCEPTANCE CRITERIA: The Contractor shall conduct spreading operations to ensure that the paver speed matches the rate of supply so that stoppages are minimised.
label | ○ A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | REFERENCE DOCUMENTS: 407.25 (c)
label | INSPECTION / TEST METHOD: Thermometer
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.6 - Compaction
label | FREQUENCY: During paving / rolling
label | ACCEPTANCE CRITERIA: Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
label | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
label | ○ SMA-H Vibratory rollers may be used for a maximum of two passes only. Use of vibration shall be discontinued immediately if any breakdown of surface aggregate occurs. Pneumatic tyred rollers shall not be used.
label | REFERENCE DOCUMENTS: 404.14, 407.26
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.7 - Surface Finish
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.25 (c), 407.29
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.8 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: 407.29 (a)(ii)
label | INSPECTION / TEST METHOD: Visual Inspection & Measurement
label | RECORD OF CONFORMITY: Completed ITP
label | WP
label | RESPONSIBILITY: Asphalt Foreman
date | Date Completed:
checkpoint | 3.9 - Trafficking pavement after placment
label | FREQUENCY: After final roll
label | ACCEPTANCE CRITERIA: For Stone Mastic Asphalt, this must be 40°C
label | REFERENCE DOCUMENTS: 404.14
label | INSPECTION / TEST METHOD: Visual Inspection & Thermometert
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4 – Testing
checkpoint | 4.1 - Compaction Testing (Dense Graded Apshalt)
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
label | — >50mm layer depth = 96.0%
label | — <50mm layer depth = 95.0%
label | ○ SMA-H - <50mm layer depth 96.0% or more (6 tests)
label | ○ Additional Test must be undertaken on the longitudinal joints for wearing courses
label | ○ Test Lots 50m2-500m2, may be treated as a small area,in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
label | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
label | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
label | REFERENCE DOCUMENTS: 404.14 Table 404.141 407.27(a),(c) 407, Section 173, Dense Graded Compaction Procedure Table 407.271
label | INSPECTION / TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
label | RECORD OF CONFORMITY: Completed ITP, Compaction rerports
label | TP
label | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
date | Date Completed:
checkpoint | 4.2 - Level Conformance
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The minimum number of level measurements per Lot for Scale A: 80 tests per Lot
label | ○ The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.293
label | ○ Scale A: +/- 5mm Range, +/- 8mm standard deviation
label | REFERENCE DOCUMENTS: Table 407.292, 407.29
label | INSPECTION / TEST METHOD: Survey Results
label | RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results
label | WP
label | RESPONSIBILITY: Surveyor
date | Date Completed:
checkpoint | 4.3 - Ride Quality
label | FREQUENCY: Within 3 months of applying surfacing
label | ACCEPTANCE CRITERIA: Individual lane Roughness value and Mean Lane Roughness Value less than those limits specified
label | REFERENCE DOCUMENTS: VicRoads Section 180; Table 3040.021
label | INSPECTION / TEST METHOD: VicRoads Section 180
label | RECORD OF CONFORMITY: Ride Test Report ARRB
label | TP
label | RESPONSIBILITY: Fulton Hogan
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: