## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-325-CIV Landscaping - Ground Preparation
ITP Description: |  | Landscaping - Ground Preparation
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2025-10-02
ITP created by: |  | Will McCuskey
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP for Akuna Dr Link Road
Inspection & Test Plan - Landscaping - Ground Preparation
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-10-02
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
VicRoads 720 AS 4454 AS 4419 IFC Drawings
2 | Preliminaries
2.1 | Check for correct documentation | Drawings and drawing registers | Ensure that all employees and subcontractors are: - Using the correct and complete set of IFC drawings - All drawings are the latest revision | Document Review | Prior to Commencement of works | IP | SE | This ITP
2.2 | Submission and records | Section 720.03 | Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery. Following information shall be provided to the NA: Samples -Mulch -Imported topsoil Records -Details of suppliers -Soil tests on imported topsoil -Copies/Photos of fertiliser labels | Document Review | Prior to Commencement of works | IP | SE, NA | This ITP Issue to TeamBinder: Records & certificates |  |  | Insert Text Box: TeamBinder Approval No.
2.3 | Supply of topsoil | Section 720.04 Table 720.042 IFC Drawings | Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor. Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings . | Verify, Doc. Review if applicable | Prior to Commencement of works | N/A | SE | This ITP Issue to TeamBinder: material conformance docs or Test Report |  |  | Drop Down Box: Site won top soil, imported Insert Text Box: TeamBinder Approval No.
2.4 | Supply of Mulch | Section 720.04 Table 720.044 AS4454 IFC Drawings | Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings. All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings . Imported Wood Mulch shall comply with Table 720.044. | Verify, Doc. Review if applicable | Prior to Commencement of works | N/A | SE | This ITP Issue to TeamBinder: material conformance docs (if applicable) |  |  | Drop Down Box: Site won mulch, imported Insert Text Box: TeamBinder Approval No.
3 | Site Preparation
3.1 | Set Out | Section 720.06 IFC Drawings | The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings. | Inspection | Each Lot | WP | SE/Site Supervisor | This ITP
3.2 | Soil Additives | Section 720.07 AS 4419 | Soil additives, including any material used to modify the chemical properties of the soil, shall be applied by the Contractor prior to physical ripping and cultivation and in accordance with results and recommendations from site topsoil analysis tests, if applicable. | Document Review | Each Lot | IP | SE | This ITP Attach Test Report
3.3 | Ripping of subsoil | Section 720.07 Table 720.071 | All ripping works shall conform to the requirements of 720.07 Situation- Ripping of subsoil • Planting Areas in disturbed areas flatter than 3h:1v= min 400mm deep at a max of 500mm spacing • Planting Areas in disturbed areas steeper than 3h:1v= min 300mm at a max 500mm spacing • Planting Areas in undisturbed areas = Min 400mm deep at a max of 500mm spacing • Grassing in disturbed areas = Min 200 mm deep, 500 mm max spacing • Individual Tree Planting within grassed areas = min 400mm deep at a max of 500mm spacing Note: Ripping shall not occur within the extent of existing vegetation areas marked for protection or within the drip-line of existing woody plants. Do not proceed until the NA inspects and acknowledges requirements for ripping have been met. | Verify | Each Applicable Lot | HP | SE, NA | This ITP Attach Lot Map/Marked Up Area Inspected
3.4 | Edging | IFC Drawings | The Contractor shall set out the location and shape of edging in accordance with the IFC Drawings. | Verify | Each Applicable Lot | IP | SE/Site Supervisor | This ITP Attach Delivery Dockets if applicable
3.5 | Topsoil application | IFC Drawings Section 720.07 | Topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in the IFC Drawings | Verify | Each Applicable Lot | HP | SE, NA | This ITP
3.6 | Cultivation | Section 720.07 | Cultivation will only take place if easy manual excavation cannot be achieved to 300mm or deeper. If easy manual excavation is not achieved the following will take place Situation – Cultivate- Table 720.071 • Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum • Planting Areas in undisturbed areas=150mm Minimum • Grassing in undisturbed areas = 100mm Minimum Note: Cultivation shall not occur within the extent of existing vegetation areas marked for protection or the drip-line of existing woody plants. Hand cultivation shall be used within root zones of trees to be retained. | Verify | Each Applicable Lot | HP | SE, NA | This ITP Attach Lot Map/Marked Up Area Inspected
3.7 | Topsoil FSL | Section 720.07 | After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes. • Vibrating plates shall not be used. The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces. The finished level of grassed areas shall be: • not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls; • level with the bottom of fence plinths; • level with adjacent pavements, kerbs, pits and other structures. Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met | Verify | Each Applicable Lot | HP | SE, NA | This ITP Attach Lot Map/Marked Up Area Inspected
3.8 | Weed and Erosion Control Mat (if applicable) | IFC Drawings Section 720.04 i) | Jute or approved equivalent to be installed as indicated by the IFC drawing. Jute mat to be installed where specified on IFC drawings for planting areas steeper than 2:1 and in planting areas prone to flooding or within 2m of waterways, swales, wetlands and sedimentation ponds. Mat shall be laid and anchored in accordance with the manufacturer’s instructions. | Verify | Each Applicable Lot | IP | SE, Site Supervisor | This ITP Reference TeamBinder Material Approval No. if applicable Attach Delivery Dockets |  |  | Insert Text Box: TeamBinder Approval No.
3.9 | Mulching | Section 720.08 a) IFC Drawings | Wood mulch to be placed at all planting areas unless specified. Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all planting areas. If space does not permit this, mulching shall extend to the back of kerb. Ecodynamics shall install mulch rings around individual tree plantings. Mulch depths in all situations shall be a minimum 75mm and maximum 125mm. Mulch shall be raked to an even, neat appearance and kept clear of plant stems to avoid collar rot. | Verify | Each Applicable Lot | IP | SE, Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /