## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Concrete Pours - 103 - Rev B | itp |  |  |  |  | ITP - Concrete Pours - 103 - Rev B
section | 10.01 Concrete Pours
checkpoint | Construction Joint Locations
label | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Approval
label | Frequency - Prior to Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Dry Pack Mortar
label | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Pre pour
label | Frequency - Before Works
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Blinding Concrete Subgrade Inspection
label | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
label | Standard / Specification - PS 19.5.1
label | Verifying Document - Pre Pour Checksheet
label | Frequency - Prior to Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcement Pre Pour Inspection
label | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Pre pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Pre-Pour Inspection
label | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Signed Pre-Pour
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Slump Testing
label | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | Verifying Document - Pre Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Compression Testing Insutu Concrete
label | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
label | Verifying Document - IANZ Test Results
label | Frequency - One Set Daily consist of at least six field specimens
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Compression Testing Precast Concrete
label | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
label | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
label | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
label | Verifying Document - Plant Test Results
label | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 10.02 Post Pours
checkpoint | Post Pour Inspection
label | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Standard / Specification - PS 18.2, PS 19, PS 19.15
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Construction joints
label | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
label | Standard / Specification - PS 18.2, PS 19, PS 19.15
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Concrete Curing
label | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
label | Standard / Specification - PS 18.2, PS 19, PS 19.12
label | Verifying Document - Post Pour
label | Frequency - At least 7 days after pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Stripping
label | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
label | Standard / Specification - PS 18.2, PS 19
label | Verifying Document - Post Pour
label | Frequency - At least 3 days after pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Protection of Completed Works
label | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
label | Standard / Specification - PS 18.2, PS 19
label | Verifying Document - Post Pour
label | Frequency - During the remainder of the construction period
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Defective Concrete Finishes
label | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Standard / Specification - PS 18.2, PS 19, PS 19.13
label | Verifying Document - NCR
label | Frequency - Prior to non Minor Repair
label | Verification Activity: Activity - V
label | Verification Activity: By - SE