## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Retaining Wall Construction - 103 - Rev B | itp |  |  |  |  | ITP - Retaining Wall Construction - 103 - Rev B
section | 4.19 Retaining Wall Materials
checkpoint | T-CES 101
label | Acceptance / Conformance Criteria - All concrete shall comply with T-CES 101 (NZ) and NZS 3109.
label | ○ Refer to Section 5 of T-CES 101 (NZ) for Concrete Acceptance Tests which shall comply with Clause 9 of NZS 3109.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | Frequency - Prior to Works
checkpoint | Retaining Wall Concrete
label | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam. The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works
label | Standard / Specification - PS 18.2.5, PS 18.5.1
label | Verifying Document - Mix Design
label | Frequency - before the commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Hot-dip Galvanising
label | Acceptance / Conformance Criteria - Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680. All alterations to fittings shall be hot dip galvanised following fabrication.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Datasheet
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Welding of Structural Steel works
label | Acceptance / Conformance Criteria - All welding of steelwork shall comply with T-CES 301. All welds shall be fully sealed.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Frequency - Prior to Works
checkpoint | Welding Procedures
label | Acceptance / Conformance Criteria - All welds shall be weld category GP in accordance with NZS 3404. All welding procedures shall be in accordance with AS/NZS 1554. The Contractor shall submit full details of the proposed welding procedures and electrodes, with drawings and schedules as required.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Welding Procedures
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Welders Qualifications
label | Acceptance / Conformance Criteria - Only welders qualified to AS/NZS 1554, or equivalent standard shall be employed on the works. Proof of welder’s proficiency and qualification shall be made available to the Engineer on request.
label | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
label | Verifying Document - Qualification
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steel Piles
label | Acceptance / Conformance Criteria - Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680. Only new steel pile section to be used. All piles and production certificates shall be made available for inspection by the Engineer at any time.
label | Standard / Specification - PS 18.2.4, PS 18.2.1, PS 18.2.2
label | Verifying Document - Mill Certs
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steel Reinforcement Compliance
label | Acceptance / Conformance Criteria - Conforming Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied.
label | Standard / Specification - AS/NZS4671 & NZS3109
label | Verifying Document - Detail Sheets and Mill Certificates
label | Frequency - Prior to ordering steel
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | Reinforcing Welding Qualifications
label | Acceptance / Conformance Criteria - Welders and Procedures are to be qualified to AS/NZS 1554.3, reviewed by TPI for conformance and submitted to the Engineer for Acceptance.
label | Standard / Specification - Drawings
label | Verifying Document - TPI Report
label | Frequency - Prior to Welding
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcing Welding
label | Acceptance / Conformance Criteria - All welded reinforcing shall be completed as per AS/NZS 1554.3 and be 100% Visually NDT inspected by an independent and approved Third Party Inspector (TPI).
label | Standard / Specification - Drawings
label | Verifying Document - TPI Report
label | Frequency - Prior to concrete pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Pile Concrete Mix Design / Tremmie Mix Design
label | Acceptance / Conformance Criteria - Mix design compiling with the requirements of the contract to be approved by the Engineer.
label | Standard / Specification - Drawings
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Concrete Aggergate
label | Acceptance / Conformance Criteria - Aggregates for concrete shall be selected from a single source, which shall be used for all concrete that will form part of the permanent works. Nominal maximum coarse aggregate size shall be 15mm.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
label | Verifying Document - Mix Design
label | Frequency - Prior to Works
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Concrete Capping Concrete
label | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa.
label | Standard / Specification - PS 18.5.1
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Capping Steelwork
label | Acceptance / Conformance Criteria - All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process. Quench and tempered is not permitted.
label | Standard / Specification - PS 18.5.2, PS 18.1.2
label | Verifying Document - Detail Sheets and Mill Certificates
label | Frequency - Prior to ordering steel
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | PFC & UC Steelwork
label | Acceptance / Conformance Criteria - Sections shall be grade 300 unless noted otherwise. All PFC & UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P. All welds to be 6mm minimum continuous fillet welds, unless noted otherwise.
label | Standard / Specification - PS 18.5.2, PS 18.1.2
label | Verifying Document - Detail Sheets and Mill Certificates
label | Frequency - Prior to ordering steel
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Precast Mild steel fixings
label | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
label | Standard / Specification - PS 19.15.6
label | Verifying Document - Datasheet / Mill Certs
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Precast Stainless steel
label | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
label | Standard / Specification - PS 19.15.7
label | Verifying Document - Datasheet / Mill Certs
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Reinforcement cover spacer blocks
label | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
label | Standard / Specification - PS 19.7.8
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 9.01 Pile Construction
checkpoint | Contractor’s Methodology for Pile Construction
label | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works.
label | Standard / Specification - PS 18.3.1, PS 18.1.2
label | Verifying Document - Approved Methodology
label | Frequency - At least two weeks prior to commencement of the works.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Construction of Piles
label | Acceptance / Conformance Criteria - in T-CES 213
checkpoint | Setting Out
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings.
label | Standard / Specification - PS 18.4.2
label | Verifying Document - Survey Records
label | Frequency - Each Pile
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Setout Approval
label | Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer.
label | Standard / Specification - PS 18.4.2
label | Verifying Document - Engineers Approval
label | Frequency - Each Pile beofre excavation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Depth of Foundation
label | Acceptance / Conformance Criteria - The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals.
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Engineers Approval
label | Frequency - Each Pile Before Survey and Concrete
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pilling Records
label | Acceptance / Conformance Criteria - The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded. The daily records from the driller shall be submitted no later than noon the following day.
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Pilling Records
label | Frequency - Daily
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Pilling Timming
label | Acceptance / Conformance Criteria - During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time.
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Survey Records
label | Frequency - Each Pile
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Pile Excavation Survey
label | Acceptance / Conformance Criteria - On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete.”
label | Standard / Specification - PS 18.3.2
label | Verifying Document - Survey Records
label | Frequency - Each Pile before concrete
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Construction Tolerances for Piles
label | Acceptance / Conformance Criteria - The allowable positional tolerances of the concrete piles shall be ± 50 mm. The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical.
label | Standard / Specification - PS 18.3.3
label | Verifying Document - Survey Records
label | Frequency - Each Pile
label | Verification Activity: Activity - I
label | Verification Activity: By - SV
checkpoint | Remedial Painting
label | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
label | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2
label | Verifying Document - Site Records
label | Frequency - Each Occurance
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 9.02 Monitoring Points and Survey
checkpoint | Monitoring Surveys / Deformation Surveys
label | Acceptance / Conformance Criteria - Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures.
label | Standard / Specification - PS 18.7.1
label | Verifying Document - Survey Records
label | Frequency - As Required
label | Verification Activity: Activity - I
label | Verification Activity: By - SV