## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - General - Materials ITP - 105 - Rev B | itp |  |  |  |  | ITP - General - Materials ITP - 105 - Rev B
section | 4.34 Traffic Service Materials
checkpoint | Safe Lane Delineator Concrete
label | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
label | Standard / Specification - PS 23.7
label | Verifying Document - Datasheet / Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Guard Rail Concrete
label | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Datasheet / Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Proposed Guard Rails
label | Acceptance / Conformance Criteria - The Contractor shall submit details of proposed proprietary materials and systems.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Datasheets
label | Frequency - Prior to material order (4 weeks prior to installation)
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Guard Rail Maintenance Instructions
label | Acceptance / Conformance Criteria - The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Maintenance Instructions
label | Frequency - Upon completion of the Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Coloured Surfacing
label | Acceptance / Conformance Criteria - The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33.
label | Standard / Specification - PS 23.4
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.35 Sign Materials
checkpoint | Retro-reflective sheeting
label | Acceptance / Conformance Criteria - All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting.
label | Standard / Specification - PS 23.2.6
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Anti-Graffiti Coating
label | Acceptance / Conformance Criteria - Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign.
label | Standard / Specification - PS 23.2.14
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Dew Effect Coating
label | Acceptance / Conformance Criteria - All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’.
label | Standard / Specification - PS 23.2.15
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Sign Shop Drawings
label | Acceptance / Conformance Criteria - The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign.
label | Standard / Specification - PS 23.2.6
label | Verifying Document - Shop Drawings
label | Frequency - At least ten working days prior to manufacture of the sign.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Timber Posts
label | Acceptance / Conformance Criteria - Timber posts shall not exceed 100mm x 100mm section size. They shall be Building Grade or Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level.
label | Standard / Specification - PS 23.2.19
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steel Posts
label | Acceptance / Conformance Criteria - Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.20
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Aluminium Poles
label | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.21
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Impact Resistant System Posts
label | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
label | Standard / Specification - PS 23.2.22
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Sign Fixings
label | Acceptance / Conformance Criteria - All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign.
label | Standard / Specification - PS 23.2.23
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Training
label | Acceptance / Conformance Criteria - The installer shall demonstrate prior to undertaking the works that its staff has attended, or are scheduled to attend, a recognised training course in the handling, installation, and maintenance of retro-reflective road signs.
label | Standard / Specification - PS 23.2.25
label | Verifying Document - Training Records
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.36 Long-life Road Markings Materials
checkpoint | Applicator Approval
label | Acceptance / Conformance Criteria - The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12. No installation shall commence without the written approval of the Engineer accepting the certification and suitability of the applicator(s) proposed.
label | Standard / Specification - PS 23.5.2
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Long-life Road Markings Materials, Marking System and Format
label | Acceptance / Conformance Criteria - Only products approved to NZTA specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works. The submission must include:
label | a) Material Type (Cold Applied or Thermoplastic)
label | b) Format of the marking (Structured only)
label | c) M07 or M24 approval list with the product highlighted, or NZTA approval letter or NZTA interim approval letter.
label | Standard / Specification - PS 23.5.3
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Installation Limitations
label | Acceptance / Conformance Criteria - The Contractor shall supply the Engineer with the Supplier Specifications or Instructions on Installation for the long-life road marking system proposed to be used. No installation shall commence without the written approval of the Engineer accepting the suitability of the long-life road marking system proposed.
label | Standard / Specification - PS 23.5.4
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Glass beads
label | Acceptance / Conformance Criteria - The Contractor shall ensure that glass beads have appropriate adhesive coatings for the long-life road marking product being used. No installation shall commence without the written approval of the Engineer accepting the suitability of the glass beads proposed.
label | Standard / Specification - PS 23.5.5
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Raised Pavement Markers
label | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers.
label | Standard / Specification - PS 23.5.6
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Application Crew
label | Acceptance / Conformance Criteria - The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed.
label | Standard / Specification - PS 23.5.7
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 4.37 Pavement Marking Materials
checkpoint | High performance markings
label | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified.
label | ○ The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Glass beads
label | Acceptance / Conformance Criteria - All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17).
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Raised Pavement Markers
label | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Edge Marker Posts:
label | Acceptance / Conformance Criteria - Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Datasheets
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 4.38 Fencing Materials
checkpoint | Post and Wire Fencing Materials
label | Acceptance / Conformance Criteria - All in ground timber posts shall be treated to H4 standard and all other timber shall be treated to H3 standard. All posts to be sunk to the required depth and supported to form a rigid boundary fence.
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Datasheet / Docket
label | Frequency - Prior to Installation
section | 4.39 Landscaping Material Supply
checkpoint | Plant Supply
label | Acceptance / Conformance Criteria - All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag. All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper. All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs.
label | Standard / Specification - PS 25.2.1
label | Verifying Document - Plant Details
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | General plant species and quality
label | Acceptance / Conformance Criteria - The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material.
label | Standard / Specification - PS 25.2.1
label | Verifying Document - Notice
label | Frequency - 5 working day notice
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Street tree grades, species, and form
label | Acceptance / Conformance Criteria - All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens. No substitution of species or grade shall be made without the written approval of the Engineer.
label | Standard / Specification - PS 25.2.2
label | Verifying Document - Plant Details
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Chemical applications for weed and pest control
label | Acceptance / Conformance Criteria - All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Qualifications and Datasheet
label | Frequency - Prior to Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Biodegradable plant guards
label | Acceptance / Conformance Criteria - All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39.
label | Standard / Specification - PS 25.6
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Fertilisers
label | Acceptance / Conformance Criteria - Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser.
label | Standard / Specification - PS 25.7.3.2
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Imported Topsoil
label | Acceptance / Conformance Criteria - Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Biodegradable Weed Matting
label | Acceptance / Conformance Criteria - The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved.
label | Standard / Specification - PS 25.9.1
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Mulching fabric Testing
label | Acceptance / Conformance Criteria - A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky. It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Test Results
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Mulch
label | Acceptance / Conformance Criteria - The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Engineers Approval
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Turf / Instant turf
label | Acceptance / Conformance Criteria - The turf shall be of good quality in line with industry standards.
label | Standard / Specification - PS 25.10.5
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE