## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Landscaping ITP - 105 - Rev B | itp |  |  |  |  | ITP - Landscaping ITP - 105 - Rev B
section | 4.39 Landscaping Material Supply
checkpoint | Plant Supply
label | Acceptance / Conformance Criteria - All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag. All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper. All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs.
label | Standard / Specification - PS 25.2.1
label | Verifying Document - Plant Details
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | General plant species and quality
label | Acceptance / Conformance Criteria - The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material.
label | Standard / Specification - PS 25.2.1
label | Verifying Document - Notice
label | Frequency - 5 working day notice
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Street tree grades, species, and form
label | Acceptance / Conformance Criteria - All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens. No substitution of species or grade shall be made without the written approval of the Engineer.
label | Standard / Specification - PS 25.2.2
label | Verifying Document - Plant Details
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Chemical applications for weed and pest control
label | Acceptance / Conformance Criteria - All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Qualifications and Datasheet
label | Frequency - Prior to Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Biodegradable plant guards
label | Acceptance / Conformance Criteria - All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39.
label | Standard / Specification - PS 25.6
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Fertilisers
label | Acceptance / Conformance Criteria - Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser.
label | Standard / Specification - PS 25.7.3.2
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Imported Topsoil
label | Acceptance / Conformance Criteria - Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Biodegradable Weed Matting
label | Acceptance / Conformance Criteria - The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved.
label | Standard / Specification - PS 25.9.1
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Mulching fabric Testing
label | Acceptance / Conformance Criteria - A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky. It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Test Results
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Mulch
label | Acceptance / Conformance Criteria - The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Engineers Approval
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Turf / Instant turf
label | Acceptance / Conformance Criteria - The turf shall be of good quality in line with industry standards.
label | Standard / Specification - PS 25.10.5
label | Verifying Document - Datasheet
label | Frequency - Prior to supply
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
section | 18.01 General
checkpoint | Topsoil Placement Inspection
label | Acceptance / Conformance Criteria - The Engineer shall inspect the cut surfaces prior to the placement of topsoil and planting.
label | Standard / Specification - PS 15.10.10
label | Verifying Document - Engineers Approval
label | Frequency - Prior to Topsoil Placement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Setting out Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Applying herbicide Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Applying herbicide.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Cultivation of planting areas Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Cultivation of planting areas.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Delivery of plants and trees Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Delivery of plants and trees.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Planting or seeding Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Site visits during maintenance period Notice
label | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Site visits during maintenance period.
label | Standard / Specification - PS 25.1.6
label | Verifying Document - Notice
label | Frequency - At least two days prior
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 18.02 Weed, Pest, and Litter Control
checkpoint | Litter control
label | Acceptance / Conformance Criteria - The planting area shall be kept clear of all rubbish, including domestic and building materials.
label | Standard / Specification - PS 25.5.1
label | Verifying Document - Site Records
label | Frequency - Ongoing
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Spraying Operations
label | Acceptance / Conformance Criteria - All spraying operations shall be carried out in windless, dry conditions, when rain is not imminent for at least 12 hours and at times which minimise possible hazards or disruption to the public, animals or other beneficial fauna. Care shall be taken to prevent spray drifting onto non-target areas or plants and comply with notification requirements as required by the proposed Waikato Regional Plan.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Chemical weed control in planting areas
label | Acceptance / Conformance Criteria - Chemical weed control in planting areas shall be kept within the edge of the planting beds, within a maximum of 500mm of tree trunks, within 50mm of the edge of any undefined mulch surface, and within 50mm of any posts or the base of any landscape structures.
label | Standard / Specification - PS 25.5.2
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Biodegradable plant guards
label | Acceptance / Conformance Criteria - All plants to be fitted with biodegradable plant guards.
label | Standard / Specification - PS 25.6
label | Verifying Document - Site Records
label | Frequency - Each Plant
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 18.03 Planting
checkpoint | Planting Layout
label | Acceptance / Conformance Criteria - All plants shall be positioned in the locations and in the quantities shown on the drawings., Planting Schedule and Typical Cross Sections for inspection and authorisation by the Engineer prior to planting.
label | Standard / Specification - PS 25.7.1
label | Verifying Document - Site Records
label | Frequency - Prior to Planting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Specimen and street trees
label | Acceptance / Conformance Criteria - Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation.
label | Standard / Specification - PS 25.7.2.1
label | Verifying Document - Site Records
label | Frequency - Each Tree
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Irrigation and Fertilising
label | Acceptance / Conformance Criteria - During installation and establishment, the soil in all planting areas moisture shall be retained to ensure active plant growth throughout the growing season (September – May)..
label | Standard / Specification - PS 25.7.2.3
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fertilising
label | Acceptance / Conformance Criteria - Generally, some form of fertiliser shall be applied to planting depending on the soil type. For shrubs and trees, all fertiliser shall be well mixed with the backfilled soil. For bedding or groundcover all fertiliser shall be well mixed with the site topsoil prior to planting.
label | Standard / Specification - PS 25.7.3.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Plantings
label | Acceptance / Conformance Criteria - All specimen tree plantings shall have two-year slow release fertiliser tablets installed at the time of planting.
label | Standard / Specification - PS 25.7.3.3
label | Verifying Document - Site Records
label | Frequency - Each Tree
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Topsoiling (1)
label | Acceptance / Conformance Criteria - All topsoil and operations relating to topsoil for the project shall fully conform to Section F of NZTA P39.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Site Records
label | Frequency - prior to planting.
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Topsoiling (2)
label | Acceptance / Conformance Criteria - All new planting areas on existing topsoil shall be deep ripped to a minimum of 300mm prior to planting.
label | Standard / Specification - PS 25.8.1
label | Verifying Document - Site Records
label | Frequency - prior to planting.
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 18.04 Biodegradable Weed Matting and Mulching
checkpoint | Biodegradable high density mulch matting
label | Acceptance / Conformance Criteria - The blanket shall be installed according to the Manufacturer’s directions and shall include stapling the blanket at a minimum of 1 metre centres and perimeter edges buried to 300mm depth buried soil.
label | Standard / Specification - PS 25.7.1
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Flat Site Mulch
label | Acceptance / Conformance Criteria - On sites flatter than a 1:2 grade (1.0m high by 3.0m metres long), bark or arb mulch shall be spread evenly to a depth of 80-100mm over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Steep Site Mulch
label | Acceptance / Conformance Criteria - On slopes steeper than 1:2 mulching for weed control shall consist of an Engineer approved matting with the following criteria:
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Very Steep Slopes Mulch
label | Acceptance / Conformance Criteria - On steep slopes (1 in 4) with erosion issues that are receiving planting, biodegradable netting with no geotextile or geonet content shall be used at the Engineer’s discretion.
label | Standard / Specification - PS 25.9.2
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 18.05 Grassing, Sowing and Turfing
checkpoint | Preparation for sowing or turfing
label | Acceptance / Conformance Criteria - Excessive compaction of subsoil in existing grassed areas shall be relieved to achieve satisfactory long-term growing conditions. All topsoil removed to permit contract works to be carried out shall be stockpiled for reuse. All new grass areas shall be built on soil prepared to industry best practice standards. Sloped areas shall be neatly contoured into adjoining grassed areas. Perennial weeds shall be controlled with industry best practice methods.
label | Standard / Specification - PS 25.10.1
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Fertilisers
label | Acceptance / Conformance Criteria - Fertilisers shall be lightly arrowed into the topsoil, 2-3 days prior to seed sowing, at the following rates at 200kg/ha. This shall be followed one month after sowing, with an application of: Di-ammonium Phosphate (DAP) 100 kg/ha.
label | Standard / Specification - PS 25.10.2
label | Verifying Document - Site Records
label | Frequency - 2-3 days prior to seed sowing and 1 month after sowing
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Grass sowing
label | Acceptance / Conformance Criteria - On large areas the seed shall be “check” sown in at least two directions and surface rolled with suitable flat roller. On small areas the grass seed shall be evenly applied and raked into the soil.
label | Standard / Specification - PS 25.10.3
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Establishment of sown areas
label | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Grassed areas shall be watered as required to achieve an efficient germination of the seed. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
label | Standard / Specification - PS 25.10.4
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Grassed areas adjacent hardscape
label | Acceptance / Conformance Criteria - If base of grass level is 30mm lower or more than adjacent hardstand, grass will need to be removed min 1m back from path, soil put back in, levelled and re-consolidated to spec and grass res-own to correct level. If less than 30mm top dressing at 10mm each time, over time will be acceptable until the correct level is achieved.
label | Standard / Specification - PS 25.10.4
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Turf / Instant turf
label | Acceptance / Conformance Criteria - Turf shall be installed and maintained in accordance with supplier’s requirements.
label | Standard / Specification - PS 25.10.5
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Slope areas
label | Acceptance / Conformance Criteria - In all sites, except natural gully systems, where the slope gradient is steeper than 1:3 (one metre high by three metres long), it is preferable that the embankment is either scarified or grooved on an angle to a depth of 200mm, from the top of the bank to the base. This assists topsoil adhesion and prevents separation of the top 150mm topsoil from the base material due to gravity and/or glazed/planning of base material.
label | Standard / Specification - PS 25.10.6
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 18.06 Fencing
checkpoint | Seven Wire Fencing Order
label | Acceptance / Conformance Criteria - The Contractor is to liaise with the property owner to establish the preferred spacing and order of the seven wires.
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Comms
label | Frequency - Prior to Installation
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | Post and Wire Fencing Installation
label | Acceptance / Conformance Criteria - New seven wire standard boundary fence shall be erected with the following Offset tolerances 0.0m towards the centreline and 0.0m to 0.3m away from the centreline. The fence shall be vertical, and the grade shall generally follow the contour of the ground.
label | Standard / Specification - PS 25.12.2
label | Verifying Document - Survey Records
label | Frequency - Each Fence
label | Verification Activity: Activity - I
label | Verification Activity: By - SV