## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Traffic Services ITP - 105 - Rev B | itp |  |  |  |  | ITP - Traffic Services ITP - 105 - Rev B
section | 16.01 Signs
checkpoint | Redundant Signs
label | Acceptance / Conformance Criteria - All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use. All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner.
label | Standard / Specification - PS 23.2.2
label | Verifying Document - Site Records
label | Frequency - Where Required
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Relocated Signs
label | Acceptance / Conformance Criteria - All relocated signs shall be Firmly installed in a vertical position and securely attached to posts where appropriate. Fixed to posts with appropriate fixing brackets. Signs shall not be fixed to posts by bolting through the sign unless specifically approved by the Engineer.
label | Standard / Specification - PS 23.2.3
label | Verifying Document - Site Records
label | Frequency - Each Sign
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Posts and poles
label | Acceptance / Conformance Criteria - The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification. The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures.
label | Standard / Specification - PS 23.2.17 PS 23.2.18 PS 23.2.24
label | Verifying Document - Checksheet
label | Frequency - Each Sign
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | Ground Mounted Signs
label | Acceptance / Conformance Criteria - All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1.
label | Standard / Specification - PS 23.2.27
label | Verifying Document - Site Records
label | Frequency - Each Ground Mounted Sign
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 16.02 Pavement Markings
checkpoint | Surplus Chip Removal
label | Acceptance / Conformance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Prior to Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | High Performance Marking
label | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified.
label | Standard / Specification - PS 23.3.1
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Roadmarking Removal
label | Acceptance / Conformance Criteria - All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide. The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Removed marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Raised Pavement Markers
label | Acceptance / Conformance Criteria - These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Edge Marker Posts:
label | Acceptance / Conformance Criteria - Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings.
label | Standard / Specification - PS 23.3.2
label | Verifying Document - Site Records
label | Frequency - Each Marking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Coloured Surfacing
label | Acceptance / Conformance Criteria - Coloured surfacing shall be laid in accordance with the requirements of NZTA P33.
label | Standard / Specification - PS 23.3.2, PS 23.4
label | Verifying Document - Site Records
label | Frequency - Each Application
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
section | 16.03 Long-life Road Markings
checkpoint | Mark out the Contract Works with Engineer
label | Acceptance / Conformance Criteria - The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site.
label | Standard / Specification - PS 23.5.9
label | Verifying Document - Markout Records
label | Frequency - 5 Working Day notice prior to mark out
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Applicator, Marking System, Marking Format and Applicator Crew Trial
label | Acceptance / Conformance Criteria - The trial shall be completed using the applicator(s), marking system(s), marking format and crew approved for the contract works. The Contractor shall give the Engineer 5 Working Day notice of the date for the trial(s). Installation shall commence only if the Engineer is satisfied with the trial result(s). Verbal acceptance will be given to the Contractor immediately after the trial with written confirmation to follow.
label | Standard / Specification - PS 23.5.11
label | Verifying Document - Trail Results
label | Frequency - Prior to Installation
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Inspection and Measuring During Installation
label | Acceptance / Conformance Criteria - The Contractor shall inspect the long-life road marking against dimensional and installation tolerances as installation progresses. The Contractor shall on a daily frequency complete a Daily Quality Assurance Form (Thermoplastic and CAP respectively). The form records the material data, environmental conditions, etc.
label | Standard / Specification - PS 23.5.13, PS 23.5.15
label | Verifying Document - Daily Quality Assurance Form
label | Frequency - During installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Inspection Post Installation
label | Acceptance / Conformance Criteria - Formal visual drive over inspections. The visual inspection shall include An initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor of the first 25 to 50km per type of roadmarking installed (approximately 5 to 7 days of installation). The inspection shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Subsequent visual inspections by the Engineer and the Contractor shall be jointly carried out of a sample of the contract works.
label | Standard / Specification - PS 23.5.16
label | Verifying Document - Report
label | Frequency - Minimum of 20% of the total contract works will be inspected per type of roadmarking
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Monitoring Post Installation
label | Acceptance / Conformance Criteria - The Engineer and the Contractor shall agree on representative sites for ongoing monitoring. Monitoring sites shall be 2 per 100km of edge-line per roadmarking type. Three sets of monitoring shall be carried out First monitoring following installation of all contract works. The monitoring shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Second monitoring approximately six months after the first monitoring. The Engineer may waive the monitoring if they are satisfied with the performance of the markings based on the first monitoring. Third monitoring prior the issue of Final Completion Certificate.
label | Standard / Specification - PS 23.5.17
label | Verifying Document - Report
label | Frequency - 2 per 100km of edge-line per roadmarking type
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 16.04 Safety Barriers
checkpoint | Ground profile
label | Acceptance / Conformance Criteria - The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Site Records
label | Frequency - Prior to post installation
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Installation Notice
label | Acceptance / Conformance Criteria - The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Notice
label | Frequency - Prior to Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Guardrail Alignment Visual Inspection
label | Acceptance / Conformance Criteria - The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Site Records
label | Frequency - When erected but before posts are permanently fixed
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | Guard Rail and End Post Installation Checksheets
label | Acceptance / Conformance Criteria - The Contractor shall submit a completed and signed installation check sheet for each terminal and guardrail section installed to the Engineer for acceptance
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Checksheets
label | Frequency - Upon completion of the Guardrail Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Galvanising Repair
label | Acceptance / Conformance Criteria - After assembly, any areas of the galvanised coating that have been damaged or show signs of deterioration shall be wire brushed and washed to thoroughly clean down to fresh zinc or parent metal. They shall then be spot painted with two brush coats of un-thinned approved zinc rich paint the first coat being applied to a dry surface immediately after cleaning.
label | Standard / Specification - PS 23.6 M23
label | Verifying Document - Site Records
label | Frequency - Where Required
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | 16.05 Safe Lane Delineators
checkpoint | Safe Lane Delineator Installation
label | Acceptance / Conformance Criteria - The safe lane delineators are to be installed in accordance with the manufacturer’s specification unless otherwise directed in the Contract Drawings.
label | Standard / Specification - PS 23.7
label | Verifying Document - Site Records
label | Frequency - Post Installation
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
checkpoint | Chemset Safe Lane Delineator
label | Acceptance / Conformance Criteria - Where detailed in the Contract Drawings the Contractor shall excavate a 300mm x 300mm diameter hole and ensure all loose debris is removed from the hole. The hole shall be back filled with 20MPa concrete and the safe lane delineator is to be chemset in place. The concrete shall be level with the existing surfacing around the hole and water shall drain away from the delineator.
label | Standard / Specification - PS 23.7
label | Verifying Document - Site Records
label | Frequency - Each Post
label | Verification Activity: Activity - S
label | Verification Activity: By - SE