## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Utilities ITP - 105 - Rev B | itp |  |  |  |  | ITP - Utilities ITP - 105 - Rev B
section | 17.01 Services
checkpoint | Existing Services
label | Acceptance / Conformance Criteria - The Contractor shall locate or arrange for the relevant service authority to locate existing services prior to commencing work in any area. Where a clash of services is identified the Contractor shall summit a proposal for overcoming the problem to the Engineer. The Contractor shall give service authorities reasonable notice when excavating within close proximity to their services.
label | Standard / Specification - PS 24.1.1
label | Verifying Document - Comms
label | Frequency - Prior to commencing work
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Private Services
label | Acceptance / Conformance Criteria - Any private services such as domestic water and power supplies, rural mailboxes etc., damaged by the Contractor’s operations shall be repaired at the Contractor’s expense. The Contractor shall keep disruptions to individual landowners/occupiers to the minimum practicable. The Contractor shall consult with all affected landowners/occupiers to arrange for a mutually acceptable time for works that will interrupt availability of services and to identify any special requirements for continuity of supply. Where there is a requirement for continuity of supply the Contractor shall take all reasonable measures necessary to satisfy the affected party’s requirements. Where possible at least 10 Working Days’ notice should be given before shutdowns.
label | Standard / Specification - PS 24.1.2
label | Verifying Document - Comms
label | Frequency - 10 Working Days’ notice should be given before shutdowns.
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | Service Connections
label | Acceptance / Conformance Criteria - The Contractor shall liaise with the appropriate service provider to coordinate connection of the new service into the existing service.
label | Standard / Specification - PS 24.1.3
label | Verifying Document - Comms
label | Frequency - Prior to connections
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 17.02 Locate and Pothole Services
checkpoint | Service Location
label | Acceptance / Conformance Criteria - All locations where connection to an existing pipe is proposed, the Contractor shall pothole and expose the pipe and level the crown. If an issue is identified from potholing, the Contractor shall notify the Engineer.
label | Standard / Specification - PS 24.2
label | Verifying Document - Potholing Record
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Service Clashes
label | Acceptance / Conformance Criteria - The Contractor shall notify the Engineer immediately of any service clashes identified and the Engineer will advise on how to proceed.
label | Standard / Specification - PS 24.2
label | Verifying Document - Notice
label | Frequency - Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Service Plans
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for obtaining all service plans and identifying all existing services on site, including potholing where required to confirm the exact location and depth.
label | Standard / Specification - PS 24.2
label | Verifying Document - Service Plans
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE