## Basecourse Construction
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1603A Waikare Gorge Descent Retaining Wall |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Basecourse Construction |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | C1603A WG Retain Wall TREC Work Methodology - SIGNED |  | Compliance with Work Instructions and Specifications
Detailed Location: C1603A - SH2 RS577 RP13.922
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Sub Base Signed off | H | All previous Activities completed & signed off before Placing base course | Prior to commencement | Document Review | Previous ITP completed | ITP - Subbase Construction | Site Engineer | CPS Engineer
2 | Survey Setout | H | Cross Fall and levels to tie in with pre-existing carriageway | Prior to commencement | Visual | Set out and levels agreed with CPS Engineer on site | Photo's | Site Engineer | CPS Engineer
3 | Material Compliance | M | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. | During construction, traceability of all materials delivered to site | Visual check, document review | Conforms to TNZ M/4 specification | Delivery Dockets / Records | Site Engineer
4 | Basecourse Construction | M | Basecourse Aggregate | 1 sample/10,000M3 or 1 per source stockpile. | PSD, Atterberg Limits, MDD, OMC and CBR | Comply with TNZ M/4 specification | Lab test result | Site Engineer
5 | Basecourse Construction | H | Degree of Compaction | 1 per 1000m2 staggered | NDM Lab Testing | Avg. >= 98% MDD and Min. >= 95% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
6 | Survey checks | H | Cross fall check Surface shape check | 1 per 20m staggered | Visual check & Measurement | No point of the surface shall vary more than 10mm over a 3m long straight edge | Photo's / QA records | Site Engineer | CPS Engineer
7 | Surface finish visual inspection | H | Surface finish check | Prior to sealing | Visual inspection by CPS Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping | Photo's | Site Engineer | CPS Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: