## ChipsealingEmulsion
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1603A Waikare Gorge Descent Retaining Wall |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Chip Sealing Reinstatement of Carriageway |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | C1603A WG Retain Wall TREC Work Methodology - SIGNED |  | Compliance with Work Instructions and Specifications
Detailed Location: C1603A - SH2 RS577 RP13.922
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Seal Design | H | Seal Design to be submitted by Contractor for review and approval by CPS | Prior to commencement | Document Review | Approval by CPS Engineer prior to activities commencing on site | Seal Design | Site Engineer | CPS Engineer
2 | Previous Lots Completed | H | All previous Lot ITPs - Basecourse Construction and/or Modified Basecourse completed & signed off before Chip sealing laying commences | Prior to commencement | Document Review | Previous ITP completed | ITPs - Basecourse Construction and/or Modified Basecourse | Site Engineer | CPS Engineer
3 | Survey Setout | H | Mark out the extent of the seal if not working to a kerb line. Square off edges to tie-in to existing pavement if encroachment is into wheel path. | Prior to commencement | Visual Inspection | Spray paint edge of seal lines | Sketch / Photo's | Site Engineer | CPS Engineer
4 | Survey Setout - spray runs | W | Determine spraying runs start/stop locations | Prior to commencement | Visual Inspection | Mark out on site | Sketch / Photo's | Site Engineer
5 | Material Compliance Bitumen | H | 1st or 2nd Coat Chip seal - Bitumen (Design dependent on season) | 1 test per bulk shipment or grade | IANZ Lab Testing | NZTA M01:2020 | Test Report | Site Engineer | CPS Engineer
6 | Material Compliance Sealing Chip | H | Sealing Chip Source Properties as per seal design | Prior to Delivery | IANZ Lab testing NZTA M/6 | NZTA M/6:2019 | Test Report | Site Engineer | CPS Engineer
7 | Chip seal - pre-seal Inspection | H | Pre-seal inspection | Each site | Site Measurements | Walk over site | CS-4060 Pre-Seal Checksheet, Photo's | Site Engineer | CPS Engineer
8 | Chip seal - bitumen temp | W | Record Bitumen temperature at time of spraying | Each sprayer load | Temperature of load using sprayer calibrated temperature probe. | Temp. appropriate to base emulsion and +/-5 degrees. IANZ calibrated probe | Subcontractor QA Records | Site Engineer
9 | Chip seal - bitume app rate | W | Bitumen application rate each spray run to be determined on the day dependent on conditions by sealing supervisor | Each spray run | Measure by calibrated dipstick reading | Current E/2 Certificate +/- 4% per Spray Run | Subcontractor QA Records | Site Engineer
10 | Trafficking/Rolling | W | Details of roller type, etc please | After completion of sealing, rolling. 24 hour trafficking post rolling | Visual Inspection | Walk over site | Photo's | Site Engineer
11 | Post sealing inspection | H | CPS Engineer to carry out inspection and check the bitumen is completely bonded to the sealing chips. (No stripping) | At Completion of Chip sealing, for each site | Visual inspection | Walk over site | Photo's | Site Engineer | CPS Engineer
12 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Lab Testing Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA/Procore | Test Reports, Lab Tests | Site Engineer
13 |  | W | A complete set of subcontractors QA to be included in QA file | At completion of Lot | Document Review | Check all subcontractor QA records | Subcontractor QA Records | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: