## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction | itp |  |  |  |  | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction | f2874e3e-d6e4-4b93-9b52-60e0c58a929c
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Sub Base Signed off
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All previous Activities completed & signed off before Placing base course
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Previous ITP completed
label | Records - ITP - Subbase Construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cross Fall and levels to tie in with pre-existing carriageway
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Set out and levels agreed with CPS Engineer on site
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile.
label | Frequency - During construction, traceability of all materials delivered to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check, document review
label | Conformance Criteria - Conforms to TNZ M/4 specification
label | Records - Delivery Dockets / Records
checkpoint | 4 - Basecourse Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Basecourse Aggregate
label | Frequency - 1 sample/10,000M3 or 1 per source stockpile.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - PSD, Atterberg Limits, MDD, OMC and CBR
label | Conformance Criteria - Comply with TNZ M/4 specification
label | Records - Lab test result
checkpoint | 5 - Basecourse Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction
label | Frequency - 1 per 1000m2 staggered
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Survey checks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cross fall check. Surface shape check.
label | Frequency - 1 per 20m staggered
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check & Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - Photo's / QA records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway | itp |  |  |  |  | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway | b2a4f3ca-28dc-473a-93ab-0a0e4511bb8c
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Seal Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Seal Design to be submitted by Contractor for review and approval by CPS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Approval by CPS Engineer prior to activities commencing on site
label | Records - Seal Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Previous Lots Completed
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All previous Lot ITPs - Basecourse Construction and/or Modified Basecourse completed & signed off before Chip sealing laying commences
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Previous ITP completed
label | Records - ITPs - Basecourse Construction and/or Modified Basecourse
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Mark out the extent of the seal if not working to a kerb line. Square off edges to tie-in to existing pavement if encroachment is into wheel path.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Spray paint edge of seal lines
label | Records - Sketch / Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout - spray runs
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Determine spraying runs start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Mark out on site
label | Records - Sketch / Photo's
checkpoint | 5 - Material Compliance Bitumen
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 1st or 2nd Coat Chip seal - Bitumen (Design dependent on season)
label | Frequency - 1 test per bulk shipment or grade
label | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab Testing
label | Conformance Criteria - NZTA M01:2020
label | Records - Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance Sealing Chip
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Sealing Chip Source Properties as per seal design
label | Frequency - Prior to Delivery
label | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab testing NZTA M/6
label | Conformance Criteria - NZTA M/6:2019
label | Records - Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Chip seal - pre-seal Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pre-seal inspection
label | Frequency - Each site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Walk over site
label | Records - CS-4060 Pre-Seal Checksheet, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Chip seal - bitumen temp
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Record Bitumen temperature at time of spraying
label | Frequency - Each sprayer load
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature of load using sprayer calibrated temperature probe.
label | Conformance Criteria - Temp. appropriate to base emulsion and +/-5 degrees. IANZ calibrated probe
label | Records - Subcontractor QA Records
checkpoint | 9 - Chip seal - bitume app rate
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bitumen application rate each spray run to be determined on the day dependent on conditions by sealing supervisor
label | Frequency - Each spray run
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure by calibrated dipstick reading
label | Conformance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
label | Records - Subcontractor QA Records
checkpoint | 10 - Trafficking/Rolling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of roller type, etc please
label | Frequency - After completion of sealing, rolling. 24 hour trafficking post rolling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Walk over site
label | Records - Photo's
checkpoint | 11 - Post sealing inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to carry out inspection and check the bitumen is completely bonded to the sealing chips. (No stripping)
label | Frequency - At Completion of Chip sealing, for each site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Walk over site
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Lab Testing Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | Records - Test Reports, Lab Tests
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A complete set of subcontractors QA to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Check all subcontractor QA records
label | Records - Subcontractor QA Records
checklist | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair | itp |  |  |  |  | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair | 603ba293-9bd7-4ac8-9b04-134dbc4a3749
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Dimensions and Setting Out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Dimensions of concrete breakout on bridge deck must be agreed with the CPS Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Dimensions at top deck and deck soffit agreed upon
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Materials
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor must provide a list of all proposed repair construction materials with any technical data sheets available for each material for CPS Engineer approval.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - List of all materials and technical data sheets
label | Records - Materials list, Data sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Concrete break out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to inspect the areas broken out to inspect surface edge preparation
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - 45° taper cut on all 4 edges, no damage to existing reinforcement and shear cleat.
label | Records - Photos, Site visit record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Concrete break out
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Exposed and accessible (top and bottom) reinforcing steel must be power tool cleaned to SSPC SP3 standard. Other areas cleaned to SSPC SP2 standard
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - SSPC SP3 and SP2 standard.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - HD10 longitudinal bars to comply to design
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure all new and existing reinforcement bars are coated with a cement-based polymer modified coating material containing silica fume. Ensure all surfaces are fully coated
label | Records - Photos
checkpoint | 6 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Straight bars
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - HD10 hooked straight bars, crs 150mm, to form closed loop with hooked bent bar, embedded minimum 150mm, distance between 45° breakout face to be between 20-30mm
label | Records - Photos
checkpoint | 7 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bent bars
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - HD10 hooked bent bars, crs 150mm, to form closed loop with hooked straight bar, embedded minimum 150mm with chemset, distance between 45° breakout face to be between 20-30mm
label | Records - Photos
checkpoint | 8 - Reinforcing bars
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to inspect placement of reinforcing steel after it is fixed in position
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Hooked bars tied with 2mm wire as per construction drawings
label | Records - CS-4040 Concrete Inspection Record & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to inspect formwork before casting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Forms must have sufficient rigidity and strength to prevent distortion due to pressure from the concrete. Formwork to remain in place until concrete reaches a compressive strength of 30MPa
label | Records - CS-4040 Concrete Inspection Record & Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Pre-pour inspection
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure exposed concrete edges are free from dust and loose particles
label | Records - Concrete pre-pour checklist, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to witness casting of concrete deck repair
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - All concrete used in deck repair must be in compliance with T-CES 101. Surface finish in accordance with NZS 3114. Deck top surface - U3. Exposed soffit of deck - F5.
label | Records - Concrete pre-pour checklist, Photos
checkpoint | 12 - Concrete casting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Contractor to provide minimum of 9 concrete cubes for laboratory material compressive testing
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Minimum compressive strength of:
label | ○ 25MPa (1 days)
label | ○ 50MPa (28 days)
label | – Patchroc C (Fosroc) or equivalent should be used.
label | – All concrete supplied shall comply with NZS 3109
label | Records -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Concrete curing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Curing
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Contractor to provide details of the proposed measures intended to protect the concrete during curing
label | Records - Proposed Methods
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Concrete curing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prior to resurfacing, CPS Engineer to inspect the newly cast deck repair and make the decision whether crack injection is required
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Crack injection required if crack between newly cast concrete and existing deck exceeds 0.3mm. Sealant strip will be applied instead of crack injection
label | Records - Photos prior and after sealant
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Reinstate surfacing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Road surfacing reinstated to be consistent with rest of deck surfacing (Grade 3/5 racked in Chipseal). Contractor to provide methodology for resurfacing
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Methodology, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Completion Sign-off
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of works, Site Engineer to inspect works to confirm it is completed to required standard for sign off
label | Frequency - At completion of works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Signatures from Site and CPS Engineers
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 18 - Completion Sign Off From Fields Below
label | Records - Completion Sign Off From Fields Below