## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction | itp |  |  |  |  | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Sub Base Signed off
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All previous Activities completed & signed off before Placing base course
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Previous ITP completed
label | Records - ITP - Subbase Construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cross Fall and levels to tie in with pre-existing carriageway
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Set out and levels agreed with CPS Engineer on site
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile.
label | Frequency - During construction, traceability of all materials delivered to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check, document review
label | Conformance Criteria - Conforms to TNZ M/4 specification
label | Records - Delivery Dockets / Records
checkpoint | 4 - Basecourse Construction
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Basecourse Aggregate
label | Frequency - 1 sample/10,000M3 or 1 per source stockpile.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - PSD, Atterberg Limits, MDD, OMC and CBR
label | Conformance Criteria - Comply with TNZ M/4 specification
label | Records - Lab test result
checkpoint | 5 - Basecourse Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction
label | Frequency - 1 per 1000m2 staggered
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Survey checks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cross fall check. Surface shape check.
label | Frequency - 1 per 20m staggered
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check & Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - Photo's / QA records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT