## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway | itp |  |  |  |  | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Seal Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Seal Design to be submitted by Contractor for review and approval by CPS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Approval by CPS Engineer prior to activities commencing on site
label | Records - Seal Design
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Previous Lots Completed
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All previous Lot ITPs - Basecourse Construction and/or Modified Basecourse completed & signed off before Chip sealing laying commences
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Previous ITP completed
label | Records - ITPs - Basecourse Construction and/or Modified Basecourse
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Mark out the extent of the seal if not working to a kerb line. Square off edges to tie-in to existing pavement if encroachment is into wheel path.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Spray paint edge of seal lines
label | Records - Sketch / Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout - spray runs
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Determine spraying runs start/stop locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Mark out on site
label | Records - Sketch / Photo's
checkpoint | 5 - Material Compliance Bitumen
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - 1st or 2nd Coat Chip seal - Bitumen (Design dependent on season)
label | Frequency - 1 test per bulk shipment or grade
label | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab Testing
label | Conformance Criteria - NZTA M01:2020
label | Records - Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance Sealing Chip
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Sealing Chip Source Properties as per seal design
label | Frequency - Prior to Delivery
label | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab testing NZTA M/6
label | Conformance Criteria - NZTA M/6:2019
label | Records - Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Chip seal - pre-seal Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Pre-seal inspection
label | Frequency - Each site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Walk over site
label | Records - CS-4060 Pre-Seal Checksheet, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Chip seal - bitumen temp
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Record Bitumen temperature at time of spraying
label | Frequency - Each sprayer load
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature of load using sprayer calibrated temperature probe.
label | Conformance Criteria - Temp. appropriate to base emulsion and +/-5 degrees. IANZ calibrated probe
label | Records - Subcontractor QA Records
checkpoint | 9 - Chip seal - bitume app rate
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bitumen application rate each spray run to be determined on the day dependent on conditions by sealing supervisor
label | Frequency - Each spray run
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure by calibrated dipstick reading
label | Conformance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
label | Records - Subcontractor QA Records
checkpoint | 10 - Trafficking/Rolling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of roller type, etc please
label | Frequency - After completion of sealing, rolling. 24 hour trafficking post rolling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Walk over site
label | Records - Photo's
checkpoint | 11 - Post sealing inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to carry out inspection and check the bitumen is completely bonded to the sealing chips. (No stripping)
label | Frequency - At Completion of Chip sealing, for each site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Walk over site
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Lab Testing Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | Records - Test Reports, Lab Tests
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A complete set of subcontractors QA to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Check all subcontractor QA records
label | Records - Subcontractor QA Records