## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 004 Earthworks Cut |  |  |  |  | Yes | ITP 004 Earthworks Cut | 46bb3171-5048-4e01-ba74-7b262ae04ed8
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.01 - Approved CWP
label | b9b05130-21d0-59f5-81b8-3a1a66ee3588 |  | note | Method/Description - Document Review
label | cca29099-c6de-57fd-ae2f-5ea7651289fd |  | note | Test frequency - Prior to personal starting
label | 4905a6bb-47b9-5612-ae3f-f47e06a3b0f0 |  | note | Constructor - H
label | 1f5798a0-6591-5954-918a-aee49800be2c |  | note | Verifying Records - signed off CWP
checkpoint-status |  |  | checkpoint | 1.02 - IFC issued
label | 24af5ac5-dc0f-5572-9f8f-f968599806a2 |  | note | Method/Description - Document Review
label | d029f256-64c1-5d38-8894-c6b955988ec4 |  | note | Test frequency - Prior to starting
label | 9ccc7c7c-c593-53c9-9870-a2b85c4ac74e |  | note | Constructor - H
label | 72f7fbe8-8bd4-59ac-ac7e-03030dbfa37b |  | note | Verifying Records - IFC drawings or written approval from PAB
checkpoint-status |  |  | checkpoint | 1.03 - Approved SCWMP
label | 0f4c9061-2d18-5631-8ae0-0ec860083288 |  | note | Method/Description - Document Review
label | a327f40c-0cc6-5dcc-a5dd-6af44d88cad3 |  | note | Test frequency - Once prior to works commencing
label | e23ce9b7-d559-5ade-84ab-75a9ecf1e255 |  | note | Constructor - H
label | 3080528e-d0ce-5ac5-86cf-2503bbfaeec7 |  | note | Verifying Records - Approved SCWMP
checkpoint-group |  |  | section | 2.0 During Construction
checkpoint-status |  |  | checkpoint | 2.01 - Set out extents
label | 103bcb86-e5f6-5c01-af96-35bd1d9e7fee |  | note | Method/Description - Survey/visual
label | 262daded-4c81-56e9-8f2d-3e49f5dff431 |  | note | Test frequency - Prior to Commencement
label | 1ea47dec-8e81-5dcb-a913-446cacda69f8 |  | note | Constructor - H
label | deb203b7-5718-5616-9630-a1d5c9b53cb4 |  | note | Verifying Records - Earthworks Cut Checklist dsr reports
checkpoint-status |  |  | checkpoint | 2.02 - Verify Machine Control
label | 1eb179e8-4c86-5fa2-9225-acc058072e50 |  | note | Method/Description - Survey/visual
label | ff8ab6ca-fe21-580e-91cd-305bc4ec1caa |  | note | Test frequency - Daily
label | 0bd6ade8-f046-5723-bd0b-cff871f84ada |  | note | Constructor - W
label | 81b1d103-1a86-5f80-98b9-ade368456739 |  | note | Verifying Records - Plant Pre Starts
checkpoint-status |  |  | checkpoint | 2.03 - Assess Crest detail
label | f3ac45c9-18de-5552-a055-bfe70ec804e4 |  | note | Method/Description - Hand augers/ slope assess
label | b75a31c8-d7b1-5a3f-9647-11984d4d8ef7 |  | note | Test frequency - Prior to Excavation
label | d2943094-13b2-5e7a-a39e-0717e6228ecc |  | note | Constructor - H
label | 5cbe8ddb-a41b-53d1-8cde-c352d85b9596 |  | note | Designer - H
label | bafc3aed-08c4-5976-9598-1264d363e6e2 |  | note | Verifying Records - Earthworks Cut Checklist dsr reports
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04.01 - Install crest detail: Soil Nailing
label | adac4e33-95b4-5458-9ce8-697f3b3b7dbc |  | note | Method/Description - Visual Inspection
label | d9512120-644e-57a0-b43a-c5e04cd770db |  | note | Test frequency - Prior to cutting rock slope
label | 84f258ea-3834-54e0-8cbd-ed1f3850922c |  | note | Constructor - H
label | a3a10b54-2402-59ce-bb85-8f6c786ccc34 |  | note | Designer - H
label | 8aa35759-d24a-5aaa-a711-b1cb733df60c |  | note | Verifying Records - Sub Contractor QA Records
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.04.02 - Install crest detail: Erosion Matting
label | d57b4711-e40c-53cf-8d1b-f0876f8d9957 |  | note | Method/Description - Visual Inspection
label | 95465785-0b13-5703-9136-61773491d56b |  | note | Test frequency - Prior to cutting rock slope
label | 93f1b126-b28e-5388-a0bc-f4e064b993de |  | note | Constructor - H
label | c5badbe0-bac7-5e2b-93aa-25331a045951 |  | note | Designer - W
label | 5778f670-eae3-5fd7-bc03-4203a0c7e7ca |  | note | Verifying Records - Sub Contractor QA Records
checkpoint-status |  |  | checkpoint | 2.05 - Cut Face inspection: Cut Face inspection
label | acfa0d9c-0bcd-515d-a750-0c97ef4b5f5a |  | note | Method/Description - Survey check by construction team, visual inspection by designer.
label | 31f04f6c-d015-5817-98c6-d1fe5971b4ce |  | note | Test frequency - 100m2 or maximum 5m vertical cut
label | 41ae2613-b497-5a9d-a029-654d7e2bd51d |  | note | Constructor - H
label | 59fc9c46-102d-5bb7-a357-2a09a166aedf |  | note | Verifying Records - Earthworks Cut Checklist, Survey record, As-built
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.06 - Cut Face inspection: Cut face material verification - Geo mapping
label | 4d6bb129-d861-5f8e-81d3-dc1f94ac6fee |  | note | Method/Description - Geo inspection and face mapping
label | a8b16777-a627-5be9-9840-c87648cdc4cf |  | note | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | f226a919-790e-56f6-8c3b-36bbcf89b915 |  | note | Constructor - H
label | 056b5fad-0b37-52be-a52d-471442da127d |  | note | Designer - H
label | 5b8b5c68-2bae-5e3c-824e-c2b2f5d84c39 |  | note | Verifying Records - Earthworks Cut Checklist dsr reports, And face map from geotechnical engineer/geologist
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.07 - Install Rock Drape: Set out drape anchorages
label | 5183685a-f9a1-54de-b5a8-55d252383bd4 |  | note | Method/Description - Geo walk over
label | 2265fabb-5f12-543f-974b-43bbd5ab3478 |  | note | Test frequency - Prior to drilling
label | 8fb6da51-6d90-5d71-8c95-1facf5504a92 |  | note | Constructor - H
label | b3d8e1dc-497b-5d87-acbe-02ca013aa778 |  | note | Designer - H
label | 0cdcf132-3e26-5085-8ea2-a1f512f388e8 |  | note | Verifying Records - Sub Contractor QA Records
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.08 - Install Rock Drape: Install anchors
label | c5eb9fb5-a4ec-5c94-b7dc-4604772bf060 |  | note | Method/Description - Drill and grout records. Stressing records.
label | dfa0837c-37da-5a6d-8c65-32929a1f1296 |  | note | Test frequency - During construction and at end
label | 6ae8403c-b05a-5a44-b2a3-25561d0b3959 |  | note | Constructor - H
label | 8258a11a-e5cc-52de-97d0-f25ba8a92110 |  | note | Designer - H
label | ebacc7f3-1f60-5c72-8025-72696e0ca23a |  | note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.09 - Install Rock Drape: Install Drapes
label | fc21ffbb-bd96-598a-96b1-6db9e1946805 |  | note | Method/Description - Visual inspection
label | 8072ffbf-0279-5439-9379-5d52e34ff66b |  | note | Test frequency - During construction and at end
label | de624760-9f81-522a-9b58-c0003f7f368e |  | note | Constructor - H
label | bdff8204-3322-5084-8aab-73333ca33573 |  | note | Designer - H
label | 4cf2dc7d-1a23-5873-981a-c1c24b4001d4 |  | note | Verifying Records - Sub Contractor QA Records
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1 - Install Rock Bolts
label | 87b32ff1-a65e-5141-bc7f-05d8afa61fe4 |  | note | Method/Description - Drill and grout records. Stressing records.
label | c40dcf3d-f43c-5a07-92ef-f797e8f4187b |  | note | Test frequency - During construction and at end
label | 2c83b556-60d1-58ed-ae76-55188c239b0f |  | note | Constructor - H
label | 4d079ed6-1e69-5da2-ac1b-b1da20dea177 |  | note | Designer - H
label | 9ee04451-2404-5d7e-90b8-340826f2ec8a |  | note | Verifying Records - Sub Contractor QA Records. Calibration certificates for stressing equipment.
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Catch Ditch Inspection
label | 00e58ffe-037b-545d-bace-5b883e0647b3 |  | note | Method/Description - Visual inspection
label | 750aae21-4e55-55ee-95d8-d2214481286c |  | note | Test frequency - During construction and at end
label | 38c24efb-1c17-5bfc-8867-5830c39a3cdb |  | note | Constructor - W
label | 1b2daf5e-43d3-523f-9929-d91a9a0cbfdc |  | note | Designer - H
label | 49901b71-e92f-5910-92b8-f91214a6bb2b |  | note | Verifying Records - EarthworksCut Checklist
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | 3.0 Post Construction
checkpoint-status |  |  | checkpoint | 3.01 - Rock Fall Test
label | 01881ecd-5f95-53d8-9234-8808dd9fbc0a |  | note | Method/Description - Visual inspection
label | f6e238b7-83bb-57db-8393-f9fd6e598922 |  | note | Test frequency - After catch ditch is formed at each rock cutting site
label | 20517f6f-4dc0-53d7-b6cc-bda6897dc3a5 |  | note | Constructor - H
label | b50f0b20-1e92-5d53-b575-7fa220612f21 |  | note | Designer - H
label | c8176c17-9c21-5b7c-830f-603325d44830 |  | note | Verifying Records - Designer assessment Memo
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.02 - Survey As-builts
label | 96e8f962-2b54-5686-b51d-3c930ba3629b |  | note | Method/Description - Survey As-built
label | adec30b1-222c-5cca-9b84-a8fff78f3ce7 |  | note | Test frequency - During construction and at end
label | 696c0ab2-add1-5162-a27c-a6be042143f9 |  | note | Constructor - H
label | d0445372-fb8a-58cc-a492-62a96ba38b50 |  | note | Verifying Records - Digital file
checkpoint-status |  |  | checkpoint | 3.03 - Monitoring Data
label | a4a65e69-72d3-54bd-bff7-c79b0236a9e3 |  | note | Method/Description - Visual inspection and review of monitoring data review.
label | 849a4e4b-61b2-5118-bf7b-39abb9f6c1c8 |  | note | Test frequency - End of construction
label | 3bcde90b-3f05-5b5a-b4d3-04605f0478fa |  | note | Constructor - H
label | 3e6bdc87-1ffa-51a4-b7e2-789510c68974 |  | note | Designer - H
label | 5204e30e-6e3d-59f7-8aaa-6c8263b29352 |  | note | Verifying Records - Digital file
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Red Line Mark Ups
label | ba02192f-3b0c-5b84-a1cd-58a1b7a4a369 |  | note | Method/Description - Red Pen Mark up
label | b040b799-4cd0-5bc0-984a-70a0dc98eace |  | note | Test frequency - End of construction
label | cdedf424-4590-5f49-a9f5-e4f800f21a12 |  | note | Constructor - H
label | 8c2ed140-05e6-564e-84d1-1868fec32d9d |  | note | Designer - W
label | ed08f1da-48e6-5d19-83b3-e1012293eca4 |  | note | Verifying Records - Red Pen mark ups
checklist-sectioned |  |  | checklist | ITP 001 Cableway Works | itp |  |  |  | Yes | ITP 001 Cableway Works | e9c79f31-8943-4eb9-b1e2-74bcc4a27366
checkpoint-group |  |  | section | Construction - Earthworks
checkpoint-status |  |  | checkpoint | 3.1. Removal of Topsoil and Vegetation
label | f446cf7b-05ab-5495-b466-d0e3f249c2b2 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | ec3ddf8c-a3c9-52f8-8775-6d2cca7e1bfa |  | note | • Drawings
label | cac61a98-1105-52b7-8330-64b1c149b435 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | be59532d-0bce-5d68-a579-86de718394d0 |  | note | • Confirm when topsoil and vegetation stop
label | fd443fef-f2fa-5125-a828-8a3f9f1f1c29 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | ca7b77a7-17eb-5284-9e68-c6070efbe9aa |  | note | • Visual Checks
label | c6cb625f-26e7-5493-9885-07b84061c5f5 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 28d53178-2f58-5162-b80d-5635e3d0af6f |  | note | • Ongoing
label | 7164c0f2-90aa-505e-aa41-e419fcf72d86 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | ede6a507-f4b6-5208-97b5-5af4aeac3162 |  | note | • I
label | 2ec9688f-0f10-5bbb-89cc-2c906031f137 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 3d5d285e-29dc-5daa-a838-a987095bfe17 |  | note | • PE
label | a2f07ebc-f767-5e05-8044-56b1eff727d1 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 776b06e8-64a2-5150-9dc5-cd04b81dd42f |  | note | • N/A
checkpoint-status |  |  | checkpoint | 3.2. ESC Measures
label | 4d4ffe01-b599-5b6b-82b6-824b347e03a7 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 82292996-b39c-5ed4-a138-b810503877a0 |  | note | • ESCP
label | 8bad29e3-4d28-5493-bc0a-8b544875b442 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | a30b8b7b-d84a-5844-a587-ed0c3ffa6d47 |  | note | • Environmental controls to be installed as per ESCP prior to removal of topsoil
label | 93f53a88-385a-54cb-9546-4521a3c6e60b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | baa5ed11-4caa-55bc-8af3-5bd3a312b479 |  | note | • Visual Checks
label | 9dc30442-9ae1-5f90-9128-052248c5b8b1 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | bfa81637-972e-51ea-b882-71d5ec2e5d09 |  | note | • Ongoing
label | 4cde16de-d88d-5bfd-b964-527759515c17 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 2b931c43-0234-57fc-af3d-50e0cc58101a |  | note | • I
label | 4bbebaee-9383-5324-81ae-ed66caee389f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 21f20ff1-be2f-5168-a121-46e8abd20700 |  | note | • PE
label | 327ea502-e626-5cd3-a9a0-34daa5fab716 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 152632e1-ec83-5423-9f93-15f4c4abd00b |  | note | • N/A
checkpoint-status |  |  | checkpoint | 3.3. Cut to Waste – Bulk earthworks removal
label | 0510bb34-6df4-5870-abc2-89ccc0403d62 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 9c193eba-96de-54d4-9cfd-ed4fa5e1e486 |  | note | • Drawing
label | 4419470d-b4f2-5f20-b5d5-1a66505409c5 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 27f704c8-9c2f-569d-ad98-860f1bc6dd5a |  | note | • Level of cut matches drawings
label | 4286bfef-2f98-5c8d-90e9-c0151e943636 |  | note | • Global Position of cuts
label | 2fab4e7a-a63a-59c0-81c7-cd2d0decab8a |  | note | • Inspection by MSQA
label | a101317d-a0f7-542d-a4c3-edd010a4e5b0 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c49f0e1c-f813-5234-9b6f-6e0739b07e5f |  | note | • Survey Checks
label | 5e0d5509-497e-5e6d-94d6-319756479af2 |  | note | • Survey Checks
label | 8c09e4f8-fbcf-503c-b199-d7c00108b718 |  | note | • Visual Inspection
label | 1d66461a-ac73-5e07-bf97-0e5dbf767e3d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 72f9bf49-645c-5327-9ac2-1732b2da362a |  | note | • Daily
label | 5262752c-8f0c-5cc8-bbb4-beb1f3735c5a |  | note | • Daily
label | 75520e72-e460-5cfb-8583-dc2516cbbf52 |  | note | • 3 x visit per location
label | a05d2171-63cf-589a-8700-718a8cded3b8 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | eb19f1cc-37ea-5378-b2ec-0593f107c724 |  | note | • I
label | 45572226-71db-5e36-9629-5b05bce0eced |  | note | • I
label | b940d53d-0a6f-5ef4-9bcc-99d8b8e8c167 |  | note | • H
label | 2460b0db-4b5e-530e-9a99-fb65d15b0c6e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 9d6c1ef6-d405-5b4b-8a40-889aae36dfcd |  | note | • PE
label | 3f88913a-2237-5d6f-a898-90c98f633c5a |  | note | • PE
label | e460ac10-0540-5e72-8032-8f75dc3f0660 |  | note | • MSQA/DSR
label | 45d7d401-1fa1-5a4c-9d94-910ad6b6e783 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 7c1e5d85-5363-5c79-88b1-8d58082e778c |  | note | • Survey Records, As Built (3a)
label | 52f748fe-7bd2-5df8-9ad9-48659fefbc66 |  | note | • Survey Records, As Built, 3D mapping to be provided (3b)
label | b6dfe628-0696-5d97-a540-c23c13ff339c |  | note | • Site Report (3c)
label | a1c53a01-c8d3-5e0f-a010-ae4aedde5508 |  | note | CERTIFIED COMPLETE (DATE, RELEVANT CHECKLIST TITLE/LAB REPORT NUMBER ETC):
label | 82369f8f-e107-54a5-b4a9-72301c63afa5 |  | note | • 3a No details received
label | bd803e80-891b-538b-83d9-8cdb241614e0 |  | note | • 3b No details received
label | d078bc43-14b4-5371-8d99-6d40d8c17934 |  | note | • 3c Tower Site – 13/10/22 Three site reports uploaded for Tower Site. NAB – 1 site report unloaded – missing two reports. SAB – missing 3 reports
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 3.4. Install Fill Retaining Area (North Anchor Block only)
label | 840a6f4e-0865-5376-9ed4-d869c2acda83 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | a37abe55-c354-5eae-8953-bdd1442b7205 |  | note | • Temp works design
label | f7ff324d-6507-5178-83fa-3bf2bd551a42 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 90e3fe80-68e6-5ab9-b243-dec4d653ca1d |  | note | • Level and Position
label | 043a4502-27b6-5a30-9ac4-f2db912fb991 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 5e7daf55-28a1-5d7c-8fe4-d5dbcebc706f |  | note | • Survey Checks
label | 4abcb998-7f41-56e1-a4a4-363a101e8366 |  | note | • Visual Checks
label | 1740af0e-2138-569b-9cf9-080baf8ba77b |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 61454d78-ea80-5e74-846b-15bdd8c4b7be |  | note | • Each Temp works
label | a73b3217-fa40-5fcc-b8d9-20054ba77a6a |  | note | • Daily
label | 00e50aa8-482b-5895-a0cc-205550e5eb9a |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 088757b5-4143-5eb5-8a05-524e45d4d9e1 |  | note | • W
label | fb2ef8bb-a07a-5f36-b6d6-62eba00575f8 |  | note | • H
label | ba5a3fdd-2817-53c4-8335-a93692b4d48c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b9ef9355-211f-53cf-a356-223417b31981 |  | note | • PE
label | 5c162536-dca0-59b9-901e-831b66d85f98 |  | note | • PE
label | 6d575111-72a8-586f-933c-36605f13e4cd |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 6d45613a-bb68-5f34-b156-58bdc7b2d1c1 |  | note | • N/A
label | acbf9c61-30e4-5fdf-92b8-5270aebc6b65 |  | note | • Temp works sign off
checkpoint-status |  |  | checkpoint | 3.5. Cut Access Track (South Anchor Block)
label | 0296bd65-109e-5d79-b43e-b4009a94f08c |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | a12a652b-0f65-5cb0-8fa9-9f57231899b3 |  | note | • Temp works design
label | aab5b90c-c035-5999-92eb-d1b5213888bc |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | d9742b39-3681-5a5b-8d54-bfdf52b656b1 |  | note | • Level and Position
label | d69fab44-7e58-5638-bd1f-ebffa08a1c12 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 020df4c0-11a8-51d2-a117-53a4a05b47f0 |  | note | • Survey Checks
label | e7ecf537-f50f-5644-bc27-70d23628939d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 21e30579-e39a-527c-a516-1e0da9178352 |  | note | • Each Temp works
label | f1a916d3-4afa-5783-b1b9-3db7e7e5fe8f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 8985f5ca-a61b-5372-ad05-c61547e5bdde |  | note | • W
label | d4326e56-ca63-5431-b4c2-6936bc93cc82 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 481b3d24-3215-5ccf-aae1-67394e8c29eb |  | note | • PE
label | 14678cf9-b4a9-5e8b-9c08-6c45f8e29346 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | a6cd570a-5685-55f3-b313-c872e93774d1 |  | note | • Survey Record
checkpoint-status |  |  | checkpoint | 3.6. Trim to Grade (Compound Only)
label | 3ee56e6b-42c2-5339-8748-879019ed37b0 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | f501d13f-57af-52f6-b501-c5860e0719b0 |  | note | • As required
label | e590f687-6a3c-58ec-83fd-9d7e7c2d4495 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 2058ee40-5d46-5f4e-940c-223f46af7195 |  | note | • Grade to control water
label | e5025be0-b307-5e95-99e8-6c22f692732b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c1d4efff-4179-5e33-8780-97d947731499 |  | note | • Survey Checks
label | 7b973601-3e06-52eb-b452-6624a3d50ff7 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 9702a9bc-2888-5a6b-9092-dac49f0e4e16 |  | note | • Daily
label | f6951156-71aa-5b0e-b76c-dfccfcf34119 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 376a2884-bd16-59b6-9979-9238d964fce8 |  | note | • W
label | e05ef43e-4a01-5008-b875-d5ea0bc83558 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 04535899-7df2-56bf-af7d-db315fe74ae5 |  | note | • PE
label | 9d28e230-8b83-53f2-8f3a-cc6c155ac7dc |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 94a96841-0e6a-5b30-8ef0-5f93887a3fc8 |  | note | • Survey Record
checkpoint-group |  |  | section | Structures - Piling Works incl Micro Piles (Central Tower Only)
checkpoint-status |  |  | checkpoint | 4.1. Set Out Piles
label | afbd161d-f768-56a1-a6f4-8a258594fab8 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 8fe47ac2-b682-5cd1-87eb-b0e34e56cd9d |  | note | • Drawings and Survey Model
label | 97026ff4-3e7a-5d16-b8f9-237a5c6679fa |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 194ac4fd-8e04-5d74-b6e6-be0e13778478 |  | note | • Position and Depth
label | eeccdd2c-6a6c-520c-9057-2d3d5087f2f1 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 3dc1eb25-1611-543a-8e4e-50cd5dcc0b9f |  | note | • Survey
label | 0eae9148-16b2-56d2-904a-f1649d4c9a9b |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 24664740-5fc9-5a15-bf27-68086cf75d01 |  | note | • All Piles
label | e6fbd6e6-0e6a-57ad-b708-82ca60820dd3 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 69b9c6b2-90bb-53e5-87ac-9fd51ff7ebe4 |  | note | • I
label | a7f71cae-cad6-5195-8a30-3f1565a36c29 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 10de8b3f-31a9-5787-b03e-55bd6891d1a3 |  | note | • PE
label | 1fe6e74d-0dba-5d6d-9735-dec1fef67ae1 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 9291c85b-437a-5819-96fa-c513e9eff3a3 |  | note | • Pile Record Sheet
checkpoint-status |  |  | checkpoint | 4.2. Drill Piles
label | 23798a48-4725-5c1f-bab3-6deebb12d0f9 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 4d4abece-2e3c-5c6f-b4c0-049b4ee53daa |  | note | • Drawings & Spec (TBI)
label | 8aefd90a-16e1-5fab-a300-b52b85776714 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 627500fa-3900-55b6-adf8-cdf8b5384bfa |  | note | • Piles drilled to set and/or required depth as per design drawings. Location within +/-75mm. Verticality of 1 in 75
label | 67baab02-bfe7-5953-b897-fd184199ccd2 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | d20076ca-01cf-5084-8d3a-ca7cb10e6f88 |  | note | • Visual Inspection
label | 939c8ee2-4718-5f89-9c24-b8d1c08d5f7d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 4660e484-2661-5bac-ae09-95d6611551d8 |  | note | • All Piles
label | 91a4fa9e-0f18-5e78-a76f-fa80826199ad |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 3dd45958-dbaf-59f2-b481-833edab21acb |  | note | • H
label | 8f6e01f8-f9f6-5903-95d0-3e11d0c09ac8 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 371dea6e-2f33-5dbd-9e39-597b19897d06 |  | note | • PE, MSQA/DSR
label | a4f06133-2cee-5617-875e-a350359f65b1 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | b4f136b3-bb67-5879-9b2e-3e4f9e038ec7 |  | note | • Pile Record Sheet, Site Report
checkpoint-status |  |  | checkpoint | 4.3. Inspection of ground conditions
label | 9fd8ea15-13d6-5181-be4d-9267f218548a |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 363d7832-a943-553f-b6dd-5526bcaa32dd |  | note | • Drawings
label | cdd3dd28-50c4-5826-91f9-b3934e53104b |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 8caf943f-be91-5ad0-8825-b2ef5bad38a4 |  | note | • Confirm as expected
label | e20e554f-2918-5536-a85d-7800fc2d0a67 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 066469dc-3222-55b1-a97f-79b11c01962f |  | note | • Visual Inspection
label | 098c7633-e6e8-5391-84cb-b8adedf5f6c3 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 3c202d14-908f-56c1-8da8-0880ef639ec5 |  | note | • 1st Pile
label | 7b92fd7f-a11f-5acd-a930-5020f9a73b14 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | bc11ca72-c34e-5270-bd06-3105af2dc58e |  | note | • H
label | 3151e508-6076-5614-9787-8c1a844506ce |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b5c0489e-7a77-5f88-8951-875812f435fe |  | note | • MSQA/DSR
label | 0caf3356-58e2-57d0-bb0b-58fb6abb2564 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 80a34909-005c-564a-8953-9dde1fa82232 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 4.4. As-built
label | e9a13268-54f3-5368-8269-b9c81f1062b3 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | c78357ca-bad1-5361-a2b4-d12da5e22572 |  | note | • Drawings & Spec (To be issued)
label | b3bb51d0-1c9d-5f2c-b8ce-be8c99631899 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | f50155e3-b1a9-5b0c-b4ea-a55a2e572385 |  | note | • Cut off level correct for follow on connections.
label | d2cc34b6-1aef-5321-b06f-481df0fe3702 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | be933e2c-b74f-546b-b3ef-5a01e0dffd8b |  | note | • Survey
label | 09da8206-34ad-50db-b635-72b5f604388b |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | a0a5becf-062a-5308-8f16-dfd366665215 |  | note | • Once per pile
label | fd7c7df7-1b93-5615-84a7-617e11edd34b |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 9cdc8855-81a3-59a9-b90e-90dde8f01b6d |  | note | • I
label | cd2cd197-569d-5db0-a18d-e3cc9a4e3d65 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 965fad1b-6a56-5389-81b0-41c5df8986e2 |  | note | • PE
label | de74877c-cc93-544c-bfb9-e9692d42a6c0 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 513e6ee2-5918-5ef7-b24c-3afd002a43d2 |  | note | • As built, Pile Record
checkpoint-status |  |  | checkpoint | 4.5. Install Reinforcement
label | 736e31ac-9d22-5666-ace3-d1caa58396ed |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d5995795-2ee3-5220-8459-28ee4dccd01e |  | note | • Drawings & Spec (To be issued)
label | 9f622647-52eb-5ecf-abca-e258e6ba3b95 |  | note | • NZS3101 & NZS3109
label | b10b0c7b-72cd-5c6a-8f2b-f8524e272045 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 78caa8ef-cb4f-5e9f-b176-9858e56dde53 |  | note | • Reinforcement is fixed to design of IFC Drawing. Correct reinforcement used that is not damaged.
label | 15d2ebbf-6a27-5a9c-b745-23f136700ffb |  | note | • All cover block/wheels installed to achieve minimum 50mm cover.
label | 8fd03d2c-0c7a-52ca-8931-52c4a5c48049 |  | note | • Confirm all reinforcement matches drawings
label | 18a79500-5aac-51bf-bf99-be7507a4f890 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | f8bc78cc-04f0-51f4-9842-1469aa65f0f2 |  | note | • Visual inspections
label | 5593e5d4-47bb-55ec-aca3-8cb4bfc8fbd9 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 23a931eb-b7b3-5378-8151-25be5c2ddb47 |  | note | • Each reinforced cage
label | f255343c-5431-5746-95f5-bc5b16c0a62f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 84dc1d8d-3110-5fc5-9e0b-3707717dc738 |  | note | • I
label | 4d93497c-e78a-541b-ac0c-d278298f99b9 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 6c6afb15-71a1-5151-93db-3aabe0895b8c |  | note | • PE
label | 5634a5b8-6036-5e74-b48c-b9512eb7e4fa |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | a0b0b318-81ec-5b54-aa86-0e4d5af72341 |  | note | • Concrete Pour Inspection Check sheet, As built
checkpoint-status |  |  | checkpoint | 4.6. Pre-Pour MSQA Inspection
label | 991448a5-f7c4-518b-a6c9-fda7e9c71929 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 7ee8aa61-5039-55a9-ba07-9d63d8da4b85 |  | note | • Drawings
label | d7a9aaeb-772f-587d-9341-abf3f525ad06 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 3578c6a9-aba9-5255-9012-73b304e4e96b |  | note | • All above is as drawings
label | c2dd6fe0-b977-5bb1-8f64-98c46fdfa496 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 30a37170-aa7e-58e5-b22b-0d13e716705c |  | note | • Visual
label | b9b43c83-0fa1-5d58-88af-a21cc4c3f0fc |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 69b1aaad-2261-5799-9fb1-77993cb15767 |  | note | • All Piles
label | b04585fc-de7c-529e-82ad-1a1c4c657330 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 20c19885-3067-54d5-9155-b15cffa3bfb1 |  | note | • H
label | b18626a4-fc1f-5d66-97a1-772c797800a1 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | fe8bfa77-f048-5b10-9005-8caba3e4b7ec |  | note | • PE, MSQA/DSR
label | 8cfb0014-4d79-50c6-8cc0-221b19e0512e |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 743327f1-b7f1-5649-9030-6312cc88b551 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 4.7. Concrete supply
label | 032d7ce1-446c-5bcd-9bdb-73aea61448dc |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 198c326d-a8df-55cd-b082-80cc54a1765e |  | note | • Drawings & Project Spec
label | a3a3a402-9b0a-576d-a8d1-e6f233ecdec2 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 3a3d029f-44e3-5c15-bdc9-dd3f1df2dbb4 |  | note | • Request a minimum of 3no cylinder test on all structural items, 7 day, 28day.
label | 9df9431d-e8f7-518f-abf7-f371eadf0235 |  | note | • Concrete cures to strength (40MPa).
label | b177ec3d-f8b7-5e16-aa9c-d5297962f6ee |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | dd300bb5-a65f-56a5-8af9-1d02cf1f9d8b |  | note | • Concrete sampling and cylinder crushing
label | 20e582b9-3497-5c0b-afd2-ed5639635744 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | df076d07-f9be-5c33-9f53-fa9cb5b69cb7 |  | note | • Each Pour (or 1no set every 75m3)
label | 39a3ae16-6e8d-5027-834a-210c838d75e6 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 6bb38144-a861-547e-b547-a088a83527b7 |  | note | • R
label | bbaf2431-6888-5d4b-b583-a54c097ce530 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 8b1d2888-4a38-5c93-b83a-297e33f88380 |  | note | • PE, MSQA/DSR, Lab
label | d974aa5a-dce8-56f0-b26e-6dad36f11747 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 3aac9b27-c56a-54ea-af54-d89c1dcbefe1 |  | note | • Concrete Test Result Register, Compressive crush lab test results
checkpoint-status |  |  | checkpoint | 4.8. Concrete Finish
label | 47ccefd2-e8da-5149-b0d7-8f25ba2bbc82 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | b6b84316-eb9b-57cf-80b3-f457094a344f |  | note | • Drawings & Project Spec
label | a80583c2-b41a-52b7-8ae4-fbe4521fcda6 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 05e35909-663a-536d-a71e-b6a5c66f70a6 |  | note | • As per drawing request, type B joint on top
label | f9296017-8b0e-5aa0-8c3e-4f0344ec24fd |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | d30945b0-ae45-5f1c-89c5-32998430dabb |  | note | • Visual
label | 026b379a-9404-5aec-b923-f44daa7732b5 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 0a758f03-9a78-5023-9fad-2b528e3e777f |  | note | • Each joint
label | cf8ac7ec-7d07-5b45-a3da-0676f517c3b9 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 86775a06-2d8f-5601-b1b0-74897bf471c8 |  | note | • I
label | 1706c6fe-4e77-5b21-befc-532b4e15e919 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 50a6ab0d-b797-5b6d-82bb-b570d7b224b9 |  | note | • PE
label | ec2ac623-2268-5e7a-a985-d935bafb15ea |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 9b187eee-9f51-5a22-a3c3-9ffecd673250 |  | note | • Post-pour inspection record.
checkpoint-group |  |  | section | Structures - Formwork and Steel Fixing (NAB, SAB, Central Tower Footings, misc)
checkpoint-status |  |  | checkpoint | 5.1. Install Footings for Temp Works
label | e268598c-e2c3-5ceb-aae7-1c74d25d0420 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | bb25648b-a534-5151-8012-d635744a7d70 |  | note | • As per Drawings
label | 82ae4e69-304f-5a15-aeea-a204ee1b2eaa |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 071d7c61-b8ba-5c0f-aac8-0fb82a5d0255 |  | note | • As per the formwork design
label | 835099f4-04a2-5773-a60b-d9c2e5b90c8c |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 5aadcd3e-6c6c-547c-b039-ae591594d07f |  | note | • Level Check by Engineer
label | a37b9509-747d-55ce-bd6e-9624718682ea |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 85be25e4-2789-5a6b-b76a-3e10c7723d90 |  | note | • Per Element
label | aef767e7-d43a-56ac-adf3-c8cb984f9bea |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | f9d38607-21fd-5b5d-a7b0-4a98281f9216 |  | note | • W
label | 29378c0f-47a1-5d40-bdb4-1ad2c64be667 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | d28460d2-f230-50f7-b78c-5116c0ecd58c |  | note | • PE
label | bc3c2cf0-9a96-5533-a86b-4cf3b4686d56 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 43302cf0-dc16-5977-9414-dd20f968c0d1 |  | note | • Concrete Pour Inspection Check sheet
checkpoint-status |  |  | checkpoint | 5.2. Install Blinding
label | c72f13d6-eb54-58fe-a99f-48afe95305b4 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 68be54f4-b071-58d1-bf7d-f7d5ba7cdad4 |  | note | • As per Drawings
label | c8e891e7-8b36-5e2a-9bfd-0da017c7bcf3 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 87490d91-9d31-5c52-a23f-8ace31786cce |  | note | • Blinding thickness and level to be as per drawings/required
label | 158fe809-1428-595a-9786-bb86b16a3443 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 983e1c19-1c1c-5015-8276-c5b04bb49f2d |  | note | • Level Check by Engineer
label | cd9ee49f-7b64-554e-bad3-28a6474caa41 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | c5d2add7-5a41-52e2-84cf-cceb93925b56 |  | note | • Per Element
label | f8a92c6b-1453-59b9-bdcd-fc702dcccdad |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 1277f853-ad06-5633-ae23-888008f6c7bf |  | note | • W
label | 9e30256f-7c23-59d6-ac83-9cdbf1b1d30c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 1acdf262-91dc-5312-9337-0c0105214596 |  | note | • PE
label | cc287c50-55b6-5772-bbc6-0e3d91dc7547 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 33413fbc-0a66-57fa-b08a-6fcf28067d7b |  | note | • Concrete Pour Inspection Check sheet
checkpoint-status |  |  | checkpoint | 5.3. Formwork Placement
label | 437ac288-5afc-50e0-b536-17e189957f66 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 99c7903d-4f94-52e4-b0bb-0f4097005717 |  | note | • Drawings & Spec (To be issued)
label | b17009a4-2672-5b40-bfb3-8cebee5a6517 |  | note | • Formshore Temp Works
label | 7c24b5ee-aa45-5c1f-b32e-2e98994409c5 |  | note | • Doppelmayr Drawings
label | d55a4a42-32d2-58ac-92f1-2f524bef6a65 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | c8c24328-58a1-54fc-b6b8-e0484ecdb83f |  | note | • Formwork as per temporary works drawing if relevant.
label | 5cb74200-be5f-5997-a786-25fa0a162793 |  | note | • Position, orientation, dimensions checked.
label | 9eb9126b-690a-5345-9613-c6adb9a32e14 |  | note | • Oiled, Area cleaned of all debris, Cover correct as per spec and drawing requirements.
label | 01f1f0de-5894-5181-a35f-03ab37d6cefc |  | note | • All inserts inserted, block outs, dross backs, bolt clusters etc See temporary works design.
label | 87193310-b343-5bf7-a740-3a7dc30a38de |  | note | • Confirm any inserts are included as per drawings.
label | 08bd278d-4ff4-59e8-bd57-858c914160f6 |  | note | • Ground anchor drossbachs critical – placement takes precedent over all over items.
label | a0254689-ac92-5c2a-96e3-b961893d7fce |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c38c96e1-577c-56eb-8ed8-b672a6e0a46e |  | note | • Onsite Visual Inspection
label | f5b60228-a58f-5ff8-9ac8-cf88ac9a9f27 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | f4779be4-9e3e-516e-a49c-6c1a3d28ab38 |  | note | • Per Element
label | 6f3df709-1078-59a2-9843-d3a50b60f224 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 8bf2f972-9d4d-50af-8faf-b21a1b6eb074 |  | note | • I, R, H
label | 706351bd-ad7e-5519-a309-823eaac3bd86 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 89bea273-9eb6-5926-b1de-3a07caaa3dc0 |  | note | • PE
label | 1ff3a2cd-bd8f-577e-b76c-c5ff172cce42 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 872e5186-1874-57c2-b18e-31e7f214d8ae |  | note | • Concrete Pour Inspection Check sheet Photographic evidence, Survey Checks pre pour
checkpoint-status |  |  | checkpoint | 5.4. Earthing
label | 179068e3-2a4c-5050-ad92-ec72211b74d2 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 13ac616b-7696-5169-8129-1e49a73a9baf |  | note | • As per requirements
label | 85882a9c-8e2a-50e1-b886-37a4d15a627b |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | cd199acf-4057-5037-a5ef-8681a188eee1 |  | note | • Each concrete element TO BE ELECTRICALLY GROUNDED BY AN APPROPRIATELY QUALIFIED CONTRACTOR.
label | acda63c9-56d5-5be3-8d16-7565bb53496b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 08cb715d-9cd4-509c-b48d-2a0d46bcef54 |  | note | • Visual Inspection
label | b073c7e5-2c9b-53ca-a309-f878fbac87c2 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | a82b1937-9954-53c7-9d88-932ce82ccd9c |  | note | • Per element
label | 18275b99-0739-5687-9ab8-9eb8932ac79e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 34a046d1-a132-521f-bdbc-592560056b69 |  | note | • H
label | 9c407851-ae51-5cfc-b76b-3dd07870deee |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | fdb4f05b-c02f-5ecd-bd26-e39d88ddcc97 |  | note | • PE
label | ddda06e8-5cb8-5cfe-a748-5e7c766e3f8d |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 05f189fe-7ab9-53d0-a43d-3490a4320d9b |  | note | • Report, Photo
checkpoint-status |  |  | checkpoint | 5.5. Reinforcement Placement
label | 1f93b989-a739-528d-8023-8891866d3b48 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 80c1e902-229c-525c-b0a2-8e419db5ab09 |  | note | • Drawings & Spec (To be issued)
label | 692a076a-a433-556c-9562-e4df13363127 |  | note | • NZS3101 & NZS3109
label | 287cba95-828d-5278-ac58-e7bf89bb2130 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 72145de4-044e-5cfe-885d-540a4693bf9d |  | note | • Reinforcement as per relevant design IFC and standards NZS3101 & NZS3109
label | abb37c2a-9c09-5a4b-bcf4-f4f74ae8ce97 |  | note | • Grade, number, diameter, spacing, starters, cover, welds, lap length and position all checked.
label | 25452442-36f6-57cb-9122-c39da4f29266 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | ec69c584-4d8f-5989-bc6f-dc8946ccda1a |  | note | • Visual Inspection
label | ad63d122-cc30-5ff5-a30e-5f8ad3829f4e |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | b91d0cd9-51be-58a5-83a6-44d90f0518e6 |  | note | • Per Element
label | eb3461ef-4443-5a38-bcdb-df653a36a894 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 2d4a55ad-5626-538c-acac-c33926da3252 |  | note | • I, W
label | dfde7c5e-ba22-503e-8a3b-643a9d99db44 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 1925c479-78a4-5962-9205-9085d2d4db75 |  | note | • PE
label | 7e1660f8-6df3-5f43-96a2-b5286df89802 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 60c4c56e-2ebd-59e9-9b10-2621c4f4f2fd |  | note | • Concrete Pour Inspection Check sheet, Photos taken and stored in QA File
checkpoint-status |  |  | checkpoint | 5.6. Cableway SAB/NAB Williams bolts
label | ff63ea0e-7e74-5f2c-a77c-43f6a0f24795 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 962de1da-1433-5d3d-a61f-cd6041eb3ece |  | note | • IFC Drawings
label | 57f40c0d-70fe-5905-ac38-e555e703df6a |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | dc5ef26c-ed66-5a76-8288-e1c95df3a4f9 |  | note | • Size, length and position of the bolts to be as per the design
label | cc07cdc5-1168-58d7-942e-3d44a7d83eae |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 4c890d17-0612-54d3-828e-728f104c6f91 |  | note | • Visual Inspection
label | 4a060cbc-fbc2-52b4-9781-427a7115ceb9 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 58e64bad-afdc-5b60-9c53-067af7178010 |  | note | • Per bolt
label | fdcbbf4c-45da-5e28-ab77-50f9436daeec |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 3285f756-ade8-510a-8336-231ddbf8178c |  | note | • H
label | 1688a166-2562-5e6b-b431-3f1b2881e9f3 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | d2fd7f3e-b593-54a9-bddf-93cc5f3bc1b8 |  | note | • PE, MSQA/DSR
label | 06da6a19-9a5d-5ca1-b329-6267a070662d |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 7c609c0a-d5d6-5b01-9849-d723f3d59bf7 |  | note | • As-built
checkpoint-status |  |  | checkpoint | 5.7. MSQA Pre Pour Inspection
label | f0fd00fb-f614-5bbb-b393-5b5b8768392e |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | a83e7a70-62e2-5295-8ce9-9da4aa279e1d |  | note | • Drawings
label | efad27e3-2ea5-50f4-a82a-058d8b48909e |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 947a35c4-de07-5f19-b012-130c823a44a2 |  | note | • Confirmation of all above, reinforcement, dimensions, inserts, finish
label | 10fa8e6b-d2bb-5993-8a1c-4daa73cff85b |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 78173002-645c-536b-8426-a8122f654340 |  | note | • Visual Inspection
label | ba33cce6-9010-5b7b-ba1f-97e9287fab3a |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 784da88f-3073-5688-9a83-756703e08c69 |  | note | • Per Element, Holmes provided 48hour notice to inspect.
label | b5f0f3a2-00f0-5d66-9cb0-7c8ef865f1e2 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | ebab0b2e-59c5-549c-90f8-cdc2e10a46a2 |  | note | • H
label | 26a37a1e-52d5-520d-aec8-b51f5472d824 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | f231e42e-ffbd-59aa-a6e5-a4da3ca8a72b |  | note | • PE, MSQA/DSR
label | 2f5e6ec7-a01f-5927-9409-922dd3abce84 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 970e3e1b-8f11-5d65-bcd0-a61cf8fc12fb |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-group |  |  | section | Structures - Concreting
checkpoint-status |  |  | checkpoint | 6.1. Concrete Delivery
label | c1789aed-752d-5bd2-9fa8-7f6e26d8479f |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 8cff6ca9-ffdd-5437-b8b5-2a4359cf00c2 |  | note | • Drawings & Project Spec
label | d962de97-cf50-5705-a665-8e17438dfcff |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 62afc40b-0f17-5ff5-bb22-7999bc82e126 |  | note | • Supply to match design drawings and specification.
label | e0aa8a2a-87df-59e2-8ff9-ea57e8e474a7 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 6a69ce40-44bc-53f1-84ea-afd0ec0dc72f |  | note | • Docket Checked on site for correct Concrete type.
label | b53c6379-44c6-5099-8dbf-41193b98a1a8 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | f65ab9f7-5d30-5c47-8b31-968d1642a461 |  | note | • Per Element / Per Pour (minimum)
label | 13efd765-8cb9-531c-8620-601999e3dc04 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | df44e847-1b76-597c-bc87-656e923b49c0 |  | note | • W
label | 730b32f6-7cff-505d-80e2-6714b3809052 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b104134c-07a2-5880-808a-52b36bbbc7bf |  | note | • PE, Lab
label | cd96dd29-ebb3-5952-8104-2132e6d3e597 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | dab9479b-0ce8-524b-b236-d6bccd38b201 |  | note | • Concrete Pour Inspection Check sheet
label | 9229eca3-4676-51db-88bd-2336528a83db |  | note | • Concrete Test Result Register
label | 165fd99d-4e22-5d87-a174-3a99b38aecdf |  | note | • Docket checked onsite/Filed
checkpoint-status |  |  | checkpoint | 6.2. Concrete Finish
label | 7a43dcd1-75b4-58d0-a1c8-31083ef43fdf |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | c1b9ac54-cfa1-5a7e-8eba-39300a951b7c |  | note | • Drawings & Project Spec
label | e513370a-78e7-5dff-b612-c8af62b68437 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 800cd600-a0f6-5089-88f9-d5b618bbfb18 |  | note | • Concrete finish to be as per on drawing, U1-5 or F1-5 (inline with relevant NZS standard 3109 and NZS3101)
label | eba79f05-f6ff-5c2b-9281-c9c2fdfa9520 |  | note | • Concrete checked for any cracks and other irregularities.
label | 79d65d07-b94c-5148-bf68-cac3093a321a |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 10986c05-633c-5bf6-8b4a-698ed892af64 |  | note | • Visual
label | 4fc0f5a8-612b-5ae8-a2b4-bdf32fadaa41 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 84d13530-4021-596b-98f4-d027207f78f5 |  | note | • Per Element
label | 01768efc-f44b-5d12-9e99-961b35ab1c09 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | dac6bf88-0de5-5b72-aaff-97e40cea1409 |  | note | • W
label | 8b2daeee-6ec1-59a7-ba98-3379c9a69a32 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 83c92c0b-9e13-50ec-8712-9941cc778619 |  | note | • PE
label | b3482b89-e1f9-5e36-b7f5-ad24cba35ff3 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | dc5a2134-8e17-5e5a-bf5c-f2f79bfe507e |  | note | • Concrete Pour Inspection Check sheet
label | 68e6f27d-a7a8-524c-80fa-5988171d0177 |  | note | • Photographic evidence
checkpoint-status |  |  | checkpoint | 6.3. Concrete Strength
label | b59f4473-1956-55cd-ac57-24b6f3691f8a |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | dc6b6518-9f1a-5aa9-8839-2b15f5a56822 |  | note | • Drawings & Project Spec
label | 92dafc3b-8539-5339-be15-199674041e7d |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | ef077e8a-cf7d-5140-94ee-665f8390ecd6 |  | note | • Compressive strength results to match design drawings and specification.
label | b2f17c9b-9fa9-50f1-ae14-d8b764a37cd0 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c3bee8e5-931b-5614-a3f7-e78fdc3a6344 |  | note | • Review of 7day and 28day strength results.
label | 7664085e-0ad9-5afe-a6fa-1fdaba8509c1 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 0b714584-2c8f-5d11-b77e-403ce9fc0157 |  | note | • Per Pour (minimum) or 1no set of 7day, 2no 28days taken for every 50m3 +
label | c5f245c8-9d07-5904-bd60-784439c78566 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | c1bcadb9-0fd0-54d5-8331-0a9e949952cf |  | note | • R
label | 307741a8-14fa-5925-89d9-63ff64446687 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b27a237e-75af-5171-9f91-296b4ba3dbb5 |  | note | • PE, Lab
label | 4b931d97-7f7b-5ea7-8599-ce3a17ef1bcb |  | note | • (MSQA/DSR)
label | d086303c-227c-5c34-bbfd-905145ed4553 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | ababe297-35e5-5845-b376-00c7e0d6daf8 |  | note | • Concrete Test Result Register
label | a2af986b-60a0-528b-8d8e-91a8d95d47f5 |  | note | • Compressive Strength Results.
checkpoint-status |  |  | checkpoint | 6.4. Construction Joint Creation – Type B
label | 66fa461a-3d7e-56b8-995f-b8b2d3185212 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 446dd4fc-c6e1-5c73-a3d4-0ee194655a1a |  | note | • Drawings & Project Spec
label | 3ae21d96-bfbe-508d-aafc-f9dc50922111 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 46b15712-0fe5-59a6-a7e1-2a8c3cd88c0d |  | note | • Construction Joint type B
label | 18993b11-2616-5315-b18c-9df955876458 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 0b49efa0-006f-529b-bdd5-933bd8b8d5f9 |  | note | • Visual
label | d53ea45a-2cf9-5bc3-9019-358c9f0ab8ba |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 6ee674f2-54c6-56cf-8499-4fcfcbeae9c2 |  | note | • Per joint
label | 35d68d67-fed2-5471-856e-111861476888 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 46d89852-b12c-5cd8-b425-96072bb58693 |  | note | • H
label | 70be5109-b57d-5b10-b483-479a8c628905 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | f7e42152-a1ac-516e-bddc-e4c434018461 |  | note | • PE, MSQA/DSR
label | d836dfec-aae4-52b3-bc7e-042c200a6571 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 2bdeed45-c32f-50f0-b4de-9a2bd7f66bf5 |  | note | • Prepour inspection
checkpoint-status |  |  | checkpoint | 6.5. Curing
label | b517d131-5c90-5b25-a0af-b3bd124b86f8 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 329c82e7-812c-53ea-a1f4-52017db87883 |  | note | • Drawings & Project Spec
label | 3f42da58-24ba-5053-b817-0cd15d173600 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 53ab0f8c-55e8-5770-a9bb-3227b010a6b0 |  | note | • Wet curing method or As per approved alternative curing method
label | d9d062a7-326b-5d2c-87fe-7cee618ea746 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 13ca13bf-6159-50eb-9bf6-48ee31032e40 |  | note | • Approved curing method
label | 4d6cee37-7ac7-53e5-a701-9a4f16e1dc8c |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | b113d2a5-5382-5092-9574-cee6cf655f15 |  | note | • Per Element
label | 0246f6ef-db3d-5ef1-b95d-1fc109622a54 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 4ddb561c-8deb-58a6-bd7f-23b17f7a7aaf |  | note | • W
label | 60082181-85ea-5b99-a2df-be1336333d5f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 136683cc-bc55-5fad-bff9-a67cebfd377b |  | note | • PE
label | fd3d84a4-e80c-5a67-a689-90c5ccc3d029 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | c624afa2-78cb-5343-b8a3-f018d67c10f6 |  | note | • Concrete Pour Inspection Check sheet
checkpoint-group |  |  | section | Structures - Anchor Install (NAB & SAB)
checkpoint-status |  |  | checkpoint | 7.1. Drill Anchor Hole
label | 2aef55d4-79c5-5e33-ad1a-fe0d8053e229 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | b8a43414-7851-5480-9cfd-59d504cba5d5 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 08cc91ff-fb7f-5e83-9ebb-e191a750e09b |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 78ef6b86-200b-5f0e-acbe-0ce2797c349b |  | note | • Inclination angle of anchor 13deg North & South
label | 5bd92697-5430-521f-bacc-0172863d0fcb |  | note | • 4no Anchors at each anchor block – 2 contingences if required
label | d69ac742-df60-5202-896e-92d53d4d00a4 |  | note | • Length – 18m North (TBC), 15m South
label | 5452b269-354a-515d-bd76-272f78102aa6 |  | note | • Tolerance on drilling angle is ±2° both horizontal and vertical.
label | 247f4b9d-45f7-535c-b2da-f703f4aec4d2 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | c2e39778-54fd-5b6f-a57c-66104d497e46 |  | note | • Onsite Checks by Engineer
label | d3e17edf-011c-5b8c-9127-6405ef350076 |  | note | • Inspection by MSQA Checker
label | b9af2402-6f96-534c-8898-3dbe54e66d4e |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 30ae3177-9f5e-5af8-8aa7-db1fae16a78b |  | note | • All Anchors
label | d24ad75d-751a-530c-ade6-f493333b6800 |  | note | • One Anchor per anchor block
label | f0dc9fc8-b844-58e3-b1b3-20ded3a2e637 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 866c0e5f-b2b6-528e-8580-fdedf2dcc53e |  | note | • W
label | e4163eb5-36d9-5da5-9e01-e4c34d10516b |  | note | • H
label | eedc747f-62d5-5dfa-a31c-224f8ae10da1 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 817e8c47-282b-5b7c-bfbe-42fd7f566035 |  | note | • PE
label | c9cff728-416c-56c7-8160-ee88358f808c |  | note | • MSQA/DSR
label | d260c863-57d8-5c03-a5bb-2f0c1340670a |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 6d75ec59-5e93-5bf5-b96e-e8ac193c89f2 |  | note | • Drill Log/Anchor Install Check sheet
label | 78314b2c-ceb5-56ad-ad34-a4384f9863b5 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.2. Camera/Inspection of Drill Hole
label | f0380a49-1226-5222-99a3-c055a8755c42 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 84fafd66-469b-5dcc-9c39-d154c183da93 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | a5e8c377-2b55-5522-b1c7-79630308f069 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 7378136a-227e-5ca5-b3ea-973d539f7c3e |  | note | • Anchor to be open and clean of debris.
label | 2cce5180-9e36-5fa6-ad3a-12960324cff0 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 218f6e8f-6464-53fb-8ff2-c993bce8a696 |  | note | • Visual Inspection
label | fe7635e7-12a5-58fe-88f0-169f397358cc |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 89855936-c104-52d3-9ae7-f406c11233fe |  | note | • All Anchors
label | ac7c0fbb-16de-52fa-8d0c-225b8d13e5bc |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | d7478e24-e08b-580f-99e4-85a340a75dd8 |  | note | • W, R
label | 40031843-f9fe-56e0-b760-221ff7373e9c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | f8974acd-57c7-5c82-8f16-2fadfc9e97dd |  | note | • PE
label | f0718beb-3c24-5daf-ab2b-37e5ed7f9e5b |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 9cb75679-9c45-582f-9a30-535b4ee877fc |  | note | • Drill log/Anchor Install Check sheet, Video footage
checkpoint-status |  |  | checkpoint | 7.3. Install Anchor Tendon
label | d030f946-cd46-53bb-845c-e572b102ae58 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | dc02220b-5b59-5e4e-b3e2-5299a3909efd |  | note | • MMA-DES-GEO-E1-DRG-4081
label | adeff8fa-6893-5717-9a4b-c732627587cc |  | note | • BS 8081:2015+A2:2018
label | 0496b8c7-0cc8-5606-a86a-3d33295f49d3 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | ad16959f-a0ea-5183-872c-9c986a07e77d |  | note | • 11strand Anchor for North Anchor Block
label | f91b5c88-616a-5d69-9e10-241e65b21f6c |  | note | • 10strand anchor for South Anchor Block
label | 3354f77f-ac93-5936-9b8c-07bef61836bf |  | note | • Anchors to be installed with fixed length and free length indicated on drawings. Centralisers (internal and external) should be in accordance with manufacturer’s instructions.
label | c1bf3969-bcf4-5c2c-83c4-42895f691e26 |  | note | • Anchors to be kept clean and free of any detritus materials. Anchor strand stick-out to be sufficient for wedge removal during future maintenance/re-stressing.
label | 15697f23-09b7-5b97-b5af-e60c286b9737 |  | note | • Anchor corrosion protection in accordance with design drawings.
label | 43666071-6870-51f0-a598-44a44cf60cb4 |  | note | • The anchor head shall be protected with a galvanised end cap, fixed to the bearing plate and filled with grease.
label | 0de21082-e86f-5c15-b742-7905b82b8731 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | a3b7a33a-fb02-5c9b-964c-6b987b5aee92 |  | note | • Visual inspection
label | 37f022bd-7611-5747-a1f7-5901868de2c1 |  | note | • MSQA Inspection
label | d59f08ba-f147-57b5-8a2e-4656f125c264 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | c0266762-d75d-5094-9c37-67b4faf9e786 |  | note | • All Anchors
label | 15b87e7c-6eb2-5052-961c-1dd32b985056 |  | note | • One Anchor Per Block
label | 5b04035b-0b7c-59b5-907a-a411975d254e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 969bdf10-fe67-5d94-8218-6f61bc975539 |  | note | • W
label | b185fe54-749b-56cf-8f75-ea616383fc65 |  | note | • H
label | aa37b538-6bae-5aee-bf46-29c8ebbefded |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 28559f47-7550-5e89-8b8b-9ae9b64b15e7 |  | note | • PE
label | 94fd321d-8f1a-5015-b7f7-70002eeb3804 |  | note | • MSQA/DSR
label | 87af0cda-1e9f-5166-b764-6560d5ab172d |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 2e6bab53-3a6f-5f48-a363-f592a99bf104 |  | note | • Drilling log and Anchor install check sheet
label | 2e5218f9-fef7-5ca7-88f3-124fda7b23c4 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.4. Place Stage 1 Grout
label | cfd5d6b2-5d25-559d-b101-b02cc8d7c4e5 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d9ccfc7a-850e-543d-aff7-1b32eb6cf5d9 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 8a5b982a-205d-531a-a395-3fc2e970ee95 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 2daba3c6-44b2-5589-bc26-1ccb58744d54 |  | note | • Holes to be grouted within 3 hours of flushing hole/completion of drilling.
label | 631221a1-0709-5345-8604-42291bef2d51 |  | note | • Confirm 10m Bond Length grouted and top of grout is behind anchor block.
label | 51cc2083-34a1-5a0a-835e-f74d818ea09d |  | note | • Grout for anchorages to have 30 MPa compressive strength at 28 days and a maximum water/cement ratio of 0.45.
label | f6e35a24-3666-5f8e-b2aa-505427efd4e1 |  | note | • Grout shall not be used more than one hour after mixing.
label | c3968f41-c160-5fa3-89a2-cd4fcc482b09 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 9c2626c3-e7bc-54fa-94ab-f54120183447 |  | note | • MSQA Check
label | 7d9245bc-bfed-5ad2-9b8f-39a0a4cc049d |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | b4ff0389-6088-5d6f-8df3-6c9c1da9e829 |  | note | • One Anchor per anchor block
label | 8d935654-67dc-5a3b-8a81-54c64aa0f6c8 |  | note | • Take grout samples for each grout batch. Review laboratory documentation for all anchors
label | 0bc609bb-0fdd-5971-ac72-f620f519d508 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 9b989be8-9847-5f57-964f-6e21d638d0e4 |  | note | • W
label | 378cef99-2b3a-540f-9e63-6d7dba3faaa0 |  | note | • H
label | 0e7f7dbe-bf07-5ffa-a16d-b08aa41477aa |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | bdd32e71-7359-547b-9b48-06f2ddf7b7dd |  | note | • MSQA/DSR
label | eb4d06fa-1ee2-51b9-8ea0-2759d456319f |  | note | • MSQA/DSR, Lab
label | ff5a0662-7e06-5a77-8522-cac2e7e8462c |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 378a9a58-2148-5ef1-981c-4d0a848712dd |  | note | • Anchor install check sheet
label | d9eb75a2-855a-5c0e-b379-37badb8142d8 |  | note | • Photographic evidence of grout pouring
label | ccc2c777-e386-51ee-8025-12031ec33797 |  | note | • Grout strength results
label | fa6057fe-f5c5-54ec-963e-38a1923cddef |  | note | • Site Report
checkpoint-status |  |  | checkpoint | 7.5. Stressing Jack Calibration
label | b13cc457-6418-5af4-899c-9e2f3eb2c6bb |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d7cad1fb-9139-5a2f-ad0c-68f01dc3d6ea |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 67df6b19-334e-56a4-a1bb-d0e4ce5a4081 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 2c4ce277-193e-5c97-b7d8-9781c873255d |  | note | • All jacks and Pressure gauges used need to have current (within 12 months) calibration sheets.
label | 89a5906e-f6fa-5418-ab9a-2629bc18bbaf |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 707340ff-c3f4-5d50-9091-a97d618d3a79 |  | note | • Contractor to get calibration sheets from sub-contractor
label | 606df6f0-1adc-5958-a770-298fc210c086 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 686ce674-4c85-5423-aca4-0bb435c7a775 |  | note | • Once – prior to work starting
label | e0589f1d-d2f5-56d7-85af-6bc004a560cd |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 52e52f40-f0a7-5bc9-ad20-3d03cc6fe0a5 |  | note | • W
label | e9c22565-204a-5938-8a44-a10df4aea376 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b0bce8de-00d0-56ca-bdd5-c8b9df61265d |  | note | • PE, Lab
label | b37f39bc-eba1-5d6d-bb33-5ba24c0fbc97 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | acabf496-9621-5f6f-b91a-c0e50a0d5952 |  | note | • Photo graphic evidence, Anchor install check sheet
checkpoint-status |  |  | checkpoint | 7.6. Smart Cell installation
label | c587e0f0-0df7-56b3-aeab-9de7e33ce9ea |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 41636209-9b21-5c37-8ceb-f80ae6797563 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | b51ecf03-7be1-5f2e-b76d-fc9b194f4ac3 |  | note | • Manufacturer Instructions
label | 7528b220-0abb-5b3a-8a8f-b2f537f87dea |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | ff75d6e3-dad9-57a7-b98d-001dd04be76b |  | note | • Need to be appropriately installed and calibrated.
label | 77a646b8-defe-5d07-a66c-b1fed107335a |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 135bc391-c851-5155-84e3-6f6ab5dda88a |  | note | • Physical testing
label | 5b6dbd0e-92f7-599d-9330-39f608d9ee08 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 72472d8d-6bd1-56f8-bd83-b65226d19a63 |  | note | • Prior to working and after pre-load
label | 8bda275e-e5fb-57fa-b0b6-69ee10f9233e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 309aa66c-d656-5f38-a49b-109ca669d2bc |  | note | • W
label | 08928ec8-d72c-5c4a-ab29-5338cfffe03e |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 5c91c43a-150c-53ff-b021-62cfb705cfa6 |  | note | • PE, MSQA/DSR
label | 6f3d67c5-be0e-51f2-9cfa-47086a0a11c0 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | f3d9636b-9d9b-566d-926e-e722ef9e9d61 |  | note | • Contractor records.
label | d172d617-0c02-5d9f-9d80-d6cb6496668a |  | note | • Site diary.
checkpoint-status |  |  | checkpoint | 7.7. Stress and Lock off Anchor
label | 5906d67b-db74-5030-924b-e7785fc513a7 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 20b167d7-56e6-5821-8a52-98a5562f9f54 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 7dee3307-8a96-5919-9af9-f296449ad657 |  | note | • ISO 22477-5:2018
label | b97ceb95-a716-5404-9026-e0a98a2fd661 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 3de7c8a3-aaf6-504a-bce1-e717932444e0 |  | note | • Confirm RC block concrete and anchor grout have achieved a strength of minimum 30 Mpa.
label | 1c854980-d747-5deb-a7e4-9dff7408b35b |  | note | • All anchors shall be stressed and locked off at the lock off load shown on design drawing.
label | d1859baf-e3ef-5fe8-81b8-4ba521943633 |  | note | ○ Acceptance test Proof Loads:
label | e3105079-fea2-5529-baa8-a7eefb36d6e3 |  | note | – NAB -1500kN,
label | ff3528ad-3adf-51b8-aa57-3ed8ee14453b |  | note | – SAB – 1350kN
label | 87171c6b-ffc8-572c-8b89-ddab3970c13d |  | note | ○ Anchor Lock off loads:
label | 695e6527-c729-5eab-916c-2c1ce9cd095a |  | note | – NAB – 1350kN
label | 95d00891-4484-5565-8f25-79b96b11ee5a |  | note | – SAB – 1230kN
label | 3ed04603-4e2a-56ac-bf1f-0476a7112b61 |  | note | • All anchors to be acceptance tested in accordance with ISO 22477-5 and Table 2 of design drawing.
label | 63b0dac1-6b15-55ab-890a-ccb1c6d82315 |  | note | • If anchors pass acceptance criteria on design drawing (displacement, creep, and apparent tendon free length) they can be locked off. If fail these criteria must inform Engineer immediately for instruction on how to proceed.
label | ad9051dd-ca79-526d-81fd-e5e65955a520 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 62b49a4b-5287-5cd0-9841-9559795f590e |  | note | • Visual Inspection, grout tests, stressing records.
label | 4780e038-cdac-5fa1-b67b-eaec727e301c |  | note | • Acceptance test reports prepared in accordance with ISO 22477-5:2018 are to be provided to the designer's representative within 48 hours of completing each test. Results to be provided in electronic format, including raw data in .xls or similar format for ease of interrogation.
label | 78d2b485-be50-5778-a8a3-7e11f2c83345 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | bc4eaa11-c6d6-56ed-a043-f74676da41a1 |  | note | • Each Pour by PE & One Acceptance Anchor per anchor block by MSQA
label | bcc9299f-82b3-543a-941a-8db0eb03759c |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 37593edc-5979-5039-b56f-35342c4d7d83 |  | note | • I, H
label | 967783e4-b249-51a1-aa1d-34236ad160ff |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b672ea79-c6a9-516e-89c0-a561b9f9dd4f |  | note | • PE, MSQA/DSR, Lab
label | b8311861-dba8-5897-8ff9-931068ee95d7 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 0eb6f617-0b62-5979-a99b-4742f4a887e0 |  | note | • Grout test Results
label | 79cf509f-1ab9-56dc-98e3-7f9872d23e1a |  | note | • Stressing Acceptance Test
label | 4f3b0a46-f968-50cb-82dc-231f6280c889 |  | note | • Stressing Record
label | 643ead2d-aed9-5edb-a013-40314f3afd9d |  | note | • Anchor install check sheet
label | a8bf8ad9-7ecc-53fb-8e1e-a1d5ed2d48db |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.8. Place Stage two grout
label | bbf7c506-da8a-5c80-abb6-3e42c4925cf1 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | b8518063-fac5-5ec9-86ce-bea9a7653470 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | 6623cc7a-d7d7-519a-9b67-558b684b927a |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 62a79a77-60f5-5690-b865-223524faefe3 |  | note | • Grout for anchorages to have 30 MPa compressive strength at 28 days and a maximum water/cement ratio of 0.45.
label | ec11d289-5378-51d0-bb73-df2e47abab90 |  | note | • Grout shall not be used more than one hour after mixing.
label | 51bdd483-e2f1-508c-a617-d24dce6cefa4 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 1d02b962-d66a-58dc-85b5-aa9c6cad3992 |  | note | • Visual Inspection - MSQA
label | a005cae9-5cc8-5b6f-9f30-af1744fdbb89 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | eed4cb44-e4be-5772-810d-623cbef249af |  | note | • One Anchor per anchor block
label | c381de70-8574-56ba-b087-3ac4f23d0813 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 25186918-2fa8-52bd-bd42-d6b82933f39c |  | note | • W, H
label | d64287c0-fa1a-5f25-9f01-d3e8298e775d |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | bf22cd46-6f72-52ce-a7c0-e809e516e914 |  | note | • MSQA/DSR, Lab
label | 18c789c9-0215-5ccf-9840-f5cf2c2333f6 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | b3ea81cb-2545-553c-ad06-75bf4468dd2c |  | note | • Anchor install check sheet
label | 3769a5e4-d7f9-55d9-bd53-06a66a210dfd |  | note | • Photographic Evidence of grout pouring
label | 95f52c8c-6348-52c7-8e72-cf8f436eef3f |  | note | • Grout test results
label | eab18c75-2cc8-5315-9d6f-a9363ec71237 |  | note | • Site Report
holdpoint |  |  | signoff | MSQA HOLD POINT – DO NOT PROCEED PAST THIS POINT UNTIL THE ENGINEER HAS SIGNED OFF THE ABOVE
checkpoint-status |  |  | checkpoint | 7.9. Finishing Works
label | 21c60541-38e0-5569-823a-ba2f2d87a121 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 26ba656c-5977-5a71-817d-f12ec653efb7 |  | note | • MMA-DES-GEO-E1-DRG-4081
label | a4d50a92-e93e-5bf2-b415-abc4ae5a3f2e |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 27bfc3da-c26d-5acd-aded-7dcdce3226b5 |  | note | • Install Rubber Gasket
label | 1d432c2c-016e-58e2-94de-75e4d09fdb46 |  | note | • Strand to be left (100mm or more) as advised by contractor beyond anchor head to allow for wedge withdrawal and future re-stressing.
label | c3be627f-70b3-571c-8ddf-f29d6e0a12d8 |  | note | • Top Cap (HDG) Installed and Packed with Grease
label | 484a31fb-3960-5f27-abc7-8993a7df516a |  | note | • Bearing Plate and anchor head detail to be in accordance with drawings.
label | e04409eb-4522-5a96-82dc-776499944d34 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | f34872d6-2b77-5f5d-b885-108dcc56c8c5 |  | note | • Visual Inspection
label | 6d5a3526-3317-5c56-bb03-fac39f291c37 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 8a2711a4-024b-57fd-ac09-29cf6ad9f6fb |  | note | • All Anchors
label | 08890ef9-298d-57d9-881a-d59de240404a |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 6a48b1e0-9780-5d01-b8b5-0688efa6154c |  | note | • W
label | 89d411c8-30d3-59c9-9d43-5a6ab372a798 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | fe128b84-d8da-5f70-9c1e-1cdc23f0216e |  | note | • PE
label | ad2a9973-0231-55f0-97a3-d45531c1d6a5 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | fbfa9864-a7c2-5e8a-9c54-b8a8bb5486f1 |  | note | • Mill Certs for Plate
label | ae743f65-9b88-5edf-b4fa-cee3304b7b6e |  | note | • Anchor install check sheet
checkpoint-group |  |  | section | Structures - Structural Steelwork Fabrication and Erection (Drive Station Shelter Building and Tower Footings)
checkpoint-status |  |  | checkpoint | 8.1. Weld Inspections
label | ba33134b-b330-5492-8650-4e42ead6ce9f |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 29616399-4a00-5a73-8581-9bbdf440b7c6 |  | note | • Structural Steel Work Specification, AS/NZS 1554.1
label | 03643554-676c-5ac7-87f8-748ff4d630e2 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | cfe2939b-2a3d-5a28-8d28-095353e8f7c1 |  | note | • 100% Visual Inspection
label | 9d941a0f-4d8d-519c-bfd2-3479cecf7c0c |  | note | • 100% Visual Examination
label | ef012016-c7f9-5899-b8b6-791affe790df |  | note | • 100% NDT (Ultrasonic or Radiographic Inspection) for butt welds
label | fa07419d-91e2-5a7b-b551-dc7d95ed8911 |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 1dad4487-b85e-5885-be19-770297a4d7b0 |  | note | • Visual Inspection/NDT
label | 78ed558d-02b9-5cc7-9227-e62fdcdf1532 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 1d1b87d0-0ff9-50e1-8df1-d61f4dae2581 |  | note | • All welds
label | 07c44b9c-3c41-550a-8131-44171d43db32 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 18e89607-1e21-5715-8620-65f18b8be1ef |  | note | • I
label | 919f1b09-4615-5d3b-bb0f-74fc7ea020a7 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 7bb37fc5-ba5f-5e5d-b53f-9ea9cfd3ba23 |  | note | • PE
label | f90eb9f2-4cfb-546c-b44e-7a1aaaff8e75 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 42873eef-4ffb-5c35-9a10-50a4f5263668 |  | note | • Weld Inspection Report
checkpoint-status |  |  | checkpoint | 8.2. Weld Inspector
label | 51362cac-edcc-5f3c-a9ac-f7f7e1232613 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | f098dd26-72ca-51a0-9c27-29b3aeb6f1a3 |  | note | • Structural Steel Work Specification, AS/NZS 1554.1
label | 0d7abdd0-1ce1-569b-9bde-708db5726aad |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 536bc3d0-5f13-57a1-a2ea-e135124e584d |  | note | • Weld Inspector to be independent of Fabricator
label | ff5cec3e-1f84-5e68-8011-8a0b0a8341fa |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | aaed8b71-a89c-56a4-82a0-4bf9b381431e |  | note | • Review of Qualifications
label | 0b609d6a-dba1-5ca6-bc60-303f8f159705 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | ed036ab5-e9b3-5e59-8345-3089bc3802f5 |  | note | • Once
label | 3d7104cd-9c89-5f98-a48e-bf3a34f6b04f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | fe75674c-c24e-59bb-a9ad-6fc722a3c261 |  | note | • R
label | 8b5b11be-d0a0-558e-b4dc-67540044f5a4 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 2d7065e5-d908-5878-92a1-2690af579243 |  | note | • PE, MSQA/DSR
label | 2bf45c07-34cf-5a15-a8d5-c5b842afb4f5 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 7e31d082-d1ab-5ca9-b8fd-174e49b78e47 |  | note | • Inspectors qualifications/Certification
checkpoint-status |  |  | checkpoint | 8.3. Shear Studs
label | af7e38e8-35e4-5e4c-9167-0e82438fe4b3 |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 880f7036-4f2e-528b-8585-4a9494c6052b |  | note | • Structural Steel Work Specification, AS/NZS 1554.2
label | 0e16f785-688a-5979-844c-037c8e075dff |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | d6b639ca-af94-5e71-b696-0198c4fc4572 |  | note | • All studs to be ring tested in accordance with AS/NZS 1554.2
label | a49baf49-ec5b-5658-a536-7b98311d3224 |  | note | • Any studs that fail the ring test to be bend tested in accordance with AS/NZS 1554.2
label | d3fb0851-fb1e-5953-8ecf-472c9545f175 |  | note | • Bend tests to be performed on 1st and 2nd Stud from production run followed by 1 in 50 there after
label | 45fb79ba-79a6-5406-a6c0-3e9b7bb290ac |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | ecfaaf52-669b-5d58-826a-cdf597b570b7 |  | note | • Bend/Ring Test
label | 3f3260dc-d5d1-5bea-bf8b-5b1fa8fb6828 |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | bc875b9c-30a7-5d0d-a538-d40fee723d73 |  | note | • Ring Test all
label | 87833d64-7573-59ab-ac24-f4bca4faee54 |  | note | • Bend test 1st and 2nd, 1/50 and then as required
label | 989c6a7e-0d4f-5bd0-ab35-e9ae8184230b |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 8614e4ea-4fab-5657-88c0-0d6bbfc900a9 |  | note | • I
label | 2001407d-e59e-5cef-8d54-a30f0918cf72 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 66c01beb-7341-51be-9e50-810186ffe5ec |  | note | • PE
label | c27ae4aa-7ace-5ebc-b38d-bdb728bb0289 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | c9ec53a3-c707-5a36-89fb-9f4ec07ebd69 |  | note | • Test Report
checkpoint-status |  |  | checkpoint | 8.4. Inspection of Bolted Connections
label | ec93ce4a-1885-5af1-b394-c52cfafccbcd |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | d766a913-1736-5401-9d10-a683da132b0d |  | note | • Structural Steelwork Specification, AS/NZS 5131
label | f365f078-5c85-51fd-9047-d6391f374cee |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 7c8b58f4-06a0-5b5c-a7f5-994cc72d02b3 |  | note | • Designer/DSR to inspect min 10% of bolted connections
label | 862c36a4-7f93-5c7c-a296-915bd8c49faa |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 15f6b036-abba-5f4d-bbce-272cd8225a50 |  | note | • Visual Inspection
label | a5930786-1323-5d61-908f-fb749c542cfd |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 504e92a3-bf88-531c-aeaa-faa2afa95e5d |  | note | • Minimum 10% but no fewer than 2 per connection
label | 84c8e556-898b-5a5b-97d9-6f5c247ac4be |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 29dcb543-c5d0-5768-80af-a09f85e2b932 |  | note | • I, H
label | c5fdbd7e-a1ff-5143-b1a3-8037fbcb2a75 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | 8b62a166-4173-5f0e-9723-9acf1a6a3773 |  | note | • PE, MSQA/DSR
label | 4b3b6245-e8da-5404-89cd-2df87434c6d9 |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | d65f5e5e-af22-5226-858b-e027a3ed6bc2 |  | note | • DSR Inspection
checkpoint-status |  |  | checkpoint | 8.5. Inspection of Fabricated/Erected Steel Work
label | 6cf27208-0f22-5b3b-bd83-b73e37abd4cb |  | note | APPLICABLE STANDARD OR SPECIFICATION:
label | 5badd6b2-357b-5424-be4e-26c3089384a3 |  | note | • Structural Steel Work Specification, AS/NZS 5131
label | 27764164-59ba-527b-9e4a-9e0c3f38a776 |  | note | ACCEPTANCE CRITERIA AND TESTING - DESCRIPTION:
label | 7fada03c-f191-5c9d-9fd3-d5b5ffd07c13 |  | note | • Designer/DSR to inspect fabricated steel work
label | 7bd67302-88c9-57c6-93b4-8c9a07f1ea9d |  | note | ACCEPTANCE CRITERIA AND TESTING - METHOD:
label | 9bc0dfb8-3a79-5905-8937-073462e4629e |  | note | • Visual Inspection
label | 2862460f-6615-584b-a674-3c471fec9d9c |  | note | ACCEPTANCE CRITERIA AND TESTING - FREQUENCY:
label | 120503d1-8084-5e0c-9e83-3f0b0cfef51b |  | note | • Per Element
label | b0de2df8-7e01-58ac-a71d-2ba4e0f2811f |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - METHOD:
label | 57c3d65b-10cd-5ace-9b1c-a296d02e3a33 |  | note | • I, H
label | 50c8b810-b818-5258-9e36-41eee8503b32 |  | note | VERIFICATION METHOD AND RESPONSIBLE INSPECTORATE FOR HOLD POINTS - RESPONSIBLE:
label | b3c714eb-4657-51f4-92ee-d67da24e249c |  | note | • PE, MSQA/DSR
label | f89b1150-13e4-5c8d-910d-af87707f4baa |  | note | VERIFYING RECORDS CHECKLISTS, TEST AND SUPPLIER CERTIFICATES:
label | 1dbc3972-f751-56af-a505-1609c9a82e42 |  | note | • DSR Inspection
checkpoint-status |  |  | checkpoint | Completion Verification
label | c7a84e57-84b4-5814-be7b-1eb68a616f55 |  | note | Work under this ITP has been Certified complete by:
text | e6f51531-700f-5aad-8a9b-7d0b7a0ed105 |  | textbox | Name:
text | 9515b7c7-2d95-57bb-837a-4ab02bcb92f0 |  | textbox | Date:
label | 55ad0b7c-ea15-57be-8f79-cfbb9b951cff |  | note | Reviewed by [as applicable]
text | 264c0f64-8419-5254-bd37-d741f5f21c4c |  | textbox | Name:
text | a6ace094-bbec-5f6c-96f6-55b441411afa |  | textbox | Date:
label | d0d2fe25-b83d-5222-9413-d7d0836ea8fd |  | note | Reviewed by [as applicable]
text | c368c579-e632-5c5c-803b-ca915f223ff1 |  | textbox | Name:
text | b654b67e-a819-5afd-b5fa-cdef1b467410 |  | textbox | Date:
label | d7341bb1-1a59-5932-9451-25105159d29c |  | note | Approved by [as applicable]
text | 33c84292-cfca-57e0-97dd-f5807986ed1f |  | textbox | Name:
text | dd952e5b-5f8e-541a-9e18-33c62baada87 |  | textbox | Date: