## Structure
Pre-pour & Concrete Delivery
PSC01
|  | Pre-Pour | Pre-Pour Checklist
|  | Concrete Delivery | Concrete Delivery Checklist
| PSC02 |  | As Above
| PSC03 |  | As Above
| PSC04 |  | As Above
| PSC05 |  | As Above
| PSC06 |  | As Above
| PSC07 |  | As Above
| PSC08 |  | As Above
| PSC09 |  | As Above
| PSC10 |  | As Above
| PSC11 |  | As Above
| PSC12 |  | As Above
| PSC13 |  | As Above
Transport To Site

## Checklists
type | name | values | prefix | postfix | usage count | user addable
checklist | Pre-Pour Checklist
section | Product Detail
checkpoint-no-status | Details
text | Product ID
text | Weight
text | Manufacture Date
section | Formwork
checkpoint | Check Length
text | length
checkpoint | Check Width
text | width
checkpoint | Check Thickness
text | thickness
checkpoint | Check Diagnonal
checkpoint | Sideform Trueness
checkpoint | Magnets / Forms Secure
checkpoint | Splayed forms checked
checkpoint | Penotration dimensions checked
checkpoint | Curves / Radius Checked
checkpoint | Rebates size and location checked
checkpoint | Weather steps dimensions checked
checkpoint | Weather steps orientation checked
checkpoint | Form release applied correctly
section | Reinforcement
checkpoint | Reinforcement mat as per shop drawings
checkpoint | Reo Mat Orientation
checkpoint | Perimeter Bars Size Correct
checkpoint | Perimeter Bars No. Off Correct
checkpoint | Additional Bars Correct
checkpoint | Reo Changes Noted
checkpoint | Reo Changes Passed By PM
checkpoint | COGS / Laps As Per SD
checkpoint | Any Splice 40 x Dia Min
checkpoint | Rebar Photos
section | Fixings / Cast Ins
checkpoint | Ferrule Location Checked
checkpoint | Ferrule Cross Bars Inserted
checkpoint | Lifting Inserts as Per Lift Design
checkpoint | Lifter Type correct
text | Lifter Type
checkpoint | Lifting V Bars Inserted
checkpoint | Cast Plates Per Design
checkpoint | Cast Plate Location Checked
checkpoint | Additional Cast Plate Bars Inserted
checkpoint | Starter Bars Correct Per SD
checkpoint | Pertruding Bars Orientation
checkpoint | Grout Tube Size Checked
checkpoint | Grout Tube Exit Orientation Checked
checkpoint | Grout Tube Photo
checkpoint | Lifting Insert Photo
checkpoint | Cast In Plate Photo
checkpoint | Penetration Photo
Final Checks
checkpoint | All SD Dimensions Shown
checkpoint | Photo of For "Construction" Shop Drawing
checkpoint | Panel ID Tag Placed
checkpoint | Idencia RFID Tag Placed
checkpoint | Product Cleared For Pouring
checkpoint | Inspector sign off attached below
checklist-flat | Concrete Delivery Checklist
checkpoint-no-status | Details
text | Concrete Docket Number
text | Pour Date
text | Time Batched
text | Load M3
checkpoint | Picture of Concrete Docket
checkpoint | Load size match order sheet
checkpoint | Mix type match the order sheet
checkpoint | Mix color match the order sheet
checkpoint | MPa match the order sheet
text | Concrete Strength |  |  | MPa
checkpoint | Spread / slump within range
text | Spread / Slump in mm |  |  | mm
checkpoint | Water Added (N/A if no)
text | Quantity of water added
checkpoint | Concrete test taken (N/A if no)
checkpoint | Picture of spread check before dispatch
checkpoint | Inspector sign off attached below
checklist-flat | Transport Checklist
checkpoint-no-status | Details
text | Shipment Number
text | Shipment Date
text | Install Date
text | Time Requested Onsite
text | Carrier
text | Delivery Driver Name
text | Delivery Drivers Phone Number
text | Trailer Rego
checkpoint | Correct Products on Transport
checkpoint | Safety Restraints
checkpoint | Rego Photo
checkpoint | Drivers Side Photo
checkpoint | Passenger Side Photo
checkpoint | Transport Safe To Leave Yard
checkpoint | Inspector sign off attached below
text | Item Status
checklist-flat | Defects Checklist
checkpoint-no-status | Details and photos below

## Matrix
Delivery Report - Matrix
Dynamic Row | Panel ID No. | Weight (Tonnes) | Length (MM) | Width (MM) | Thickness (MM) | Lifter Type | Inspector Sign Off Attached Below? | Pour Date | Time Batched | Strength (MPA) | Inspector Sign Off Attached Below?
Set folders --> | P001 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P002 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P003 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P004 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P005 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P006 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P007 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P008 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P009 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Set folders --> | P010 | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE
Appears as they add --> |  | text box | text box | text box | text box | text box | TRUE | text box | text box | text box | TRUE