## Breakdown
Quality Heating Solutions Ltd. (Kevin Hickman - Riccarton Park)
Project Build QA
Stage 3 - THB11 & THB13
THB11 (TH33, 34, 35, 36)
|  |  |  | TH33 | Pre-populate | S - S - Air conditioning
|  |  |  | TH34 | Pre-populate | S - S - Air conditioning
|  |  |  | TH35 | Pre-populate | S - S - Air conditioning
|  |  |  | TH36 | Pre-populate | S - S - Air conditioning
THB13 (TH37, 38, 39)
|  |  |  | TH37 | Pre-populate | S - S - Air conditioning
|  |  |  | TH38 | Pre-populate | S - S - Air conditioning
|  |  |  | TH39 | Pre-populate | S - S - Air conditioning
Compliance Documentation
|  | Stage 3 - THB11 & THB13 |  |  | Pre-populate | CST - S - Completion Documents

## Checklists
Type | Name | Value
checklist | S - S - Air conditioning
section | Pre-start checks
checkpoint | Area/base/wall ready for outdoor unit
checkpoint | Pipework route all clear, penetrations complete
checkpoint | Nogs/ply in place for indoor unit
checkpoint | Drain 1m from indoor unit location by plumber
section | First Fix
checkpoint | Complete length of pipework is insulated and acceptable
checkpoint | Drain installed and insulated
checkpoint | Supply cable installed correctly, protected and secured
checkpoint | Outdoor wall brackets in place
checkpoint | Interconnecting cables correctly installed and protected
checkpoint | Mechanical First Fix complete and acceptable
section | Second Fix
checkpoint | System pressure checked and still holding pressure and acceptable
checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
checkpoint | Correct Outdoor unit installed and secure
checkpoint | Indoor unit serial no. recorded
checkpoint | Outdoor Unit serial no. recorded
checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
checkpoint | Air conditioning Second Fix complete and acceptable
section | Commissioning
checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint | Electrical testing complete
checkpoint | Commissioning complete and acceptable
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name | Value
checklist | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | LBP Memorandum/ Record of works filled out, signed and attached
button | Any Additional Compliance Documentation - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff