## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | S - S - Air conditioning |  |  |  |  | Yes | S - S - Air conditioning | 6d282243-ed29-497f-8832-da1d2ee1f34e
checkpoint-group |  |  | section | Pre-start checks
checkpoint-status |  |  | checkpoint | Area/base/wall ready for outdoor unit
checkpoint-status |  |  | checkpoint | Pipework route all clear, penetrations complete
checkpoint-status |  |  | checkpoint | Nogs/ply in place for indoor unit
checkpoint-status |  |  | checkpoint | Drain 1m from indoor unit location by plumber
checkpoint-group |  |  | section | First Fix
checkpoint-status |  |  | checkpoint | Complete length of pipework is insulated and acceptable
checkpoint-status |  |  | checkpoint | Drain installed and insulated
checkpoint-status |  |  | checkpoint | Supply cable installed correctly, protected and secured
checkpoint-status |  |  | checkpoint | Outdoor wall brackets in place
checkpoint-status |  |  | checkpoint | Interconnecting cables correctly installed and protected
checkpoint-status |  |  | checkpoint | Mechanical First Fix complete and acceptable
checkpoint-group |  |  | section | Second Fix
checkpoint-status |  |  | checkpoint | System pressure checked and still holding pressure and acceptable
checkpoint-status |  |  | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
checkpoint-status |  |  | checkpoint | Correct Outdoor unit installed and secure
checkpoint-status |  |  | checkpoint | Indoor unit serial no. recorded
checkpoint-status |  |  | checkpoint | Outdoor Unit serial no. recorded
checkpoint-status |  |  | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
checkpoint-status |  |  | checkpoint | Air conditioning Second Fix complete and acceptable
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Installer confirmed commissioned and paperwork submitted
checkpoint-status |  |  | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
checkpoint-status |  |  | checkpoint | Electrical testing complete
checkpoint-status |  |  | checkpoint | Commissioning complete and acceptable
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 6f7a8164-024a-4173-9dee-42a31b8d47db
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | cc98dcad-e05c-5442-82fb-f425cbbfca9d |  | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes, No
button | a1abc465-3e03-5e92-aa23-2d3c339bca01 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, No
label | 71cf2a5a-65ec-599b-aff4-42866bcae4e9 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Sign Off