## Sheet1 (hidden)
Project Breakdown |  |  | Level |  |  |  | Checklists
QA
| RECEPTION BUILDING | GROUND FLOOR | Lower Ground Floor
|  |  |  | Slab Penetrations |  |  | Slab Penetrations Template - DPFC EXPANSION
Below Ground
Fix 1
[6 empty] | Sewer BG | Sewer BG
[6 empty] | Stormwater BG | Stormwater BG
Overall Floor Plan
Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Cold Water | Cold Water Checklist
[6 empty] | Hot Water | Hot Water
|  |  |  | Corridor |  |  | Corridor Template
|  |  |  | RB002 HOLDING CELL | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
RB003 HOLDING ROOM
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
RB004 FOYER
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
RB005 PRE-STERILE WAITING
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
RB006 WC
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
RB007 WC ACC
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB008 RECEPTION | Fix 1 | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
RB009 BODY SCAN + X-RAY
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[5 empty] | Fix 2 |  | Fix 2 checklist
RB010 RECORDS
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
Ground Floor
|  |  |  | RB011 INTERVIEW | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB012 CLOTHING ISSUE | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB013 SEARCH+SHWR | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB014 SEARCH+SHWR | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
Level 1
|  |  |  | RB015 WAITING | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
RB016 INT. 01
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB017 INT. 02 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB018 BOX WRITER MOVT. OFFICER | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
RB019 CORRIDOR 01
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB020 INT. 03 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB021 INT. 04 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB022 INT. 05 | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
|  |  |  | RB023 SINGLE HOLD 01 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
Slab Penetrations Template - DPFC EXPANSION
|  |  |  | RB024 SINGLE HOLD 01 | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
|  |  |  | RB025 CORRIDOR 03 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
Level 5
Slab Penetrations Template - DPFC EXPANSION
|  |  |  | RB027 LAUNDRY | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Hot Water | Hot Water
|  |  |  | RB028 STORE RECEIPT | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB029 PROPERTY STORE | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
|  |  |  | RB030 CORRIDOR 04 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB032 GROUP HOLD 01 | Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
|  |  |  | RB033 CONSULT 01 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
|  |  | Excavator |  |  | Sewer AG | Sewer AG
|  |  | Bobcat |  |  | Fire Collars | Fire Collars
|  |  | Tipper |  |  | Stormwater AG | Stormwater AG
|  |  | EWP |  | Fix 2 |  | Fix 2 checklist
Tools
|  |  | Ladders | RB034 CONSULT 02 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
|  |  | May 2021 |  |  | Fire Collars | Fire Collars
|  |  | June 2021 |  |  | Stormwater AG | Stormwater AG
|  |  | July 2021 |  | Fix 2 |  | Fix 2 checklist
August 2021
|  |  | September 2021 | RB035 CONSULT 03 | Fix 1
|  |  | October 2021 |  |  | Rough-In | Rough In Checklist
|  |  | November 2021 |  |  | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB036 ARUNTA | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB037 GROUP HOLD 02 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB038 GROUP HOLD 03 OSTP | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB039 URINALYSIS + SEARCH | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB042 VALUABLES | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB043 SER | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB044 COMMS | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB046 MED. STORE | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB047 CLNR | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Hot Water | Hot Water
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB048 STAFF WC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB049 STAFF TEA ROOM | Fix 1
[6 empty] | Hot Water | Hot Water
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB050 A/L | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB060 EXTERNAL PLANT 01 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB061 EXTERNAL PLANT 02 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | RB062 ARCHIVE | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  | LEVEL 1 |  | Slab Penetrations |  |  | Slab Penetrations Template - DPFC EXPANSION
Below Ground
Fix 1
[6 empty] | Sewer BG | Sewer BG
[6 empty] | Stormwater BG | Stormwater BG
Overall Floor Plan
Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Cold Water | Cold Water Checklist
[6 empty] | Hot Water | Hot Water
| MULTIFAITH BUILDING | GROUND FLOOR
|  |  |  | MP001 LOUNGE | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP002 OFFICER'S POST | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP003 TEA | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP005 SER | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP006 STAFF WC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP009 FITNESS STUDIO | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP010 STORE | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP011 PRISONER WC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP012 WC ACC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP013 LEGAL LIBRARY | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP023 MULTI-PURPOSE 02 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP024 MULTI-PURPOSE 01 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP032 STAFF WORK STATIONS | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Hot Water | Hot Water
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP033 TEA | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP035 STAFF WC ACC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | MP036 STAFF WC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Hot Water | Hot Water
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
| DAWSON | LEVEL 1 |  | Slab Penetrations |  |  | Slab Penetrations Template - DPFC EXPANSION
Below Ground
Fix 1
[6 empty] | Sewer BG | Sewer BG
[6 empty] | Stormwater BG | Stormwater BG
Overall Floor Plan
Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Cold Water | Cold Water Checklist
[6 empty] | Hot Water | Hot Water
|  |  |  | DA001 ENTRY A/L | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA002 FOYER | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA008 STAFF WC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA009 STAFF TEA | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA011 LDRY & CLNR | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA012 COMMUNAL KITCHEN DINING B | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA 14 - DA 28 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA029 COMMUNAL KITCHEN C | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA030 COMMUNAL LOUNGE C | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA 31 - DA 39 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Hot Water | Hot Water
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA040 COMMUNAL KITCHEN DINING A | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | DA 42 - DA 70 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  | LEVEL 1 |  | Slab Penetrations |  |  | Slab Penetrations Template - DPFC EXPANSION
Below Ground
Fix 1
[6 empty] | Sewer BG | Sewer BG
[6 empty] | Stormwater BG | Stormwater BG
Overall Floor Plan
Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Cold Water | Cold Water Checklist
[6 empty] | Hot Water | Hot Water
| AVON | GROUND FLOOR |  | Slab Penetrations |  |  | Slab Penetrations Template - DPFC EXPANSION
Below Ground
Fix 1
[6 empty] | Sewer BG | Sewer BG
[6 empty] | Stormwater BG | Stormwater BG
Overall Floor Plan
Fix 1
[6 empty] | Stormwater AG | Stormwater AG
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Greasy AG | Greasy AG
[6 empty] | Rainwater | Rainwater
[6 empty] | Gas | Gas
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Cold Water | Cold Water Checklist
[6 empty] | Hot Water | Hot Water
|  |  |  | AN001 ENTRY | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN002 OFFICER'S POST | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN003 CONTROL ROOM | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN005 STAFF TEA | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN006 WC | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN007 SER | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN008 COMMS | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN008 COMMS | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN010 URINAL | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN011 MEDICAL CONSULT | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN012 MED. STORE | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN014 HOLD CELL | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN015 LOUNGE C | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN016 INTERVIEW 01 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN017 INTERVIEW 02 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN018 STORE /VESDA | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN019 LOUNGE B2 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN020 OBS SH | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN022 MUIRHEAD 1 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN024 MUIRHEAD 2 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN025 ENCASE COL | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN027 TELECOURT | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN028 PROGRAMS 01 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN029 LOUNGE A | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist
|  |  |  | AN31 - AN40 | Fix 1
[6 empty] | Rough-In | Rough In Checklist
[6 empty] | Hot Water | Hot Water
[6 empty] | Sewer AG | Sewer AG
[6 empty] | Fire Collars | Fire Collars
[6 empty] | Stormwater AG | Stormwater AG
[5 empty] | Fix 2 |  | Fix 2 checklist

## Project
Level 1 | Level 2 | Level 3 | Checklist
Sheet 1 | Fire |  | Fire Service BG
| Gas |  | Gas BG
| Water | Meter | Water Meter Validation
|  | Pipeline | Cold Water BG
| Stormwater | Drain | Stormwater BG
|  | Pit | Preform
| Telstra |  | Excavation & Backfill Checklist
| Conduits |  | Excavation & Backfill Checklist
| Boring |  | Excavation & Backfill Checklist
Sheet 2 | Fire |  | Fire Service BG
| Gas |  | Gas BG
| Water |  | Cold Water BG
| Stormwater |  | Stormwater BG
Preform
| Telstra |  | Excavation & Backfill Checklist
| Conduits |  | Excavation & Backfill Checklist
| Boring |  | Excavation & Backfill Checklist

## Master Checklists
type | name | values | prefix | postfix | Notes
checklist | Slab Penetrations Template |  |  |  | Can add pours
section | Pour 1
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Fire protection installed (as per approved samples)
checkpoint | Support & fixings done correctly
checkpoint | Pipework laying & lagging acceptable
checkpoint | Material type (as per sample submission)
checkpoint | Pipework tested (add below)
text | KpA of test
checkpoint | Penetration secured down for concrete pour
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photo's below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Pour 2
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Fire protection installed (as per approved samples)
checkpoint | Support & fixings done correctly
checkpoint | Pipework laying & lagging acceptable
checkpoint | Material type (as per sample submission)
checkpoint | Pipework tested (add below)
text | KpA of test
checkpoint | Penetration secured down for concrete pour
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photo's below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Pour 3
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Fire protection installed (as per approved samples)
checkpoint | Support & fixings done correctly
checkpoint | Pipework laying & lagging acceptable
checkpoint | Material type (as per sample submission)
checkpoint | Pipework tested (add below)
text | KpA of test
checkpoint | Penetration secured down for concrete pour
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photo's below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Corridor Template
section | High Level Services
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type as per approved sample submission with AGA or watermarks
checkpoint | Welding , press fittings, witness marks visually checked
checkpoint | Fixings & seismic support to standards
checkpoint | Pipework installations to code requirements
checkpoint | Water meters installed to authority standards
checkpoint | Gas 25mm separation achieved from other services as per AS 5601.1
checkpoint | Penetrations, fire protection, wall sealant installed to the BCA requirements
checkpoint | Identifications of services, valves & meters to standards
checkpoint | Pressure test to code requirements
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Drainage
checkpoint | Stormwater riser
checkpoint | Syfon drainage
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
bool | Area clean
section | Sewer AG
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Grades, fittings & joints installed to standards
checkpoint | Fixings & seismic support to standards
checkpoint | Expansion joints per floor installed correctly & clipped
checkpoint | Pipe risers sealed per floor & capped off to prevent damage
checkpoint | Correct invert level (As per Standards)
checkpoint | Vents and AAV installed (As per Standards)
checkpoint | Acoustic lagging installed to acoustic specification
checkpoint | Pipework water tested to 15Kpa
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Fix 1 Checklist
section | Sewer AG
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Grades, fittings & joints installed to standards
checkpoint | Fixings & seismic support to standards
checkpoint | Expansion joints per floor installed correctly & clipped
checkpoint | Pipe risers sealed per floor & capped off to prevent damage
checkpoint | Correct invert level (As per Standards)
checkpoint | Vents and AAV installed (As per Standards)
checkpoint | Acoustic lagging installed to acoustic specification
checkpoint | Pipework water tested to 15Kpa
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Stormwater AG
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Grades (as per AS:3500)
checkpoint | Location (as per hydraulic drawing)
text | Location
checkpoint | Fixings - Securely fixed (As per Standards)
checkpoint | Fittings Joints ETC (as per AS 3500)
checkpoint | Inspection prior to closure
checkpoint | Operation of pumps (Commissioning report) if Applicable
checkpoint | Test water and discharge requirements are met
checkpoint | Correct invert level AS per AS 3500
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Rough In
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type (as per sample submission)
checkpoint | Pipework installation checked against standards (as per AS 3500.1)
checkpoint | Welding / pressfit / push fit / witness marks (as per AS 3500.1)
checkpoint | Support & fixings checked (acoustic / seismic / water hammer/ silicone)
checkpoint | Check for no cross connection
checkpoint | Heights double checked before room sign off as per sample submission
checkpoint | Pipe risers water sealed per floor and capped off to prevent damage
checkpoint | Correct sewer ventilation
checkpoint | Pressure test water lines to (1500kpa)
checkpoint | Identification of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Rainwater
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type as per approved sample submission
checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
checkpoint | Welding / pressfit / push fit (as per AS 3500.1)
checkpoint | Support & fixings (acoustic / seismic / water hammer)
checkpoint | Pipework Installation (as per AS 3500.1)
checkpoint | Check no cross connection
checkpoint | Pressure test (1500kpa pressure test)
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Fix 2 checklist
section | Fixtures
checkpoint | Correct product (samples provided)
checkpoint | Check products for imperfections
checkpoint | Location & fixings (as per drawings & manufacturer guidelines)
checkpoint | Silicone seals are acceptable standard (as applicable)
checkpoint | Operation of all fixtures, taps & points of demand
checkpoint | Final fit off inspection on all items
text | Inspection date
checkpoint | Items protected until commissioning (Attach photos below)
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Commissioning
checkpoint | Check products for imperfections
checkpoint | Fixtures location & fixings all correct (as per drawings & samples)
checkpoint | Clean out all strainers / aerators
checkpoint | Check for no cross connections / leaks / access to isolation valves
checkpoint | Floor wastes (clear of debris & draining correctly)
checkpoint | Quality of silicone seals to fixtures acceptable
checkpoint | Hot water tempering valve set to 50c (+/- 5c) & DDA thermostatic mixing valve set to 42 degrees.
checkpoint | Water pressure acceptable 350Kpa to 500 Kpa
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Stormwater BG
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct approved materials as per sample register
checkpoint | Excavation undertaken & no issues (Any issues comment below)
checkpoint | Pipe bedding material (as per AS 500)
checkpoint | Grades, fittings & joints installed to standards
checkpoint | Pipe clean out via water flush
checkpoint | Inspection and Testing Prior to Concealment to AS 3500.2 section 13
checkpoint | Builder sign off prior concealment
checkpoint | Seal open ends with caps & high light to avoid damage
checkpoint | Backfill & Compaction of Material (As per Specification / Geotechnical report)
checkpoint | CCTV on completion & record results (If applicable)
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Stormwater AG
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Grades (as per AS:3500)
checkpoint | Location (as per hydraulic drawing)
text | Location
checkpoint | Fixings - Securely fixed (As per Standards)
checkpoint | Fittings Joints ETC (as per AS 3500)
checkpoint | Inspection prior to closure
checkpoint | Operation of pumps (Commissioning report) if Applicable
checkpoint | Test water and discharge requirements are met
checkpoint | Correct invert level AS per AS 3500
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Greasy BG
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct approved materials as per sample register
checkpoint | Excavation undertaken & no issues (Any issues comment below)
checkpoint | Pipe bedding material comply (as per AS 3500)
checkpoint | Grades, fittings & joints installed to standards
checkpoint | Pipe clean out via water flush
checkpoint | Inspection & Testing Prior to Concealment to AS 3500.2 section 13
checkpoint | Builder sign off prior concealment
checkpoint | Seal open ends with caps & high light to avoid damage
checkpoint | Backfill & Compaction of Material (As per Specification / Geotechnical report)
checkpoint | CCTV on completion & record results
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Greasy AG
checkpoint | Employee trained for task
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct material as per sample register
checkpoint | Grades, fittings & joints installed to standards including witness marks
checkpoint | Fixings & seismic support to code requirements
checkpoint | Expansion joints per floor installed correctly & clipped
checkpoint | Pipe risers sealed per floor & capped off to prevent damage
checkpoint | Correct ventilation installed including AAV
checkpoint | Acoustic lagging installed to acoustic specification
checkpoint | Testing to 15KPA with air or full water test
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Sewer BG
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct approved materials as per sample register
checkpoint | Excavation undertaken & no issues (Any issues comment below)
checkpoint | Pipe bedding material comply (as per AS 3500)
checkpoint | Grades, fittings & joints installed to standards
checkpoint | Pipe clean out via water flush
checkpoint | Inspection & Testing Prior to Concealment to AS 3500.2 section 13
checkpoint | Builder sign off prior concealment
checkpoint | Seal open ends with caps & high light to avoid damage
checkpoint | Backfill & Compaction of Material (As per Specification / Geotechnical report)
checkpoint | CCTV on completion & record results
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Sewer AG
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Grades, fittings & joints installed to standards
checkpoint | Fixings & seismic support to standards
checkpoint | Expansion joints per floor installed correctly & clipped
checkpoint | Pipe risers sealed per floor & capped off to prevent damage
checkpoint | Correct invert level (As per Standards)
checkpoint | Vents and AAV installed (As per Standards)
checkpoint | Acoustic lagging installed to acoustic specification
checkpoint | Pipework water tested to 15Kpa
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Pipework Flushing Procedure
checkpoint | Pipework Flushing Date & Time
text | Date & time
checkpoint | All "Flush Out Points" on the floor requires warning signage
checkpoint | Check Required volume to be flushed from each system - hot & cold - calculations can be found in "WPD Pipework Flushing Folder" for time durations per area
checkpoint | Cold Water System - Start by opening tap located furthest from the meters, open others on the way back & observe time to ensure system has been sufficiently drained. Open outside taps for enough time to empty volume of the main line, then flush each toilet the required amount to empty each branch.
checkpoint | Hot Water System - Start by opening tap located closest to end of the return line, open others on the way back & observe time to ensure system has been sufficiently drained.
checkpoint | Flushing showerheads & hoses - let the shower hang down (without touching the ground) it will let the water drain out afterwards. The water in a showerhead & hose when it sits there inside can become a risk and also causes scale buildup.
label | Faucets/taps with an aerator on it, should be removed during flushing, to allow the outlet to flush at high volume.
checkpoint | All taps turned off & area made safe
checkpoint | Complete register & attach photos
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Prefab Checklist
checkpoint | Current task
checkpoint | Employee trained for task
checkpoint | Check materials products for imperfections
checkpoint | Site sample, diagrams, & materials list clear to understand
button | Order complete | Yes, No
button | Delivery booked with site team | Yes, No
checkpoint | Completed stillage or pallet weighed & materials do not exceed SWL of stillage or pallet
button | Factory paperwork attached to package including weight stamp | Yes, No
button | Delivery weight total does not exceed SWL of delivery truck | Yes, No
checkpoint | Delivery sent to site
checkpoint | Order complete
type | name | values | prefix | postfix
checklist | Fire Service BG
checkpoint | Employee trained for task
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct material as per sample register
checkpoint | Bedding material installed correctly
checkpoint | Fittings & joints correctly installed to manufacturer's requirements
checkpoint | Satisfactory welding/pressing of copper pipe
checkpoint | Witness marks visible
checkpoint | Pipework layed correctly & to AS 3500
checkpoint | Concrete anchor thrust blocks installed as per engineers report
checkpoint | Testing to 1700 kPa with no leaks for 120 minutes
checkpoint | Identification of services via I.D tape
checkpoint | Backfill & compaction to specification in 300mm layers
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Cold Water BG
checkpoint | Employee trained for task
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct material as per sample register
checkpoint | Bedding material installed correctly
checkpoint | Fittings & joints correctly installed to manufacturer's requirements
checkpoint | Satisfactory welding/pressing of copper pipe
checkpoint | Witness marks visible
checkpoint | Pipework layed correctly and to AS 3500
checkpoint | Inspection and Testing Prior to Concealment to AS 3500
checkpoint | Seal open ends with caps & high light to avoid damage
checkpoint | Identification of services via I.D tape
checkpoint | Backfill & compaction to specification in 300mm layers
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
checklist | Gas BG
checkpoint | Employee trained for task
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct material as per sample register
checkpoint | Bedding material installed correctly
checkpoint | Fittings & joints correctly installed to manufacturer's requirements
checkpoint | Witness marks visible
checkpoint | Pipework layed correctly and to AS 5601.1
checkpoint | Inspection and Testing Prior to Concealment to AS 5601.1 (ESV start works notice)
checkpoint | Seal open ends with caps & high light to avoid damage
checkpoint | Identification of services via I.D tape
checkpoint | Backfill & compaction to specification in 300mm layers
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean and As-Built Markup
type | name | values | prefix | postfix
checklist | Hot Water
checkpoint | Employee trained for task
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type (as per sample submission)
checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
checkpoint | Welding / pressfit / push fit (as per AS 3500.1)
checkpoint | Support & fixings (acoustic / seismic / water hammer)
checkpoint | Pipework installation (as per AS 3500.1)
checkpoint | Check no cross connection
checkpoint | Pressure test (1500kpa pressure test)
checkpoint | 3rd Party Inspection (Including the below as applicable)
text | Name
text | Company
holdpoint | Click to Add 3rd party signature(s) & any documentation
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Cold Water Checklist
checkpoint | Employee trained for task
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type (as per sample submission)
checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
checkpoint | Welding / pressfit / push fit (as per AS 3500.1)
checkpoint | Support & fixings (acoustic / seismic / water hammer)
checkpoint | Pipework installation (as per AS 3500.1)
checkpoint | Check no cross connection
checkpoint | Pressure test (1500kpa pressure test)
checkpoint | 3rd Party Inspection (Including the below as applicable)
text | Name
text | Company
holdpoint | Click to Add 3rd party signature(s) & any documentation
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Water Meter Validation
checkpoint | Employee trained for task
checkpoint | Correct meter installed as per sample register (Attach photo below)
checkpoint | Clean out all strainers & flush water before validation starts
checkpoint | Check BMS is connected
checkpoint | Check meter has correct labelling tag as per the meter matrix
checkpoint | Check right pulse rate to be recorded
text | Pulse rate
checkpoint | Turn on test point & fill test bucket with water to marked litre level
checkpoint | Record reading is the same with BMS contractor
text | Record reading(s)
checkpoint | Remove test lines & insert plug, test for leaks
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Rough In Checklist
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type (as per sample submission)
checkpoint | Welding / pressfit / push fit / witness marks (as per AS 3500.1)
checkpoint | Support & fixings checked (acoustic / seismic / water hammer/ silicone) - Add Photos below
checkpoint | Pipework installation checked against standards (as per AS 3500.1)
checkpoint | Check no cross connection
checkpoint | Heights double checked before room sign off as per sample submission
checkpoint | Pipe risers water sealed per floor & capped off to prevent damage
checkpoint | Correct sewer ventilation installed
checkpoint | Pressure test water lines to (1500kpa)
checkpoint | Identification of services
text | Services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Rainwater
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type as per approved sample submission
checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
checkpoint | Welding / pressfit / push fit (as per AS 3500.1)
checkpoint | Support & fixings (acoustic / seismic / water hammer)
checkpoint | Pipework Installation (as per AS 3500.1)
checkpoint | Check no cross connection
checkpoint | Pressure test (1500kpa pressure test)
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Greywater
checkpoint | Setout and alignment as per drawing (include revision in comments)
text | Grades, fittings & joints
checkpoint | Fixings and seismic
checkpoint | Expansion joints per floor installed correctly and clipped
checkpoint | Pipe risers sealed per floor and capped off to prevent damage
checkpoint | Correct invert level
checkpoint | Check for no cross connections with waste drainage
checkpoint | AAV installed
checkpoint | Acoustic lagging installed to acoustic specification
checkpoint | Testing to 15KPA
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Recycled Water
checkpoint | Setout and alignment as per drawing (include revision in comments)
text | Material type (as per sample submission)
checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.1 section 2.6)
checkpoint | Welding / pressfit / push fit (as per AS 3500.1)
checkpoint | Support & fixings (acoustic / seismic / water hammer)
checkpoint | Pipework installation (as per AS 3500.1)
checkpoint | Check no cross connection with domestic water supply
checkpoint | Pressure test (1500kpa pressure test)
checkpoint | Identifications of services
checkpoint | Final inspection (3rd Party)
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Gas
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Material type as per approved sample submission
checkpoint | Welding, press fittings, witness marks visually checked
checkpoint | Supports & fixings to ESV and WPD standards
checkpoint | Pipework installations to ESV standards
checkpoint | Penetrations, fire protection, wall sealant installed to the BCA requirements
checkpoint | Witness marks / labels / tiger tape / kpa signage
checkpoint | Pressure test (as per AS/NZS 5601.1)
checkpoint | Test appliances (as per AS/NZS 5601.1)
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | Fire Collars
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Installation as per manufacturer's requirements
checkpoint | Correct fire collar location (as per drawing)
text | Location
checkpoint | Fire tags as per fire matrix installed
checkpoint | Structurally correct (Engineers Approval required)
bool | Engineers Approval attached
checkpoint | Fire sealant installed correctly
checkpoint | Final Inspection - 3rd Party (Including the below as applicable)
text | Name
text | Company
holdpoint | Click to Add 3rd party signature(s)
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
type | name | values | prefix | postfix
checklist | Sanitary
checkpoint | Setout and alignment as per drawing (include revision in comments)
text | Materials Type (as per sample submission)
checkpoint | Fittings & fixings (as per AS 2032)
checkpoint | Identification of services
checkpoint | Heights double checked before room sign off off fixture approvals tech data
checkpoint | Pipe risers sealed per floor and capped off to prevent damage
checkpoint | Correct ventilation
checkpoint | CCTV drainage
checkpoint | Testing (air testing to 15kpa)
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
type | name | values | prefix | postfix
checklist | CCTV Checksheet
checkpoint | CCTV Completed & Attached
button | Drains clear, free of obstructions & in acceptable condition | Yes, No
text | If No the above explain why
checkpoint | Final sign off - CCTV completed, Pass when satisfied to proceed (Any issues please comment & Add photos below)
section | Vacuum Drainage
checkpoint | Setout & alignment as per drawing (include revision below)
text | Drawing & revision number(s)
text | Material type (as per sample submission)
checkpoint | Correct invert level (as per AS 3500.2 Section 16)
checkpoint | Pipework fittings, bends, joints etc (as per AS 3500.2 Section 16)
checkpoint | Support & fixings (acoustic / seismic)
checkpoint | Pipework installation checked against standards (as per AS 3500.2)
checkpoint | Check no cross connection
checkpoint | Pipework water tested to 35-70Kpa
checkpoint | Identifications of services
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Inspection Chamber
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
text | Correct approved materials as per sample register
checkpoint | Manufacturer's Quality
checkpoint | Inspection Chamber Excavation
checkpoint | Inspection Chamber Installation & correct invert levels (as per AS 3500.2 Section 4.8)
checkpoint | Builder sign off prior concealment
checkpoint | Backfilling (as per AS 3500.2 Section 5.5)
checkpoint | Compaction of Material (As per Specification / Geotechnical report)
checkpoint | Clean and Flush
checkpoint | Inspection Prior to Closure
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Preform
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
text | Correct approved materials as per sample register
checkpoint | Manufacturer's Quality
checkpoint | Pit Excavation
checkpoint | Pit Installation & correct invert levels (as per AS 3500.3 Section 7.5)
checkpoint | Builder sign off prior concealment
checkpoint | Backfilling (as per AS 3500.3 Section 6.2.11)
checkpoint | Compaction of Material (As per Specification / Geotechnical report)
checkpoint | Clean and Flush
checkpoint | Inspection Prior to Closure
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Trench Grate
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
text | Correct approved materials as per sample register
checkpoint | Manufacturer's Quality
checkpoint | Trench Grate Installation & correct invert levels
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | In Ground Tank
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards nominated in ITP
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
checkpoint | Correct approved materials as per sample register
checkpoint | Manufacturer's Quality
checkpoint | Tank Excavation
checkpoint | Tank Installation & correct invert levels (as per AS 3500.1 Section 8)
checkpoint | Builder sign off prior concealment
checkpoint | Backfilling (as per AS 3500.3 Section 6.2.11)
checkpoint | Compaction of Material (As per Specification / Geotechnical report)
checkpoint | Clean and Flush
checkpoint | Inspection Prior to Closure
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Backfill & Compaction
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards
checkpoint | Location surface type as per approved drawings
text | Specify surface type
checkpoint | Minimum compaction requirement (%)
text | %
checkpoint | Compaction of Material (As per Specification / Geotechnical report)
checkpoint | Compaction layer thickness (mm)
text
checkpoint | Backfilling (as per AS 3500.3 Section 6.2.11)
checkpoint | Compaction test
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
bool | Area clean
section | Pump / Macerator Station
checkpoint | Employee trained for task
checkpoint | Latest specifications and standards
checkpoint | Setout & alignment as per latest available drawing (include revision below)
text | Drawing & revision number(s)
text | Correct approved materials as per sample register
checkpoint | Manufacturer's quality
checkpoint | Pit excavation
checkpoint | Pit installation & correct invert levels
checkpoint | Pump installed correctly
checkpoint | Guide rails installed correctly
checkpoint | All valves installed correctly
checkpoint | Pressure transducer installed correctly
checkpoint | Builder sign off prior concealment
checkpoint | Backfilling (as per specification / geotechnical report)
checkpoint | Compaction of material (as per specification / geotechnical report)
checkpoint | Clean and flush
checkpoint | Inspection and photos prior to closure
checkpoint | Final sign off - Pass when satisfied to proceed (Any issues please comment & Add photos below)
label | Passing above includes Builder sign-off
section | Commissioning Pump / Macerator Station
checkpoint | Condition as when it was installed (report any changes)
checkpoint | Control panel installed
checkpoint | Electrical wiring connected between pumps, controller & level sensing system installed correctly
checkpoint | Connected to BMS
checkpoint | Connected to power supply
checkpoint | BMS faults in working order (specify faults)
checkpoint | High level alarm in working order
checkpoint | Supplier commissioning sheet
bool | Area clean
section | Storage Tanks
checklist | Excavation & Backfill Checklist
checkpoint | Employee trained for task | Pass, Fail, N/A
text | Machine details (size & ownership)
checkpoint | Setout & alignment as per drawing (include revision below) | Pass, Fail, N/A
text | Drawing & revision number(s)
checkpoint | Excavation undertaken | Pass, Fail, N/A
checkpoint | Excavation details
text | Excavation depth
text | Excavation width
text | Excavation length
checkpoint | Delays if any | Pass, Fail, N/A
text | Delay details
checkpoint | Bedding material comply as per specification | Pass, Fail, N/A
checkpoint | Bedding material installed correctly | Pass, Fail, N/A
checkpoint | Backfill & compaction to specification | Pass, Fail, N/A
checkpoint | Excavation & Backfill Completed - Signoff | Pass, Fail, N/A
holdpoint | Principal Contractor Signoff