## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-020
Revision : 2
Client: |  | Wyndham City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd Cliffs Project |  | Rock Beaching | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications:
|  |  |  | Structure / Component: Beaching | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2025-01-17 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Inspection / Test Method | Acceptance Criteria | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Material Approval |  | Once per source | Verify rock source, size, and quality. | Rock to comply with AS2758.4 (Grading, density, and durabillity) and GWW specifications. | Material Test Certificates, Supplier documentation | WP |  | N/A
1.02 | Delivery Inspection |  | Per delivery | Check rock quality upon delivery. | No signs of contamination, segregation, or damage; size within specified range. | Site inspection | IP |  | N/A
1.03 | Subgrade Preperation |  | Every 500m2 | Inspect for compaction and grading. | Subgrade compacted to >95% MDD, Level within +/- 25mm of design, free from debris or soft spots. | Site inspection | IP |  | N/A
1.04 | Geotextile Placement |  | Per installation area | Verify installation, overlap, and anchoring | Overlap >300mm, securely anchored, free from tears, and installed per approved design. | Site inspection/records | WP |  | N/A
1.05 | Rock Placement - Base Layer |  | Continuous | Inspect placement and uniformity. | Rocks placed uniformly with no voids, ensuring interlocking; comply with specified grading. | Site inspection | IP |  | N/A
1.06 | Rock Placement - Top Layer |  | Continuous | Check surface finish and grading. | Surface finish within +/- 50mm of specified elevation; proper interlocking achieved. | Site inspection | HP |  | N/A
1.07 | Scour Protection Features |  | As required | Inspect additional stabilisation measures. | Installation of measures (e.g., concrete aprons or additional rock)per aprroved drawings. | Site inspection/records | WP |  | N/A
1.08 | Final Grading |  | Final | Measurre and verify surface levels and slopes. | Finished structure complies with design levels, gradients, and specified tolerances. | As built survey records, QA sign off | WP |  | N/A
1.09 | Erosion and Drainage Check |  | Post-construction | Inspect for potential scouring or drainage issues. | Ensure effective drainage and no areas prone to erosion around the structure. | Final inspection report, photos | WP |  | N/A
1.1 | Final Inspection |  | Final | Conduct visual and dimensional inspection. | Entire structure complies with GWW-approved drawings, specifications, and standard. | Final inspection records | HP
COMMENTS |  | _________________________________________________________________________________________________________________________________________________________ _________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent