## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1.32 - ROCK BEACHING (GWW) | itp |  |  |  |  | 1.32 - ROCK BEACHING (GWW)
section | 1 - Construction Works
checkpoint | 1.01 - Material Approval
label | FREQUENCY - Once per source
label | INSPECTION / TEST METHOD - Verify rock source, size, and quality.
label | ACCEPTANCE CRITERIA - Rock to comply with AS2758.4 (Grading, density, and durabillity) and GWW specifications.
label | RECORD OF CONFORMITY - Material Test Certificates, Supplier documentation
label | WP
date | Date Completed:
checkpoint | 1.02 - Delivery Inspection
label | FREQUENCY - Per delivery
label | INSPECTION / TEST METHOD - Check rock quality upon delivery.
label | ACCEPTANCE CRITERIA - No signs of contamination, segregation, or damage; size within specified range.
label | RECORD OF CONFORMITY - Site inspection
label | IP
date | Date Completed:
checkpoint | 1.03 - Subgrade Preperation
label | FREQUENCY - Every 500m2
label | INSPECTION / TEST METHOD - Inspect for compaction and grading.
label | ACCEPTANCE CRITERIA - Subgrade compacted to >95% MDD, Level within +/- 25mm of design, free from debris or soft spots.
label | RECORD OF CONFORMITY - Site inspection
label | IP
date | Date Completed:
checkpoint | 1.04 - Geotextile Placement
label | FREQUENCY - Per installation area
label | INSPECTION / TEST METHOD - Verify installation, overlap, and anchoring
label | ACCEPTANCE CRITERIA - Overlap >300mm, securely anchored, free from tears, and installed per approved design.
label | RECORD OF CONFORMITY - Site inspection/records
label | WP
date | Date Completed:
checkpoint | 1.05 - Rock Placement - Base Layer
label | FREQUENCY - Continuous
label | INSPECTION / TEST METHOD - Inspect placement and uniformity.
label | ACCEPTANCE CRITERIA - Rocks placed uniformly with no voids, ensuring interlocking; comply with specified grading.
label | RECORD OF CONFORMITY - Site inspection
label | IP
date | Date Completed:
checkpoint | 1.06 - Rock Placement - Top Layer
label | FREQUENCY - Continuous
label | INSPECTION / TEST METHOD - Check surface finish and grading.
label | ACCEPTANCE CRITERIA - Surface finish within +/- 50mm of specified elevation; proper interlocking achieved.
label | RECORD OF CONFORMITY - Site inspection
label | HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Scour Protection Features
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Inspect additional stabilisation measures.
label | ACCEPTANCE CRITERIA - Installation of measures (e.g., concrete aprons or additional rock)per aprroved drawings.
label | RECORD OF CONFORMITY - Site inspection/records
label | WP
date | Date Completed:
checkpoint | 1.08 - Final Grading
label | FREQUENCY - Final
label | INSPECTION / TEST METHOD - Measurre and verify surface levels and slopes.
label | ACCEPTANCE CRITERIA - Finished structure complies with design levels, gradients, and specified tolerances.
label | RECORD OF CONFORMITY - As built survey records, QA sign off
label | WP
date | Date Completed:
checkpoint | 1.09 - Erosion and Drainage Check
label | FREQUENCY - Post-construction
label | INSPECTION / TEST METHOD - Inspect for potential scouring or drainage issues.
label | ACCEPTANCE CRITERIA - Ensure effective drainage and no areas prone to erosion around the structure.
label | RECORD OF CONFORMITY - Final inspection report, photos
label | WP
date | Date Completed:
checkpoint | 1.10 - Final Inspection
label | FREQUENCY - Final
label | INSPECTION / TEST METHOD - Conduct visual and dimensional inspection.
label | ACCEPTANCE CRITERIA - Entire structure complies with GWW-approved drawings, specifications, and standard.
label | RECORD OF CONFORMITY - Final inspection records
label | HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | 1.33 - ROCK BEACHING (SRW) | itp |  |  |  |  | 1.33 - ROCK BEACHING (SRW)
section | 1 - Construction Works
checkpoint | 1.01 - Material Approval
label | FREQUENCY - Once per source
label | INSPECTION / TEST METHOD - Verify rock source, size, and quality.
label | ACCEPTANCE CRITERIA - Rock to comply with AS2758.4 (Grading, density, and durabillity) and SRW specifications.
label | RECORD OF CONFORMITY - Material Test Certificates, Supplier documentation
label | WP
date | Date Completed:
checkpoint | 1.02 - Delivery Inspection
label | FREQUENCY - Per delivery
label | INSPECTION / TEST METHOD - Check rock quality upon delivery.
label | ACCEPTANCE CRITERIA - No signs of contamination, segregation, or damage; size within specified range.
label | RECORD OF CONFORMITY - Site inspection
label | IP
date | Date Completed:
checkpoint | 1.03 - Subgrade Preperation
label | FREQUENCY - Every 500m2
label | INSPECTION / TEST METHOD - Inspect for compaction and grading.
label | ACCEPTANCE CRITERIA - Subgrade compacted to >95% MDD, Level within +/- 25mm of design, free from debris or soft spots.
label | RECORD OF CONFORMITY - Site inspection
label | IP
date | Date Completed:
checkpoint | 1.04 - Geotextile Placement
label | FREQUENCY - Per installation area
label | INSPECTION / TEST METHOD - Verify installation, overlap, and anchoring
label | ACCEPTANCE CRITERIA - Overlap >300mm, securely anchored, free from tears, and installed per approved design.
label | RECORD OF CONFORMITY - Site inspection/records
label | WP
date | Date Completed:
checkpoint | 1.05 - Rock Placement - Base Layer
label | FREQUENCY - Continuous
label | INSPECTION / TEST METHOD - Inspect placement and uniformity.
label | ACCEPTANCE CRITERIA - Rocks placed uniformly with no voids, ensuring interlocking; comply with specified grading.
label | RECORD OF CONFORMITY - Site inspection
label | IP
date | Date Completed:
checkpoint | 1.06 - Rock Placement - Top Layer
label | FREQUENCY - Continuous
label | INSPECTION / TEST METHOD - Check surface finish and grading.
label | ACCEPTANCE CRITERIA - Surface finish within +/- 50mm of specified elevation; proper interlocking achieved.
label | RECORD OF CONFORMITY - Site inspection
label | HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Scour Protection Features
label | FREQUENCY - As required
label | INSPECTION / TEST METHOD - Inspect additional stabilisation measures.
label | ACCEPTANCE CRITERIA - Installation of measures (e.g., concrete aprons or additional rock)per aprroved drawings.
label | RECORD OF CONFORMITY - Site inspection/records
label | WP
date | Date Completed:
checkpoint | 1.08 - Final Grading
label | FREQUENCY - Final
label | INSPECTION / TEST METHOD - Measurre and verify surface levels and slopes.
label | ACCEPTANCE CRITERIA - Finished structure complies with design levels, gradients, and specified tolerances.
label | RECORD OF CONFORMITY - As built survey records, QA sign off
label | WP
date | Date Completed:
checkpoint | 1.09 - Erosion and Drainage Check
label | FREQUENCY - Post-construction
label | INSPECTION / TEST METHOD - Inspect for potential scouring or drainage issues.
label | ACCEPTANCE CRITERIA - Ensure effective drainage and no areas prone to erosion around the structure.
label | RECORD OF CONFORMITY - Final inspection report, photos
label | WP
date | Date Completed:
checkpoint | 1.10 - Final Inspection
label | FREQUENCY - Final
label | INSPECTION / TEST METHOD - Conduct visual and dimensional inspection.
label | ACCEPTANCE CRITERIA - Entire structure complies with SRW-approved drawings, specifications, and standard.
label | RECORD OF CONFORMITY - Final inspection records
label | HP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP