## ITP-xxx
|  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document
Revision : 1
Client: | Department of Transport and Planning |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Safety Barrier Installation Princes Hwy Wellington Rd to James St |  | Safety Barrier Installation, NDD and Service Location |  | Name: | Justin Barnes | Name: | Cameron Beattie |  | Name: | Cameron Beattie
Contract No: | DOT36563 |  | Specifications: VicRoads Specifications Sections: 160, 166, 168A, 173, 175, 176, 201, 204, 602, 610, 703, 707, 708, 709, 714, 720, 750
|  |  | Structure / Component: Barrier Installation / NDD / Service Location |  | Signed : |  | Signed : |  |  | Signed :
|  |  | Location: Princes Hwy - Wellington Rd to James St |  | 2025-01-09 |  | Date : | 2025-01-09 |  | Date : | 2025-01-09
Lot No: |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Obtain up to date Dial Before You Dig (DBYD) Information | Prior to commencement | All current DBYD information received prior to commencement of works | 100.5(1) |  | This ITP signed + documentation received | HP* | Site Engineer | N/A |  | N/A
1.2 | Obtain necessary approvals and permits from the relevant service authorities | Prior to commencement | All current permits approved and issued prior to commencement of works | 100.5(1) |  | This ITP signed + Permits issued | HP* | Site Engineer | N/A |  | N/A
1.3 | Receival and activation of authorised Memorandum of Authorisation (MOA) | Prior to commencement | The Contractor shall not commence work until the relevant authorised MOA has been received and activated | 100.6 |  | This ITP signed + Authorised MOA's received | HP* | Site Engineer | N/A |  | N/A
1.4 | Submission of relevant PMP Documentation, insurances etc. | Prior to commencement | All PMP documentation submitted to DTP 14 days prior to commencement of works. This includes QMP, EMP, IERP, TMP, HSMP, SWMS | 160.C1 |  | This ITP signed | HP* | Site Engineer | N/A |  | N/A
1.5 | Submission of overall works procedure | Prior to commencement | Works procedures for GPP process, NDD, Service Location and TreeTrimming/Removal to be submitted to DTP 14 days prior to commencement of works | Fulton Hogan works procedures |  | This ITP signed |  | Site Engineer Project Manager | N/A |  | N/A
1.6 | Submission of Contractors representatives | Prior to commencement | List of contractor representatives submitted to DTP | 160.C6 |  | This ITP signed | HP | Project Manager Superintendent |  |  | N/A
1.7 | Review of Traffic Management Plan | Prior to commencement | The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point | 166.08 |  | This ITP signed | HP | Superintendent |  |  | N/A
1.8 | Road Safety Audit | Prior to commencement | First batch of MOA's and TGS's submitted for approval to be audited by an external auditor. | 100.1 100.6 100.7 |  | This ITP signed + RSA report received | HP | Project Manager Site Engineer Superintendent
1.9 | Condition of Site | Prior to commencement | Undertake precondition inspection of site prior to works commencing | MP4 / video file for records |  | This ITP signed | HP* | Site Engineer Project Manager Foreman | N/A |  | N/A
1.1 | Sign removal and installation | Prior to removal of signs | The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences. | 714.06 |  | This ITP signed | HP | Site Engineer Foreman Superintendent |  |  | N/A
2 | NDD and Service Location
2.1 | Service Location and marking | Prior to excavation, stripping, clearing/grubbing, ground penetration | All underground services must be located by a suitably qualified service locator. Where denoted NDD in the drawings, services must be visually inspected | 100.12 100.5(2) Drawings |  | This ITP signed | HP* | Site Engineer Foreman GPP Subcontractor | N/A
2.2 | NDD Works / service locating | Prior to barrier installation | NDD locations confirmed within 10 working days from submission of prior to completion of Non Destructive Digging (NDD) works | 100.5(3) |  | This ITP signed | HP* | Site Engineer Foreman GPP | N/A
2.3 | Approval of NDD information | Prior to barrier installation | NDD information supplied to DTP a minimum of 14 days prior to any works commencing on any safety barrier run. | 100.5 |  | This ITP signed | HP | GPP Foreman Superintendent |  |  | N/A
2.4 | Refilling of NDD potholing | Prior to leaving site for the day | Potholes refilled with compacted sand the same day | 100.5 |  | This ITP signed | WP | Foreman GPP Subcontractor | N/A
3 | Vegetation Works
3.1 | Approval for vegetation removal | Prior to commencement | Meeting held with DTP and Council to identify and mark trees / vegetation for removal and approval permits issued | 176.I1 |  | This ITP signed | HP | Site Engineer Project Manager Superintendent Council Representative |  |  | N/A
3.2 | Tree trimming | During NDD/Service locating works | Trees to be trimmed in accordance with specification and in designated locations as per drawings and Superintendent's advice | 201 Drawings |  | This ITP signed | WP | Foreman Superintendent Council representative Subcontractor
3.3 | Tree removal | During NDD/Service locating works | Trees can only be removed with the approval of Council Representative and Superintendent. All tree matter removed from site and holes left from tree stumps filled accordingly. | 201 Drawings |  | This ITP signed | WP | Foreman Superintendent Council representative Subcontractor
4 | Safety Barrier Installation
4.1 | Setout of barriers | Prior to barrier installation | Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence. Barriers to be set out in accordance with contract documentation and VR specification | 708.08 |  | This ITP signed | HP | Site Engineer Foreman Superintendent Subcontractor
4.2 | Approval of ground beam locations | Prior to barrier installation | Details provided to DTP and proposed location for ground beam approved prior to installation | 708.08 (a) |  | This ITP signed | HP | Site Engineer Project Manager Superintendent Subcontractor
4.3 | Compliant safety barrier installation | All barriers | All safety barriers installed within VR and Manufacturers Speficiation | Manufacturers specification |  | This ITP signed | AP | Site Engineer Superintendent Subcontractor
4.4 | Certification of steel for guardrail | All barriers | The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation. | 708.05 |  | Certificate received | AP | Site Engineer Superintendent Subcontractor
4.5 | Safety Barrier CoC documentation | All barriers | Certificates of Compliance issues for all barriers installed | 708.1 |  | CoC received | AP | Site Engineer Subcontractor | N/A
4.6 | As-constructed drawings | Completion of project | Submission of As-Constructed drawings to DTP within 20 days of practical completion | 160.A9 |  | As-constructed drawings | AP | Site Engineer Superintendent |  |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on J16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on J17: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L17: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on J18: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L18: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on J19: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L19: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on J20: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L20: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L21: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L22: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on J27: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on J28: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L29: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L32: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on L41: Rodrigo Anchico: Write "N/A" to disable the cell.