## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DOT36563 ITP - Safety Barrier Installation, NDD and Service Location | itp |  |  |  |  | DOT36563 ITP - Safety Barrier Installation, NDD and Service Location Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Obtain up to date Dial Before You Dig (DBYD) Information
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All current DBYD information received prior to commencement of works
label | REFERENCE DOCUMENTS: 100.5(1)
label | RECORD OF CONFORMITY: This ITP signed + documentation received
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Obtain necessary approvals and permits from the relevant service authorities
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All current permits approved and issued prior to commencement of works
label | REFERENCE DOCUMENTS: 100.5(1)
label | RECORD OF CONFORMITY: This ITP signed + Permits issued
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.3 - Receival and activation of authorised Memorandum of Authorisation (MOA)
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: The Contractor shall not commence work until the relevant authorised MOA has been received and activated
label | REFERENCE DOCUMENTS: 100.6
label | RECORD OF CONFORMITY: This ITP signed + Authorised MOA's received
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Submission of relevant PMP Documentation, insurances etc.
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All PMP documentation submitted to DTP 14 days prior to commencement of works. This includes QMP, EMP, IERP, TMP, HSMP, SWMS
label | REFERENCE DOCUMENTS: 160.C1
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Submission of overall works procedure
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Works procedures for GPP process, NDD, Service Location and TreeTrimming/Removal to be submitted to DTP 14 days prior to commencement of works
label | REFERENCE DOCUMENTS: Fulton Hogan works procedures
label | RECORD OF CONFORMITY: This ITP signed
label | RESPONSIBILITY: Site Engineer, Project Manager
date | Date Completed:
checkpoint | 1.6 - Submission of Contractors representatives
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: List of contractor representatives submitted to DTP
label | REFERENCE DOCUMENTS: 160.C6
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Project Manager, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Review of Traffic Management Plan
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point
label | REFERENCE DOCUMENTS: 166.08
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Road Safety Audit
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: First batch of MOA's and TGS's submitted for approval to be audited by an external auditor.
label | REFERENCE DOCUMENTS: 100.1, 100.6, 100.7
label | RECORD OF CONFORMITY: This ITP signed + RSA report received
label | HP
label | RESPONSIBILITY: Project Manager, Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Condition of Site
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Undertake precondition inspection of site prior to works commencing
label | REFERENCE DOCUMENTS: MP4 / video file for records
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Project Manager, Foreman
date | Date Completed:
checkpoint | 1.10 - Sign removal and installation
label | FREQUENCY: Prior to removal of signs
label | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | REFERENCE DOCUMENTS: 714.06
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer, Foreman, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - NDD and Service Location
checkpoint | 2.1 - Service Location and marking
label | FREQUENCY: Prior to excavation, stripping, clearing/grubbing, ground penetration
label | ACCEPTANCE CRITERIA: All underground services must be located by a suitably qualified service locator. Where denoted NDD in the drawings, services must be visually inspected
label | REFERENCE DOCUMENTS: 100.12, 100.5(2) Drawings
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Foreman, GPP, Subcontractor
date | Date Completed:
checkpoint | 2.2 - NDD Works / service locating
label | FREQUENCY: Prior to barrier installation
label | ACCEPTANCE CRITERIA: NDD locations confirmed within 10 working days from submission of prior to completion of Non Destructive Digging (NDD) works
label | REFERENCE DOCUMENTS: 100.5(3)
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer, Foreman, GPP
date | Date Completed:
checkpoint | 2.3 - Approval of NDD information
label | FREQUENCY: Prior to barrier installation
label | ACCEPTANCE CRITERIA: NDD information supplied to DTP a minimum of 14 days prior to any works commencing on any safety barrier run.
label | REFERENCE DOCUMENTS: 100.5
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: GPP, Foreman, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Refilling of NDD potholing
label | FREQUENCY: Prior to leaving site for the day
label | ACCEPTANCE CRITERIA: Potholes refilled with compacted sand the same day
label | REFERENCE DOCUMENTS: 100.5
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Foreman, GPP, Subcontractor
date | Date Completed:
section | 3 - Vegetation Works
checkpoint | 3.1 - Approval for vegetation removal
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Meeting held with DTP and Council to identify and mark trees / vegetation for removal and approval permits issued
label | REFERENCE DOCUMENTS: 176.I1
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer, Project Manager, Superintendent, Council Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Tree trimming
label | FREQUENCY: During NDD/Service locating works
label | ACCEPTANCE CRITERIA: Trees to be trimmed in accordance with specification and in designated locations as per drawings and Superintendent's advice
label | REFERENCE DOCUMENTS: 201 Drawings
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Foreman, Superintendent, Council representative, Subcontractor
date | Date Completed:
checkpoint | 3.3 - Tree removal
label | FREQUENCY: During NDD/Service locating works
label | ACCEPTANCE CRITERIA: Trees can only be removed with the approval of Council Representative and Superintendent. All tree matter removed from site and holes left from tree stumps filled accordingly.
label | REFERENCE DOCUMENTS: 201 Drawings
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: Foreman, Superintendent, Council representative, Subcontractor
date | Date Completed:
section | 4 - Safety Barrier Installation
checkpoint | 4.1 - Setout of barriers
label | FREQUENCY: Prior to barrier installation
label | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the Superintendent the required location and length of all guard fence. Barriers to be set out in accordance with contract documentation and VR specification
label | REFERENCE DOCUMENTS: 708.08
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer, Foreman, Superintendent, Subcontractor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Approval of ground beam locations
label | FREQUENCY: Prior to barrier installation
label | ACCEPTANCE CRITERIA: Details provided to DTP and proposed location for ground beam approved prior to installation
label | REFERENCE DOCUMENTS: 708.08 (a)
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer, Project Manager, Superintendent, Subcontractor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Compliant safety barrier installation
label | FREQUENCY: All barriers
label | ACCEPTANCE CRITERIA: All safety barriers installed within VR and Manufacturers Speficiation
label | REFERENCE DOCUMENTS: Manufacturers specification
label | RECORD OF CONFORMITY: This ITP signed
label | AP
label | RESPONSIBILITY: Site Engineer, Superintendent, Subcontractor
date | Date Completed:
checkpoint | 4.4 - Certification of steel for guardrail
label | FREQUENCY: All barriers
label | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: 708.05
label | RECORD OF CONFORMITY: Certificate received
label | AP
label | RESPONSIBILITY: Site Engineer, Superintendent, Subcontractor
date | Date Completed:
checkpoint | 4.5 - Safety Barrier CoC documentation
label | FREQUENCY: All barriers
label | ACCEPTANCE CRITERIA: Certificates of Compliance issues for all barriers installed
label | REFERENCE DOCUMENTS: 708.1
label | RECORD OF CONFORMITY: CoC received
label | AP
label | RESPONSIBILITY: Site Engineer, Subcontractor
date | Date Completed:
checkpoint | 4.6 - As-constructed drawings
label | FREQUENCY: Completion of project
label | ACCEPTANCE CRITERIA: Submission of As-Constructed drawings to DTP within 20 days of practical completion
label | REFERENCE DOCUMENTS: 160.A9
label | RECORD OF CONFORMITY: As-constructed drawings
label | AP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: