## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 2 | itp | CHK-001-CIV-Stormwater Drainage Pipes Installation |  | aa8cf543-13db-40aa-b7c2-844f6f7c80f6
| section | Referenced Documentation
| checkpoint | Referenced Documentation
b1dece8b-320e-5f03-bea4-d6cc7e86dbcf | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
5b2e91cb-7fc8-5608-b824-210769628860 | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
89cbc121-9693-5a66-8fda-83497881e5ca | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
45883644-3603-524d-8db0-a2073837a0f8 | note | Discipline (e.g. CIV/STR/RAIL): CIV
784756f4-439a-52d4-b873-db7269832303 | note | Revision Number: 2
8ba7c0fa-ab61-5cfa-a35e-15afdcc71cc7 | note | Revision Date: 7/12/2023
9bfd0648-f500-5441-92fd-35f422f19210 | note | ITP created by: Victor Mira
e3e462ac-bde1-5ac0-b474-ef8fe5be88d4 | note | ITP approved for use by: Victor Mira
a3d11e14-7f99-5a81-bb52-7314d4559336 | note | 1.1 Non Dependent
0d6661d2-cf07-5a31-8893-8e85c559eb40 | note | Reference: VR 701
f5d661f7-b46e-51f8-8c50-e0a4a55713a7 | note | 1.2 Main ITP
20a126bc-d9e0-53d3-9da6-4a4b7108a8d4 | note | Reference: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
64e644a3-35a0-5e40-a7ed-4d6b16429d06 | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
adf430eb-788e-5e7b-89f8-587a5b058061 | textbox | Enter: Main ITP Lot Number
| section | Preliminaries - Materials
| checkpoint | 2.1 Bedding
0b36b268-ce3a-5cda-8fcf-fa70e495a207 | note | REFERENCE: VR 701
543eebfc-3791-526e-9bd5-5dabe41fb58a | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
04ae4900-0c63-5594-8a56-4b21aa86b749 | note | METHOD: Document Review
debf6564-dc10-58cc-a1a9-a55bd6c85b30 | note | FREQUENCY: Each Lot
63cdf1d6-7f22-55ec-8f42-08c0ea74d824 | note | CATEGORY: HP*
ae64a7f4-bf32-5f8e-a8c9-ae9ec4d140f7 | note | RESPONSIBILITY: SE
f72dd6b9-a78d-5f17-9295-8862c78327f5 | note | VERIFYING DOCUMENTS: Material Delivery Docket
d219760d-6f0b-5c8e-909b-81c8c7798338 | date | Date Completed:
| checkpoint | 2.2 Backfill Material
46a5e3e0-6dc6-5182-b358-e0a9deb6726d | note | REFERENCE: VR 701
03dafda0-6f04-5a8a-bc31-7744df2836de | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
6978dab9-1199-5b6d-ad4f-915b7f002336 | note | METHOD: Document Review
9750fd14-2393-5539-b9b8-8f8cc35dce2d | note | FREQUENCY: Each Lot
0b2e1404-d737-5ffa-99b3-a31fac2ca0b3 | note | CATEGORY: HP*
d8710aec-e1f6-5b7b-8652-96382e6a711a | note | RESPONSIBILITY: SE
e8c5bb31-21d8-5246-b0e1-9765c56a080f | note | VERIFYING DOCUMENTS: Material Delivery Docket
affadd9d-a024-5bea-86cf-e54802dbfd64 | date | Date Completed:
| checkpoint | 2.3 Stabilized Sand
2b0f8474-58af-5d8b-a796-97651902a889 | note | REFERENCE: VR 701
b68c8441-b1f1-5382-8ec6-f08ed513e248 | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
57fcf703-7548-5dac-a028-3d6eca268362 | note | METHOD: Document Review
8f7f82ae-703b-595b-b726-7b86e5898211 | note | FREQUENCY: Each Lot
3abd029e-227c-5703-86a1-c82ac928cb64 | note | CATEGORY: HP*
8fc47305-3a6a-5f05-9c1d-b0c16e503894 | note | RESPONSIBILITY: SE
5358996e-e0f6-5131-bb20-8c717caa968d | note | VERIFYING DOCUMENTS: Material Delivery Docket
b713a6e3-bb0f-57fd-bc59-c3955dc3a3d1 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Subcontractor QA Submissions and ITP
dd0f2d9b-9b24-5294-9026-a1a0b1e8006e | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
24a2dcc5-4fc6-5dec-8c1e-96c7dbbf94de | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
8ed531b7-f0e5-5ca4-862d-4d81f6e4de70 | note | ATTACH: Subcontractor Signed ITP
b78644bb-ea40-5caf-b586-362ddd1f6b64 | note | METHOD: Document Review
60eb5fd9-bf4b-5333-b07d-21cf723dc9d1 | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
9eff7623-9631-5b95-9fa3-72acacef1d8d | note | CATEGORY: HP*
b5ad3ee9-b878-5e4e-832a-fea8e0ab8f1d | note | RESPONSIBILITY: SE
4ec0b7af-5239-5fa0-956f-343c6cc539f6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
dc431774-7ae0-5dc6-8c8d-2c528867f646 | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 Survey Set-Out
c2282f5a-b8ea-570c-aee2-9703ecb62b4d | note | REFERENCE: 710.10
797659a0-a56c-59ab-93ea-2b1dbb174f0e | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
b917af37-64bb-59b8-aad6-e0e232e224c9 | note | ○ The culverts constructed shall be constructed true to line and level.
024aca26-882f-5325-bcc9-37b0df477294 | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
964653f2-652d-5507-9251-e6c47ac43a23 | note | METHOD: Survey, Measure
1d9028c6-00d2-5cf8-b6ff-cdd7dc2fde53 | note | FREQUENCY: Each Lot
7c0f39a8-f269-575b-820e-c57a4a7f8d38 | note | CATEGORY: HP*
4ba07a9c-d680-5525-9c11-ba78e2246b5d | note | RESPONSIBILITY: SE
5a2d5334-a3cc-5c9b-95ff-33dd6e068858 | note | VERIFYING DOCUMENTS: This ITP, Main Lot Map
c8980374-fa54-5422-9909-08477bf60a9b | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Trench Excavation
10dd7a34-1d21-55d2-b7cd-8d4cd37bf18f | note | REFERENCE: VR 701.15
e0655f80-0382-5de7-988f-d81dabb0ce05 | note | ACCEPTANCE CRITERIA: For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
20932b62-5589-5c94-b4a2-e6dd4f18d430 | note | Horizontal Clearance to wall of trench
4527244d-624e-5e5e-8cc8-4a158980a91a | note | Pipe Culverts:
595b112e-b94b-5885-aaf6-80edc5c90d28 | note | ○ 300mm<Horizontal clearance for corrugated metal culverts<1000mm
aaa5c6bf-66ad-54cc-affd-2b94ed8edc35 | note | ○ 300mm<Horizontal clearance for other Pipe culverts<600mm
d1fa284f-a7da-5b8c-8d06-8302019c8a49 | note | Box Culverts:
65475937-292f-55cc-bfa3-9bafe43e6afb | note | ○ 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
bb7235f2-8eab-50ff-b5eb-2a39d82c36bc | note | METHOD: Measure
de709c6c-b62b-56fd-b2f1-076f2509ae1f | note | FREQUENCY: Each Lot
36df3b93-313d-57a1-b249-85bf880074ac | note | CATEGORY: IP
b163b685-34e7-5df1-9d80-13644e42cb28 | note | RESPONSIBILITY: SE
86dfd443-441c-533d-a939-52cb9d76c0d6 | note | VERIFYING DOCUMENTS: This ITP
329ff529-9fd2-5440-9734-19e832980e4c | date | Date Completed:
| checkpoint | 5.2 Trench Base
728aa9c6-3096-51fd-8b9a-ed6555932494 | note | REFERENCE: VR 701.15
2905db11-bf18-50dd-85e6-2031ae3da4d8 | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant
f04d3520-6320-5527-ab07-d2745ae118f0 | note | METHOD: Visual
83076747-457b-53a3-8abd-d6587098b0b0 | note | FREQUENCY: Each Lot
2aa165b4-5951-5a84-9850-93961eb0a8f0 | note | CATEGORY: SP
8cac7e92-88b9-50c6-9ec8-6b360b0dd5a0 | note | RESPONSIBILITY: SE
4a0343ec-eebd-507b-83eb-416418fa870e | note | VERIFYING DOCUMENTS: This ITP
03056e4a-d680-5677-a8e2-d622baed0187 | date | Date Completed:
| checkpoint | 5.3 Bedding-Placement and compaction
c43bfa13-6741-5a50-811d-b4a44537efc5 | note | REFERENCE: VR 701.16, VR 701.20 (a)
6e2c384e-7dd0-5b82-8298-04ae68b6e721 | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
c6c013f3-a164-5519-9bd0-c5b23a5e37e1 | note | ○ 100 mm where D < 1500 mm
f77b0413-5d8c-5628-b554-7e17763e48ba | note | ○ 200 mm where D ≥ 1500 mm
ac3bccc1-3bb9-5904-9ab1-fefbbbb1b388 | note | Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
5c437689-3c90-5975-b8ed-0674c3bad6a9 | note | METHOD: Visual, Measure
218a8726-1adb-58ec-a25b-a885c167e781 | note | FREQUENCY: Each Lot
f5855308-fc28-5eb6-9d49-c06f5d7eb424 | note | CATEGORY: SP
6a976c88-861e-567d-982e-ba48bc265375 | note | RESPONSIBILITY: SE
730f87f3-fe60-544d-b196-bf3d2c0fd733 | note | VERIFYING DOCUMENTS: This ITP
7ffd5247-cd6b-59e4-890a-ee46fcdb0d8e | date | Date Completed:
| checkpoint | 5.4 Laying pipes-Bedding conformity
adaaeaef-0d63-580d-911e-f1a823c41046 | note | REFERENCE: VR 701.17
07c0b3c9-4ebb-5d75-8e9e-b7ed43799328 | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
45942d14-cfad-5283-b9c8-f7048465f74c | note | ○ Laying of pipes or box culverts shall commence from the downstream end.
1daec5e1-086f-554a-bd47-1f2017d83012 | note | METHOD: Visual
7c51c851-065f-51cc-9594-f288604d115e | note | FREQUENCY: Each Lot
9cc827cf-0cd7-5f5a-b5cf-fa3301472b33 | note | CATEGORY: HP*
26c1ab6f-a11c-51c5-8e0a-13ec54e8ac01 | note | RESPONSIBILITY: SE
c886ac85-7ead-5c90-9b95-6ec063e62a8d | note | VERIFYING DOCUMENTS: This ITP
01082f63-d017-503e-a6f5-f9dc64601db0 | date | Date Completed:
| checkpoint | 5.5 Pipe Laying
c6530a39-e7d5-53a0-a093-fc6b643b28b1 | note | REFERENCE: VR 701.16, VR 701.17
6f75ec44-aa8c-5076-b75c-964807424665 | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall commence from the downstream end.
78931b84-52b8-5c34-a45d-3cb155d7cf22 | note | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
56305124-9c8c-505d-a02f-45d7376edd66 | note | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
c420ed5e-2259-5388-b26c-87f9cd310719 | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
da8e9a7e-eaa0-5fdf-af18-ce266ec554e7 | note | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
68c292f3-65a6-5333-805c-a795a0e337ec | note | METHOD: Visual
13267c4d-9933-51eb-9c6e-a1f2793e7e88 | note | FREQUENCY: Each Pipe
b99c9766-ae86-5c70-93c1-48a08a149b90 | note | CATEGORY: SP
2236b5fa-f32c-58bd-a65f-1c3da00850ca | note | RESPONSIBILITY: SE
668a2d1c-4519-5287-bb2a-f084bc7e1026 | note | VERIFYING DOCUMENTS: This ITP
b19e6b85-ba2f-5ff6-a70d-797644cb7bea | date | Date Completed:
| checkpoint | 5.6 Pipe Joints and rotation
94c40845-1252-5b4c-91bb-934d825ce561 | note | REFERENCE: VR 70.18
cef64d7d-888c-54cf-a4dc-b94a7c4eb1bf | note | ACCEPTANCE CRITERIA: All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
590ec354-7414-53d0-8586-640db5f1970e | note | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
0097a504-1ada-589c-b608-c0dc33141781 | note | METHOD: Visual
d1cf2ee8-7ba6-594a-b1f1-7e538d7afce9 | note | FREQUENCY: Each Pipe
e7b1eb92-8f19-5713-973e-a75cdcccf4ee | note | CATEGORY: SP
b24b35cf-f618-55ac-9a4d-7a347ed5398a | note | RESPONSIBILITY: SE
625b21cb-eec5-5434-914e-47d294f7c2b1 | note | VERIFYING DOCUMENTS: This ITP
5cbd7178-b531-53e7-b961-5836f0d7309b | date | Date Completed:
| checkpoint | 5.7 Conformity with drawings
96ef94ea-e8bc-5318-8e68-53d342b5aba1 | note | REFERENCE: VR 701.10
c5e5cb9e-e17a-5a7e-8223-bebb90e0825d | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
5942c81a-5773-5bee-ae01-89c28ccc2173 | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
2e6051a1-7fed-556d-aae9-4ed09d64c194 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
0854e21a-6b84-5772-ad9b-98135fa1a1e8 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
fb2d99a1-0ed9-51e0-828c-04c225300b4e | note | (c) invert level of pipes at pits ±50 mm
c70957fc-51dd-5a71-b588-1c60fa2b8496 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
52e47aa6-0178-52bc-a654-bb12b22f9c87 | note | ATTACH: Survey Report
a9759810-a442-5f01-bfe1-85a9ccb9fb90 | note | METHOD: Measure
bca36410-8d53-5f24-8102-21b7239c6cad | note | FREQUENCY: Each Lot
61b66fb8-e260-5d52-a1fa-d6d73d930c0c | note | CATEGORY: HP*
679c50ee-a545-5f8f-a2e1-263e08fd7776 | note | RESPONSIBILITY: SE
74d28269-9384-5762-92b8-8950cbc1d145 | note | VERIFYING DOCUMENTS: Survey Report
708df606-2739-5184-b46b-882e3ac1b0ec | date | Date Completed:
| checkpoint | 5.8 Backfill-Under area to be paved
0ecfe407-8db6-545f-a954-00fe87a16d73 | note | REFERENCE: VR 701.19 (a) i
f6aee447-b8dc-59f6-a0b4-7f4c90956082 | note | ACCEPTANCE CRITERIA: Culvert under area to be paved
991aa84b-f2ab-5878-9b8a-bf98adca5955 | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
c00400a7-8db9-5897-8019-60178e89c355 | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
8ba2f810-cf7d-5568-bcb1-abbfccea86ed | note | METHOD: Visual
c0a5f155-255b-577f-948e-8df8ad73ef61 | note | FREQUENCY: Each Lot
acbc417d-5b41-5662-9229-f8a5d1cf0b94 | note | CATEGORY: SP
94f14696-6bbb-5a4b-a084-bd4d35668f13 | note | RESPONSIBILITY: SE
9bad6892-1740-57a1-9a48-7e81deccd206 | note | VERIFYING DOCUMENTS: This ITP
1940ff1e-2a2b-5d0e-9d05-cf8043d39b9b | date | Date Completed:
| checkpoint | 5.9 Backfill-Under area not to be paved
ac587971-4c0b-51a4-bd83-4592cfa97cc5 | note | REFERENCE: VR 701.19 (a) ii
c71159a1-7b74-5aca-810c-a71bfb0a1e1b | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
6b577fe6-95f9-56d1-91f7-4885ae7aeeb9 | note | METHOD: Visual
2b5e8070-7bc2-5ee6-8f56-5c591762484b | note | FREQUENCY: Each Lot
fa1fb367-088f-509d-b75b-d92cb64adbdd | note | CATEGORY: SP
f8b9344b-b7d3-52e3-b6f3-fc7cc18e81a1 | note | RESPONSIBILITY: SE
a2e2b509-da64-5a19-849b-6d32f9025b28 | note | VERIFYING DOCUMENTS: This ITP
59a28c4b-0c13-50d8-84c1-c5e2220d3f2c | date | Date Completed:
| checkpoint | 5.10 Backfilling with cement stabilised sand
88341e2b-4839-55ba-a81d-b3b3ab568d63 | note | REFERENCE: VR 701.19 ( c)
afb641fe-9078-5011-b03a-379c2e3b74a8 | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
09092c86-6254-50e7-8ce6-c776ad5c9918 | note | METHOD: Visual
d2d59e25-7b53-5740-85c2-8a2f7402cf3c | note | FREQUENCY: Each Lot
7951f93b-0ae7-5c0e-a888-53b74fc4d123 | note | CATEGORY: SP
8f36aeff-5b47-56f7-a72b-2428c370108f | note | RESPONSIBILITY: SE
a2eeb583-01da-5564-88b8-feb03692a3fe | note | VERIFYING DOCUMENTS: This ITP
9325fbac-7ef4-5bfb-a739-daca94562d80 | date | Date Completed:
| checkpoint | 5.11 Backfill Placement
edecb0cf-aae3-5c0d-ad34-0c15674d69a5 | note | REFERENCE: VR 701.20
038b2690-c2e2-5de8-90ff-d1791bc50a7d | note | ACCEPTANCE CRITERIA: backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
09f4d551-fc44-55f9-87ea-5aaed635ee61 | note | METHOD: Visual
e364fff4-6a63-5396-82aa-52cfc02ef50a | note | FREQUENCY: Each Lot
15f651ba-6563-503c-b902-59c2a26c62d3 | note | CATEGORY: SP
0f15d7bd-5e1d-56c7-af27-9958846c219c | note | RESPONSIBILITY: SE
c33285cd-b014-5a61-8446-9a434a38eaa7 | note | VERIFYING DOCUMENTS: This ITP
cf8eeb18-c1f3-5620-8458-1feb9d9e527a | date | Date Completed:
| checkpoint | 5.12 Backfill Compaction
c5aa5f67-f0a9-538e-8abf-6eba37d0ca24 | note | REFERENCE: VR 701 (b)
5322690b-d6e5-58c4-b203-198356c782b0 | note | ACCEPTANCE CRITERIA: 20% of all bedding/Backfill layers for each culvert shall be tested.
731340ed-fc80-5770-8c1b-fd8ea75385f5 | note | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
18306498-39d5-5408-96ec-b929b341ef4c | note | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
550ff429-84d7-54c6-b3c8-b02462be8a02 | note | METHOD: Test
e79190dd-315c-555b-a1f2-f434fb1a1a7e | note | FREQUENCY: Each Lot
4ffcff48-b178-5ff7-9ad3-a60697e7f575 | note | CATEGORY: HP*
23504c87-8e9f-5abc-8844-93742a1d3d52 | note | RESPONSIBILITY: PE
f91e49dc-925e-50ce-9c94-804933a1f750 | note | VERIFYING DOCUMENTS: This ITP
955ad31b-4fc5-50ac-831f-809b20a2a7b4 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Compaction and Moisture content tests
bd303d66-8d57-55de-ac3c-ed77fc013a6b | note | REFERENCE: VR 701.20
aa737218-0400-5d7a-984e-64b6ac5a7422 | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
12f35f77-925b-53f1-b105-0ef630c49e2b | note | ATTACH: Compaction and Moisture content test results:
93c730a8-a809-57dd-9be5-560fc1fbe2be | note | METHOD: Document Review
1548800b-1468-5023-8228-6a6a8326f1c8 | note | FREQUENCY: Each Lot
0b1f7f6f-531d-5579-9071-251fe20c7511 | note | CATEGORY: IP
bdb1bb63-4019-53fb-a291-52d37a943cd8 | note | RESPONSIBILITY: SE/PE
6d6d0f4a-97ae-51c6-96e1-ce8a8307f1fe | note | VERIFYING DOCUMENTS: Test Results
43f261e5-2ac2-5ea7-9e55-ae730c8bfcee | date | Date Completed:
| checkpoint | Final Inspection
c6a8f0c4-3161-5b5b-a149-53a60062a9ba | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
4a45ca88-857d-54b5-898c-7f4cba7ba9ce | textbox | Name:
b442326f-2cdf-5483-9aa6-d6a9ffdd8aee | textbox | Position:
edf7353b-649c-57a9-a958-5bcc5efacea9 | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-002-CIV-Stormwater Drainage Pit Installation Rev 2 | itp | CHK-002-CIV-Stormwater Drainage Pit Installation |  | 6cce7d99-4222-45fb-a483-afc97e114c9e
| section | Referenced Documentation
| checkpoint | Referenced Documentation
1059b5dd-322e-5f33-8128-e1503fb29acb | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pit Installation
e2cc06ed-68f3-5ce0-8c54-9667e3faf1a6 | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
0b1c8c27-715a-5535-b71e-c34282f8c3bb | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
01af07ba-8a0e-5b4a-bc46-d153421a6234 | note | Discipline (e.g. CIV/STR/RAIL): CIV
2744e92b-4729-5b7c-b859-992bc31eac15 | note | Revision Number: 2
88cf025b-7341-5612-84b3-a32d245e445c | note | Revision Date: 6/12/2023
9dd9946b-a8e4-5159-acee-f343bcd6fe37 | note | ITP created by: Victor Mira
3905a3d1-8b6e-5ab5-824a-56846384204a | note | ITP approved for use by: Victor Mira
541e4ad2-1e7b-5b46-ac4f-27534d5bcda0 | note | 1.1 Non Dependent
a26d74fa-72d8-5007-9ffc-672a7cfb911b | note | Reference: VR 701
736d0272-15d3-5945-a59c-cb35488ad7fa | note | 1.2 Main ITP
5d5fcd0e-4ba1-5dc8-bc5a-6730db80d40c | note | Reference: Project Storm water Drainage Main ITP
b9ed2c67-5868-5f41-90ef-bbfc7f55562b | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
972e75a1-6fca-5b87-a005-2b9a1c100c21 | textbox | Enter: Main ITP Lot Number
| section | Preliminaries - Materials
| checkpoint | 2.1 Bedding
1f6d8c56-2959-5348-afe1-e36e9aa9722f | note | REFERENCE: VR 701
a13fa797-fba4-5fb3-af44-6451d973fe7d | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
e1b36fe7-cb2c-5dfe-b29d-415fc35d56ec | note | METHOD: Document Review
5420bf31-0fcb-59a8-a2aa-86e8cd822a9f | note | FREQUENCY: Each Lot
57dbf6d4-52ce-5b51-9a9e-8c8c47521c8b | note | CATEGORY: HP*
badfcd8a-e9e1-58c1-802e-04ba8e384842 | note | RESPONSIBILITY: SE
f8f19f5d-4244-5b95-8f97-f9b9c8e6d394 | note | VERIFYING DOCUMENTS: Material Delivery Docket
04ec41dc-d554-58bf-bfe2-09f259d857d5 | date | Date Completed:
| checkpoint | 2.2 Backfill Material
39f7f10a-d625-5b6b-8648-46a064593462 | note | REFERENCE: VR 701
36d2907d-44f3-59cf-a6a8-47a3ae904bd3 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
d6fc9a17-a65c-5e71-b32f-457126b2c2bb | note | METHOD: Document Review
35ab21ae-84a1-5ddb-acd9-6d9c467feddf | note | FREQUENCY: Each Lot
7e48bacd-d9fa-5dbb-a3d6-51afa87be37d | note | CATEGORY: HP*
d234bc48-2817-50c4-959c-5b3c08d6e5e7 | note | RESPONSIBILITY: SE
9ac22a2c-deee-5bac-8023-53a6938c1a62 | note | VERIFYING DOCUMENTS: Material Delivery Docket
baeadcd2-b733-553d-a3ef-c906bc31d2b7 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Subcontractor QA Submissions and ITP
e625595c-4e07-5605-a395-9c61f46435ca | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
82046a45-8a6d-5734-952e-4dded890a124 | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications..
50e15413-630f-50dc-a7e4-609456aaa596 | note | ATTACH: Subcontractor Signed ITP
5e4a13c5-74b1-53c0-a71d-2a1cd4189f7e | note | METHOD: Document Review
01fddb99-91d0-5089-abf8-9523249652ed | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
374233fb-6d54-537f-8c01-11b8af368d84 | note | CATEGORY: HP*
e8a16dae-7948-5fa9-8ccf-4195baf159a6 | note | RESPONSIBILITY: SE
8842c718-b322-53f3-974d-786e1a6e3618 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
341424e0-6da0-56c5-aac1-fd1050f29500 | date | Date Completed:
| section | Construction Activities
| checkpoint | 4.1 Survey Set Out
95090731-2672-530e-9b11-ce618974a790 | note | REFERENCE: VR 701.10
bf54edec-cb70-59e1-84c6-6cbc686c8198 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
031c0c4d-8f8f-5e14-9eff-7e2087f8916e | note | METHOD: Visual inspection
0626a794-60bf-52da-860d-5a7c9c4a45e6 | note | FREQUENCY: Each Lot
093dec7e-5951-5cc3-b314-103b66cd46ba | note | CATEGORY: HP*
a335cde0-427c-51fa-8b23-c27296d4f355 | note | RESPONSIBILITY: SE
325fd8e8-163a-5a9f-9fb0-52633219f4ea | note | VERIFYING DOCUMENTS: This ITP
746d2174-d9b3-5563-9ccf-ea684a674ca4 | date | Date Completed:
| checkpoint | 4.2 Pit Excavation
f1d17630-c86c-5eeb-8a82-945ca448f6b5 | note | REFERENCE: VR 705.05
93689cd3-0bc3-5cde-aa71-5292e0e1eb60 | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
f9c8b174-6945-5df0-b490-0c3ea9a4980f | note | METHOD: Visual inspection
360339a1-6cef-5c29-9229-6d8ecd4203d0 | note | FREQUENCY: Each Lot
112051c7-b560-5064-8367-3cf2a9ea60bf | note | CATEGORY: IP
60d88eed-d574-5ddc-8d69-8ee09b0cb94d | note | RESPONSIBILITY: SE
e2ece3dc-3972-5b37-b869-e21b3fd9dfc5 | note | VERIFYING DOCUMENTS: This ITP
d1bff01a-a105-55d7-bade-9506c810c533 | date | Date Completed:
| checkpoint | 4.3 Excavation Foundation
8edd3bb3-89d2-5579-9b51-cab83d5ac43d | note | REFERENCE: VR 705.05
79a022d7-a1e6-53c7-9f21-ff72343efe34 | note | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
b817ca89-5200-57a7-a7e7-d0552008bc66 | note | > 80mm for clay foundations
8da2fbea-a14c-542c-ae87-e8acfff3b7a7 | note | > 150mm for rock foundations
f0b822e5-6c4f-52a5-a0f2-c418ea734399 | note | METHOD: Visual inspection
5b7e0648-11f6-594e-827a-a573ed3ae77e | note | FREQUENCY: Each Lot
4724b2d3-beff-57b9-ba65-35eaefdbac40 | note | CATEGORY: IP
961e3b25-e5d9-5e3a-9f27-f92f8ed5346e | note | RESPONSIBILITY: SE
054393d0-58da-52f2-a5af-e5dd1a25028e | note | VERIFYING DOCUMENTS: This ITP
0573c1b3-add8-5c43-870c-eae160198830 | date | Date Completed:
| checkpoint | 4.4 Jointing
b6b71a95-cd37-5e09-a730-8b5ab7820b82 | note | REFERENCE: VR 705.11
9f9ae5a4-564a-51af-9b77-9f461a7c5421 | note | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
ddd2bfce-97c7-57b1-96e0-9e8197d8ef9b | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
098ddcb3-63c4-57f7-b5dc-22005942ad0e | note | METHOD: Visual inspection
87c72705-e162-5805-9baa-52b3dd359a19 | note | FREQUENCY: Each Lot
89f641e9-8cf1-503f-8129-40072b1b189d | note | CATEGORY: IP
9e4f424d-e4be-5bc4-90dc-2c58091dfadb | note | RESPONSIBILITY: SE
cba1d4c5-1330-5c94-b5be-019f76f21310 | note | VERIFYING DOCUMENTS: This ITP
9c45999b-ffd9-5c9f-9a72-a15b40d7b097 | date | Date Completed:
| checkpoint | 4.5 Shaping of Floor
9d9f6745-d765-5de4-8eea-6b0497b3a2d0 | note | REFERENCE: VR 705.13
8e34bb91-1c87-5b4b-9b00-752998b68e09 | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
14748ec2-f1e3-585d-ac6f-fe87645a913e | note | METHOD: Visual inspection
c10a2d91-2a60-5972-b471-0e894e9e3d96 | note | FREQUENCY: Each Lot
43504930-5091-514a-b812-d0fb63b08f3e | note | CATEGORY: IP
8e7968d3-aa23-5cc9-9763-2d48daa8369b | note | RESPONSIBILITY: SE
1757c5de-8312-5381-a3eb-cca15ee15c8a | note | VERIFYING DOCUMENTS: This ITP
68dcdc2c-38da-5112-a880-c2f89e89d7ce | date | Date Completed:
| checkpoint | 4.6 Step Irons
2d50c676-09ac-5a41-a525-b071b0a5178a | note | REFERENCE: VR 705.12
b06af494-85c6-5ec8-82da-7c4d0fd44939 | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
2ebea370-6686-5cc0-94f5-7aa92bf8b42c | note | METHOD: Visual inspection
d2d309a2-9e8c-5073-bca2-e6defad0f237 | note | FREQUENCY: Each Lot
1b444b30-905b-5002-82e7-3c8db8cb38a6 | note | CATEGORY: IP
01037711-359e-5898-b7d5-0d591caa7fcf | note | RESPONSIBILITY: SE
822b2a8e-970b-587b-9f93-6f39a07253a3 | note | VERIFYING DOCUMENTS: This ITP
84d3e685-18e5-5d6c-a72b-d4e274952b66 | date | Date Completed:
| checkpoint | 4.7 Fitting of Covers
5330c520-7349-5c20-a4d9-6acd4861ccfd | note | REFERENCE: VR 705.17
d040e1a8-104a-5ce9-93a7-be3986651bfb | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
96cebb8e-c83e-5e90-aecb-4614eaf5ef0e | note | ○ Height shall be within 10mm of the design level
e830d3cc-0374-52d2-ac8d-1b61709c147e | note | METHOD: Visual inspection
ed5e2a0d-c26e-5c84-950f-f919c10545ca | note | FREQUENCY: Each Lot
39a7633b-9aad-518b-a406-3abd528ca50d | note | CATEGORY: IP
2aa60c86-76b5-554f-a39c-1841bbaffa30 | note | RESPONSIBILITY: SE
63854145-da0c-5cc3-9335-29a8a575f0ff | note | VERIFYING DOCUMENTS: This ITP
92b18ea5-1d7d-50d9-871c-7e0d6c14a4a4 | date | Date Completed:
| checkpoint | 4.8 Backfilling Around Drainage Pits
99449984-7ef5-55c4-bed1-2b2e4c6eee8d | note | REFERENCE: VR 705.18
98c05316-785b-5a0b-97cd-05042bed1e1a | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
4c3cd8bd-3f44-565d-a5e3-f635f75b4d4a | note | METHOD: Visual inspection
506b5cf2-3b16-517b-a60c-d4bddd38a0a0 | note | FREQUENCY: Each Lot
ac79961c-75dc-5a1f-9296-2f6afeed61bb | note | CATEGORY: IP
4f366c07-0275-5a30-9cfb-dddb22cae1eb | note | RESPONSIBILITY: SE
9306df1c-acc2-5800-b696-8a0bfaf8ac8a | note | VERIFYING DOCUMENTS: This ITP
c27a24ef-cf2f-5138-8c45-55ee11934b3f | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Placement of Pit-Conformity with drawings
2d5a5548-3d32-50e0-8260-a3ca84560c46 | note | REFERENCE: VR 701.10
982dcd11-c865-5129-b9c0-0f65357d56ef | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
c2c576e5-01c4-51b6-8f53-0330bc6e48a3 | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
6849767f-ee2f-5c2b-8464-9e7d3b012739 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
20aa2a37-9cea-5cc9-87b0-961c47c986a2 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
1f42dd70-9f13-58f9-9fc4-38d47466d360 | note | (c) invert level of pipes at pits ±50 mm
9fb8b063-e730-55c3-878a-d75907c3da71 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
f73e87ed-ff0c-5f0a-9098-63c5a316b624 | note | ATTACH: Survey Report
89b1ae99-5e67-5ffc-8567-d502e8adc381 | note | METHOD: Measure
6efc8eff-d2ee-5d1b-be3e-f2516ffe7e0b | note | FREQUENCY: Each Lot
87343b12-b3b3-5fbf-b779-5fd4049021ef | note | CATEGORY: HP*
c5036daf-cdc5-57df-bc9b-00c8ba2c42b6 | note | RESPONSIBILITY: SE
a8647564-923a-53a0-8520-4d60fdff406e | note | VERIFYING DOCUMENTS: Survey Report
241ba779-cb1f-5804-abaa-7d40f05e982f | date | Date Completed:
| checkpoint | 6.2 CCTV Inspection
7bcd0375-d644-5be7-a40e-6def36da4fe0 | note | REFERENCE: VR 701.30
184755e6-84d3-551e-97a4-fbc3f6c1e9a0 | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
44a4a3ff-0537-5214-b738-08c862f723bc | note | ATTACH: CCTV Report (PDF):
f75b31b0-1ba7-5374-8f5c-753c7e939afd | note | METHOD: Document Review
d3fa30b7-2538-54bb-838f-bef6b139f004 | note | FREQUENCY: Each Lot
fb549aef-76af-5873-b110-80537fbefdb7 | note | CATEGORY: HP
b2edbf57-a43b-5f91-8450-5a868ee2425a | note | RESPONSIBILITY: Nominated Authority
8f65017c-ca9b-5c74-9def-f13708e6d70b | note | VERIFYING DOCUMENTS: CCTV Reports
f368172f-f26c-5e4f-8330-8ea86a18e590 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
fac3e35c-b455-5910-bc21-6892b3de02b6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c5b73a63-fc06-5829-a78f-7eaf7288db6a | textbox | Name:
ba690567-9f64-520e-9e7b-abb3460ae5b0 | textbox | Position:
e78e7ba8-0989-5dbb-ad68-d64aad9fc1d0 | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-003-Civil-Material Delivery Inspection-Precast Pits and RCPs Rev 0 | itp | CHK-003-Civil-Material Delivery Inspection-Precast Pits and RCPs |  | eda3aa5c-306f-477e-83a4-0bf807433b49
| checkpoint | Referenced Documentation
be1d4509-9d47-52f8-a5bc-e306a7d036a2 | note | Document Title: CHK-003-Civil-Material delivery inspection-Precast Pits and RCPs
9d7351df-1c63-528c-9bfd-026800063515 | note | ITP Description: Material delivery inspection-Precast Pits and RCPs
b8414883-3e40-5e40-ae14-95abd319ebcd | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
f7134f6e-6cc7-57e7-8723-7816f23f3097 | note | Discipline (e.g. CIV/STR/RAIL): 003-Civil
fe011665-f134-544d-b6a5-fa908ed75af0 | note | Revision Number: 0
a24cd612-4bf9-576c-9adf-37c2068bee10 | note | Revision Date: 6/12/2023
b092acb1-f660-5211-b39e-fd5498c318d3 | note | ITP created by: Victor Mira
3050289a-d891-5dc9-9dc1-16afe0868239 | note | ITP approved for use by: Victor Mira
| checkpoint | 1 - Delivery Details
bf888bbb-e426-5780-bec0-226074aa7290 | note | ACCEPTANCE CRITERIA:
cf42f3f7-5145-581e-9aab-b2d514a47cc7 | textbox | Enter: Delivery Docket Number:
e9b709c1-d152-563a-a29f-d8d90aa16cdf | textbox | Enter: Delivery Date:
f908076d-14b2-5c45-89f5-9f6066b261ae | textbox | Enter: Element ID (s):
16099a67-b219-535e-89b7-55484b0fa252 | note | Attach: Delivery Docket and packaging Slip
15dce400-7cd7-590e-9bbe-f327798c6000 | note | METHOD: Document Review, Visual
989992d8-6171-552b-91a0-86680d655213 | note | FREQUENCY: Each Delivery
d7f55c53-d549-59b8-9f51-05d79ce1b62c | note | CATEGORY: IP
3f6af3b3-a2ce-5d85-815f-49fefefcad64 | note | RESPONSIBILITY: PE/SE
9c2b40cf-8ba1-564e-8184-26fdad1f2f1e | note | VERIFYING DOCUMENTS: This Checklist
0a28494c-c4f2-56d0-8f5a-e8269f51897a | date | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
edf91b52-bfd8-56b6-a8cb-f369295f1ca9 | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
e6814c1d-0ccd-5844-922e-ad0c22032eb9 | note | METHOD: Visual
2dd37412-9696-58ba-a74a-8e2de1777840 | note | FREQUENCY: Each Delivery
cefc7dc9-7514-564d-8d54-b475ccbd2914 | note | CATEGORY: IP
9256d912-2787-5f75-b387-c9453af8a9dc | note | RESPONSIBILITY: PE/SE
48744d8c-99cd-5018-b8f6-f02ef154a058 | note | VERIFYING DOCUMENTS: This Checklist
74e014a8-7bcc-5001-9a53-737b55d2610f | date | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
4df401f9-8960-53a9-b469-cfadbbf71442 | note | ACCEPTANCE CRITERIA: Do the contents of the delivery match the freight list/packaging slip?
683761b7-bdd2-58c8-a5f0-53f1c4b8b400 | note | METHOD: Document Review, Visual
14051d1a-d59e-52c2-a1c9-17d7c3740061 | note | FREQUENCY: Each Delivery
044adf34-e7df-5e12-ae93-356e75457ad4 | note | CATEGORY: IP
90831b46-8024-5c73-baf1-73d37c8ece26 | note | RESPONSIBILITY: PE/SE
ff65b49e-55b7-5966-86d4-e95d698ca4c2 | note | VERIFYING DOCUMENTS: This Checklist
7cedf3fc-73dd-5ca7-bd8e-f877172119d1 | date | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
7b932e97-9bcb-558c-8074-b05238f8c041 | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
571f1a5a-7274-5ee9-be22-e8d919d5b0f2 | note | ○ Precast components are to be marked on the birth certificate.
a7254cb3-9175-5f4b-8787-a05b9a157427 | note | ○ Cast date and lot are to be marked on the birth certificate.
0b34de6d-f367-5673-ba80-beb461d4c1a0 | note | METHOD: Document Review
727ad533-3b07-54ef-9354-8878be0feac0 | note | FREQUENCY: Each Delivery
da27e886-6cf8-5835-a21c-3943c6592696 | note | CATEGORY: IP
f685850b-b13c-52d2-8d69-1c93af1e47a2 | note | RESPONSIBILITY: PE/SE
d37c9f15-b3fb-53ea-8df1-a5e9f811007d | note | VERIFYING DOCUMENTS: This Checklist
a1ab8964-1b48-54a9-8292-f2a1b3641cd1 | date | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
7e51c573-2cc0-5c5f-a5d0-835e18b4ca36 | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
1456bc17-a3a7-56f1-b0d4-50a42bf5662c | note | ○ Precast items are protected from damage during the transport
f3d08b9a-e04d-5536-935b-a3a2039d8981 | note | METHOD: Visual
09357f07-661d-563b-af17-f91428e2bc06 | note | FREQUENCY: Each Delivery
b27f52f4-9226-5d42-a08b-e444d30b4d5f | note | CATEGORY: IP
4e8bd3ee-db82-5dff-97fe-727bf939a7b0 | note | RESPONSIBILITY: PE/SE
9afa5f25-ef47-5f51-aac4-69e53cf42780 | note | VERIFYING DOCUMENTS: This Checklist
d9d6399b-58ff-57ed-b01b-9db2a578b1d2 | date | Date Completed:
| checkpoint | 6 - Fault IDs:
22b2e01b-ec08-518b-92eb-0b17e09f21c0 | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
f126b8cf-1cdb-5f6f-87db-ad7176ad91e4 | note | 1 - Identification markings match the Precast type
00ddcecd-3021-5e05-94f5-f7c62370ebd3 | note | 2 - Precast Pit fabricated as per drawings - inverts size.
b1981768-527a-5aee-85fd-3f860f1866a9 | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
9906b2b4-0433-50d1-910e-342b13beb0eb | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
5c56ded8-1bb2-5b5b-83ea-17d9d7c35d2a | note | 5 - Precast Pits - Inverts coliding.
e675c9b2-c6e5-5deb-896e-59af67524f72 | note | 6 - Precast Pits and RCPs - Inspect for Cracks.
0ded8a6f-1b3a-5ba8-a045-44641a438a5d | note | 7 - Precast Pits and RCPs - Inspect for Spalling/Damage to concrete surface.
a987a1ea-c7e1-5860-aa2b-059058606ef6 | note | 8 - Precast Pits and RCPs - Inspect for Exposed Reinforcement.
2d24bfbf-5aa8-53b3-b589-02361ad7f004 | note | 9 - Precast Pits and RCPs - Inspect for correct Lifting mechanism.
2bf78551-2c7b-58fd-b557-253bdd486c99 | note | 10 - RCPs - Inspect rubber rings
3ede2c37-e263-5f0a-81f7-8aba6ff2be9d | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
61b265a2-7741-5162-9de1-17c3a31e3f54 | note | METHOD: Visual, Measure
038a0460-ad96-5bdd-a6c3-718a98ae15b8 | note | FREQUENCY: Each Delivery
06a8196d-3e45-51a2-b644-6ee5d9904362 | note | CATEGORY: IP
f2dc4bac-3807-5a2d-9ad6-97095c90ab43 | note | RESPONSIBILITY: PE/SE
db5045c7-69dd-51a7-b942-6e10f4ddca33 | note | VERIFYING DOCUMENTS: This Checklist
f6470be4-0736-5aa9-a3d3-c3c1ce7d6b3e | date | Date Completed:
| checkpoint | 7 - Check for Faults - 1
56edcacb-0a28-5257-aa27-d5996d999a22 | note | REFERENCE: Item 6 on this Checklist
231c30c2-0fd8-5a61-a11f-ef5282cdb046 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
09c3ad32-59c4-5a42-9e65-28c2470e2df6 | textbox | Enter: Panel Identification
a828bf58-8825-5ffe-95ee-8e6c6d7c3a9f | textbox | Enter: Quantity
89b25c3c-6e73-5b0b-84de-3134d7ae80a2 | textbox | Enter: Fault ID if any
8c93cba5-6e79-5434-9142-c2ae0248fe39 | note | METHOD: Visual, Measure
a4e3c3fe-0f61-5485-be25-194317f316f5 | note | FREQUENCY: Each precast type delivered
f49cf2c7-1eed-546e-9271-ba023a9200cc | note | CATEGORY: IP
dc7167fb-9692-5811-9462-afd03f08f06c | note | RESPONSIBILITY: PE/SE
7705db87-a5ed-5263-92c1-69ccc1a0c55f | note | VERIFYING DOCUMENTS: This Checklist
99ee7cd6-b843-5d7a-b2b2-6d8537e694ce | date | Date Completed:
| checkpoint | 7 - Check for Faults - 2
47f275bc-3cd0-56de-bf33-4bc7b85eaf57 | note | REFERENCE: Item 6 on this Checklist
2cb7f630-6401-5870-b568-6fd6d9d0d394 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
358d7608-8d3d-594b-8c6f-31bdf9d6a977 | textbox | Enter: Panel Identification
43a32293-12c9-549f-ad8e-f5edb713d99d | textbox | Enter: Quantity
d68e7110-4d3a-52d6-a524-1f5b4b667acb | textbox | Enter: Fault ID if any
a425ad1c-f646-50fd-bca4-548030b43ff1 | note | METHOD: Visual, Measure
f5e0870b-e2a4-540e-a705-d6adb13bb7b5 | note | FREQUENCY: Each precast type delivered
512f4bb4-b902-5144-9ec7-2ff11a425500 | note | CATEGORY: IP
e0f525a8-f6b1-5368-9561-b868fb1a213e | note | RESPONSIBILITY: PE/SE
ebc50cb4-6282-500e-99ed-e6db236359f6 | note | VERIFYING DOCUMENTS: This Checklist
4d14a96b-26b2-5acf-a90a-f50f02e565d3 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 3
7163d552-e551-5af3-9007-4f8742973eb9 | note | REFERENCE: Item 6 on this Checklist
33c43c0a-b93d-5de2-884d-2ee098649cc2 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
a0d67bfb-7128-50c3-8e6d-aeb88d737d34 | textbox | Enter: Panel Identification
c4ee366e-33d7-5175-b0d7-8bcd33b8185e | textbox | Enter: Quantity
21508273-52d4-5bca-9466-78b32de7af26 | textbox | Enter: Fault ID if any
ac393090-b4a4-5625-97bc-ea56faa58761 | note | METHOD: Visual, Measure
79cc5455-a250-59c5-aad6-111960ab6e43 | note | FREQUENCY: Each precast type delivered
28acaffb-44ef-52af-a2a5-a562e1bfb031 | note | CATEGORY: IP
53d7016f-2ad0-58e4-8ba9-019c6a5bf7c1 | note | RESPONSIBILITY: PE/SE
f36e0fd1-66f0-52dd-90b3-fe061ddf657b | note | VERIFYING DOCUMENTS: This Checklist
95b238d6-7f99-5e7f-bb78-de075e3cf2db | date | Date Completed:
| checkpoint | 7 - Check for Faults - 4
bea9c3f5-001d-5720-8faf-950cfa706c60 | note | REFERENCE: Item 6 on this Checklist
025d3f75-4f7c-5bf4-9fd7-f8ed22329df4 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
25943a12-755f-594d-99c4-a4b079cd1ad4 | textbox | Enter: Panel Identification
69b308c9-551e-5c93-a2e2-9dfaa0d3cce8 | textbox | Enter: Quantity
10b55baa-3869-53de-9a85-2ccbe33a609e | textbox | Enter: Fault ID if any
b9374a20-2d84-55cf-9207-237304f8c070 | note | METHOD: Visual, Measure
e3cd5376-9a2c-5e18-bbd9-c86f76cb0080 | note | FREQUENCY: Each precast type delivered
be1bf93b-f9cc-56f1-bad0-f13e15f54df0 | note | CATEGORY: IP
7dd498d1-967b-5258-ad14-a85ebd3c4986 | note | RESPONSIBILITY: PE/SE
3fdaf2bc-6ee5-569f-b514-60ca25f0a59c | note | VERIFYING DOCUMENTS: This Checklist
d7fb09fa-5120-51e5-8538-5d758f53d66c | date | Date Completed:
| checkpoint | 7 - Check for Faults - 5
fef9a71a-21db-5bcf-9054-1d0c7ce60314 | note | REFERENCE: Item 6 on this Checklist
dcfc25cd-bae7-5d2d-9d8b-e47871235bd9 | note | ACCEPTANCE CRITERIA: For Each Precast type delivered:
fb4d79c9-03fb-5f18-8e7b-211f3e0165b4 | textbox | Enter: Panel Identification
3e32db60-486e-5e21-8a5f-d9bbda8cc2db | textbox | Enter: Quantity
d043088a-4bbf-56e8-824b-8c88a68bc1ae | textbox | Enter: Fault ID if any
5f47be41-175d-5e85-b8d2-545df0d7d973 | note | METHOD: Visual, Measure
28354ba6-9979-5873-9242-4f35ff608ca8 | note | FREQUENCY: Each precast type delivered
8ed74d92-226a-5076-a13d-f12ce3bb8282 | note | CATEGORY: IP
d3c1c813-73e7-5373-ae62-e87f4a66ac7a | note | RESPONSIBILITY: PE/SE
12308c40-7d4e-5592-aa7a-a51d0175f098 | note | VERIFYING DOCUMENTS: This Checklist
144b4a25-1154-5db2-aa48-cc4fa2aab5b1 | date | Date Completed:
| checkpoint | Final Inspection
252ea524-ef47-509e-905d-d5ffb40a63e9 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
de981dee-ce50-528a-872e-7f0f689299f4 | textbox | Name:
5ca4ecfa-e261-54b0-bf76-d6abb9e0cfda | textbox | Position:
271c363c-d9b7-5746-a79d-46ea54b89f2d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-077-CIV-PSDS-Subgrade Preparation-Road Rev 0 | itp | ITP-077-CIV-PSDS-Subgrade Preparation-Road |  | 488e1df5-291e-44b1-b81d-ee5185a4ad71
| section | Referenced Documentation
| checkpoint | Referenced Documentation
a48d66c0-894e-5948-bcf0-f12038958b0d | note | Document Title: ITP-077-CIV-PSDS-Subgrade Preparation - Road
e4625747-28d3-5d68-97e8-94c26c9addeb | note | ITP Description: PSDS-Subgrade Preparation - Road
e07b4132-2d59-5588-8116-6299a6a41330 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
a1fb18e9-1b6e-5b6a-9795-0ae974c79ab5 | note | Discipline (e.g. CIV/STR/RAIL): 077-CIV
c4e99df4-6dc6-5da0-89d7-544f5ac74162 | note | Revision Number: 0
d4ac226b-638e-5029-97e8-5c0a1b35f9d9 | note | Revision Date: 21/12/2023
cf9c0afe-e511-52bc-8c79-02d58d2aa527 | note | ITP created by: Victor Mira
7d696924-d706-5012-9ac7-8926a1377758 | note | ITP approved for use by: Victor Mira
01659c66-156d-5fb1-87da-bc4ecf55b634 | note | 1.1 Non Dependent
68322612-12a9-54e4-845f-99f754678b3b | note | Reference: VicRoads Section 204
a5a168a6-6025-53a3-a2a9-d38e8151352f | note | 1.2 Non Dependent
030abb92-c8a0-593c-87ce-ff1dac02e5d1 | note | Reference: VicRoads Section 173
| section | Mater
| checkpoint | 2.1 Material Approval
cc15bfa8-a92a-528f-b683-b763359bbc9d | note | REFERENCE: VR 204.04 (C) MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
2f808ccf-5ed5-5ae1-9e34-6a85b1c92459 | note | ACCEPTANCE CRITERIA: Material used for subgrade preparation shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
9acf7b0b-7f5d-5be3-bb6a-5736d53ea27e | note | ○ Material shall have a minimum Assigned CBR as indicated in IFC Drawings, and Assigned Percent Swell less than the value indicated in the IFC drawings.
fac73c56-d541-5da3-9530-9d2e76868063 | textbox | Enter: Teambinder Material Approval number
850f6036-ff71-5106-88b2-58b289e536e6 | note | METHOD: Document Review
074c6e03-92ca-5500-b0c7-ae8691924f13 | note | FREQUENCY: Once, for each mix material
15181c2e-91d2-5488-ac25-5467450cc34d | note | CATEGORY: HP
1bbbe49b-49fc-5037-a64a-7af98851e402 | note | RESPONSIBILITY: Nominated Authority
89ab2191-180c-5228-a77b-fcdea24433af | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
234388bc-6245-592c-8bed-5debae54122e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documentations
| checkpoint | 3.1 Non Dependent
1ff798c2-cded-59c0-9e6a-9cab0dfb8de9 | note | REFERENCE: N/A
ddc9dc8e-8164-5966-826a-f6be59044572 | note | ACCEPTANCE CRITERIA: N/A
1762311f-f4e4-5d4d-989c-9b787bf86bef | note | METHOD: N/A
df5b8439-1a06-5e21-ac3c-ff41faea2956 | note | FREQUENCY: N/A
2627712e-b1b3-5100-bedf-25f806ef4c74 | note | CATEGORY: N/A
1ec6e44e-8c08-51ae-a5ff-53e60a8dbb82 | note | RESPONSIBILITY: N/A
fe104d15-102f-5866-96e2-603b689e1ffb | note | VERIFYING DOCUMENTS: N/A
5739eac9-a4cf-529c-8a51-c6d511b644a8 | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-Out
19635583-96de-5188-8ed6-8fcf1a175ee4 | note | REFERENCE: IFC Drawings
ca61ebc4-1b11-537c-ac02-6ae5c8bf310e | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
ac3f2fb2-ea7a-538f-a165-a971e03f8b0d | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
22f0bb1f-257f-5524-ab8a-c15d26e087ad | note | METHOD: Verify
8ef44350-162d-5450-b89e-12e250451eb2 | note | FREQUENCY: Prior to commencement of excavation
8a7e0f6d-4d8b-504e-9c31-517d0fc5278a | note | CATEGORY: IP
f9989393-29e5-5a82-ac88-4bc452bc2655 | note | RESPONSIBILITY: SE/Surveyor
8aef91a2-1c2f-5ba2-8075-8b3b94123e86 | note | VERIFYING DOCUMENTS: This ITP
a11ebe6a-e07c-531b-8640-b466849e24ea | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Inspection of Subgrade Material-Subgrade Material Properties
8b49d3ee-1485-59b1-8ab7-7d4a4122d2ef | note | REFERENCE: Section 204.06 (c), Section 204.06 (e), IFC Drawings: MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage, Barriers, Pavements & S&L)
7fcba309-6c96-55e3-a0fb-3354dbda15e6 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
bb592932-f611-535d-8124-031b734afc9e | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
50c70d7b-31d9-56f5-a8e0-820092814215 | note | ○ Assigned CBR and swell as per MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
bd37584b-7ac8-5b2e-8bf9-b2030955bdfb | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
d1d0db08-e4d9-533d-8374-614421c81848 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming fill material.
79002180-6cb4-5127-a239-42b3dd31d7d9 | note | Attach: Laboratory testing Verification:
d783471c-e79c-5c40-8c5e-d50b43dfb6f2 | note | METHOD: Verify-Document Review
1090dbbe-8389-545f-a516-a9aa6d504999 | note | FREQUENCY: Each lot
287341f8-6704-55c6-904d-26beccd89343 | note | CATEGORY: HP
3ad806cb-6e5f-5b61-8c93-0e2a7f48e8fd | note | RESPONSIBILITY: PE/Nominated Authority
8af4e62f-1690-50f6-9b4f-7345e9493022 | note | VERIFYING DOCUMENTS: This ITP/Test Report/Referenced Lot number
ef611fa3-a1b8-521a-bcf3-40e923678645 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.2 Material classified as silt
cb416677-a3ac-5900-9358-ac3816737845 | note | REFERENCE: Section 204.04 b)
c18d3959-9e28-57a1-b333-e2ab2f5f6cc3 | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
4d981136-0c33-52d6-892a-9d662d45051b | note | METHOD: Document Review
0d7eb51b-2703-5b11-8a5e-140235a12efe | note | FREQUENCY: Prior to commencing
e0347212-d188-5189-9f4b-42cc9808f345 | note | CATEGORY: HP
5cd2bd63-77a3-5912-a566-59f4d1af3cb3 | note | RESPONSIBILITY: SE/Nominated Authority
018d11ce-2fa0-5f41-b52e-d994a892ef35 | note | VERIFYING DOCUMENTS: Superintendent satisfied with Stabilisation, Signed ITP/ records
36c02dea-1c81-5758-99c6-4e524afb6b91 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 Acceptance of Rock Subgrade (where applicable)
a415de54-5414-5e28-b921-bab68b677b37 | note | REFERENCE: Section 204.06 f)
fb3fa1aa-ec7c-56ba-a16f-8f3465d546d5 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
28c010bb-e311-519b-8890-8ebda4e7c879 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
a24d7df8-eb75-516c-b24d-c8d4a4eb2830 | note | METHOD: Site Inspection/ Document Review
6117c7fb-35f8-5346-9a66-d05e8a8a2ae0 | note | FREQUENCY: Prior construction of the regulating layer
e3265566-ae82-55a5-ba1a-d475618d7878 | note | CATEGORY: HP
46d25171-3039-54d1-9e6c-c592a9751adb | note | RESPONSIBILITY: SE/Nominated Authority
33ae55b9-af72-51db-8c54-cd9e93d8336a | note | VERIFYING DOCUMENTS: This ITP
b2f5c12c-ec3c-5119-a27d-0ff876128f8c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Unsuitable Material
6c34d66f-33b3-5f39-8c74-0b121909e397 | note | REFERENCE: Section 204.07 d)
175b4207-c731-5c4e-8076-f3221ace154f | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
79a574d6-67d3-54de-bad6-137030f79c75 | note | METHOD: Visual inspection
9f4212d5-1fda-56df-ad8e-a4b54e61f662 | note | FREQUENCY: Each lot
4664e2d1-1d52-5e3d-a1be-7c46d05eff75 | note | CATEGORY: HP
64d6a90f-0f2e-58d8-be79-aeac97d97b49 | note | RESPONSIBILITY: SE/Nominated Authority
cf580054-16ca-521d-bb28-35a2e9cfb12f | note | VERIFYING DOCUMENTS: This ITP
9a7ae309-1678-5d9e-815b-2c825f562eb7 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.5 Groundwater
6374f297-f20c-5080-ae6e-1d972ad71967 | note | REFERENCE: Section 204.06 h)
777f3cd5-2834-5b62-acf1-d79e9a666d13 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
1ff029de-f2d0-5be5-ad96-c018104ccc0e | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
a8a85504-b511-52b9-9f4e-781d1b80027b | note | METHOD: Visual inspection
d02b1dd3-570c-5d5d-9e19-5301cbb10969 | note | FREQUENCY: Each lot
33399df5-fb99-5621-9290-8190cc1c8e28 | note | CATEGORY: HP
bff287bf-2c2f-5692-8487-fbaa299bb1ea | note | RESPONSIBILITY: SE/Nominated Authority
7aa007fe-0304-589a-871c-74777fc61d33 | note | VERIFYING DOCUMENTS: This ITP
7e61b246-c266-5d09-bd7f-474e03f50a85 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.6 Cut to Fill Zones
b66ca4b7-c5dd-5c68-89f5-dd2a85077d42 | note | REFERENCE: Section 204.06 g)
f6197293-7543-5b44-953a-c8a4c15aacf2 | note | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
cc9054fc-a599-58e8-8501-a625d1fe38d5 | note | METHOD: Site Inspection
a2c52e45-0c33-5e0b-a346-fc8b00816d6b | note | FREQUENCY: Each lot
0b4c5976-3380-5b5d-91f3-ff75d6551cb7 | note | CATEGORY: IP
c793e3cb-704b-55fc-8b27-68f4b8c30e9f | note | RESPONSIBILITY: SE/Site Supervisor
482c74f1-14ab-587d-b896-b9f55b3e4dcc | note | VERIFYING DOCUMENTS: Sign ITP
7b814770-6342-525f-9f0d-9ecb4f235c24 | date | Date Completed:
| checkpoint | 5.7 Proof Roll
58413b66-18bd-5f48-9205-57cf85e897e9 | note | REFERENCE: Section 173
40b47644-8cdc-5737-ba28-efbf10387014 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
d852f588-d496-5015-ad9f-c51b229ea7a4 | note | METHOD: Visual inspection
d823eca5-496c-5ad2-807a-e13f2077fcbd | note | FREQUENCY: Each lot
877c4d70-462a-58c1-a37c-5d5c89044ab4 | note | CATEGORY: HP
33cbee85-1ee1-555f-89d1-0c0b7bf59ed3 | note | RESPONSIBILITY: SE/Nominated Authority
f9971d4c-b3e7-5d97-9801-0883591c37bb | note | VERIFYING DOCUMENTS: This ITP
a76c35ab-61a3-5393-a4ec-e1fb448bec22 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.8 Compaction Testing
a7563933-9f7c-5de5-aa4d-117f3ea7bfa3 | note | REFERENCE: Table 204.131
87ded265-10e3-5b1e-b30c-7f8a0222ec44 | note | ACCEPTANCE CRITERIA: All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
d8219a23-6d62-5ad7-9885-931ce5f1b2ff | note | ○ Ripped and re-compacted material below Cut Floor Level
c9d20ddc-12c8-5418-b20b-ebb2566b122c | note | ○ Scale A: Characteristic Density Ratio 99%.
43e332ec-aa2e-50ee-94fd-fce70971b523 | note | ○ Scale B: Characteristic Density Ratio 98%.
6d2ec4fe-9495-5fe7-b701-4ceb2b07bcdc | note | ○ Scale C: Mean Value of Density Ratio: 100%
8a527c56-27d4-5bae-8991-29cb988e94e7 | note | Attach: Compaction Test Result:
d9227e81-6b5a-55b7-9dce-d6d4cdb6c434 | note | METHOD: Document Review
ef9e40c4-a03c-559d-9f68-b51224da58d3 | note | FREQUENCY: Each lot
05e255b5-c832-5dd9-9f92-1f9db2a2b9d1 | note | CATEGORY: IP
9515a711-81ed-51aa-965e-cf7b42d3b2ef | note | RESPONSIBILITY: PE/SE
b84415de-0e85-5672-9b8a-cc3f214f463d | note | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report
a59bf131-f58b-5594-9f99-c266cae7be01 | date | Date Completed:
| checkpoint | 5.9 Post Compaction Material Property Testing
83c24d6d-6edf-5454-b90c-5f00b8970753 | note | REFERENCE: Section 204.04 (c), Section 204.14 (a) and Table 204.141 For Scale A, Section 204.14 (b) for Scale B, IFC Drawings MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
4513759f-40d4-5e16-aca3-8848d0aa3b16 | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
aeee463a-3202-5656-864f-854d8499493e | note | Scale A:
b4e0bcb8-f56c-59f9-9478-659a5917e9ac | note | ○ CBR and Swell as per IFC for design packge:
a3b3620c-4e4d-5790-9e28-88f099a2129e | note | – MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
f4a1b736-1d4f-5a44-9062-268913f29c7a | note | – as per table VR 204.141
64a75462-a4ba-516e-9542-40995a6f2add | note | Scale B:
ee35fdc8-1e6f-50d7-9299-57f888379ebe | note | ○ CBR and Swell as per IFC for design packge:
3d381e3f-1707-5333-af5e-2d4b067b7216 | note | – MRP-DPK-091-00-CFN-0011 - Civil Details (Drainage,Barriers,Pavements & S&L)
8a99a9fd-4297-590e-911e-eca277aee5d2 | note | First Lot for Max Particle Dimension:
d4a9cb62-b3d5-5d27-9905-1b7bfdcb83c2 | note | After compaction Type B material shall have a maximum particle dimension of not more than:
4699934c-8c0b-52c4-9754-fe33e7cdf35c | note | ○ 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
10e55403-a23e-5b3f-a682-90d2650b5e65 | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
c6cd8e80-76f0-5a20-9c4a-bf3cc7722451 | note | Attach: Post compaction test results:
a072a3c3-154d-5eee-873f-3e2da5c24086 | note | METHOD: Review Document
57189ab2-8ce6-54bc-94c3-74d0d8e81100 | note | FREQUENCY: Refer to Section 204
6ee5ce3f-ea17-58e8-9a35-2d61ad511855 | note | CATEGORY: IP
84dc2d14-f7a7-56f7-9fb2-9735a3b727d8 | note | RESPONSIBILITY: PE/SE
511f3356-2368-56c3-8a87-8c4a77cb41ac | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
941d41e2-6a88-5824-ac7d-82169fef9861 | date | Date Completed:
| section | Post Construction Activities
| checkpoint | 6.1 Survey Conformance
5a406530-61a9-5247-9109-90eec95d2b05 | note | REFERENCE: VicRoads 204.03f,g and h
fca6c499-fe25-59ab-bd4f-05f260d22fae | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
02f12284-dfb6-58a1-ba8e-e58a7d8271d8 | note | Level tolerances (Scale A):
165d2c6a-fcf9-58f0-ab8e-d5d2fed45bce | note | ○ Range x = +5, -15mm
bf1e2a7e-ea85-5c05-912a-5fc5d6edcf0c | note | ○ Max S = 12 mm
5dd1a84a-57f1-513b-ba72-12444be54cc9 | note | ○ 80 measurements per lot
fb0b64f9-1d4c-5ae0-bfbe-977129c3a54c | note | Level tolerances (Scale B):
92aeb724-e952-52c4-ba55-796f7c5eca1c | note | ○ Range x = +5, -25mm
279c416c-0739-5ab0-8238-f4409b69b0c1 | note | ○ Max S = 15 mm
a864de12-9ec7-5317-92ab-800b6225559d | note | ○ 40 measurements per lot
b9ed6cc3-4ef2-5d1e-9a93-5a2f2462c685 | note | Level tolerances (Scale C):
0605a1a8-0bf6-5f5f-97bf-9de7e486f2b6 | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
0a702658-aa91-56af-b22f-73a5eed4a1f0 | note | METHOD: Review Document
6f405732-181f-5912-af9e-f768f3c2a297 | note | FREQUENCY: Each lot
c71441ce-19c6-59ae-85eb-cabda9870374 | note | CATEGORY: SCP
da7a3dbe-255c-55fc-af6b-1dc31f2d80ba | note | RESPONSIBILITY: SE/Surveyor
a974f132-7fea-5068-9989-7a95245cfedc | note | VERIFYING DOCUMENTS: Sign ITP, Attach Survey Report
549435f2-495e-55cc-9461-2ab4e97a76e6 | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
e02fcc19-7986-50aa-9623-f47b937e70a4 | note | REFERENCE: MRPA Quality Management Plan
a11bc5b8-c03f-5afc-9e10-e2f8ba9c9412 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
0683969d-e99a-53db-b774-cb7be0265a0c | note | METHOD: Document Review
1cfcfa69-c388-5ce5-b94d-9c8ada9bac6c | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
e7f556e5-4d70-5cd2-af6a-b9544a532576 | note | CATEGORY: HP*
c8436153-1bab-5a54-8bb7-2c1ac17620dc | note | RESPONSIBILITY: SE/PE/SPE
75b20c93-82d1-5bff-878f-3a9ac8f29084 | note | VERIFYING DOCUMENTS: This ITP
78df3ccf-4bbe-5eb8-9210-9bc2293d7a04 | date | Date Completed:
| checkpoint | Final Inspection
b5f226f4-b1aa-55e0-a96b-67a6aa964c59 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
79dec377-2a1c-5241-aa25-a58106f5368b | textbox | Name:
4d13ad8d-410e-58aa-a92b-18ab98f0cce8 | textbox | Position:
3f4cceea-b968-5b0a-963f-d2498404fa23 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-079-CIV-PSDS-Unbound Flexible Pavement Rev 0 | itp | ITP-079-CIV-PSDS-Unbound Flexible Pavement |  | 00ce19a5-b7e1-48de-a60f-b9a60fe48467
| section | Referenced Documentation
| checkpoint | Referenced Documentation
cef3a341-06a6-5741-b7f3-6363be62f35e | note | Document Title: ITP-079-CIV PSDS-Unbound Flexible Pavement
30e10dc7-4c4b-5a8b-9bc7-175c04c6ecec | note | ITP Description: PSDS-Unbound Flexible Pavement
49e8df52-c97e-52d8-943b-c63fdde38e94 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
0d195aba-0c49-5216-8179-61f1bd6e5d43 | note | Discipline (e.g. CIV/STR/RAIL): 079-CIV
f67e4602-8c9f-5138-b1b8-3ac14fbed052 | note | Revision Number: 0
1c542c7c-d38a-58de-a0c6-990b9e83257c | note | Revision Date: 2/05/2024
2dd475ec-acf3-576a-ba23-9abf168a3f54 | note | ITP created by: Victor Mira
6037f25b-fd12-526e-a2cb-605c02927892 | note | ITP approved for use by: Aldrin Guinchoma
484eb0e8-c8ff-5f14-813e-afcedafd614f | note | 1.1 Non Dependent
275a4933-520c-55d6-8c59-5f9972d0574d | note | Reference: Reference Documents: IFC Drawings
30392006-2b4d-5bf1-ae16-2424a9a9a53f | note | 1.2 Non Dependent
c19726c2-b665-560a-b289-f211815f9121 | note | Reference: VicRoads Section 173 (10/9/2008)
79f044fb-d1b2-5a2d-adf7-98dfbc6a0c60 | note | 1.3 Non Dependent
5335d17e-63e4-5a4a-930d-afea86ea8134 | note | Reference: VicRoads Section 304 (13/8/13)
a9b9c3a8-ad5e-5f9d-bbc8-e61a01b81ae0 | note | 1.4 Non Dependent
95b1e796-67b4-5a07-ae46-9ab597136704 | note | Reference: VicRoads Section 801 (19/07/18)
aa7f871b-c0a0-531c-9c63-838a7f692699 | note | 1.5 Non Dependent
d01c5f1a-461d-560e-a197-349474a7b170 | note | Reference: VicRoads Section 812 (13/07/16)
| section | Preliminaries-Materials
| checkpoint | 2.1 Crushed Rock Mix Design
c7ab21e8-fd53-5967-945a-de04dacc1294 | note | REFERENCE: Section 304.03, Section 304.05, Section 812.04, Table 812.121
1b9fcb75-dfdd-5034-8605-c6fe2b158a01 | note | ○ IFC Drawings
82a9a098-1532-5001-802e-39510d80f4b3 | note | ACCEPTANCE CRITERIA: All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
b28f0e5e-20bb-5438-b647-df03d263f2f2 | textbox | Enter: Teambinder Material Approval number
e5e0dbb2-578e-5a57-b864-78634836c619 | note | METHOD: Document Review
53b1725c-b1b1-512c-8c89-e25e557e6145 | note | FREQUENCY: Material conformance as per Table 812.121
5d383a67-04be-509d-88e9-8e26c2f279f1 | note | CATEGORY: HP
36c338dc-de1a-581f-85ab-ac693cc8a4fc | note | RESPONSIBILITY: NA
ed320a6c-206d-5e98-b058-9b3d61607890 | note | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documentation
| checkpoint | 3.1 Subgrade Preparation
00b6df5c-e96f-510a-94a4-e9688085ebdd | note | REFERENCE: 304.04
626924a5-5135-50ff-94a9-dc5a6f94fecb | note | ACCEPTANCE CRITERIA: Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
eae82c91-a115-5efe-b071-d06cad2b5128 | textbox | Reference: Subgrade Preparation/Type fill Lot Number:
3efd383a-3b8d-53ce-a246-fd70a3cce9ef | note | METHOD: Document Review
b0ecf72c-3c16-531b-ac19-d7a3a6b0b7e0 | note | FREQUENCY: Each Lot
2561cc73-94ea-538c-8997-f37b52a7eba7 | note | CATEGORY: HP*
0c384e62-7b7c-5586-8b53-59ab556bfe23 | note | RESPONSIBILITY: PE
d88ce992-0bf0-572e-8299-b221612dad70 | note | VERIFYING DOCUMENTS: Underlying layer Lot number
| checkpoint | 3.2 Select Scale
712d64fc-452b-54c6-b761-3250a8eda3aa | note | REFERENCE: Project Requirement Specifications, IFC Drawings
f6aeb190-ecd2-511e-b716-1f8d41090fc3 | note | ACCEPTANCE CRITERIA: Specify site specific scale:
250b1d4f-0cbc-5139-8ab9-b0d3a23f0624 | textbox | Enter: Site Specific Scale (A, B or C)
b55c5ba4-b62b-58a9-8450-d3b03b01ddfe | note | METHOD: Document Review
8bf86c9c-9072-5b59-a954-3a406f714c2d | note | FREQUENCY: Prior to Commencement, Each lot
67b59b3f-0471-5ce7-b6ee-11178edc551c | note | CATEGORY: HP*
086ffdb2-dc27-528c-ae60-3bf45e7c38fd | note | RESPONSIBILITY: PE
4120512b-40fa-568c-8ca5-c7b0ea597aa3 | note | VERIFYING DOCUMENTS: Sign ITP
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-out and Lot size
a78e8915-7b9b-5bac-8fb9-0154585168e8 | note | REFERENCE: IFC Drawings, Section 304.06
46bbb357-8f8c-5098-81ca-0fdb112076ca | note | ACCEPTANCE CRITERIA: Lot size shall be the lesser of 4000sqm or a days production.
fceb0ee7-0eeb-5be5-9b07-581d92a963af | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
f07706b4-558a-5fcc-b307-0671b34b5283 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
90e28c58-bad1-56a3-bb97-bd80d8dc427e | note | METHOD: Survey, Document Review, Measure
1da9680d-1d08-5efe-a3c6-73effb6cb91c | note | FREQUENCY: Each lot
87fcd0a0-7f24-592b-bc7c-489dc4868ec5 | note | CATEGORY: IP
8027e650-7230-56a4-8cd8-07d20c56b5a0 | note | RESPONSIBILITY: Surveyor, SE
14c8331d-f5ea-5802-9f47-13fc03f355d1 | note | VERIFYING DOCUMENTS: Sign ITP
| section | Construction / Installation Activities
| checkpoint | 5.1 Crushed Rock Delivery Dockets
4db240f5-e443-5e0a-b563-c1c26f2a8d19 | note | REFERENCE: 304.04
c513eb79-8441-54f3-adb6-b933c376fd96 | note | ACCEPTANCE CRITERIA: A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
1d55f61e-7c04-5cbb-988d-ebe27cb8cacf | note | ATTACH: Delivery Docket(s)
0d7799ef-5c76-5a76-b33f-934e3f6d5b4d | note | METHOD: Document Review
18323f05-4d89-54f9-9694-db1a7134e995 | note | FREQUENCY: Each Lot
f79cb719-5c2a-5be6-bd67-32dea6c73d0b | note | CATEGORY: IP
d0dac598-6eb4-5438-a81f-1e80a24edad2 | note | RESPONSIBILITY: SE
5ac18faf-c39d-512c-95dd-d7e217ea4438 | note | VERIFYING DOCUMENTS: Attached Docket, Sign ITP
| checkpoint | 5.2 Placement of Material
1fb390f1-c04f-56ab-bfb6-68f2cfd88227 | note | REFERENCE: Section 304.03, Section 304.06, Section 304.08
915f0388-1cf1-5826-9719-905b77cc1a15 | note | ACCEPTANCE CRITERIA: Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
74034b81-a01d-50f0-846f-21c467384621 | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
8809830e-81be-5b77-b5e1-f1fadd3927a9 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
d99de4d7-59fd-5fdb-b444-d35c62932452 | note | ○ At no location shall water pond on the surface of any pavement layer.
84952766-1143-5692-a95c-a5f577cf958e | note | METHOD: Visual and Measure
4f748420-fdbc-5a73-8ea5-e464e1c3ade4 | note | FREQUENCY: Each lot
d1dd225c-48dc-541c-9ce3-fed1e39f003e | note | CATEGORY: IP
1535fc6f-0b5f-5b97-b28c-409c570ef4b7 | note | RESPONSIBILITY: SE/Site Supervisor
36c12fdf-1bc1-56fd-9651-ac3beebb830d | note | VERIFYING DOCUMENTS: Sign ITP
| checkpoint | 5.3 Construction - Jointing
2d1dc520-182b-53d3-96df-a0c58c29f2ca | note | REFERENCE: Section 304.07
d779c5c3-cb73-585c-9238-4a08ec3ab12d | note | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements:
ec94a1eb-91ff-5a39-b265-d54cbedfe272 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
ed915a23-6535-5888-a205-a4e525e6d442 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
1494c860-e976-5869-a38d-7cbabb525899 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
55a63410-8663-5084-a56d-4a2f24bee33a | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
430b7d4b-601d-53a2-82d2-e5c78f847119 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
f25aef4b-b158-5d82-abaa-c4131a034417 | note | METHOD: Visual and Measure
eb4b3c71-1e89-577c-8890-7bb9c1b0dd8c | note | FREQUENCY: Each lot
96796d8e-e2b4-53f2-8cff-38141e272014 | note | CATEGORY: IP
4e6aec9b-07fb-51e3-a417-13df6678e187 | note | RESPONSIBILITY: SE/Site Supervisor
6ea282fd-f2b1-55d8-9187-6df3de9d095c | note | VERIFYING DOCUMENTS: Sign ITP
| checkpoint | 5.4 Compaction test (Frequency)
32dd9277-7ef3-5c2f-aac2-90d139b0a722 | note | REFERENCE: 304 .11 (b)
b26560ec-0eaa-5a6f-951a-46c17d505a26 | note | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
6bb55173-64a3-54f0-ac93-ecebd0a495de | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
7aa04efd-e7b8-532c-be7f-49efbfb28ae2 | note | ○ Scales A and B: 6 samples
6ead8bad-2356-5e23-a718-de4d80f267ca | note | ○ Scale C: 3 Samples
e53da36d-6076-55a3-8f26-0165b33dfec1 | note | ○ Pass: Tested
03f119e9-b7a5-5ac5-9514-9b9dd7ede52d | note | ○ NA: Not Tested
906e0f9e-9d97-5605-b9e6-144ab5d3d24b | note | METHOD: Visual
c4302e68-b771-59ba-9381-83abbc05cd0d | note | FREQUENCY: Each Lot Where applicable
0b16455d-3349-5a5e-b272-cad238192b7a | note | CATEGORY: IP
9cc23d60-b8d7-5994-99f3-e3949c6a9220 | note | RESPONSIBILITY: SE
d5f04b7c-3ae8-5cf2-9ec9-415b4fe0ef8a | note | VERIFYING DOCUMENTS: Sign ITP
| checkpoint | 5.5 Post Compaction Materials Testing (Frequency)
96c28014-5fb4-5206-8d6f-035746a8e8ad | note | REFERENCE: 304.11 (c )
62aeba6f-c5ad-551a-819e-38a0e41bfeeb | note | ACCEPTANCE CRITERIA: SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
fd93bde6-b7f3-5688-9c69-e4a90d9bcc12 | note | Compaction:
49037c19-61d6-5031-acc6-c158b5b43f4c | note | ○ Lower Subbase: none
a4709940-898b-5da2-867b-e905951d5b22 | note | ○ Upper Subbase: 1 in 4
aa209008-bb10-54d8-bb4c-f5f990371e75 | note | ○ Base: 1 in 2
a84443cd-c32e-59fa-bdc5-9bf76821e3ad | note | PI:
2936c5f2-6d96-5a33-987c-18237c4d458b | note | ○ Upper Subbase and Lower Base: 1 (two samples) in 8
695fede1-ddd4-5970-8b1e-81146992aa2b | note | ○ Upper Base: 1 (two samples) in 4
c36eaf4f-19ec-557c-a1ca-2cc94653f222 | note | SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI.
56ab86b9-a0d2-51c7-9f5e-b226dec5e0a7 | note | SCALE C: Post compaction grading and PI testing is not required (CHOOSE NA)
11db2b3c-328c-52d1-8add-86f71f513db3 | note | METHOD: Visual
e3c89340-b0d5-559f-affb-bf477c3f5a6c | note | FREQUENCY: Each Lot Where applicable
f45fc7c7-ea57-5c2c-b7b2-281e005141a4 | note | CATEGORY: IP
da6c1f49-cf14-57c7-95c7-cb01349fb829 | note | RESPONSIBILITY: SE
590c5018-d219-5a89-bf42-335695669289 | note | VERIFYING DOCUMENTS: Sign ITP
| checkpoint | 5.6 Proof Roll
52587933-4a14-5453-9f8c-e7107c8a536f | note | REFERENCE: Section 304.08
b2e174c1-a51a-5353-be0e-084df3d3b096 | note | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
92bccc4c-5864-5c8e-9e36-b64bfbe4c568 | note | METHOD: Visual
c09c7469-0473-5a47-a3ba-b6ac06c54602 | note | FREQUENCY: Each lot
fb415e7f-6342-54c0-b50e-1d7408238c39 | note | CATEGORY: HP
e77d9bff-d104-5ca1-9c9f-8003081dbbf1 | note | RESPONSIBILITY: Nominated Authority
c3f5d5ca-f3ae-5547-ae7b-5dcd95c1fd96 | note | VERIFYING DOCUMENTS: Sign ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.7 Protection of compacted layer
fd6a512c-cecf-5c86-92d3-ae03bfda6e0f | note | REFERENCE: Section 304.09
8523fc8f-c8ea-5d04-94de-58be3fd4bfc2 | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
24b52b1f-29ec-5e7b-94cf-0403d4bc600d | note | METHOD: Visual
a449087c-a597-5781-8c05-f5641f0cba25 | note | FREQUENCY: Each lot
4cd1e6b3-4ab0-518d-876f-794f3b42e061 | note | CATEGORY: IP
5b847e08-5322-5f4a-bd68-4ec7b6e0d9e5 | note | RESPONSIBILITY: SE/Site Supervisor
f0949d29-8fe6-5b6d-84f5-76a35b7237c3 | note | VERIFYING DOCUMENTS: Sign ITP
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Compaction Testing (results)
7ffdcf9b-88d4-5a50-8269-f1dcc0268968 | note | REFERENCE: Section 173, Section 304.08, Table 304.081
8799cfa2-d652-5710-bca8-ba0f87c2dd82 | note | ACCEPTANCE CRITERIA: During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
df2eef2d-b0b1-50e0-a1b4-f08ffe6b99c3 | note | – Density Ratio to be based on tests performed with Modified Comp active Effort.
31f85b55-21d2-55f3-adcb-1616b78eae7f | note | Scale A:
4d2eb2a7-a705-55ea-bd4a-c6bfe289ae61 | note | ○ Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
5293c14f-ae35-553a-82d0-240a016a96a9 | note | ○ Base Layer CDR ≥ 100%
275849ca-3b17-533b-9411-0751edc7747c | note | Scale B:
d829a031-7e24-526f-a5f6-48b35d52fc77 | note | ○ Subbase Layer CDR ≥ 97%
4e897f31-033d-5e89-ad5c-cac08293e3b7 | note | ○ Base Layer CDR ≥ 98%
4a0a4dd2-0950-586f-985b-1b380cc13ce1 | note | – 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
cf216203-88bb-540e-8463-2cbd31993b0b | note | Scale C:
28f5185e-4ca2-510e-b984-963f35379ad3 | note | ○ Mean Value of Density Ratio (3 tests):
03f54338-e317-59e0-bf04-6f9d98d9e9b2 | note | ○ Subbase Layers >98%
be3f9da3-37b7-52e4-a967-5ed7fb3be214 | note | ○ Base Layers >100%
cb6d80b3-f505-5201-af90-47f4f5e17f7d | note | ATTACH: Compaction Test Results
ee56a5d8-c5cb-5380-8ab6-bdae0d7c9a37 | note | METHOD: Document Review
10e0004e-6761-5bc1-b590-0eb466af0b2c | note | FREQUENCY: Each Lot Where applicable
23a98375-3064-5ef5-b5fd-dfc22c7a1442 | note | CATEGORY: IP
41c0e1f8-a179-5aa0-856e-563516beddba | note | RESPONSIBILITY: PE
8549d675-6c64-5013-ac60-ad6c26997cfd | note | VERIFYING DOCUMENTS: Compaction Test Rersults
| checkpoint | 6.2 Post Compaction Materials Testing (Results)
9b713491-6971-571a-9ac7-d2ddc2bbf517 | note | REFERENCE: Section 304.10, Section 304.11, RC 500.02
d8cfa0ab-341b-5b22-a33e-200145d00eef | note | ACCEPTANCE CRITERIA: Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
28351dea-34c3-52cd-9947-94b80e8424b4 | note | 20mm Class 3:
240cbf16-f219-5d9c-956d-04d801b314e5 | note | Grading
d0d51424-6c41-5fed-b6f6-c1d8a80f13a6 | note | ○ 26.5mm 100%
189d324a-5359-5933-be97-01baa1f78a94 | note | ○ 19.0mm 95-100%
226ef87d-c2ac-5c22-b658-5bb3159fc2a1 | note | ○ 13.2mm 75-95%
e1eed7ee-dc3c-5de2-8a51-c14c07640eaa | note | ○ 9.5mm 60-90%
9191e94f-6965-5006-8b50-c18c58885845 | note | ○ 4.75mm 42-76%
c022ffa1-6c71-5209-b38a-9145d9a83322 | note | ○ 2.36mm 28-61%
c1573c81-d9e2-5227-a5a5-b693ffa2c3c5 | note | ○ 0.425mm 14-29%
3552dcbf-a430-5835-a14d-8693d92453ed | note | ○ 0.075mm 6-14%
6af56664-6a2e-5902-8fd5-8774ce26a26c | note | – PI between 0 to 10
a817dd2d-1dae-515c-be9c-d5f5297c4556 | note | 20mm Class 4:
4dafb8e7-93d6-5c16-9b7c-bd6a198ab240 | note | Grading
70ca23d3-cad1-5f37-9a00-f010554aff6a | note | ○ 26.5mm 100%
7bf3f4a6-0e40-5689-803c-e21095d48efb | note | ○ 4.75mm 42-76%
8f8e5771-d67f-5af0-a6fd-c673eabb585e | note | ○ 0.425mm 10-28%
de8f4d1b-dbec-5d9b-9020-dd24308e28d9 | note | ○ 0.075mm 2-14%
77517e14-88fc-50e6-8055-0ee7410ec1e3 | note | ○ PI between 0 to 20
cfc97939-8788-507b-8802-dca33189980f | note | ○ PI x % passing 0.425 mm sieve (max) 450
72864ab8-e876-5557-9a0a-d60038344477 | note | – Scale C: Post compaction material testing is not required (Choose NA)
8b12899f-c8c0-57ff-b38c-dfdd369d7478 | note | METHOD: Document Review
0c994ae4-125b-5ed4-8f72-8ee85a4c29f4 | note | FREQUENCY: Each Lot Where applicable
46306a9a-7dfe-56fd-b9ae-5c42e37aae6f | note | CATEGORY: IP
54459c0a-00de-581c-a5d1-0bce812a55fc | note | RESPONSIBILITY: PE
a433151e-7843-5ec0-9ffd-6b36d0b6d17a | note | VERIFYING DOCUMENTS: Compaction Test Rersults
| checkpoint | 6.3 Survey As-Built - Surface Level
08ff0f3d-7f61-5f59-8ede-07d10db17113 | note | REFERENCE: IFC Drawings Section 304.06, Table 304.061, Table 304.062
e8be84ff-024f-5213-a98a-caf4f67dd4e8 | note | ACCEPTANCE CRITERIA: No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
13e46e32-e131-53ad-ba29-2b5f2938565e | note | – Subbase course shall be not < the specified thickness by more than 15 mm.
43889a6a-d08b-540f-95cb-7e81fef20578 | note | – Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
859c1b31-785e-5579-826e-f60770f33187 | note | – The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
5881bb3f-ad1e-5a86-8082-6854a74de2ab | note | Scale A: A minimum of 80 measurements per lot
5cb6a851-206f-5623-8690-732d765d5fdb | note | ○ Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
d452ad46-9fec-5f6b-9743-416dd985370e | note | ○ Base: mean range ±5mm, maximum Standard Deviation of 8mm
2997fd6b-30dc-5002-9fa8-fea73e1c6b33 | note | Scale B: A minimum of 40 measurements per lot
1f5fdb4d-de76-57e7-950e-003fbc88b084 | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
b30f53d8-3bb2-58b6-9557-f6cdb4b70ae2 | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
03aa7317-cfe6-5eef-9dc8-36b849bde235 | note | Scale C:
713f3faf-1e1c-56f7-952e-9bc1dcff686f | note | ○ Lower Subbase (mm) +15/ -25
ceb912fa-ebff-5542-844f-2cf0b443f8c9 | note | ○ Upper Subbase (mm) +10/ -25
a6dee611-0c09-5296-8b9d-4876d6269b17 | note | ○ Base (mm) +/-15
7108300a-2b17-51ad-9f3f-73f84148ffa3 | note | METHOD: Document Review
bbaab1b5-aa57-56a9-9adb-788ba383e996 | note | FREQUENCY: Each lot
c94b7100-e3ea-5003-ac52-32852b3eda79 | note | CATEGORY: IP
9b731604-77f5-56f9-a788-a78c053238a7 | note | RESPONSIBILITY: PE/Surveyor
d72a0a9a-5901-5a42-b966-13ec1abd7b7f | note | VERIFYING DOCUMENTS: Survey Conformance Report
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
f7ea952a-aefc-5867-9289-9a4ee708036b | note | REFERENCE: MRPA Quality Management Plan
ff8a6e3b-2581-5fcd-b250-9397da94ae01 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
35b1ad16-1004-5acc-a294-35c0076cfd9d | note | METHOD: Document Review
f55b3776-432e-5263-9cf8-768a5b058925 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
d88358ab-bc71-5c8e-83d8-dfb681129782 | note | CATEGORY: HP*
b31cf737-2a08-5ec6-a13f-5e7d6f54ae5b | note | RESPONSIBILITY: SE/PE/SPE
c4ad8c94-7890-51ed-b7e7-75d94fb7b81b | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | Final Inspection
e26d1242-68bf-5a87-adca-f3a623233568 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8abd23b5-2f1f-5073-9fce-c927c09b4635 | textbox | Name:
103e4a65-bdbb-5296-891e-9603c858be75 | textbox | Position:
0178a5e0-b9b9-5bc8-8aaa-4da01b0574bf | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-080-CIV-PSDS-Stormwater Drainage Supply & Installation Rev 0 | itp | ITP-080-CIV-PSDS-Stormwater Drainage Supply & Installation |  | d2268e3a-e814-48a3-9e21-a432edc88fa6
| section | Referenced Documentation
| checkpoint | Referenced Documentation
600c2332-b412-5fd7-b2f3-70f27e67fbba | note | Document Title: ITP-080-CIV-PSD-Stormwater Drainage Supply & Installation
d362aba9-4c79-5e3f-a516-aaa1d8de4e10 | note | ITP Description: PSD-Stormwater Drainage Supply & Installation
9ac38935-e2d3-5217-a29c-a775e4f0e8c2 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c70f1f63-3516-5874-8d70-64704ddda9a5 | note | Discipline (e.g. CIV/STR/RAIL): 080-CIV
42283c48-dcff-59e2-9de2-bef5c4e091e6 | note | Revision Number: 0
90e853be-7d07-53e3-8615-37c12d4df467 | note | Revision Date: 5/12/2023
9e446fdf-be4c-50bf-9bf6-ab488827c709 | note | ITP created by: Victor Mira
ee8ddc47-b786-5167-ac0f-c7c9730080a1 | note | ITP approved for use by: Victor Mira
8c623ed3-a667-56f0-b9ed-0432e62879ad | note | 1.1 Non Dependent
6a93b4a5-491d-51e2-9e90-367b2d58e276 | note | Reference: VicRoads Section 701 (May 2020)
0916ed94-2703-5264-aa9b-d100f4bd1fe0 | note | 1.2 Non Dependent
2c5d66e8-a3cd-51cb-bc23-6de400310eec | note | Reference: VicRoads Section 705 (June 2021)
9b7beb45-f68a-5c54-a1cc-8d78d97cfbbb | note | 1.3 Non Dependent
18f8e8fb-6096-52da-9352-18c011edcec2 | note | Reference: IFC Drawings
c699c219-f237-5183-af39-880507346d57 | note | 1.4 Non Dependent
0d16cd4f-0c37-5d04-8d65-a4137c47061b | note | Reference: CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
f82663dd-b80e-5e1b-a8a9-eb37e3cce4b7 | note | 1.5 Non Dependent
5d29125a-6c99-53f5-a886-08c0cd81908f | note | Reference: CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
| section | Preliminaries-Materials
| checkpoint | 2.1 Drainage Reinforced Concrete Pipes (RCP)
d7ae0d3d-24f7-53e9-bf1b-e66ca886557d | note | REFERENCE: Section 701.04, Section 701.05, Section 701.09
25710082-d7ee-5d48-a16c-7dc4a3d5f81a | note | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
e4bd7a22-e2b4-5d67-b6ec-5e800302c891 | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
689dc06a-6647-54b1-8bae-2e6b5d0e29a5 | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
eefc6907-5a3e-5660-bc34-871d0361b09c | textbox | Enter: Teambinder Material Approval number
1f492c15-37ac-5770-91ec-037b6149c8ef | note | METHOD: Document Review
cc2e8367-ce73-59c6-a965-8d8b33c23a69 | note | FREQUENCY: Each lot
163efa54-0b92-5674-ba35-b661bc945394 | note | CATEGORY: HP
ae847fc2-0fa0-5141-8ae5-c82109cbf3a8 | note | RESPONSIBILITY: Nominated Authority
b195a6b4-6a1a-5b91-a2ee-e72e7606e657 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
d5c5b447-f0ba-56fb-b2af-f6490e1506d3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Drainage Flexible Pipes
88481045-e553-531b-9b3c-d58a7a39d026 | note | REFERENCE: Section 701.08
ae5070c3-175b-57f4-9527-4ce453870078 | note | ACCEPTANCE CRITERIA: Flexible pipes shall be supplied in accordance with 701.08
c4969ba4-7d6b-5f59-9ce9-1640cb8a989e | textbox | Enter: Teambinder Material Approval number
1099b183-df55-5ce9-96f7-8834077c0cfd | note | METHOD: Document Review
612cb6cf-1287-5643-a25c-83d31d93c32f | note | FREQUENCY: Each lot
a69ac451-d166-5b35-81fa-54d929d980d1 | note | CATEGORY: HP
7a212fd5-2ce5-5477-99e1-babee1ad100e | note | RESPONSIBILITY: Nominated Authority
e881ab87-bd6a-5460-af5f-5d4fa1a6388d | note | VERIFYING DOCUMENTS: Teambinder Material Approval
69bf56ec-0a34-5cd9-bb92-7ffe3bb76d3e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Precast Drainage Pit
966312e7-a515-57e8-a5d5-29095d4cedf8 | note | REFERENCE: Section 705.07, Section 705.04, Section 705.09
819858a1-2ca2-544c-8568-6cb9cfa99108 | note | ACCEPTANCE CRITERIA: Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
1e046086-2698-5ed2-8ee9-fccca3b1d5ff | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
39edd419-85d0-5671-860f-3cd1343b6f48 | textbox | Enter: Teambinder Material Approval number
39b0ca6c-38f4-5606-b981-a3f6fe291fda | note | METHOD: Document Review
3bfc8c2e-b4eb-5555-8686-39a40ef0d448 | note | FREQUENCY: Each lot
11fd2d47-d8e9-5f11-b7eb-90c720dc88e6 | note | CATEGORY: HP
8421d591-efe5-5586-9709-1a5a6c6b8033 | note | RESPONSIBILITY: Nominated Authority
98405887-1716-5e25-91c6-2cb7e5d7c22f | note | VERIFYING DOCUMENTS: Teambinder Material Approval
e7139071-ba45-53ed-a4f8-d513e8547ae1 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Cast in Place Drainage Pit
0c3686e1-92de-5681-9c11-3960e0f3b26c | note | REFERENCE: Section 705.06 IFC Drawings
a5209a94-fcca-5530-8d12-efc3ccada8f4 | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
c80b10e4-c298-52a5-9a23-fa5d805bdb29 | note | METHOD: Document Review
5b871556-0895-5855-9e7f-4a29a2820fcc | note | FREQUENCY: Each lot
a251024f-e4dc-50f7-982f-ebc250cc7fbd | note | CATEGORY: HP
f9707f52-8bdf-5425-8407-a880cfe6a84a | note | RESPONSIBILITY: Nominated Authority
2b178c73-fd08-5ec2-9100-06fecd26eccc | note | VERIFYING DOCUMENTS: Teambinder Material Approval
042347a1-a8de-5717-b104-34a491db63b4 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Drainage Pit - Step Irons
7af73ace-45be-5815-af00-e2fe386e2f59 | note | REFERENCE: Section 705.04, Section 705.12
ba9a20de-beb3-5dfe-9655-0bcefd2acdd2 | note | ACCEPTANCE CRITERIA: Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
0895ea75-8b5c-56af-9c9d-441942c06906 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
8720890f-c959-5436-89da-8f405be4fa41 | textbox | Enter: Teambinder Material Approval number
821c79a9-9226-597b-b9e3-6d186bc95e9b | note | METHOD: Document Review
59ed9799-0fb1-5b58-b1b1-28461c4f8209 | note | FREQUENCY: Each lot
c66d90b4-75e3-5a96-b988-1ab9baa4e7f1 | note | CATEGORY: HP
37fef470-574b-58b5-aa6c-d4f293cf2700 | note | RESPONSIBILITY: Nominated Authority
62a06a1f-4422-547f-b09e-167c2e19ef42 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
d250de2d-dbc6-5c6c-a8a4-ff7c86ec4e44 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.6 Drainage Bedding Material
4cf4620c-e213-5269-a0cd-bf628fb0eb32 | note | REFERENCE: Section 701.09
edd5287b-ad8f-52f8-b25c-8ecc6b39e718 | note | ACCEPTANCE CRITERIA: Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
dde6ff40-7bf9-5979-8f7c-4b1005a66863 | textbox | Enter: Teambinder Material Approval number
26e4dfa6-dd7b-5761-a8df-f0eee4b52097 | note | METHOD: Document Review
594f9955-e4fd-5bb8-a8d6-2da792bc6eaa | note | FREQUENCY: Each lot
87385f88-0759-535b-b607-45cc6b290175 | note | CATEGORY: HP
17a581c2-4906-5ed9-9ef4-b03cbe346888 | note | RESPONSIBILITY: Nominated Authority
0d678601-1699-5d7c-8313-5cbbc8ab6f4c | note | VERIFYING DOCUMENTS: Teambinder Material Approval
9be2a211-7601-5d6d-bccd-1cb9e79bf79c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.7 Drainage Backfill Material
0b00e8e8-5ab2-549f-8acd-004824cdf1df | note | REFERENCE: Section 701.09, Section 701.19
007b8ebe-f976-5a90-9ca7-12a08458a549 | note | ACCEPTANCE CRITERIA: Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
37b2ae3a-454c-5834-be83-e7a4f1f2e6e9 | note | Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
caf07ddb-a8f6-5e72-ba23-8d04ce9b5a76 | textbox | Enter: Teambinder Material Approval number
8c6ffb7d-0cf8-55f9-a93c-8a642d2ef742 | note | METHOD: Document Review
e292d443-c59d-5c95-a849-ec3a5352ad5e | note | FREQUENCY: Each lot
38bac9c6-f571-5a30-94fe-9fbdc31487ad | note | CATEGORY: HP
7c05704a-84d3-580d-a9b2-222e01425424 | note | RESPONSIBILITY: Nominated Authority
b398498e-22d0-505c-bc38-d6bc26a40907 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
3fb3a8f5-791c-58e0-89f3-2640810e3bb2 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documents
| checkpoint | 3.1 Subcontractor ITP (where required)
0d23b5a7-1694-5939-a78d-23f4abec61c1 | note | REFERENCE: Subcontractor ITP
389c4bd0-0525-5d4c-b557-74ceaf34c434 | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
3d0c714f-e892-5092-a4fc-3a754029e6f6 | note | METHOD: Document Review
df24c44b-2e8f-5db0-911e-4fc12fba36e0 | note | FREQUENCY: Each Lot
65de36ea-b993-535f-913b-8d7c44bc39f6 | note | CATEGORY: HP*
74f3e0cb-33b6-569f-9463-f174a4a917cf | note | RESPONSIBILITY: PE
1aed5a09-7f7f-59ac-bb5f-24dd9a04e793 | note | VERIFYING DOCUMENTS: Subcontractor ITP
83088625-3de0-5371-84b8-addd54078551 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Survey Set Out - Pits & Pipes
05fed162-5986-5e27-96cf-d33e6b85d7cd | note | REFERENCE: IFC Drawings Section 701.10
f53ee18a-cb41-5053-973c-6044b0edc34d | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
343c1cd7-2808-5d21-bd86-e3e4bfdc61dc | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
928cfb65-4d58-5fe6-8dc7-694fd90106a1 | note | METHOD: Survey
287e8eae-b4bf-5d20-befa-1423f16de33b | note | FREQUENCY: Each Lot
b297cf43-22a2-519b-baba-e2e7411215c3 | note | CATEGORY: HP*
f182351c-b445-5f78-abb9-711902793962 | note | RESPONSIBILITY: PE
0d35a704-5aa2-56db-ad52-f536a2f030bb | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
850b7c18-4673-5c57-bb31-77d657cc87c6 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Pits - Excavation
6180b69b-e794-501d-959e-1a6939812772 | note | REFERENCE: IFC Drawings Section 705.05
d0da53f2-e061-50d9-a78d-afa34b1106c0 | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
0534fb57-3346-5c71-b580-7f55b5b16496 | note | METHOD: Visual inspection, Measure
4fe439a8-91f1-5427-a8d5-3850004a3aa8 | note | FREQUENCY: Each Lot
70bb8ee7-0c09-5593-a43d-8f9a4708ab29 | note | CATEGORY: IP
69906040-6eb8-58f8-8370-386dd1374874 | note | RESPONSIBILITY: SE
12cc318a-fc51-5790-b056-58a15c34198c | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
29843405-ba20-5fcc-847d-7d629d9d13e7 | date | Date Completed:
| checkpoint | 5.2 Pits - Placement of Bedding Material
9852f554-ac42-5999-9551-8b07bc811b5a | note | REFERENCE: IFC Drawings Section 705.05
d7eaaf24-0036-557f-ba2e-481bdffad764 | note | ACCEPTANCE CRITERIA: Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
80696860-a2d0-5a54-a57b-218045d7ca3c | note | > 80mm for clay foundations
c38ea44e-2a63-511f-8d0f-973406cefd74 | note | > 150mm for rock foundations
09a32e87-3704-5d85-b155-b9b61db12b2f | note | METHOD: Visual inspection, Measure
65455da0-9ffc-5479-b479-2fcac0405dfd | note | FREQUENCY: Each Lot
c3f407c2-03f8-5df9-894e-57d23d703b06 | note | CATEGORY: IP
33deda73-139a-5773-bed2-e6f83623d007 | note | RESPONSIBILITY: SE
6b3fcec9-6295-5e91-ac1c-a568765c6eb9 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
6110f313-a3f2-5de7-be6e-866b7ca760d7 | date | Date Completed:
| checkpoint | 5.3 Pits - Bedding Testting
c7d104bf-efad-5d1c-865e-3f7d017f5e53 | note | REFERENCE: IFC Drawings Section 701.20
9ceed93a-45a7-5f51-a521-3e4f8e493329 | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
ca387ebd-6222-578f-85d6-3547d73f066d | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
f43600d4-99ba-5aa8-ac38-44901148ea2e | note | METHOD: Compaction Test
b8b52cbd-dc49-5bc1-a2f3-ea6398f072a1 | note | FREQUENCY: Each Lot
e1a12376-d5d0-5de5-aed1-d63a87309aa5 | note | CATEGORY: IP
4ea523ae-3ed0-5964-b8e0-9bb0eba023cd | note | RESPONSIBILITY: SE
78294686-7238-5529-8f3f-1a2dabb16a52 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
9420238a-d4ab-5ab0-b144-5eb43bd4181f | date | Date Completed:
| checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
79abcd28-4853-5a38-bf18-a25fa3f6d4d6 | note | REFERENCE: IFC Drawings Section 701.10
4a342cdf-9df7-5cf2-840c-8901bfc0bc6d | note | ACCEPTANCE CRITERIA: Survey pick-up to verify:
9f227c38-ed23-587d-b2bd-490d30cd6f40 | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
658ad066-466a-580d-8bd8-e28006648a1a | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
8a9c1659-9b5e-5143-81b9-60e144b98bd2 | note | METHOD: Visual inspection, Measure
33fcf54f-48a4-5725-bd41-177b70eb1f48 | note | FREQUENCY: Each Lot
753bb8fe-3196-551f-b875-8d7fca190719 | note | CATEGORY: IP
c3ec03dc-dd7c-5e75-9928-14f248e5f98e | note | RESPONSIBILITY: SE
06808838-ddeb-5b15-bbb6-203476218bed | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
60aa6399-6228-531c-b46d-cbaaec2ec2e3 | date | Date Completed:
| checkpoint | 5.5 Pits - Cast in Place Drainage Pit
15922bcd-3857-5b0b-853f-d709f19c1c30 | note | REFERENCE: IFC Drawings Section 705.06, Section 610, Section 611
d47c70e8-d6c8-586f-ba26-df2c6106291b | note | ACCEPTANCE CRITERIA: Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
42c53b71-f111-5762-b618-56d54599253d | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
2a7d0a4f-c640-5c91-8cf0-5e5c2f6d7391 | note | METHOD: Survey, Measure
e34b75c9-7642-5845-99e9-9020788b87d5 | note | FREQUENCY: Each Lot
be98908b-1d45-5d56-866f-9eba653b3ecc | note | CATEGORY: IP
1e531859-071f-524e-90a3-59bceb13b73d | note | RESPONSIBILITY: SE
190fdf42-e90f-5d18-8f69-851c5bd509de | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
05a68788-fff9-58b5-a36b-77b4b806bc2e | date | Date Completed:
| checkpoint | 5.6 Pits - Jointing & Drainage Connections
100a91ea-511d-5378-af90-d82f2501a8a0 | note | REFERENCE: Section 705.11
feeb2c16-4f4e-5f7b-a85b-5e749de5f1e8 | note | ACCEPTANCE CRITERIA: All connections to drainage pits shall be neatly made in accordance with Section 705.11.
b67df2a8-a020-52ea-8e03-f9b0a1af1f86 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
4aeeec66-f089-59fc-a344-dbbae5381dfb | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
87e4d03e-a26b-506a-9a18-f30f9ae90dcf | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
0363d2d3-59d5-5133-af87-b0b26e4182a3 | note | METHOD: Visual inspection, Measure
8b9003b1-b6b3-5ab8-88da-dfed4ef14cf3 | note | FREQUENCY: Each Lot
975b9ad5-11fd-5b86-86e9-499fdae6d53c | note | CATEGORY: IP
bd47372f-5d06-584e-a653-9c85502f8ca2 | note | RESPONSIBILITY: SE
18df06e8-1a1b-5965-99c6-f3793c8c2396 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
f9e09eb3-0947-501d-ae88-fb6cfe4ed37f | date | Date Completed:
| checkpoint | 5.7 Pits - Shaping of Floor
b7b78f1d-8385-513f-b0e3-a1bd7c79b5bd | note | REFERENCE: Section 705.13
dcff66d0-99f9-50ed-a1e8-620afd30617d | note | ACCEPTANCE CRITERIA: Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
f5a04665-72da-5951-9346-8b31323ccd78 | note | METHOD: Visual inspection, Measure
403bcba3-e238-57f8-abc3-35910e609893 | note | FREQUENCY: Each Lot
f8a4aed1-1512-53eb-8552-f5ccca2b34f5 | note | CATEGORY: IP
acc2f5b5-1356-5caa-9ecf-a19b12001ab4 | note | RESPONSIBILITY: SE
35b9e9b0-a229-5daf-a29a-c684b2c8bd6b | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
3b66eede-0889-5dcc-b173-54904c97d660 | date | Date Completed:
| checkpoint | 5.8 Pits - Step Irons
3fffffa2-8249-584a-a4c3-f5c633cb14d2 | note | REFERENCE: IFC Drawings Section 705.12
29ef4c4f-9861-5d95-9b30-6aa5d2af753d | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
258e4457-3232-534f-af92-c1e2081b491f | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
4cbf2eeb-e1dc-51de-9bbd-c843fcae166b | note | METHOD: Visual inspection, Measure
07dcaea1-aa25-5eaf-a74e-8caa56da4004 | note | FREQUENCY: Each Lot
7b6c2ad6-2491-5f31-91d6-a825287f7344 | note | CATEGORY: IP
dbfcd9ef-76c5-5f87-979a-17add77c9b29 | note | RESPONSIBILITY: SE
cddbdc90-c739-5388-9e01-8c51db231b70 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
244ed648-cbd6-5226-8666-d3b74709807c | date | Date Completed:
| checkpoint | 5.9 Pits - Fitting of Covers
c13db66b-9930-50b4-aa9d-5b83ce59a776 | note | REFERENCE: IFC Drawings Section 705.17
3e77fc39-03b1-56c7-9e88-26e3243b6a48 | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
1e8a1877-d7b5-5334-a13a-dacfbe4c76a4 | note | ○ Height shall be within 10mm of the design level.
fb3e84f3-1d7d-54f0-9b72-29783d565dee | note | METHOD: Visual inspection, Measure
012da919-01c9-55ec-9f68-6e34e1161a3d | note | FREQUENCY: Each Lot
b62908f6-6c63-58ff-9581-229ab3e5da74 | note | CATEGORY: IP
30dffbbf-c11c-5973-8744-38d80320aaec | note | RESPONSIBILITY: SE
cd238386-fc21-5ca5-8062-3b0f16c250e7 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
66f4f92b-518d-52fc-af3b-c50be9d21969 | date | Date Completed:
| checkpoint | 5.10 Pits - Pit Lids
acb61b99-48e0-51f2-aa10-9923c45fd240 | note | REFERENCE: IFC Drawings
6c4d10ff-ecf4-5923-9ba3-af3f2bdd2f72 | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
6676001f-19e8-53b5-b24a-837949361182 | note | METHOD: Visual inspection
402b0d35-507e-5183-a020-eb2e3545804d | note | FREQUENCY: Each Lot
a1acf8ae-6843-5e22-a629-e144a591994f | note | CATEGORY: IP
fe1e7d29-3023-5cd9-b8b3-4a8be664c8e8 | note | RESPONSIBILITY: SE
681962b9-d186-57c9-a868-f0dd6d20da6a | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
9fc9eeec-977e-59b4-862c-a492185e1742 | date | Date Completed:
| checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
c9ae1c7b-e628-5dbd-a8e6-2c2644c72576 | note | REFERENCE: Section 705.18
73e799ac-5775-5ce7-9141-6484b47cc6d5 | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
26d84730-2e83-50e2-a6f0-c872f64cb470 | note | METHOD: Visual inspection, Measure
324b2d80-6d57-538a-aa1d-762b5090256e | note | FREQUENCY: Each Lot
ae7ac52e-0c95-5b29-806a-7760aa7118db | note | CATEGORY: IP
89c5975e-dc2a-5b9b-8452-40c67f48f3d3 | note | RESPONSIBILITY: SE
8d4d7c17-4e04-5f5c-b8f3-b2d749efb33c | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
a4764594-eb67-561d-9705-23edec740193 | date | Date Completed:
| checkpoint | 5.12 Pipes - Trench Excavation
8b30f105-2f55-5907-83c8-fef940607e8e | note | REFERENCE: IFC Drawings Section 701.15
17988918-6f8e-55cf-8161-44244ce4317f | note | ACCEPTANCE CRITERIA: Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
f98b4d64-2567-599c-9369-2ca472fe3fa5 | note | > 300mm, < 600mm for RCP
43dc62b3-e07b-58e9-a9d6-ed6f7ecd9ace | note | > 150mm for Flexible Pipe
0f55565f-b191-5458-accb-4e6fd62681bb | note | ○ The base of the trench shall be compacted to refusal using mechanical plant.
dce0a5ea-b26e-53b7-ab39-3c57ea247c19 | note | METHOD: Visual inspection, Measure
af689f14-522a-5a48-94b5-608276fb9472 | note | FREQUENCY: Each Lot
7c4383ca-2fe5-52f5-89c6-d2d6427b5c65 | note | CATEGORY: IP
0ea67620-28f7-5a5a-a0ee-bcd6dba2bf37 | note | RESPONSIBILITY: SE
12783c13-e71b-51f9-8b5d-53e0efa98d6a | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
b0ab98b9-1827-52b0-a7f2-4b05314ff080 | date | Date Completed:
| checkpoint | 5.13 Pipes - Bedding Placement
a7a34bb9-0d3a-57d7-8a8e-b1ca5728d076 | note | REFERENCE: IFC Drawings Section 701.16
dcb02e76-f5cc-5d40-b613-8a091ca77f63 | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed in the full width of the trench to the below minimum:
5534e307-a4b5-503f-98c5-c3a6d62cdfa1 | note | > 100mm where D<1500mm
6bba818a-0424-591c-88c3-855380baaaf9 | note | > 200mmwhwere D≥1500mm
327588b2-068f-5dcd-b1b2-ff5771273850 | note | ○ Bedding material shall be placed and compacted in layers <150mm loose thickness
757c1c0b-a997-5603-9215-ce6d2c8e6e78 | note | METHOD: Visual inspection, Measure
c8fb6afe-6d42-51fb-83de-a4450bfc3aef | note | FREQUENCY: Each Lot
b3977e19-215a-5b60-a730-3028bb8678f7 | note | CATEGORY: IP
43d4e213-34b3-5c40-b410-069d2bd61fdb | note | RESPONSIBILITY: SE
a8f5d2eb-def4-5440-b014-a5dfa9569ea4 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
a8bdf9c8-3ddc-5286-aedf-d82c1f795a71 | date | Date Completed:
| checkpoint | 5.14 Pipes - Bedding Testting
b1910bdb-92d1-5614-b1c9-861b8f82411d | note | REFERENCE: IFC Drawings Section 701.20
6a18981a-c974-580a-bc95-a2ca1e05afdb | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
c7cf0478-2669-5fd8-b3a5-2b57f06213e0 | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
d6763649-14c8-5b7f-86cc-a0aa0fe79141 | note | METHOD: Compaction Test
4ddf459a-4a14-5cf8-b183-00539b6a660a | note | FREQUENCY: Each Lot
9b474d17-7ee3-5f08-8868-ca07c0b6bb65 | note | CATEGORY: IP
dac0ae45-0eee-53cf-8e11-794dbc7af37b | note | RESPONSIBILITY: SE
ee525334-7f56-5ca6-b641-ad6797568452 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
41f52620-2ddc-5f51-a055-d923989f02e3 | date | Date Completed:
| checkpoint | 5.15 Pipes - Placement of Pipe - RCP
73f5c19d-6708-5ace-a1c5-4a5c02331287 | note | REFERENCE: IFC Drawings Section 701.17, Section 701.20
4e4f889e-9fd3-5624-abf7-bf09eb2577fa | note | ACCEPTANCE CRITERIA: Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
867ef1a9-9c54-57f5-807a-3eebb5a4c256 | note | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
f79b6800-7240-520d-9ca0-4ddb76899233 | note | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
36bc6514-8169-5765-916c-060bd2fd1334 | note | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
a0d895fa-738a-50a1-b708-2db376a2ba18 | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
7109be85-035e-519e-862f-14500dd9aa7d | note | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
ca52d52d-0003-5520-957a-08c115b11fb9 | note | METHOD: Visual inspection, Measure
b36be2fd-78f4-5946-946f-c3a837cf1e3c | note | FREQUENCY: Each Lot
44aeb80a-5188-529a-92bc-e4aae3d06464 | note | CATEGORY: IP
ae6a8fea-37f5-57c5-b00e-4d4db6648f07 | note | RESPONSIBILITY: SE
7b4da0f9-7f61-5783-857f-e729c15540f7 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
f42c5889-11d3-5754-9c06-e34d309a225b | date | Date Completed:
| checkpoint | 5.16 Pipes-Placement of Pipe - Flexible Pipe
479fc994-cf49-54c2-9199-1e7b0c8083f9 | note | REFERENCE: IFC Drawings Section 701.17, Section 701.22
852718a3-7626-5113-a6bd-ccd24713abbb | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
8ffe5395-1671-5937-a21b-746d2ef38687 | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
44ccc78d-0c0d-55cf-9034-6b145bc500b2 | note | METHOD: Visual inspection
b2c37190-f39e-5923-a6ad-8a5186cc1679 | note | FREQUENCY: Each Lot
34fdca1c-a978-5be2-89d8-f96e3858410c | note | CATEGORY: IP
13957fc1-4ecd-53f7-b26a-caf2b7690632 | note | RESPONSIBILITY: SE
b868bcef-f94f-5851-a65d-7104a0f3c660 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
112a1d7b-43aa-52ee-a466-8a128e6671fe | date | Date Completed:
| checkpoint | 5.17 Pipes - Lifting Holes
2a1de408-d5c7-56cc-9a5c-2f2044fd18d3 | note | REFERENCE: Section 701.18
3f4412e9-5bca-5c71-bf08-df798158d137 | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
9833993a-66d8-507d-b33e-ddcd0ddbe6ea | note | METHOD: Visual inspection
0d457fc5-24d3-57ce-b84c-f5d196f3dab6 | note | FREQUENCY: Each Lot
89d0d04d-f097-52d8-b659-2608b349c58e | note | CATEGORY: IP
5733b10c-2e2b-56ac-bff9-81a48f523b8c | note | RESPONSIBILITY: SE
c9d904b8-1030-5815-a31f-d35159484f26 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
03dd1387-c459-55f3-996b-9887acb1ebfd | date | Date Completed:
| checkpoint | 5.18 Pipes - As-built survey pick-up
fa3425a7-98db-515d-9260-ec4ccb8e3cc5 | note | REFERENCE: IFC Drawings Section 710.10
921cf323-bf47-5fca-986d-5232221d3022 | note | ACCEPTANCE CRITERIA: Each run of underground drainage shall be Survey verified prior to backfilling.
a6d78408-8a15-5109-8f31-2fe7230f0f14 | note | – Offset pits to kerb +/- 20mm
2d10cb31-7bde-5635-8e75-38e9e092f792 | note | – Plan location pits not adjacent to kerb +/- 100mm
c779f1ac-47e9-57b0-a01b-91018269f9a4 | note | – Invert level of pipes at pits +/- 50mm
4dfbd7b7-9a6f-5713-8ff9-8e372d1d5e47 | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
3e3de48f-d691-5997-b42c-77b84a1784e7 | note | METHOD: Survey
109745b1-c91e-5ea4-8c4a-e03e3b6cd6c2 | note | FREQUENCY: Each Lot
e1d5c005-3075-5011-9916-ce185375ccef | note | CATEGORY: IP
7ed5f41a-217b-594f-bcea-536a78ec638e | note | RESPONSIBILITY: SE
4f640641-0548-5e3d-846f-5889d44e85f9 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
60b7d6d0-7e6c-5dee-92d7-88309482adb0 | date | Date Completed:
| checkpoint | 5.19 Pipes - Backfill Placement
62ac3769-d08b-550c-b0dc-0f5c5f98118b | note | REFERENCE: IFC Drawings Section 701.16
3fc201a6-eb2b-533e-a350-e6ef01f76e4d | note | ACCEPTANCE CRITERIA: Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
e7a7e578-fcd2-5a19-acf3-c72fe59b7cd6 | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
62170fa0-67de-5850-9fb6-037765d24a54 | note | METHOD: Visual inspection, Measure
866d1f88-058b-5084-b5fa-88eb349ef223 | note | FREQUENCY: Each Lot
028773e3-c8ca-5429-8b99-1e9baefb2aab | note | CATEGORY: IP
d694c9da-2f0e-5712-9641-14b0b0342d69 | note | RESPONSIBILITY: SE
f2d0f130-e0c5-5bb8-9a72-8aa9dcb391a4 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
ce232754-6088-509d-b7df-10832b2641ec | date | Date Completed:
| checkpoint | 5.20 Pipes - Backfill Testing
245e99c7-65e2-593f-89e5-8c94825062e4 | note | REFERENCE: IFC Drawings Section 701.20, Section 701.29
3a711691-3321-5751-b6cc-e7f97819d13f | note | ACCEPTANCE CRITERIA: Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
c32e5ee2-3741-5cf3-8d1e-026ed9b18b75 | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
9f419473-c36b-52a7-ac1a-d19dcbbb322b | note | METHOD: Visual inspection
30f45d80-8fcd-5fe9-9805-ffaa7f17ba80 | note | FREQUENCY: Each Lot
74101bb7-f5a1-5fd7-b92a-9452506e1ca1 | note | CATEGORY: HP*
1cbe4d49-e2ff-575a-85dd-0cc2fba4e493 | note | RESPONSIBILITY: PE
c27f306e-b19b-5fa6-a61a-6779f4d1eb0f | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
a2eea4ec-4f7c-542f-89db-25c5c6799ea9 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Flushing & CCTV
bdae0840-7e5b-5898-93ae-2d8b8bbc86ad | note | REFERENCE: Section 701.28, Section 701.30
859bd84d-6969-5998-bb27-4d8b3101b69d | note | ACCEPTANCE CRITERIA: All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
7ce55413-4b29-5756-9723-2fb08f14bc77 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
c94933d5-dad7-5696-9bf6-c41a9770af62 | note | METHOD: Record Review
9850f3c1-6e7e-50b0-bc89-227e5ae1ed5c | note | FREQUENCY: Each lot
a83dbb4b-5bec-5145-94f4-77cf385e684b | note | CATEGORY: HP
06fa9d69-03ca-5c4f-b1de-ce9d0168f828 | note | RESPONSIBILITY: Nominated Authority
16ab72e4-ade3-5104-866b-c4eaed3b2ea7 | note | VERIFYING DOCUMENTS: This ITP, CCTV Reports
625e0772-0668-59fa-aa15-af0566016b96 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.2 As Built Survey
97df07a8-192b-532b-b4a4-425463913559 | note | REFERENCE: Section 701.10
8121313b-1395-5e27-afc8-9ef4bf8e89cd | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
35a8e7f1-991b-5cc1-9e4c-c90915ece1b9 | note | METHOD: Document Review
e9d81887-a271-5840-bfd1-f89a65640188 | note | FREQUENCY: Each lot
785da560-d9b9-5e6e-950e-0e5b96b9e6c3 | note | CATEGORY: IP
c4da27be-23c3-5ae6-9f0a-ff27202776da | note | RESPONSIBILITY: SE
ca30db6c-0d42-5f01-a031-9c1d4e799237 | note | VERIFYING DOCUMENTS: This ITP, As Built Survey Report
4a5e3f08-75a1-5ae2-b2e4-c1cc205b906f | date | Date Completed:
| checkpoint | 6.3 Repairs to Damaged Pipes
4108422a-8e64-5c2f-aab3-b8b60da10997 | note | REFERENCE: Section 701.31
dab07ac0-1512-510a-989c-28ed374aafe1 | note | ACCEPTANCE CRITERIA: Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
72936ca4-0e69-52de-ae29-96fa70332abe | note | ○ cracks wider than 0.5 mm
fd9a433f-46a8-590c-aa40-076cdcb2cd33 | note | ○ spalling of concrete
ad60de67-6d15-563a-b7cb-f177ff858ee8 | note | ○ exposed reinforcement
054bd3b0-e691-553a-ad10-4499c3121e92 | note | ○ joints that are not fully engaged.
5de4b956-6912-52e7-8f0b-930b0257e650 | note | Any pipes with defects greater than the following limits shall be removed and replaced:
6a50a2e0-ce04-5b1c-ba98-b9e30f7c71cc | note | ○ longitudinal cracks greater than 2 mm
849c430a-5fe9-5913-8f50-b1fbbb919a99 | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
035b0762-7dd8-5485-8809-265ab9e3934d | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
e24a01f8-8783-56da-b325-ebee7825abb8 | note | ○ penetrations with area greater than 400 mm2
b10f2199-2e14-5acd-ba5d-01a21748c10b | note | ○ pipe joints that are separated.
b3d27302-be44-582b-9ac8-2819bd008b15 | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
836e9fd0-20b3-59c2-8b55-ed8fc3a45544 | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
ffe79127-3fd6-5994-b44c-cd7f3bbd8b68 | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
3b35302a-3b53-5218-8222-a335942abaf9 | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
0dff35d8-9997-5415-90fa-3ec9eb160a49 | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
59064655-9b99-50e2-bad0-db1f1f7b8d9a | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
3d570150-972f-5b06-a40d-74033371161d | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
2410fa6b-c062-59ad-a04e-f561d9c52aeb | note | METHOD: Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
fe7867cf-1546-5f4f-b7cd-b415313b95b1 | note | FREQUENCY: Each lot
dff3f1d0-31a3-53eb-803f-5c5f0eefb258 | note | CATEGORY: HP
f5c1bae4-ccc8-50d9-ac93-742291d3915b | note | RESPONSIBILITY: Nominated Authority
8f2aeba1-03b0-5b20-b5d7-8268cfaee634 | note | VERIFYING DOCUMENTS: This ITP, Approved Repair Procedure, Post Repair CCTV Report
39ea62eb-a8bf-5d92-8947-fe9a158870ff | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
4a7737d3-dd65-54e1-a601-34b604d5104f | note | REFERENCE: MRPA Quality Management Plan
e3d35e2d-5ac4-5663-af00-c2a407946e2d | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
141a5e92-e839-5b1b-ae16-6d5605cd577e | note | METHOD: Document Review
4abd3fa9-43ec-5837-ab09-fcaa24ddd7f4 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
99bb9803-cdce-5fe0-a505-f16a42c1a34f | note | CATEGORY: HP*
32a9836a-9d20-5c3c-8a7e-a1fb88db331f | note | RESPONSIBILITY: PE
247e7ecf-67a3-5b8a-9a08-ed97630052a4 | note | VERIFYING DOCUMENTS: This ITP
5e3e94b6-fa21-5ce1-aa7c-1f60bf58e612 | date | Date Completed:
| checkpoint | Final Inspection
30f2f451-6f2e-5c2e-9357-7f8edadd7438 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
21fdb08a-adbd-5d82-9198-994ac4d013b0 | textbox | Name:
b44ae525-1888-58b3-a591-bbecf37797b8 | textbox | Position:
29c63d2e-9fdf-5653-9c65-70577800ddc1 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-081-STR-PSDS-Bored Piling Rev 0 | itp | ITP-081-STR-PSDS-Bored Piling |  | c2c09775-4839-4e2b-8cb4-bbe36522d05b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
f326ddb1-4792-54d0-ba31-cf7b86b25b48 | note | Document Title: ITP-081-STR-PSDS-Bored Piling
93dd001b-4332-52c7-9ec6-7771fb765776 | note | ITP Description: PSDS-Bored Piling
8d3c26e6-c501-5daf-a411-cb64f9e30cfa | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
2a5ad82d-b9d7-521c-8ede-9939d8174138 | note | Discipline (e.g. CIV/STR/RAIL): 081-STR
a53bbbc5-02cd-56ab-9d8f-e2784169b6d1 | note | Revision Number: 0
48c990fd-ab84-561f-a450-c0ada065505b | note | Revision Date: 7/12/2021
14bf47d3-4ca6-52d8-9ccb-634e169bacb4 | note | ITP created by: Mathew Velcek
34c58b80-46f7-55ce-b2de-15279b0b33ef | note | ITP approved for use by: VM
94a1dc9d-c92e-5556-8e57-9c4c8688f55f | note | 1.1 Non Dependent
f0865b7b-b478-563d-b6b1-c7f44d47f1e4 | note | Reference: VicRoads Section 606 July 2017
449db959-4367-5731-b00e-50dd2ef7a7ce | note | 1.2 Non Dependent
650b3a57-e9b9-530b-a0ee-2a1b5e6bef4c | note | Reference: VicRoads Section 610 Feb 2020
ec91a4d7-6905-58e0-95ac-e12699c941b6 | note | 1.3 Non Dependent
b9481284-bf61-51ab-a2b5-15e2cfccef66 | note | Reference: VicRoads Section 611 November 2018
472ef902-18ef-54ff-91a3-4a17658ec531 | note | 1.4 Non Dependent
db480f1c-ef99-5526-b732-2c25ba5d25da | note | Reference: AS2159-2009
1bce4b83-4cf1-5341-a540-1f27d774c2a3 | note | 1.5 Non Dependent
21034320-ccf7-51b2-b1d6-3ad6b95fb205 | note | Reference: AS3810.1 2018
bf8e0e88-e499-509c-866f-d7a1135c6bcc | note | 1.6 Non Dependent
087ec198-e6bb-5b2c-9d75-c2d838867e67 | note | Reference: AS5100.3-2017
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
82678dbf-ab85-5475-b2f1-b730830b0419 | note | REFERENCE: 610.07 Table 610.071
657d8f62-b731-5d9f-a670-75ecd5c02119 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
a3ee4bd1-6b54-571d-aba2-10f0f5f1cdd9 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
d14c6d8a-3f5c-5cb5-88d4-26e2fc8ec385 | textbox | Enter: Teambinder Material Approval number
c73cadd2-303e-5e91-abe0-2c8df6aa792a | note | METHOD: Document Review
b9a920af-7d03-5a4b-8b50-ae5eea953211 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
e6d52e13-7264-5277-99ff-3a6833ef2320 | note | CATEGORY: HP
a57062ee-db59-50ad-843d-d8512edf2890 | note | RESPONSIBILITY: Nominated Authority
aa00c048-1820-5fdb-aa66-bd00430aba71 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5149354d-8155-538d-a6ab-a2b35e46d827 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
f75194de-5b83-5301-98a2-63667b253e98 | note | REFERENCE: 611.05 (a)
7b2f4671-38e7-557d-9ea0-12fdb7b76b86 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
27aad95c-cee6-536b-803c-e755fb93db6a | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
db64d243-76ab-5f33-adcb-8a559679df97 | textbox | Enter: Teambinder Material Approval number
478df3ae-294e-5f53-b55e-76277771a827 | note | METHOD: Document Review
99b98f88-bd85-5dcf-a8c4-916093448cd4 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
2c3b8f4f-7f1a-53d2-a864-e1e4c7d7633f | note | CATEGORY: HP
44fe3b88-6b3f-570f-819b-d178afbd23ad | note | RESPONSIBILITY: Nominated Authority
12249fa8-b3c7-5668-a13b-4478ff422f0e | note | VERIFYING DOCUMENTS: This ITP
9107f57b-b5b9-55e9-ac0b-d063304f81d2 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
48353566-d1ea-5ead-b8d5-b7f31734636c | note | REFERENCE: 610.26 (a)
4bae30bf-219e-5642-b57c-c63bc699b541 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
cb41ea81-5f99-5711-b6fb-9b6cdc95a719 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
a25afb7f-934b-5db9-a695-bc8b2d2c912a | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
fb4c1f08-f307-5c60-9abb-e7d75ec14b24 | textbox | Enter: Teambinder Material Approval number
45c115b2-b18f-5c12-997b-b781e058e731 | note | METHOD: Document Review
e8e33c27-c9cf-5ffe-adcd-4db454b2bb0d | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
1ac17c1a-15ed-5582-8d90-4013c247ecf0 | note | CATEGORY: HP
1275826b-5005-5083-a53d-24326058c8a5 | note | RESPONSIBILITY: Nominated Authority
7dcbd13a-2143-5753-ab4a-f06079a6bb34 | note | VERIFYING DOCUMENTS: This ITP
5fbad56b-6caa-50d8-9130-5de5abb3c823 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Working Platform certification
7744db66-00fc-5b1b-8f5b-471978d4ef25 | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
ba941438-487d-5577-b095-338486a968fc | note | METHOD: Document Review
cbbc55f0-46d0-5abb-b6b8-cd8c1c0ebf6c | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
4d135f49-557a-54ae-8150-0fe511febcf7 | note | CATEGORY: HP
df9890fa-09d8-5640-a181-27de3a28b1d5 | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
ed5d7bf7-97f0-5040-a122-70eb35d46bb6 | note | VERIFYING DOCUMENTS: This ITP
0757e3f8-4be1-56b8-a442-99a9b20fae6d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Piling Operations Work Procedure
aa48faff-59bb-5b4d-809d-2a87719821a3 | note | REFERENCE: 606.03 (a)
32b79a1d-3094-5198-9896-c5c2b52f0067 | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
d6b2b9c4-52ea-5c5c-b742-3bfe19952a64 | textbox | Enter: Teambinder Approval number
6c0dd415-7138-512a-aacf-5de1228302f8 | note | METHOD: Document Review
f0ba6001-a576-5093-9fd0-6bde9e0156a6 | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
132a54e1-ec1a-504b-9359-a83fd72b6bfc | note | CATEGORY: HP
0c563ecc-5bcd-5331-8a75-d1225c97baf8 | note | RESPONSIBILITY: Nominated Authority
9e7a93ed-321a-53ea-89d3-f79b77de2a39 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
33eb915a-8655-5888-8102-158abd0ece8d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Temporary Steel Casings
8cd584d2-403f-518c-b09a-8ce518451601 | note | REFERENCE: 606.03 (b)
38697f73-c1c5-5f18-b66f-3d5749f3411c | note | ACCEPTANCE CRITERIA: Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
54466cce-663c-5dfc-a03a-0b4aba32d253 | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
7b5aacdd-73da-5fa9-bc45-64a165e1a309 | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
3252a745-900d-5740-9df1-38983dace3e3 | textbox | Enter: Teambinder Approval number
b1875357-1120-50f4-aeae-31dce7f50210 | note | METHOD: Document Review
5efa2bee-ff4d-5547-b5ef-f254c71c55fe | note | FREQUENCY: Where applicable, once, prior to use
0e05d688-fb3e-5324-9566-baeea8cda2fe | note | CATEGORY: HP
4960618c-5c88-51e4-bd56-150ef164f0d6 | note | RESPONSIBILITY: Nominated Authority
a02e0b1a-aa97-5d87-9ba6-43e38556d194 | note | VERIFYING DOCUMENTS: This ITP
8d0549f7-ae75-59be-94ea-c562f8ef9813 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Casting Under Water Procedure
8e3b80e7-4c61-5b85-94b0-31f0aca3e49e | note | REFERENCE: 606.06 (a)
f7c0d83b-0197-5d06-af3f-555d07fafefd | note | ACCEPTANCE CRITERIA: Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
0e6bc281-eedb-521b-8a05-b5a3fe2ec5b3 | textbox | Enter: Teambinder Approval number
3a367a99-00a4-5504-ac3e-e173a793d562 | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
9c127f07-0b37-5ad0-8ecf-00681e6b47cb | note | METHOD: Document Review
7d4bc386-4cbd-50c2-8600-9fdcafd5e708 | note | FREQUENCY: Where applicable, once, prior to placement of concrete
691ca531-1168-574e-92b7-5cf006fefe2c | note | CATEGORY: HP
757ca6bd-b6ae-5e75-b3bd-2fd56395f114 | note | RESPONSIBILITY: Nominated Authority
cf2bc7d7-667d-5688-8312-571cee818575 | note | VERIFYING DOCUMENTS: This ITP
80b9daba-a833-559d-b5bd-3df779ed53a8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
1d885dba-5211-54a9-b37a-9a423b636891 | note | REFERENCE: 606.03 (c)
64b397b6-c1f2-5ba9-835e-c2f1c2b18769 | note | ACCEPTANCE CRITERIA: Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
057aca05-cc1a-53af-b208-5eb5e1e4b4a6 | textbox | Enter: Teambinder Approval number
7aef41e1-5887-596b-8e36-f46209189226 | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
e2ed7f50-ff43-5b9a-976e-a167a17e1ff6 | note | METHOD: Document Review
62527ce2-483e-57d2-9a4f-2644974962eb | note | FREQUENCY: Where applicable, once, prior to commencement of boring
f9c85ff2-4871-584a-8951-018223536bf4 | note | CATEGORY: HP
7ddd2017-5a38-57ba-bf19-b82ff32b1230 | note | RESPONSIBILITY: Nominated Authority
6cc70316-85c7-5005-88f3-035916a96647 | note | VERIFYING DOCUMENTS: This ITP
f99bd3b7-e7c2-5170-a1a8-369ee29146a8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.6 Dynamic Pile Testing Procedure
27443ea4-867a-5bc2-80ed-1d2f622c25d1 | note | REFERENCE: 606.07 (c)
ef3ff52b-9e51-5c97-aeda-810232d0983a | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
7dc07aef-4ee7-500d-a7ce-d389e7dfa849 | textbox | Enter: Teambinder Approval number
ca09eaf5-c926-5ca9-956f-c59374f30819 | note | METHOD: Document Review
a4c35d64-179b-5ab2-b351-d1f584b44c50 | note | FREQUENCY: Once, prior to testing
7ea67c41-7c5b-5825-a01e-da3a4b2a2440 | note | CATEGORY: HP
a1426721-8b4e-5d38-b4a8-128b98fddd8a | note | RESPONSIBILITY: Nominated Authority
7ddf1563-88cc-54ed-9f0f-3d5ccabb9971 | note | VERIFYING DOCUMENTS: This ITP
70e765b0-f3a3-510b-873e-4fe86441c21a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Pre-qualified Pile Testing Consultant
c46a8e19-e45c-5869-9c35-388203f1cdf5 | note | REFERENCE: 606.07
fd47a797-3d5e-58d3-9c7b-25df5d1d93e6 | note | ACCEPTANCE CRITERIA: All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
0bc90919-0b28-5433-abd6-689ced1c8663 | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
db722084-b21e-5314-a18f-6e5c9c7936c8 | textbox | Enter: Teambinder Approval number
e741b5e1-3f6d-527b-aaf2-24c5718ac441 | note | METHOD: Document Review
b6de5653-6172-54fc-8dc8-239c99e8b38f | note | FREQUENCY: Once, two weeks prior to testing
828c06e2-8752-5391-9cb6-6287fdcceb3e | note | CATEGORY: HP
5cdc2f28-eb2d-5819-be9e-5b68125cae5d | note | RESPONSIBILITY: Nominated Authority
8a0ae626-ba00-5680-86b9-a033b329fbdf | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4147cf34-01bb-5728-92ef-d7102c67e599 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
772bd7d4-b513-5622-b23d-4a54a5f0fc8e | note | REFERENCE: 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
a35ed773-c46f-55ed-b306-2363ee871a1a | note | ACCEPTANCE CRITERIA: Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
29663543-a2a4-5e0f-b80f-a3fcc4465822 | textbox | Enter: Teambinder Approval number
d0da2f48-3e0f-5720-a2f8-1ad6ed9f1e61 | note | METHOD: Document Review
3efb9e61-c4bd-5542-81b9-88bb085e37c7 | note | FREQUENCY: Where applicable, once, prior to welding
93496a8e-3d4f-5376-860a-1bd69b939336 | note | CATEGORY: HP
cab223d4-bd75-56ed-9f48-eac29a813431 | note | RESPONSIBILITY: Nominated Authority
706ca335-ced9-5d50-a67c-4e7a13a160eb | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
10b05633-5762-5cce-b8d1-5ce20ce62c81 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
d96364c2-871b-5ed3-8cfb-f3486557b281 | note | REFERENCE: MRPA Quality Management Plan
a594099b-e63b-5ac9-be02-511a5a5daa42 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
b9de2857-63c8-5e40-bdc9-fe307bfb4a96 | note | METHOD: Document Review
4f7b7f23-3afd-512b-b479-f18b38a0fe47 | note | FREQUENCY: Prior to starting Works and at regular intervals
6bd6c086-9b9d-56a8-b97c-1acc3a770b06 | note | CATEGORY: HP*
6c2e8731-f488-595e-acef-5e3abe9ee621 | note | RESPONSIBILITY: All
9592842f-c65e-5f34-83cb-6f4e428ffe20 | note | VERIFYING DOCUMENTS: This ITP
728af4b2-29f3-5f10-af54-7274cdc2ef03 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
a3207bf1-e9a8-5aea-be68-46363ad1924b | note | REFERENCE: IFC Drawings 606.08 (a - c)
f1fe569a-cb4d-5339-a480-b02eb855677a | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
b14944dc-5b04-5b83-b241-f9b507321e72 | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
725620b2-4885-5a38-af88-e016ba66887e | note | METHOD: Measure, Visual
5c0125e8-4398-5fc8-809a-22c3f2149460 | note | FREQUENCY: Each pile
e5181657-d31e-52a8-af72-4a8a3cdcb72e | note | CATEGORY: IP
f9a16679-d99f-594e-b3d9-4046a1459336 | note | RESPONSIBILITY: Surveyor, SE
97d54947-d385-5f92-9b54-b214e89b90d6 | note | VERIFYING DOCUMENTS: This ITP
dad3c509-1aef-5884-ae13-e467052e2f3c | date | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
6e3e94df-460c-58f7-8696-1bb1691a47b4 | note | REFERENCE: 606.04
adee33fe-90c3-5c50-af6b-435b479f3303 | note | ACCEPTANCE CRITERIA: Pile construction shall not:
0a8ebb80-f8b5-52ab-8278-3dc48d468faf | note | i. result in damage to adjacent newly cast piles due to ground vibration.
8b2fea53-31ff-55d8-a659-ffff3a1a40c8 | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
5d18f1a9-037c-53c0-bffa-8c6a5a110748 | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
6988391c-4483-5eb3-bb79-842437d54edd | note | METHOD: Measure, Visual
b4b54985-e36d-5b59-a987-95223fabe34b | note | FREQUENCY: Each pile
c1f06a99-9130-512f-87e2-33726c3026f8 | note | CATEGORY: HP*
2840bef0-31ed-538a-9859-2b6b11063187 | note | RESPONSIBILITY: SPE/PE
ef8fba63-f847-5852-95e2-9b8d346a6f5a | note | VERIFYING DOCUMENTS: This ITP
11f17f0f-e73f-55f7-812f-4b5716e70395 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Boring Operations
2270728e-c812-5a07-812c-cb8f0f1f3b29 | note | REFERENCE: IFC Drawings 606.03 (a)
12fd69b4-b536-564a-a0e6-b734412b7c96 | note | ACCEPTANCE CRITERIA: Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
587f6e68-784a-538e-85e2-7ee02ea495ec | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
462acc74-809c-5a4e-a92a-a3586db05be5 | note | ○ Excavation clean and de-watered (where applicable) for inspection.
f57e5441-32be-5bbb-b850-523bba6d86ae | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
e78b7950-f9bf-5645-bced-23c7ba803c0e | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
144c0c75-4644-5bae-ad92-3a2e409e0e64 | note | METHOD: Measure, Visual
e956eca6-a83b-594a-a7a7-068908792320 | note | FREQUENCY: Each pile
df2e1df7-45e2-5fb7-97ab-2d23ebfc13e2 | note | CATEGORY: IP
3e45adc9-6ecd-5f50-9708-d87dc4722654 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
24b16ed5-c1da-50eb-959b-baf09cf88418 | note | VERIFYING DOCUMENTS: This ITP
531134d3-c58e-51c4-a5d8-b02cc8d643fc | date | Date Completed:
| checkpoint | 5.2 Formwork Extension
2daa278c-51ba-510e-9a38-35f41600aba5 | note | REFERENCE: IFC Drawings
01aff162-0ee1-5b49-839c-62606d16394a | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
e12327d7-72ff-55ab-9b00-6ab21293d953 | note | METHOD: Measure, Visual
4a856d57-fb59-5ce2-a5e1-5fa2aad41f6b | note | FREQUENCY: Where applicable, each pile
70c4d11f-6f9e-5b75-b22a-82761a699174 | note | CATEGORY: IP
7508389f-962b-5e39-8280-d9c832434b8c | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
e2c5eb3a-15a2-5546-bd21-253095b81d40 | note | VERIFYING DOCUMENTS: This ITP
b216e0ca-d42b-5b09-8586-72617a0ae831 | date | Date Completed:
| checkpoint | 5.3 Inspection of Pile Excavation
5cd3c8f4-f2ca-5c1f-9200-372ca5388c7d | note | REFERENCE: 606.05
419e63e4-cb67-51e9-818b-31174c9e8d7f | note | ACCEPTANCE CRITERIA: Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
6327e892-7366-5fb4-86c6-2e493020dce7 | note | Attach: Geotechnical Field Sheet or Report
bb2eb868-8080-5a2e-9b21-de3197247be8 | note | METHOD: Measure, Visual
c8433d71-dffc-55b9-a496-a28b8f752b94 | note | FREQUENCY: Each pile
6be27d44-1316-5a31-9628-251ec80cba10 | note | CATEGORY: HP
6b420364-5ed8-5bca-ba16-4d2ac4549eff | note | RESPONSIBILITY: Geotechnical Engineer
5b8fe170-6a30-59ec-8770-d9720da9e764 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f073e05e-9f61-52fa-9798-fd5a448b165e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Reinforcement - Placement
451f57ec-e641-57fd-b949-e1c604d74b6d | note | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
8cd7f5d9-dae6-51d4-aee2-dd3fe6b5e052 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
43803fc4-166f-564c-bdc3-d954144dd84b | note | ○ Projecting reinforcement is the correct length and location.
987b341a-e714-51c1-99ab-21343c0c971d | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
f9c7ce27-589d-5af3-a4c0-d7aeefd8911d | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
ebe4a2a2-ffd7-56d7-840e-64d900528514 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
62ba4ef5-9cee-5c7d-a73b-de88cb43133a | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
97208176-362d-5e84-af31-f1353fdd76dc | note | METHOD: Measure, Visual
af62d5da-3275-5377-83e2-416b92aefac4 | note | FREQUENCY: Each pile
d5afecbb-e208-5198-9764-8c99860cebfe | note | CATEGORY: IP
ae84ca09-fa3c-551e-90dc-4cb950ee85b3 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8b4a87ec-fd4f-57fb-bc47-0281a945bf00 | note | VERIFYING DOCUMENTS: This ITP
d766edf9-cb9b-5756-bd3c-795ddf3e7d96 | date | Date Completed:
| checkpoint | 5.5 Reinforcement - Electrical Continuity
8a2f7572-799b-55cb-9854-7e6b2c689cd1 | note | REFERENCE: IFC Drawings 610.29 (d), 610.43
6505e994-9643-511d-bccf-e7127d92ec8f | note | ACCEPTANCE CRITERIA: Pile reinforcement cage to be made electrically continuous by:
a6efc339-530b-52b2-9b47-268bbbd8dda6 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
3d69fa71-7f57-5d1d-a9e3-8da2316e43fa | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
e552ff4a-4286-5aab-b75f-fae66b76dd5c | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
f2bb27f6-6227-5ac5-877a-ce77f2bed94c | note | Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
a9e34c88-2c9f-5901-9e3c-e75669bec05f | note | Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
cae3c22c-5fd3-50a8-81e9-93cf073f5e17 | note | METHOD: Measure, Visual
dc3a0fd3-890d-5fef-8b39-5d7702cc8916 | note | FREQUENCY: Where applicable, each pile
ede5e1ac-f2db-52c9-8178-9da7029455b5 | note | CATEGORY: IP
947c5288-28a3-5b6b-a1d2-e3de8a04d1e1 | note | RESPONSIBILITY: Earthing Engineer, SE/PE/SPE
31793175-5a30-58c2-b33b-c3be1ae38810 | note | VERIFYING DOCUMENTS: This ITP
93a3b0cc-dc28-558b-b49a-17237ceea546 | date | Date Completed:
| checkpoint | 5.6 Cast-in Items
e256df11-37ab-514f-bec3-dd4c2f850c80 | note | REFERENCE: IFC Drawings 610.46 (a) Table 610.462, 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
0b6f8a5b-1753-5b87-a41f-fb2579727ff3 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
d5678c3e-c6b9-5c4a-831e-2c1727043e0c | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
056f245f-3cd2-50c8-bd5c-bbdd7c896297 | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
c4d0a5a2-fe9b-529f-8bcf-54a3e67a8ac4 | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
2ea4d951-5a14-5172-819a-afba6773ca33 | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
ad8be45d-375f-507b-aefd-ae31c879ca03 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
14617339-0ee5-579e-af53-f78f02933541 | note | ii. Running dimensions of a group of the above = ±6mm
eb9d5054-4cd7-52ae-b509-821813e2d26d | note | iii. Ducts and conduit location = ±12mm
9c7fb907-3503-5cc4-a0cf-a9ce2f33c122 | note | iv. Diameter of ducts and conduits = ±3mm
6a97b748-5d1a-5ea0-8739-a8bf3d2dcb3c | note | METHOD: Measure, Visual
11b31d9d-c9c1-5022-b386-f8656e31b0cd | note | FREQUENCY: Where applicable, each pile
dea0d236-c5aa-579c-bfb6-864e3c39437a | note | CATEGORY: IP
3016c6c5-8315-5ab4-b360-f504369a8623 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c6b7d356-ea42-53ed-afeb-2d9b59712bc6 | note | VERIFYING DOCUMENTS: This ITP
a383da06-cdf6-5f22-b7ca-03509b82a57d | date | Date Completed:
| checkpoint | 5.7 Pre-pour Inspection
2559bda8-cd1a-5dd2-b20c-114a7ef4cbf9 | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
8816c2f1-ab6b-5f2e-8e80-b041f308f893 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
77eb3055-c4de-556c-a9f7-186c45583f10 | note | ○ All foreign material has been completely removed from the excavation.
7a822bf3-340f-5550-8e20-95c348912cc7 | note | METHOD: Measure, Visual
3bd439b8-7034-5192-b03b-fba994f16581 | note | FREQUENCY: Each pile
56fca8fb-f97e-5a9e-b4a7-4bdfdd9efed7 | note | CATEGORY: HP
b6cd2ccd-ee35-5a34-9562-0760b0e749bb | note | RESPONSIBILITY: Nominated Authority
0690b574-55e8-55a0-80b1-0eaacf6d1d71 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
283b7315-5abd-5590-b5ec-d0cbdc76481b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.8 Weather Conditions & Evaporation Limits
09d36b95-dc69-5a44-8978-82abe9910005 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
ddbcb0c1-132f-50b6-821a-ced79b16a416 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
ffc87719-808b-58a5-b415-a3176878ad38 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
bc315877-ab6a-5a5b-92da-100f049f5ecd | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
dab41219-8c4b-5b5e-9328-ba7e507aeed9 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
5d76e5bb-ecb6-5bed-acff-5fe341454167 | note | Record: Required information on the Concrete Pour Record.
e954c18f-c6f8-5da6-9f9e-9dd6e557ec3b | note | METHOD: Measure, Visual
9df3e87c-be0d-5b78-909c-68ba133c9d1f | note | FREQUENCY: Each pile
939241fe-73cb-549d-b9c5-f5eeec0d8695 | note | CATEGORY: IP
fe4c5a97-3df7-5b32-8703-6e2f6dd1a71b | note | RESPONSIBILITY: Foreman, SE/PE/SPE
eaccba3e-5e0b-539c-9e76-5b76dc8e8383 | note | VERIFYING DOCUMENTS: This ITP
94ab64b2-d047-5515-bcde-b03401a1863c | date | Date Completed:
| checkpoint | 5.9 Concrete Testing - Sampling Frequency
f7c0e158-8602-54ad-a61d-7b1fb8b49ab0 | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b) Table 610.161
1a5d7799-d675-543e-9721-3aec50e7bc6a | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
5e8355b5-18f3-50e1-8feb-8eebc62f7193 | note | 0m³ to 10m³ = 1 sample
546f921b-654c-54be-8d13-038841d1be2e | note | 10m³ to 25m³ = 2 samples
ec83ac58-dd20-5522-9832-947889ef0cfc | note | 25m³ to 50m³ = 3 samples
28dc1cce-652e-519e-8b49-483fa5669992 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
fda1e5f6-2a41-57cd-8400-28bd658fa7de | note | ○ For each additional 50m³ and additional sample shall be taken.
91b7c070-d50b-5b84-a84e-013ae3fa1d23 | note | ○ where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
05293a22-07b4-5c0e-b6b7-e2679ba46fb5 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
513a2cb9-a5a2-5ee4-b235-078c488061f4 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
5d9754b1-21fa-5f59-b18f-8f8ed4b03e25 | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
6153f30a-f868-529c-bb85-3506382a2bf7 | note | Record: Required information on the Concrete Pour Record.
9ffb957c-ec7e-5b75-b7d3-ae2f40ea9103 | note | METHOD: Test
7f496865-2d2b-5b36-b8d9-ef1f5089918a | note | FREQUENCY: Each pile
0de2bc4e-b2a4-5c24-a68c-690c25f42624 | note | CATEGORY: IP
cd366c9b-a06f-5443-aa48-aec6f7e63f15 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
db6553ee-e595-5237-9455-4f07f7b685c9 | note | VERIFYING DOCUMENTS: This ITP
01127d29-8a90-568b-88bd-3b1bbb60aa7d | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
9717e5af-0616-5c3b-a404-d770e2a2758e | note | REFERENCE: 610.13 (b)
bdf10e67-53d2-560d-9f2b-8245eb6c9108 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
9ab529e4-fbdb-51d2-9f44-cef8001357e3 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
ded3da3f-55fc-5608-93da-02f209b0f6c7 | note | ○ Passability = ≤10mm (aggregate height differential)
95c3bab1-e29a-57f4-95f1-405ef0eef587 | note | Record: Required information on the Concrete Pour Record.
a5756e7c-c483-58e6-850d-0fd4900bae2e | note | METHOD: Test
69cabe36-8d5a-5288-8d6b-65615dc13037 | note | FREQUENCY: Each sample of Self-compacting Concrete
c1330993-72ef-54ad-9451-d9c6cc3e2ada | note | CATEGORY: IP
b587bcb3-a118-513c-9101-cfa21b2e572a | note | RESPONSIBILITY: Concrete Tester
839f03d6-f146-5ac4-8ee2-d3001cfeca53 | note | VERIFYING DOCUMENTS: This ITP
13a45fb4-1a4f-57de-ac6a-3f7337133274 | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
14dfa034-4b61-5c93-a22b-f0e5452fc115 | note | REFERENCE: Site Sampling & Testing Procedure 610.16
960654de-d4e6-510b-b1c4-8e7405f04281 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
d8429a5e-b0c2-59d8-abae-6dd54380dcec | note | Record: Required information on the Concrete Pour Record.
2fb0ddcf-3f45-52b3-bfe4-194db169b65a | note | METHOD: Test
b4036952-acfd-570f-a04b-edb85c4c1dce | note | FREQUENCY: Each sample
c5a452e4-4f38-5878-8252-c740ec2cc2a8 | note | CATEGORY: IP
326794e8-68af-55ce-8b75-d009898902ac | note | RESPONSIBILITY: Concrete Tester
1a25bbbe-f252-5bbb-893c-73151cd1ea75 | note | VERIFYING DOCUMENTS: This ITP
81912e31-b4a6-5f08-9950-fc79c85fd2d9 | date | Date Completed:
| checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
b38e4860-0ea4-5d49-91d0-955e1b3620b0 | note | REFERENCE: Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
fcfe4fea-5c53-5423-b8df-f3d6726a341d | note | ACCEPTANCE CRITERIA: Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
f3e3abca-eb99-5bcb-8eee-4ab21cf70906 | note | ○ All concrete batches are traceable.
2a19af8d-dacc-55d1-81fc-e76f7aa71e15 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
21082d24-cadb-54ca-858e-e7fc86e88d05 | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
afd5c334-86c8-57ae-a162-22f28eca6666 | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
a5737527-6007-5c45-b7ff-62b78ce87625 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
3e2c083d-1394-5432-9adc-ff99a9c17b58 | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
474912b6-892e-5a4f-ae93-47c9a236d2b5 | note | Record: Required information on the Concrete Pour Record.
4deb65c5-f1d1-5130-a06b-ff8d4141dcd9 | note | Attach: Concrete Pour Record
66e81d02-0074-50e8-b6a9-57cba6ef2287 | note | Attach: Concrete Dockets
1de19c9c-af93-5d0d-a3c5-8d53f393268c | note | METHOD: Visual
b55b5756-89f8-540f-88b2-d04ab7282545 | note | FREQUENCY: Each load
ab06549e-badb-56ea-9e63-2e5b304d5a2a | note | CATEGORY: SP
d6b3a27a-6a26-573b-9eff-61f737cd6192 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b39518e0-f702-5bf8-90ef-3a362657e279 | date | Date Completed:
| checkpoint | 5.13 Surface Finishes
b80cc77b-f475-5df5-b8ab-d985e947e77f | note | REFERENCE: IFC Drawings 610.31, 610.20
9569bf39-7f89-5e17-ae58-bc748653bc7e | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
d4635bc6-bcd3-5207-927a-183f89ebb3e4 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
907447d0-6f45-5ae1-adaf-6fa5f5588c97 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
3c0cb462-8b38-53ae-a0be-4814a7823c2b | note | METHOD: Visual
49027dce-c153-52f6-9ea1-1c576a7a1a3d | note | FREQUENCY: Each pile
ed84d3a7-ae5b-5b90-96a9-b7c5c39f4ebf | note | CATEGORY: IP
5d046493-982f-56b2-9524-8891f0c35d08 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
d0307dbe-371d-553f-8494-cab2144c68b2 | note | VERIFYING DOCUMENTS: This ITP
6628bac5-02d6-5dcf-a685-bfca24e8e389 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Pile Trimming
1f5e83ce-63d7-5b65-9985-530e3e87ab14 | note | REFERENCE: IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
72c492a6-15b9-5bb3-8846-a094e196594e | note | ACCEPTANCE CRITERIA: Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
be91a28d-d1bd-507a-b655-5618260ccc50 | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
cf0c018d-a203-5c3b-bcab-ca8990e4ab16 | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
5274eb6c-ecb1-5f77-84db-f49044110b2d | note | METHOD: Measure, Visual
08dbda93-8be9-5587-b63b-1030062ec733 | note | FREQUENCY: Where applicable, each pile
1f39d61f-8297-5eb9-ae87-5b2357c65420 | note | CATEGORY: IP
89e17810-136b-5e61-b6ac-8cc859ab13fb | note | RESPONSIBILITY: SE/PE/SPE
87063104-25d4-525d-8ae5-c3d5ceb44317 | note | VERIFYING DOCUMENTS: This ITP
9b7f46fe-ff6d-5487-bea7-e6fda5605edd | date | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
a4b3d289-8a57-55dd-9bff-bae2e3d505b1 | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
adb80a7a-7918-535b-8670-e4c434f15288 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
f086bcd4-7bf6-5190-8df6-642cf918c0c3 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
48a7eee6-15e0-5c8b-96a6-42561d2fd310 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
a3cf1abd-253e-5d8e-a6e7-3594d84e8c7d | note | Attach: Compressive Strength Test Results
983e1d9c-dda5-56fc-b1c2-609712e50dca | note | METHOD: Document Review
20aa5e45-9ed6-574f-bd73-26e65fec30cf | note | FREQUENCY: Each cylinder
e4778b40-f5de-5932-80d2-a51e6df19033 | note | CATEGORY: IP
67e304d7-62cb-51b7-a88d-f54bb21482ac | note | RESPONSIBILITY: SE/PE/SPE
42e094b7-921e-5bfe-82d4-1e5cbadc81c3 | note | VERIFYING DOCUMENTS: This ITP
3fd8283a-fbfe-5860-9d0c-79686e85fcc6 | date | Date Completed:
| checkpoint | 6.3 Pile Integrity Testing
94db05cd-c982-5262-b41f-042b1b6f0bfa | note | REFERENCE: 606.07 (a, d & e) AS2159 Clause 8.8
d6de77cf-45a2-5f57-b710-e7c6ca230000 | note | ACCEPTANCE CRITERIA: Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
6cb23655-1e08-59c7-9ba5-2404225741f6 | note | ○ Cross-sectional area = ≥95%
4ffa1241-a68f-54c2-8844-e90227c574d3 | note | ○ If any test fails, all piles shall be tested.
4e262d49-2a09-5194-8641-33d89d7e99b5 | note | Attach: Pile Integrity Test Report
ffd5025a-fcf9-54f9-ba6b-5411da9f73b7 | note | METHOD: Document Review
c6f799f3-8537-5058-9d64-c8f83b8eca02 | note | FREQUENCY: Piles #1 - #6.
ab184c6c-4383-5316-92c9-5309666a09ae | note | ○ Reduced to 1 test per 3 piles if the first 6 tests pass
d6fb1087-e0ab-5671-83ab-28c2bf4a6d39 | note | CATEGORY: IP
deae3f0a-71cd-5948-a5b5-c054130f3b64 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
6781f3b6-6eee-5f0e-9877-a5819a140a59 | note | VERIFYING DOCUMENTS: This ITP
0e64d149-c17c-5bc8-8957-283eed0478ef | date | Date Completed:
| checkpoint | 6.4 Static Load Testing
50492801-6045-5fb6-8a8e-6b670730a8f1 | note | REFERENCE: IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
d6c3eb3c-ffdf-5fb1-9c6b-87c593deb1f8 | note | ACCEPTANCE CRITERIA: Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
f4e82e0c-e87d-5ece-aa5d-d32496f063eb | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
79fd0dba-facb-5c6b-a28b-a49ce00c093d | note | ii. Creep rate = <2mm / log cycle of time at the test load
1b1721c7-c888-56ce-bf43-43cbccfcf9f3 | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
d21cd3c1-0028-565e-94a8-ce30cd45162a | note | Attach: Static Load Test Report
aa89e497-5168-59bd-a9cd-1b0d3b5bfc1a | note | METHOD: Document Review
d3edf817-6406-5914-8aac-a72a597fba2e | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
1a60dda5-7612-58cb-ad1c-022793f2b2bd | note | CATEGORY: IP
498fe558-082e-594a-a3b1-576b30b02378 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
fbd9d725-a93b-542d-97c5-f318a47020c3 | note | VERIFYING DOCUMENTS: This ITP
f77738fd-b49c-528f-b3c2-663777f9e91d | date | Date Completed:
| checkpoint | 6.5 Dynamic Pile Testing
dc08357e-847d-52c3-9d6f-3fcba5f3c3b4 | note | REFERENCE: 606.07 (c, d & e), AS2159 Clause 8.7
7e17bfa6-7286-5c7d-895f-34ef43a5d6a5 | note | ACCEPTANCE CRITERIA: Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
37189798-8b28-514b-8cef-a5b4c2ae0c2c | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
df8e36d7-ceca-51c4-a5a5-f8bca887ab6f | note | Attach: Dynamic Pile Test Report
d785e235-47fd-5ab5-b3e8-d19a8f87ac9b | note | METHOD: Document Review
81e14007-c823-5ded-ba2b-83a73a3d49a9 | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
17661caa-d7fd-5105-b44a-88645b1d998f | note | ○ At least 1 test per 10 piles
4f9f605c-c70b-5beb-a83b-82114ddea7ba | note | CATEGORY: IP
91a8f50c-aa7f-51cc-bcc5-a440acd6e880 | note | RESPONSIBILITY: Testing Consultant, SE/PE/SPE
61976b1d-bd2a-5476-8a25-0b7751079dfe | note | VERIFYING DOCUMENTS: This ITP
8c8e6f15-bd4f-52c3-a22e-f0feb0b1e861 | date | Date Completed:
| checkpoint | 6.6 As-built Survey
ad29f10b-2ab6-5df8-af68-269645c0ff9b | note | REFERENCE: IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
7b02c025-9035-543b-8a14-13d7d89f1852 | note | ACCEPTANCE CRITERIA: The following tolerances apply to piles:
9318c57e-50bf-54a7-bf1d-f256815292fd | note | i. Pile head plan location = ±75mm
77785c0a-5841-5d79-ae33-eeaf4c76236a | note | ii. Variance from vertical or rake = 1:100
76e02fef-848b-56ef-96df-6f8a9ae9ff6d | note | iii. Irregularities in straightness = 1:100
11f33dcb-ee1e-5297-9a52-c82ecac09529 | note | iv. RL = ±25mm
37fa4614-dbd6-553a-97aa-6b6354fdb1f0 | note | Attach: Survey As-builts / Survey Report
9d61e835-c8f9-52f6-b8a5-56dcde5d3fce | note | METHOD: Document Review
276cca9d-90e3-56bb-896b-76c5ede469c2 | note | FREQUENCY: Each pile
3dde48fa-08b6-5395-9094-ad17b98464ee | note | CATEGORY: IP
86ac65c3-5b7c-5425-8398-6a3e79cf5c79 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f85992bb-57db-5418-b6b1-60353a797478 | note | VERIFYING DOCUMENTS: This ITP
8a52ef6f-a1e0-5e17-a7a5-f7783bc73fe1 | date | Date Completed:
| checkpoint | 6.7 Non-conformance Report (NCR) Closure
90a14310-9f38-54e6-9302-13bdb7a95beb | note | REFERENCE: MRPA Quality Management Plan
c05f8a5b-5124-5088-b373-88aadd279b39 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
3d3e40a1-51ad-5fe0-869d-045238a2fe08 | note | METHOD: Document Review
d7aced71-9a6b-5862-8754-dea2b0409ce8 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
c077ae9f-a429-5019-8819-54dddced5f5f | note | CATEGORY: HP*
0ef65c01-7ee1-5c6f-bd27-4dc5ad9866d6 | note | RESPONSIBILITY: SE/PE/SPE
a07997ff-29ee-5d5d-8379-d9e0228e9978 | note | VERIFYING DOCUMENTS: This ITP
d5db49aa-ff33-5255-b7be-71f6e2a9027b | date | Date Completed:
| checkpoint | Final Inspection
54b94864-4847-5111-9b1a-ee995b5b6da0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6867b7cb-683e-5cd2-838b-4f661720bd38 | textbox | Name:
0b346b4b-87d3-58b0-a474-55920c864a96 | textbox | Position:
a8977d35-9736-5652-93a0-e60deb46d849 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-083-CIV-PSDS-Footpath-Industrial Crossover-Traffic Island Rev 0 | itp | ITP-083-CIV-PSDS-Footpath-Industrial Crossover-Traffic Island |  | b8e26a58-6649-43a3-9f00-9748bd8f6eab
| section | Referenced Documentation
| checkpoint | Referenced Documentation
4e26ffba-03c6-5642-8764-602bff3be227 | note | Document Title: ITP-083-CIV-PSDS-Footpath-Industrial crossover-Traffic island
bad55f8a-7afb-5835-946b-56752dfefb9e | note | ITP Description: PSDS-Footpath-Industrial crossover-Traffic island
3c85ecd5-3e2d-5885-9fc1-27fdfa14d781 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
d77622b4-6463-5af6-8a7f-c49794f7ae2f | note | Discipline (e.g. CIV/STR/RAIL): 083-CIV
86668c5e-67a4-556c-9c11-d12589069298 | note | Revision Number: 0
33602419-082b-5d3a-b6ce-707359d6e4f1 | note | Revision Date: 21/02/2024
1912c470-bf25-517a-90cb-f6f809cdfa97 | note | ITP created by: Abhi Patil
84f754c1-5b83-5a91-9845-aca5f158cda5 | note | ITP approved for use by: Victor Mira
1f1e08ab-4700-5551-b647-c9ecabd6ddd0 | note | 1.1 Non Dependent
d8d3205a-b962-5010-96ee-2b8409bf4ff1 | note | Reference: VicRoads Section 304 August 2013
9ea7a373-d0c5-5140-9b6d-4623f1e11a7b | note | 1.2 Non Dependent
da148009-5366-5fe2-ac03-2e9c6f672821 | note | Reference: VicRoads Section 703 April 2019
235e27db-2b86-5a62-8e3c-28e0c636f335 | note | 1.3 Non Dependent
7f0fca8c-05b1-5c69-861f-16b993eb21aa | note | Reference: Council CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
7474ecba-1b00-5d85-9341-988d4c9f3869 | note | 1.4 Non Dependent
c2ba7a52-0eb1-5c15-a20e-714db234adb4 | note | Reference: AS 1379-2007
fcd17006-dcb4-5c86-8779-ecd63479292d | note | 1.5 Non Dependent
bb69cdf0-051b-54e7-979a-90f61e2d3d57 | note | Reference: VicRoads Section 812 July 2016
1fe4df38-c115-5f70-b89b-685f02943c82 | note | 1.6 Non Dependent
3dcc8ed6-bd8b-5b79-8368-d37e3e30a6a4 | note | Reference: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
| section | Preliminaries - Materials
| checkpoint | 2.1 Bedding Material Placement & Compaction
ad3139a2-0745-52cb-98e9-a3921cf7190c | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 812.04, 703.21
5186c6f4-7f2e-5f53-9962-3c5662f66841 | note | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
764a8924-facc-5faf-a8b6-75309742d818 | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
49365a2e-9711-5d9d-8de9-2890ab3689bc | textbox | Enter: Teambinder Material Approval number
00b7d399-8984-5787-b260-82ff9515e3d3 | note | METHOD: Document Review
53219220-452c-5150-b88e-af59c4d93cb1 | note | FREQUENCY: Each Lot
eac2e012-6b2d-5402-8f64-6cd10016897a | note | CATEGORY: HP
70212c48-5100-57aa-bb4a-8acc42822287 | note | RESPONSIBILITY: Nominated Authority
2fda8e62-91d2-54e9-9e7d-e11ae529f2da | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
7450adec-9d77-567a-87de-eaf70d9f64f3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Concrete Mix
28da9624-c447-564e-bf9f-622f482c7072 | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.05 (a), 703.07
254fdd86-6150-5bc1-b96c-6879e98e2c60 | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
d52aa123-742f-5385-9eec-eb3959133ca1 | note | Footpaths (Pavement Type 7):
6bdcb154-ff9f-5d81-be71-0dd1ba7b8183 | note | – Concrete Strength: 25Mpa
cb4906a3-cc93-5f2e-ae4f-a45e9a5eaa89 | note | – N25 with eMesh (Macro Synthetic) Fibres Applied at 5.6kg/m3
7c7c6c1d-d5e4-5eb4-bda4-99f1d4381fa7 | note | – Min 30% SCM
a0139f58-f0b6-5ed6-b458-3a38e4f4cf07 | note | Industrial Vehicle Crossings (Pavement Type 8):
cc07f253-c5e0-5c28-92f9-1353f993e037 | note | – Concrete Strength: 25MPa
35086c01-cd3c-56f5-8613-6b98951e093e | note | – Min 30% SCM
bd0ee2c4-cf59-5376-9e30-87a299c1f5f2 | note | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4)
7e92a7bc-dd22-54b0-b747-280f2e702ab4 | note | – Concrete Strength: 25MPa
e6e73323-19a7-55a8-928e-30378c79223d | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
946372ab-0bd1-5cd9-a449-5f166d846437 | textbox | Enter: Teambinder Material Approval number
41c710d8-680f-5b40-9cae-b74dd80ca9b5 | note | METHOD: Document Review
ed52977a-446a-572a-b4e6-52e268640e14 | note | FREQUENCY: Each Lot
0fe34eaf-987f-5984-a222-e39b77937e71 | note | CATEGORY: HP
57bc92e2-48cc-5a20-b172-b6d2abc52486 | note | RESPONSIBILITY: Nominated Authority
e622c55c-f46a-520a-aa54-63b54bcd309f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
2bbabd10-d171-5ca3-b962-8cbe4d84de31 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Reinforcement
aeba8d86-584e-5bdf-b983-d2a81f10019c | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.16
4a41a3b4-0778-562b-a3ce-38b87685afc2 | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
24b0b3f2-3851-53cf-a633-512e390333bd | note | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
74853313-2fe7-5bbb-a104-b71da40eaab0 | note | Footpaths (Pavement Type 7):
ba6faa57-8ad4-5c26-9a92-5c784e3d7003 | note | – eMESH Fibres Applied at 5.6kg/m3
8407506a-5516-5b6b-b444-48c3815ae740 | note | Industrial Vehicle Crossings (Pavement Type 8):
196f4e91-2a91-530f-a664-f4b98b1ef49a | note | – SL82 Mesh (Centrally Placed)
bfaf579b-2109-5a1d-95bf-3123d190b196 | note | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4)
a110d79c-0d70-59a4-a2c1-1a42b402830e | note | – SL72 Mesh (Centrally Placed)
872d5ffb-3eec-50f8-a9e0-776fbd91cf0f | textbox | Enter: Teambinder Material Approval number
cce98823-40e8-514a-b035-dbe9ff5c1d19 | note | METHOD: Document Review
e7be3383-1415-588f-bdb3-89efbfbaeaf1 | note | FREQUENCY: Each Lot
29c9019f-5cdf-5001-936a-e08fd6577592 | note | CATEGORY: HP
cae70c2e-a4fe-5564-b734-164bcc397fb0 | note | RESPONSIBILITY: Nominated Authority
71a638d1-7d93-5c0f-a662-ad4c975497bb | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
81172436-12db-5861-bd30-c068bf93b573 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
e0bc67a4-75f7-59aa-93f4-08b92379edf2 | note | REFERENCE: 703.09, 610.17 (f)
157df81a-7417-5da1-a7cc-99736c109dc4 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
033458a4-cb20-51d3-bba3-41c20be920d0 | textbox | Enter: Teambinder Material Approval number
9c6da5dc-2f00-5f6c-8427-5dbe906651f9 | note | METHOD: Document Review
bfdb8ed4-5d7a-5450-8fa9-cd885737601d | note | FREQUENCY: Once, for each product, prior to placement of concrete
bdf8798a-1ada-561d-bb21-9e8a5cc197d7 | note | CATEGORY: HP
76b70af7-3c0a-5b77-a644-317078e7502f | note | RESPONSIBILITY: Nominated Authority
1cecad8d-722a-503d-8b57-1768c072f4e4 | note | VERIFYING DOCUMENTS: This ITP
154b377e-8e6c-5081-b879-ff9a95f0d243 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
f4290ab4-4d51-5da6-885f-9c9762371ede | note | REFERENCE: 703.10 (a), 610.23 (d)
cfdae339-2a7c-5f6c-b675-d4befe12f1de | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
6e39f2b6-0e40-5b99-9503-2492e1838dc1 | textbox | Enter: Teambinder Material Approval number
c8dbff0b-5663-5dad-b3d6-0ec698a17c6b | note | METHOD: Document Review
78f33c87-4cd8-599b-927b-f4d36183d432 | note | FREQUENCY: Once, for each product, prior to placement of concrete
740652f1-871f-5b34-89fa-01af76c012b5 | note | CATEGORY: HP
dfdda8e2-afc9-5a84-b01e-b8ea117198f9 | note | RESPONSIBILITY: Nominated Authority
706fe65e-f8aa-5c3c-8eb7-1ff3991574ca | note | VERIFYING DOCUMENTS: This ITP
4faa9e2f-3d74-57c2-8cd9-bb3b60d88b08 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Documents
| checkpoint | 3.1 Survey Set-out
fdb23812-ff5d-5104-b7d3-a4323220ec7c | note | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.17
86cc9950-68a1-5e57-bea7-b57f5040bb4e | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
dc900a2c-0aff-5bf0-930e-63a028bc70b2 | note | ○ The Nominated Authority will review and confirm the set out.
6f37dba7-af1b-5b25-94af-de916550a73c | note | Attach: Survey Report
33e25196-169a-5a91-88ee-4e2681c72733 | note | METHOD: Document Review, Measure, Visual
4e7f1ac5-c8e9-5101-a1db-c89bfeecf0e8 | note | FREQUENCY: Each lot
8e941e89-7122-50ce-a74f-e1977b124086 | note | CATEGORY: HP
6d7cca15-f924-5756-b756-182ffcc9458a | note | RESPONSIBILITY: Nominated Authority
e5eb45f3-b6f3-5fec-b8e3-d3726d749de0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
bdbf97fe-6fc2-5724-9a97-f0327111bffc | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Lot Map
625340b9-8d5a-57f9-b48c-1f6ccc125822 | note | REFERENCE: MRPA Lot Management Plan
8b6a14a8-31e4-52e3-a6b3-956696e3393e | note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
a1c3f7a8-b252-5e01-a0d1-f4f11ad69337 | note | Attach: Lot Map
c94d35ea-d2ea-5f09-a53f-d4a6b19c6317 | note | METHOD: Document
4b804730-c6c2-5c17-932c-0a8f09d8f6ed | note | FREQUENCY: Each Lot
96e426eb-4fe5-5f0a-9715-3a7bcf3e965c | note | CATEGORY: HP*
06cdc695-674e-5efb-8bff-e6c22d3f7261 | note | RESPONSIBILITY: SE/PE
8914a7ee-0b5c-5e2d-a0d0-bb5f01575fe9 | note | VERIFYING DOCUMENTS: Attached Lot Map
2aa9fc93-af00-5c45-be34-48f38cf9a068 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Site Clearing & Grubbing
ce39a6fb-0ccb-5caa-a719-3b473d7035e3 | note | REFERENCE: IFC Drawings
da420ed2-e538-5a91-bdfd-58bfc388ffe2 | note | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
45cef61c-b56b-5abb-84e4-945f8956bdfb | note | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
9e03eeb2-7c9e-5726-b7f9-c5484fbbb2db | note | METHOD: Visual
565b6993-2882-57b0-ae0f-d944c6682847 | note | FREQUENCY: Where applicable
560c0f89-79d2-5e4f-ae14-17bb8b1f96ac | note | CATEGORY: IP
94efdd9f-5481-5474-a606-29bcca8ce2a2 | note | RESPONSIBILITY: SE/PE/SPE
9b3bb9ca-d595-5222-b187-e46dd7d38822 | note | VERIFYING DOCUMENTS: This ITP
b06dec8e-148b-50be-b3d4-1223e7778dbd | date | Date Completed:
| checkpoint | 4.2 IFC Drawings
c53a93c0-42e7-5fa2-a489-25beee94ec31 | note | REFERENCE: MRPA Quality Management Plan
7a657049-c397-5a01-b09d-76ac6c035c41 | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
6083128e-ddcd-56a8-b38e-3f89058f014d | note | – Using the correct and complete set of drawings
e636d3c8-5974-571a-8a95-a2474d5586ab | note | METHOD: Document Review
8726facb-ad11-53ab-8ff0-ca8068fb3322 | note | FREQUENCY: Prior to starting Works and at regular intervals
a1d11053-bf92-54fe-b01d-b7fd04e06abe | note | CATEGORY: HP*
2e011b18-21c6-5f7f-bc3d-8e1dd4ebb62e | note | RESPONSIBILITY: SE/PE/SPE
76c04d81-6d38-590a-89c0-20810ac16add | note | VERIFYING DOCUMENTS: This ITP
cb9b0e9d-6587-5286-93f5-32f4a741f17d | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Excavation
c674d4e1-d380-5b1f-b448-34a646a1d0be | note | REFERENCE: 703.20 IFC Drawings
2478dd2c-8f69-56da-b2b6-d59c658f71e9 | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
c439d0f4-bdae-5981-967a-d477b754e88e | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
93e1d570-d31c-5ea1-ac9d-36e913822e99 | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
b8df9b90-9d90-5718-be33-df7bf6c0f75a | note | METHOD: Visual, Measure
57e80157-20b1-5c86-a464-0d9e19bd19e5 | note | FREQUENCY: Each lot
92fd1485-2f78-5ba4-8220-83271ca60660 | note | CATEGORY: IP
e453f4aa-4db0-5ed8-b7e5-8035ea6a65b9 | note | RESPONSIBILITY: SE/PE/SPE
d0f71159-d277-5439-ba71-6d81645f2fc0 | note | VERIFYING DOCUMENTS: This ITP
41c68ede-e99b-5cf1-9a9e-23e8dfbca874 | date | Date Completed:
| checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
d7f8ca0c-b32a-550a-9b65-3b3faf02cdf9 | note | REFERENCE: IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
b7ba1034-002b-5247-8a81-88d7dccf8f9f | note | ○ Relevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
97221ab5-49b1-5fa3-af77-ef03d3e53375 | note | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
2479cb6f-ea53-5b18-8914-6e36af387db8 | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
6251cff6-a9d2-5f99-bafb-b2246b60c391 | note | METHOD: Visual, Measure
fc8f6580-00e5-5a5b-b6f4-22febf72926d | note | FREQUENCY: Where applicable, each lot
abd138fe-5bbf-5a0d-8a75-d998bd064a86 | note | CATEGORY: IP
c85504f7-9c34-5b81-aa4a-9998d308b843 | note | RESPONSIBILITY: SE/PE/SPE
4e837cb4-b0f8-5289-ad1d-1e9f039deb6d | note | VERIFYING DOCUMENTS: This ITP
e5dd5e44-fcbe-5674-89d2-66e6ef5bac98 | date | Date Completed:
| checkpoint | 5.3 Bedding Material Placement & Compaction
1d8471f9-d550-5387-9dc3-3362e27b2fbd | note | REFERENCE: 703.21 IFC Drawings: MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
ddea3e8a-ed92-576b-a462-87b3a7bedd51 | note | ○ Relevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
8aa70893-c4fc-5ce9-bb87-aa06a445c4bb | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings :
f4869004-d160-552a-a508-d954a7f911ca | note | Footpath (Pavement Type 7) / Industrial Vehicle Crossing (Pavement Type 8):
38344c9f-b943-58c7-9e16-ce2fc102f3e7 | note | – 20mm Class 3 Crushed Rock or Crushed Concrete
5f0b9771-a0a2-59ff-8b74-afe2b98d4a9f | note | – Bedding shall be 50 mm compacted thickness
10bc280b-0ec9-550a-9a75-439f44db4ab8 | note | Raised Concrete Median / Traffic Island on Remnant Pavement (Pavement Type 4):
65de545c-3aec-510c-8e3f-f3b2a4f4d6f7 | note | – Remnant pavement in SGH or minimum 100mm Class 3 Crushed Rock or Crushed Concrete)
ab1c9d0c-0122-50a6-bfb8-013bccedb307 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
bf4983c1-7e97-5cca-a36f-7250b03e8c85 | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
2b6f498e-aabe-5ed0-9c9a-cb8c42c2eab3 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
231cf9f9-7e9e-5669-a959-c5ab960cdde1 | note | Attach: Bedding Material Delivery Dockets
4431ec28-a9da-5e1a-a9b4-06a4968e6ba7 | note | METHOD: Visual, Measure
f00d7a03-dd7d-5ede-888b-ea0f410c1858 | note | FREQUENCY: Each lot
80f626d6-9c62-5760-a913-20576bfc1fef | note | CATEGORY: IP
fc8a1c39-ccb3-53c2-ab2b-64050e898147 | note | RESPONSIBILITY: SE/PE/SPE
be819f7f-0447-5617-8d30-acb2fc2c70b2 | note | VERIFYING DOCUMENTS: This ITP
a2d22608-a460-59e9-b5d3-fe7aa09d8d48 | date | Date Completed:
| checkpoint | 5.4 Compaction Testing
1c802f9b-78a6-5abd-9d4d-7d7da39d1543 | note | REFERENCE: 703.21, 304.08 (a) & (b), 304.11 (a)
be607efb-d61e-5ea1-ab8f-63dd1961acec | note | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
b7573a34-578e-5661-abdc-1635b0418642 | note | ○ Scale of Surface Level Measurement = Scale C
3caf6532-bc85-51ad-9d33-973f8374b5ed | note | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
58ead751-cb6b-5500-a825-4f6760637cb4 | note | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
2f126c6f-5998-5682-9b31-fba438a761cc | note | Attach: Moisture Content Test Results
e327a0ea-c1ad-51c2-b125-9e973317330d | note | Attach: Mean Value of Density Ratio
baec22a0-e1ec-5bd5-9952-f1010a02433d | note | METHOD: Document Review, Visual
d039e5f2-2b7b-5644-b3b4-93414173fc65 | note | FREQUENCY: Where applicable, each lot
26fc2d65-2c5e-5856-b547-5c1c728a7ed2 | note | CATEGORY: IP
b8b9c6ba-8b9b-5d7a-8a4f-4bbcb23824b6 | note | RESPONSIBILITY: SE/PE/SPE
dc6c34b4-439d-5c7a-975e-af5e2fe07dff | note | VERIFYING DOCUMENTS: This ITP
4e90ad11-d24b-5858-8946-df6a1574fefd | date | Date Completed:
| checkpoint | 5.5 Formwork Construction & Placement
aadeb3a9-f38d-53eb-aa5d-1b6bc1c25239 | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.12
9ae80755-80f0-54a3-be7a-708f24444420 | note | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
d5322e46-d6fd-5afd-9ec3-8f044a4443c1 | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
6bf5a9e7-2532-58bc-90e9-646b07d0b831 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
ae8d077b-af6e-5b4b-901f-20c4707cfe11 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
af066d6e-13cd-527e-93c9-86156f84c453 | note | METHOD: Visual, Measure
7b0c79c6-4cd1-5c2c-a504-0fa8413430e4 | note | FREQUENCY: Each lot
9b4a4ec0-bfdb-5e7c-ba64-e055006299b5 | note | CATEGORY: IP
65a706e7-45f6-55cf-98d9-d7effb2e7c63 | note | RESPONSIBILITY: SE/PE/SPE
fea790b1-6686-548b-9f29-f0511bdecf35 | note | VERIFYING DOCUMENTS: This ITP
e4e7fb93-942f-5c5b-a807-ff45d2d7b211 | date | Date Completed:
| checkpoint | 5.6 Construction Joints & Matching Existing Surfaces
82de5737-6b1f-556c-8f01-674d2abc5815 | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.24
fe1adc32-37d6-574d-a5e1-0fbf279d22f2 | note | ○ Relevant Council Standard DrawingsRelevant Council drawings: CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
a7055fc3-f1d0-5d3c-84e6-1b2d694b813b | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
e0143f6b-ba3d-5bc7-a07a-f2d30a8169d6 | note | Consult the relevant Council Standard drawings for the joint detail, these may require:
3ed44e56-4491-53ca-8a2e-2e464ef1463c | note | i. Concrete cutting of a shear-key
fa7e50fb-2dfa-5b47-bdd1-4340c85dac6b | note | ii. Surface roughening
e7d839aa-7aa7-55bf-ab63-f5cd6dd4c4d4 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
2f89ad39-69ed-5a62-a785-44194a0226e9 | note | iv. Cutting a groove for sealant
a29b895d-0fc8-5e6e-82e5-af9ea595642a | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
87ed83f7-38d5-5751-920d-c8d5144ef191 | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
e1049e30-d594-5e0c-8334-f5bb81b1d250 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
1ed1f024-2d21-5ff8-acb7-01fcdf907b89 | note | METHOD: Visual, Measure
8599e3ad-1e47-51c8-83c1-9fbd7d31b205 | note | FREQUENCY: Where applicable, each lot
66b6d219-c378-5257-bde0-4f0c060a7681 | note | CATEGORY: IP
fd7d3294-2017-5aca-a408-4a0249e7c767 | note | RESPONSIBILITY: SE/PE/SPE
0487b1d7-f38c-5187-8bd0-21848a74c1e5 | note | VERIFYING DOCUMENTS: This ITP
fa52de06-3b6e-524e-9b9f-26a9292da47e | date | Date Completed:
| checkpoint | 5.7 Isolation Joints
acaa7cd9-8760-504d-84fd-3d9cb50f4d7f | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.26 (c)
f20dc6f6-d471-5ce8-86f1-7e89e1a200f1 | note | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
1caa3938-9114-502a-9390-01755c60b017 | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
881e9128-dede-5772-bd1d-a18635e07882 | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
f08c67a5-ebe7-5fc4-b9f0-73c190db01da | note | ii. at any location marked on the drawings
c49839b4-e94a-5ab7-bf7b-4cdbdccff781 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
7d08bc8e-f070-5da0-b079-53d09ed9eb0f | note | METHOD: Visual, Measure
88b52edd-6545-54c8-a83a-955f9d05aa4d | note | FREQUENCY: Where applicable, each lot
39afa697-8702-5c18-b8be-07194cf0aa00 | note | CATEGORY: IP
5a9c6dd3-78b7-55d9-a3c5-1dc1cfe05a38 | note | RESPONSIBILITY: SE/PE/SPE
34d846b8-2fac-51bc-ab6f-18d4fc015691 | note | VERIFYING DOCUMENTS: This ITP
40fb8294-4440-5462-9e03-87a72dfc854e | date | Date Completed:
| checkpoint | 5.8 Expansion Joints
66225ecb-5acd-5da2-bd29-2a6592d7a223 | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.26 (a) (ii) & (b) (i)
a8dcaf2b-ab1b-5b79-9bfd-5fa5613ccc55 | note | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
e3a1fa8a-415e-5527-a7c4-4badcdbc7281 | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
b8534d2f-f209-5288-96b0-4a022aaac870 | note | i. on either side of vehicle crossings
499a1af9-8f1b-5a98-af48-126840fe8075 | note | ii. at junctions with existing footpaths and shared use paths
c673b6bf-4d7b-585c-9a40-da16995309aa | note | iii. at junctions with bridges
c9feb0d3-8314-5c06-99d3-7b872eb3a7a6 | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
6b2248a2-1c7b-5222-b0f4-aaea768c6280 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
4d8bf207-d26b-5158-a787-7c220b183d5f | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
c139202f-9ba6-5170-a6a4-8618f116127e | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
1779de7f-dcea-5555-8dbe-cada07fd8763 | note | METHOD: Visual, Measure
070e311b-fc09-538a-a277-b3bf12d8a044 | note | FREQUENCY: Where applicable, each lot
b6fb170e-812b-5ab6-bcaf-b47a18e631d2 | note | CATEGORY: IP
ad22ca89-ed68-5997-b140-2c5470e0b188 | note | RESPONSIBILITY: SE/PE/SPE
519749e1-56d5-5653-9b44-ec8ed64159e3 | note | VERIFYING DOCUMENTS: This ITP
69018f68-9650-5d25-bc2b-c75434ce83c9 | date | Date Completed:
| checkpoint | 5.9 Reinforcement Placement
35e19cee-9d4c-591b-98d2-ef0a974a827c | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232, 703.13
af96dfaa-cb8f-5065-975b-124b4d8e1de1 | note | ○ Relevant Council Standard Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B
77b50c5c-1089-5358-af6f-29d4fed2dce5 | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
4b8a60f1-9f78-5956-8bd4-07e136d808dd | note | Footpaths (Pavement Type 7):
b61ebcdc-0cde-50f7-8693-21c19bede4df | note | – eMESH (Macro Synthetic) Fibres Applied at 5.6kg/m3
29b983b0-8cb0-5b6d-857d-18eee04752bc | note | Industrial Vehicle Crossings (Pavement Type 8)::
dcdb07ab-8058-5615-ad37-ef7855546884 | note | – SL82 Mesh (Centrally Placed)
271ffa39-a9a5-566a-aa57-c6498324fbd3 | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
27dadb88-2d12-50e8-b352-057f06e02bc2 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
b7137be1-9eb8-5879-ad37-e9c7a3b5a4df | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
86f48dc4-37d6-5110-ab61-17f15c92c463 | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
b60eda47-2dad-56d7-8064-9388891a1c5b | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
d19b05e3-a7a0-5f72-86e1-ee3db020a13d | note | METHOD: Measure, Visual
849e53d6-5450-5155-875d-0c89ed6ab3f0 | note | FREQUENCY: Each element
29dfa952-af42-5ce6-b9a0-ebfcae8b117d | note | CATEGORY: IP
36d9c293-6be0-580a-9b83-299ab81f28c6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
22b05c21-05d4-5bcc-8e5a-9c6b79a1121b | note | VERIFYING DOCUMENTS: This ITP
1294f2f1-abd7-532f-a546-8acc70f29c9d | date | Date Completed:
| checkpoint | 5.10 Pre-pour Survey
e372ce33-8923-5edc-879f-825e1aa2dd2e | note | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.15
91aac27b-1cc1-51e2-a411-b8fc826fbf9b | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor. Erected formwork and base layer within the tolerances below:
edf04979-a8ba-5b60-8f44-3d84a38b3ebb | note | ○ Departure from RL = ±10mm
09e6a103-60f2-51ca-80da-7931f715e2df | note | ○ Departure from alignment = ±10mm
b98f08bd-ca9b-5c32-8245-2ce20603fdc3 | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
9ab4ec1e-4e8e-514a-afa0-5d724d1a1f16 | note | ○ Irregularities in alignment = 5mm in 3m
dc2cbbb9-334e-5856-a863-84b589175789 | note | ○ Section dimensions = ±5mm
1c05a738-7bac-59a7-84cb-7880e3193d00 | note | ○ Section dimensions (less than 25mm) = ±3mm
05332485-3bf3-56d2-afbc-3074f52fbde4 | note | ○ Width of pavement = -5mm, +15mm
71e3b615-078f-5c7b-bfc7-e50a7ea0e86c | note | Attach: Survey Report
8f1260bb-c0fe-589f-9a74-aafef140d1d0 | note | METHOD: Measure, Visual
cadae1fc-dc51-56c0-9f80-5ca85944185c | note | FREQUENCY: Each lot
78c041c7-73ab-5178-8576-0cb86915d6a1 | note | CATEGORY: HP*
6fd8da17-ac04-52e2-a200-f2d9d483fc61 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
78e952be-cda1-5330-9217-201f2f990292 | note | VERIFYING DOCUMENTS: This ITP
f795ca23-9c4f-59f5-a1e4-8cbaefd897e8 | date | Date Completed:
| checkpoint | 5.11 Pre-pour Inspection
34b3d9e3-3dd6-5cc9-a1b4-49aa87c170c9 | note | REFERENCE: Section 703.09, Section 703.21 Section 610.17a), b) & c)
161d37ec-ada4-5f15-bb1f-12cecf971a44 | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
cd594241-2ce7-5f95-820a-3414c654851a | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
214f1271-1fae-55c1-a8e5-476e1c003a79 | note | METHOD: Measure, Visual
077b67ff-3137-5be8-aa6c-7081c1124ad5 | note | FREQUENCY: Each lot
ded009dd-73a8-5f46-815e-d1b1fd5cf1c8 | note | CATEGORY: HP*
f59373eb-a856-567b-8f0c-3c4d12290331 | note | RESPONSIBILITY: SE/PE/SPE
a6b1fc1c-0eb2-5c26-a512-f799f788a50c | note | VERIFYING DOCUMENTS: This ITP
e5990b67-729b-5b27-8629-9d5490d3ed23 | date | Date Completed:
| checkpoint | 5.12 Weather Conditions & Evaporation Limits
f6475b6c-5d65-5bf0-879f-a4de9afe72bb | note | REFERENCE: 703.09, 610.17 (a - f) Table 610.171
74fc7209-8811-534c-a773-5e859fe98bc5 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
beb6df1d-c57c-58e4-942d-53ad4afc8aab | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
345bd725-1d62-5b43-871f-868990607146 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
b06337ef-b557-5eab-b28d-913f76788d58 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
2eafdedf-2b7a-5a32-b358-3142f1e4f220 | note | Record: Required information on the Concrete Pour Record.
178325fa-6a8f-5df9-8c95-2dcffc9ee663 | note | METHOD: Measure, Visual
6604d31b-44d3-5fc2-809e-728273772ed4 | note | FREQUENCY: Each lot
dad1d179-4b66-5cd5-b032-3cbe2f5938ae | note | CATEGORY: IP
eb445298-81e0-5682-bf55-076d55be211a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
2aad06ff-7bfa-5e5a-8cd4-8933a5706168 | note | VERIFYING DOCUMENTS: This ITP
fb0eee52-068a-5c6b-84d2-425451fba1f4 | date | Date Completed:
| checkpoint | 5.13 Concrete Testing - Sampling Frequencies, Footpath, Industrial Driveway, Traffic Island
2f8eeced-b63f-5700-acb3-4ba9eba5b82d | note | REFERENCE: 703.11, 610.16 (b) AS 1379-2007 Cluse 6.2
0bac76c8-7ab0-593e-88b6-9e6193ac08ff | note | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
3a24736b-cc5d-538c-bb66-f56a332720bf | note | ○ Correct quantity of cylinders manufactured per sample.
85cc2aa4-e644-5bf7-aca2-bbdaa15cac17 | note | Record: Required information on the Concrete Pour Record.
7e2c32fc-1e97-58b1-b002-6726637624d0 | note | METHOD: Test
2ebb6602-0680-59e3-92a1-019e07e830e3 | note | FREQUENCY: Each lot
66873bcb-9519-5463-a677-9501d2d36a63 | note | CATEGORY: IP
ffcf4563-f462-56f0-8834-0e10a467c46a | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
8df0169d-4ee6-55d0-96aa-67e1c1c67040 | note | VERIFYING DOCUMENTS: This ITP
89669457-23ce-5676-84c9-b0e1202db49a | date | Date Completed:
| checkpoint | 5.14 Concrete Testing - Slump
03cc68be-7d6c-51fc-8bf7-fea518ab6bb3 | note | REFERENCE: 703.11, 610.16 (c)
0cb85eda-d6d2-521d-9f81-fee4fe7ccadc | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
e266a8db-eacc-58be-b262-4ac9c5362583 | note | <60mm = ±10mm
3efa41e9-437d-5c63-9da6-36049ca75128 | note | ≥60mm to ≤80mm = ±15mm
e6f40b30-a775-564f-a760-e0b25706f16d | note | >80mm to ≤110mm = ±20mm
c811701c-a0ec-5dd0-a690-a2513422d0c4 | note | >110mm to ≤150mm = ±30mm
45fa0b88-1c65-5315-83d8-9a894fffb029 | note | >150mm = ±40mm
6f913174-e291-5099-8fe8-ca53adfcc775 | note | Record: Required information on the Concrete Pour Record.
15c1bfcf-ae4c-5d24-b31a-af063ceb8024 | note | METHOD: Test
344302a6-7627-5e6e-9275-90fc3e3868c5 | note | FREQUENCY: Each sample
12581612-74d1-50e7-8295-e0513ef6c5bb | note | CATEGORY: IP
6671bd60-90da-5373-91d2-e383cc51c44b | note | RESPONSIBILITY: Concrete Tester
03eaaaec-bbe6-57c9-a1c8-889a4e5050ea | note | VERIFYING DOCUMENTS: This ITP
53a341cb-f1e9-52cd-a880-258c8872be84 | date | Date Completed:
| checkpoint | 5.15 Placement & Compaction
33dc26a6-0c95-59e3-9217-ccc7cd7a655c | note | REFERENCE: 703.08
9e0338c7-d68f-5ced-bfeb-d383cc58b3c8 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
7516cd2e-c7b5-5f9c-b817-4c726a0ae6df | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
a8e0b1da-55ab-5361-baae-2090929483ca | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
e1e41d1f-8d20-52ec-87f2-0b75b061324d | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
c9ca6130-b7b2-50d5-a226-9e9f2801718b | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
632662b2-70e9-5615-8dc3-ed0d1eec47cc | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
388540f9-8d24-5496-ab85-5acd1ec8a1de | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
ecc11998-9a8d-50a3-a4e8-5e430e819d2e | note | Record: Required information on the Concrete Pour Record.
9fb18074-20b8-591c-bf38-233633f29217 | note | Attach: Concrete Pour Record
477243ae-932e-53ca-af46-9fa92eb4bc74 | note | Attach: Concrete Dockets
05b28115-65e2-52fc-a835-dd116fb33fbb | note | METHOD: Visual
f7fb0cb5-e5f0-568c-b108-5130b3943db9 | note | FREQUENCY: Each load
5ad24efe-31e1-5ca8-955f-b8b47869fe95 | note | CATEGORY: SP
8825fb70-5064-52b2-9696-fbf6449dfde7 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
cc64b45c-c6d1-52e8-a482-54dc98668596 | date | Date Completed:
| checkpoint | 5.16 Surface Finishes
3b404280-a40b-5489-b844-2e9aa5b76e7e | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
3a9d429e-24b4-5808-87f6-42d88eb8ff84 | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.25
280463a3-3b89-57d0-87bc-a282426527c1 | note | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
4c4badba-a492-5242-bd82-17d6cf7b2bf9 | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
ced06453-2aca-55af-8ee4-acd2a813f943 | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
f1d9f35d-497d-5a1e-8dcb-21aee89ae4fc | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
d0bae9e3-1b14-5046-a58a-aa218c7a7856 | note | METHOD: Visual
c9a60337-4f2f-5106-8fb3-ed278d153bb9 | note | FREQUENCY: Each lot
222886b1-870c-5a2a-bd45-682bff260c5e | note | CATEGORY: IP
611691cf-7c08-504f-a715-647f872179df | note | RESPONSIBILITY: Foreman, SE/PE/SPE
599f7bde-01fc-5cdd-9a12-52ca3ac150bd | note | VERIFYING DOCUMENTS: This ITP
a2243563-2c4c-569c-8f65-70c635e9c86e | date | Date Completed:
| checkpoint | 5.17 Crack-control Joints / Weaken Plane Joints
0195d76a-da36-51fb-88d3-3b091a87beda | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
e2dd8529-1a49-571f-88f7-358066eef8ce | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.26 (b) (ii)
d24d5719-135f-5fa2-a464-4e621f93e8c4 | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
a960b2ed-2bd0-5fa0-9460-583249089d8b | note | METHOD: Visual
d1227381-4b8e-54a0-a0e0-7d999d55ca33 | note | FREQUENCY: Where applicable, each lot
8668d251-9b1b-5223-a894-f69f1ffd4a4c | note | CATEGORY: IP
f599f4fa-29a1-50da-8186-964b9dc23f5d | note | RESPONSIBILITY: Foreman, SE/PE/SPE
fe720b4d-2a13-5b67-a4f9-1ea5bd1c81ad | note | VERIFYING DOCUMENTS: This ITP
64a9e453-5e3f-5c6a-a446-97a208f85b98 | date | Date Completed:
| checkpoint | 5.18 Curing
882ecb4b-1635-5cbd-a063-3392f8e24334 | note | REFERENCE: 703.10
bb0c55e9-fbd0-5c55-8ef2-7e3b3ecc86a5 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
7eb4610d-e62c-511b-86b8-5e69e6f746f5 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
f0506576-8eaf-5385-8b43-d0a1f70f74fc | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
d837d132-ff9f-56f1-bd2f-14e45c4c78a5 | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
b7e13689-beb9-5b12-9667-118fe4bb1e2d | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
ef04f531-7ac2-5b37-97b2-57ee8e8e39dd | note | METHOD: Visual
18f65b6d-e168-550c-aaa2-04ec22a62b4e | note | FREQUENCY: Each lot
7c1ab2b1-6b1d-5349-9d24-4336abb05cec | note | CATEGORY: IP
19de72d6-013e-5aea-ad35-0cace25033ea | note | RESPONSIBILITY: Foreman, SE/PE/SPE
cf1e6376-26cb-5fb3-8a58-a29b19826f9c | note | VERIFYING DOCUMENTS: This ITP
91c650bf-b904-5e2d-a0dc-83c748819fbf | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Crack-control Joints / Weaken Plane Joints
a68aa0ac-b5a3-51b9-a9da-a7288b1e640f | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
faeef5fa-43d7-5db8-9345-0b71041d1f32 | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B, 703.26 (b) (ii)
c3477859-daf9-58cb-9c16-708b4ac0bfcc | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
ad839319-1beb-5727-95e1-3f9448e3234b | note | <20°C = within 24 hours of finishing operations
d193052a-a6b3-5583-9924-f84508d89c76 | note | ≥20°C - 35°C = within 4 hours of finishing operations
60cdd52a-7f64-554e-b6f9-bf1dac324bc9 | note | METHOD: Visual
5826da7c-1a6c-5616-a526-74c92a954821 | note | FREQUENCY: Where applicable, each lot
220992d0-46ba-517a-b302-bff71682f0bc | note | CATEGORY: IP
14bba591-6430-56d9-9d4e-55c6aabb098c | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8a74f785-1dc4-5bb1-9971-733008de6d93 | note | VERIFYING DOCUMENTS: This ITP
b54e73e5-9432-5fe1-8468-cb7e791de982 | date | Date Completed:
| checkpoint | 6.2 Protection of Newly Poured Concrete
d8e6ecba-ca80-5f30-b579-222213a9b614 | note | REFERENCE: 703.27
fa00d0bf-a33e-5141-8630-bfb5164a9390 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
c1392798-a49a-582c-a2e1-9cbd10186da0 | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
285c6209-05cf-5177-a6fc-8023d1987c6e | note | METHOD: Visual
d4f542c0-1156-51df-af3b-7ec734d2fd30 | note | FREQUENCY: Where applicable, each lot
4db25502-7fbf-5dd5-bb34-de208f7ea17c | note | CATEGORY: IP
121aa3e4-2940-5390-9ac8-b2ed3ff16c05 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
152e2e7c-7997-5f16-bf22-d7c22ee38048 | note | VERIFYING DOCUMENTS: This ITP
10f37618-d665-51ee-ab5b-8ff32c9a9d93 | date | Date Completed:
| checkpoint | 6.3 Stripping Formwork
487b8993-5cc5-5656-a263-3e3a61f85a5d | note | REFERENCE: 703.12 AS3610 Table C2
e65ecd02-bdb1-5f05-9821-907f8ab8729f | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
e71b3d27-e9e9-565c-be20-409cba057fba | note | i. 2 days for vertical formwork on external surfaces; and
9e57a27d-86c7-5da4-b5a4-da6ab7287dfa | note | ii. 1 day for vertical forms on permanently hidden surfaces
52eadf41-24a2-576a-b0ca-ff7202701971 | note | METHOD: Visual
d5fb040a-5354-5800-af31-5e0767ef520b | note | FREQUENCY: Each lot
c7cb76af-ba44-5841-bc08-d04f22ea644a | note | CATEGORY: IP
98c4372b-0637-5ef4-9e62-5a3ae49a65c2 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
55d7eb1c-55c9-5f42-854f-8aa734c08740 | note | VERIFYING DOCUMENTS: This ITP
1f466dd8-8f4c-58ff-99aa-31602d188705 | date | Date Completed:
| checkpoint | 6.4 Backfilling & Pavement Restoration
4f9876d9-3c7c-520d-b114-a5c20734bdf7 | note | REFERENCE: 703.29
a91b9264-a5a4-5317-ad10-824474be37c0 | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
cdf9ca87-b742-59b0-95ea-c492bb7c150e | note | METHOD: Visual, Measure
4467d8ae-aa15-5b1a-a685-7a8b6f444d2e | note | FREQUENCY: Each lot
a38b90fc-d0d8-517d-aa12-3641d160ca06 | note | CATEGORY: IP
76b2ef3f-f9d7-5a62-9866-bf3836a085ff | note | RESPONSIBILITY: Foreman, SE/PE/SPE
458d740e-9204-5803-bfaf-3d6dde672f8f | note | VERIFYING DOCUMENTS: This ITP
9b506ea7-f3f5-5cd8-9710-1625ecd8fa53 | date | Date Completed:
| checkpoint | 6.5 Surface Inspection - Cracks
6d49261d-0657-5b81-8d1e-841ad8533278 | note | REFERENCE: 703.3
9accbd90-a2de-5067-8714-7aaec9e78215 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
0ecab4a8-8538-59ea-bb47-f84e3c361abd | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
8a7e1752-801f-5a0f-86a7-87d799407704 | note | METHOD: Visual, Measure
6bca73c3-bd71-5320-84c4-1c6ab4d9f019 | note | FREQUENCY: Where applicable, each lot
8c4a4aa3-51f6-5d08-9612-5213d6588fa5 | note | CATEGORY: IP
b73f6b96-c587-595f-99e6-a74a91d22085 | note | RESPONSIBILITY: SE/PE/SPE
04de9326-8b7e-5ce5-abf3-489cea109f7b | note | VERIFYING DOCUMENTS: This ITP
60033343-a573-51ca-a491-a5fa8f206ed6 | date | Date Completed:
| checkpoint | 6.6 Surface Inspection - Surface Finish
e96e7eb5-fa35-5466-bdb7-a6b1a01e53f8 | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
7b5e101f-d5f1-5163-b01f-1b590c69bb53 | note | ○ Relevant Council Drawings CoGD SD 308-F, CoGD SD 304-E, CoGD SD 704-B 703.25, 703.10 (a) AS3610 Clause 3.2
b09c4f4e-3108-581d-beae-3345554f9d67 | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
cc70f582-00c2-5a49-ba0d-c4f4dedbd2cf | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
573b8066-4c4e-5789-a382-eeba19da54a2 | note | Class of finish:
0eda494e-d311-5ee6-a363-07ad2a59ad5f | note | – Permanently hidden surfaces = Class 4
f3880f4e-66b6-5e5c-896c-400de43b7cf0 | note | – All other surfaces = Class 3
18367678-9917-5958-9adb-7d7b9c8f39cc | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
5c8fb5c1-c52e-5ee0-908a-0a9e6bca3ab7 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
154dbaf4-2057-5371-a851-8e547c85b82b | note | METHOD: Visual
bf4b0b50-b9c2-57ee-939a-203eac70650e | note | FREQUENCY: Each lot
29b15251-d73f-5273-be7f-57767cf0986c | note | CATEGORY: IP
0fd52cc4-9c20-5d3f-be5f-4d298da9d715 | note | RESPONSIBILITY: SE/PE/SPE
7c90356c-3dde-583d-9ebc-b7f9909aadba | note | VERIFYING DOCUMENTS: This ITP
a04b5809-6e79-54c2-804a-69461618166a | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
2d42bdc0-7b17-52f0-a229-fef1a843a34d | note | REFERENCE: IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CPT-7231/7232
bda3c81d-1958-5e5a-a570-56ccb2d2dd99 | note | ○ Relevant Council Drawings 703.11 Table 703.111
2fafc145-fd99-51ef-ac4a-474283764c94 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
fcb83308-a792-5303-8c70-797e26fca304 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
12c4ead0-6e74-5c22-ba72-2ec45f8a1790 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
0c4722f2-0a25-538f-878e-2bd1e6f67eed | note | Attach: Compressive Strength Test Results
c16e3d5a-56ba-5fef-8f32-6ceb423c20ce | note | METHOD: Document Review
f333d0e1-09e1-5e77-a187-1113e37c967c | note | FREQUENCY: Each cylinder
dee714bc-1dae-514c-a4be-b0aa160b364a | note | CATEGORY: IP
8c1c6ef6-b24b-5d94-a94a-07b434e9fa07 | note | RESPONSIBILITY: SE/PE/SPE
21b32fca-8eba-5d89-8933-54c5e1fbc898 | note | VERIFYING DOCUMENTS: This ITP
c1510746-e393-5fee-ae0f-f83e9bdb0b34 | date | Date Completed:
| checkpoint | 6.8 As-built Survey
ba18835b-6782-5a83-84c2-a5e7dc9f33c5 | note | REFERENCE: IFC Drawings MRP-BEC-TRANS-000131-091-CRG, 703.15
b8af119f-4998-54f3-95a1-5d6e8923dfe4 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
e06d94e0-1b05-51d6-af2a-9aa28b613bb0 | note | ○ Departure from RL = ±10mm
85bac33e-2633-5f7b-a0d5-3d5daf80ac4d | note | ○ Departure from alignment = ±10mm
ea7bc43c-0e98-5754-b8d9-ed191522a383 | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
a2447aa3-7b10-530c-9804-0f6256aaf52c | note | ○ Irregularities in alignment = 5mm in 3m
6055e5b1-d575-5976-a237-d12525792989 | note | ○ Section dimensions = ±5mm
286a090c-1a6a-5355-abd4-13011a6a957e | note | ○ Section dimensions (less than 25mm) = ±3mm
14b9b6e6-fe87-5dc7-a3f6-b76f95e115ce | note | ○ Width of pavement = -5mm, +15mm
cd6d0576-feb2-545f-869d-089a44daacc1 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
62abe951-1199-52c8-b561-9630fa316249 | note | Attach: Survey As-builts / Survey Report
f073bf9a-c0cb-55c6-ab9a-278f6c12fc51 | note | METHOD: Document Review
65634999-508f-5be5-8f5b-9636cec2db79 | note | FREQUENCY: Each lot
31045f43-b94f-5c52-b3b8-6ac7f001fbf0 | note | CATEGORY: IP
7dc6d0ec-7f3c-5cc6-a278-497cce67e624 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
47534e5b-e4bc-5d18-a399-55bb057916e3 | note | VERIFYING DOCUMENTS: This ITP
bfc98a56-10ea-52fb-9e05-fbd516bc10a2 | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
26fbfc30-51fe-5077-a439-610a238f45a5 | note | REFERENCE: MRPA Quality Management Plan
480a0648-ac1b-5c2a-b9b8-b8c7dea54bb4 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
53c41841-6afc-5a84-b653-f1823486ba90 | note | METHOD: Document Review
8c4075ca-daea-5c03-8d11-0d7b3008ce07 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
51a4141a-6fbb-54e8-b8aa-55ee1cb08b91 | note | CATEGORY: HP*
4950726d-0c8d-5afe-9d44-4d9ffdd91cd3 | note | RESPONSIBILITY: SE/PE/SPE
92b199bc-40e8-5f05-a7e1-43c53f765334 | note | VERIFYING DOCUMENTS: This ITP
4a2c931d-d685-53ef-a3f3-66e4b52a5f4f | date | Date Completed:
| checkpoint | Final Inspection
211ea329-8dd6-5591-ba80-206e853c55f7 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ac80d955-7b75-528a-a09f-03451ebc45fd | textbox | Name:
d7e42e08-e351-5f1d-8750-ba0a7dee0be4 | textbox | Position:
cbab8dc8-7f87-586f-a693-aefc1acdbc10 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-084-CIV-PSDS-Kerb Construction Rev 0 | itp | ITP-084-CIV-PSDS-Kerb Construction |  | 6161f126-b9d0-4442-b6cb-53ddb3c1687f
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7e70ba66-c7fb-5ba2-b35b-fe228e35f490 | note | Document Title: ITP-084-CIV-PSDS-Kerb and Channel
adb9ccfa-4de7-501a-a9c4-85a7f0204fa3 | note | ITP Description: PSDS-Kerb and Channel
95b6e35d-de30-5e71-b006-e077b485ae86 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
551b2692-4a10-5119-a9fc-f51d45b65134 | note | Discipline (e.g. CIV/STR/RAIL): 084-CIV
1a5eba5b-629a-506d-aabe-85b944da90ee | note | Revision Number: 0
7fc51a29-ddcc-5250-a744-bf3f09ca05ff | note | Revision Date: 13/06/2024
112cdfa3-a9fb-5325-bd80-35fbc869a1ab | note | ITP created by: Anthony Pearson
f396ac64-bd81-5d67-9ed2-e2ee2a53836f | note | ITP approved for use by: Victor Mira
359c0d22-91b6-5b9e-8048-638d2810e79c | note | 1.1 Non Dependent
784bcdc8-b92e-5a74-8665-66677f1e22aa | note | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
| section | Preliminary Works - Materials
| checkpoint | 2.2 Mix design
adbd5bb1-2c86-57a4-ad79-dbaeaeb1c5e8 | note | REFERENCE: SD2001, AS1379, Section 703.05, 703.06, 703.07
c08d3491-8e6a-5ec8-a83b-f1e66002224c | note | ACCEPTANCE CRITERIA: Kerb and Channel
71089049-ce7f-5547-a675-941983fb0d0d | note | ○ Concrete used in kerb extrusion machines will not be subject to compressive strength requirements but shall have a minimum cementitious material content in the finished concrete as follows:
76c4f0fa-fc36-539c-9683-a606fb04527a | note | ○ Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
e4ab4ed8-dfa2-57da-b0cb-9839f3cf8b8a | note | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete.
bbf445fe-1197-5bd8-9127-9720f9f15510 | note | ○ Where kerb and channel is placed and compacted with internal vibration between previously placed formwork, concrete shall be:
ae932af2-3136-5b9f-a95e-7848fd0f5d15 | note | ○ Traffic Routes – N32 portland cement–based concrete or 32 MPa geopolymer concrete standard strength grade; and
5284059b-4b43-5ace-9b0d-0cfd7730f385 | note | ○ Local Streets – N25 portland cement–based concrete or 25 MPa geopolymer concrete standard strength grade as specified.
c05004a4-bca7-5795-bd1e-02ccca3c4549 | textbox | TeamBinder Material approval number for the Concrete Mix:
d476947f-9f2f-5e80-bf2b-86c106212a6f | note | METHOD: Verify
f37d407d-13c0-5083-9ca2-6a537227fe24 | note | FREQUENCY: Prior to commencing any activity
f9d7dffb-82d8-5af7-8350-cccc97dfe04b | note | CATEGORY: HP*
f2e3e75a-4e38-591b-8a6a-020cd19fe8ce | note | RESPONSIBILITY: SE
e4d322b5-4cf7-58f5-8cdb-e12f2402701a | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
| checkpoint | 2.3 Bedding Material
f66f8689-e941-5bdc-8669-447ef73f345b | note | REFERENCE: Section 703.21, IFC Drawings
d111385c-4829-5739-a0d0-f9181924375f | note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
858cf1d4-5f6c-5c4c-bff3-bbca4dc6b3e3 | textbox | TeamBinder Material approval number for Bedding:
df4e9077-491d-5ef1-bd3c-a07050312d17 | note | METHOD: Verify
5b020111-e0b5-5c85-be64-e698298065ca | note | FREQUENCY: Prior to commencing any activity
a1ac643c-b4eb-5ee1-a0eb-09fa289bc923 | note | CATEGORY:
ee5da769-a740-5b4b-8575-58b5d32e3fe9 | note | RESPONSIBILITY: SE
6ca3286b-e88f-54ef-86b7-6d481c74626b | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
| checkpoint | 2.4 Curing Compound
c36c02fa-611e-5cf0-809e-69855a8e05e9 | note | REFERENCE: Section 703.10
41bea725-6b61-54d5-8c61-fa0b31906581 | note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
4339f1ef-4312-5aef-8190-ec4196c1f4b4 | textbox | TeamBinder Material approval number for Curing Compound:
c391827e-977e-58f2-9709-614a2882ccdc | note | METHOD: Verify
c93b53e0-ddf5-50f1-a34d-ca7e6f1a4cc0 | note | FREQUENCY: Prior to commencing any activity
1b6331bc-3ed0-5c27-9666-91aca9dc9f0f | note | CATEGORY: HP*
04f90df5-3769-5ee0-acc7-3e4ee27bc288 | note | RESPONSIBILITY: SE
a721e20a-9467-5f10-857b-66f815e6c8b1 | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
| section | Preliminary Works - Documents
| checkpoint | 3.1 Check for correct documentation
07b5940f-b694-55da-86b4-1365c85218cb | note | REFERENCE: Drawing and Drawing Register
25f93eef-9a82-5590-9fc2-68deb5a824b7 | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
3cb82dc2-3f17-540e-86fd-19e10c54ce22 | note | – Using the correct and complete set of drawings
fea657a3-009b-584a-9609-188f65215687 | note | – All drawings are the latest version
df40dd65-803c-554d-a569-41da1738f769 | note | METHOD: Visual inspection
1c645591-42da-57b3-b538-99118152b6ba | note | FREQUENCY: Prior to commencing any activity
f5f19afe-c65e-5ffe-8835-5dccd6ff6d3b | note | CATEGORY: HP*
d6a5e45a-abf2-5280-92b2-9044a65b2738 | note | RESPONSIBILITY: SE/PE
cb1ca8d7-7a1f-5c7c-9c34-e5442b51fc05 | note | VERIFYING DOCUMENTS: ITP Signed
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Setting out
b321b8fb-40a8-523c-aca8-7c01efe4f297 | note | REFERENCE: Section 703.17
c20011f9-b62b-51ea-bb4a-1583aa675547 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
a8ca0321-3100-50c0-ab85-88e7534accda | note | ○ The superintendent will review and confirm set out.
473f5a2b-7db4-5f2e-acb1-7373fe0fc441 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
fe408063-b052-5747-b35d-6f5b66c8afb4 | note | Attach: Lot Map (Marked up drawing with the location of this Lot) and Survey report
a1bb599d-14e9-568f-a023-6536d8743cae | note | METHOD: verify
a41ee887-ddc6-51cb-aa54-daf6db0f0cf5 | note | FREQUENCY: Prior to start
65046915-9328-56be-856a-f21fe2cb19a3 | note | CATEGORY: HP
eed929fe-e3fd-595d-a22f-26d59ab08343 | note | RESPONSIBILITY: Surveyor
6421f306-8dbf-55c0-aeb9-e77862a88e6d | note | VERIFYING DOCUMENTS: ITP signed, Survey Report
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.2 Temporary drainage provisions
ac3a428a-d39b-5554-9769-36ce60574834 | note | REFERENCE: Section 703.18
727b7709-a740-5686-8f33-3c0effd1c77d | note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
c258e980-9a3b-556a-8a97-63662d77c67b | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
aca39e16-6899-50ee-a2d4-1de09afa880b | note | METHOD: Visual inspection
dd65436d-118f-5968-9ef8-a46fcb2cb43a | note | FREQUENCY: If required
1f89c5f7-0e02-5df7-b226-35ab0281c33e | note | CATEGORY: WP
4ba275c3-81d1-5f95-80fe-acb35e9d9370 | note | RESPONSIBILITY: SE
0e887bd0-7e34-5541-9333-3482ee205fd1 | note | VERIFYING DOCUMENTS: ITP signed
| section | Construction / Installation Activities
| checkpoint | 5.1 Bedding
630829a2-05c0-5e04-8415-6394e4290924 | note | REFERENCE: Section 703.21
a545beed-5d38-56ba-a0d9-bfd5fe05773a | note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
527dbbe0-fe37-5b43-b255-00bd06e2a356 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
f1219649-0525-5f20-87cb-462d38fb7f7e | note | METHOD: Visual Measure
574df404-2686-50fa-97c6-30b64b08c87a | note | FREQUENCY: Each lot
37cee3d2-a17c-5227-bcc6-cc99a2d6e4d1 | note | CATEGORY: WP
e52f3ecf-0823-577f-9714-a0629057d4e2 | note | RESPONSIBILITY: SE
9970e4b3-1455-58db-801d-69cb1843871a | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.2 Formwork
331b0149-2ca8-522e-a8e8-bbe5c8f54da8 | note | REFERENCE: Section 703.12, AS3610
f7960750-be2b-566d-9cfd-493b8931b2f5 | note | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
62b2b518-ac8b-5331-b207-1900d434e7e9 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
3aec18b0-d9f9-5746-998b-959191b601e6 | note | METHOD: Visual Inspection
4542b77e-8fab-57d1-951e-48175c5e0d0a | note | FREQUENCY: Each lot
b617a586-15df-537c-ac74-fd511b5876e7 | note | CATEGORY: WP
8c28348e-a7f3-5563-b3c8-077c6186237e | note | RESPONSIBILITY: SE
289c9b2e-05b8-5acb-b2fd-12ce393afd5d | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.3 Pre Pour Check
87847d34-a1ac-5237-b3ac-a6df42d1efd1 | note | REFERENCE: Section 703.09, Section 703.21, Section 610.17a), b) & c)
782978a6-eca2-5231-b644-de67dd6f3fd2 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
51c556b0-b37f-5918-b8eb-dc5409959b10 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
08fe7b49-56a2-52cc-9fe7-3d43db11a01c | note | METHOD: Verify
7083f974-50bb-51f9-89b2-8bf8df5fc447 | note | FREQUENCY: Each lot
94a3e41d-1d19-5cb1-bad3-6c10038a6865 | note | CATEGORY: HP*
5775e0ee-139c-5cec-82da-70550ba718c7 | note | RESPONSIBILITY: SE
979095d5-2f32-5ac8-a96f-e112a65dcd8d | note | VERIFYING DOCUMENTS: ITP signed
ce4442a6-69ec-5fe3-98b9-83f432e5875d | textbox | Ambient temperature |  |  | °C
| checkpoint | 5.4 Concrete placement
de11ab5d-f219-5a48-a858-f8eddeb63215 | note | REFERENCE: Section 703.08, Section 703.23
a38bd323-3fe3-5024-b823-50169244ef9c | note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
edc75b1b-4609-5c0f-9a91-26bb7e278ab5 | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
8f4090e1-7103-559e-b381-f7ab9ad15405 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
1176d4ba-9522-56c8-90d8-6a359094d38c | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
f22dd339-b269-5797-92ee-ca33e10461f1 | note | METHOD: Visual Measure
6e6ac408-8c97-56c1-b1cc-4b5f41b324e4 | note | FREQUENCY: Each lot
7419cd77-ca79-589c-a76b-8f29c2f41435 | note | CATEGORY: IP
41dfce61-c54e-5af3-81a1-995e0c1bd094 | note | RESPONSIBILITY: SE
5325996f-d5e7-59a6-9ac6-3438f31f265b | note | VERIFYING DOCUMENTS: ITP signed
52c36ed2-11dd-5d54-9ce7-b3fb506242d1 | textbox | Concrete Temperature |  |  | °C
| checkpoint | 5.5 Transitions
21cc58f4-c49f-5d81-8d96-485ecb23ff74 | note | REFERENCE: Section 703.24
0572a3c3-8c48-564a-9c56-c2397e4099fb | note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
4ff78105-90cf-54be-a7e1-4b53853847c9 | note | METHOD: Site inspection
8fb0da9a-6ea3-5bab-b799-1a83dc8a4a3e | note | FREQUENCY: Each lot
d2908b6b-a4a5-5e33-8eda-a2fe16bf7062 | note | CATEGORY: IP
4672e519-4147-59f5-bd2f-afd1775c508a | note | RESPONSIBILITY: SE
da2bcf35-14e4-5006-8c4d-b01eb2f53d2a | note | VERIFYING DOCUMENTS: ITP Signed
| checkpoint | 5.6 Surface Finish
059de6ed-f962-5244-ab3e-3872df227fa1 | note | REFERENCE: Section 703.25
e8884c34-e46e-5e14-a1b8-15306b8e10ba | note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
83002e46-9aab-5a35-9ce2-8329f92f658a | note | ○ Renderings shall be applied within 30 minutes of extrusion.
890a95dd-07b0-50ce-9fbc-0fbde62063d7 | note | ○ Concrete to have a neat appearance and uniform colour.
b175800a-9ebd-5eb4-8264-c1d635f63b6b | note | ○ Class 3 finish required for external surfaces.
ae6b1174-22b2-5e28-a8d9-3cf7ec061858 | note | ○ Class 4 finish required for permanently hidden surfaces.
779d532b-4138-58f3-9b7a-72041f2f40c4 | note | METHOD: Visual inspection
94a9f211-1a7f-5e13-908d-8bfaf45f2bd9 | note | FREQUENCY: Each lot
95b5fcac-e59b-56a3-beb9-c7e190c39e86 | note | CATEGORY: IP
1d968baf-760e-54e0-9c0f-fe6a9c1e5b4f | note | RESPONSIBILITY: SE
182578fb-91aa-5139-876b-88f6e8da16dc | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.7 Formwork Stripping
e7944365-13bd-5b6b-90f3-0ce5f74515ac | note | REFERENCE: Section 703.12, AS3610
9b4a8b44-f39f-5fa7-9f11-45a23c6107f3 | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
e98900a6-f73b-54a0-9e38-5f27243bc14a | note | – External faces 2 days
31c6b8c1-d7f3-5bcc-aaa6-6d408fd454b7 | note | – Permanently hidden faces 1 day
e0b9db1b-07ec-5c1a-8635-d466a4b7fb00 | note | METHOD: Visual inspection
addef582-2807-50e1-9aee-797ac9448f5f | note | FREQUENCY: Each lot
4b7963a9-1100-57a3-a602-cb11ab4abf0a | note | CATEGORY: IP
4f8e2550-f84c-5f57-ae8d-654e3cc121f5 | note | RESPONSIBILITY: SE
2a3877c5-2bd8-5161-861c-34624d4b83c8 | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.8 Tolerance
488f87e7-81bd-5e8a-882f-0f84a6e8d919 | note | REFERENCE: Section 703.15
3ec17352-cef1-5906-bdaa-4bc2f7c454b1 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
f50f5259-99b2-5025-af1b-4106e7567383 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
2f73b122-fd48-5c85-867b-2f76dc68e37a | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
2a356e98-7201-5f2f-b626-a69898c56e5d | note | METHOD: verify
5b9170ea-d9f7-56db-9f48-8ccfe4813c06 | note | FREQUENCY: Each lot
cd23caa4-10bb-5e9f-a254-22c33b2200dc | note | CATEGORY: IP
7f748b19-af83-57f1-a03a-c7712dcda85d | note | RESPONSIBILITY: SE/surveyor
d3beef61-4a00-5968-8bd4-055960c689fd | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.9 Curing
ebf00e99-b041-50f3-bb01-99487d5e7dcf | note | REFERENCE: Section 703.10
e1b904ba-6f58-5e19-8f77-8be3a14c033c | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
31f16557-5d49-5271-9232-238229e312c1 | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
b5344a80-7d48-5d01-b80f-f515211f9de2 | note | METHOD: Visual inspection
75a2778d-b709-5682-8f7c-b8b7ffd9f391 | note | FREQUENCY: Each lot
d1672b3d-5ff1-588c-9b05-edcc619a8c66 | note | CATEGORY: IP
754c07d6-c753-5144-aed5-aa0d77bbcd4e | note | RESPONSIBILITY: SE
0b7b4fa4-4905-56ed-92d1-6aaa987dafc9 | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.10 Joints
35528433-ff24-5a7d-83f4-c173d879a8d7 | note | REFERENCE: Section 703.26
0f5093cd-4663-52ff-a399-02d776ac9f6e | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
0566ac5e-8df0-5a1b-b876-493c87fbb63d | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
a48a06d7-ab8e-59cf-be82-80b9f19364b2 | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
2167e497-309a-5903-aeb6-59da46a896d3 | note | METHOD: Verify
302796a8-e526-5476-9596-b8bd74abe64b | note | FREQUENCY: Each joint
bf36e017-1866-53de-be4a-a40b38f942fd | note | CATEGORY: IP
7e4bd63c-d1dc-5b15-b4b6-e3b1b4b92427 | note | RESPONSIBILITY: SE
4ed4df45-87f9-568a-9e09-1c93ce53b4a5 | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.11 Proteciton of Concrete
a6bf28f9-f2d1-5365-817a-32dada72e61b | note | REFERENCE: Section 703.27
f1dcc5e1-5f32-5280-8fe4-0bf1f7d3a021 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
2539c3d7-b6c6-589b-96d7-209769910cd9 | note | METHOD: Visual inspection
5bf992b2-d14a-5c44-b16a-6af07f74120f | note | FREQUENCY: Each lot
4371b3b1-5e9d-59d3-ac0e-060398d2fd96 | note | CATEGORY: IP
e8e1f8c5-c302-5b03-83b6-9fdedfdd1417 | note | RESPONSIBILITY: SE
048ed370-be8e-5258-9444-5cf3fece3631 | note | VERIFYING DOCUMENTS: ITP signed
| section | Post-construction / Post-installation Activities
| checkpoint | 4.11 Backfilling
685c1666-c2f6-5ce1-891e-7d7fae3f0f98 | note | REFERENCE: Vic Road spec 703.29
6a47bc90-4bde-5e2b-b32a-1b8a8d88cbe3 | note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
7436dce2-f8a6-5799-81e5-76c07d285282 | note | METHOD: Verify
677484d0-496b-523f-9354-b77023467b42 | note | FREQUENCY: Each lot
b72e5d26-0920-564c-90de-ab93c5b364cf | note | CATEGORY: IP
7cf3b75d-e1b2-5544-87a6-42af03a9a5e9 | note | RESPONSIBILITY: SE
d332bf23-13d5-5b8c-bab8-36df0a6893e7 | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 4.13 Cracking of Concrete
4d345c8a-6d57-5467-9714-cc03005cc063 | note | REFERENCE: Section 703.30
ffbc0040-72a8-5aff-a8cd-9dec122a5c19 | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
d923c39c-57fc-5931-a382-c1a632f3928c | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
72d57f7f-8ea5-5aab-9b36-f59bb2247fb0 | note | METHOD: Visual inspection
8ae5daa7-39c1-5589-9aca-f04f09ecba41 | note | FREQUENCY: Each lot
c37397d2-7720-583c-827f-5febc7266ad2 | note | CATEGORY: IP
e2832d8a-d9a1-5054-951c-032b00b691d2 | note | RESPONSIBILITY: SE
ad0f9c0a-4c05-59ae-9ddf-22c9be69d9d6 | note | VERIFYING DOCUMENTS: ITP signed
| checkpoint | 5.1 Survey Conformance
e97232f1-45f6-577e-beec-422ba0058300 | note | REFERENCE: Section 703.15
b94fbbb6-f064-51fa-a1ee-5ee7320913eb | note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
65d1b1a9-a314-5b0d-9834-79f99d9b4347 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
4066852b-d13a-5ab9-8b1d-cd5c34be4e86 | note | Attach: Survey Report
c81207e8-66bd-5c14-b2c0-ed272add2ae7 | note | METHOD: Document Review
2e0102f4-1411-52bf-87bc-b8bac2561e30 | note | FREQUENCY: Completion of each lot
22cec1f7-ef50-5d70-a118-51fbf8462b1b | note | CATEGORY: WP
d84f021e-a8f2-57f2-b5c0-4b02da009256 | note | RESPONSIBILITY: PE/Surveyor
a74e3a66-75a6-5412-a10c-8cbf59e85992 | note | VERIFYING DOCUMENTS: As-built survey records
| checkpoint | 5.2 Non-conformance Report (NCR) Closure
dea84317-b117-595b-a6eb-2d1662a57ee5 | note | REFERENCE: MRPA Quality Management Plan
1814376d-a5b1-5d0e-bc3d-5d83464bb608 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
c917839e-eca7-5dcc-bc9a-1244f8bfc52e | note | METHOD: Document Review
9326b18c-badb-58fe-9f4b-94dc2cacb66b | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
cab9fced-7254-5bec-b2ca-dcfc3f61a3b6 | note | CATEGORY: HP*
64daf7cc-3a94-5fd7-9063-3e3a5c00ded5 | note | RESPONSIBILITY: PE/SPE
df1c9629-deb8-5fda-8037-d7e2a53f0d8d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.3 Lot Map
491c50a1-d615-5655-afa3-dfce99c6ae57 | note | REFERENCE: MRPA Lot Management Procedure
252eca54-cacb-5432-858d-20ae7d8adadf | note | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
877f1c86-5dd8-5308-a303-3a64bb050599 | note | Attach: Lot Map
7c822a70-2aa8-54f1-b754-3a49a9869537 | note | METHOD: Document Review
452d9908-8cb5-5248-ad8c-42dd3795dcdf | note | FREQUENCY: For Each Lot
aea98885-c0e3-55a1-93db-603c7e5c1e96 | note | CATEGORY: HP*
f028222e-7687-5e79-bc0c-e2bc80d76b30 | note | RESPONSIBILITY: SE/PE
fdc771d0-f15d-5a66-a3a8-419a3f9b59e8 | note | VERIFYING DOCUMENTS: Lot Map
| checkpoint | Final Inspection
5ecda76c-e1a6-53dd-a08c-1a67974d9312 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
96f2cf91-bc15-5c51-ba91-4eb3cb231f49 | textbox | Name:
950b9e41-cae1-507b-bbb2-0ee4006926e7 | textbox | Position:
8bf4c405-ff10-556c-9559-d780ef6c5c30 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-085-CIV-PSDS-Subsoil Drainage Rev 0 | itp | ITP-085-CIV-PSDS-Subsoil Drainage |  | 69b4ab54-beec-4d51-a2b3-e39260c03c99
| section | Referenced Documentation
| checkpoint | Referenced Documentation
cce032b9-c74e-5a6c-8e5c-f8c18bf91239 | note | Document Title: ITP-085-CIV-PSDS-Subsoil Drainage
7048bed4-a866-52ed-af82-4e3bef5c4ab7 | note | ITP Description: PSDS-Subsoil Drainage
4231b2e1-5953-502d-a3f6-352690ee1944 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
6414af0e-8904-59ef-b549-b07869b88550 | note | Discipline (e.g. CIV/STR/RAIL): 085-CIV
a070b092-0e6d-5633-9840-1087f363a7a7 | note | Revision Number: 0
6bc5fbca-48a0-5984-9d0b-8923f0944543 | note | Revision Date: 13/06/2024
6fec1067-19c0-5ccd-8e76-0bad9a4e0b3a | note | ITP created by: Victor Mira
b6339849-357f-592a-bb7f-9401691a3c45 | note | ITP approved for use by: Victor Mira
0bbec16b-6d7e-52cc-b9ce-3c95e2683863 | note | 1.1 Non Dependent
8b0e9974-e78f-50a9-947b-6c18ae652711 | note | Reference: VicRoads Section 702 (May '19)
| section | Preliminaries-Material
| checkpoint | 2.1 Pipes
07346123-d65e-534d-9e09-28fdcd313654 | note | REFERENCE: IFC Drawiings VR 702.04
2a2239f1-19f6-5a8e-8556-9c94a9633031 | note | ACCEPTANCE CRITERIA: All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
0fa921b8-0fbc-52c2-bf3c-afd1fc3e96d5 | textbox | Reference: Material approval in Teambinder:
85cf22f9-29f6-5f9f-9356-02511dae7e89 | note | METHOD: Verify, Document Review
ae666bf3-1f4a-56dc-8da2-d8e692c82494 | note | FREQUENCY: When applicable
fec384ef-6d3a-5ffb-91e0-a690ba488528 | note | CATEGORY: HP
92b02e38-1c6b-5c7a-a3b3-9facff2577b3 | note | RESPONSIBILITY: PE/Nominated Authority
c12197c0-0b4e-5046-beef-49dd66541cd1 | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Granular material: Filter Sand
aa6d4390-e087-5efc-ac82-9f8a5686cbaf | note | REFERENCE: IFC Drawings VR 702.05
c5ad8732-3a9c-5e31-ac06-0e14c28cb3fd | note | ACCEPTANCE CRITERIA: Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
ed014cc8-2741-57d3-9867-a1c2aba69f4f | textbox | Reference: Material approval in Teambinder:
3af822d9-7b28-5ddd-8931-487011c664a1 | note | METHOD: Verify, Document Review
e97c1ed8-5e6b-5462-b88c-8a673a759bc3 | note | FREQUENCY: When applicable
ccd8f57e-4e14-5256-9068-8c98d979fe22 | note | CATEGORY: HP
6c9bdff5-039c-58c5-83ca-ad95f333641c | note | RESPONSIBILITY: PE/Nominated Authority
8685b1b7-2450-5f7b-bddc-6adee77d366a | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Granular Material: No Fines Concrete
7332cc9c-31b2-5ab8-963c-1a9077a85428 | note | REFERENCE: IFC Drawings VR 702.05 (e)
8d906940-6f9c-537a-b691-3fd72b772662 | note | ACCEPTANCE CRITERIA: No Fines Concrete: Shall comply with 702.05 e)
6e3de969-6777-52e4-8ac5-4fdced8f80dd | textbox | Reference: Material approval in Teambinder:
2f6ff507-b268-50fb-9f4c-83ff1d9cc48d | note | METHOD: Verify, Document Review
73c15ba9-e37b-58d5-9cc2-e19de0ac350d | note | FREQUENCY: When applicable
b989f902-a7d6-50ca-9ef5-d8601db46e13 | note | CATEGORY: HP
58e8f52e-9269-5e64-bc6c-3cd53dff8a63 | note | RESPONSIBILITY: PE/Nominated Authority
7f6d4a80-b53d-57f1-9ced-b1d89ca84932 | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Geo textile
8c377245-1dd8-5bf8-a5d2-1db6d74b51f0 | note | REFERENCE: IFC Drawings VR 702.06
99dd03cb-0087-5b69-8dc1-0b37b60c1580 | note | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with table 702.061
2ce1f1db-49ff-58ec-928c-b8029683673c | textbox | Reference: Material approval in Teambinder:
bde3034d-3f8d-5f8d-81da-8e87d38ff549 | note | METHOD: Verify, Document Review
55934709-9e5f-5a82-a83c-cdc3d9aed400 | note | FREQUENCY: When applicable
1dac0ba7-0e6c-5e8b-8b7b-82c345db818c | note | CATEGORY: HP
5e85435a-170c-542d-9739-67f7459fc1e3 | note | RESPONSIBILITY: PE/Nominated Authority
96ead859-6ce6-596f-9175-4c228624c78f | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Subsurface Drain Pits
7374e0d2-bdfe-5914-9b93-bbb2db54ad05 | note | REFERENCE: IFC Drawings Section 702.04, 702.05 & 702.06
f624ad96-a07f-5166-9172-8bf75e6b674d | note | ACCEPTANCE CRITERIA: Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
69185067-f4b9-53b4-84b1-f5e5b33d57d6 | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
1838221e-c7da-5218-ad9a-ea5f9e823b2d | note | ○ Flushout risers: As per SD 1631
c1d5db4b-626f-5350-8030-6b265e615442 | textbox | Reference: Material approval in Teambinder:
f10aa9b4-0eb0-5a42-b354-9660889333bf | note | METHOD: Verify, Document Review
ddf14887-13ba-59bb-8562-fc9a85065e73 | note | FREQUENCY: When applicable
78184c37-110a-5009-b9bf-3fbba14dfa45 | note | CATEGORY: HP
92b05653-6a0f-5c57-8284-7f7c9472dd4a | note | RESPONSIBILITY: PE/Nominated Authority
e8652b4b-35aa-5201-b088-993794a69d3d | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 3.1 Survey Set Out
e2f10c2f-087d-5b52-92d5-39f0546f1bda | note | REFERENCE: Section 702.03
ce67e194-16be-525a-9974-b62c94172330 | note | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
867c037a-697a-5683-aba4-3e3361a456ec | note | METHOD: Visual inspection
027b0725-61af-5989-96a0-dff359a23f72 | note | FREQUENCY: Each Lot
512a3b11-527c-5365-92c3-7451206598ee | note | CATEGORY: HP*
223f6fa6-6b54-5a50-924a-f1f06f60d2fd | note | RESPONSIBILITY: SE/Site Supervisor
4454dd33-be4e-5adb-ae53-7d709906e622 | note | VERIFYING DOCUMENTS: This ITP
| section | Construction / Installation Activities
| checkpoint | 4.1 Trench Excavation
f97af22d-d25b-5d0c-b368-f1439d70cc32 | note | REFERENCE: IFC Drawings Section 702.08
6fab28c0-5dbe-5e4c-ad02-748ee76183e6 | note | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
6484da18-4b7c-5778-9a42-9c0154149670 | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
65e25faa-3d44-571d-9f05-67eefe898b7e | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
d7f79315-1914-54bc-b6b7-3b6da9ce4003 | note | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
08e2ba5c-83e8-5e39-a7e0-2b3fdbd8435b | note | METHOD: Visual Inspection
0239da19-d5a8-50cc-8056-f5c7d313e726 | note | FREQUENCY: Each lot
6dc070d6-9dff-5ad8-bd67-27875ebb75d3 | note | CATEGORY: IP
d9caa05b-95f0-5896-a881-5c7af6038fd0 | note | RESPONSIBILITY: SE
e9f5c768-9d71-5938-96e4-416d59fd0bd9 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.2 Trench Excavation
4e916350-b52f-5539-ba9b-ec2c6b451b2a | note | REFERENCE: Section 702.08
3e6e1d17-7f87-5d36-9562-00581f3c431a | note | ACCEPTANCE CRITERIA: The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
85319a16-c192-5850-a841-1923cfb3c7da | note | METHOD: Visual Inspection
6c217661-ad20-5e61-8095-80cb274689b4 | note | FREQUENCY: Each lot
dd940c12-e946-51dc-810f-5d8c4d45bbb6 | note | CATEGORY: HP
e22c375b-00e0-5aa6-ab1f-5352f1fc1328 | note | RESPONSIBILITY: SE/Nominated Authority
4bbec629-a9f1-504a-9635-0dde0b3c9fb1 | note | VERIFYING DOCUMENTS: Nominated Authorith sign off ThisLine
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.3 Placement of bedding
a369ecab-fdb8-57fd-bc21-c738ab2cf81b | note | REFERENCE: Section 702.09 c)
783f4054-c549-5d48-8976-b8dab057f0e5 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
02a597bc-7083-56bc-b855-e586b12b469b | note | METHOD: Visual inspection
06be8054-1021-52a5-b0e5-19eef553644f | note | FREQUENCY: Each lot
b34d9881-56ca-509f-9bba-5fb095c1bfaa | note | CATEGORY: IP
5ee27d77-64a5-54d4-9dab-413b8a82e5d2 | note | RESPONSIBILITY: SE/Site Supervisor
634dac83-4f5c-5861-97da-9f8f171cc77d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.4 Traficable Pavements
bb5e94ef-312a-56d3-a1cf-d86e5ddb9552 | note | REFERENCE: IFC Drawings SD 1601, EDCM 201
56362d20-8fa7-5445-87cc-4bb295602302 | note | ACCEPTANCE CRITERIA: Choose pass when applicable
6214dbcf-346a-5ee4-aa01-0c5569f4c31f | note | ○ All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and EDCM 201
3b6830ad-99df-5640-80ba-c114be857391 | note | METHOD: Visual inspection
f6f4df86-00d6-5c91-9cad-82d78b9469c1 | note | FREQUENCY: Each lot
a0154984-e5eb-548f-a69c-f6b15ce5f10a | note | CATEGORY: IP
6b06c29f-75e6-517a-9fa6-f9f28229fcda | note | RESPONSIBILITY: SE/Site Supervisor
0d7450f5-3311-551d-bb2f-927abe36dfc4 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.5 Outside trafficable pavement
9ebb0c49-20bb-5342-9682-256435fc2302 | note | REFERENCE: IFC Drawings SD 1601, EDCM 201
b2d328ee-1980-59e1-bd5c-82ceaa8b11b0 | note | ACCEPTANCE CRITERIA: Choose pass when applicable
c3f0c6e0-f1ac-5b99-9558-dd111944eb76 | note | ○ Pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
56eb93db-99a0-55a5-81d3-7aee835454c8 | note | METHOD: Visual inspection
657c166b-a516-5796-a617-5526f0f1f84b | note | FREQUENCY: Each lot
baf9d268-764d-5bf1-93fa-4677a07502b9 | note | CATEGORY: IP
528243cf-a302-5db1-81cd-f14a8a342429 | note | RESPONSIBILITY: SE/Site Supervisor
3c6db907-9290-5be6-9d72-66bb0ba3a67c | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.6 Pipe and Geotextile Installation (if required)
ed7ecd83-871e-56cf-9a5e-4e1d66f7477b | note | REFERENCE: Section 702.03, 702.09
fa3d4ee8-3191-5572-8821-38705a600f67 | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding.
7af8b7b4-889e-5de0-a3ca-534758279041 | note | ○ Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
0dddbb73-23a3-5ba6-aebd-272445b89e25 | note | METHOD: Visual inspection
d4e9b06d-08e3-5754-9aca-7dc7cd6862c5 | note | FREQUENCY: Each lot
d611b80f-ef36-5e54-8275-e97fe4355e6b | note | CATEGORY: IP
33e498dd-381b-56e0-a458-5cd8f11f380b | note | RESPONSIBILITY: SE/Site Supervisor
faae96b2-38a2-5f2e-b676-a720e4e038e4 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.7 Backfill Installation (Granular Filter Material)
542fda8f-dafa-55ec-aab5-21536feb6df6 | note | REFERENCE: Section 702.09 (g)
8d0576fc-bbf2-5f78-b036-6a42630ea641 | note | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm.
125a58ae-ec56-58b8-9b7f-b648d5772f43 | note | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
d85d9f4e-5f10-550e-92e3-6098d64d7060 | note | METHOD: Visual, Doc. Review
f3cb8f6e-ea75-5b63-98af-a19fb447ef7f | note | FREQUENCY: Each lot
950736e5-4463-5e89-b04c-6796ad4b7b97 | note | CATEGORY: HP
b35375d9-9a04-5792-909a-67434ae5c255 | note | RESPONSIBILITY: SE, Nominated Authority
a0ba2c15-c0b8-5432-9195-1c42f2425a37 | note | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.6 Backfill Installation (No Fines)
3f982e67-b21f-5e1a-bc8d-878dca19f89e | note | REFERENCE: Section 702.09 (g)
0c9f26b4-6a1a-5098-868f-19f2602f0ff4 | note | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
eb8b79ec-9a01-530a-99d1-fe081c0b76ff | note | ATTACH: No Fines Delivery Dockets
f69e63ad-9e14-5a3f-bce3-f6f2d14feaeb | note | METHOD: Visual
67e39d9c-6c0d-5a15-8dc4-ecdcf107da16 | note | FREQUENCY: Each lot
30be6de3-7654-5626-8f8a-041d95a677b5 | note | CATEGORY: HP
91dc5290-f731-5a01-8e30-ce9ee958f66f | note | RESPONSIBILITY: SE, Nominated Authority
45d99e37-f632-5079-88c9-3745e11e3b50 | note | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.7 Install Pits and Flushouts
4b5797a2-f9cc-5fc6-aa7e-6aeea30142f0 | note | REFERENCE: Section 702.10
8685b9ff-8284-5b8f-8ab6-ed9e3452e427 | note | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
1e57e6f4-cd97-589b-885f-b17077911107 | note | METHOD: Visual
8dc8b89e-c110-513d-9276-5a4b2ca0c83a | note | FREQUENCY: Each lot
ccb2b10c-003d-5c8d-b66a-204de84158b4 | note | CATEGORY: WP
df1ab66c-b892-5bc9-afea-ccd0b4940dde | note | RESPONSIBILITY: SE/Site Supervisor
2aa466ed-f8ae-5b6c-ac50-735afb3a2142 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.8 Marker Points
26bcafba-9494-53c3-889a-94ee180b9569 | note | REFERENCE: Section 702.11
8ae3e94e-f1ff-5b15-bf50-51e9cb4ba3b0 | note | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
2d22767c-3ba7-5f3b-93ed-78573545326d | note | METHOD: Visual
a40296e1-2128-571f-913f-93c5e7ffce32 | note | FREQUENCY: Each outlet
d89590aa-4afe-56ef-b3c1-7ce2cb0fcbc9 | note | CATEGORY: IP
673a453d-d6d7-5b1b-bd67-37a7ff289dad | note | RESPONSIBILITY: SE/Site Supervisor
8154fae0-16f8-5cab-9c14-2d35542bc956 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.9 Flushing
46a13d7b-c4bb-5958-ad21-2b1d10f79fd0 | note | REFERENCE: Section 702.09 (h)
8e9f40b3-d99d-50e8-9ce0-7bfa5cfe431e | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
48b041bf-94f5-5e76-8237-cca2101d0404 | note | METHOD: Record Review
31bf9225-c08a-53c2-80f9-7980e46d5e90 | note | FREQUENCY: Each lot
2216e84a-099b-5efe-82ff-bc77d4d1f233 | note | CATEGORY: HP
b76f7c3e-2626-5527-97e3-41d4848e763e | note | RESPONSIBILITY: SE, Nominated Authority
51244f34-c311-5107-afb9-3b16de3ad910 | note | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.10 CCTV
9873ee84-3b7e-5109-81e0-7022634d2c7e | note | REFERENCE: Section 702.09 (g)
5074211a-b88a-50ec-a3d4-0b969f742b79 | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
d6ed5729-b3eb-5b6c-9b80-b44ca0024863 | note | METHOD: Record Review
8b2842df-a14c-5e67-b42f-c82a156b2145 | note | FREQUENCY: Each lot
92953274-75f2-58bd-b80d-dca5279430aa | note | CATEGORY: HP
db35c939-cd04-5009-a0d8-3e73bd2e97c0 | note | RESPONSIBILITY: SE, Nominated Authority
5e3e58fb-5149-59cf-af75-c5dcbf149178 | note | VERIFYING DOCUMENTS: Nominated Authorith sign off This Line
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Post-construction / Post-installation Activities
| checkpoint | 5.1 As Built Information
bd0135a7-fe0f-5ca5-8f7a-9fc9b1538283 | note | REFERENCE: Section 702.03
868ae837-2769-54d8-8007-d570530d714e | note | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
36657acb-0fa2-5134-b24f-ff83ab813d79 | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
81cffae5-cc24-5ba5-9ffe-5c4dcfe6c552 | note | METHOD: Document Review
b2eafb12-ca24-56c5-848c-b5b9cc163e00 | note | FREQUENCY: Each lot
318f28cb-3ede-5295-9689-3fc7575437fb | note | CATEGORY: IP
8343bc9e-7100-5fbd-a57f-d6b340092117 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
90f21f30-937c-5673-8df7-9c2c990595cc | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
| checkpoint | Final Inspection
4b2518aa-acd8-5ac9-b229-15f1b53ff1cf | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e36e9ce7-49a6-55cd-a9f7-f34e588faa60 | textbox | Name:
d33cbee1-9870-50f8-a7b8-bb601caa3b4d | textbox | Position:
6f36a570-0c4b-52a8-b2bd-1be5fe2d773b | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-087-CIV-PSDS-Type A Fill-Road Rev 0 | itp | ITP-087-CIV-PSDS-Type A Fill-Road |  | 0f81a8e1-cfbd-4940-b1bf-bd7943c0759e
| section | Referenced Documentation
| checkpoint | Referenced Documentation
d8c503cc-839b-544a-a8df-faa1b287df0d | note | Document Title: ITP-087-CIV-PSDS-Type A Fill-Road
3d2bef9a-7313-5136-b025-a84d65f35379 | note | ITP Description: PSDS-Type A Fill-Road
0df140b5-db5d-507d-8e30-f8361ee76c24 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
01295a75-323e-5a66-9618-61c5b26fb24a | note | Discipline (e.g. CIV/STR/RAIL): 087-CIV
04affd15-e2fb-5f15-8e71-885dc0366f2c | note | Revision Number: 0
1e82c968-39c2-51ee-9771-ce070e651e85 | note | Revision Date: 21/12/2023
a967ba78-99e8-5405-b43a-f17eea504c15 | note | ITP created by: Victor Mira
0b1c9520-355a-5fcb-83a6-cdab517bd5e4 | note | ITP approved for use by: Victor Mira
79f80e26-a0a8-507d-88e0-6fadf601a6a6 | note | 1.1 Non Dependent
2bebb49b-79a4-5317-8e22-118aed780f04 | note | Reference: IFC Drawings
b34f7f31-a5c6-5918-8b4c-753083784d29 | note | VicRoads Standard Section 176 (Sept 2008)
d0c3c679-3a18-5b46-8bd0-eed396e13a2f | note | VicRoads Section
854b458e-2b5f-56a8-aad3-d0669d31d5b3 | note | 204 (Dec 2015)
7c40b2df-4139-5405-8242-653d7094e1f1 | note | Code of Practice RC500.20
47b748b3-876d-5c00-96f9-93e8c9202405 | note | Code of Practice RC500.5
| section | Preliminaries-Materials
| checkpoint | 2.1 Material Conformance
70e21d28-c039-56c0-a0b4-5c37137bf699 | note | REFERENCE: Section 204.04 b) Table 204.041
fce10395-13e6-5e11-b3e7-18201c6806d8 | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
18461f61-fadc-515f-9734-7ffed1e24708 | note | ○ Assigned CBR≥10%
b51baf55-c73f-5a23-9f18-6eb2c597eab5 | note | ○ Swell ≤ 1.5%
97c083c4-9365-5b3c-b623-cc71171714e8 | note | ○ Permeability ≤ 5X10-9 m/s
1a24131b-e922-5cbe-96eb-9f7f4be9a12a | note | Grading:
8d1e1e62-89ef-5e08-8463-9d95d4672e37 | note | ○ 75.0mm 100%
48b4bb9f-318c-59b1-a908-4ae35b28ea0b | note | ○ 4.75mm 40-80%
68653841-982c-5cf5-a01e-1706611ff7e2 | note | ○ 0.075mm 10-40%
26fb8062-17c5-53db-b961-de671332210d | note | Reference: Material approval in Teambinder:
2bf6f867-cbd1-529e-98a8-b7f0231d7619 | note | METHOD: Document Review
e50fc0c7-ca5a-53c2-a500-990e1760d184 | note | FREQUENCY: Once, for each material type
88f1b364-8fb0-50e9-987b-e6da9daff75b | note | CATEGORY: HP
39523a05-60e9-503c-a859-e4d13079bd38 | note | RESPONSIBILITY: SE/Nominated Authority
6dcd4859-336f-5ab3-8f9c-977c76180656 | note | VERIFYING DOCUMENTS: Supplier Material Conformance Certificate
4de70f69-ba89-51b8-92ad-e977130b0d19 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documentations
| checkpoint | 3.1 Pre-Commencement of Fill Works
7d9c38c3-31fa-517d-adf2-207406192fb5 | note | REFERENCE: Section 204.10 (b)
a59162b0-7f91-5559-a1bb-a8ebe0a6a5b7 | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
0acb5e00-5f2d-5354-9fd4-0bc7daedb27b | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
b99027bd-55a8-5be8-9fcb-d7adb34d79f0 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
7e26cae3-931b-5fe5-bba6-406ed808fe60 | note | Reference: Subgrade Preparation Lot Number:
7a1ec4cb-66db-5b9a-aedb-dd7659cb5fe1 | note | METHOD: Visual Inspection
6dca032d-e34b-554f-8407-83d1e6634ca3 | note | FREQUENCY: Prior to commencement of fill works
67d12b29-b36d-5eee-9feb-6e6e5953cca9 | note | CATEGORY: HP
067c0bd1-feb0-5573-8902-17ffbb4a3a43 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set Out
34f92b05-ac40-5354-be83-cbfc21e26fd1 | note | REFERENCE: Design Drawings
18066e2f-555c-5454-9499-c560bfd60b40 | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
0c9c25d9-c3c6-532a-9ec1-fc29af8638ec | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
5d8860d9-cf46-5e14-a9f9-ebdbb53274b2 | note | METHOD: Visual Inspection
aac5f72a-1491-5eed-97b4-5f4fb7c0b714 | note | FREQUENCY: Each lot prior to commencement
6bb98a5e-6657-5287-a06f-5f8505f2cdd5 | note | CATEGORY: HP*
87b9ff9a-c14c-55f8-b950-e7c705e96075 | note | RESPONSIBILITY: PE
748269d0-45fa-57e4-a4e6-cf6d373ccf65 | note | VERIFYING DOCUMENTS: Signed ITP, Lot Map
e2b4482b-4a6b-5ffe-a21d-3fb1bdc4699b | date | Date Completed:
| section | Type A Fill/Verge Activities
| checkpoint | 5.1 Placing of Fill
27801d2f-e829-5b1f-9f70-71ba569adbf8 | note | REFERENCE: Section 204.10
6e25f0c8-3057-5538-8626-24380af842ee | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
43a18ab6-4572-521d-814b-270cec4922db | note | METHOD: Visual
b60cc1c5-62eb-5e16-a8f5-32ae6f82663c | note | FREQUENCY: Each Lot
c0c61884-10df-5817-b211-c3135a219c65 | note | CATEGORY: WP
8cd8fb34-aa88-5ed6-b3f2-0b5274be0bd6 | note | RESPONSIBILITY: SE/Site Supervisor
35478f95-d8fc-553f-b259-40f5ea01c17b | note | VERIFYING DOCUMENTS: Sign ITP
dc072b4f-8681-5c69-8d17-b32dd171eadb | date | Date Completed:
| checkpoint | 5.2 Test Roll
ec8e069c-9b32-5ae0-b0f4-add19eef6122 | note | REFERENCE: Section 173.03, Section 204.12
b7da5c2b-310f-5b27-b31e-e09afe7bf24f | note | ACCEPTANCE CRITERIA: Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
f692e437-1b93-517b-9396-695710c0a6c7 | note | METHOD: Test Roll as per 173.03
37d3b29a-be86-54c0-bce7-5546d1336022 | note | FREQUENCY: Each Lot/Layer
55012926-785e-500a-be3e-58f5cac76a49 | note | CATEGORY: HP
c15e60b6-a596-5cf4-8b4b-c18614213d2c | note | RESPONSIBILITY: SE/Nominated Authority
5ef3cd9d-5661-5a32-a473-0f2c740ec330 | note | VERIFYING DOCUMENTS: Sign ITP
12763c3a-8cd6-518d-b38c-99a471a7de1f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 Compaction Testing
b3364d57-ddb4-53e9-be3d-6e6df9337896 | note | REFERENCE: Table 204.131 Section 204.14 c) Table 204.142
e2db3875-9b97-586b-94ee-23c3ffbd7c47 | note | ACCEPTANCE CRITERIA: Testing as per 204. Ensure testing is tracked and reports available.
1135fd80-47d9-5a95-994c-bc7bca7ce2f1 | note | Standard Compactive Effort
7d865066-31d6-5426-8ef9-4d0efb703f2f | note | ○ For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
3051f2cc-3bc2-5259-b3de-d28ccecaabb9 | note | ○ For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
c1ed7d82-2cef-5659-bbf8-4e8cd63b4764 | note | Compaction and Moisture content
a29e9dfe-f350-5648-a8fe-e33425a42fda | note | ○ Scale A: Characteristic Density Ratio 99%.
aa490aab-cf80-599e-b494-c225b3aa0e18 | note | ○ Scale B: Characteristic Density Ratio 98%.
a38618b9-404b-52da-b5ae-55d3f33cf637 | note | ○ Scale C: Mean Value of Density Ratio: 100%
081eca3f-f62d-5d85-b20c-41cadeb18fed | note | Lot size - the leser of one day's production or 5,000sqm
21e194f8-5c42-5ff3-8762-9ec80c4a2550 | note | ATTACH: COMPACTION TEST RESULTS
2e685b9c-de82-557b-abdf-ebd81fe7bbe7 | note | METHOD: Review Document
de1cd64a-ff83-55ed-90b5-d7c2225a47c5 | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
74ad15d4-ef2a-51a0-b43e-faa31fc8c1ec | note | CATEGORY: IP
fdd0d825-f6e7-5234-ac27-5dc6ed95b939 | note | RESPONSIBILITY: SE/Site Supervisor
09266928-6d82-5606-a17c-739b7aeb5e71 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Compaction Test Report
d150fde9-653d-54e4-9e85-5a03edf7acd4 | date | Date Completed:
| checkpoint | 5.4 Preparation of final surface
8eec47d8-b3a2-5d6e-80a4-3cc161c4ef3c | note | REFERENCE: Section 204.15, 204.03 (g)
7e880842-8e5e-5393-bbbf-bfb275510ca7 | note | ACCEPTANCE CRITERIA: The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
13ea9b41-26dd-5bc7-b3ae-54d16409d328 | note | METHOD: Measure
46628d2b-663b-51d3-81ce-45e365e714d4 | note | FREQUENCY: Top layer
b6673f4a-a8a8-5318-aae3-e455c7122ab5 | note | CATEGORY: IP
be528ef2-f016-5044-9086-73633d0a7cbe | note | VERIFYING DOCUMENTS: Signed ITP
d6d4e38e-ce69-54b4-8b66-cfb6f8fe84fb | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Post Compaction Material Property Testing
0f522fae-c87a-5eb9-b64c-d21f872bb542 | note | REFERENCE: Table 204,041, Table 204.141 Section 204.14 a) or b)
213854c4-bed5-51b4-9b28-771f6c4041a9 | note | ACCEPTANCE CRITERIA: Material Properties (Not Applicable for Scale C):
8ef2d5b2-7e61-5a7e-9c6a-0db1ff573ec4 | note | ○ CBR ≥ 10% and Swell ≤ 1.5%
957f2a43-09c3-547c-81aa-54a106e966ce | note | ○ Max Permeability = 5X10-9 m/s
e18b0092-1e29-542d-9271-f87b764ad43a | note | Grading:
cd36077b-ab85-5a9c-96c9-21250c75a7ee | note | ○ 75.0mm 100%
97e36a1c-f955-5ae2-bb49-0652a50a3285 | note | ○ 4.75mm 40-80%
6f3c7cb9-fc70-5192-9023-78bbe2986771 | note | ○ 0.075mm 10-40%
3d2fc21a-74e5-57ac-8625-e10c2711b500 | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
23be3e5f-bd65-5e9e-8e45-9de5de477cb1 | note | Scale A:
802c9b72-0bc8-597d-bb7f-07faf3617cf2 | note | CBR & Swell
c48c7fd3-90ed-5ab1-b145-ae6f153bc4f3 | note | ○ Initial - 1 Lot Test to determine Assigned CBR and swell
b328e556-de03-57a3-ac99-9da49bdedeed | note | ○ Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
bb1234fe-67f9-5013-885d-056e40065a10 | note | ○ Max Permeability
0aa49c2b-2210-5c0d-bf52-b8bdb5f2278a | note | ○ Initial - 1 test per 2 lots
17de055e-af2e-588e-bab8-7e4d66a816c8 | note | ○ Reduced - 1 test per 4 lots
39ee7e5b-00ed-5bdf-8a62-f1e104f92bad | note | Grading:
91b66d5a-42db-5165-aa8e-3e2c9691d73c | note | ○ Initial - 1 test for each lot tested for compaction
1520c416-f275-58dc-8190-31f72acdf99f | note | ○ Reduced - 1 test for every second lot tested for compaction
bca267ee-501d-5f2d-8290-64b49d7bc7fd | note | ○ Max. PI x%Passing 0.425mm & PI
a746f0f7-7570-5cc6-992a-4d650ad2e6f4 | note | ○ Initial - 1 test per 2 lots
269a7f31-b697-5290-8474-05d27b4cc432 | note | ○ Reduced - 1 test per 4 lots
16a52ca2-7ee7-5f9d-9399-c41d02fc580e | note | Scale B:
997ead02-415b-59bc-8cab-87b0b2f51389 | note | ○ 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
f7e5c1d6-f3e4-5fcf-8a04-03a92c9df28d | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
fc52edab-56de-524a-9736-ccfb8e49d1b7 | note | Attach: Post compaction test results:
f0dc556f-458e-5310-a55a-32426c4c20a9 | note | METHOD: Review Document
997f8ae8-ceda-580d-b0e1-6abb545ba062 | note | FREQUENCY: Refer to Section 204
838c83fa-cc77-5f1a-8a81-79b62a4cac31 | note | CATEGORY: IP
e709013c-f0a1-5fec-b822-0f37d3826413 | note | RESPONSIBILITY: SE/Site Supervisor
ee672198-701b-5ff5-9e31-c6618a6e27dc | note | VERIFYING DOCUMENTS: Sign ITP, Attach Material Property Test Report
9b0dd658-da8f-54de-a92c-2f6980fbba8c | date | Date Completed:
| checkpoint | 6.2 Survey Conformance
4260f1c1-3c07-5e2e-bb5a-71ffa18f0f88 | note | REFERENCE: VicRoads 204.03f,g and h
f6ac3f76-cd60-5d5d-b9e0-4fb323c9e645 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
365a2fc4-acdd-56f0-af59-119079625ac3 | note | Level tolerances Scale A:
8a76ad16-8891-5463-9238-b960841db647 | note | ○ Range x = +5, -15mm
f3aa0dc7-8cae-5382-bd7a-7a2eb193c018 | note | ○ Max S = 12 mm
a34bed6a-23b1-5ae2-9825-78c6ab7ba561 | note | ○ 80 measurements per lot
2fa44353-c35d-54e6-b2ae-e69bed023fe8 | note | Level tolerances Scale B:
efce45fe-b728-5b04-9845-5076be6ae1fd | note | ○ Range x = +5, -25mm
19026b68-f093-5669-859c-f653df8306a7 | note | ○ Max S = 15 mm
407bc8f3-b892-55da-a1a2-c3fd9a430a74 | note | ○ 40 measurements per lot
50aa2ba0-d1e0-5542-a20f-8a348649ad6f | note | Level tolerances Scale C:
95fc868b-7e15-58cd-be22-40273244a061 | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
98b1d2ce-cddc-5e20-817d-498cdd3de4bc | note | METHOD: Document Review
166597c7-8f5e-53f2-b462-e74da4241c13 | note | FREQUENCY: Top of Type A/Verge
dcbba2e6-3215-5f50-b3b1-1476ddac2f58 | note | CATEGORY: IP
6b184051-8baa-5f27-93eb-cdf9b46e7843 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
2b129928-22b7-5b86-84d5-18c7886fb9bc | note | VERIFYING DOCUMENTS: This ITP, Survey Conformance Report
de3f508d-0f71-554a-86d3-19e1f1bff601 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
c7cd8969-1bd3-5b27-b9e4-6f9fe658185b | note | REFERENCE: MRPA Quality Management Plan
e6ea9d0c-acf2-53a0-a087-f6ec0fa8a2e7 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
8a3fae7a-3ed0-52b1-bc40-9bec712fc8a0 | note | METHOD: Document Review
8e5002b1-7b11-5e67-8544-f49b635ea062 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
e8cee319-8daf-5fe8-83c7-301e205bc980 | note | CATEGORY: HP*
6eceb162-f4f0-50c7-af63-270f6fb5021a | note | RESPONSIBILITY: SE/PE/SPE
304c7ea7-3a37-5e0f-8203-245166688d08 | note | VERIFYING DOCUMENTS: This ITP
4d03c647-3e58-50b6-8f94-a7b666e81815 | date | Date Completed:
| checkpoint | Final Inspection
f214a374-e344-5920-93be-2a7007c4815d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
69de427b-1752-55f2-9e9e-453478eb0020 | textbox | Name:
832ab578-ec67-538a-a8dc-b82b1ded6015 | textbox | Position:
1179106e-1f40-5517-a00d-9600cb3a98c3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-090-CIV-PSDS-Site Clearing and Grubbing Rev 0 | itp | ITP-090-CIV-PSDS-Site Clearing and Grubbing |  | 209ca522-e2e2-48e9-8278-8f0e401dc427
| section | Referenced Documentation
| checkpoint | Referenced Documentation
2dc18d0a-e369-56e9-8029-57b43deeda4e | note | Document Title: ITP-090-CIV-PSDS-Site Clearing and Grubbing
580bc6cb-80ec-5970-94cb-b6a86bfaa7b3 | note | ITP Description: PSDS-Site Clearing and Grubbing
f7c9af2a-1d90-5ce9-b578-6953bdaa722e | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
4d091128-4c98-5d39-af3f-d236b9368f15 | note | Discipline (e.g. CIV/STR/RAIL): 090-CIV
e6263147-312e-59c5-882b-ad27f7f5b6aa | note | Revision Number: 0
39174801-064b-55ae-b452-c8565c383c09 | note | Revision Date: 28/02/2023
9d32b3a6-c641-5735-92a6-e2218d0ea475 | note | ITP created by: Jason Lee
bfda0bbe-84b0-5712-947c-80ccc4d7a010 | note | ITP approved for use by: Jon De Castro
429245e9-ca1b-52e9-9198-c9ce8b51197e | note | 1.1 Non Dependent
7c93ddde-066b-57bc-b56e-141d7ad5a8c8 | note | Reference: VicRoads Section 201 (Feb 2023)
4cc87ada-9671-5256-9ab1-9a7748fa9fad | note | 1.2 Non Dependent
6f5a9a10-d2fd-50ad-ac1b-5b24d5f769ef | note | Reference: VicRoads Section 204 (Dec 2015)
0c40eb66-6c59-5a3e-8608-48beda0d5016 | note | 1.3 Non Dependent
ee10b73c-62ba-5007-995c-ab3dbc381e03 | note | Reference: IFC Drawings
| section | Preliminaries - Documentations
| checkpoint | 3.1 Environmental Controls
ea9218c6-1df8-5966-8814-67c2fba59169 | note | REFERENCE: MRPA Environmental Management Plan
0b302b3f-07de-513a-9f80-3da0bb2de65e | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities.
1dab666c-593f-5ce8-80b9-eb03a5f0cc6a | note | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
919725d4-9645-5161-a31e-26b86c4f0337 | note | METHOD: Visual
893aa6b8-5609-53dd-8166-e26590c10013 | note | FREQUENCY: Where applicable, prior to starting Works
44e129e5-686b-594b-bc7d-c285e87f88bb | note | CATEGORY: WP
bf1a3e58-141b-5b25-a0db-92a7f10561e1 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
f24bd01a-cf6f-50b7-9fff-1f2386ac6822 | note | VERIFYING DOCUMENTS: This ITP Signed-off
e3db71fd-4d4a-5905-854d-4f7c0d278440 | date | Date Completed:
| checkpoint | 3.2 Vegetation Removal Permit
f582f725-0e22-5c06-871e-967e877fc0db | note | REFERENCE: MRPA Environmental Management Plan
15724757-7307-5547-9fad-0b3860ea3c5b | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat:
c8aa2627-4510-583f-8a47-8189e5ae0739 | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
27b13eff-98ef-5dee-aed9-2190d80dddc8 | note | A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
640c17b6-a930-57e9-aab5-631886f159b2 | note | ii. fence and sign all sites nominated as No-Go Zones.
c2403a41-7842-54e7-9e22-a398416c29e4 | note | Attach: Vegetation Removal Permit
5dab51c8-a239-55f6-a6c5-2250c9dcee2a | note | Attach: Ecologist's Report
d33e7c57-d4fc-565f-b52f-5151c3012212 | note | METHOD: Document Review, Visual
f2c89450-0ae6-5099-9bd1-e9e0710afa90 | note | FREQUENCY: Where applicable, prior to starting Works
b24280d3-bf0e-5f59-8a48-336c30860626 | note | CATEGORY: HP*
1a7b2582-a7fc-516d-ae77-73d63f50f62d | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
0780cfd2-ae87-537d-aa52-77df85a949de | note | VERIFYING DOCUMENTS: This ITP Signed-off
318be9d8-cf01-5dfa-a135-675c52282de6 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Survey Set-out / Limits of Work
1c77958e-d0f2-5de5-a403-30d7a8f95c5b | note | REFERENCE: IFC Drawings Section 201.03
1137455d-d66a-5561-83dd-6d54d0c61795 | note | ACCEPTANCE CRITERIA: The limits of clearing and grubbing shall be:
0176eae2-401a-551c-ba0f-8917087751fb | note | a. the limits defined on the IFC drawings
3def38aa-ff7a-5844-ad04-80afc6dd52ee | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
fbee31e3-82b0-565e-a569-42c20b01c43f | note | c. no more than the width required for completion of the Work under the Contract.
0509db5d-a07a-5020-a4a2-22ff78a0d83c | note | METHOD: Measure, Visual
0af7eed4-aff0-509b-a403-71d4525f1fc9 | note | FREQUENCY: Once, prior to starting Works
9f54eb71-437a-55ae-83fe-f46db301ed14 | note | CATEGORY: IP
197b5d0d-9688-5f19-acf2-ae959706b383 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
c3f22741-b86a-5bb1-a726-41a6444cdfc7 | note | VERIFYING DOCUMENTS: This ITP Signed-off
c9bc782f-9d74-53bd-b868-bcad0a231568 | date | Date Completed:
| checkpoint | 4.2 Cultural Heritage and Areas of Significance
b124b9eb-0e65-531c-bb35-14ac0f506b78 | note | REFERENCE: MRPA Environmental Management Plan Section 201.10
019b3125-1f78-581b-8140-53af78174986 | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
add7cf5b-c142-58a6-9d1d-43081c3da586 | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
df5ef560-94fb-5011-9f5d-0d44bad70d8a | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
f930f183-5e00-55bf-b935-fb04188fa22a | note | Attach: Cultural Heritage Report
417dd0d6-eed7-5609-a043-7d16879c9b5d | note | METHOD: Document Review, Visual
974d2104-3074-57b7-908b-1b129b57d212 | note | FREQUENCY: Where applicable, prior to starting Works
d051bb65-b7db-5300-b32f-d1e6e95446cd | note | CATEGORY: HP*
101fe6a7-72be-5a7b-ae2e-a863fb3e77a6 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
3280fef2-9e74-558d-bddb-cd25cf5216b8 | note | VERIFYING DOCUMENTS: This ITP Signed-off
07631dbc-6dd7-52d1-a3fd-614589c84327 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Stripping of Topsoil
9f3ad103-909b-5ee5-91bb-ac46964e1185 | note | REFERENCE: IFC Drawings Section 204.05
43dc5218-e34e-5183-ba81-f49b7c138d5a | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
2cb488d5-a582-5f58-97ec-f73a99717e09 | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
df15be73-6823-5623-a272-38d327cbf1fb | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
98dbe752-a124-57c0-902c-a4bca6d97983 | note | METHOD: Visual
a7e847ae-4449-5a58-9b75-830cf27bd9cd | note | FREQUENCY: Each Site
641f2ca6-8af7-5426-aea4-d59ae2717ca5 | note | CATEGORY: IP
34d65b5d-ba7d-5b1d-af97-dd164abb6cdd | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
e45a37b8-f4f0-5e85-99e2-bc9963005010 | note | VERIFYING DOCUMENTS: This ITP Signed-off
e0aecd8a-5796-5752-80cb-36e8a822bae1 | date | Date Completed:
| checkpoint | 5.2 Stockpiling
664f8807-3b65-593e-8ae6-651c776a9cbb | note | REFERENCE: MRPA Environmental Management Plan Section 204.05
c0a5ddea-3c91-5719-9017-6a5c73899ce6 | note | ACCEPTANCE CRITERIA: Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
465b0db2-bc34-5ca7-831d-3504fab51d3f | note | ○ If this clearance is not possible,additional protection shall be provided.
d9f72fde-35a9-5fce-8511-4911719c7807 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
6834a746-e4db-505d-a0e9-532cabf305bd | note | ○ Topsoil shall be re-spread as soon as practicable.
a1c2f0cf-ae4a-546b-8d03-710b095ca289 | note | METHOD: Visual
c99a7c7d-7831-56fc-8b66-c41171f86066 | note | FREQUENCY: Where applicable, each Site
40cee9f3-96d6-52ae-919b-3068e77789d6 | note | CATEGORY: IP
c0858729-3a16-5027-a77b-089f3fa2aa46 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
00b04db8-dfa8-529a-8597-5a3b007d185e | note | VERIFYING DOCUMENTS: This ITP Signed-off
7307bb6e-8a7d-5883-84d1-0fb1e5e9d886 | date | Date Completed:
| checkpoint | 5.3 Abandoned Services
b147027c-3513-507f-8548-6c2868b95d02 | note | REFERENCE: IFC Drawings Excavation Permit Section 201.05
68dca96c-bde1-5e60-80b2-2aaf13386d0e | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
ac30d8c5-e369-5ea4-8421-837b0b58673a | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
74b7ca2d-1a54-5a36-81f4-01b0e84c69c5 | note | ○ Decommissioned services to be disposed of in a suitable manner.
1b3a58d3-e481-5342-b52a-eed95472b1ae | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
5d4072a2-81d4-5627-bc2f-10943e9baa75 | note | METHOD: Visual
80df4e50-db99-5a0d-8db3-1fb203ee1136 | note | FREQUENCY: Where applicable, each Site
31bc7c41-5b8e-58ef-b64b-20c77a6232b3 | note | CATEGORY: IP
98b2e9e6-8e8c-5c8e-b469-74e8e767ae30 | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
1289b4f5-76e4-57a6-b84d-ce272012bce1 | note | VERIFYING DOCUMENTS: This ITP Signed-off
1e3e1fdd-c9ec-5df0-8fb8-bfb1d597d812 | date | Date Completed:
| checkpoint | 5.4 Clearing of Trees and Vegetation
aa4aa639-08fa-53f9-b3ea-1629dde32606 | note | REFERENCE: IFC Drawings Section 201.04
513be186-9ec9-54e5-813a-e5ed456f7c65 | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertaken outside of the specified limits of work.
3c083e60-222f-5f6b-9df1-3375238f0541 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
e12b29a3-3871-5f64-baa4-938d201b8cae | note | METHOD: Visual
f78c842d-546c-5a47-ba12-7c0b722bada7 | note | FREQUENCY: Where applicable, each Site
0086b6b3-fc35-55d4-bfa3-e9c6a184d681 | note | CATEGORY: IP
3e1e86d2-917e-557e-95a5-aceb7f31d54b | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
e6de8a83-29ad-5767-9386-cecda7254c9d | note | VERIFYING DOCUMENTS: This ITP Signed-off
7750fac7-da01-5518-b712-dec6ce6a7eb6 | date | Date Completed:
| checkpoint | 5.5 Grubbing of Vegetation
9ad91a23-9dbf-588f-a549-6982ef7097b0 | note | REFERENCE: IFC Drawings Section 201.05, Section 201.06
c3dc66dd-77e6-59c8-9776-4c22ae9cd9ae | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
541a3b39-04c7-509f-a208-2322d2a997e8 | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
93997030-0db3-5b19-ab19-e0133f7badae | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
07294389-a019-52b7-ad3d-9e5539b2e0e6 | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
f10b1534-1c37-551f-8f5f-d22d10874d6d | note | METHOD: Visual
b27f5c64-222c-5a63-9ee1-6a4b301434be | note | FREQUENCY: Where applicable, each Site
39c2f70b-9a87-51b5-8639-e304bc238334 | note | CATEGORY: IP
eaa5b6ec-ded6-538d-a0c1-c3286ced397b | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
27cbb7ec-8797-5ba0-8a03-3f65bc4f8e46 | note | VERIFYING DOCUMENTS: This ITP Signed-off
009308da-9187-5465-8b6f-a3b0b686ca56 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Disposal of Materials & Vegetation
bc2b59ce-8171-5644-8cdd-5ae91d1d5c82 | note | REFERENCE: Section 201.07
68385a44-42ab-5d82-8d21-3158d326ec3b | note | ACCEPTANCE CRITERIA: Salvagable material to be used wherever possible, the remainder is to be remove from site.
4413e017-bc62-565c-88bb-9198fddbcbe8 | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
004354ee-76ce-575f-a6fa-ac96f31684c4 | note | ○ Tree trunks and large branches shall be removed from the site.
9bac7ff1-4800-593a-8ea6-731aca98510a | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
d46218cb-8ca1-5e7b-ac6d-c29da7106d4b | note | Attach: Delivery Dockets (for Items sent off Site)
99268393-3958-5c33-9b5c-9e4ec75eb457 | note | METHOD: Visual
b2c2467c-19d2-50bc-8b13-5cddf0db2dbd | note | FREQUENCY: Where applicable, each Site
d8655c99-9e8a-5dae-8b0d-f4ffd89ad9a9 | note | CATEGORY: IP
c0581f8b-d32d-5fe8-a6f3-cc0081eff1ba | note | RESPONSIBILITY: Supervisor, SE/PE/SPE
205fbd8e-20b1-50d4-b5dd-e545839c4f44 | note | VERIFYING DOCUMENTS: This ITP Signed-off
9e585868-7bea-5665-830d-e000f3ed0887 | date | Date Completed:
| checkpoint | Final Inspection
474c9552-a0eb-578a-a4f8-f9c69a272b26 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d7135bc4-8fc1-5b80-99c2-61a9a12de519 | textbox | Name:
f4134ac6-9921-5e7b-afd0-74c52884ae4f | textbox | Position:
3eb3294a-1953-55f6-8222-9df25e8e5efb | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-091-CIV-PSDS-Conduit & Pits-MTM Rev 0 | itp | ITP-091-CIV-PSDS-Conduit & Pits-MTM |  | 2967b10f-ba1a-4be6-b9f7-ee41481e6886
| section | Referenced Documentation
| checkpoint | Referenced Documentation
b0aa64dd-79eb-56dd-a21f-d825229e344c | note | Document Title: ITP-091-CIV-PSDS-Conduit & Pits-MTM
69eb7c74-b5a5-52c3-b15a-1632d6c303ba | note | ITP Description: PSDS-Conduit & Pits-MTM
b8282235-496f-5af3-ad9e-4e705950bfb7 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
27c7939a-fe8f-59d8-adf6-d669dcf73fb8 | note | Discipline (e.g. CIV/STR/RAIL): 091-CIV
dab0b4a6-75b0-532d-a63b-b8a02c58d347 | note | Revision Number: 0
60f477fb-1a1f-5216-bf40-a32160b879d1 | note | Revision Date: 13/01/2023
93a6f5ae-2f8a-57c2-b0bc-79f118112e0c | note | ITP created by: Shubham Bajaj (Sammy)
bb6cd3c8-02a0-5d93-b292-c5f3c6a77e3a | note | ITP approved for use by: Jon De Castro
9292a766-a262-5791-bc10-73d470998ae4 | note | 1.1 Non Dependent
23731fcb-f8ee-508b-986b-2810d60b13cc | note | Reference: IFC Drawings
42fad78a-d4b6-54ae-bc78-cab06b81a20e | note | L1-CHE-STD-043 (VRIOGS 012.2.1)
49dea0ea-ad91-5961-a779-36022aa7b0ae | note | L1-CHE-SPE-070
a5535252-a17a-5969-8ba8-559386516a0a | note | Australian Standards
7bfdc0ae-38d6-5e4c-93e3-187b4d5a0965 | note | MRPA Standards
| section | Preliminaries - Materials
| checkpoint | 2.1 Conduits
cb0c21a8-747f-57c1-a227-d81fe8824030 | note | REFERENCE: HV Conduit: AS 2053
f25930cf-ba05-54b6-ad95-ba10e50e8cf1 | note | ○ HV Conduit (boring): AS 4130
ee6f46a3-af15-5730-b39a-3cd053d8b056 | note | ○ Comms Conduit: AS/ACIF S008:2006
6b17d3f1-0880-57ae-8840-cf570656cae4 | note | ○ LV Conduit: AS/NZS 3000 - 2000.
ad96fd2e-a5d8-5c6b-8317-7277b1d93bae | note | ○ L1-CHE-STD-043
1a3a256d-cab8-5b6d-b854-2c58ac92ad21 | note | ○ L1-CHE-SPE-070
3d703d37-2303-5719-a816-70e28afdde2e | note | ACCEPTANCE CRITERIA: LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
4f5fadb2-33d9-54a6-a775-2f4de90f1461 | note | ○ LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS
bdc36042-ccec-54ec-a75e-3b013c54cc43 | note | ○ Inspect materials upon delivery and attached delivery dockets.
cf061803-304a-5a2f-aba8-5da69fe36a6f | note | METHOD: Visual, Document Review
22800182-21cf-5451-a9a8-5d5ceccea388 | note | FREQUENCY: Each Material Type, Each Delivery
9cdbb40a-76d9-5e3e-b880-5cd3995f88fc | note | CATEGORY: IP
41b582f4-f92d-5225-abce-d416796704f4 | note | RESPONSIBILITY: SE/PE
f910cf08-ba99-5961-9201-51abe0de8dec | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
2cf9678a-770c-575b-89bd-5160485afa90 | date | Date Completed:
| checkpoint | 2.2 Pits and Pit Lids
5a2186f6-45c6-50aa-947e-d3fc28f054b5 | note | REFERENCE: IFC Drawings VRIOGS 012.2.1 Section 6.15-16, VRIOGS 012.2.1 Section 6.9, VRIOGS 012.2.1 Cl.6.7 (c), L1-CHE-SPE-070 Cl.10 AS1289
24d45b36-c750-5e1b-ad8d-39365888369f | note | ACCEPTANCE CRITERIA: Pits:
32005582-ef40-5b79-8a66-d3d31a07b5ae | note | ○ Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading
615cc7a0-e057-565e-9382-ae4e9765d48f | note | ○ Pits 900x900mm or greater, multipart pits lids to be used.
3c92cec0-404f-589d-87af-837b956a3499 | note | Pit Lids:
2aaab00a-d39d-5788-ab91-d2b0ded588b4 | note | ○ Pit Covers shall comply with AS3996-2006
b146551c-cd74-5c20-8bc3-0f101c7b7485 | note | ○ Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
796b9297-b966-5c0e-87fd-06e9b4a4450b | note | ○ LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
43bd2b8c-0ab5-5301-85df-3ac131f3c464 | note | ○ Inspect materials upon delivery and attached delivery dockets.
506499a0-a91a-5390-9195-6fd201fd84ef | note | METHOD: Visual, Document Review
9e73bca8-24f7-573e-86d0-cc53c5129f55 | note | FREQUENCY: Each Material Type, Each Delivery
78747d53-d2f3-546f-bb18-eb42f1744baf | note | CATEGORY: IP
34197545-92e0-5486-ae3a-d50010bf931e | note | RESPONSIBILITY: SE/PE
97087625-7a87-5484-923d-7bc512d6ff0b | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
427a43e8-2470-55e8-bf60-f0e4bd466e60 | date | Date Completed:
| checkpoint | 2.3 Warning/Marker Tape
fb9dddf6-3102-5180-881e-3434701a6acd | note | REFERENCE: IFC Drawings AS/NZ 2648.1, TS-SP-013, L1-CHE-STD-043 6.4
f36d6c1a-01a1-54d7-8ceb-cea9dc8f4619 | note | ACCEPTANCE CRITERIA: Warning/Marker Tape:
3fb2cc9a-1ba5-5594-93cb-34daa4d0c6be | note | Above LV:
ef7d5b60-f01b-58a6-ad83-4405bc4556ae | note | ○ 150mm minimum wide orange coloured PVC
4f1fea3c-6b16-5ec6-b145-3ba6a63411e8 | note | ○ ‘DANGER RAILWAY SIGNALLING CONDUITS’
9dcf05e4-f629-5afa-99ce-7b1890db5e4f | note | Above Comms:
72f70429-8363-5e6c-af65-5dde4ec83a7a | note | ○ 75mm minimum wide white coloured PVC
90722e60-7cc5-5da8-a59b-54456b26b682 | note | ○ ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
26b0b155-90d1-5309-9f1c-4714fb2f595f | note | Above HV:
fe88022c-2209-52e4-aa38-8181b2a64dce | note | ○ 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
397379e5-d929-5fdf-968f-455c9fdabd65 | note | ○ Inspect materials upon delivery and attached delivery dockets.
97cdf769-0c9a-5316-b7f1-af758e7d9cbe | note | METHOD: Visual, Document Review
43a5343e-5dfa-58dc-9026-31118e35d102 | note | FREQUENCY: Each Material Type, Each Delivery
eb45f8d7-10b8-5fd6-9f91-52f3a34561c3 | note | CATEGORY: IP
bda9770b-ef3e-5c8d-ab7e-8746bbdea9e8 | note | RESPONSIBILITY: SE/PE
0fe7b806-d205-505e-b0fd-086eb495866f | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
3dee491a-cd42-5a52-8c22-56b92b39a83e | date | Date Completed:
| checkpoint | 2.4 Protection Barriers
d3b00733-d9a1-57d3-a845-8651dbbea107 | note | REFERENCE: IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
77f6b3c0-07eb-5c12-a734-cfaedd11a070 | note | ACCEPTANCE CRITERIA: Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days
a241f246-4abd-5dc3-981a-3fcb0d539835 | note | ○ Inspect materials upon delivery and attached delivery dockets.
f4376df3-5538-581e-b592-3a3bc98a16a3 | note | METHOD: Visual, Document Review
0248775d-67bf-562c-a272-147251cb0e62 | note | FREQUENCY: Each Material Type, Each Delivery
10bbffe8-293a-5b11-a2d8-b33b5dddc7ec | note | CATEGORY: IP
dfc09fdf-e7b9-5abf-8f74-63d89fdf4fdf | note | RESPONSIBILITY: SE/PE
dd13f8d2-7ef1-584b-a6d5-1bfb4ee28674 | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
b4ff9a0a-fc24-58dc-9c3d-31f94e75fb51 | date | Date Completed:
| checkpoint | 2.5 Backfill Material (stabilised sand)
5567bf84-c5d7-5876-9638-9c67b0e61959 | note | REFERENCE: IFC Drawings L1-CHE-STD-043 Section 2 Table 1
ac817eaf-446e-5f24-96f5-211c52f31695 | note | ACCEPTANCE CRITERIA: Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
eb35d5fc-5be6-5376-8da8-9d192f78dcab | note | ○ Inspect backfill material.
d9c7a733-ebc1-5ab1-a055-cc6d47ade521 | note | ○ Attached delivery dockets (if applicable).
61a480b2-8c5f-57b0-ab21-ba91f843734d | note | METHOD: Visual, Document Review
8fc48ec9-1368-5b89-9e39-02a1085ebc0b | note | FREQUENCY: Each Material Type, Each Delivery
c88514e6-8948-5ce8-ae09-4fbecd953792 | note | CATEGORY: IP
9073cb15-bfaf-5478-a0d9-4a8f3d84c2ba | note | RESPONSIBILITY: SE/PE
8b2d342f-9f80-5b7f-943b-841f465f7f04 | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
6d915142-7041-50c6-83c1-6a58f06339dd | date | Date Completed:
| checkpoint | 2.6 Bedding Sand
03e2f977-3463-526f-b471-59ce79c31eaf | note | REFERENCE: IFC Drawings AS2758.1
89bde411-dd2f-53a9-9ac7-4bab43f788fc | note | ACCEPTANCE CRITERIA: Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
a5c7b82b-5022-5447-8fa6-09fb018b6eb4 | note | METHOD: Visual, Document Review
68b126fe-16c4-547f-a6e6-7f21859609eb | note | FREQUENCY: Each Material Type, Each Delivery
e9b684bf-1424-5bce-ae1a-5af0a8a2060c | note | CATEGORY: IP
123809c2-1c18-5c21-9832-71bee486c00f | note | RESPONSIBILITY: SE/PE
b2eaa0a5-deb1-5293-8505-350767f1ee6f | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
cae859a2-4046-5257-8ae7-69fbb5f248f6 | date | Date Completed:
| checkpoint | 2.7 Draw Wires
5fa0724d-f3ec-5db7-841e-6ca8688380ee | note | REFERENCE: TS-SP-013, AS 4142
be284cd0-6e99-56dc-8d68-09b681e42385 | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
fec3307e-dfdc-5cbd-828f-ea84b0713295 | note | METHOD: Document Review
1dde2de4-2e8f-53bf-9a37-8f57757665b7 | note | FREQUENCY: Each Material Type, Each Delivery
0098074e-7a1a-544f-9441-b094a0dec7f3 | note | CATEGORY: IP
7e6d9ad5-89a2-5a15-a32a-8cb0499fc190 | note | RESPONSIBILITY: SE/PE
a3ebcc5c-b9ec-5aed-8390-c298631005e4 | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
6e6df19f-41e4-5a14-84f5-2ef01cf543e2 | date | Date Completed:
| checkpoint | 2.8 Concrete Mix - Trench
3ea0c6a0-2d7f-5e1d-960e-a2714f5802e2 | note | REFERENCE: L1-CHE-STD-043
72bc0bca-c0ce-5ce4-b8b5-4d1728a0f107 | note | ACCEPTANCE CRITERIA: Concrete strength at 28 days shall be not less than 25MPa.
f0f3bf25-a085-552f-b9c7-b0dc187dc412 | note | ○ Chemical admixtures or fly ash shall not be used
2832f9fa-9064-5cea-bb51-e0e2e8a3dd2e | note | METHOD: Document Review
367416e8-def6-5758-b773-8860711f816f | note | FREQUENCY: Each Material Type, Each Delivery
f5aa180a-ffaf-512a-9785-3b43a9012df9 | note | CATEGORY: IP
83012c2b-9421-5d71-9be3-95a53ba39d8b | note | RESPONSIBILITY: SE/PE
0ab4aff9-f872-5c5a-90bb-a29609cfec16 | note | VERIFYING DOCUMENTS: Attach Material Conformnace Certs, Attach delivery dockets
b90b6b3a-2dfa-5706-9db5-5c1896c5deeb | date | Date Completed:
| section | Prelimnaries - Procedures & Documentation
| checkpoint | 3.1 Services
60e9d061-c8ae-56ef-adf7-ae4cba57b184 | note | REFERENCE: Services CAD file
af2573dd-8b9a-539b-9e2e-fbc4fae4502f | note | ACCEPTANCE CRITERIA: All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit).
37744404-4b14-50bf-9c82-bcb09fd0ebfd | note | ○ Survey to mark out existing services.
e5502a9f-28cd-51fb-91c0-d8394ce5597c | note | METHOD: Visual
e1371372-89f7-55d6-8832-de12949efdc0 | note | FREQUENCY: Prior to commencement of works
818dfd37-a908-5c54-83a7-e99c125fe90c | note | CATEGORY: IP
ceb66d53-ba67-56bb-8645-3f4236e5e017 | note | RESPONSIBILITY: SE/Site Supervisor
628dce13-5641-54de-8728-725792e4d0d9 | note | VERIFYING DOCUMENTS: This ITP
e7641f01-6dd8-59f3-a776-65721d08074e | date | Date Completed:
| checkpoint | 3.2 CSR Works Procedure
52e264aa-6bc2-52a6-89c2-eb122738806e | note | REFERENCE: WAP_BRU_201
de6b5ce3-792a-5caa-877b-b44940cff492 | note | ACCEPTANCE CRITERIA: WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
7c40fa3a-02c7-5a44-8feb-4f811637acd3 | note | METHOD: Document Review
128336a4-2ac9-5b35-a051-8c2d65c81bd3 | note | FREQUENCY: Prior to commencement of works
81dd8a2f-c584-5da8-9d9d-9deb244192f2 | note | CATEGORY: HP*
909ccfb2-05c9-5694-9f77-5dbd7f6daa8b | note | RESPONSIBILITY: SE/Site Supervisor
3219e64c-0664-57c1-8f8f-d9beaec423a2 | note | VERIFYING DOCUMENTS: This ITP
fdabcc66-0d7e-552e-9d68-5e9918bd4dd3 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Survey Set-out
39069863-5d34-5f86-a3d4-78e9ee692231 | note | REFERENCE: IFC Drawings
e989f423-8e9c-5214-ad67-142a848ed797 | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
bbec44af-b245-523d-b304-8a48e7aab0a5 | note | METHOD: Measure, Visual
257e720b-5fc2-5b8f-a865-84a8c68b9649 | note | FREQUENCY: Each element
992a1095-6d6c-5bd4-97c2-9ae6b7065b2e | note | CATEGORY: IP
0cb0d1b2-b650-5180-a1d3-ab7274d5d1dc | note | RESPONSIBILITY: Surveyor, SE/Site Supervisor
9d00d5ee-65bc-5a3f-bd6c-48e434131e99 | note | VERIFYING DOCUMENTS: This ITP
17cfb9df-d6b5-5ff7-a8d2-eadf247482d6 | date | Date Completed:
| checkpoint | 4.2 IFC Drawings
0b3277fb-9fe2-503d-80e8-442beaa55cba | note | REFERENCE: IFC Drawings
e9a43790-7809-5dc6-bd94-f2680ce11be7 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
ddaefefc-6825-53a5-bb52-651bdf18fa4f | note | METHOD: Document Review
9f34680b-8b5c-5a70-bf53-a04b1eac7772 | note | FREQUENCY: Prior to commencement of works and at regualr intervals
633d160d-3360-505c-b03d-3ca3937709f1 | note | CATEGORY: IP
d1192729-0fd9-5561-80a2-295def5768f3 | note | RESPONSIBILITY: SE/Site Supervisor
84e029a3-55f1-5e29-8d5a-62c23306dcfe | note | VERIFYING DOCUMENTS: This ITP
3bb03b1c-e894-5a5d-81ee-c49982ae9ee0 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Trench Excavation
530ec0a3-0145-5ebd-904d-296313f93f6c | note | REFERENCE: IFC Drawings L1-CHE-SPE-070 7.3 Table 2, L1-CHE-STD-043, L1-CHE-STD-070 7.1c
e64d84cd-7ddc-592a-bc4b-cb4a09db0ea4 | note | ACCEPTANCE CRITERIA: Trench profile and depth as per IFC drawings.
61d18464-c4c7-533a-9b05-475678ef3b92 | note | ○ Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms
cd805c92-42e1-5599-80fe-116ab3e5e495 | note | ○ The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits.
2693faf2-61db-5dfd-ab7d-964be4e27da1 | note | ○ The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
9c49aa78-215e-5f85-9e1f-8829d9908d4a | note | METHOD: Measure, Visual
4d02b7af-5f5e-5ce5-a4c6-5ac8c4327aa8 | note | FREQUENCY: Each lot
4564eb17-accc-5e17-b571-9c10c3f28c11 | note | CATEGORY: IP
d5b03b7e-1db4-533b-805a-642aa950e962 | note | RESPONSIBILITY: SE/Site Supervisor
fcf7c160-d9a7-54bc-94e8-add23d76f011 | note | VERIFYING DOCUMENTS: This ITP
b39768e3-c2b8-50b8-b56f-cd957b3fad94 | date | Date Completed:
| checkpoint | 5.2 Trench Stability
a11e1530-89b4-5cc2-ab66-748289d3f78e | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings MRPA Standards
7b272644-a1a4-5fc7-8c98-e41cc0d9191a | note | ACCEPTANCE CRITERIA: Trench stability check:
4a5bb328-b2d3-5170-a886-060adff8ecc4 | note | – Shoring,
1fd159f6-59d5-5ad7-a0c0-79d5bef3f998 | note | – benching
c6f89c97-7a69-5e70-b556-bf55d0e6276f | note | – geotech signoff
863f31a3-c58d-5139-87b3-4f7ad4ed84e7 | note | Attached Geotech Report
39f22e15-16c3-5fd9-995f-9d49ea913396 | note | METHOD: Visual, Document Review
5dae644d-9ae4-5a83-a791-657990079bd8 | note | FREQUENCY: Each lot
ce1d51ad-a96a-5ed9-b856-6c981f98c7ea | note | CATEGORY: IP
062b74cc-80da-5490-8b8d-fe6851ea0823 | note | RESPONSIBILITY: SE/Site Supervisor
9d01ccc7-7eaa-5e70-bc08-dd6b75df8c94 | note | VERIFYING DOCUMENTS: This ITP
75058eb1-d7a6-54e2-97e7-17ed71a362c5 | date | Date Completed:
| checkpoint | 5.3 Placement of Bedding Sand for Conduits
f174d590-7860-5c1b-b33a-c9524b3418a9 | note | REFERENCE: IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070
5c1d321a-a94c-5eb8-97f5-dc6755aeb78c | note | ACCEPTANCE CRITERIA: 100mm of bedding sand/crusher dust to be places at the base of trench.
a8c48100-3d5a-5eb5-8230-6e043cd2cd80 | note | METHOD: Measure, Visual
3682af5d-c08d-5aa1-9119-031d55840eb7 | note | FREQUENCY: Each lot
984d3ba8-2971-5513-b0b2-04e5eb921286 | note | CATEGORY: IP
f44328a3-c0eb-592c-8c80-501f2b4e35cb | note | RESPONSIBILITY: SE/Site Supervisor
b222585f-e61a-5e72-8b03-2fb6a40d8281 | note | VERIFYING DOCUMENTS: This ITP
9d2fcdb6-a9c8-5e0b-84a8-1d21a00b2c6d | date | Date Completed:
| checkpoint | 5.4 Conduit Placement & Configuration
79171b55-8a74-5367-8e5c-240f524b04c5 | note | REFERENCE: IFC Drawings L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077
7baad5e5-0a58-5df2-b067-a02e651c9066 | note | ACCEPTANCE CRITERIA: Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
32290e10-7a4c-5d2d-a3cd-a3cf107b2e72 | note | Min Cover
fc0c540c-c0b4-5e26-8f7f-00c6ee361085 | note | – HV: 1000mm
7a47a9c4-99ce-55c0-8bb8-c8c0d898e728 | note | – VicTrack: 650mm
cb65a474-fec4-58fa-a513-a9e010a2633c | note | – Signalling: 800mm
2ff23918-34a3-51be-adac-cc4fec9523ee | note | – LV: 800mm
ca54b1e7-c7f4-5b1c-881b-e2ae4dfcbf0a | note | – Electrolysis: 800mm
25672c16-e8b9-5011-b960-cfe020fce9fa | note | – SCADA: 800mm
9a20de99-7037-5d39-a618-20d498edbb10 | note | – MTM Comms: 600mm
c13ca5a0-c10e-5ae9-9bc3-af12a0c5cacb | note | – 800mm below water coarses (stab sand encasement)
9cb08112-73fd-5494-92ab-d8a81c6aec62 | note | – 1200mm Under VicRoads Roads & top of Rail
c70f653d-bd88-5119-878e-a11064579142 | note | – 900mm below council roads
47ca82b7-218c-596f-b2b3-c5817e2a71fc | note | METHOD: Measure, Visual
eb347824-4d07-5e61-9f13-d219dbed8f8c | note | FREQUENCY: Each lot
b3a6cc8d-5cb0-53f4-8506-375fb2e7bdd3 | note | CATEGORY: IP
284d5926-899d-5dca-a1dc-260dc30c9403 | note | RESPONSIBILITY: SE/Site Supervisor
298d8fd6-5573-5cb3-96fb-3fe6e2bcc7bb | note | VERIFYING DOCUMENTS: This ITP
6ed84b40-9d7e-5686-8bd8-e497bb9f34b3 | date | Date Completed:
| checkpoint | 5.5 Separation of Services
542deb7b-4aec-5eb9-bfc7-eb0c83fced8a | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070, L1-CHE-STD-077 IFC Drawings
6d1dd2bd-108c-505c-a822-86fbc6e1c7b4 | note | ACCEPTANCE CRITERIA: Separation of services
e02d0b21-fee7-5b27-bcb2-fca30e72f999 | note | – HV: Min. seperation distance between HV conduits at least 50mm
237b9a9d-cc62-5ff5-8798-f94d4fcbb695 | note | – VicTrack: fiber 300mm from HV
a0b450dd-ac64-55a7-a8cd-b17aa08d10ac | note | – Utility: 300mm to utilities
83e3fba1-82fe-5131-9618-4d6ab3b117a1 | note | – Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
164fbaf6-9954-5045-a7f9-07ed0cbc39ac | note | METHOD: Measure, Visual
f396906c-3387-5e33-b74b-41dad97cee63 | note | FREQUENCY: Each lot
04273a28-5303-5fc4-9429-ac14118cb544 | note | CATEGORY: IP
2891aa21-d01b-53c0-b3a3-8378943cb637 | note | RESPONSIBILITY: SE/Site Supervisor
6abc363b-f52f-5c3e-a995-74a35e81b86c | note | VERIFYING DOCUMENTS: This ITP
8db40914-40c6-596a-b43c-448e69a2ae68 | date | Date Completed:
| checkpoint | 5.6 Joints
8a1e77a5-a1b4-5d7b-94e1-aeb9627c953a | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
4bfa4627-5858-524c-98b1-db17924fce79 | note | ACCEPTANCE CRITERIA: All conduit joints shall be made by utilising the spigot and socket ends.
8926bbca-66d0-5df1-ae09-6a0b604f5c96 | note | ○ Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
cac6af79-71cc-5f03-bcdb-dd706fe95d5e | note | ○ The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
4e66016d-5083-587a-9d36-df02729fec10 | note | ○ Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
29bb7401-6195-5a26-8671-e249b977bdef | note | METHOD: Visual
7db5fc00-b53d-5560-ad16-80d6cfa3589a | note | FREQUENCY: Each Joint in each trench
756aee3d-918c-5cfe-b27d-7735ae535181 | note | CATEGORY: IP
fcf8f793-ae63-544d-b789-67210a76d5bf | note | RESPONSIBILITY: SE/Site Supervisor
8a2e35d7-8fb1-5d80-af90-5b6320874580 | note | VERIFYING DOCUMENTS: This ITP
fcb16f55-1ae5-504f-8454-6b126d097992 | date | Date Completed:
| checkpoint | 5.7 Conduit Inspection
356b7afe-8337-5a42-9557-639dfa9fbae5 | note | REFERENCE: L1-CHE-STD-070 16
44ab4d23-032a-5767-8e6e-bf58b76041ae | note | ACCEPTANCE CRITERIA: Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
a5eba1cf-bef2-582a-94ca-156f810d9409 | note | METHOD: Visual
c86658da-32fb-5153-891e-b52101e92cb1 | note | FREQUENCY: Each lot
af0f5ab7-a5bf-5ff2-bc8b-bd0aa3084785 | note | CATEGORY: HP*
7691b9f5-5da9-58da-8d87-9ceb2a008871 | note | RESPONSIBILITY: SE / PE MTM / VicTrack Rep.
db9f2740-a1ef-5f47-82aa-6c11d4697a85 | note | VERIFYING DOCUMENTS: This ITP
4cca3388-f724-5a1f-b477-f0134de0326f | date | Date Completed:
| checkpoint | 5.8 Bedding Sand Installation
2c9d5624-baec-5470-ae66-bbd207bfdf1e | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 CL13.1 IFC Drawings
1416be2c-98a2-5e9c-a5ec-fee4d5ec1db6 | note | ACCEPTANCE CRITERIA: Bedding sand/crusher dust extends 50mm past edge of conduits.
8410d5ae-427f-52d2-8141-2859773957b0 | note | ○ Bedding sand/crusher dust extends 100mm above conduits.
46764d1a-8076-51a8-a8db-ae667163c0e4 | note | ○ Attach Delivery Dockets
baf4c657-bdc3-5a87-94c6-96a6a1b8e2c7 | note | METHOD: Visual
0e9d3cba-728f-5554-96b6-fb6dedda4744 | note | FREQUENCY: Each lot
2cb34320-ff40-598c-ad94-a39654f796e8 | note | CATEGORY: IP
336c5438-cf95-5c58-ae42-23e01832378d | note | RESPONSIBILITY: SE/Site Supervisor
783ac3a5-7291-57a5-bce8-5fdb2ad6a479 | note | VERIFYING DOCUMENTS: This ITP
a84dc77d-313f-5dc5-a50f-d35d9706372e | date | Date Completed:
| checkpoint | 5.9 Marker Tape
d8e1bf85-060b-53cf-8b94-d9d29e895618 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-SPE-070 Cl10.3.3
b740b100-d0d8-5e63-96b8-446961b2a429 | note | ACCEPTANCE CRITERIA: Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers.
d7d11d21-2392-5dba-838f-e25a88039ff1 | note | ○ Tape to be one continuous length.
d8eaf905-350e-52a6-94dc-3fca881cd294 | note | ○ VicTrack to inspect the Marker Tape placement..
4df3164e-a4b4-5275-a494-acd361a406dd | note | METHOD: Visual
ef244d7d-96fa-5f6b-87d7-e70620e1b0dd | note | FREQUENCY: Each lot
7d5f05d1-b14d-5991-a9fe-ee735ac1152c | note | CATEGORY: HP*
7ae286ff-f601-5c09-9ddf-05ea32343b7d | note | RESPONSIBILITY: SE/PE, MTM / VicTrack Rep
d78cca81-674d-5a3e-9514-3ef00209366c | note | VERIFYING DOCUMENTS: This ITP
a9f18dc3-113e-5c4b-9898-cc32f035ca10 | date | Date Completed:
| checkpoint | 5.10 Backfill Installation for Conduits
3c0d9281-2739-58e1-8551-6074e22822b2 | note | REFERENCE: IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
f2c4631a-03a9-5004-b149-87fe2f7afa80 | note | ACCEPTANCE CRITERIA: Backfill per trench profile
1dc94e01-2b1c-573f-8e6e-52b5ae57f0e0 | note | ○ 150mm layers of 3% stabe sand
9ec06418-7569-5272-ae3c-193ca05229e0 | note | ○ conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
ebe077fa-7e9e-53b2-a7d5-05a5240c9492 | note | ○ The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
3c981d79-8864-56d3-8eb4-eb656097ff6e | note | ○ Trenches under road pavement - backfill to be same material as the road formation material.
2cdddc8e-fbed-50d1-b37c-a02fe3d0857a | note | ○ Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits.
9950c272-cf2a-5c32-99f3-dd67b525196d | note | ○ When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
d72cbecd-1322-5318-bb3a-adb3017e9610 | note | ○ VicTrack to be notified and witness the first layer of backfilling.
51549555-056c-5b99-816b-4fed237653d7 | note | ○ Attached Delivery Dockets
31b5c386-5191-52df-b1b2-39cae961a836 | note | METHOD: Visual
cc2b7b86-0ed0-53c0-b138-d2121e34aa57 | note | FREQUENCY: Each lot
24137a8d-e0ed-53f1-9b8b-66d0c22259fb | note | CATEGORY: HP*
fd375785-849c-5a30-9895-9953434b325f | note | RESPONSIBILITY: SE/PE, MTM / VicTrack Rep
77d7862c-480d-50d3-a2c8-2e9de127fac2 | note | VERIFYING DOCUMENTS: This ITP
a982f2b7-eeb8-5c7c-8335-b6b6a230f6f0 | date | Date Completed:
| checkpoint | 5.11 Signalling Pits, LV Pits, Electrolysis Pits, SCADA Pits, MTM Comms Pits
5218c639-2055-5840-9753-d3fa35cde5e1 | note | REFERENCE: L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
3d9219be-1669-57a2-9230-de6dfa849cd4 | note | ACCEPTANCE CRITERIA: intervals no greater than 400m (electrolysis 190m)
c38b604e-cd87-577a-ab8e-b7d2bd4638b3 | note | ○ 3m from rail
93ed4ed3-aa0c-5343-92e9-920c9f731272 | note | ○ Access Roads, Class D lids
1ddd36db-1361-5d5c-9f59-d2a5d881c7c1 | note | ○ Footpaths and non traffiacl areas, Class C Lids
c73795aa-0aec-5492-adb5-12df11782d3b | note | METHOD: Visual, Measure
269ccd52-bdcf-5172-abcd-c265566968ee | note | FREQUENCY: Each Pit
0544bf50-24a2-5fed-b627-baf7205c1d68 | note | CATEGORY: IP
e79e61fb-e8d0-5bc1-b86c-1e0a9c77b410 | note | RESPONSIBILITY: SE/Site Supervisor
049f1aa0-8fa2-5945-af21-0ecfe994f974 | note | VERIFYING DOCUMENTS: This ITP
7b2474b0-465a-5d88-a336-267d6202e7e4 | date | Date Completed:
| checkpoint | 5.12 Additional Considerations
d72d5104-9167-59a0-8299-e78a1fb6d9e2 | note | REFERENCE: IFC Drawings
cfd93b2f-1de6-5604-b695-4642c163a6d1 | note | ACCEPTANCE CRITERIA: Access tracks to pits
628b7f05-797e-5573-bc07-f458c8ab31aa | note | ○ Safe access and egress (i.e. lid doesn't open up with workers back to the rail)
9c631ff0-6cc0-541f-a10d-96719afe7167 | note | ○ Hand rail & retaining wall installed as required
eaba00c8-bd7f-5958-b5ad-e6dffe78d0eb | note | METHOD: Visual
61969190-fc79-5095-9b01-fbb2a7a0abb2 | note | FREQUENCY: Each Pit
adf0ad7c-c96f-5e7d-85a2-f3e82d440ace | note | CATEGORY: IP
d965a625-f903-5258-b4d2-14ad62c54238 | note | RESPONSIBILITY: SE/Site Supervisor
930ac6d3-cc47-54e4-b796-8ddd299bc3a2 | note | VERIFYING DOCUMENTS: This ITP
f97c49ec-1847-5257-902f-300cd9a41ef3 | date | Date Completed:
| checkpoint | 5.13 Bedding for Pit Installation
93d01f06-7251-50b0-ab40-81ba61a1a126 | note | REFERENCE: L1-CHE-STD-070 Cl 7.21.u, L1-CHE-STD-043
1f0744ef-44ba-5005-aed9-ac369a71cdfb | note | ACCEPTANCE CRITERIA: 150mm of crushed rock under pit extending 500mm past the pit
f2a37646-077e-531a-b00a-cf9eeb8c9a39 | note | ○ Drainage arrangements shall be provided at the base of each pit.
c2a2a390-c48f-5260-aa29-89e0a850bf72 | note | ○ Attach Delivery Dockets
b11905e2-c4d1-58c8-898d-c1a249c6e1fd | note | METHOD: Visual, Measure
092f9633-61c1-5bd3-810e-01e388f3d9b2 | note | FREQUENCY: Each Pit
646602c6-02ef-588c-a2c5-101c7d4d9804 | note | CATEGORY: IP
6eb43bdd-3e4b-510c-a3af-4b950ecc5415 | note | RESPONSIBILITY: SE/Site Supervisor
fbe0cb30-eb5b-56c8-b112-4a0f28f32140 | note | VERIFYING DOCUMENTS: This ITP
ef10e5f7-b8ae-5f9f-844c-be7d005b6cfb | date | Date Completed:
| checkpoint | 5.14 Pit Orientation
0e6c0c9c-afad-5829-8c34-2563ded7a13a | note | REFERENCE: IFC Drawings
5c709462-bee5-54e8-9cab-fabc5fa7d815 | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
88978cf6-8f19-5f9a-bb23-aeeecbb7ee13 | note | METHOD: Visual
5ac8252c-51eb-5f04-86e1-efc7b6c43557 | note | FREQUENCY: Each Pit
5a2746bf-aa4f-5a0a-b3a2-83235e173e35 | note | CATEGORY: IP
6bb38415-5b34-52aa-ac7b-faeaaeaaacdd | note | RESPONSIBILITY: SE/Site Supervisor
e73b32ee-a781-582b-8771-8150bba62482 | note | VERIFYING DOCUMENTS: This ITP
04585113-9778-523b-aaab-72244099d780 | date | Date Completed:
| checkpoint | 5.15 Pit Installation
2cc78682-36ac-5ba4-bd86-f3cbc83ad1ff | note | REFERENCE: IFC Drawings
c04b0b56-46d2-59fe-b792-4db0046605ed | note | ACCEPTANCE CRITERIA: Pit installed to design specifications
dcabe336-1a03-5abb-b2e8-77fabefa21a2 | note | ○ Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
48e3db38-2b55-50a0-a65e-fe8a335c3e6f | note | METHOD: Visual
01859ce4-96a8-58cc-a840-3b8adbc1065c | note | FREQUENCY: Each Pit
ffc9428d-6396-52a8-87eb-04bb5ba8020b | note | CATEGORY: IP
34bedc70-9c27-51e2-b460-d1026300c9f6 | note | RESPONSIBILITY: SE/Site Supervisor
3998d324-5d28-573f-bf46-4474c036d428 | note | VERIFYING DOCUMENTS: This ITP
b6b4cb41-48dd-5839-be51-10e8c5aca13c | date | Date Completed:
| checkpoint | 5.16 Conduit Entry onto Pits
99ba90a0-7693-588a-89e6-86b88f272288 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
8b78a58a-52e3-5303-8968-69fd7b6a5bbe | note | ACCEPTANCE CRITERIA: Lowest conduit 100mm from the pit chamber floor.
327eed41-3bd5-5fcf-8a6d-6a8dae3b3d65 | note | METHOD: Visual, Measure
2e929625-a2c7-5a8b-bf03-8ea7bfb61948 | note | FREQUENCY: Each Pit
4edb8c49-ce2d-51aa-ab30-0f0209dad09e | note | CATEGORY: IP
3a56e5d4-c2bb-530d-b5ea-bcb2fb1f7023 | note | RESPONSIBILITY: SE/Site Supervisor
b3dce4df-2d22-51b2-8cd0-0d91f7a7856a | note | VERIFYING DOCUMENTS: This ITP
269a6da8-2674-5235-8ba5-f0e4c95bc510 | date | Date Completed:
| checkpoint | 5.17 Tracer Wire
ae5e1d17-d3aa-5a93-b721-e08db6179e51 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
04158a8c-079a-5f42-8111-f6623b6a8ee1 | note | ACCEPTANCE CRITERIA: Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off.
f56178fd-caac-5d36-a318-34dfb44355b7 | note | ○ If tracer wire broken needs to Crimped
b335b81f-a727-56a5-a84f-d84b7d271ac7 | note | METHOD: Visual
e8b6c624-1a2b-5e10-b828-d729cc4e2ffe | note | FREQUENCY: Each VicTrack Pit
ad7558b3-47d7-5935-b52e-5776784bf8ef | note | CATEGORY: HP*
f73159d8-ee9c-5794-bf5c-ba8bf365882d | note | RESPONSIBILITY: SE/PE, MTM / Vic Track Rep
921b9e2b-e036-5d87-8834-0346598fe5a1 | note | VERIFYING DOCUMENTS: This ITP
47a24740-cf3b-5ab1-ba92-7e6460e6ff01 | date | Date Completed:
| checkpoint | 5.18 Spigots and Bell Mouths
8ce5ff8e-32b3-59a9-bcfe-97d0eb2f7f03 | note | REFERENCE: L1-CHE-SPE-070_9.3.4
8c84e389-54fa-532a-bb41-b5891fc32d13 | note | ACCEPTANCE CRITERIA: All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots.
28f53404-bdec-5e67-ad00-0c240abbf431 | note | ○ HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
b8c4f5a0-baa9-5777-82a9-1f10d5936918 | note | METHOD: Visual, Measure
04cee6cd-d876-58e9-948e-c40e451ebf54 | note | FREQUENCY: Each Pit
90678a2a-5d19-52e0-999e-55fa43884945 | note | CATEGORY: IP
494367b5-e5ca-5ff9-a5bb-18c41a5fb10f | note | RESPONSIBILITY: SE/Site Supervisor
1f345f4a-224c-59bb-b19a-dd96c23946c9 | note | VERIFYING DOCUMENTS: This ITP
9ed1bdb5-00fe-5662-9de2-f4d10608561e | date | Date Completed:
| checkpoint | 5.19 Draw Ropes
4260b33b-1ccc-54aa-aa2f-6dc38451739d | note | REFERENCE: VRIOGS 012.2.1
c6b80c47-bea5-5b73-9f76-57887241a8ac | note | ACCEPTANCE CRITERIA: The draw wire shall be continuous for the complete length of the conduit run.
a3bc7c58-81e6-54bf-a453-d32f2d3e8ce4 | note | ○ The draw wire shall have a minimum of 2 metres of slack within every pit.
980bdf9b-efee-569a-b6a5-cecab1d34789 | note | METHOD: Visual
14240aa3-8847-5b07-91be-47e81c86bac6 | note | FREQUENCY: Each Pit
d7caa487-5fc5-5cc8-b504-6a95b03265e4 | note | CATEGORY: IP
fd8d3b65-729c-5332-a248-a2e54ec6428d | note | RESPONSIBILITY: SE/Site Supervisor
3845978c-c4dd-5b08-bde0-ede7454fbce8 | note | VERIFYING DOCUMENTS: This ITP
5ce8b6e4-8d4f-5d11-93d7-707ef82d4ed5 | date | Date Completed:
| checkpoint | 5.20 Backfill and Compaction Testing (if applicable) arouns Pits
99d077c9-1a2f-5058-aaae-0080d6854a19 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
ad391d66-dd63-5ad6-b1d6-ec7e164c34b5 | note | ACCEPTANCE CRITERIA: Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
663231da-fc55-51bc-9e64-729ce0554801 | note | ○ Sand within sand pits to be compacted in layers no more than 250mm layers
e7d11807-1cbc-5959-ad17-12988242b05f | note | ○ Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
755fcb60-3ab7-53c3-8544-099242757f35 | note | ○ Attach Test Report
deec2004-1246-5886-8c20-3d785ee79359 | note | METHOD: Document Review, Visual
764aa750-fd3f-54fb-9c38-98250ed0103e | note | FREQUENCY: Each Pit
b147eb79-fe0f-5632-b070-1dccb0bbfc75 | note | CATEGORY: IP
9f94dbc3-eb65-54b3-81c7-8a3c7238ff2d | note | RESPONSIBILITY: SE/Site Supervisor
8f851a7b-759b-5be7-a9db-00696a8514db | note | VERIFYING DOCUMENTS: This ITP
c92f6202-10a8-5a54-90e3-85ddcda7bd54 | date | Date Completed:
| checkpoint | 5.21 Spare Conduits
69034040-247e-566c-b9d6-69691c9118c3 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
a141062b-5e71-5c05-8121-0f327d40d1c5 | note | ACCEPTANCE CRITERIA: Spare conduits to be sealed and to be included on survey report.
6758ff2c-eb0f-55f8-a9f4-c87c64bc2359 | note | METHOD: Visual
371de5d8-8542-5454-b112-5c76fe48fa64 | note | FREQUENCY: Each Pit
e05cb314-a55a-5484-96b2-b288f2bc1301 | note | CATEGORY: IP
48f983aa-b6c2-5a59-8aba-1a9d4075c32b | note | RESPONSIBILITY: SE/Site Supervisor
8732663a-6493-5fa0-9773-30ee8b49e84b | note | VERIFYING DOCUMENTS: This ITP
d228b58d-3dda-5229-a445-a39b50761dd4 | date | Date Completed:
| checkpoint | 5.22 Pit Labels
11039533-9e05-5cab-a111-3e2c2c232e1b | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
01121451-b87d-575c-bc73-8e06e983e8fc | note | ACCEPTANCE CRITERIA: Pit labels Brass Label (30mm x 150mm)
739023ac-fd41-5e68-b13b-ddf51360fa92 | note | – HV: DANGER - Railway High Voltage
cd912f2d-b3d8-5d84-a5b0-23366d5d5a84 | note | – VicTrack: Victrack Comms
fb5e1bac-4100-5e02-874c-37ed215c0987 | note | – Signalling: Rail Sign Comms
916d2744-33de-5919-9e82-776bd4c7cec6 | note | – LV Pits: Electrical
d982417a-c23d-5256-b931-e9c3259a31e1 | note | – Electrolysis: Electrolysis
42efec68-e96c-575f-a2c6-5a11e20c573c | note | – SCADA: Rail Sign Comms
28ccc759-d1f4-5594-9a50-ecaa433aedcc | note | – MTM Comms: Rail Sign Comms
1cc70578-0041-5010-8272-c36afbcfbfb5 | note | METHOD: Visual
33d82225-9a72-5da1-b945-d64fa7d849e6 | note | FREQUENCY: Each Pit Lid
e2e52c6c-e619-547a-9da9-7664345eb89d | note | CATEGORY: IP
ad4f4132-a2cb-5013-b6d6-d9230a2702ba | note | RESPONSIBILITY: SE/Site Supervisor
212e65d0-bd4f-57a8-9ff7-571d1dfffe57 | note | VERIFYING DOCUMENTS: This ITP
9a32a0e5-b8a2-5f63-b24d-972826244be7 | date | Date Completed:
| checkpoint | 5.23 Pit Numbers
513b16b0-a4e9-5159-848c-31a4461bb470 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
cbaf1e41-1c6e-55a4-b171-71a589d1c0b8 | note | ACCEPTANCE CRITERIA: Pit Number Brass Label (30mm x 150mm)
2090f8df-220e-5dfd-a8ef-5cbca9cf903e | note | – HV (22kVV Feeders): ###HV
9e55c501-ff12-53a5-b097-49795edc9d65 | note | – DC (HV Feeders for OHLE): ###DC
836083e5-89e1-5f9f-9ad9-a41ba5481c89 | note | – VicTrack: ###C
6c7918ec-e7c6-578b-9833-2562fa87ee87 | note | – Signalling LV: ###SL
cf173a66-0dd1-5a0e-8379-325d7a1dcb63 | note | – Signalling HV (2.2 or 3.3kv): ###SH
5fbd8e25-be84-5f64-bf84-0e1d4cd84347 | note | – LV Pits: ###L
0fbedc0d-4a09-5cf3-9341-16205477b159 | note | – Electrolysis: ###E
4a406ad8-13a9-5a0b-8469-42115c59593b | note | – SCADA: ###MS
619d8fdd-6fce-57d9-880a-a0fcbe9581c3 | note | – MTM Comms: ###M
8ca4aeb9-737b-56d6-8931-c17384d2ace2 | note | METHOD: Visual
65e3c8f7-2480-5611-986e-b3f926b88e98 | note | FREQUENCY: Each Pit Lid
9e4493a5-91c6-5ed3-ae6d-7086374eda3d | note | CATEGORY: IP
f4922314-a52b-590f-a965-c721bca899ea | note | RESPONSIBILITY: SE/Site Supervisor
645dbca6-7559-55f0-b20f-f40a8d03ba51 | note | VERIFYING DOCUMENTS: This ITP
37d3c94a-d0b5-5069-8476-4f448f94e3a8 | date | Date Completed:
| checkpoint | 5.24 Cable Route Markers
6ee50af3-a402-531a-a6a0-a1a54996f6e5 | note | REFERENCE: L1-CHE-SPE-070_13.2, STD_E0169 and STD_E0170, AS 4799, STD G0003 and STD G0004
123e2320-5c03-504b-915b-e4adaf40a4f1 | note | ACCEPTANCE CRITERIA: Cable Route Markers
d8dcf363-53a6-55f9-8232-5212b6e10b3f | note | – points entering & leaving the rail corridor
b56ec145-0fa4-58ec-9a54-a60ab3c3903b | note | – no greater than 100m spacing
a770701e-216c-561d-92da-2b4b68ef0ad8 | note | – Change of direction (more than 5 degrees)
d0e5f72d-9289-5d77-9c8d-97e76dd6b1bd | note | – White posts with marker plates for conduit runs
02d02c0c-5e13-559b-aaa9-a4f826dd5d69 | note | METHOD: Visual
78619c73-9406-5080-a0ba-c7aede3a9b59 | note | FREQUENCY: Per Cable Route
280eb45a-b2de-5477-a25e-003b5d62f093 | note | CATEGORY: IP
728a14eb-6f77-52a2-84ed-16ce67c0c5f0 | note | RESPONSIBILITY: SE/Site Supervisor
6c7998df-be64-546d-bec5-fd7f2052c385 | note | VERIFYING DOCUMENTS: This ITP
ceeb4639-0cfc-5bc7-9677-32a8d733addd | date | Date Completed:
| checkpoint | 5.25 Cable Pulling
a7f62723-c0c9-5d6d-9c77-a7e6ffaabee3 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
6c7f6e0b-1eb1-5316-886c-4af899afffe9 | note | ACCEPTANCE CRITERIA: Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
db0cb5d8-a1dc-5c1a-8330-61f4fce3584c | note | METHOD: Visual
cca8bc22-960f-5d35-bd1c-fa85607165f3 | note | FREQUENCY: Per Cable
1839e8bb-08e4-5e51-abd3-d03c1d2fed5c | note | CATEGORY: HP*
92aeba12-b3fb-5392-a102-8ff31b542ad1 | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
9ec21f6b-6aae-546e-8d8c-f3eba15c2a02 | note | VERIFYING DOCUMENTS: This ITP
9b4e6fbe-2b46-5285-bf93-0d55678f533e | date | Date Completed:
| checkpoint | 5.26 Cable Labels
5a774c10-4d54-5ed3-a4f1-e3973dc7914e | note | REFERENCE: L1-CHE-SPE-070 Section 13.3
edaf4e8d-428a-521e-a35f-e7a9f0ffb4cf | note | ACCEPTANCE CRITERIA: All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints.
248a2120-dfad-5e23-8ae4-e86e36112d2b | note | ○ The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
80f1e92a-75f4-580f-881a-7f03ca289273 | note | METHOD: Visual
1a36bc33-e748-5cd2-b97d-4e0824f2e7b6 | note | FREQUENCY: Per Cable
3549893a-9e2d-5ea8-831b-1c582fa1db10 | note | CATEGORY: HP*
9c194d1b-73ee-5bc4-8e51-8bc226950572 | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
8694ad37-fe4f-5ff7-ba39-8a03ae965174 | note | VERIFYING DOCUMENTS: This ITP
3f894f5d-8806-5817-a6e9-8c4276afb655 | date | Date Completed:
| checkpoint | 5.27 Cable Joints
c3b5dfb8-ed9c-5470-91c7-ef4d72554bc9 | note | REFERENCE: L1-CHE-SPE-070, L1-CHE-STD-043, L1-CHE-STD-070 IFC Drawings
fd231ced-4492-5b7f-ada0-157918007ef3 | note | ACCEPTANCE CRITERIA: Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
8f7a433c-2cab-592b-a587-248832620b6a | note | METHOD: Visual
d913e6e3-aff8-508e-b6df-2fe7373c0a90 | note | FREQUENCY: Per Joint / Termination
321cf65a-8684-5b2f-9087-a6e276673650 | note | CATEGORY: HP*
14211237-f0f9-5576-807b-cfc20ae928ab | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
17a68fd4-3ed4-5281-b0e4-f32524154579 | note | VERIFYING DOCUMENTS: This ITP
6a081a85-cafa-5f66-87a5-2038001cfb06 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As-built Survey
66d1e62c-22c9-5d91-b090-c80bffe5468b | note | REFERENCE: IFC Drwings L1-CHE-SPE-070 Section 13.1
e53f70f3-7f65-5815-9c0c-862c146ec936 | note | ACCEPTANCE CRITERIA: Survey report to include but not limited to:
8b2123b9-b87f-5215-90dd-6229e89cd206 | note | – Cable joint locations.
34f9a9e1-2ce6-5446-a9b1-cecf86482566 | note | – Cable pit locations (Corners)
ec80c736-b3d2-563f-aea8-ab068d48bc44 | note | – Pit dimensions & pit lid type
7db45838-94be-5bd9-b01d-f4034e323cae | note | – Under line crossings
e79a90e8-07c0-5eef-8aa2-013db166d5c9 | note | – Under road crossings
0b137d3e-2672-58b0-8686-286a8ca4d2b0 | note | – Changes of direction
bbcc1bb4-c47d-5959-ba96-1a1c2f44a392 | note | – Spare Conduits
9b3ba0cb-9117-5f7d-9e70-5570c13ea47e | note | – Conduits labelled as per trench profile
9b3be22b-9b95-5e3a-9c6f-ba859ea68c7c | note | – every 10m
baa77a76-83bb-5c0c-b036-80631fd25a88 | note | – Other significant points of the cable route
a7a3c834-6d7b-58c6-8cac-4a6fb8f2e438 | note | ○ Attached Survey Report
82e4e4cf-418d-5554-bd71-3e869e3aad8a | note | METHOD: Document Review
f874931a-e08e-570f-824f-274efa23174d | note | FREQUENCY: Each Lot
6eb27fdb-3e57-57df-9cdc-35167d4002d0 | note | CATEGORY: IP
71283e86-5e82-59a3-88bf-0cf2b52c214a | note | RESPONSIBILITY: SE/PE
0aacc399-f0c5-5722-b736-de494f1790f5 | note | VERIFYING DOCUMENTS: This ITP
e25c8f76-a41a-50c5-b377-092ff97d7c62 | date | Date Completed:
| checkpoint | 6.2 Handover Check
e666f92c-4756-55d4-bcbf-3e8351eadd79 | note | REFERENCE: IFC Drawings
2176bcff-76b0-5150-9ddc-f2ee92a132d1 | note | ACCEPTANCE CRITERIA: Handover check completed for Testing and Commisioning.
9f060cae-c41e-58bc-a7a2-436f67e7ee61 | note | ○ Attach MTM/Vic Track Check Sheet (Signed-off)
f2e1063f-26b8-5a6e-8381-43599d7098d7 | note | METHOD: Document Review
a0f2d367-01dc-56eb-a4dd-b861015b8a9b | note | FREQUENCY: Each Lot
7386a227-bb23-5da6-b014-80cdb864f5ef | note | CATEGORY: HP*
4dda6aed-fc9d-5b27-a5eb-953b10d27605 | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
60a55a59-32c4-5c62-a2f6-185931f6619a | note | VERIFYING DOCUMENTS: This ITP
c32c4c13-28a6-50fb-8fe6-79ac85f3272e | date | Date Completed:
| checkpoint | 6.3 Testing and Commissioning
fa4ca134-bcff-5d20-ba2b-fa3a14535347 | note | REFERENCE: IFC Drawings
88196051-8110-5ee9-9dbe-23bc835180e3 | note | ACCEPTANCE CRITERIA: Testing and Comminsiong to be completed
2b2fd64f-173b-54a2-9f8d-b9ff82f6355c | note | ○ Attach Testing and Comminsiong Report
2507b3c0-410c-5c38-b812-2779fddb1459 | note | METHOD: Document Review
2d885c79-367d-5d09-bb5e-a058ff99d8b1 | note | FREQUENCY: Each Lot
12e8ee34-63ef-5865-bfe7-36d3b5726c1c | note | CATEGORY: HP*
7ff3e05d-ca11-571d-b2b3-352c375952e5 | note | RESPONSIBILITY: PE, MTM/VicTrack Rep
76af0b18-e86a-5175-ad39-4b2a86771e3a | note | VERIFYING DOCUMENTS: This ITP
e4a9c679-3a79-591c-bac2-0f8c7edb390a | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
03176dcf-ce5a-597e-a9a5-330a3f5c1db6 | note | REFERENCE: MRPA Quality Management Plan
fe4cb5d3-e5b5-569d-8018-c30743523f7e | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
5e5e4708-1977-5910-bcdd-50dea287f70d | note | METHOD: Document Review
2fdc2027-5f9a-51ca-999f-99953f452520 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
05eec57c-d289-5e2d-8d3c-c2d6ec2396e7 | note | CATEGORY: HP*
66dc9642-a9f4-5451-9f8e-c4604a7454c0 | note | RESPONSIBILITY: SE/PE/SPE
bd3068cf-987e-5c59-82b5-51a0d88a2e37 | note | VERIFYING DOCUMENTS: This ITP
e01c50b5-157b-5d2c-9c05-8cd969db49b2 | date | Date Completed:
| checkpoint | Final Inspection
f5f0dda7-8ed4-59f0-b0ac-ab1a773c8aa7 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1c90f279-519f-533f-9f1f-1254a5c2179b | textbox | Name:
bcb84c9b-615b-566d-bb7a-632b8c2767fd | textbox | Position:
7d7a778c-f75b-52da-b777-60e1d71a72fe | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-092-CIV-PSDS-Private Property Fencing Rev 1 | itp | ITP-092-CIV-PSDS-Private Property Fencing |  | 5aeb5a02-a825-4ad5-a219-9267f083e13a
| section | Referenced Documentation
| checkpoint | Referenced Documentation
bcfee22c-2443-507c-ac38-1e726e76d709 | note | Document Title: ITP-092-CIV-PSDS-Fencing
131ccf07-a8b4-5e87-86e6-4491ed2be6aa | note | ITP Description: PSDS-Fencing
6f68c1ff-c5de-598b-ae70-b3ac2f7af2ee | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
59f1b3c4-20cb-5e5e-bb9d-a870f7861be2 | note | Discipline (e.g. CIV/STR/RAIL): CIV
2fe77d48-3738-52b8-831e-8867df86a18c | note | Revision Number: 1
ee869a03-2b87-57d7-9ab0-ac2bfee5e74f | note | Revision Date: 26/02/2024
3bcf41dc-1ea4-5910-95a8-93a5d943323b | note | ITP created by: Nathan Cooper
a0c04f1f-b3c0-5562-bb1f-276a53f441ae | note | ITP approved for use by: Victor Mira
fb58cc97-c089-5006-a0fa-01febde89eeb | note | 1.1 Non Dependent
dfcfc7c3-a0b5-5aba-875a-187672859e49 | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025, VicRoads Section 610, VicRoads Section 630
| section | Materials
| checkpoint | 2.1 Concrete
78501596-b09f-5cb2-8f30-73aa489e251e | note | REFERENCE: IFC Drawings Section 610.07 Table 610.071
a54ac429-ea63-533c-8cd3-718da254fd38 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings.
f0d5d953-31b6-5435-bcf9-5115cdab8fa9 | note | METHOD: Document Review
326871f6-b05e-5b8b-9c36-9b5139615bb6 | note | FREQUENCY: Each Mix
c1f2bac4-48b9-5087-8edd-414336092cdb | note | CATEGORY: HP
8f2e293a-bda0-5d42-80b2-abc58ce2a03e | note | RESPONSIBILITY: SE/Site Supervisor
283505d9-966b-5cae-8265-6a270e492bc1 | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
29248fa6-f6ba-568a-9298-0ecd27cf3362 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
300ad61d-d91d-50a4-ad4a-ab9cb7098172 | note | REFERENCE: IFC Drawings AS41000, AS1163
ba47aa9b-4626-5e5f-be14-5ad1113dd3fc | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
7f7bf3d0-ffbc-548b-b1f1-09e064c11541 | note | ○ Steel section sizes must be checked on site.
b88589a1-e221-5fde-971c-fe4d3b475f6d | note | ○ Steel posts to be CHS with a grade of C250
4c250280-fe37-5115-ad21-fd22ae91d655 | note | METHOD: Document review, Visual and Measure
5eddbbec-caa4-5627-8e2a-9380977ddcb4 | note | FREQUENCY: All elements
68c55aa9-c2e7-5d32-93be-20fb63f0f70f | note | CATEGORY: IP
597c9685-0d64-5c8a-9920-dca23d1c4e81 | note | RESPONSIBILITY: SE/Site Supervisor
9c09d7c5-56fa-5630-b0e6-05beb2856384 | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
70f06ec2-1d12-582a-96af-75d66b95ce55 | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 3.1 Survey Set-out
8f1d304b-5fa2-5dd6-9232-1f5ab45720c5 | note | REFERENCE: IFC Drawings
f3397189-fb11-5a8f-adad-d893da95fae5 | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
bdad203e-ac5d-57e9-bb96-3bc3ac86c988 | note | ○ Offset checked against the running edge prior to installation of posts.
566b9c3b-ff51-5ade-a919-0622daeeab06 | note | METHOD: Measure, Visual
54692f09-8a9f-5486-8467-bd6604ab7b77 | note | FREQUENCY: Each element
fe7e9824-e5e2-532f-99f9-d227b7775f15 | note | CATEGORY: IP
299283fc-4aa9-56f0-8f2e-ae969af7c0c7 | note | RESPONSIBILITY: Surveyor, SE/PE
b5ef011d-2248-59e4-92f2-b4b60d054fbd | note | VERIFYING DOCUMENTS: This ITP
d7440c57-bca3-523f-ac69-4bf10ce0c2ba | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 4.1 Excavation works
7cb9a474-e1d5-5eb3-992b-0f8022eee35f | note | REFERENCE: IFC Drawings
ab014a4d-900e-51e0-8338-50c0d3354f53 | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
85c89dad-f818-5848-a2aa-ceff3586a04a | note | ○ Follow asset owners guidelines for work around their service.
ea09ad65-040f-501a-9925-d6f69c9445fe | note | METHOD: Visual
d57caab8-8833-5234-bb17-1a861ad9190c | note | CATEGORY: IP
722fd217-277d-59f3-b810-a1ef1d842a1c | note | RESPONSIBILITY: SE/Site Supervisor
987f67f5-ef76-5207-adfb-0aa2b63090c4 | note | VERIFYING DOCUMENTS: This ITP
af50346b-c0fe-5b5f-b51d-52395042abb4 | date | Date Completed:
| checkpoint | 4.2 Ground Conditions
44788d42-6444-518b-8d46-0a9dc78ba351 | note | REFERENCE: IFC Drawings
ebd96176-393f-5600-820e-b9e49bc22e61 | note | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
529a37e6-e4d2-5e12-a653-0c1ff248a058 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
ee75b060-1eec-5076-a14a-6e5405712388 | note | METHOD: Visual
0e7fb7af-c709-5105-8419-5dcdb1b91ccc | note | FREQUENCY: Each post
211d166f-140d-5391-96dd-bbaa5f6cf7be | note | CATEGORY: IP
598246b9-386a-50cb-a1ff-31bfe511d381 | note | RESPONSIBILITY: SE/Site Supervisor
3edc6626-5cab-5035-8c50-a27907c0775f | note | VERIFYING DOCUMENTS: This ITP
a39b5057-6969-5f3f-a345-f96c64d00b8f | date | Date Completed:
| checkpoint | 4.4 Fence Post Foundation
7e707588-d013-5b7b-b54d-aba299bc1cb9 | note | REFERENCE: IFC Drawings
1a15f5f5-92a9-5b82-befb-bfcb1871568a | note | ACCEPTANCE CRITERIA: 32MPa concrete.
afaeca32-a2ee-5140-a806-4f3f88809bc3 | note | ○ Footings as per IFC drawings or standard design to match existing.
fe6ef4ba-9959-55c7-baa2-2e3012a3a209 | note | ○ Refer to IFC drawing for reinforcement details.
3a3e6ecb-7df0-5ec6-9a74-bcfcd6db33d8 | note | METHOD: Measure
25768b57-b0bc-56b4-a413-811158179a98 | note | FREQUENCY: Each footing
ef87bca7-582a-5072-8d45-1da476ee5f64 | note | CATEGORY: IP
af94314f-c8ff-5519-82c2-087e84e81f04 | note | RESPONSIBILITY: SE/Site Supervisor
9035e9ef-3f58-565d-bba0-6d12d6394471 | note | VERIFYING DOCUMENTS: Post and concrete dockets
c1098ea4-e59c-5bbe-85d5-761c86626cf2 | date | Date Completed:
| checkpoint | 4.5 Fence Post Installation
df26cfd6-9944-51ac-8ca9-7d5ae464e967 | note | REFERENCE:
50dfc27b-9efa-56d3-8553-808a5eb761b4 | note | ACCEPTANCE CRITERIA: IFC Drawings
c48543ec-1669-56fd-9355-099c5a07bda2 | note | METHOD: Maximum post spacing to be 3.25m ± 250mm.
fe7547c4-5073-582a-a2d3-6a8284031e88 | note | FREQUENCY: Measure
39c6ba19-ad71-5401-92f6-92e64e759cd9 | note | CATEGORY: Each post
37c6a6cd-3c5f-5eeb-b94c-602d61d2c85e | note | RESPONSIBILITY: IP
938a054a-5d27-533e-b00e-747972ab49a3 | note | VERIFYING DOCUMENTS: SE/Site Supervisor
ffd1581d-2b11-5221-b986-88b8dc96a667 | date | Date Completed:This ITP
| checkpoint | 4.6 Chain Wire Mesh Installation
47cb2698-0308-58a8-9eb8-345c1d0ba4af | note | REFERENCE: IFC Drawings
b5689626-eea9-5e8d-882b-93abfc34d3bb | note | ACCEPTANCE CRITERIA: Chain-wire mesh to match existing and or IFC drawings
50b2a7f7-08d3-5e21-ae35-aadc5a7329c6 | note | METHOD: Visual
edbd0886-c65c-564c-9b41-b6293177f7c8 | note | FREQUENCY: Each element
833cd6df-a61d-500f-9604-502e40abcba7 | note | CATEGORY: IP
e9accff2-7e9c-5542-89b6-7aba7aeaeb20 | note | RESPONSIBILITY: SE/Site Supervisor
bda1fd75-feeb-54cd-8a52-5d1ae05c5e64 | note | VERIFYING DOCUMENTS: This ITP, Delivery dockets
376f57b7-f8c1-5a09-8733-c5d4f2c661cc | date | Date Completed:
| checkpoint | 4.9 Gate Post Foundation
52d80363-180f-5efc-bfdb-506f839b2b67 | note | REFERENCE: IFC Drawings
f583bc0a-3ab3-54b8-9a2c-8b0ea6d54193 | note | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
441fac10-7cbb-5383-a24e-25447e13aaef | note | METHOD: Visual/Measure
eefa7e49-909c-57bf-9ef6-c9feba4f9a50 | note | FREQUENCY: Each footing
81ca5066-b0fb-57be-90dd-c14ccf347373 | note | CATEGORY: IP
b5d1f8f6-40cf-5e25-b4d1-2d71e996643f | note | RESPONSIBILITY: SE/Site Supervisor
4b24222b-d41b-5f85-a2dc-a24a9aebd9bb | note | VERIFYING DOCUMENTS: Post and Concrete Dockets
bd78b44f-65c2-5db2-be1d-0937fd2df802 | date | Date Completed:
| checkpoint | 4.10 Gate Installation - Post
bf920a40-ac6e-58a6-922a-18793b604a92 | note | REFERENCE: IFC Drawings
aef59f0e-ed59-5260-be37-7d863d879bb5 | note | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
6ae88ab3-b79a-586f-865a-c67239938516 | note | METHOD: Measure
a35abd11-5e5a-504a-b7d3-1b3a16e63f2d | note | FREQUENCY: Each Post
3881cae8-bd19-56b7-918b-e7b14ea0beb9 | note | CATEGORY: IP
c5a14780-2cc7-538e-a058-0577c6e3ae1f | note | RESPONSIBILITY: SE/Site Supervisor
546cbceb-1aea-5471-ab79-fa652cef9db7 | note | VERIFYING DOCUMENTS: Delivery Dockets
78cab5a4-7d8e-5541-9267-85109d54f7fb | date | Date Completed:
| checkpoint | 4.11 Gate Installation - Gate
f3a3d63b-27aa-5c2f-b4a9-21481080faae | note | REFERENCE: IFC Drawings
c95c5049-1b7e-5508-b458-6a7b78a658d5 | note | ACCEPTANCE CRITERIA: As per standard drawings and or IFC drawings
9a090227-5e81-5f8b-b4d9-5330b4b4daa8 | note | METHOD: Measure
cd07af45-f2b9-59f2-b111-c8203639f13b | note | FREQUENCY: Each Gate
520b17a6-f304-5c88-9e4b-1c03dabaf26a | note | CATEGORY: IP
bab1440f-e6ea-548b-b653-bc349f17ddd9 | note | RESPONSIBILITY: SE/Site Supervisor
07574356-4227-5172-91c5-ea5a4f81d84e | note | VERIFYING DOCUMENTS: Delivery Dockets
af27c8fa-2535-581a-a18a-6c6193a9b26d | date | Date Completed:
| checkpoint | Final Inspection
5a5ec471-3e59-542c-922e-53f89b06291b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8196ccf4-894f-57c4-a35c-89375c896b21 | textbox | Name:
fd9a66d1-2069-5dc0-8d4e-47ddcc3021c7 | textbox | Position:
e0be5ae8-0cbf-50ff-979a-9d4fa8a3d4d0 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-120-CIV-PSDS-General Concrete (COGD) Rev 0 | itp | ITP-120-CIV-PSDS-General Concrete (COGD) |  | 2a6c7f83-b464-46e8-ba89-d279f9bc0b50
| section | Referenced Documentation
| checkpoint | Referenced Documentation
0474ecd5-4ffb-5357-a530-2fec5200ed36 | note | Document Title: ITP-120-CIV-PSDS-General Concrete (COGD)
5c5012ce-74dc-5f55-acb5-3fa1eb378c25 | note | ITP Description: PSDS-General Concrete (COGD)
e01df02c-4075-5163-b78b-3cf81f71b435 | note | Discipline (e.g. CIV/STR/RAIL): 120-CIV
2c726687-4565-5941-9840-1e3117597806 | note | Revision Number: 0
d0ed8ff1-44dc-51e2-9ff4-bfdf563470ac | note | Revision Date: 9/09/2024
f185145a-591a-5579-993a-c358b03dcde4 | note | ITP created by: David Chai
15f86423-a349-5a2a-832b-a4e72359419f | note | ITP approved for use by: Victor Mira
037818c0-ee0f-5e72-9a2f-bcdcd4b15fa5 | note | 1.1 Non Dependent
af4cf636-7d83-5780-b39e-31e872603263 | note | Reference: VicRoads Section 703 June 2018
4278eb87-f0fe-5298-a7aa-ae9a0eec432a | note | 1.2 Non Dependent
b44b94b7-da26-5e63-8728-3147ced0fd6c | note | Reference: VicRoads Section 812 July 2016
23b86b67-7d75-5ee8-a95b-94e36c5cb04d | note | 1.3 Non Dependent
5041953d-d382-5acf-84ed-4ed09f193648 | note | Reference: AS1379-2007
3439733e-b2de-521d-af8b-e67af418d132 | note | 1.4 Non Dependent
e21c6c6f-d31e-5fd5-938e-95f3b9ec4386 | note | Reference: AS3610-2018
33fe3502-53d6-570d-9c85-8892a7c4dc2e | note | 1.5 Non Dependent
692e751a-8c37-5405-a9b4-3f4f947d0a41 | note | Reference: AS4671-2019
| section | Preliminaries - Materials
| checkpoint | 2.1 Bedding Material / Base Layer
bc4d7c56-f3e2-51ee-a75c-844587ff1e75 | note | REFERENCE: IFC Drawings 703.21, 812.04
402369d3-0c9e-5d27-9bbf-410d93c9d278 | note | ACCEPTANCE CRITERIA: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
0233edeb-8c5d-552b-8ffa-563bd20263a7 | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
c66e1793-d1a4-5f2c-90cb-e1909225ec2d | textbox | Enter: Teambinder Material Approval number
8720ae52-ce0b-5d09-889c-4bbe20dbd437 | note | METHOD: Document Review
f4a5ae13-659b-55df-a39e-798c5868e278 | note | FREQUENCY: Once, for each mix design, prior to placement of material
41f5b4e7-7b92-5e37-94b6-d5e66bc5ba1f | note | CATEGORY: HP
c42a19a9-c54f-562e-b2ba-3ce46b42770e | note | RESPONSIBILITY: Nominated Authority
f258c539-4a69-5da8-af21-3fae6a988066 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Concrete Mix
8dfc3ca9-b50f-538f-9af1-ac1429e44b93 | note | REFERENCE: IFC Drawings, 703.05 (a), 703.07, MRPA Quality Management Plan
6ee92ceb-da9e-55f2-b0f2-109fe9129540 | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
d989208c-88d5-508e-8523-7b9a646880fe | note | ○ Paving concrete mix conforms to AS1379.
0b22e7bc-c930-5f04-8c7f-96905e30c99f | note | ○ SUP concrete mix is registered with VicRoads.
5609f277-d541-5f71-aafb-07b890e546a7 | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
340ef16f-79cf-50fb-bdfd-883f7866238e | textbox | Enter: Teambinder Material Approval number
ae7541c8-388c-572d-8ea2-5bafc12b7662 | note | METHOD: Document Review
e3649883-7070-540f-afc9-19ca6d4c4428 | note | FREQUENCY: Once, for each mix design, prior to placement of concrete
52ecfcce-e45b-5fef-badf-4af959de7983 | note | CATEGORY: IP
062fc346-e795-5916-92ea-36d5daabe204 | note | RESPONSIBILITY: Nominated Authority
838d7203-44ab-5bf5-8afc-e9c101fb7f66 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| checkpoint | 2.3 Reinforcement Certification (or ACRS Certification)
d988244c-68cb-53b4-ae64-1e5153b5b283 | note | REFERENCE: 703.13, MRPA Quality Management Plan
61658277-61eb-52a6-9dd5-274d964b1225 | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
1ef22bfe-ffe9-525d-8045-ab2b04c52af1 | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
a2af4f91-42e9-59e0-a3b8-d9f8f03c4917 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
3d808740-d1f6-5910-b2e0-81a06ac12df7 | textbox | Enter: Teambinder Material Approval number
ded1c0b6-7bc8-5081-a21a-ae0151f51762 | note | METHOD: Document Review
b4b18a13-256a-5173-a6b5-816089c3bc1b | note | FREQUENCY: Once for each supplier, prior to placement of order
db444859-eb33-5f7c-bdc1-9c574aa43a1a | note | CATEGORY: IP
bc8f9aca-59c7-5e3c-856b-77c747dd4049 | note | RESPONSIBILITY: Nominated Authority
737acb32-3fd2-563a-989c-f1cf7e038f9a | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 2.4 Evaporative Retardant
19afd6d9-a8b4-52eb-9a57-93e7bca3b4a4 | note | REFERENCE: 703.09
4ad14e16-c766-5290-847f-334b7fa96c3c | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
348461ac-1eda-5e8d-9ef9-c071004ef721 | textbox | Enter: Teambinder Material Approval number
15050c86-ee02-55fc-9e8a-d8cf81c648f7 | note | METHOD: Document Review
8beac704-191f-5b99-8845-9dd99e16f862 | note | FREQUENCY: Once, for each product, prior to placement of concrete
8bc5a264-f5d2-5d32-9354-dda09209f809 | note | CATEGORY: WP
4deed863-20b7-55ed-b673-8680073d8b28 | note | RESPONSIBILITY: Nominated Authority
d83e94f3-610b-5802-8249-fc2a9f95a046 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 2.5 Curing Compound
466c2beb-51fa-502b-b344-d2348a914aae | note | REFERENCE: 703.10 (a)
850af083-ccec-5513-9ff0-ca2fb59107a0 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
52071065-d496-56a8-99ff-0117ef2f432c | textbox | Enter: Teambinder Material Approval number
7cfac7f1-c38c-55c4-aca1-7c5b81902749 | note | METHOD: Document Review
8463e5aa-5aab-56e7-8108-d6829a6e5532 | note | FREQUENCY: Once, for each product, prior to placement of concrete
8cd38a2f-858b-58dd-8c3c-1c64f62e14b9 | note | CATEGORY: IP
7d7cb1aa-7aec-5540-ac7e-f79d7eda1137 | note | RESPONSIBILITY: Nominated Authority
517816d1-61fe-51f3-b421-7f896852442c | note | VERIFYING DOCUMENTS: This ITP
| section | Preliminaries - Documents
| checkpoint | 3.1 Lot Map
c3e2b9e3-d1a6-59fe-acc1-5b4d964b2e5f | note | REFERENCE: MRPA Lot Management Plan
c5645b45-208d-5c51-8808-97f34e0a9951 | note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
1ca5cc4a-4cb8-569e-8f21-efff95932bf5 | note | ○ Attach: Lot Map
ffda74cd-3dc7-5fa0-a4d2-e38cdac9194f | note | METHOD: Document
a29df101-2e1c-579a-a8e1-94c020b54404 | note | FREQUENCY: Each Lot
7776075a-854a-5ba5-8fed-521b9dcd789a | note | CATEGORY: HP*
174d1dc3-7de8-55be-a4ee-95d84a5c4a70 | note | RESPONSIBILITY: SE/PE
72bcd9b0-27c7-5f0f-8839-9ad2dd394b39 | note | VERIFYING DOCUMENTS: Attached Lot Map
| checkpoint | 3.2 IFC Drawings
524b82ee-6d89-54f4-ba8d-c06f36aaa46d | note | REFERENCE: MRPA Quality Management Plan
61f5e9b6-c0b2-58ea-84e1-22df877bb057 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
88858e0c-4874-5f7f-9b65-77445322777e | note | METHOD: Document Review
a493f46f-ee31-55fb-907b-41a8e659deb3 | note | FREQUENCY: Prior to starting Works and at regular intervals
4403ea17-7802-5460-95d7-b0edb82ff0e3 | note | CATEGORY: HP*
62a26ac8-fb5c-5be8-97f0-f99f53f5b4a2 | note | RESPONSIBILITY: All
0896568c-7389-5fde-a0b9-1f539ed39417 | note | VERIFYING DOCUMENTS: This ITP
| section | Pre-construction Activities
| checkpoint | 4.1 Survey Set-out
640934c4-70a7-5798-a140-36cef422f966 | note | REFERENCE: IFC Drawings, COGD SD300 Series
3f843d4c-e74c-5909-b03a-4978be5a2d45 | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
021358d7-3a04-5b75-a6cd-abb7a7f81488 | note | ○ The Nominated Authority will review and confirm the set out.
0baeb17d-5a5b-53bd-a24b-542cca618046 | note | ○ Attach: Survey Report
21ed48b5-16d2-5857-b91b-ef223839cf63 | note | METHOD: Document Review, Measure, Visual
798ab8aa-1b6d-585e-b7b7-5e9329ac754a | note | FREQUENCY: Where applicable, each lot
8bc46a75-6cf5-51ac-aa93-a733ad72a108 | note | CATEGORY: HP
4b81f69a-f760-5d91-95ed-84ae5426328e | note | RESPONSIBILITY: Nominated Authority
63b9d5ca-2be6-5d55-bab3-2de3ace76d50 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Excavation
0b69b730-9c25-56d5-b2c7-8b5dffbfeb0d | note | REFERENCE: IFC Drawings, COGD SD300 Series
4afdf023-99da-5fd3-a150-99df5d1d2a30 | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
8b70fc62-78a5-59d2-9e8f-b774e77c8e0e | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
18c71b91-a61b-5063-8ed8-640cffbd62f6 | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
01c26627-f8fd-5f1e-8701-4573c5d4b292 | note | METHOD: Visual, Measure
db2c4814-fb84-5123-8b43-853857657af2 | note | FREQUENCY: Where applicable, each lot
9880afbc-44a0-59d3-bd29-afa8460b78b4 | note | CATEGORY: IP
31b5af12-0940-5912-b1cd-e3fa73857cd3 | note | RESPONSIBILITY: SE/PE/SPE
3242e758-b7b9-52de-ab6a-0bde405781c2 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.2 Bedding Material Placement & Compaction
6f2b138a-18fd-5b46-a2f1-6b8b331ae987 | note | REFERENCE: COGD SD300 Series
e52a89bc-2969-515b-898d-c542dbfacf27 | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
9652e30d-60b4-5151-9707-52cc6fc69627 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
4ae77c3f-3eab-56de-985f-6f4b1e103cf7 | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
3b064f71-2bbe-5052-afeb-c89bbc1c5e00 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
f54d4552-8c9d-5ff1-8a7a-ec683c3f2dfe | note | ○ Attach: Bedding Material Delivery Dockets
ddf8ae9d-9c2d-5038-b7a8-e670eb1653f9 | note | METHOD: Visual, Measure
75b57703-6b8a-5fcc-937c-c7d7f1313d15 | note | FREQUENCY: Where applicable, each lot
e96c86e0-cfe7-59ee-88e7-13f4871f8915 | note | CATEGORY: IP
0ccde554-f8df-5d31-8d58-63ab72a096a9 | note | RESPONSIBILITY: SE/PE/SPE
73e75b57-41a2-5918-a029-ebfb14094307 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.3 Formwork Construction & Placement
4f196723-60f3-5a49-9734-db7dbc219d41 | note | REFERENCE: IFC Drawings, COGD SD300 Series
cc416266-9bed-5ed6-b417-1fb6107c9465 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
b0dd3c18-2ebd-5230-94f4-3d97f209a00e | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance.
6e215aa2-a596-54b6-b39f-474fc7a6c4ec | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
b6b2155b-706b-5011-94b2-52bfc6ac15f6 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
4f48ba03-3eed-5dd9-a86f-209552688e55 | note | METHOD: Visual, Measure
afd48a3f-ad01-5367-8238-95cf4cb43a4d | note | FREQUENCY: Each lot
3ec77a2a-c85d-590b-bfeb-d7e8693e8697 | note | CATEGORY: IP
5aaa6dfa-8010-53b0-a4a1-ca208b08d686 | note | RESPONSIBILITY: SE/PE/SPE
f968c83d-e639-5b8c-bfa7-949bfa2a7d1a | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.4 Construction Joints & Matching Exisiting Surfaces
52975616-7fa2-5d7b-ace2-b19700311a32 | note | REFERENCE: IFC Drawings 703.24, COGD SD300 Series
944585f7-2477-500a-b7f6-e71b140f6400 | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
fa9c30c1-c2f0-5068-8d9a-d92d84890bc5 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
b387d9e0-8886-5ff4-9e15-bdeed153b005 | note | i. Concrete cutting of a shear-key
e38f78b3-b984-5eb6-be2e-2885ef8f1051 | note | ii. Surface rouighening
ca23feec-a397-5a4f-9956-ceca983e2da8 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
ae6fbfe8-7699-5c59-bc74-ed86a45d8e48 | note | iv. Cutting a groove for sealant
007e5016-3467-5987-874a-14cbed630d25 | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
efae33ad-403e-5bb2-a10f-c3640bb1b21a | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
0186c1a4-d934-5b3f-9e7b-d0dc66eb349f | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
888b02f5-c79b-5e03-bcfd-ff2d0168497f | note | METHOD: Visual, Measure
20808ff2-a0ab-5d02-9a22-9bbaf6861ebe | note | FREQUENCY: Where applicable, each lot
5cf32015-385b-5355-8441-79e48a7b1dc4 | note | CATEGORY: IP
8cf31be9-28d4-5eeb-a7a4-ebd2096a2349 | note | RESPONSIBILITY: SE/PE/SPE
517ee740-709d-59e6-b76d-9bfbf292f5fa | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.5 Isolation Joints
a4a539df-b897-5022-9289-436b18c03edf | note | REFERENCE: IFC Drawings 703.26 (c), COGD SD300 Series
64a2e524-9fe8-5e40-9fff-af34932163f8 | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
80d6b7e9-84f9-5b37-9023-81e4420dcedb | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
46f8325f-0cd9-51be-9263-0ad5ee5904af | note | ii. at any location marked on the drawings
e9354278-4eaa-5e78-bb07-e384b9b6d6a8 | note | ○ The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
55cef6f5-0f47-579a-9e01-dec6e5787177 | note | METHOD: Visual, Measure
10cabd44-4640-583d-8413-9f8341fd5e33 | note | FREQUENCY: Where applicable, each lot
e2d1c91e-78b2-577a-ad5f-6ea3d4c66910 | note | CATEGORY: IP
934011eb-dc1a-5065-b624-c5f89bc9e69c | note | RESPONSIBILITY: SE/PE/SPE
c7cff81c-948a-5c87-a67e-3b73104e1d9f | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.6 Reinforcement Placement
2f205daf-32df-5c37-9861-1ae3448fe154 | note | REFERENCE: IFC Drawings, COGD SD300 Series
f18ef0fe-9409-51a3-9f93-6c88a82b8385 | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
d628deea-09a8-5a76-aea1-c07cf44bdd97 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
626e0e15-b8e1-5e08-a6f9-426bca966b97 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
942c5fc0-6f2c-5c23-8192-e64afd733137 | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
07da0079-48e3-582a-9ff4-e98613a5631b | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
e29e51cb-2efe-510d-b3c4-617e12c5ae93 | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
66dc36b7-19d7-5c15-82ce-5d79bab10321 | note | METHOD: Measure, Visual
74f010e0-5d14-5237-937c-cb5f5f2c3b76 | note | FREQUENCY: Each element
1489d651-0fdc-534a-b7aa-0bd71f0bdff1 | note | CATEGORY: IP
026c4a48-b188-5cbc-be32-10b295114417 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b86cadec-3df9-516f-aaf9-4129c43b98bf | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.7 Pre-pour Inspection
808df5bd-dba6-5eb1-b330-7a07774d885b | note | REFERENCE: IFC Drawings, COGD SD300 Series
e40fc37c-55be-57bb-8e1e-b69bd8e7c656 | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
210e0f68-4fd0-564d-be0e-430a905e9479 | note | METHOD: Measure, Visual
08784fc0-030d-5a02-8943-1ebbdbe6a4d0 | note | FREQUENCY: Each lot
ca401658-bf71-50e2-8d06-6d27582df78e | note | CATEGORY: HP
3de2c8b9-5122-5319-acfe-7738d27d1348 | note | RESPONSIBILITY: Nominated Authority / Council Inspector
137eeb68-ce6c-5793-bd68-08f2b790c1b9 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.8 Weather Conditions & Evaporation Limits
b7bb19f0-30b9-5b9f-86d9-e36012180141 | note | REFERENCE: 703.09 & COGD SD300 Series
96d278a9-df10-5c79-9909-f28742aef879 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
aa0b700c-6bb7-5419-b8ca-fdaa8c6756e7 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
675738a9-1c59-5ec2-8d6f-0042b8ac1376 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
fd12cb0b-9b91-538b-9ecf-5c951730b062 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
93c9d11b-81fa-554c-b183-c5b504f5c6c1 | note | ○ Record: Required information on the Concrete Pour Record.
75623ab3-14ff-5ced-bfd6-4c80fddde7a1 | note | METHOD: Measure, Visual
dd24ec34-74f8-58ba-ad68-1c992450a181 | note | FREQUENCY: Each lot
0d12923a-a456-57b6-ad13-27c800578c50 | note | CATEGORY: IP
ac6182a7-0445-53a6-83a6-934b87beedb0 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
df14e97f-20d9-562e-b2fb-b96c81ced977 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.9 Concrete Testing - Sampling Frequencies
502d780c-5545-5ea6-ab37-d4f3952321ff | note | REFERENCE: 703.11 & COGD SD300 Series
0eccb6aa-bd34-530c-a3f5-7e9e8ec9e4f4 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 50m³ = 1 sample
312865ce-1269-5af5-9352-300464090cdf | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
5822eab3-bee8-5bd9-822b-98b984b264fc | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
63f98799-fe89-5758-9dc1-96a5edd815bb | note | ○ Record: Required information on the Concrete Pour Record.
199560ba-75fd-5ed0-99a5-b7432ae0a3d4 | note | METHOD: Test
77c3c838-b790-51c5-b2aa-9dca27285e2c | note | FREQUENCY: Each lot
f58dfd7a-edd4-5f90-8e0e-91699e08bdda | note | CATEGORY: IP
4b8ab732-32b6-5593-906d-e473bfa4b419 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
a5cc5ab6-7a0d-50ac-8d61-8eb6b7125915 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.10 Concrete Testing - Slump
7a689826-6681-5fa1-8240-0f41788e9ecf | note | REFERENCE: 703.11 & COGD SD300 Series
71e5396c-cfa7-540d-a178-b76d68c15742 | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
a49fa13c-a28c-5594-9b01-858a1cbc74fb | note | <60mm = ±10mm
0d641228-c003-52e1-8b50-a0ee8b65707e | note | ≥60mm to ≤80mm = ±15mm
03a36a30-4a5a-5b44-8094-89980dda4d1a | note | >80mm to ≤110mm = ±20mm
1bbaca69-55c6-5d67-989c-67b3c7fbd14e | note | >110mm to ≤150mm = ±30mm
19c5316e-74fc-512a-8a80-c07795e46b4c | note | >150mm = ±40mm
01633ba6-6372-5b78-b1d0-a3f1df69e83c | note | ○ Record: Required information on the Concrete Pour Record.
2db80980-fd55-5d10-a272-e4480496de2c | note | METHOD: Test
9d80002b-5983-5a5b-a613-b2ee5b0f0079 | note | FREQUENCY: Each sample
01bfd4bb-9dbb-5fa4-861f-36585ce0cb70 | note | CATEGORY: IP
a1ad8c6e-653a-5e6c-854b-f43bc718a069 | note | RESPONSIBILITY: Concrete Tester
f7b25832-0e64-5eeb-9b19-0ffbfe9b04cd | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
ac15bab2-0553-5106-a58c-d67eb79026ad | note | REFERENCE: 703.11
919da251-5e87-5313-954e-d43faaf33a97 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
fb42537c-8729-5732-9d0e-5977c5306938 | note | ○ Record: Required information on the Concrete Pour Record.
c6fa3462-0576-5c88-9768-487ff2baff89 | note | METHOD: Test
440a28fd-5cff-5d62-9f2e-4f9bd0e7201d | note | FREQUENCY: Each sample
1feddc97-950c-5f4d-aac2-13c7f8d0cc08 | note | CATEGORY: IP
95ad09c2-e39f-51a7-b32d-7bcf00d4ccf9 | note | RESPONSIBILITY: Concrete Tester
0fd15bee-27c0-59a8-ac05-e3d43da050ed | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.12 Supply & Discharge Rates
4369e18e-cbdf-5ee9-a006-fa80bcdc3e0e | note | REFERENCE: 703.08
7dbdf6d2-885c-55f0-98a6-dce4143fc7aa | note | ○ AS1379 Clause 4.4.1
219a3012-c894-55bb-8f5a-7c2b63ce948b | note | ○ AS1379 Clause 4.2.3
7015895c-8ade-5f3b-b975-4493ca470167 | note | ○ AS1379 Clause 4.2.5
17f78d3c-3d92-5842-a6dd-3ae9beb84c9f | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
ea72aad2-402b-5b5e-85c4-96bc2f139882 | note | ○ Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
49b28450-ecb2-55fb-86c0-f14a9f106315 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
34187db6-fd46-5ed1-94f8-26a9487ca408 | note | ○ If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
1f9a9d53-79f2-5457-95c0-df7328ca2367 | note | ○ Record: Required information on the Concrete Pour Record.
a7b94268-a17b-530f-b801-020b365bfc72 | note | METHOD: Measure, Visual
28fe989e-a861-5480-953f-db50afaf96c1 | note | FREQUENCY: Each load
c4b1226b-928b-5db2-863a-6ccafaa75413 | note | CATEGORY: IP
80fe0e86-02db-5784-b23b-f337eb8c181b | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7f571a49-1b96-5287-83c8-83a4bf752411 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.13 Placement & Compaction
859887ef-2df5-5509-b539-129c0e549afc | note | REFERENCE: 703.08
2bb9640a-05a6-5134-a93b-2cec7f43b1a6 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
e3999910-9701-52a9-8012-18b7f6bba6a7 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
dce40fe2-7dc9-579c-ad02-c6a09ad242be | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
d8864ca8-621e-526a-9fc0-f0f2c84cf062 | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
f558546d-6394-569e-9ce0-791b20b47fdc | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
ea6f7566-2b35-59d9-a9ca-48e4f0958a9c | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
73877f57-0912-5e65-8cc3-f30cb34d5ec3 | note | ○ Record: Required information on the Concrete Pour Record.
8a1fb600-bb82-5ee5-b26d-add7acfd77f0 | note | ○ Attach: Concrete Pour Record
7bcd979b-8d5f-5dda-9f88-2ffd955cc986 | note | ○ Attach: Concrete Dockets
36783e34-9996-5366-ad89-b48000f4f60b | note | METHOD: Visual
2a80e82e-ef6a-56af-a094-9a47fdbcfa21 | note | FREQUENCY: Each load
7933d938-0322-5b9d-b4cb-3af6d1965746 | note | CATEGORY: SP
a51c5419-f1db-55d2-bebd-89dc3e3880f6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
9a6f96f0-9e61-5448-b888-14094be15612 | note | VERIFYING DOCUMENTS:
| checkpoint | 5.14 Surface Finishes
8b4e40b9-b351-5d0d-a2be-86e011084f07 | note | REFERENCE: IFC Drawings, COGD SD300 Series, 703.25
50b7878c-fbdb-5c9a-a5ae-abdcbe9f9131 | note | ACCEPTANCE CRITERIA: Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
99af81d5-0b4f-5470-b0ef-ecff11362f2f | note | ○ All outside edges of slabs and all joints shall be finished with a suitable edging tool.
0369db5d-a061-5f73-bbc4-ace7270a8111 | note | ○ Vehicle crossings to have a bull nose (25mm max)
2518776e-4709-59f4-9de7-6eb51497598f | note | METHOD: Visual
db469389-4d5f-5f06-afef-36824551c5aa | note | FREQUENCY: Each lot
1aa8ad9e-9dad-5c2c-b2e3-2c14b2738dd6 | note | CATEGORY: IP
6e0c6a1b-5b52-5c7b-84e2-71f87e19a01d | note | RESPONSIBILITY: Foreman, SE/PE/SPE
6855b231-5153-5921-b1ae-af8b2853d3bd | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.15 Marking of Conduit Locations
ec1f2b0e-d70f-5ca9-b9ef-a8cc5fe8c909 | note | REFERENCE: IFC Drawings, COGD SD300 Series, 703.28
d0fe254c-11bd-5030-a20d-e87e63b06974 | note | ACCEPTANCE CRITERIA: The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
bea10590-8837-5744-951c-4b5be58b8935 | note | METHOD: Visual
f47876a4-1716-5afa-a62e-dfda778f6a38 | note | FREQUENCY: Each lot
b833130f-b1f2-565b-9581-85df21b5a51c | note | CATEGORY: IP
ab84ea1a-9abd-525d-9fb2-967af794197e | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b634aa54-8339-5db6-978a-e470a7ee6611 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.16 Crack-control Joints / Weaken Plane Joints
c1b4dce1-13e2-5df3-8c88-ebe08a696c73 | note | REFERENCE: IFC Drawings, COGD SD300 Series, 703.26 (b) (ii)
976797c0-26fe-57f8-ace9-6e53234238bd | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
7aa7ae76-ad62-5f42-a346-2c4532730675 | note | METHOD: Visual
c718a36f-5575-55c6-9b2d-68549f7a7557 | note | FREQUENCY: Where applicable, each lot
629914aa-94ac-547b-bddf-6789e2395be7 | note | CATEGORY: IP
ed2f0411-625f-5d9c-b1de-fc9213285399 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
1f1c8278-a183-5048-bcd2-49e9dd1a5a15 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.17 Curing
f37efa99-82cb-540c-94cb-9cd0c432a872 | note | REFERENCE: 703.1
5dfddc93-47ea-54d8-865d-0a31de1d506f | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
268e6e64-252e-58b3-a59f-14be21604221 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
40777854-2277-5859-b437-abc359ccf7e4 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
6f644d3e-b885-5508-8bd9-c262a6c534df | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
64ad0e39-4884-53ce-b4d4-89a83e3d5aaa | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
3e10e984-9bca-522b-9262-b3379d6f6c08 | note | METHOD: Visual
a4e75aa7-9664-505e-88fb-b0b2b71e592c | note | FREQUENCY: Each lot
cfa1c986-6447-5207-9be8-f61b01442d92 | note | CATEGORY: IP
36df82a3-5016-5a33-9e50-58ae985ba043 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
3b8f7c48-2774-5e46-a29e-5291cf3facf4 | note | VERIFYING DOCUMENTS: This ITP
| section | Post-construction Activities
| checkpoint | 6.1 Protection of Newly Poured Concrete
9dd8dd19-a967-5329-9b4a-897a91a3200c | note | REFERENCE: 703.27
cd8471f5-5ec0-5145-89d1-af474f26b678 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
2981252a-ba75-5452-a377-57203bd8da9a | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
07baaeb8-2ae9-5067-a00e-7b8c9097fc74 | note | METHOD: Visual
e1e9faed-9288-5754-86dc-c434f16c73e8 | note | FREQUENCY: Where applicable, each lot
0c0c69a1-a7b0-5d05-9060-aeba5db1bc5f | note | CATEGORY: IP
cca9d8ae-f554-579f-acf6-8b6365939ad9 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
3a1857ea-8fae-5590-a74e-913c25983511 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.2 Stripping Formwork
b74ba870-47ac-5bf3-b308-0eb9eddb5edf | note | REFERENCE: 703.12, AS3610 Table C2
92954765-87ed-5c36-9fb2-28c8cc8d2dab | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
fa5a93f7-e110-5d3e-9f8f-f8577d7b342a | note | i. 2 days for vertical formwork on external surfaces; and
550b7c59-3ddc-501d-952d-ceaff92daf74 | note | ii. 1 day for vertical forms on permanently hidden surfaces
fd900381-d0f1-56d6-bb53-d4b7262e68fd | note | METHOD: Visual
703e0604-2a0c-5b55-aedd-190bfae3adb6 | note | FREQUENCY: Each lot
a729365d-d25d-5272-a8a0-7923a4c4a012 | note | CATEGORY: IP
9c1ef50b-c8ff-58e1-b35d-eb3cd61747fd | note | RESPONSIBILITY: Foreman, SE/PE/SPE
2bec400b-33eb-5818-aab1-a758ba26bf1c | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.3 Backfilling & Pavement Restoration
0ccdbb38-f548-50f8-bc4c-79fda3761e10 | note | REFERENCE: 703.29
8b5959a6-b323-5d27-a2be-0e9460b9b23a | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
2bd977dc-a2ed-5e72-b249-077168fb363d | note | METHOD: Visual, Measure
cbe02f42-be42-537d-a884-28c1884a3cea | note | FREQUENCY: Each lot
1edb015f-7907-55c8-9bdb-43ed72ca10c7 | note | CATEGORY: IP
eb5e448f-4b9c-5a7e-b5c6-4a14edd76786 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
d896fd56-8dcf-5a6a-bcd5-31cbbac84a50 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.4 Surface Inspection - Cracks
5fd0d2b7-ad3a-57a3-a02d-9fe940216bc6 | note | REFERENCE: 703.3
fb212079-ac3f-51f6-a13c-4a9860aacee5 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
6f798d3f-245c-52dd-a734-3b383fdd01c2 | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
8db19a72-c214-5709-870b-6b9ab0ffc6eb | note | METHOD: Visual, Measure
3a04ff05-0784-567b-bb41-df4c81a43fde | note | FREQUENCY: Where applicable, each lot
c02bdfff-edc5-5496-9ece-eb8a0fe2870b | note | CATEGORY: IP
58d34da8-8bc2-5dcc-87d1-0f584bb9df13 | note | RESPONSIBILITY: SE/PE/SPE
e7b23e70-5a59-5e4a-a9db-1fa7e8ae5ab8 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.5 Surface Inspection - Surface Finish
0a1770b6-184d-5cf3-8050-8faba3529400 | note | REFERENCE: IFC Drawings, Relevant Council Drawings, 703.25, 703.10 (a), AS3610 Clause 3.2
b3d5185c-ba40-5ec8-b3ad-7c960f653a9b | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
d91dc512-11f1-5d88-a38f-d2e1c4407943 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
b67811ec-5157-5227-909f-18ecb32c723c | note | ○ Class of finish:
b799ec0e-1501-5bd6-ab73-0f7ccfb47fcd | note | – Permanently hidden surfaces = Class 4
98ee3d25-8cd4-54dc-acf5-5e5054d1bd92 | note | – All other surfaces = Class 3
342f8480-3260-52be-8337-6c3ef24c6cb8 | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
22f3b052-5246-53a5-8524-15ffa3091edd | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
d5431e66-e49b-5e58-aab2-40b02291a682 | note | METHOD: Visual
eb931c71-b34b-52ed-bd3a-bf08233f0e07 | note | FREQUENCY: Each lot
d670a959-246e-535c-b519-7f962c66f159 | note | CATEGORY: IP
7477990f-7980-5fe3-83d2-e019a6aca90b | note | RESPONSIBILITY: SE/PE/SPE
d86ee824-7a11-52cb-a2f4-b6c16b012887 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.6 Compressive Strength Test Results
89968fb8-dca1-5e19-9ff0-aead03247951 | note | REFERENCE: IFC Drawings, Relevant Council Drawings, 703.11, Table 703.111
851d18f1-2430-5008-9281-2290155c32d8 | note | ACCEPTANCE CRITERIA: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
5e1e9cec-8b1a-5a48-bad3-11f1b5566df1 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
982d045d-fd50-583d-b24a-d74bf057bcbe | note | ○ Attach: Compressive Strength Test Results
b3563bce-44b5-58fe-a645-7be11ed02d63 | note | METHOD: Document Review
74be0883-a4fb-5b6a-b650-4b9ec87de224 | note | FREQUENCY: Each cylinder
7de692bd-10b5-5df7-902f-91df6c4c654a | note | CATEGORY: IP
0f9da3e5-27f5-54de-bea5-8e99a112bdc1 | note | RESPONSIBILITY: SE/PE/SPE
e3eb3eb9-61ce-5aee-b81c-651298afb89d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.7 As-built Survey
969a9bc1-b8c9-5f29-bef9-73e59abd9253 | note | REFERENCE: IFC Drawings 703.15
cf019cfa-fe96-51cd-9375-eb57098c65c0 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
1bb57ac1-b29d-5e47-a28f-d14a15081efb | note | ○ Departure from RL = ±10mm
8420a2c6-2e7e-5af9-bc47-8f87a36e60b2 | note | ○ Departure from alinment = ±10mm
8ea8aae4-cc95-5619-afb3-d2c5cf09126a | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
206f6b09-3d2d-529e-902d-cfe0d5a2c7f3 | note | ○ Irregularities in alignment = 5mm in 3m
0098e10f-1839-552d-a5cf-9d98bc72ed05 | note | ○ Section dimensions = ±5mm
ac214638-57a9-52c9-9b06-45f3778b5adb | note | ○ Section dimensions (less than 25mm) = ±3mm
1bc9c388-c920-5a69-916e-b596e67a1080 | note | ○ Width of pavement = -5mm, +15mm
874b41b4-d88f-56ca-a0cd-68ba6474ea47 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
d73e2ea5-400b-5a1f-8d4f-795f3384e04e | note | ○ Attach: Survey As-builts / Survey Report
c40556f3-cf08-52a4-a3e7-6ae23dd8c11b | note | METHOD: Document Review
b5e24128-1792-58da-a51a-abffeacb8a24 | note | FREQUENCY: Where applicable, each lot
abc47c3a-2b87-5d0a-8f59-5fca025f2e0e | note | CATEGORY: IP
992d5ba7-baa7-538b-8a31-8bfd6b25b52b | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
fffe3e89-def4-5f45-bc91-b22d8f7cfee6 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.8 Non-conformance Report (NCR) Closure
b242ca58-4d21-58fd-b924-9d8aefd93200 | note | REFERENCE: MRPA Quality Management Plan
b8aeef17-0418-58e0-a265-a9eaf455387f | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
513b0874-a950-53ca-aa84-78a30c0e309f | note | METHOD: Document Review
3d4e5d14-c24f-51e4-85a4-20f18d11e02e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
e4151f54-e11f-5e38-9bfe-df46fdf73dbf | note | CATEGORY: HP*
64b675dc-8a3d-57ef-82eb-eb8cdbdbe59f | note | RESPONSIBILITY: SE/PE/SPE
2fe97269-3026-5c48-b6d1-54e11d3e4911 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | Final Inspection
d88d1a44-b725-5b35-9275-707ed65e8a0a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0023c700-f736-5fec-bb31-3bedd2fea41b | textbox | Name:
aeaa0c0d-6ae0-5ab0-ac6a-2f2b7b36244b | textbox | Position:
2b5647ed-058f-569c-9040-64d88ab94934 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-137-STR-PSDS-Structural concrete Rev 1 | itp | ITP-137-STR-PSDS-Structural concrete |  | 5c887c79-71db-44d0-9f72-34979af99431
| section | Referenced Documentation
| checkpoint | Referenced Documentation
48a37867-445e-5f61-8615-7bb3be5ffd64 | note | Document Title: ITP-137-STR-PSDS-Structural Concrete
3e1a2a50-7465-590d-b712-df4c3693f804 | note | ITP Description: Structural Concrete
4ad6017e-b824-5ca7-8b57-dc45dd858856 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
da5e4b15-08d0-5f20-b689-eb1b6da65f0f | note | Discipline (e.g. CIV/STR/RAIL): 137-STR-PSDS
9b7935f0-eac1-5df5-8ea8-3e6bce3f58e9 | note | Revision Number: 0
04cef9f9-6c4c-5538-9b75-8bbe410fd3ab | note | Revision Date: 22/02/2024
bceb11ff-03a1-5604-b6b9-922dea858964 | note | ITP created by: Mathew Velcek
6128d632-32bb-51c1-b160-6469a23bc4bd | note | ITP approved for use by: Victor Mira
c6221acb-23b5-5922-9770-34adfff5d9b3 | note | 1.1 Non Dependent
367c6d38-1382-5df2-a7f9-10aabb71ba4c | note | Reference: VicRoads Section 602 October 2007
ec8e537c-5e0d-58e8-b11a-a54bd94dc9e5 | note | 1.2 Non Dependent
a6b17e13-c81d-533c-8a14-9000c04db92a | note | Reference: VicRoads Section 610 February 2020
0171e6f5-ca1c-5cce-b88e-f79bdcadef5f | note | 1.3 Non Dependent
d9a771ed-617b-50a9-b52f-d679b31399c2 | note | Reference: VicRoads Section 611 November 2018
c8c2b75a-a301-5ed3-8999-b5f31a22b77b | note | 1.4 Non Dependent
e6ab4ef5-9ee6-546e-83d0-9f0a8d1d8afa | note | Reference: VicRoads Section 614 June 2017
9c0570a3-4094-55e8-b297-727e1e6118e4 | note | 1.5 Non Dependent
309a84ce-c6f5-5528-a186-71ec168701e9 | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
78b20ae1-63a5-540a-95ca-d93780af0afb | note | REFERENCE: 610.07, Table 610.071 IFC Drawings
b3e3dc01-92b5-59c3-b308-a9fe88410ea2 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
34569e10-65c8-55ba-a75d-a9a2f6d3a93c | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
2aa071fa-8316-5f22-80ba-0bc17f9fabe0 | textbox | Enter: Teambinder Material Approval number
c2c3b474-831d-55a4-9be8-4f55e8f7010a | note | METHOD: Document Review
58814631-4da8-5508-9b28-5f771b623ebc | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
293b4e9f-2954-5e0d-9e9b-093490464704 | note | CATEGORY: HP
dee4be3f-1883-5471-928b-8f304d885cd6 | note | RESPONSIBILITY: Nominated Authority
c4815363-6c36-5768-ace5-1117bb65e3a5 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
006676c1-6d90-5882-ad29-f8ac97161663 | note | REFERENCE: 611.05 (a)
2bdfb7e3-c53f-53dc-b50c-f1f95537b4af | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
0f657101-e8fe-506d-81fa-c7a10952e5ac | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
ff9c9a72-fc0c-5fbe-b923-14189cbc5eca | textbox | Enter: Teambinder Material Approval number
4ed7bb95-821d-50c5-989f-f2f50ebcf908 | note | METHOD: Document Review
894ca53d-c229-53c6-aa32-ac8c3001a18c | note | FREQUENCY: Once for each supplier, 14 days of award of contract
cce69068-04d3-5f71-b6ac-bf65d8c14b66 | note | CATEGORY: HP
e9add410-3ad3-5893-9ee8-7c89c239d5fd | note | RESPONSIBILITY: Nominated Authority
9b91c09b-f2da-5304-8416-9d49cb97fc7b | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
50bf5c07-262d-5245-8c53-d9d5c0cbee90 | note | REFERENCE: 610.26 (a)
1ffb80ae-ad23-58c8-83c4-faff39bb0c19 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
b62dcc87-c546-523e-bffa-1d7d1646cbb8 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
47c11224-1c6c-5a76-8f01-187cf0c2d788 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
7dd9c8d4-48fa-5428-8a7a-9deb5755fa93 | textbox | Enter: Teambinder Material Approval number
50ae08a6-2fff-5cef-a7b7-47455d574c19 | note | METHOD: Document Review
062c23e0-1ecb-5490-ac58-eeb561a56bb1 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
6ee2660c-387a-525c-b8f5-f6414b34a1ad | note | CATEGORY: HP
f4472654-7567-5fc4-9d86-8a436717695c | note | RESPONSIBILITY: Nominated Authority
80f80b76-c015-54dd-bb22-4a7a599ae0fb | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
95c17965-9db8-538e-8f49-68d42fb6d14d | note | REFERENCE: 610.17 (f)
b83ac77e-27b6-5e45-8796-0f3c75d79d63 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
6d0579e1-4203-5ef1-a3b4-65dfb12fd080 | textbox | Enter: Teambinder Material Approval number
39cd6bad-d690-5fe9-8870-83d0a2567776 | note | METHOD: Document Review
92bbe2a4-eff2-5c07-b389-3f476f867653 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
be914ab1-1c99-5ba7-91f4-bd1035b9a27c | note | CATEGORY: HP
dc46b5b7-70db-5a04-b01a-05b8b3b9a7dd | note | RESPONSIBILITY: Nominated Authority
b99fb48c-a91c-5151-a70a-c5d02647c6a5 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
a35c12df-3a67-5b21-abb9-7d7f7ad489af | note | REFERENCE: 610.23 (d)
7e118efe-c360-5e33-a996-cd749f6a06e9 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
91d05db3-71a4-5052-9e92-2f2ef5d6b547 | textbox | Enter: Teambinder Material Approval number
2d6cea99-4be0-5a14-9423-ec6922b6d569 | note | METHOD: Document Review
e9d41fd5-1e2e-5e82-9571-676e3ca646fc | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
fb269b69-89fa-58f8-82df-56c1c44a2ffe | note | CATEGORY: HP
c78e8f86-a35f-5883-a62b-f45e9fb9a465 | note | RESPONSIBILITY: Nominated Authority
7db5aee7-d4a8-54a3-b361-b584d0663ba8 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
6e91258a-4dfd-5a1d-bb44-67916855fc72 | note | REFERENCE: 610.18 (a) (i)
380a378e-1be3-5804-a9f8-3b62ffc77d7d | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
9332ebfa-7b4d-51b4-99ef-5664d037f721 | textbox | Enter: Teambinder Approval number
72214396-ae29-521b-a280-5b8d7e4fba8c | note | METHOD: Document Review
c95a071a-34b0-5891-9888-f92afd9ed971 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
65cabe31-2124-590b-b099-2364615199da | note | CATEGORY: HP
208d22ef-d923-529a-8771-74991bc57b73 | note | RESPONSIBILITY: Nominated Authority
f2ed0892-adb6-54ea-994f-a54a4325576f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete Sampling and Testing Procedure
3ca0ab6b-293b-5875-a6c2-ac29350403cd | note | REFERENCE: 610.18 (a) (v)
4f8ae491-3a7f-5ed6-ae02-b852e563d2cd | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
4b83c0f8-9dc8-51e1-8e41-73193d6abfe7 | textbox | Enter: Teambinder Approval number
7bb86482-f46d-51b7-81ed-1801bab70d39 | note | METHOD: Document Review
edc29478-b629-5233-aab8-d670000a45be | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
01df8587-9d39-5aff-9746-ec3d63c8c274 | note | CATEGORY: HP
58b4c558-e6be-5589-b19c-2b36b7ee19ee | note | RESPONSIBILITY: Nominated Authority
021441d4-10ef-513a-ad42-f0282c169643 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
b0b017c2-7bc6-5cf7-aae5-850fe5d6a087 | note | REFERENCE: 610.18 (a) (iv)
2247496b-728a-5e63-b6e2-7ece3e239eda | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
c929b29f-9529-57e6-88e2-d80cf0dbd8dd | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
2f4c9ad0-f99a-56f6-b85d-0f0ae2e44a27 | textbox | Enter: Teambinder Approval number
e2786f67-4339-51ac-a0dc-f83e69cf132d | note | METHOD: Document Review
d74aa5f4-e4b1-54c8-99b0-6809d4c8d7ef | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
2f392c6a-ca44-5be2-9fc7-13a0e3a4ffd0 | note | CATEGORY: HP
09497351-9563-5325-b4b1-d5cc18f0d537 | note | RESPONSIBILITY: Nominated Authority
e1542e51-f1c6-5ca0-b485-7b4ede298d15 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
3007903f-94ce-5c94-b5d1-45447afba44a | note | REFERENCE: 610.17 (a)
2fa3e953-83ed-5b5d-a921-b2d09aecf7b5 | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
dd2de02b-2ad6-5b8a-8695-6ee659414ef7 | textbox | Enter: Teambinder Approval number
6c236726-e03a-5412-ae42-ac64df9a69c1 | note | METHOD: Document Review
cb81c107-675f-5cd3-89ff-1fc98ba3d7e6 | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
fd2c61a3-a394-5092-ba4b-79eae22315b6 | note | CATEGORY: HP
f1b5781a-4d28-51dd-85db-fb900dff069e | note | RESPONSIBILITY: Nominated Authority
d82bf127-6ede-5acf-acf9-d108c35329b4 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
e2e5e209-7c63-5698-909e-ec432f96ec7c | note | REFERENCE: 610.23 (a)
5e19b961-cf55-5c0a-8be7-8a08c942eb3f | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
8d49a449-64c3-5d3e-8876-da9d6e178f23 | textbox | Enter: Teambinder Approval number
c6ece6fe-af68-5175-8351-f9b2b2d5fbc3 | note | METHOD: Document Review
e5efc0d4-6785-5d9e-959d-d86bde933873 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
ee60cd66-6889-540f-aac3-f9f2ad36e523 | note | CATEGORY: HP
32b31899-a6c7-50b2-93b4-558a775fcb55 | note | RESPONSIBILITY: Nominated Authority
8824c402-f80f-5f6e-b9bc-ff001cc7a5ac | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.6 Concrete Drilling Procedure
7040c9e3-da83-59a7-8803-69428fd2dd9a | note | REFERENCE: 610.46
0f2e4719-f0b1-502a-85f1-5ebd121f4f78 | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
faf72bac-9625-589a-bebb-aa273975121a | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
b9fea75a-e0ff-5dad-aac4-f5a7b3825dd2 | textbox | Enter: Teambinder Approval number
8b6e4626-5086-55f3-ab45-8ec7acb6cb6e | note | METHOD: Document Review
e29fccc4-994c-58e3-bee2-7719acd3e8a0 | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
9549c89f-49bc-5042-99a2-cdf74c008aba | note | CATEGORY: HP
321ab5cd-4b90-56eb-970f-33216ab86ad8 | note | RESPONSIBILITY: Nominated Authority
eb339755-3c96-5f90-a245-938d14b3ead6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Temprature difference measuring-Calibration
11329de4-6dbb-5515-9c53-c2bd85618b81 | note | REFERENCE: MRPA Quality Management Plan
3a678f47-e8de-57af-9db5-31d0fda83d5c | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
0cd25656-a09a-593e-bf85-346ce734702c | note | Attach: Calibration certificate
4206ef2a-67f5-5b5f-b6a5-9875ed465b37 | note | METHOD: Document review
4557a4a4-2877-52b6-9215-ff999f8759cd | note | FREQUENCY: Where applicable
53d3c6a6-3f06-534c-a410-becee309de24 | note | CATEGORY: HP*
62df030e-eec9-56f2-bea7-aecd8dd1f573 | note | RESPONSIBILITY: PE
8af81bf4-6517-5261-b0ee-f1fc1922a403 | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
f762b9fb-09ed-5015-a996-83f8b41818b6 | note | REFERENCE: MRPA Quality Management Plan
2f0b823f-706d-54a6-a469-cc71c5fd14ca | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
09aa2e01-3f49-5476-8be5-5c1ee18a9280 | note | METHOD: Document Review
00a6fdf2-b527-5ff6-9cbe-2948c86cff82 | note | FREQUENCY: Prior to starting Works and at regular intervals
8ffd8aff-526e-5d10-aa7b-5e56e6263de1 | note | CATEGORY: HP*
916d2d31-b0d9-56c9-b552-c70a3df69375 | note | RESPONSIBILITY: All
9a2ddfb5-e823-5b1d-bd71-71d08bd84ab9 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.2 Survey Set-out
a882ab04-5cf2-56fc-8ec3-84e6e2b21867 | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472
5b238228-4397-5184-a664-8d77f809e65c | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
edb8aec7-7fff-5d81-95b3-2f393f99b022 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
41368af7-cb50-5bde-a382-801cacbd28c0 | note | METHOD: Measure, Visual
f85aee46-0dd2-57f5-984e-aa0b3e384323 | note | FREQUENCY: Each element
f8c2e71a-cb5e-58fa-8b71-8d7d6c874409 | note | CATEGORY: IP
bf4c05c3-3c70-53cc-bc22-f8764a408590 | note | RESPONSIBILITY: Surveyor, SE/PE
8bb963cb-772c-5208-98d7-3566970f0910 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.3 Excavation support
ab85e0f8-7f12-5610-ba4b-9869af0b365d | note | REFERENCE: 602.02
4a893a43-5c89-5405-ba32-f72beafcfee0 | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
74144183-36e3-554a-b1eb-be594a5aef78 | textbox | Enter: Teambinder Approval number
2bcaa7c3-6c8b-5421-8de4-05bf5b2ea7f3 | note | METHOD: Document Review
d9613f4a-fe1c-5cbb-b34c-ef2a920957d3 | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
00a2925a-b265-579c-b3c4-aa2b56d99a82 | note | CATEGORY: WP
93d20014-ded8-5e9f-8cf4-5b04a7440bc7 | note | RESPONSIBILITY: SE/PE/SPE
489a925a-9e5d-5b62-a808-73942f4405a2 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| checkpoint | 4.4 Excavation Inspection
499b4fb6-8ee8-5263-aa60-f179ca95f779 | note | REFERENCE: 602.03
379dfe3a-0f95-56e5-b7c8-a1f883c13634 | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
bf8cf939-956c-51aa-8a07-669cf707468a | note | METHOD: Visual
8cd5bd33-2362-5463-ad9f-73b031e1d867 | note | FREQUENCY: Where applicable, prior to placing blinding concrete
56b9d25f-d216-5277-8708-4a8dfb1d3665 | note | CATEGORY: HP
86d67415-d3f6-5f36-949b-27619a1b4427 | note | RESPONSIBILITY: Nominated Authority
c80e8954-e62c-59d3-ab1d-285230afa21f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Formwork Design and Construction
ac411c8b-f6ae-5e94-b314-fb85b2033464 | note | REFERENCE: IFC Drawings
0c403a63-15dd-5a52-b2f4-089e10d0eb0c | note | ○ 614.04
69a03307-46fc-5f6c-82e6-08241afb7eea | note | ○ 614.05
a4b285ea-7e9f-5996-abf6-1b0f0211ee4d | note | ○ 614.06
f1f7ab10-1112-5ec3-8bdc-a73c784ac6b3 | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
32229d91-390b-5fbe-8b95-91af42a0225b | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
50955bea-238c-5f69-b870-ec78d9ae82fa | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
4f93f5d5-f63c-545c-962c-6bf5cf6e8ddd | note | METHOD: Document Review, Visual, Measure
d265eff4-f2aa-5229-b689-ad9e5b4e09e6 | note | FREQUENCY: Each type of element
8a15be88-8dfc-534b-9ad4-b0b975208522 | note | CATEGORY: IP
382623e6-3ecb-5ae5-accf-ba004d5ae140 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
6d007b48-369e-5c9d-adf8-51a17ce9da40 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
bb84e584-20ff-5e97-9ceb-10e3a16210ea | note | REFERENCE: 614.08
010ab915-f7d2-5390-8c31-2d1f72916e89 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
95e09125-41ae-536b-ab81-6e20f444002c | note | ○ Walls with heights greater than 2.0 metres
7d24156e-9a81-5231-9c9c-fca928158f42 | note | ○ Any member for which self-compacting concrete is proposed.
1e18dff5-32cd-5c24-9aa0-1fab4fe62db7 | note | Attach: Attachment A
fb737f20-a908-537d-8559-4e4c9e897660 | note | Attach: Attachment B
50245ed1-c42b-56ec-9709-d1b71024f7fd | note | METHOD: Document Review, Visual, Measure
4d4564de-27e5-5232-8a53-27c7e75f9bd9 | note | FREQUENCY: Each element (where greater than 2m)
19caee64-9516-5f05-8fb9-ee380241b402 | note | CATEGORY: HP
e68e5b9f-d626-5c08-817b-0c8d57c467d3 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
f1c61ce2-254a-5c47-bc97-98683c6b3a6f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
67ba62e8-23ac-58ce-8af7-27eb29844803 | note | REFERENCE: 614.08
58eded0b-92b0-586d-83a3-c01777808561 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
dff5f1aa-ccc2-59b6-8f1f-1825f9bd84fd | note | ○ Walls with heights less than 2.0 metres
a3b4ee9e-e1d2-55e8-9d8b-b8330e2a7322 | note | Attach: Attachment C
4217ad5f-7aa0-5c6c-b98e-26aaa25aef41 | note | METHOD: Document Review, Visual, Measure
7b5442fa-d8c1-5ed5-a0e8-14e660ba5707 | note | FREQUENCY: Each element (where 2m or less)
ec51b777-4a69-5ef2-a659-346370e6497c | note | CATEGORY: HP
07fe32d9-5145-564b-8701-5e0c39914a27 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
36b3c291-c4dc-5a8a-8358-0354e7767995 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Pre-pour Survey
c0e95b3b-b8c5-5de3-b80e-6666097a509e | note | REFERENCE: 610.47 (a), Table 610.472
60872c36-2d95-522a-b1de-9313d4e60b4b | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
7f9257ca-4cdb-5eb3-83b7-a8850938a796 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
cf548554-9968-537e-96f1-e11c41bb0c38 | note | METHOD: Measure, Visual
0995faf1-48d9-505c-a721-be255ee6e893 | note | FREQUENCY: Each element
ad1a2381-2a54-582c-afaa-62c0d6fe49e9 | note | CATEGORY: HP*
aa08a970-02af-5e6b-be75-2dcc025cc2b2 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
58b83609-c045-5ddb-8614-1e1ce280223d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.5 Reinforcement Placement
ef5578b8-64af-5ae3-bd02-30e7d91407ff | note | REFERENCE: IFC Drawings
5d9c0d91-989b-5615-828b-1c3c85a8f315 | note | ○ 611.06
1a46d952-0323-5ef1-bedf-5ba38add2880 | note | ○ 611.09
02fd0ff4-2d66-5914-9ed2-06b5c3a8be8b | note | ○ 611.10
32e27238-df5b-506c-b980-c72fa6bea5ad | note | ○ 611.11
774b9341-5480-545e-a756-0d447352ed94 | note | ○ 611.12
d7a87f0b-0fb3-59b6-8fdf-b3ebb22328c8 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
c698252b-5fb3-5d13-b19d-433b7d168906 | note | ○ Projecting reinforcement is the correct length and location.
94729b30-b4e7-59b8-8ba4-a61db4cb872e | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
7761c8b0-b573-5382-818f-71d7c6ff6214 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
6d36785a-addd-5e93-aeeb-b8522b1444b1 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
8d5a274a-71c6-5aa2-ad33-becf363a358a | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
71c5d3f6-6c60-5410-bae3-74774684762f | note | METHOD: Measure, Visual
a8f6efeb-4c71-5891-9ac7-65b45c878701 | note | FREQUENCY: Each element
9c901f61-19cc-548f-b9c9-5bdf958b1a8b | note | CATEGORY: IP
796801de-2183-51cb-a67f-adcd90c8f7bc | note | RESPONSIBILITY: Foreman, SE/PE/SPE
428a1fb5-09e2-5aaf-92e4-37bd65a284b4 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.6 Cast-in Items
2e1a7f69-5e98-50a2-9fc2-431276630233 | note | REFERENCE: IFC Drawings
267d8bdd-0fa9-5317-8adc-707c705a9d00 | note | ○ 610.47 (a), Table 610.472
ab9d8e66-54f7-5fcd-9415-fb0a6bad076c | note | ○ AS3810.1 Table 3.3.6.2
0102d4b4-be91-5a8d-b21c-98c3f0f098f9 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
cc1a63e9-dd93-5400-a5b7-d095ea81446d | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
7767602e-a95f-506c-830d-d9f652e57825 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
6fb0634d-9ef1-515a-b7b1-69c94e35c6e2 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
bbf32c55-fba8-5916-85a9-c51ba6ba968f | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
acc84001-317f-528f-b4a0-2c51e8e3ef43 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
88afca78-4e57-5402-b979-36466f8924fa | note | ii. Running dimensions of a group of the above = ±6mm
f3262ae6-ebe4-5c38-8d40-df9608bb508e | note | iii. Ducts and conduit location = ±12mm
7d3dcd28-ffd6-5ac1-8caf-4201cd40d27b | note | iv. Diameter of ducts and conduits = ±3mm
d658aca6-2e9c-58a7-8c8d-5c88bfb3da95 | note | METHOD: Measure, Visual
863741d9-e7a9-5ccc-a8e3-71ed5f8a062f | note | FREQUENCY: Where applicable, each element
1dcda6fa-3bc2-5773-92ee-a8403193ec92 | note | CATEGORY: IP
b0455395-6176-5f81-9ea7-2d29fe4043ae | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8162d388-ad3c-5f45-92c4-ce9f82a27fb3 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.7 Thermal Differential Monitoring
ff17f1c5-53de-5acb-baed-27d10e60624b | note | REFERENCE: 610.22
8e5032f7-76b7-5262-9ed5-51e40d9867d7 | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
951ef0af-a58b-5ff5-90f8-b3949cb0ae8b | note | Only applicable if the element has:
f65ce090-7921-5158-a3a7-0ff8010c9b88 | note | i. the smallest sectional dimension exceeding 500mm
cc94943b-8b73-52e3-883f-b984bde69515 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
8e581407-5236-5d51-8299-ca1934cec9b4 | note | METHOD: Measure
35482c5e-d86c-51df-8ffb-5e55e35a83ed | note | FREQUENCY: Where applicable, each element
c40b6554-5683-5c85-9a7b-4d396fe93cc2 | note | CATEGORY: IP
bc1d111c-a197-5e82-b4ae-8963e9dcab81 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
dfa80979-d295-5e6d-b9f7-2406f95d0b95 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.8 Pre-pour Inspection
85cc9a72-ab42-5377-b9ce-d8fe7b8ed524 | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
32312840-9fd8-5b7b-ba7b-35a546c1a4da | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
4ba57218-d7a3-5054-8034-ef04654ddc26 | note | ○ All foreign material has been completely removed from the forms.
67a98274-f023-52b7-89cc-145270896243 | note | ATTACH: Pre-Pour Checklist
d81254ce-6f2a-5c10-b846-e015a4510973 | note | METHOD: Measure, Visual
f1ca7c07-e48b-529a-ab36-5063349dea44 | note | FREQUENCY: Each element
4d4716e8-946e-578a-8b25-741ed05bfa9f | note | CATEGORY: HP
b926ad55-eb55-5d01-956f-5eefe78cd31e | note | RESPONSIBILITY: Nominated Authority
5589f9f3-eb3a-54e3-a553-6c029fa4e116 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
52b95cf7-0ab7-5f73-950a-aca0f3832f75 | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
73d8104d-70f7-590d-9a7b-6b5b7e84355c | note | ○ 610.17
80a68c37-95c8-504d-aa00-6d408770c0dd | note | ○ 610.17 (a) & (e), Table 610.171
038b2e13-63f6-50de-a695-9e0b0c06e1d9 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
7d569abb-fd97-5370-b525-cb4ebc314a06 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
c41aeff1-b544-5391-92ce-607648826086 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
fe584986-9580-5519-ac54-ad5995ef5e00 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
0479f38e-5f5e-58ae-8e92-ccc7a04574bb | note | Record: Required information on the Concrete Pour Record.
9b5f0985-3a6d-5fbd-845c-a27fb9d41fa6 | note | METHOD: Measure, Visual
209d4a6c-bd9b-56b1-b061-b3c12eb9512f | note | FREQUENCY: Each element
6f1cbb61-3b20-5895-8ea7-3c61b0534691 | note | CATEGORY: IP
f7a830e0-39c6-5e5e-b06e-3167d4d9c2cb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8d7e553e-6fd4-50fc-bf39-36af1e1fefe0 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
70d646e3-b498-5cd5-bc84-f7f2a846bd11 | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
ea4901cc-d27b-50a5-9004-9f8acab1952f | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
bcc2fbb5-d2c1-50f4-8b20-740358ec02f7 | note | 0m³ to 10m³ = 1 sample
0638878b-45d3-507f-b3a1-5cc4d9b8bbb1 | note | 10m³ to 25m³ = 2 samples
d4beeacd-1e5d-5533-bb91-4ff8edd02bc2 | note | 25m³ to 50m³ = 3 samples
0d8a7479-8d77-5924-ab2d-8aff98b9e9a9 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
83b96ac3-5668-54dc-a893-b4f005a72328 | note | ○ For each additional 50m³ and additional sample shall be taken.
3570d254-62ac-5c37-a834-dfe932b88559 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
107c8492-a32f-59bd-9d45-bdc73a99acd1 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
1892a383-62e0-51f6-919c-c2c8ddc3b631 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
30f6a7f0-0e07-53ad-8d58-bb880714e36f | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
e4684260-8c30-5a99-9d6a-8ff058727a94 | note | Record: Required information on the Concrete Pour Record.
998ad40f-be4a-5ff6-a843-3e7db0bb8706 | note | METHOD: Test
ddbfd493-854e-50fe-aedb-3c4a00cb83e0 | note | FREQUENCY: Each element
92ef3c17-eba6-558c-9e8a-5c84de5d2396 | note | CATEGORY: IP
df307976-d854-5198-86f9-e79c1db0d1da | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
4e0b8c23-d50a-576e-b8dc-ad83fcc69229 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.11 Concrete Testing - Slump
810846ec-f736-57dc-b07c-adec3d037724 | note | REFERENCE: 610.16 (c)
9063bf9a-7da4-5e7a-961e-5cddbb4724ea | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
57c75ae2-3201-5cae-9bc8-12f66dec87c3 | note | <60mm = ±10mm
2df01aea-418e-503c-b86a-58c8a5c9448a | note | ≥60mm to ≤80mm = ±15mm
06d50ff0-dd35-5576-be99-34baf19100d7 | note | >80mm to ≤110mm = ±20mm
ba2e4b3c-2fff-5603-b7e9-24b4ba071159 | note | >110mm to ≤150mm = ±30mm
a3c9b718-4168-585a-8d61-dffbd320a4ee | note | >150mm = ±40mm
c2e69ad6-8e1e-5b3f-ad88-c218ac4ae0d5 | note | Record: Required information on the Concrete Pour Record.
3ce788c2-7fd1-5afb-8f23-0b61a865e29a | note | METHOD: Test
558f3f8c-35f0-5f32-b741-e0c2c2b32d6a | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
484e70c3-d0f9-53c9-b059-09f169faf755 | note | CATEGORY: IP
acdce024-df68-5079-97e7-0a08a7d9440a | note | RESPONSIBILITY: Concrete Tester
deadaf34-0ca7-5491-bc77-d45d0aa3bac5 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
76601688-9cb5-5901-af8f-0f6760806bd9 | note | REFERENCE: 610.13 (b)
0c709607-69f7-5169-9c79-0c64178db33f | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
dbd5fae9-a5c7-573d-abf4-cbe412c5f47a | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
3a3410cc-fc3f-594d-8609-39ed5ff32bca | note | ○ Passability = ≤10mm (aggregate height differential)
4d7dc640-fd70-5f52-9516-1aaada5e5415 | note | Record: Required information on the Concrete Pour Record.
cf3223d1-d6de-5e3f-9dbc-9bc35dc1013c | note | METHOD: Test
1296c40a-eb5c-59aa-bd39-a353e1331513 | note | FREQUENCY: Each sample of Self-compacting Concrete
0d277f46-7076-53ec-abeb-aaef5c64deaa | note | CATEGORY: IP
926a11ca-9d5c-589c-9397-6326a4f34615 | note | RESPONSIBILITY: Concrete Tester
a024f50c-abff-599d-b698-fc80eb219387 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
af1e9a61-a7c2-5193-aa2e-e59bc7200351 | note | REFERENCE: Site Sampling & Testing Procedure
a1611d2e-352c-5c82-881f-555c5cca0f37 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
df0674db-2e51-57e3-b869-0314024ecfec | note | Record: Required information on the Concrete Pour Record.
dcfead24-1b46-58b4-b467-bdf6f4ab0eed | note | METHOD: Test
b6244837-2f32-54e1-a296-6d590c8dfe04 | note | FREQUENCY: Each sample
fb1c81e6-3f94-585a-9022-18ef2f2e8be8 | note | CATEGORY: IP
2a1dd9e8-1235-5a32-ab87-3a77214b1f17 | note | RESPONSIBILITY: Concrete Tester
3a4058e4-6b59-581f-bddc-2f3960994a44 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.14 Supply & Discharge Rates
8059d8ff-a1a1-5f34-ac7a-62c86fe7fe05 | note | REFERENCE: 610.13 (a) & (f)
1f4be852-0422-52d2-93f9-72f9629d7602 | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
fc5c4470-bb23-511d-94fa-64f16738c79f | note | ○ No water is to be added once discharge commences.
f2a7e314-fe2e-5af6-9fbd-b402c66a902d | note | ○ Maximum time between batching trucks is 25 minutes.
95003075-4798-5148-9b56-d86011d09729 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
7cf401e9-12b5-58e8-996e-c3fb06e2084c | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
ebac800f-bcfc-52b7-96cf-2c8ac6b8a4c5 | note | Record: Required information on the Concrete Pour Record.
eed3b20c-198c-5545-9c31-c0c9d00d99f1 | note | METHOD: Measure, Visual
37df5e6a-3ac8-552b-9504-461e0ffd1167 | note | FREQUENCY: Each load
1ce52d0c-4c12-5a9e-885c-082c99afac13 | note | CATEGORY: IP
0b5851f0-baba-5549-ad77-d4e60fc95844 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
76d4daa3-0818-594a-bd3a-cc23e9a4be0f | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.15 Placement & Compaction
f1c8c4c5-66cf-57da-bcaa-8824cc59135b | note | REFERENCE: Placement & Compaction Work Procedure
c5d0e827-b9f2-5c68-97a0-1c0ca084704d | note | ○ 610.18 (a) & (b)
4752d7a2-95e4-575d-89ef-b15764162262 | note | ○ 610.18 (d) (i)
b164f2a9-1495-5c45-8b18-fe9c2b5af907 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
da8e1105-da60-5851-969a-daa45245457c | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
80e5f3e6-c46b-54d3-a278-80179ac7db32 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
779a4d91-52a7-5bdd-9c6d-1a92a4bb285f | note | ○ Concrete is not moved horizontally by use of vibrators.
2fd90353-de7e-5786-9c27-2ecda12b9e2f | note | ○ Adequate compaction is ensured
4764cec1-a177-5d0b-adea-6e40636b8a84 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
93acd8ca-a7f5-57e8-b8dd-0966de3e5dfd | note | ○ Concrete layers are not more than 350mm
63061f49-6a76-5934-83c0-da845ea5a35f | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
6378c2bc-1056-5847-936f-9722baa61031 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
eaf2a9a5-481b-5145-bdb7-15ceb36a035e | note | Record: Required information on the Concrete Pour Record.
7f8d66bb-b201-50b7-81d7-2a390210d2b5 | note | Attach: Concrete Pour Record
53d6010e-fb2f-51f6-b2ee-3c26ea1f7564 | note | Attach: Concrete Dockets
c33eae2d-84ce-57c4-a9bf-de65e0129cc1 | note | METHOD: Visual
0dc31f4e-463e-5960-a484-d557c16bf34f | note | FREQUENCY: Each load
1e971a9a-1f8a-5bab-b5d2-2ca494f7a8ac | note | CATEGORY: SP
ec7e949b-1580-5d70-b813-e2cce67b5ba7 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
f830f027-3133-568a-a74e-f7e0c2b356b2 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.16 Surface Finishes
7d1110bc-a7b0-5ba2-8319-16db30c25111 | note | REFERENCE: IFC Drawings 610.31, 610.20
7e7e513d-cbd6-52a8-876a-621fe3a71b57 | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
8dd2f674-4aab-5c68-80af-a467cab1cc2e | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
59d40032-476b-5944-8ccf-0a9204dffd8f | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
8fed469c-d9d3-5431-9afa-1e41c410a394 | note | METHOD: Visual
ab35bc79-4f7f-52f9-bc29-60fdc3cc9348 | note | FREQUENCY: Each element
20303314-1c06-5731-bf3e-f292d2b8c841 | note | CATEGORY: IP
1efdc7ab-16e4-5a24-a259-f8bbea025751 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
62eab483-dc86-54d8-9589-a9ccf82f3e9c | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.17 Curing
4486d3bd-8cdb-5523-901f-140ce5e5166f | note | REFERENCE: IFC Drawings 610.23 (f)
6aecdd21-1f2d-57ce-b349-c4e30de59250 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location.
42674716-18ea-5af8-9633-7087a4eead07 | note | ○ Where formwork is removed prior to the completion of the curing period, curing shall recommence within half an hour.
99d5daef-2bef-550c-b3ba-88571cef580e | note | METHOD: Visual
775df6b0-edb3-5fca-b4c4-b12d55c867a4 | note | FREQUENCY: Each element
e94d7885-a4aa-5f8d-859f-23ce907a5620 | note | CATEGORY: IP
29159a4b-2c71-57fb-b247-0317cc14e124 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
89f279da-f449-5cf0-943e-f601e85a9986 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.18 Curing after formwork removal
ce13fe23-8f87-55fe-9bbe-4bb571894fec | note | REFERENCE: IFC Drawings
e08aa63f-01c8-5bc5-93c7-b534392a342f | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
3a78fafb-a3fe-5dc4-b76d-dca1380f1306 | note | METHOD: Visual
d1d08fff-3439-5260-a2c7-da17cc87e72b | note | FREQUENCY: Each element
b1a739bc-eb16-5d55-9b09-03484d78a4ac | note | CATEGORY: IP
9f3b091e-dc40-5a53-9c58-5944f19befdb | note | RESPONSIBILITY: SE
fcb16fcf-9df9-5a28-b5a8-b96ab4aaadb3 | note | VERIFYING DOCUMENTS: Thip ITP
| section | Post-construction Activities
| checkpoint | 6.1 Thermal Differential Monitoring
ab730aa8-f165-5459-a08c-2e12eea0c4b1 | note | REFERENCE: 610.22
f513e9ed-b6f0-5ef4-af03-1cfcae2f2a4b | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
b8be5f3e-c2dc-5d02-8dc7-14c634c70727 | note | Only applicable if the element has:
291f9293-ff55-5b5e-9d92-1311aca65753 | note | i. the smallest sectional dimension exceeding 500mm
c6f57acd-78c6-5e88-8fe2-b50c158e61d3 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
c66036d5-64cb-5e95-8c1c-2d1d177c4211 | note | Attach: Thermal Monitoring Report
d56a96f4-567f-5c20-8415-1045922899d7 | note | METHOD: Document Review
b68f3020-d045-5ff7-9b70-8751ccc59370 | note | FREQUENCY: Where applicable, each element
6bb84073-3694-5e83-b3eb-3a1f0179dee6 | note | CATEGORY: IP
c41b85c6-6700-564b-ade6-17c0e6db4ec5 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
0259593c-e19b-5105-bd96-b48eef3593f2 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.2 Removal of Formwork
8a6273c5-41e1-57cb-bab9-593bb21b5c4f | note | REFERENCE: 610.25
0a178370-cedd-518c-8601-c6279886cea3 | note | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in Table 610.251 have elapsed, after completion of the placing of concrete.
8d9545bb-4f7c-51f6-85c4-e0270093566c | note | METHOD: Document Review
d5bdceec-4d9c-556b-aaef-da12a1b62bed | note | FREQUENCY: Where applicable, each element
f8d12fa1-3ff5-5974-a53b-667e1a2ee77e | note | CATEGORY: IP
54758895-9010-5eff-91a4-e32bab307e2a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8e8ee779-c317-5b43-88dd-cfea7784b0cd | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.3 Surface Inspection - Cracks
1cbc80bf-7ea8-5fef-86a2-2a88d1e888eb | note | REFERENCE: 610.24
9e2b5f6e-77d6-5ad3-9057-cb442ba84d8d | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
8ae3a60c-f7e2-510a-a290-a638fd4ff423 | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
a0b44f11-396b-55c5-9c00-a87f85645831 | note | METHOD: Visual, Measure
e1b28460-87c2-56a2-82c5-cb311e5bf7bb | note | FREQUENCY: Each element
28e8ebf7-ac95-593c-9882-3080ae81b528 | note | CATEGORY: IP
8e67cb79-e224-5f98-9f0d-3f2ca5bf6ef5 | note | RESPONSIBILITY: SE/PE/SPE
3836baa7-3216-58f3-ac42-86ddd7f8ddf9 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.4 Surface Inspection - Surface Finish
2b7373f3-8e1f-50f8-8bdf-ea16278086d5 | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
4d1e63b0-9ef7-58c8-8c09-6b15be52c0d1 | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
59ba086d-77c4-5e30-a645-36c2eacad78a | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
f3b1f179-38e9-5b93-a63a-368fae846c78 | note | METHOD: Visual
83205327-b449-5e3a-af1d-6cd73bcff0d3 | note | FREQUENCY: Each element
9bdd523c-cfbe-5335-9fb0-20332a047a10 | note | CATEGORY: IP
5d9e2b74-dd81-527c-9e08-82f7ffb2d51a | note | RESPONSIBILITY: SE/PE/SPE
fb7ce9ef-f49c-589e-ad24-4448559e7bf0 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.5 Measurement of Concrete Cover
548e6cae-749e-59a4-8d6a-9f4f9ccfd948 | note | REFERENCE: 610.34
e2e18b75-ee33-53d8-88c1-421a86908604 | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
a371d0ab-af59-5a37-b071-a3bc538d9e80 | note | ○ Minimum 10 no. measurements recorded in each area.
14a571da-e2bd-58c1-b063-01877ef9539b | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
0885a184-c3e7-53d0-865a-fd2f347bdcab | note | Attach: Covermeter Check Record
c9ab0d13-fb7a-5f30-9f81-e48bcb3aab11 | note | METHOD: Measure
e1fd2d18-14e2-586b-9162-75c9106b51e2 | note | FREQUENCY: Each element
455b73ec-10ab-5d48-a45d-5221cf1041dc | note | CATEGORY: IP
2e5b1788-b421-512f-9ecf-fb2f50f95e6d | note | RESPONSIBILITY: SE/PE/SPE
08372b93-19be-5b1f-8c07-7578a5bd5d30 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
fe28427c-bf52-511d-be33-209f68ba1121 | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
dd2b8086-1bb9-5d0b-ba83-7f324fdb850a | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
e04606cd-313d-54a6-b767-8a5bc65bdb8f | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
afbe2790-41f2-507a-8994-18dcc1c6f2fd | note | Attach: Concrete Test Results or Maturity Test Results
3337681d-1307-5f45-bbfd-5030cfae2428 | note | METHOD: Document Review
29f96889-f5d4-52b9-aff6-db98a3438304 | note | FREQUENCY: Where applicable, each substructure element
601e13bd-8464-5419-aa93-43e649a12bcc | note | CATEGORY: SP
9d74fbd6-aa20-5dbd-9597-012853d94e46 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
4525b4bc-38a1-5937-8aaf-19be12768ad9 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.7 Compressive Strength Test Results
6e085b77-bbf8-513a-a0f1-bbeb64dcd016 | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
11c6caba-ba1e-5db5-ae9d-bc6120fa31b1 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
de469aef-f083-5196-9c46-ec6c5d71c995 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
1a3351bd-cc6f-5241-b6a6-aedcc0912c22 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
6eee60be-0574-5c1c-b330-73c62a193087 | note | Attach: Compressive Strength Test Results
f98e2d12-b874-5363-b2b5-901e76c81380 | note | METHOD: Document Review
9e5896d8-0643-58fc-afbb-93c38b4c64bd | note | FREQUENCY: Each cylinder
f06d4bd3-480a-562c-86cc-3311ca43424d | note | CATEGORY: IP
c46cb896-dc35-5396-91d9-696b3223427e | note | RESPONSIBILITY: SE/PE/SPE
50dd208b-83c1-5aec-9e9f-f67a1e753e9d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.8 As-built Survey
7bb5b4d0-cfff-5c77-8f09-c415e8620e4c | note | REFERENCE: IFC Drawings 610.47, Table 610.472
3bcf07ad-e62c-5d08-9c00-1c722fe20051 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
eb4582c1-f6bc-5093-bc5c-baf6319caae9 | note | Attach: Survey As-builts / Survey Report
86033720-5c45-5269-b6cb-a2a53d421bfb | note | METHOD: Document Review
432d7f3e-c2c9-5dd1-8565-3c36485b651a | note | FREQUENCY: Each element
2a30ff7f-c114-59c2-b7c6-8c4159852975 | note | CATEGORY: IP
36edd975-3c7f-5bb8-b37d-bc838cc78091 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
5da77fd7-da47-5fad-9cea-d83e0627b9e9 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
1c0db92e-9a55-515a-b2b4-cf8440ef0db0 | note | REFERENCE: MRPA Quality Management Plan
e72564f1-7470-5399-9060-9633a8718f5f | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
b6cf15b2-d66b-50fd-aa81-1129f95dd684 | note | METHOD: Document Review
922836fa-f05d-50d3-aac6-e282888b7f9b | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
576431d3-e8ec-5bbd-b830-74836cae8543 | note | CATEGORY: HP*
e617ec60-067b-5302-a623-e0fd26e531ef | note | RESPONSIBILITY: SE/PE/SPE
c6e1ccf3-3dba-5ae4-ac8b-568a422f625d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | Final Inspection
2b043501-4e61-52cf-b8df-d6a6e661afa7 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
4655f156-9b90-5347-aa36-a8b0920b10d9 | textbox | Name:
9dbcbd76-7179-5721-8aab-5cdc2aff3463 | textbox | Position:
bb085d81-3d0e-591a-81cb-c236afbb4279 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-150-CIV-PSDS-Rock Beaching Rev 0 | itp | ITP-150-CIV-PSDS-Rock Beaching |  | fa2fca32-3d04-45fd-ad76-547a873af362
| section | Referenced Documentation
| checkpoint | Referenced Documentation
97c171ff-b0bc-5463-b2ea-7cf740150481 | note | Document Title: ITP-150-CIV-PSDS-Rock Beaching
6c79660e-e5a9-5161-adb9-b750783238e0 | note | ITP Description: PSDS-Rock Beaching
34ab9688-36fb-50fa-94ce-4854791bb88d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
5f0734e5-120b-5ea2-9744-20478d754e99 | note | Discipline (e.g. CIV/STR/RAIL): 150-CIV
e1cfbde8-1afa-596d-bcfe-8fb48f99711a | note | Revision Number: 0
2d0f7442-d37a-5dab-8c11-1205276b51b9 | note | Revision Date: 17/04/2024
6bac6444-389e-57e2-a207-30a7db135d7b | note | ITP created by: Jonathan Kogan
953facf1-1d6e-5d68-aae6-7a2ac69c3b0c | note | ITP approved for use by: Victor Mira
5bcb702f-993f-51c0-a7d0-8837f62a05c6 | note | 1.1 VicRoads Specification and Melbourne Water approval
6869071e-04ed-5ff5-9ea3-0436bcaaf131 | note | Reference: VicRoads Section 713 April 2017
| section | Preliminaries - Materials
| checkpoint | 2.1 Beaching Material
8b5c7718-2b05-5a2d-9ec2-9db883d4554d | note | REFERENCE: 713.03 Section 713.03(a) IFC Drawings MRP-091-C-BEC-DRG-00-DNG-CBR-5613
a00548d4-07a2-5642-9dca-462fd1018bc3 | note | ACCEPTANCE CRITERIA: All rock beaching materials shall:
9f5a1492-a3ad-568f-99aa-331ad82b37a8 | note | ○ comply with the material requirements for ‘sound’ rock in Section 801 and
6037c6fe-f384-5002-9a8e-5e8788ac6331 | note | ○ the Los Angeles Value (LAV) requirements of Table 801.033. and
ec5e2698-2e95-53a4-b6c0-fbc78173441f | note | ○ The rock shall have a minimum apparent particle density of 2.5 t/m3 and
8b6e0fcc-f781-519f-b5fe-58a504121212 | note | ○ the rock beaching shall have a minimum wet strength of 100 kN and a wet/dry strength variation not exceeding 45%
b0722ccb-3717-5581-95c0-f1fa2bd2d6ae | note | ○ The rock beaching material shall be Type 5 - Melbourne Water waterway beaching and comply with criteria set out in IFC Drawings
9220ab14-80e7-573f-9d0b-b0c7304ae95d | textbox | Enter: Teambinder Material Approval number
7d089f23-6891-5fd3-9c81-6fb4325c6603 | note | METHOD: Document Review
63462866-8fdf-52a7-ba75-7694aee1fe50 | note | FREQUENCY: Prior to each use unless previously approved
cbf55b86-086e-519d-a061-c30b1016a8eb | note | CATEGORY: HP
0118fb45-d28a-5546-aa69-69fcf4ba180e | note | RESPONSIBILITY: Nominated Authority
a9645611-7107-5d70-9df5-392f5b37c788 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
89930ddf-85ec-5f20-a8b0-d14d8df5aa5d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bedding Material
84d191c2-516f-5d74-b411-b551d9bc7007 | note | REFERENCE: 713.03 Section 713.03(b)
47c42fc2-6397-5a9c-9011-9dce61617a78 | note | ACCEPTANCE CRITERIA: The rock used for the granular filter layer is to be well graded and where a granular bedding is required, limited to 0-100 mm in size.
985b0dad-9e59-54aa-ad14-41a83d3ecf7a | textbox | Enter: Teambinder Material Approval number
f13f03f4-d4f5-5f06-96dd-25ae475ade40 | note | METHOD: Document Review
f6804f05-b6a3-51d6-922c-ae292377e69c | note | FREQUENCY: Prior to each use unless previously approved
aafbc735-5558-5365-a128-620ff5f41f23 | note | CATEGORY: HP
640938fb-daf8-5471-9176-40668625f62e | note | RESPONSIBILITY: Nominated Authority
f03d2f0e-28dd-5d36-b67e-7d5797109772 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
8023405f-ecac-5ae9-bc86-7abd6e0b84e5 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Beaching Placement Approval
64526871-1ee4-575f-ac04-02f37c0e115f | note | REFERENCE: 713.05 Sect (a)
a6b1ea13-2621-5958-bac2-7d843f1663ad | note | ACCEPTANCE CRITERIA: Prior to commencement of any work where placement of rock beaching is proposed, a detailed job safety assessment shall be undertaken by a suitably qualified and experienced professional and a suitable Safe Work Method Statement developed to cover all necessary elements.
cb386dce-c168-5111-b2a9-79be35b81df2 | note | ○ The completed job safety assessment and the Safe Work Method Statement shall be submitted to the Superintendent for review.
4c151d07-97d0-5d22-9dc4-049ce76e6da3 | note | METHOD: Document Review
2fa31661-5d1c-50f3-a09a-de726cd7be82 | note | FREQUENCY: Each Lot
68e4353b-132d-5120-b570-58443ce33b0e | note | CATEGORY: IP
0b847778-8db6-53b7-9b79-7f1426475853 | note | RESPONSIBILITY: Site Safety manager
4f7b6a0f-3ad5-5eaa-8802-164cdd0e6386 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9d87bca7-a8df-5764-9837-7e824838e8c5 | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
6398888b-1b52-57aa-9635-f013c2cde712 | note | REFERENCE: MRPA Quality Management Plan
eb60b755-a227-544a-8855-7b88ad4a8a63 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
881bd5ef-23b0-56d4-9521-eb9e032316ff | note | METHOD: Document Review
373eaa6e-b9ad-52b2-84f7-819b65b0f54a | note | FREQUENCY: Prior to starting Works and at regular intervals
be9004a0-43f7-5667-bd0b-c77b4c757085 | note | CATEGORY: HP*
25282e1c-5d00-5da6-a53b-cf6528139b31 | note | RESPONSIBILITY: All
c4fea0b5-910d-54eb-a6b0-f22434b627b9 | note | VERIFYING DOCUMENTS: This ITP
853eaa51-160a-5bf2-b75b-e37565e58bad | date | Date Completed:
| checkpoint | 4.2 Confirmation of rock sizing
464293af-3d32-55bc-802f-cc86115d96c7 | note | REFERENCE: Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
ffe37309-2ec2-5a87-8669-3e9f62ac76b4 | note | ACCEPTANCE CRITERIA: Ensure rocks being used are Type 5 with a minimum D50 of 400mm.
80f39e37-1a5f-537b-981e-8b8c794161b1 | note | METHOD: Document Review, Measure
6309681d-fcd9-5539-aaf9-0609b8e5580e | note | FREQUENCY: Each Lot
3ca57863-f42b-5c07-bef6-f92d41bbfbee | note | CATEGORY: IP
fa5f561a-4a2a-577e-b395-4e6ba6acd169 | note | RESPONSIBILITY: SE/Supervisor
7f2a183c-9310-536b-b38d-3f7030f822e3 | note | VERIFYING DOCUMENTS: Delivery Dockets and test reports to be attached to this ITP
519fe8d4-2b98-50cb-a342-ade957198740 | date | Date Completed:
| checkpoint | 4.3 Confirmation of rock sizing
fb1cee92-05e6-5920-ae0f-b6e663ffcb9d | note | REFERENCE: Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
0f6a3fc3-1219-5d72-bf67-eb940360dbcb | note | ACCEPTANCE CRITERIA: Toe rocks to be Type 5 with a 1m minimum diameter.
8f50521e-ad6a-5d20-863d-0c48176493d9 | note | METHOD: Measure
e0042c95-716c-5dad-909b-ec232760078b | note | FREQUENCY: Each Lot
d9f85300-5c9b-5843-b9c4-159937be396b | note | CATEGORY: IP
629c364c-fe32-53d0-b48d-06dc0410ac63 | note | RESPONSIBILITY: SE/Supervisor
b619ffec-d4f6-5304-8628-642b36ab4aa5 | note | VERIFYING DOCUMENTS: Delivery Dockets and test reports to be attached to this ITP
1e10ad13-c643-51dc-b2bb-1277f977f274 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Preparation of Underlying Surface
fa4d5126-da19-503c-be51-2eab199b9b54 | note | REFERENCE: 713.04
09d8a811-2441-56f9-8197-298cfd92a1bb | note | ACCEPTANCE CRITERIA: Areas on which beaching is to be placed shall be compacted and trimmed as required to provide a finished surface level of beaching in accordance with the drawings. Any scours or hollows in the surface shall be filled with compacted Class 4 crushed rock.
310753d1-aecf-5102-8e2d-69d5216b61d6 | note | ○ Trimmed material shall be removed from the site.
05bee130-dfd7-54f7-b65c-3b48b518195b | note | ○ For treatment of scours and hollows on or near Melbourne Water assets, contact Melbourne Water for the necessary treatment.
d1cc48c5-c207-588c-b911-23e1042daee4 | note | METHOD: Visual
b061350c-e543-5ad4-aab5-248cfafd7968 | note | FREQUENCY: Each Lot
ac1f0362-ce45-5fa7-b2b2-6f130d6d1276 | note | CATEGORY: IP
bdc394a3-f618-5dfe-b5d9-0928f2556da1 | note | RESPONSIBILITY: SE/Supervisor
881c84d9-167e-56d7-8fd7-b2fb07089bc6 | note | VERIFYING DOCUMENTS: This ITP
da5d6cab-a261-5e41-8ced-f35ea9cb7519 | date | Date Completed:
| checkpoint | 5.2 Toe Rock embedment
ac63fcb5-9522-52f0-866d-8ab67a34ea55 | note | REFERENCE: 713.07 Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
f7ff6d7f-61f0-515c-86f3-97bc151678b7 | note | ACCEPTANCE CRITERIA: Perimeter and toe edge rocks shall be trenched into in situ ground before bedding placement. Such rocks shall have 2/3 of the rock diameter embedded.
55ecf48b-64c3-5d88-9333-da9317ceeaec | note | METHOD: Visual, Measure
c51f1391-6dc5-5e73-8aba-d15e8e61137a | note | FREQUENCY: Each Lot
fc275579-ac38-5902-999f-70abfdf97b51 | note | CATEGORY: IP
8a6d1fc8-67c1-595f-a98b-4097757e0c6a | note | RESPONSIBILITY: SE/Supervisor
0d3d586a-4417-57b7-92af-956bd856df5f | note | VERIFYING DOCUMENTS: This ITP
c23c353a-8144-564a-8d99-06ca6bb39615 | date | Date Completed:
| checkpoint | 5.3 Bedding Placement
b239c769-08b0-5aa6-a126-bd6b69dbf87b | note | REFERENCE: 713.03 (b) IFC (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
9f4df4dd-2349-55e5-8b92-81914ca5d9bb | note | ACCEPTANCE CRITERIA: Bedding to be placed as specified in IFC Drawings: – PSDS: 150 mm
5949b4e9-c6bd-542e-ac12-4cef6e78d98c | note | METHOD: Measure
c7afd09a-c51d-507c-8340-4c5b97dbb3d0 | note | FREQUENCY: Each Lot
e55f45b6-bf73-5529-847b-467327aabfc6 | note | CATEGORY: IP
21450b9a-bd96-5979-a171-861d90a37dac | note | RESPONSIBILITY: SE/Supervisor
4af3f14e-efea-5068-9c49-4af4ad346f41 | note | VERIFYING DOCUMENTS: This ITP
7d0d9ccb-2d0d-5e23-96d3-fdecaf957e87 | date | Date Completed:
| checkpoint | 5.4 Beaching Placement-Thichness
6b04ecaf-1b7b-594c-90f0-899c7c3b283d | note | REFERENCE: Fowler Road Bridge Structure Scour Protection (MRP-091-C-BEC-DRG-00-DNG-CBR-5613)
32acb8d0-fb51-5279-846d-aa16a87e41fc | note | ACCEPTANCE CRITERIA: Thickness of placement to be 2 x D50. Rocks have min D50 of 400mm
4abeea09-fda9-5dce-9623-b9cfa224dd61 | note | METHOD: Measure
0b883393-838e-594c-8f4d-86f6e58dda1d | note | FREQUENCY: Each Lot
be8066cb-be95-5b89-a0ea-126fbd503b63 | note | CATEGORY: IP
f4cb8e14-6c5e-5ed3-b833-9b5c41893c44 | note | RESPONSIBILITY: SE/Supervisor
d3803692-c70d-5ff2-b8de-afb495ffc076 | note | VERIFYING DOCUMENTS: This ITP
9e80e997-d377-5b7d-8a09-4ac3930abb70 | date | Date Completed:
| checkpoint | 5.5 Beaching Placement-embedment
10191121-3e37-539e-92a0-b30f216a582b | note | REFERENCE: 713.05 Sect (a)
157f1764-cd17-5a20-8bb8-52158e0829a8 | note | ACCEPTANCE CRITERIA: Beaching materials shall be firmly bedded on the prepared embankment and/or bedding if required and laid in courses commencing from the bottom of any slope.
7a47a770-3ffd-5c99-88f7-bd475edd7add | note | ○ Un-grouted beaching and armour stone when placed shall form a tight ‘interlocking grid’, which shall prevent the removal of individual rocks.
e494d0ed-4cfb-5e4a-b99c-2fd6b50b1e08 | note | METHOD: Visual
323b8c64-2826-5daa-aee0-326bed184bff | note | FREQUENCY: Each Lot
b1dd292b-a4e2-54fd-ad29-2c89d868893e | note | CATEGORY: IP
3d055ef6-6b1d-5276-bf69-7ef010d491c9 | note | RESPONSIBILITY: SE/Supervisor
59e80547-662b-5fdb-aa0a-ac592db0d7ee | note | VERIFYING DOCUMENTS: This ITP
90e9cf16-d026-5004-999a-d27f2cb570b3 | date | Date Completed:
| checkpoint | 5.6 Type 5 Rock Beaching Placement-Surronding
c32d2835-14d1-5eac-8d02-25378b959543 | note | REFERENCE: 713.05 Sect (f)
d15b107e-6869-5e56-ac54-a49ff5f27577 | note | ACCEPTANCE CRITERIA: Rocks shall be placed to
7f120385-c7f5-5f36-a52e-1ffa7b216c2c | note | ○ allow for the formation of a tightly interlocked rock mass in which the larger rocks are not free to move.
0c294ee7-9ec7-554c-92ec-c3f360d1f667 | note | ○ All voids are to be sealed with smaller graded rock for stability and sufficient for water to flow over the top and not within or underneath the beaching.
e3b6df73-9bd7-54ec-9973-efb118ced4df | note | ○ All leading and edge rocks shall finish flush with the surrounding ground level.
b382ff79-a724-5730-aff0-b55eb0910565 | note | METHOD: Visual
2bcf4e68-043f-5643-a32f-8af8d8c945bb | note | FREQUENCY: Each Lot
95ed76e7-94ba-5fc7-884c-73db6fe35c12 | note | CATEGORY: IP
6c168893-c3ec-5c1a-a6e7-ef8234c81519 | note | RESPONSIBILITY: SE/PE
64e34ed4-a4c3-5987-a0f7-9b9f069bbab7 | note | VERIFYING DOCUMENTS: This ITP
e4ca96e4-0051-583c-a476-11e117be053c | date | Date Completed:
| checkpoint | 5.7 Type 5 Rock Beaching Placement-Surface
6e5d4d87-e381-5026-9af9-aab3ab2ae02d | note | REFERENCE: 713.05 Sect (a)
1c868f7f-9684-5efe-82f5-8bc16721b73d | note | ACCEPTANCE CRITERIA: The general surface of the finished beaching shall not vary from a 3 metre straight edge laid across the surface of the beaching by more than:
ed25093d-5a45-543c-9a94-cb474b4ba75d | note | ○ 75 mm for Type 5 Beaching (unless otherwise specified by Melbourne Water Authority)
6f456777-5321-5c11-afbc-851da3ac9bda | note | METHOD: Visual
2f45098c-2043-553e-b120-ec3e283daf2d | note | FREQUENCY: Each Lot
4c132d39-bcde-5915-b0b0-c004e6b1c54f | note | CATEGORY: IP
1b4e94ff-0f06-557c-8d9f-1cd0e0356f4d | note | RESPONSIBILITY: SE/PE
173d09e2-f539-5f1a-bd3e-56f83506ac04 | note | VERIFYING DOCUMENTS: This ITP
2fa6f358-9b07-5749-8fb2-ac34814eec42 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Cleaning
4dd6616c-3ff3-504c-a347-073cdd04607b | note | REFERENCE: 713.09
1dbb1c34-f2b6-52c1-910d-d2109f548fd3 | note | ACCEPTANCE CRITERIA: On completion of the work, the beaching shall be cleaned to remove all foreign materials and discolouration from the beaching surface.
b0a6876d-6f92-5b53-b517-2b82dfcb62a5 | note | METHOD: Visual
ed010c69-8bbf-5a47-a659-decf7ad0b803 | note | FREQUENCY: Each Lot
211786fd-b365-5dec-97ca-bc114801040b | note | CATEGORY: IP
9e42ff2a-192f-5c0b-8ce0-45b69b6056b6 | note | RESPONSIBILITY: SE/PE/SPE
b5da4099-d0b4-5df4-921a-6f397b82bc6a | note | VERIFYING DOCUMENTS: This ITP
f83e5731-c096-53da-95ec-856183039a0d | date | Date Completed:
| checkpoint | Final Inspection
6e70aec9-8c42-5b4b-ad66-836041543406 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ab3e2d51-8a1b-5c08-a6c4-b9809363efc6 | textbox | Name:
6e008060-2b10-5ddc-bc54-b261e9e00b65 | textbox | Position:
6493cb80-ad1d-595e-a7f9-3fe44d994533 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-157-STR-PSDS-Bridge Precast T Beams Installation Rev 0 | itp | ITP-157-STR-PSDS-Bridge Precast T Beams Installation |  | 5568fd4b-41b9-49a3-9193-4ae7956b384f
| section | Referenced Documentation
| checkpoint | Referenced Documentation
59e4b332-536c-5bbc-b9e9-68ae33a57366 | note | Document Title: ITP-157-STR-PSDS-Bridge Precast T Beam Installation
420bd3d7-7c8a-5acc-936a-ec6631583c2f | note | ITP Description: PSDS-Bridge Precast T Beam Installation
084ef988-686f-5b5e-8579-b3c00a50a582 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
91801c7b-1a7d-53db-a72d-f3aa4e3ca4e5 | note | Discipline (e.g. CIV/STR/RAIL): 157-STR
7c13b3da-8720-5e2f-851e-f77ef9883e78 | note | Revision Number: 0
553f5e46-cc4f-5122-89c4-1988ab7890ae | note | Revision Date: 8/07/2024
d0600c77-d510-509b-86d6-5b7ef80cad45 | note | ITP created by: VM
902ce354-d2fb-5b25-a31e-3651c913adb7 | note | ITP approved for use by: VM
ed8129d5-212e-5db2-93a2-aa0f33148fe0 | note | 1.1 Non Dependent
458caf34-5d39-5fe2-8663-e32c05d0e682 | note | Reference: IFC Drawings
d2cd808b-2c2d-5d04-8d19-a5aa20333b48 | note | 1.2 Non Dependent
d316f030-cea7-5ed9-abe3-80d6cc6cb0a5 | note | Reference: VR Section 613
8a15b012-0210-5ad7-8937-bccca73ef0a5 | note | 1.3 Non Dependent
1fc7ebf1-2db7-5dc9-9924-b5870645ecf4 | note | Reference: VR Section 610
48d31ee7-95fe-5518-b46c-7a9a64e9f06f | note | 1.4 Non Dependent
9ecbfe10-01b1-51e2-8776-a8106fd10693 | note | Reference: VR Section 620
| section | Preliminaries - Materials
| checkpoint | 2.1 Flowable Grout
78dfdeb2-cd03-5efc-bef2-6795db4cf521 | note | REFERENCE: IFC Drawings
e8875a6e-68f6-50ab-863b-51ac33a865a7 | note | ACCEPTANCE CRITERIA: Underside of beam shall be grouted as per IFC drawings using flowable non-shrink grout with a minimum compressive strength of 50MPa.
e299ef4a-d508-5e50-b745-1b1beffa73fe | note | ○ Grout shall achieve full strength and shall be completed prior to Stage 1 deck pour.
6558ed05-088d-5694-bd89-cf1e14d6c215 | textbox | Enter: Teambinder Material Approval Number
4258536c-5edb-5929-8215-e3cb3da207d1 | note | METHOD: Document Review
a73df1a8-0c02-50a8-8dee-8de4f6ae686c | note | FREQUENCY: Each Precast Element
c5bece09-ff84-5313-b44e-971b391782ac | note | CATEGORY: HP
fb663c91-19b9-5a5a-a9d8-53a7b760b990 | note | RESPONSIBILITY: Nominated Authority
d0c0ba5c-c436-5b93-aaf4-d62390d4d66e | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Beam Seating Pads (HDPE)
7ff38a53-0228-5c24-8bec-32e8b4c9d2a7 | note | REFERENCE: IFC Drawings
ff45a274-19ef-529f-8550-d4e34fbd8f90 | note | ACCEPTANCE CRITERIA: 2 No. 200 x 200 x 20mm thick high density polyethylene pads, or approved equivalent, to be designed for minimum 10MPa Stress.
725a2374-38d9-5be7-8656-fc8f4cb93e5f | textbox | Enter: Teambinder Material Approval Number
f9299681-82b6-5335-9a57-2e5d1e505d12 | note | METHOD: Document Review
1345f6c4-77c8-50dc-8863-3d07ee60b055 | note | FREQUENCY: Each Precast Element
c2196daf-8d39-5464-b05d-c9d4a913a980 | note | CATEGORY: HP
27d68b5b-5d23-50ad-aa80-85c3fb70fbf9 | note | RESPONSIBILITY: Nominated Authority
f20dce9a-f068-52a9-86f1-2927c45713e6 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bitumen Tape / Fibre Cement Sheet
aa02aa88-9acb-5e0c-801b-a2e234088943 | note | REFERENCE: IFC Drawings
05518848-e519-558a-a605-6c8cbeef4658 | note | ACCEPTANCE CRITERIA: Beam joints to be sealed at the flange as per IFC drawings using approved materials.
a5fc3ddf-1cc1-549c-8a58-8b2a9c41c746 | textbox | Enter: Teambinder Material Approval Number
e780ea18-fa62-5a72-bbf4-a1d8cbe4540c | note | METHOD: Document Review
92a80e9f-ba5f-590a-88ad-77119cb13bfe | note | FREQUENCY: Each Precast Element
42111ac6-f73e-5c74-8d32-0fc660e55373 | note | CATEGORY: HP
e17beec0-4681-5f39-a5a1-a96102dd1148 | note | RESPONSIBILITY: Nominated Authority
c2eb23c4-719d-5a1e-b938-c3b863c1c0b4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Precast Elements
f6febeea-a24d-59a2-9fbd-3c6a47b189d5 | note | REFERENCE: IFC Drawings Section 610.47, VR Table 610.473, Section 620.03
3f5a49cb-405c-5afa-82a7-ac47bb2605fc | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
4e2e6ee1-5bf3-5b8d-b011-6a953bb516e6 | note | i. Certificate of Compliance / Birth Certificate
43f18f6c-944f-581a-ac7c-e5dc89c469cc | note | ii. Compressive strength test results
d457bf28-3b69-5f08-a567-9938ce66a75f | note | iii. Precast Lifting Design
0397bb85-ea72-5ef7-acc7-d492da7f5e41 | note | iv. Pre-pour check sheet / ITP
5b0479df-b7fa-50d6-8a9b-dedcddcb2560 | note | v. Pre-stressing check sheet / ITP
e7e7afd5-109c-5d3e-83d7-278bfe1271d2 | note | vi. Post-pour check sheet / ITP
30f7b219-1985-53ae-8958-062e1d49838d | note | vii. Covermeter check record
dba31969-de5d-5121-835b-c6231d9cff4f | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
e8134fee-f1dc-5a28-8070-af12a9eafd49 | note | Note: Different revisions of 610 have different clause numbers
508fbe1f-902f-5cc6-aba2-13ce25cc59d1 | note | Collate: Precast Quality Assurance Documentation and upload into Teambinder
4d2ab2d7-bf99-5625-848b-3ec8800090db | textbox | Enter: Teambinder MDR Lot number
79f2592b-ae0d-5a26-be33-3682abe86286 | note | METHOD: Document Review
516508ac-11d4-5876-a48c-570469d72c90 | note | FREQUENCY: Each Precast Element
b4c11d7d-bf98-5391-832c-ed12e00e7af7 | note | CATEGORY: HP*
afc50bb1-be2c-5835-ab31-0ce195685866 | note | RESPONSIBILITY: PE/SE/SPE
89a3b69b-e5fc-5ec7-8be5-1b0065141b67 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 3.2 Curing Methodology (for Concrete, Grout and Mortar)
eba3d19e-6b8e-568e-8cc1-dd390cc55423 | note | REFERENCE: 610.23 (a)
f2c7b7e4-1cb8-5027-bc0c-0be0ea5ae3f9 | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
4d98c6b2-5e1e-54c3-980d-f1e0263406c9 | note | Note: This may be the same document used for the concrete curing.
71bd7c3b-daab-5ce4-adba-88c03378aeed | textbox | Enter: Teambinder Correspondence Approval number
91159d70-af63-5162-8962-252f2668b6d7 | note | METHOD: Document Review
687e0dbc-4a75-5128-bfd3-2ae44fb0ffcf | note | FREQUENCY: Once, 4 weeks prior to placement of product
a49d8e78-d43d-5adf-8be1-6db5f9559701 | note | CATEGORY: HP
a9e905e7-0c89-5ce5-a362-1fd8367d25a9 | note | RESPONSIBILITY: Nominated Authority
ebb6ac41-f1b7-5c7b-b062-76d0b8c52cbe | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Temporary Works Designs
f176b4d4-4704-5b7a-a679-4292e7c47388 | note | REFERENCE: Section 610.27, Section 613.04, Section 613.05, Section 613.16
1e2e6609-5df4-500d-ae18-45817527da8a | note | ACCEPTANCE CRITERIA: All temp works design shall be certified by a design engineer who is a member of Engineers Australia and with a minimum of 5 years experience in the design and construction of falsework.
fd22f8a5-9e54-5015-8bb3-e1b9491e2c4c | note | ○ The temp works design shall also be proof engineered by a Proof Engineer who is independent of the design consultant’s firm and is prequalified at Level PE under the VicRoads’ prequalification scheme.
be5c167a-4f2b-5594-854c-e10d84a68b38 | note | Attach: Temporary Works Design
f6e516a2-9d45-55e6-919e-e8a00f296c55 | note | METHOD: Document Review
7c7d6527-2e4a-52dc-be5d-1934677c41c2 | note | FREQUENCY: 2 weeks prior to installation of falsework
4d999724-9b37-5899-b7a9-dfea48a45e2c | note | CATEGORY: HP
5e990092-0ad1-5433-82a4-2603c9f7acac | note | RESPONSIBILITY: Nominated Authority
70ce7973-ee06-57bb-ad58-7ac398a57760 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
16199570-ddb9-5da8-9ca3-92b791a913f7 | note | REFERENCE: MRPA Quality Management Plan
be6ee101-ba40-5691-855d-6c7bd70fde08 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
52a29ee6-da0e-5ae3-b21a-81803b2d36d0 | note | METHOD: Document Review
adda0ca9-1de6-567c-b3e0-96f4219e460d | note | FREQUENCY: Prior to starting Works and at regular intervals
44168ba5-0829-57bb-9d04-6ca849f4a7b5 | note | CATEGORY: HP*
fe9dce51-e629-5db4-9ab5-346e169cabfb | note | RESPONSIBILITY: All
1db23ba4-fc4d-5c00-bb7c-ca347e71a972 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 4.2 Beam Seating Pads Check
bdb04dda-c442-580b-9cc0-740a40e1987b | note | REFERENCE: IFC Drawings
bfe11f74-9cf4-53e1-86fc-fc4f11081a42 | note | ACCEPTANCE CRITERIA: Beam seating pads shall be inspected after fixing to the abutments and prior to the landing of the precast beams. Ensure the setting and orientaition of the seating pads are correct.
30e166e2-63a8-5733-82b1-22e08d9fafeb | note | METHOD: Visual, Measure
2967c5d6-5e19-518f-9169-2ab7060d4439 | note | FREQUENCY: Each Precast Element
24be8627-e292-5da5-8e53-566ce5d3606e | note | CATEGORY: HP*
b85af569-371d-5a3a-bd66-f497c9462736 | note | RESPONSIBILITY: SE/PE
a39a4262-07d7-5890-868a-81e9551cd465 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 4.3 Crosshead Tolerances
481e8958-1465-5d8f-bc4e-218b082c18dc | note | REFERENCE: Survey As-builts, IFC Drawings
84559ecb-7760-559b-a9f7-ab4ae6285b96 | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements as per IFC drawings.
bf4c2a85-c444-56f6-ac79-d6c32c13a288 | note | METHOD: Document Review
94030e43-b1cb-5935-a6f1-a35781943ebc | note | FREQUENCY: Each Precast Element
4eb54f99-36e3-5350-b1c5-8fbf75160a0c | note | CATEGORY: IP
008ccb16-1809-59ed-a345-dd21630cc03d | note | RESPONSIBILITY: PE/SE/SPE
7c9e30ea-43f4-5243-b986-1680bea86ff2 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 4.4 Precast Beams Estimated Hog Values
93089ff3-1f9a-513d-b13d-2d9ac4bfa762 | note | REFERENCE: IFC Drawings
a8dee415-315c-5ca2-8ff1-9b7d4bb29a48 | note | ACCEPTANCE CRITERIA: Re-check hog values for each precast beams to ensure within tolerance prior to landing of beams.
b3237776-2b66-54a7-a149-0b0cee95cc35 | note | ○ Estimated Hog at Transfer (B1-B10) = 30mm
6c19d885-07a9-5a48-a0c3-9b0a51ec08a4 | note | ○ Estimated Hog at Transfer (B11-B20) = 21mm
17f75baf-7e61-59d5-94e2-69a7e8edf97e | note | ○ Estimated Hog at 30 Days (B1-B10) = 54mm
9e9e19f7-de8d-5d50-88dd-fd228259406a | note | ○ Estimated Hog at 30 Days (B11-B20) = 42mm
ef0db18f-f4ae-56a6-a78a-b37d8b5cab4f | note | METHOD: Visual, Measure
b37eab96-b77c-5bdf-ada6-6ab230e3fb6b | note | FREQUENCY: Each Precast Element
0994d578-3a76-52b7-86bf-e382e9732271 | note | CATEGORY: IP
d803a42a-66af-5c41-b845-90794f0e3985 | note | RESPONSIBILITY: SE/PE
8be1a68c-ee47-587c-b1a0-dee739c61d00 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| section | Construction Activities
| checkpoint | 5.1 Seating Pad Survey Set-out
49c94d09-b91e-5997-8406-d2d4bec47521 | note | REFERENCE: IFC Drawings
ddc3756f-01d9-50e9-8987-b27526929a7e | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure seating pads' locations are in accordance with IFC drawings.
adb215b6-1c73-5662-851e-e4c1bc6a3f09 | note | METHOD: Measure, Visual
fb55c5ef-7e38-55c3-b21f-e08bec19d436 | note | FREQUENCY: Each Precast Element
794b81a8-124f-5923-9d23-04d01da880eb | note | CATEGORY: IP
11b216ec-22a2-5ba6-9de5-410ac2cb2a87 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
00fcf816-5117-5143-942b-efa23ddcce35 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.2 Install Seating Pads (HDPE)
e6e9c970-0561-59c2-8c83-42855b48452b | note | REFERENCE: IFC Drawings
aea0556a-e4c3-5c69-829d-030a836fbb97 | note | ACCEPTANCE CRITERIA: 2 Nos of 200x200x35mm HDPE packers are to be installed in designated recesses on restraining blocks.
b3241cf6-51bd-5d4d-acc4-bc62f4789f5e | note | METHOD: Visual
8f39e91d-9d58-5031-9bdf-06f6ee2bd6f6 | note | FREQUENCY: Each Precast Element
ee8e6ccb-e053-508b-bc6a-d0b098f977a0 | note | CATEGORY: IP
20f6e502-a4b0-5984-af4c-894bc44547ed | note | RESPONSIBILITY: SE/PE
855811c1-4c98-5c61-8e9d-d3056dd9fa49 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.3 Precast Beams Handling
d0edcda5-6b73-5ace-8cea-acc6275f6d8d | note | REFERENCE: IFC Drawings Section 620.07, Crane Lift Study, Beam Certified Lifting Design
ec492209-1a56-5d9a-81a7-7c7e74e3a533 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using approved lifting points in accordance with the Crane Lift Study and Precast Beams Certified Lifting Design.
a187ae05-8321-5e1d-9736-d3e9470a9281 | note | ○ During storage, transport and handling, precast beams shall be kept in an upright position and supported not more than 400mm from each end.
e8e459a9-19bc-50cb-a82e-b2dc78e60f63 | note | ○ Beams shall only be lifted by the approved lifting anchords provided.
d83090d8-0b63-5ba4-b8e8-9ae1f47c8dfe | note | ○ Sling Angles not to exceed 300 from the vertical
857b6f09-61a0-58ec-b11c-1539b833a780 | note | METHOD: Visual, Document Review
21c6fb0e-2816-5d38-a396-ddec593973e6 | note | FREQUENCY: Each Precast Element
701c3f5c-3581-52df-bf96-8696548e0572 | note | CATEGORY: IP
915eae78-6b5a-57df-9f9e-8a840ae9dafe | note | RESPONSIBILITY: SE/PE/SPE
4a157fc6-8e8b-5472-ab6e-af4809f885f4 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.4 Precast Beams Placement
43bbfefa-f390-5164-aac0-c3ce0aff9974 | note | REFERENCE: IFC Drawings Section 610.27
13c87cd4-8028-5e77-a611-140529eece3d | note | ACCEPTANCE CRITERIA: Precast beams shall be placed onto the seating pads and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
220d67bc-03db-5f22-b223-a4bd20117b7d | note | ○ The nominal gap between elements is as per the IFC Drawings.
e212e07e-e12a-53c5-8d19-6eb999b049b6 | note | ○ Girder landing positional tolerance is ±25 mm
eda70cce-d6ec-50e1-ab8b-6addde3fab59 | note | ○ Precast beams shall not be erected and landed until the specified 28 day concrete compressive strength for abutment/pier crossheads have been achieved, and not before 14 days after casting.
53be743f-4cb4-56a1-84f2-0dc6c2e896dd | note | ○ Beams shall be braced in accordance with the approved Temp Works to prevent overturning at all stages of construction.
9cea720f-4a0a-5b5a-a48a-33dd4c19bb45 | note | METHOD: Measure, Visual, Document Review
8e3408f3-bcbd-54ff-b597-f7fb3d35c122 | note | FREQUENCY: Each element
0a15eecb-2e58-5699-ba1b-b51d044c0995 | note | CATEGORY: IP
32d246a8-6845-5fc9-aecc-95b542b95009 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
9ef3a06c-d087-50ff-91d9-0f0775785d97 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.5 Precast Traceability
ce168b84-19dc-5e20-bd1e-3bcadfc92d39 | note | REFERENCE: Section 620.09
5da47115-88f4-5978-b5b1-2ff5926c2467 | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
af08a3d0-c663-559b-8288-f4c75ea3edba | note | Record: The final location of each precast element, showing individual ID and date installed.
853f69ca-b1a7-51bf-8ba9-fadba43012a3 | note | Attach: Lot Maps showing beam individual IDs
5a10c10f-1d3b-5241-b7e0-f5f0037ac4d7 | note | METHOD: Visual
fcd0ea4e-f3bb-53d0-b237-c3c93b22edb9 | note | FREQUENCY: Each element
021dfeaa-a3f0-51b7-8a5f-079be38e9aa5 | note | CATEGORY: IP
ca52054d-ecce-5a25-8a80-c7dc7cc0190d | note | RESPONSIBILITY: SE/PE/SPE
1f09c7b1-263b-5fc0-b33d-1966cdb64eae | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.6 Grout- Formwork Construction & Placement
9623e1a6-76a7-5dd1-83aa-2f4c8a95be24 | note | REFERENCE: IFC Drawing No.: CBR-5633
98da5500-a68e-5757-b671-c661c68d84ec | note | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings.
6f9b0309-f1c1-59b7-b0f1-ec006a3a11ea | note | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
5232efac-1df6-5361-be91-55012584d968 | note | METHOD: Measure, Visual
a718d4cc-ee94-50c6-8194-c1f2bd2bc619 | note | FREQUENCY: Each element
50524399-5346-5b67-a754-881909736391 | note | CATEGORY: IP
b1d5c13f-264e-5ef2-81f1-3f33b95bf6d3 | note | RESPONSIBILITY: SE/PE/SPE
daf5ea0c-c752-5188-8e21-094ff189a581 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.7 Grout-Pre-pour Inspection
0277e3fc-454c-55cd-b313-2cca3a966d64 | note | REFERENCE: IFC Drawings 610.20
db21a110-2dbc-5529-8102-25344ea8d663 | note | ACCEPTANCE CRITERIA: Formwork location and dimension comply.
73d83a23-7268-59ba-ad4a-74eadd858116 | note | ○ Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
4364abbc-e572-5c89-b110-829f7416a20f | note | METHOD: Measure, Visual
6e263e43-6363-5e96-a407-386dc4541198 | note | FREQUENCY: Each element
cf08e018-84d7-5783-9b7a-16c208a4595b | note | CATEGORY: IP
63bcbfdd-dd1c-551f-84cd-e47915ed63de | note | RESPONSIBILITY: SE/PE/SPE
8535c60f-b424-5473-8751-23ae2075c869 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.8 Grout-Mixing Product
02934643-9d8c-5951-a8b0-a781ac3307b3 | note | REFERENCE: Product TDS 610.28
8dbb38a6-3461-52a2-a2a6-5cb6192bd98c | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
3a95c6fe-8bc5-524c-8b66-bc0972df211d | note | ○ Only whole bags to be mixed with potable water.
606bceb2-6f3e-52e1-ae2a-19acf627343e | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
f88dd790-58e2-5da0-acac-ce9592d9f841 | note | ○ Product poured into the mixer slowly.
c497cde3-98c8-597b-8145-e7a7a7e3ef73 | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
6fa0b5f7-a4c4-50bb-879b-ca0083abf328 | note | Enter: Required information on the Grout Pour Record
944202a9-18a5-5b99-8864-c29805adb026 | note | METHOD: Measure, Visual
ef8c3835-0507-5c94-87cd-e02570e3be6c | note | FREQUENCY: Each batch
fcbec9b2-e3b6-58b2-b854-7e60a37e7e24 | note | CATEGORY: IP
869265c4-1174-5816-b39c-f898b03150a8 | note | RESPONSIBILITY: SE/PE/SPE
13e004a0-74d4-590b-a597-208564125948 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.9 Grout-Product Testing - Compressive Strength Cubes
e09cb1c0-c03e-5c0e-aeb9-a35a7cca4a55 | note | REFERENCE: 610.28, 610.33
8dc78325-9755-5dd9-b119-8582d3a1afa0 | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
4cfdd64d-9681-5ed2-a2a2-937c8015e18d | note | Testing is be in accordance with the following frequencies:
1a323eec-20d7-566d-a96d-037ace4bb800 | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
13763dba-ccaf-5e66-9ce6-f5897c3573f5 | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
8107ec51-89f1-5c35-913b-558b386678ed | note | Attach Grout pour record
b4123b11-315b-5aed-afc9-cc222c6ed94c | note | METHOD: Test
401c4be4-3e5a-5ef5-8ba8-975228c6b982 | note | FREQUENCY: Each element
9653ca6c-4bbc-520a-b988-b6d9858a68ff | note | CATEGORY: IP
2fde7d95-d1ef-5d20-9606-45ad48929b43 | note | RESPONSIBILITY: Tester, SE/PE/SPE
94e2e631-86e8-5897-a4a1-431c62e69160 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.10 Grout-Placement & Compaction
3269f6cf-f6f5-5ad3-9a72-386b9ec8ab06 | note | REFERENCE: Product TDS
35e2aca6-23d5-5626-99c4-5878670ddaaa | note | ACCEPTANCE CRITERIA: All batches are traceable.
b86ba8da-db79-5f33-88f0-827d04d14a7e | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
8d3e6841-ba0b-51c6-92ef-aad60869664d | note | ○ Product should flow to all areas and self consolidate.
19bb4bcc-d195-5378-8d59-ce281f6ac2d7 | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
ca548e1c-e0e5-5f32-9175-f7778f97e8ad | note | Enter: Attach Grout pour record
114a4b0b-c5a7-51e1-b8be-51de0e7f7ec2 | note | METHOD: Visual
0a8a784e-0d43-563d-9d74-02760144682d | note | FREQUENCY: Each element
5f0131b2-8303-52f4-a238-6f55656f117c | note | CATEGORY: IP
716599fb-8d52-53e8-b9a4-ac5ad769f775 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
f6424c23-e476-5fad-a51d-fda7b51a6314 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.11 Grout-Curing
352c0ee6-702b-5689-b9cc-ec4ff51c24dd | note | REFERENCE: Curing Methodology 610.23, Table 610.231
ee1f641b-2661-56f6-bfdd-ef49390e45be | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
42bfc3c2-faba-51e3-9e96-d9ee2684958d | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
3b14fe9d-9c92-5493-9e05-9fee79394e94 | note | METHOD: Visual
8f6f0ef6-f971-57a7-b36e-c115a0d8e96e | note | FREQUENCY: Each element
c04ae833-ab35-5fe2-adde-d6723a9d769f | note | CATEGORY: IP
2229996c-d561-5bec-8e9e-5ac6b20705ce | note | RESPONSIBILITY: Foreman, SE/PE/SPE
ffb770bc-941a-5be6-aa82-7d6dab6fbe1b | note | VERIFYING DOCUMENTS: This ITP
| section | Post-construction Activities
| checkpoint | 6.1 Grout-Compressive Strength Test Results
e0f87dbf-b8eb-57ae-9883-4b8f7346c521 | note | REFERENCE: IFC Drawings, Product TDS
3ba22f17-bddc-51e1-bf86-27c8908233a3 | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
cb49ebea-7fa1-5ed4-9363-486cc4b9cad8 | note | ○ 28 day compressive strength per sample comply with the design strength.
c9b7400c-0ad9-5ba4-98e9-7e4fbc716b51 | note | Attach: Compressive Strength Test Results
9ef6d31c-c40a-543d-9b77-21b38ae60344 | note | METHOD: Document Review
05eb4ba9-e934-5abb-a3a9-6655a8d491ce | note | FREQUENCY: Each cube
3314637c-f1ed-5d8c-9af3-0961893c5e55 | note | CATEGORY: IP
3b0fa31e-b099-595e-bdb5-ca02c87d75a0 | note | RESPONSIBILITY: SE/PE/SPE
c54cf0a1-1ff5-5de7-af6b-e186e4eab29e | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.2 As-built Survey
f4b1f5a8-ef7d-587d-879f-b4ce41160695 | note | REFERENCE: IFC Drawings Section 610.47, VR Table 610.472
ed5da777-9dc5-5f95-b943-dfe68c2ab59c | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
0835184d-06b5-54dd-a881-0b7799fa09a8 | note | Attach: Survey As-builts / Survey Report
d7928a6e-1199-5fe4-a252-21ec26cbf060 | note | METHOD: Document Review
17b63e28-6542-5ebc-8b51-83cfc25b364d | note | FREQUENCY: Each element
cd43d3ca-1f8a-5481-81bb-e558e4481f0d | note | CATEGORY: IP
feb5d201-759a-5d2f-b495-16c4d4888288 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
ec6b26e2-a8aa-5559-b20d-a8bb6de0c44d | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
a693a4d6-fb21-5e7d-9e75-3b4ce0004138 | note | REFERENCE: MRPA Quality Management Plan
403522a8-7422-5e9b-b35a-35d1bdc28c3d | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
039f84cf-a107-5d42-8ada-be4bc0e35758 | note | METHOD: Document Review
211583fa-9785-5c43-a6ad-3dacbfee13e3 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
4c8f9557-ab52-56c1-a285-b04fbb7c20ea | note | CATEGORY: HP*
d104361e-f321-59c0-abc7-dbe94677a23a | note | RESPONSIBILITY: SE/PE/SPE
2532f1c2-0a10-5cde-8a86-2a9d4587f3bd | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | Final Inspection
70ee377d-9016-5de3-8155-cf896efe0c4e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
06165969-5e1d-5921-ab2c-2b34dcde785f | textbox | Name:
c9e0391d-9294-5ab3-9c33-dff3f7700f84 | textbox | Position:
b4fb717b-8c10-569b-b31e-1608509b1007 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-160-CIV-PSDS-Landscaping-Ground Preparation Rev 0 | itp | ITP-160-CIV-PSDS-Landscaping-Ground Preparation |  | f99d60d1-89fc-4cf5-b251-c89b674495cc
| section | Referenced Documentation
| checkpoint | Referenced Documentation
1e666e05-4a5f-562e-874b-c0ad19f9f475 | note | Document Title: ITP-160-CIV-PSDS-Landscaping - Ground Preparation
19ce3d44-067c-5b67-a15d-89a7d0394282 | note | ITP Description: PSDS-Landscaping - Ground Preparation
425c6f0a-bf8e-588f-9d0d-8d06d108e3f0 | note | Discipline (e.g. CIV/STR/RAIL): 160-CIV
a377624f-4727-5828-bff2-db89b4229fd7 | note | Revision Number: 0
e966b5ca-2258-50d2-b740-90d92a0102ab | note | ITP created by: Victor Mira
bd15bd82-22e5-512d-97a4-1c7a4185f0df | note | ITP approved for use by: Victor Mira
62f129d1-3b39-57ce-aa34-06d057040e7a | note | Reference: VicRoads 720, AS 4454, AS 4419, IFC Drawings, Sub Contractor ITP
| section | Preliminaries
| checkpoint | 1.1 Check for correct documentation
121d04d2-5bc8-58e1-9001-10e431c733a0 | note | REFERENCE: Drawings and drawing registers
a0ff9964-54c5-5ca8-98fd-619c6709301e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
96673e3c-4b09-5a6f-b7a9-8201ebc8b7cc | note | – Using the correct and complete set of IFC drawings
3af902d7-bc2b-5ca4-8e8d-7fac075ad0f3 | note | – All drawings are the latest revision
ab9ebe5f-41d1-5661-85f6-224844ee14f3 | note | METHOD: Document Review
39cbc425-273d-5e66-8e88-55768ecc4c2c | note | FREQUENCY: Prior to Commencement of works
975bfc88-53d4-505c-89a7-8a6532ac51fd | note | CATEGORY: IP
11f281cf-06d8-5b49-98ae-1473fd6d6f7b | note | RESPONSIBILITY: SE
f0a924ae-b23c-54bb-bec0-3da45d20df09 | note | VERIFYING DOCUMENTS: Sign ITP
| checkpoint | 1.2 Submission and records
f26d38d1-5b56-5731-bd94-96527e16f5c6 | note | REFERENCE: Section 720.03
d59e8a19-99e6-5f68-9ddf-479909b6175b | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
8842332d-b471-5a3f-a17f-07533a5221a9 | note | Following information shall be provided to the NA:
da257981-b2a3-5a66-9b67-77d4ce7d089f | note | ○ Samples
add8fb47-096d-5917-a5c4-1ce07cb9078f | note | – Mulch
74ea03d3-f088-502c-a060-24595ab4369d | note | – Imported topsoil
9d6c6954-dc5e-59e1-aa1b-5f03aaad437c | note | ○ Records
7aa3c4f6-5431-557a-bd06-34ca65fd67be | note | – Details of suppliers
a8bd9d28-3be6-56b5-91f7-5941856a6d0e | note | – Soil tests on imported topsoil
884523e2-db7e-5d25-ab86-dc049dbccb45 | note | – Copies/Photos of fertiliser labels
78aa5fbf-43e4-5066-b376-54c4cd8c0182 | note | METHOD: Document Review
bc81c46e-3ade-5adb-a70a-3494d7543b5c | note | FREQUENCY: Prior to Commencement of works
f6ef7372-8d6b-5468-9dd1-a25d56858006 | note | CATEGORY: HP
82a85de6-1a61-595f-8d65-9aedf24bd0a6 | note | RESPONSIBILITY: SE, NA
4c034f83-db41-550f-ac3f-f20f19053efc | note | VERIFYING DOCUMENTS: Issue to TeamBinder
a8ff9884-9115-5e8c-a1f8-5a453ebb6f6d | note | ○ Attach: Records & certificates
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 1.3 Supply of topsoil
457e8f56-ddc0-5603-af7b-737d14e7280d | note | REFERENCE: Section 720.04, Table 720.042, IFC Drawings
9b7337ed-a3cc-5d34-8794-951e3889f2f5 | note | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
5ccd3f4b-10d8-5bc0-8200-90f20dbd5225 | note | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings .
41a9c122-d7a7-5341-bf7a-dfbdbf105bcb | note | METHOD: Verify, Doc. Review if applicable
9190a892-512c-54c0-b048-2e9b51cd5ea2 | note | FREQUENCY: Prior to Commencement of works
df59ae24-e2de-594a-adf7-1af356af2e4c | note | CATEGORY: IP
a0c7eb1c-08b5-5c4b-b4d8-dbb9ca1f8eaf | note | RESPONSIBILITY: SE
cc54a105-f0ea-5380-9b8e-2364bec8f5d6 | note | VERIFYING DOCUMENTS: Sign ITP, Attach material conformance docs/Test Report
| checkpoint | 1.4 Supply of Mulch
86c2d076-baac-5dac-90b0-e4ab540fd4d0 | note | REFERENCE: Section 720.04, Table 720.044, AS4454, IFC Drawings
4ea647d0-f846-5d60-be45-f749870161b4 | note | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
18e8f2dd-4090-5865-87b7-d4a5933251fb | note | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
23dde366-5f40-5a8d-813c-3f407e759daa | note | ○ Imported Wood Mulch shall comply with Table 720.044.
f40425dc-712f-5f1d-8fde-d0ba2d0a99a4 | note | METHOD: Verify, Doc. Review if applicable
084305bb-6b15-5620-a517-a3e70d1d0fde | note | FREQUENCY: Prior to Commencement of works
2ac5122c-57fa-5a7e-a360-d5671349ffd1 | note | CATEGORY: IP
3fa65c59-826f-5bc4-8dbf-ac1e17ec8f6f | note | RESPONSIBILITY: SE
818daa52-aa80-5bcd-8282-7b9f6e09c2bb | note | VERIFYING DOCUMENTS: Sign ITP, Attach material conformance docs (if applicable)
| section | Site Preparation
| checkpoint | 2.1 Subcontractor ITP
042b5686-20ce-5d33-af2f-b09f56dc1581 | note | REFERENCE: Subcontractor ITP
181844af-9fe2-5b3d-b77a-eeafcc7cd29e | note | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
01466704-8e35-5b93-9b38-4f2666211783 | note | METHOD: Document Review
00f1ff58-e5b0-517c-9aaf-76652e1c2ccd | note | FREQUENCY: Each Lot
45db4c8f-677d-519a-8ac6-61e9d7346630 | note | CATEGORY: WP
fb10e617-fc11-542f-b1c3-fc15c455975d | note | RESPONSIBILITY: SE/PE
f9f161aa-0d96-59de-8d20-f37beee5908c | note | VERIFYING DOCUMENTS: Sign ITP, Attach completed Subcontractor ITP
| checkpoint | 2.2 Soil Additives
d1284b52-7c08-509f-88f2-427c0463cad5 | note | REFERENCE: Section 720.07 a) AS 4419
e569e3d9-e068-5e76-bbaa-d05c8237480d | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
f6d9c93b-f449-5808-9fd9-08c5339e869e | note | METHOD: Document Review
61f183b7-b7cf-5b64-9985-398e566a292f | note | FREQUENCY: Each Lot
4dcc81f3-5857-5819-bf63-2cfe9694b2f9 | note | CATEGORY: IP
deda3d67-41f7-5ad3-9c02-e7e3565f340a | note | RESPONSIBILITY: SE
107ef975-c391-54ca-b9c1-f96178bc4f29 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Test Report, Attached Delivery Docket (if applicable)
| checkpoint | 2.3 Ripping of subsoil
94630d52-4553-55ad-9dbd-052d151d0098 | note | REFERENCE: Section 720.07, Table 720.071
c498ff95-ac92-5ecc-8d44-2fe4aaf5224b | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP.
6be106fa-9469-52b1-a306-8b62be6409f4 | note | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
20d03789-ef89-5460-98e6-c3927323dea3 | note | METHOD: Verify
93098e49-d82b-539c-bf23-aa039cf7e7c7 | note | FREQUENCY: Each Applicable Lot
ace5a6ee-b5a8-5fa0-bd61-a9d3304f7f52 | note | CATEGORY: HP
2a381b36-7a44-5911-a1b1-7c3912d90fef | note | RESPONSIBILITY: SE, NA
6562d326-f3a5-58e4-9cfb-72021f67ca74 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Lot Map/Marked Up Area Inspected
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Topsoil application
17868209-5dfc-577e-9cab-c8797dcde235 | note | REFERENCE: Section 720.07
0c2de1bf-cf0f-53f9-b9b5-865ad8251b7a | note | ACCEPTANCE CRITERIA: Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071.
447ac624-da91-564d-8cc0-b34204f83bdb | note | ○ Situation
0bc2cd82-38d6-5970-967a-609e38a452bd | note | – Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
83279f07-20ac-5f78-9ffe-4702293f6d73 | note | – Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum
963eac38-2bff-56b2-b4ff-8788aee8dc6a | note | – Grassing in disturbed areas =75 mm, except 100 mm in swales
edbe63dc-be6c-5c26-bc18-86ea8540b7b4 | note | – Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas
2d803313-602b-5af9-be8e-5df21f14329c | note | ○ Topsoil shall be spread on planting areas and grassed areas.
ba208777-f0ea-5136-8e8c-7b2634df1632 | note | ○ Note: Topsoil shall not be compacted.
9c816817-f4f1-5083-958d-1c2c4aa175ae | note | METHOD: Verify
ceafdc08-59ee-5893-8315-fb3b043db490 | note | FREQUENCY: Each Applicable Lot
227583d3-6f70-5806-b2d5-7d954c97b046 | note | CATEGORY: IP
9e159a2b-7118-516d-9874-ab8d9b5a5c4e | note | RESPONSIBILITY: SE/Site Supervisor
0d5096e9-e3b7-519c-94f3-38828051e129 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Delivery Dockets if applicable
| checkpoint | 2.6 Topsoil FSL - Topsoilling and Cultivation
6a5a89b8-a6db-5121-b187-a3e2f3318826 | note | REFERENCE: Section 720.07
270ff934-546b-5a76-a803-ab5f320e67e8 | note | ACCEPTANCE CRITERIA: Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
50d06fdd-3a3d-5983-9c83-ec49a5a9cd65 | note | METHOD: Verify
de60e6fb-712f-5afd-ba6c-0821372d26a6 | note | FREQUENCY: Each Applicable Lot
b085099d-f6d3-5ebe-b6cb-8c1c17dd0c37 | note | CATEGORY: HP
90cbf3db-c9a8-5253-bd4e-8ccd34ed8d83 | note | RESPONSIBILITY: SE, NA
737a88da-1582-590c-8853-8c8c7afd4585 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Lot Map/Marked Up Area Inspected
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.8 Mulching
3121ed03-c43f-5dd3-80c6-0c969eea7c75 | note | REFERENCE: Section 720.08 a) IFC Drawings
f72a0e04-3bb5-57a7-a265-0ad7b5fcfd64 | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
c5d2ca9f-c968-5a49-91c3-039d96c6f48c | note | METHOD: Verify
3aa50421-bec9-548e-8929-22c5fbc28173 | note | FREQUENCY: Each Applicable Lot
2b002fc6-1173-5ff7-b64f-7d32147c2e0e | note | CATEGORY: IP
65d103e1-ed1a-5001-882f-8b8996cdb260 | note | RESPONSIBILITY: SE, Site Supervisor
bb86afde-45a7-50ac-bf76-e0918c2a12c8 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Delivery Dockets
| checkpoint | 2.7 Weed and Erosion Control Mat
99db04d7-441a-5dad-babc-64421662fc11 | note | REFERENCE: Section 720.04 i) IFC Drawings
23f8a06a-fb6c-5422-beb8-30cca65bf939 | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
e5c1a3aa-4421-5ab1-8771-2db55241d7a8 | note | METHOD: Verify
11a922f9-cf6f-530e-9036-6628488c6b51 | note | FREQUENCY: Each Applicable Lot
e39cff59-9844-5d47-94d1-1e338bad6325 | note | CATEGORY: IP
61ede363-b52f-50c9-ae7d-b08c59d4a121 | note | RESPONSIBILITY: SE, Site Supervisor
4a34c14b-2e0b-56a4-81c7-d699aaa362e2 | note | VERIFYING DOCUMENTS: Sign ITP, Reference TeamBinder Material Approval No. if applicable, Attach Delivery Dockets
| checkpoint | Final Inspection
a7b464df-1fc6-5edb-a189-6eaf725e1f07 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
92299cbb-5203-5f54-a4ca-b1bfb80167d8 | textbox | Name:
351b3912-3c69-569b-820c-8622469b1501 | textbox | Position:
9d889410-98e4-564d-b247-1dc683819052 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-161-CIV-PSDS-Landscaping-Planting Rev 0 | itp | ITP-161-CIV-PSDS-Landscaping-Planting |  | 41f188f0-d92a-4bcd-b0b7-b4355c4d9163
| section | Referenced Documentation
| checkpoint | Referenced Documentation
9ee099b7-a21b-5364-812d-003c3aa4bbfb | note | Document Title: ITP-161-CIV-PSDS-Landscaping - Planting
e9d703dd-7ed7-52c6-8929-f857d2fde6a5 | note | ITP Description: PSDS-Landscaping - Planting
8deab0e9-630c-55b8-83e0-3340812bca6b | note | Discipline (e.g. CIV/STR/RAIL): 161-CIV
9dd933e8-1e62-5235-baaf-eeb6ae719c82 | note | Revision Number: 0
82058e30-4cbf-5041-a39d-d61ed8d81d1f | note | ITP created by: Anthony Pearson
38c37148-28dc-5607-91be-fe3a1d37f51b | note | ITP approved for use by: Victor Mira
11539656-5b56-5af1-a527-475ca95e3536 | note | Reference: IFC Drawings
33c653aa-ebc8-5157-b3bb-0948a7d5a0ea | note | Reference: Vic Roads Section 720 (Nov '18)
| section | Preliminaries
| checkpoint | 2.1 Check for correct documentation
26f7c046-459a-5a78-bb33-53527464b041 | note | REFERENCE: Drawings and Drawing Register
7d1275ae-a74c-56da-8c4a-9382a8a63230 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using:
f75d767a-35b7-54b0-be82-aabd93476446 | note | – The correct and complete set of drawings
a308ddb3-d697-5c6b-86f7-c17046f1491c | note | – All drawings are the latest revision
85a559ef-5561-54e4-982f-09a7f9a92ac0 | note | METHOD: Document Review
457c06a2-ec6d-5fb6-8e72-33e0eaea53b0 | note | FREQUENCY: Prior to Commencing works
82156ebf-0234-55da-abf6-90f406a60ddd | note | CATEGORY: N/A
76387ecc-51fa-5166-ac58-967f609ec8bb | note | RESPONSIBILITY: SE
e9284796-68a5-5675-a1e9-5ffc38fe61dd | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 2.2 Submission and records
c4e665b2-5394-5540-8d76-17ccfbf72249 | note | REFERENCE: VicRoads Spec. Cl.720.03
2fe926b5-fb16-5478-972a-0aa2ade76b5e | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
fd4dd735-b5fa-5a47-80c5-52aa6f94a9ca | note | ○ Following information shall be provided to the superintendent:
83cae847-3685-58bb-a8ac-3f6b119e70d1 | note | ○ Inspections of plant stock for all plant species
31f399a3-8980-5c6f-9ced-605719993621 | note | ○ Records:
69dda65c-1171-5e36-8b15-e1a63a7036ac | note | – Evidence of origin of indigenous provenance plant material
ce7e03f1-6bc1-5079-843b-918f752569a5 | note | – Analysis certificates for grass seed
02941600-000f-54ab-bb8d-dfd2076bc16f | note | – Details of suppliers
e908c7bf-7913-5f60-957d-0bb8bd1c16d8 | note | – Copies/Photos of fertiliser labels
5a39cfbe-17d2-5b60-9b74-912c78d646c5 | note | METHOD: Document Review
7c7c69aa-0e0f-5e44-947a-9e80e38df68b | note | FREQUENCY: Prior to Commencing works
f279822b-571e-54dd-93b6-d180f4c3e2c8 | note | CATEGORY: HP
496665e6-e63d-5f05-9bb5-de554e4dc80d | note | RESPONSIBILITY: SE,Superintendent
f709ed67-c8bc-566d-9de0-6ad8c8b556e7 | note | VERIFYING DOCUMENTS: This ITP, Attach Records to TeamBinder Approval Form
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Supply of Plant Stock
77955e86-33dc-5607-b74c-158dff0d518e | note | REFERENCE: VicRoads Spec. Cl.720.04, Table 720.041
468e83e4-0025-582d-9360-e539fd87a47d | note | ACCEPTANCE CRITERIA: All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
8e6155c8-09ca-5612-8751-3820ad6a5753 | note | ○ Plants are to conform to the supply properties specified in Table 720.041
1b7246df-cbd7-5cbf-9a5b-ca1d2c71ff10 | note | METHOD: Verify
1ceac43a-7569-5685-a350-0eb5d4662098 | note | FREQUENCY: Prior to Commencing works
33b509cf-743e-57b1-837c-d5a55af530cf | note | CATEGORY: N/A
344105e7-5c42-5cb0-b42c-4525d91a1c56 | note | RESPONSIBILITY: SE
32e56be5-e99c-5e85-9b07-6dac7d74a71f | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 2.4 Supply of indigenous plant stock
8b4518e5-5c0c-55bb-b063-20022d40d415 | note | REFERENCE: VicRoads Spec. Cl.720.04
1d317e1c-69f2-51df-997b-4c5eec71383d | note | ACCEPTANCE CRITERIA: A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
f30f5789-93f8-5263-b8f7-b26502ffe75b | note | ○ The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
154ee7e3-835e-5590-82f8-8cbd4b276f8b | note | ○ Species name
9f077c98-adc0-5698-bd32-014a168c9bce | note | ○ Storage code
7d1fe96b-5ef9-556e-8155-e813dbb458f3 | note | ○ Collection locality - Latitude/longitude or AMG
ca4a33f6-65a7-5069-b9e7-d1a999cd901c | note | ○ Approximate number of parent plants sampled
af677e9a-ed09-58d0-b16f-00127217150a | note | ○ Approximate number of plants in that local population
b3e276e7-e834-5223-8d1c-24dff01a9531 | note | METHOD: Verify
66c80012-2b7e-5428-b1a5-9f43c7be2e2f | note | FREQUENCY: Prior to Commencing works
bb543e17-9226-5806-ae3e-81ddecc941c9 | note | CATEGORY: N/A
02d533e2-a49b-5ff6-8ed8-2788ae0dd5fa | note | RESPONSIBILITY: SE
cbe28a41-160d-5842-bb85-dfba2a817eaa | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 2.5 Supply of grass seed
c99b379a-5b8b-5ec8-8561-9aa3f34c2656 | note | REFERENCE: VicRoads Spec. Cl.720.04, Table 720.045
08fd77f4-c1ee-53a4-b2b8-5ed67c2c50ee | note | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
9fbaa4b7-00bf-5d89-9ff1-f39670e3042a | note | METHOD: Verify
b22d5ae7-302a-5468-a949-4ae856a7bc1d | note | FREQUENCY: Prior to Commencing works
d222a10c-87a6-5439-9055-81bad519245a | note | CATEGORY: N/A
8da02d3d-5c3d-526a-99c4-cb95296e3f71 | note | RESPONSIBILITY: SE
9940476a-8a28-58d8-9bca-d338caf0507b | note | VERIFYING DOCUMENTS: This ITP
| section | Pre-Construction Activities
| checkpoint | 3.1 Planting Section Approval
b65a7942-c379-5f6f-80ed-c6a775beb66a | note | REFERENCE: VicRoads Spec. Cl.720.06, ECO-LANF-005
cc8f86ef-89dd-5c05-9ffb-c261cc2c706f | note | ACCEPTANCE CRITERIA: Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
155ecc20-7b2f-5426-9674-d2db1fba7ec9 | note | METHOD: Verify
71e22678-dbec-5513-bb8e-0daf935777b8 | note | FREQUENCY: Once
1354093d-3f3e-5793-a21b-56fbd8164fea | note | CATEGORY: HP
cc257f75-bc54-542d-8f0c-d9fe8d2ecfa7 | note | RESPONSIBILITY: SE
1ff84ad5-9099-53d5-9036-ac3c8d43429a | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Pest and Weed Control
e20e3580-2a4b-5374-9d50-c7605d3fb77f | note | REFERENCE: Cl.720.05
d5f32974-4a6e-52eb-8383-4a16cc2c5a15 | note | ACCEPTANCE CRITERIA: The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
4a67f82a-aa51-5cea-9952-715276c45c25 | note | ○ Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
df60d898-00d4-59da-9733-e26f305dec15 | note | METHOD: Verify
630b7990-f60c-512c-a117-33fe229abd64 | note | FREQUENCY: Once
7037519d-4963-5ba5-9687-96d2d4f9a68d | note | CATEGORY: HP*
5ea1f889-0dab-561e-9d3b-9139884f160d | note | RESPONSIBILITY: SE
f774c2f2-af68-5001-84a6-d29f05ba67f0 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 3.3 Setting out planting areas
9d9444c9-cb08-5097-8d35-23b4a7b3e0ea | note | REFERENCE: VicRoads Spec. Cl.720.06
a0773845-4fbc-5183-97dc-c4e3d5ac9aa1 | note | ACCEPTANCE CRITERIA: Planting areas are to be set out to the location and shape specified in the landscape drawings.
ccf7ea44-7dca-591d-be4e-e20042f20c82 | note | ○ Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
0f173350-b887-5c03-bafa-830d224cc685 | note | ○ Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
5b9d66c1-e5e2-559b-947b-54f2e59f9f53 | note | METHOD: Verify
3d33f578-9472-5a33-8557-d0dd70116cf2 | note | FREQUENCY: Each Applicable Lot
5b58681c-cb63-583a-b6e5-0d66ab78f0df | note | CATEGORY: N/A
b157ce70-7644-55d5-864b-6377df755580 | note | RESPONSIBILITY: SE
292b921d-240a-5ad4-9d3c-be339ebb49ff | note | VERIFYING DOCUMENTS: This ITP
| section | Construction
| checkpoint | 4.1 Planting
8c68a0de-3255-5b06-9b2c-8d49d66bc775 | note | REFERENCE: VicRoads Spec. Cl.720.09, ECO-LANF-005
20d41f8f-0df7-5f5d-a593-3fa20adeda3f | note | ACCEPTANCE CRITERIA: All planting will be undertaken in accordance to Ecodynamics ITP ECO-LANF-005
5a8aa681-77a2-5536-adc4-a457826197c0 | note | METHOD: Verify
3eecb841-2196-56dc-888c-0ba9b66ac250 | note | FREQUENCY: Each Applicable Lot
fea47b1e-fdb4-5e15-aacd-bcdc2a185b67 | note | CATEGORY: NA
9a859799-7f71-5e63-bccd-d71f1afd410e | note | RESPONSIBILITY: SE,Foreman
002ead03-0f72-57d8-aa16-5fd2b2be9207 | note | VERIFYING DOCUMENTS: This ITP
| section | Completion
| checkpoint | 5.1 Site Final Inspection
05e2979d-38e1-5855-86c4-4abb76bc9410 | note | REFERENCE: ECO-LANF-5
48a0c873-76f7-5ea5-8363-b7bd979ed555 | note | ACCEPTANCE CRITERIA: Ecodynamics ITP signed and completed
b71ece6d-55c5-59f7-8c7b-cc8a853ae1ed | note | METHOD: Document review & Site Inspection
347edf41-9672-5485-9028-720ea2fe0a60 | note | FREQUENCY: Following completion of planting works
3e7f67c2-993a-59f9-953e-a7dd7a30d6f9 | note | CATEGORY: N/A
527ee9fe-9c3a-5f9a-8e18-bfa1f6c11b98 | note | RESPONSIBILITY: SE
81b1bbec-92d6-553c-b010-f5a78575be4b | note | VERIFYING DOCUMENTS: Sub-Contractor ITP completed, signed and to be attached
| checkpoint | Final Inspection
2a93ad05-664d-59cd-9a39-bbf0e435246b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
30a1e4af-df64-589a-bcf2-3657df876019 | textbox | Name:
f6b59cf9-e474-56ef-b772-66881a948d8b | textbox | Position:
d8dad1c5-ddf9-537a-9427-535b04088170 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-164-CIV-PSDS-Embankment Fill Rev 0 | itp | ITP-164-CIV-PSDS-Embankment Fill |  | 19668da7-f920-41a3-8212-8f8ae77b7856
| section | Referenced Documentation
| checkpoint | Referenced Documentation
6179fb4a-3323-5a36-af2e-44ecd146d785 | note | Document Title: ITP-164-CIV-PSDS-Embankment Back Fill
dc917256-716e-5612-82c8-506d29c8cec3 | note | ITP Description: Embankment Fill
03eaef7c-bfdb-522e-aafc-f298c72ff86b | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
fe47e396-935b-577f-ba36-483519e53057 | note | Discipline (e.g. CIV/STR/RAIL): CIV
f8fdb6e8-71e2-5fc0-a6d5-e271290d4013 | note | Revision Number: 0
aabe8a55-5411-5ad0-a098-387c27897cd1 | note | Revision Date: 13/05/2024
d2f43e34-c1b6-575b-b3fc-ff2c29cbe99a | note | ITP created by: Anthony Pearson
18649b95-7ced-5486-963d-f6596cd2ef41 | note | ITP approved for use by: Victor Mira
7fe9bc18-765f-57d1-9a62-08afdb7d1df9 | note | 1.1 Non Dependent
f6f2a525-0d1b-5127-a685-bbe89c23120c | note | Reference: IFC Drawings
9532f0f5-aff0-55a2-ae59-547eb131623f | note | 1.2 Non Dependent
ab347d5c-b864-556e-a765-34d949924be0 | note | Reference: VicRoads Section 173 (Oct 2008)
3f1a68ae-026c-581e-96b1-a514f8910831 | note | 1.3 Non Dependent
bdd5d18f-d94a-5910-b635-81f38845b69c | note | Reference: VicRoads Section 204 (Dec 2015)
0b659a3f-2fbd-55cc-8d76-04c3aabd91c2 | note | 1.4 Non Dependent
44677b09-b743-54ba-86f1-2b34f248dc22 | note | Reference: Code of Practice RC500.20, RC500.5
| section | Preliminaries-Materials
| checkpoint | 2.1 Material Conformance
cf166ccb-c22b-506a-a29b-9aef9dc215ab | note | REFERENCE: IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848) Section 204.04 b) Table 204.041
1b3fdc30-1442-531d-8e5b-eddf954ca2d4 | note | ACCEPTANCE CRITERIA: CBR ≥ 8% and Swell ≤ 1.5%
86517c28-988f-558d-81e5-f494dc25d3c6 | note | ○ Max Permeability = 5E-9 m/s
76ca5bf1-bfc0-5edf-bff6-db849127aef5 | note | ○ Grading:
3afe5566-3eab-5645-bf1f-465ef32513cb | note | 75.0mm 100%
a0ace503-d8c4-5043-8873-887fc131686a | note | 4.75mm 40-80%
62894fa2-a8b3-5c32-836c-5f2810eb072c | note | 0.075mm 10-40%
dc67d07f-abba-5965-8904-1593db449146 | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
27fc60bb-9e84-5ca2-9bd0-a59073163f72 | note | Reference: TeamBinder Material Approval Ref No.
93f72e97-0a8d-562c-9fad-68261c9927e3 | note | METHOD: Document Review
b7024fde-cb06-5e66-9403-49b4ee6b3192 | note | FREQUENCY: Once, for each material type
995c2bc1-8f1f-5eef-ad76-06dd520ff22e | note | CATEGORY: HP
13b94b86-5844-5d9b-a04f-10e66b04ead1 | note | RESPONSIBILITY: Nominated Authority
46ba92e1-ebec-56fb-a8bb-948ffa591a7b | note | VERIFYING DOCUMENTS: Conqa HP Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documentations
| checkpoint | 3.1 Pre-Commencement of Fill Works
aab2b68d-40a3-5291-812a-5d66f5bac028 | note | REFERENCE: Section 204.10 (b)
746d64ef-bb0c-5b1c-bdfd-ef4513874d4d | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
595accc6-bf6e-58f7-9c4a-512d4d3359b8 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
fb657644-452a-5df8-86bf-5544f77906fb | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
65078260-c556-5ae2-a02d-05e91ca93250 | note | ○ Reference: Subgrade Preparation / Previous Layer Lot Number
11895e09-5590-51c3-92e3-de0ebf9d6c58 | note | ○ Attach: Lot Maps
e6738690-a4d0-5736-83b2-529ac1959d63 | note | METHOD: Visual Inspection
e732c8a7-c2ca-588a-af29-989804c7a07c | note | FREQUENCY: Prior to commencement of fill works
d9c590ef-7ac9-5b1c-b450-fe826db6cc6e | note | CATEGORY: HP
d6e45e20-c3f3-528e-ac1d-392079ccd814 | note | RESPONSIBILITY: Nominated Authority
03accab2-63f8-57d6-9f4a-f65c5d2b02f8 | note | VERIFYING DOCUMENTS: Conqa HP Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set Out
fb74f2dd-b2f9-52c1-a602-15f07403feb2 | note | REFERENCE: IFC Drawings
2d10f03e-36ea-50ff-aef5-c961d2c83095 | note | ACCEPTANCE CRITERIA: Set out pegs in place and clearly mark out limits of works.
f3c9ae2c-0ecb-55fc-bee4-7e8c962f7735 | note | ○ Attach: Lot Maps
6fce1be9-3024-5bfa-a021-e14bf0b7212f | note | METHOD: Visual Inspection
e26a73ca-1b4f-5fd7-9ff6-169b28e66bd3 | note | FREQUENCY: Prior to commencement of fill works
335dc526-b9f9-5956-9120-7040da02b816 | note | CATEGORY: HP*
7856261c-1d97-5399-9bc7-d93d088fd1cf | note | RESPONSIBILITY: SE/PE/SPE
a526db12-1d11-5c4b-9155-62f2c0da5e2d | note | VERIFYING DOCUMENTS: This ITP Signed Off
| section | Type A Fill Activities
| checkpoint | 5.1 Placing of Fill
85edee00-bd22-5399-a42b-f0743fedf403 | note | REFERENCE: Section 204.10 (d)
b5a432b5-8f94-50d2-b5c9-1f57b443a3bf | note | ACCEPTANCE CRITERIA: Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
df0b6eca-0d81-5637-9965-4456b2116b90 | note | METHOD: Visual Inspection
e03a248b-7895-5cec-ae1d-7235436ba10e | note | FREQUENCY: Each Lot
d4d6bbc9-eca3-58b3-9eea-967b143fc91d | note | CATEGORY: WP
e29a208c-16ba-5d01-a808-dc882235967a | note | RESPONSIBILITY: PE/SE/Site Supervisor
577defbd-539b-5f1e-89be-1c1c72d51e47 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.2 Fill at Structures (where applicable)
1dff3b97-ab3d-51ab-b7df-9337cd3ec530 | note | REFERENCE: Section 204.11 (b)
38a71fa1-18fd-5890-a43e-9fae67f160f1 | note | ACCEPTANCE CRITERIA: No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
cbb06157-7985-53c6-9024-ca499fafb982 | note | ○ In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
53502727-dffd-55ff-b3e7-61451899abbc | note | METHOD: Site Inspection
ff4b11ae-f017-5a6a-9a5f-33f55ecff30c | note | FREQUENCY: Each Lot
1ef85be0-4c8d-5695-a41b-ffffbe9d8a34 | note | CATEGORY: HP*
8b6db965-db68-540f-9592-df7441f79357 | note | RESPONSIBILITY: PE/SE/Site Supervisor
3649a4bd-e51a-5c4b-a410-dbc798aa8651 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.3 Test Roll / Proof Roll
9f3d77a2-3595-5a3b-8140-bcba5ae56f40 | note | REFERENCE: Section 173.03, Section 204.12
e33797bb-38b2-5fe1-86d9-01c867889013 | note | ACCEPTANCE CRITERIA: Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
ae3306fb-af2f-53d2-923d-1b909a1fc0a3 | note | The plant for use in proof roll to comply with the following requirements:
b064e97c-821b-53c5-b4e4-2204dc02287f | note | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
f25f602d-2038-56d4-a945-0a73ce951b27 | note | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
c4581257-f29a-5aae-9cf6-85b15696579a | note | METHOD: Visual Inspection, Test Roll as per 173.03
2ced9da1-52c0-524b-9508-b436741f8dfa | note | FREQUENCY: Each Lot/Layer
1bbe000c-fd1d-5917-a85d-0f01327cd51b | note | CATEGORY: HP
28002f66-a349-5a9a-af38-e28936d3d914 | note | RESPONSIBILITY: Nominated Authority
5e22ab00-97af-517b-8fc7-e4cf1d2fc9b2 | note | VERIFYING DOCUMENTS: Conqa HP Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Compaction and Moisture Content Testing
146a3e17-83c2-5866-afb6-5ed0964b58fe | note | REFERENCE: Table 204.131, Table 204.142 Section 173.04 (d)
cc6438e3-894d-520e-b933-b2fc9d8d8ad2 | note | ACCEPTANCE CRITERIA: Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
341be7e0-3a8f-538f-90c4-5499cf7419f6 | note | ○ Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
8d8a1b93-71cc-5c22-b2ab-1edc80201ceb | note | ○ Minimum Testing Frequency: Every second lot
bc452439-0600-500e-8cf3-2ab11005cce9 | note | Lot size
471f71fc-eea5-592a-abf7-1e8dc9562212 | note | Type A Material - the lesser of one day's production or 5000sqm
d7cbd8da-ff7b-53e6-b0e3-a523bf2248cc | note | Or
638114c2-3784-5c07-9ce3-6ad0697b068c | note | – Testing Small Areas
d597b076-ff17-5dad-847d-47971c70ff28 | note | ○ For earthworks and pavement construction any lot which has a surface area less than 500 m2 may be treated as a small area. When testing a small area as a lot and where test requirements are based on characteristic values of density ratio and/or moisture ratio, acceptance of the lot shall be based on the mean values of 3 individual tests. In this case the lot will be accepted as far as compaction is concerned if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
5b5cc700-bd5e-5aca-bf4b-df4dd0465328 | note | ○ Attach: Compaction & Moisture Content Test Results
b4275c70-7dfc-59ad-a9d2-ec5a6e8d2526 | note | METHOD: Review Document
b1cec64b-e924-583d-b79c-ea10a6014a5d | note | FREQUENCY: Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
17f420d8-9d5a-5d57-b89e-ccf1e056c10f | note | CATEGORY: IP
a1f9707f-e3eb-5a25-9f2c-69a1e82f2672 | note | RESPONSIBILITY: SE/PE/SPE
8909fd70-800a-53b9-80ef-b9ee238e3f52 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 5.5 Post Compaction Material Property Testing
297f9b56-ac4f-5dd0-a8c4-e56492983ae2 | note | REFERENCE: Table 204,041, Table 204.141 Section 204.14 (a)
c9ad3583-fe00-5428-ac99-e4156bf40649 | note | ACCEPTANCE CRITERIA: Material Properties:
829a20bb-21c2-514c-ad20-45f102c644f5 | note | ○ CBR ≥ 8% and Swell ≤ 1.5%
23e088bb-21b8-5436-bef2-2da957fa0708 | note | ○ Max Permeability = 5E-9 m/s
d4862f53-9236-5c02-8b0b-a1ddbd0cc611 | note | ○ Grading:
1b9e518a-d835-5181-aead-fd8661f64db2 | note | 75.0mm 100%
3be13523-d741-56bf-bb4e-6c841c6897c4 | note | 4.75mm 40-80%
c45c1b47-318e-5db4-8866-6b9f3433e070 | note | 0.075mm 10-40%
e73d60c1-a538-53da-a8aa-53620ca3732e | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
deda2c07-313f-552d-96f7-645d4e39eb4b | note | ○ Scale B:
f29cf540-1cb1-5390-9623-9f55a27b1c03 | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
504312a2-4850-57d7-9f65-4184d3401827 | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
a319871f-4617-59e6-bff5-9bfe8d256e51 | note | Attach: Post Compaction Material Property Test Results
2f459f51-77e0-5e53-89ea-9fd919843f52 | note | METHOD: Review Document
c3bc250d-8dc5-50af-8492-2a72abca9f1a | note | FREQUENCY: Each Lot/Reduced Testing Frequency, Refer to Section 204
365a00b6-c1af-55ef-a2c3-f7cd92319a4b | note | CATEGORY: IP
dde5f18b-d185-5852-a011-051633acbd83 | note | RESPONSIBILITY: SE/PE/SPE
be7e2dc2-fe3a-529e-838e-a2161ab5a6b5 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| section | Post-construction Activities
| checkpoint | 6.1 Survey Conformance
b6be9455-365d-52fb-a8b7-13bd1de663a7 | note | REFERENCE: Table 204.031
1c8b496a-eee2-5d93-8172-fa84cab8536d | note | ACCEPTANCE CRITERIA: Level tolerances (Scale B):
03ebf2d8-6d84-5320-a62b-4d460c1d19af | note | ○ Range Mean = +5, -25mm
3f8346e5-b99b-5466-b23c-fcb3dfcddf47 | note | ○ Max Standard Deviation = 15 mm
494d6802-58c9-5a22-aeb5-7f604ed39f3a | note | ○ 40 measurements per lot
45b80ee3-ecd5-54d4-bf3b-a70798b7153d | note | ○ Attach: Survey Conformance Report
0574e57a-ed8c-5466-aa8a-b1c7e5bf826d | note | METHOD: Review Document
1b4e3815-f7d8-5e45-a6f5-a78373a87e10 | note | FREQUENCY: Top of Type A
beed8b17-ee3a-520d-9acb-b2faf7592253 | note | CATEGORY: IP
06c01f34-309a-5c70-97b6-6658fa762db7 | note | RESPONSIBILITY: SE/PE/ Surveyor
00d1db7e-ff17-5764-a632-4bebc6d844f4 | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
bad795d8-8a4b-5f08-aa1f-411065b6ba20 | note | REFERENCE: MRPA Quality Management Plan
91a95581-562c-50de-8c07-48b2cca8d9f4 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
18471690-e2bc-5e0e-8a72-1f8b5371dfbd | note | METHOD: Document Review
3997142f-e131-5f2b-b3cc-ce42f90344c7 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
7e3f666e-47d0-5122-84ae-faa474946710 | note | CATEGORY: HP*
3fccbe42-6cdb-5c10-83d9-9bdf0cdbd06a | note | RESPONSIBILITY: SE/PE/SPE
1e7f1b1a-12db-589a-93e7-ab5963689c2f | note | VERIFYING DOCUMENTS: This ITP Signed Off
| checkpoint | Final Inspection
48318fe3-076c-500f-955e-962e64483e04 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0ec5709a-e1eb-51de-82b1-b068420dd84a | textbox | Name:
4fe69126-c93f-5032-bdf3-4d9470c81eaf | textbox | Position:
a3820a9f-acd1-5e46-88a5-61834809c9c9 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-173-STR-PSDS-Precast Barriers, Kerbs and Walls Installation Rev 0 | itp | ITP-173-STR-PSDS-Precast Barriers, Kerbs and Walls Installation |  | a079a6db-7a08-4bb6-8b02-004ceedc4e58
| section | Referenced Documentation
| checkpoint | Referenced Documentation
2875bdc2-9e5b-5c92-bf89-a915fff2475b | note | Document Title: ITP-173-STR-PSDS-Precast Barriers, Kerbs and walls
8d8632c0-bbc7-568e-99cf-2eff2340a83d | note | ITP Description: PSDS-Precast Barriers, Kerbs and walls
67ee2262-4dae-527d-b911-d9144a6e98f4 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
49cd5e3c-e9be-5103-b37d-98bf26d3f597 | note | Discipline (e.g. CIV/STR/RAIL): STR
991b9420-9123-50fb-b132-ce6f767bc137 | note | Revision Number: 0
9dfee483-39b1-57b2-adbc-e7b08d160c49 | note | Revision Date: 28/05/2024
0ceba7f2-e50d-5bc6-9898-b519e0c2ef68 | note | ITP created by: Mathew Velcek
159f5982-6608-5ec0-b015-3a18a018010f | note | ITP approved for use by: Victor Mira
34251d7e-926e-5be5-84fc-c8a437688054 | note | 1.1 Non Dependent
928ed358-efe6-5e56-bebf-c25ad669cd02 | note | Reference: VicRoads Section 610 Feb 2020
4ecfea82-8089-5d08-a16c-e706477f89b9 | note | 1.2 Non Dependent
987e6f29-1b82-5c64-9731-23d959a6d40d | note | Reference: VicRoads Section 620 May 2009
0b7c1fec-3621-5ec6-a88b-9238b2b61220 | note | 1.3 Non Dependent
4c5210e1-7e8e-52cb-9ffe-559f9c0d4cf3 | note | Reference: VicRoads Section 630 October 2013
878c5957-7153-5125-b203-5382f013683b | note | 1.4 Non Dependent
7da453c2-ab38-53b7-ae40-d358978ddf48 | note | Reference: VicRoads Section 670 October 2013
572477f8-edc5-51a5-8624-9ac7aa0fff1e | note | 1.5 Non Dependent
c255780c-e75f-54e5-8d44-4cc2a128b6f1 | note | Reference: VicRoads Section 671 October 2013
| section | Preliminaries Materials
| checkpoint | 2.1 Grout
a3456562-b3d4-5a26-bbf0-4dd823baa6c6 | note | REFERENCE: MRPA Quality Management Plan
4e8166bf-f4a4-5cc0-b1c1-bcdc3df75ea1 | note | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
ef35b6ea-dfa6-5894-ac33-f8602bbfb942 | textbox | Enter: Teambinder Material Approval number
48d45a13-5642-5b02-a407-76c8e8220410 | note | METHOD: Document Review
82fb84b7-af79-523b-8c04-dc0eb3b21b68 | note | FREQUENCY: Once, for each product
3f11426e-3415-531f-8d50-e958047c8ce1 | note | CATEGORY: HP
b77a0430-e272-5fca-9424-696953766be6 | note | RESPONSIBILITY: Nominated Authority
9f8afac2-0c05-50e7-876a-e03c7ee03e16 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Documents
| checkpoint | 3.1 Precast Elements
e8b56702-5572-57a2-87d3-8f5edc6101a2 | note | REFERENCE: IFC Drawings VR 610
e36112cd-8cce-529b-abee-45329e483ed3 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
16c0bcb9-6cd9-556b-b5a2-85b07c9743be | note | i. Certificate of Compliance / Birth Certificate
d4f8b53f-4c99-5cd5-9966-429bfbacb4fd | note | ii. Compressive strength test results
3f6cbab7-1788-511e-99dc-afcf0310218d | note | iii. Precast Lifting Design
2caeedd4-8529-54ac-a77b-741aadb91413 | note | iv. Pre-pour check sheet / ITP
50f16cf6-c076-5128-b4bf-532e1eb5f2f9 | note | v. Post-pour check sheet / ITP
1291f551-ae45-5370-92e8-ec7d6ac9e063 | note | vi. Covermeter check record
f2455abd-1e3b-58e7-9a0a-5d5485eb6f8a | note | vii. Record of dimensional measurements
729212d8-6b59-5cd7-a1e6-0c38addf66ac | note | ○ These documents are typically stored in a MDR Lot in Team Binder.
9750d258-6044-56cb-9c87-f3905e58b2a9 | textbox | Enter: Teambinder Material Approval number
2eeafe75-b75a-5fd6-bf65-b7f70df148b3 | note | METHOD: Document Review
ed9108f9-0e6f-5e31-9bab-ea8813cf7012 | note | FREQUENCY: Each element
40999c1c-1ec5-5f14-8934-44573afdf295 | note | CATEGORY: IP
40acc07b-8da9-54fd-b8a1-36699ca392c5 | note | RESPONSIBILITY: PE/SE/SPE
381308dc-1de2-5113-8746-3bd95ecf8dc7 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 3.2 Bridge Deck and precast wall / Foundation Compressive Strength
d0b2e011-299b-5cba-9743-96161313689a | note | REFERENCE: 671.03
bca6b599-60ec-52d4-babd-053817aa4b14 | note | ACCEPTANCE CRITERIA: For Precast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
581e09b2-38d8-59f8-9deb-44c6348e3045 | note | METHOD: Document Review
8e273a8d-b6b6-557c-8996-aa01164752c9 | note | FREQUENCY: Each installation location
48f1147d-e2dc-5d31-842d-3e3f3780a694 | note | CATEGORY: HP*
2da1037a-50a4-5c9a-9c0d-aab49398c579 | note | RESPONSIBILITY: SE/PE/SPE
616d7d3a-7561-5a31-a250-fd6b55e65fbc | note | VERIFYING DOCUMENTS: This ITP
| section | Pre-installation Activities
| checkpoint | 4.1 Survey Set-out of Precast Elements
21bcf52e-ed4b-5e12-9369-df61a0b67266 | note | REFERENCE: IFC Drawings
5611b91e-365b-505d-8464-1df9f47b8e97 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
07d6f195-8ec6-5e1d-9449-e88c899a46a8 | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
1c6d80fd-5e9a-53e8-b9bc-5fc8e92e73b3 | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
6fe897b2-7a14-56cc-b5c8-98b32c16d17e | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
ed690a27-5a5b-5e16-bfed-fb17a732d59f | note | METHOD: Measure, Visual
f80a4125-722e-5943-9206-430c22f46565 | note | FREQUENCY: Each element
5b55fc29-6d50-529c-82cf-8dafca13bb29 | note | CATEGORY: IP
4260aa0f-c9b0-5e3b-ace1-93ed5988673e | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
8d0b6940-a494-564f-ae8e-b94b1706e929 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
f376ffc9-08d3-5147-8465-79ced4a92054 | note | REFERENCE: IFC Drawings
0ad923cb-bab2-505d-bcb7-22fe6ea51525 | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
f43cfd74-effe-5ec0-bf6e-b4e7feb8fd79 | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
204e29df-9f27-5199-b08b-38bf72d4241f | note | METHOD: Measure, Visual
a4c5a8cb-d656-51fc-ba22-35d69e0275b6 | note | FREQUENCY: Where applicable, each installation location
f21c2602-d3b3-5cc4-8cf2-1d23279d3c42 | note | CATEGORY: IP
7b9d9e7c-c327-5f6b-8fdf-3c3d0d5c504b | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
33f7fc2a-2b7c-5e14-b10b-499acfb379f5 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.3 Bitumen Board and Ableflex placement
4ea34c4e-f356-5ca4-b46e-61af6fc2591c | note | REFERENCE: IFC Drawings
8d20a65c-cc88-54e4-b9cb-26754191fea4 | note | ACCEPTANCE CRITERIA: Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
4e68129a-6237-5274-a166-d3069beb206a | note | METHOD: Measure, Visual
3e0771b0-fe38-57b0-8fb4-46925b645baa | note | FREQUENCY: Where applicable, each installation location
01f0c0cd-3ab1-50a2-9f05-bf09594eb2ae | note | CATEGORY: IP
be72535f-9778-5925-b66a-28858196ce00 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
d9d59c39-94ac-5023-aa84-31246cab7918 | note | VERIFYING DOCUMENTS: This ITP
| section | Installation Activities
| checkpoint | 5.1 Precast Handling
09b455a0-a56e-5beb-a7d1-1e9614c33208 | note | REFERENCE: 620.07 Crane Lift Study
b8ee3ad8-7f0e-5a22-93f8-a6b3d49def90 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
4874c35d-31ee-561d-80d0-0533424af0a4 | note | METHOD: Visual
08859a1c-80bf-5ed6-b788-80243b5d3387 | note | FREQUENCY: Each element
cfd545bb-3d1b-57ca-a7a5-6a927cb40f51 | note | CATEGORY: IP
fe87f47d-2c86-5404-8403-42fb342b8213 | note | RESPONSIBILITY: SE/PE/SPE
394d9bc3-11a5-5b59-9596-881dbcbd689e | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.2 Precast Placement
f52d51a7-60df-50a9-acf7-1e46c838253c | note | REFERENCE: IFC Drawings VR 670.05
c7b13a73-ab29-514c-8b3a-b0261d353a3a | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
a9dafc4e-756b-51cb-9193-4892e7dd7576 | note | Adjustments to be made to achieve following tolerances:
dcd37ca8-575b-525d-960b-2ec8dc965e8d | note | (a) Departure from plan position: 25 mm
3b7cd586-fc61-5096-bfd7-b1be29488900 | note | (b) Departure from alignment: 5 mm
fee1f00d-02bc-56ee-a73a-0572585f4e80 | note | (c) Irregularities in alignment: 3 mm in 3 m
a78ac140-bdfd-5138-bf12-7900ec5f945d | note | (d) Variation in joint gap width: 3 mm
d323e058-5996-52f0-980c-3f29899f8abe | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
921ba8d0-5553-58ad-9d5c-fd4f1807e611 | note | ○ The nominal gap between elements is as per the IFC Drawings.
59b1d3e6-7482-5979-90e3-225de9aa8c35 | note | METHOD: Measure, Visual
5752fc4d-cb29-5b53-8601-88dbbe2f3a03 | note | FREQUENCY: Each element
b3e7f1a9-c569-5772-82d9-c45d1d17c3eb | note | CATEGORY: IP
7a471c45-2002-543a-a7cf-82aa0d155eb7 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
ed2851a8-230a-5499-960f-968e5862a252 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.3 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
431d2ee7-8605-5af7-b2c0-a03d4f661223 | note | REFERENCE: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
5ebad80d-d6f8-5c89-9b31-dd0cfddf84c3 | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
bf144b24-2690-549c-88fa-20fd498169aa | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
cfdcc07b-0d37-5542-a92d-5066d8769a7e | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
5104f8e9-1720-5483-a421-5223c50d58d6 | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
3d9b383c-66dd-5362-a2bd-06f6ff287c08 | note | METHOD: Visual
cf765eb9-c78f-517f-806f-bc950e9de805 | note | FREQUENCY: Where applicable, each bolted connection
f5a3a7f8-c8b3-54e8-a127-715b1b14a77c | note | CATEGORY: IP
f97403da-d7f9-5f8d-8fcc-bc160cce10ae | note | RESPONSIBILITY: SE/PE/SPE
2f9a9dee-205e-510e-8f91-2157cb161f9f | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.4 Precast Traceability
f91308e3-536f-509f-bf22-dfef556f38e2 | note | REFERENCE: 620.09
d8736a16-24ca-51ab-bf4d-b5c04165a24a | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
0b4513e9-7abe-56fe-99ae-1a207d0979dc | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
e0236d5d-ee1d-55cc-80f4-bfe12ce1e85f | note | METHOD: Visual
77ce46d3-836a-5e4b-9a2b-d51e714a32d4 | note | FREQUENCY: Each element
ec556720-d5cd-5970-a443-72e4faae2e09 | note | CATEGORY: IP
d0e25c15-9064-5531-9d6b-6652a3b9cebf | note | RESPONSIBILITY: SE/PE/SPE
7776102b-719c-56bf-b36b-7cb3995840fd | note | VERIFYING DOCUMENTS: This ITP
| section | Post-installation Activities
| checkpoint | 6.1 Flowable Grout Pour
82a0c777-8c0c-584b-9ca6-3e32e99f3745 | note | REFERENCE: IFC Drawings
956657bf-62ab-56ff-8e8a-f946c9db2363 | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
132dc880-50f1-587b-b0e2-0ec2343d9625 | note | Complete: Grout Pedestals & Bearings ITP
8f0c6387-8e19-52c5-82f6-6693fc48a366 | note | METHOD: Visual
d6c4cb39-5add-506f-8343-9ae456eb2d12 | note | FREQUENCY: Where applicable
6aeeb822-8cb0-52d9-be7b-1da0659f2ee7 | note | CATEGORY: IP
772f446d-cbf5-58f6-9028-9939ed0b62ac | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
221c35b5-5ffc-5260-b4cc-fea32fdc2f2d | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
| checkpoint | 6.2 As-built Survey
55467e87-3b26-5089-b4d5-dd7f7f01e5dc | note | REFERENCE: IFC Drawings VR 670.05
2e0d2f85-b3f1-50b0-b7f9-72826e46b2d7 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
e7e3c088-8d6e-5abd-8d4f-d5ba93aaf0bf | note | (a) Departure from plan position: 25 mm
e88e5eca-5119-5d0d-8ff1-36b114f9a891 | note | (b) Departure from alignment: 5 mm
7e259d5e-e98b-5c67-85d2-077b94ffaf41 | note | (c) Irregularities in alignment: 3 mm in 3 m
19c37133-ab21-5bf0-b5f7-104d8946fea1 | note | (d) Variation in joint gap width: 3 mm
e7ea6fc8-074e-5d50-aead-2ac53d95dc62 | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
9b7e06ed-8de9-5584-aa03-76b634cd8ed5 | note | Attach: Survey As-builts / Survey Report
0d29ea00-4d9d-50f8-a8f8-d8a3b9a0407c | note | METHOD: Document Review
bf296c23-147a-5235-9247-5fc9b50826d6 | note | FREQUENCY: Each element
6b0df00e-f0b5-5c50-8fc4-941004da1a85 | note | CATEGORY: IP
032d373e-e217-5b56-986c-0f48c86f8596 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f52f8310-054c-58e2-8661-b5aed34f9766 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
085495de-e255-5a92-8bc9-491d6865aee7 | note | REFERENCE: MRPA Quality Management Plan
acb1b424-c0db-5421-afa6-fae72c75b8f7 | note | METHOD: Document Review
6086b81c-04a8-5c87-95e2-f7eef488873b | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
8cfc716f-9c54-5b08-b538-fe25479e2a46 | note | CATEGORY: HP*
fb80f5ba-6ab4-595a-9f0e-c608ee202ab9 | note | RESPONSIBILITY: SE/PE/SPE
e906e290-1c55-5899-8d73-7537043dd363 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | Final Inspection
3f9c069f-c730-5863-bb31-ae3ce1055070 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
82e60ca8-6e76-5e49-ad30-240349ba319a | textbox | Name:
7876fad2-933a-5dc5-9ea5-03887931fe21 | textbox | Position:
ece23079-af91-5ac3-be0c-87c074a0c220 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-179-STR-PSDS-L-Shape retaining Wall Rev 0 | itp | ITP-179-STR-PSDS-L-Shape retaining Wall |  | 6cc444d7-279a-4825-bb9e-4fe0c1bca739
| section | Referenced Documentation
| checkpoint | Referenced Documentation
8dc8a605-ef26-5f8a-9915-ad7f532785d3 | note | Document Title: ITP-179-STR-SSB-L-Shape Retaining Wall
293f6da6-bb30-5a5f-97b1-b084e7a62e5b | note | ITP Description: SSB-L-Shape Retaining Wall
c55f3433-6532-5ebd-96cd-5eeb7e484113 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
87717a9f-1a8c-5513-8421-2f10df694a73 | note | Discipline (e.g. CIV/STR/RAIL): 179-STR
781bfa02-0a55-52ff-82b6-e7dc137b8cf7 | note | Revision Number: 1
4bb4baad-fad1-5593-a146-50b00cf34843 | note | Revision Date: 24/06/2024
32da156c-add4-5bcd-856f-35f23c8388ef | note | ITP created by: Victor Mira / Isaac El Zayat
44c831bd-877b-5702-ab9c-6876e9d2a84a | note | ITP approved for use by: Victor Mira
2b1f340f-c3b3-5aaf-9da7-74b34dea7e01 | note | 1.1 Non Dependent
5ec57cd5-9947-53b7-b319-f71908cd5519 | note | Reference: VicRoads Section 610
e785d2f5-dd09-5556-8285-6299938c216f | note | 1.2 Non Dependent
995c7a6d-549a-5c9e-ad28-b16818d62895 | note | Reference: VicRoads Section 610
058edb0a-d898-536f-b8c9-f6758226013d | note | 1.3 Non Dependent
eaccbb1d-c996-59c6-a5cc-1bd9cadd189b | note | Reference: VicRoads Section 620
4070b7b4-321c-526f-ad02-0d35bb2e2890 | note | 1.4 Non Dependent
70fc483b-7bdb-5325-a1b3-86a83f7d06a8 | note | Reference: VicRoads Section 630
ace8af0f-baec-50b1-ae60-13dcf80d1ccb | note | 1.5 Non Dependent
d192fd35-a0fa-5c8e-98ee-fde81febd224 | note | Reference: VicRoads Section 614
00a5ed45-d253-549c-be3b-f86e3c3adb96 | note | 1.6 Non Dependent
6ab5e9c5-8546-5e3c-bf5d-203bfc9c3708 | note | Reference: VicRoads Section 611
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
7fb3e2bd-3b10-588e-b086-0c81bf464c5b | note | REFERENCE: 610.07, Table 610.071, IFC Drawings
5a6ead07-6690-51eb-a08f-f039a9665343 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
627f4de6-06c0-515c-882a-db0a2230c6bc | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
57c7f689-43ce-58fe-8adc-1eacba2c563e | textbox | Enter: Teambinder Material Approval number
36b5e673-f6cf-5360-a122-e9342293cc52 | note | METHOD: Document Review
ef5e79f9-40d5-5c40-b0d7-5ebf588fc927 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
3a8bb93e-64fb-5a78-8d43-379b0e4873ef | note | CATEGORY: HP
12fa5bdf-4381-545a-88bb-a97120cf4355 | note | RESPONSIBILITY: Nominated Authority
6774a32c-38e7-57c3-9feb-7302c0669fed | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
5a24b3f9-7a52-5b07-be6c-9f7367e22669 | note | REFERENCE: 611.05 (a)
fa88d045-7f73-5cad-93d4-e4e1a3100a24 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
779c6e83-6740-56a6-b310-3e8790c8d495 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
21c30f1c-d4f4-58e5-b550-8638fc58e171 | textbox | Enter: Teambinder Material Approval number
ff55d4de-faab-5dfa-b503-48a2aa0eeaa7 | note | METHOD: Document Review
0fb4a1f0-1fb4-590d-84d4-9f8c064bcf9e | note | FREQUENCY: Once for each supplier, 14 days of award of contract
dd9011f9-d716-57f9-9845-9bb454a088fe | note | CATEGORY: HP
093bb1f3-5c68-509a-90f5-de402dbae3d4 | note | RESPONSIBILITY: Nominated Authority
598f2a95-ebc1-5a71-a0d8-82069893fc9c | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
e476a587-2f71-5310-b1b5-dd7d3f2b03f1 | note | REFERENCE: 610.26 (a)
bfcbb1e8-e8a2-542e-9210-ad6336366777 | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
5db4f6cc-de83-582b-a2c6-563ff8af2680 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
8e0f66ab-ebbf-5469-b935-5083c31335d8 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
84108cbe-8b04-5d20-a34e-9ac034299759 | note | Enter: Teambinder Material Approval number
c6b953bb-2254-5257-b85f-a0951de356e2 | note | METHOD: Document Review
a147857e-7d09-551e-9b7a-67d918955cc9 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
bb508bd3-b0f3-55d6-ae6b-aceba8f251d2 | note | CATEGORY: HP
50ea6c84-de08-5b47-8440-9633dc6ae271 | note | RESPONSIBILITY: Nominated Authority
396cebcf-b864-5b45-85b0-11b0c38eb7cf | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
cd09997b-6be8-54ec-9ee7-145bec1217c8 | note | REFERENCE: 610.17 (f)
8eef2bfb-7eed-5b08-85bc-959f0aa27752 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
dda13791-e23c-549c-a2e4-1bc401a21917 | textbox | Enter: Teambinder Material Approval number
d9a85183-1aa5-5755-a57e-52eebf748b12 | note | METHOD: Document Review
6eb5cff6-50fc-5c2a-bf08-114bafd16566 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
cdd38319-a78e-5e90-aa55-48082b443a0a | note | CATEGORY: HP
6ddcd428-bb2e-50a2-827f-c398f02d1c68 | note | RESPONSIBILITY: Nominated Authority
73f30a4b-bb7a-5d19-a705-8e63d4fc4f67 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
eee7d011-6365-5352-b100-d7a8c4f46aab | note | REFERENCE: 610.23 (d)
31540933-5d2a-5755-b04d-69a6d0aa7b97 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
77468ded-120e-516b-a45e-d70d55138d22 | textbox | Enter: Teambinder Material Approval number
db8e8122-f9b2-5b78-b325-5119d1ec1863 | note | METHOD: Document Review
95f0bc85-8807-5a08-ba68-b40ba97f120e | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
0a247edb-7cfd-5feb-9fdb-e29be3a43ebc | note | CATEGORY: HP
a6d3275d-d266-5beb-908f-ff0b754b3746 | note | RESPONSIBILITY: Nominated Authority
3622fd76-815e-5591-8d13-e1edbbc070d5 | note | VERIFYING DOCUMENTS: This ITP
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.6 Joint Sealant
16237af3-a48c-5843-a0d4-9857f3ace442 | note | REFERENCE: MRPA Quality Management Plan
a7ea7ee0-d0b9-5aa2-9309-3daa690e0f41 | note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
92391907-3820-54f4-be2f-c2dee529495d | textbox | Enter: Teambinder Material Approval number
94ec26d2-b660-552f-95c6-fa90cfbf37be | note | METHOD: Document Review
0ee563df-14e1-566a-9d81-640c231dced6 | note | FREQUENCY: Once, for each product
067fa70d-8166-5c86-ab9b-783a2b375a09 | note | CATEGORY: HP*
06f540cb-b8f4-50d4-a0a0-2e1be1f12e31 | note | RESPONSIBILITY: Nominated Authority
8668bc11-7c15-5758-84c7-5dc0611bdc27 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 2.7 Subsurface Drainage
63bdddda-b372-5f46-ab32-fcbd8ce28032 | note | REFERENCE: IFC Drawings
ba5159f1-1342-5b21-bfeb-7d8aeac8dbbb | note | ○ 702.03
c289537e-305f-5bb8-9fe5-75784f92d32f | note | ○ 702.06
5e2d8822-d579-5df3-bfca-96d46eb12b96 | note | ○ 702.07
05e9e307-d686-5c54-9d85-ec307131add0 | note | ○ 702.09 (f)
1ba4e9f5-a704-5780-b699-109f3f3af490 | note | ACCEPTANCE CRITERIA: Details of subsurface drainage as per IFC drawings
e40ef51d-ce8a-5e3b-bd6a-e08eff4e6750 | textbox | Enter: Teambinder Material Approval number
f5b3358e-80a9-59a9-ab30-e49191906040 | note | METHOD: Document Review
8a5b1e8c-c13e-52a6-9120-a38f5b0fb1ad | note | FREQUENCY: Once, for each product
478ea8d1-b27d-56d6-8ed2-b54e3b58b41e | note | CATEGORY: HP*
701009fc-53fa-5158-85a5-4b39a910c613 | note | RESPONSIBILITY: Nominated Authority
cda38c67-3446-5678-8031-a488a30f7023 | note | VERIFYING DOCUMENTS: This ITP
| section | Preliminaries - Procedures and Documentation
| checkpoint | 3.1 Precast Elements
60dee8ac-e5b2-52a8-8241-c3920747518c | note | REFERENCE: IFC Drawings
ca0da234-bf15-50a6-a4e8-a33715697856 | note | ○ 610.46 (a), Table 610.463
a68c6a68-f65c-5eaa-bd50-3aa68c2fea9a | note | ○ 610.47 (a), Table 610.473
74becef8-5762-5481-ab5b-83488048b64f | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
1dbe3b32-f48d-51a6-805b-de3ed10fab5e | note | i. Certificate of Compliance / Birth Certificate
d72c335f-3791-5b03-8f4f-7afd87f4f646 | note | ii. Compressive strength test results
ae0a07c9-d37f-5d8d-b93b-622115ce205f | note | iii. Precast Lifting Design
4978c8e6-22f7-517e-9052-8acdd2209cae | note | iv. Pre-pour check sheet / ITP
870acae6-d4e0-5415-8585-0c682c753977 | note | v. Post-pour check sheet / ITP
34b0927e-12a3-559e-b81d-e42757305bef | note | vi. Covermeter check record
53ee6ec4-4405-576a-a98a-99a1ffd2aea9 | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
bfb31fca-dffc-5bda-9c6f-864d099faf05 | note | Note: Different revisions of 610 have different clause numbers
fc17e778-0f8c-5cc3-862d-f25eda16f0b4 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
ae6dfe4d-6645-599d-a57f-a11aed6955c5 | note | METHOD: Document Review
51f72c0a-bba6-51be-ba6b-feb555b82d1b | note | FREQUENCY: Each element
acc9b320-7cec-5877-9881-b9418c7a99e7 | note | CATEGORY: HP*
0607855d-df2e-5e01-98df-bae1fff1c389 | note | RESPONSIBILITY: PE/SE
2b5a09b4-9295-5e8a-a184-f8aa432a24c0 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 3.2 Precast Base Slab Founding
94df8139-db8a-5d4f-83f0-ae63ab00e808 | note | REFERENCE: IFC Drawings
09a59fd0-a016-5bd2-9663-485b33e94771 | note | ACCEPTANCE CRITERIA: Foundation material beneath the precast wall shall be inspected onsite by a qualified geotechnical engineer to ensure that soil conditions meet the following material parameters:
1fef032c-06cc-53aa-b621-d754b10e965d | note | – Soil unit at base of excavation: Stiff Clay
fafb9396-aed2-51f3-af29-04a664bd6ca6 | note | – Minimum undrained shear strength: 75 kPa
a5c42e8a-41a3-51cc-acea-5758dc68356b | note | – Minimum L-Shape wall foundation depth: 0.2m
31a05f9e-ab8c-5180-88c1-6f4b7e27f7f4 | note | – Ultimate bearing capacity on natural soil: 350 kPa
91d76833-d7e9-5381-812f-d489886ea289 | note | – Factored bearing capacity on natural soil: 157.5 kPa
7aec6e33-7a50-58b8-b6c6-d2e94f6c9807 | note | Attach: Test report or Geotechnical report
649ca8cd-90d5-5fed-bcab-84a18a71b6ca | note | METHOD: Document Review
b71cd8e1-b58f-51f6-81b2-0d0af897532a | note | FREQUENCY: Each installation location
3d92ea82-967d-56fb-98b6-b1498ebdd6f4 | note | CATEGORY: HP
c335319b-6be3-5403-a158-87f13067f20d | note | RESPONSIBILITY: Geotechnical Engineer
c891041c-f084-5a81-bcbf-b95d662071f6 | note | VERIFYING DOCUMENTS: Attached Report
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Work Method Statements
532c6779-aecd-5eab-b66f-6b4af0f3b165 | note | REFERENCE: 610.18 (a) (i)
95c187af-fec3-5904-a892-cfca8d41b8c2 | note | ○ 610.18 (a) (v)
42927acb-1988-5f73-b792-7ac4a6d46bdd | note | ○ 610.18 (a) (iv)
182bc9ed-2bde-5857-827a-e4ec709e6b1c | note | ○ 610.17 (a)
e61fc9d1-ed2e-50fd-94a8-4230892e398f | note | ○ 610.23 (a)
07078e5b-1420-5600-a805-5d359f8420ca | note | ○ 610.46
8180af9e-4f4a-5482-ad13-73ce88c485bf | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
2d32a047-e9b8-5ad0-9c9f-d87d01d1a2f5 | note | ○ Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
594056f3-27bb-5e9c-9c10-aee931b7f7bc | note | ○ Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
a2b1dc02-3180-5114-9b96-10240ebd6f30 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority
20ea6ac0-2fbc-5cd1-b6af-ff90dfe473f0 | note | ○ Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
6f66c7dd-8374-5cee-9fd0-39f1997c46be | note | ○ Curing methodology/procedure to be submitted for review to the Nominated Authority.
b762e626-4267-58f8-8301-961d092d8d9b | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
841b001f-6aaf-5256-93c7-e312b5b508ec | textbox | Enter: Teambinder Approval number
b99ef53c-2b1f-5d8d-bacc-e052d27a5dcc | note | METHOD: Document Review
fcbc3c5e-1239-51b2-a1e8-f8f3993df4d8 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
753559a3-6ec4-5b4c-b94c-2eae9f74cef4 | note | CATEGORY: HP
bd5699ac-51ce-5087-bcd2-df3274e44200 | note | RESPONSIBILITY: Nominated Authority
2a4187dd-6c0d-531c-b0ad-628bb9de830e | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Temprature difference measuring-Calibration
6d384a72-a386-5a07-9819-6c582e648537 | note | REFERENCE: MRPA Quality Management Plan
b080f5dd-203c-5d40-95bf-5aff7cdf9ce5 | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
f09b028c-cf65-5c15-bb3c-9417cccacdeb | note | Attach: Calibration certificate
3f9dc22f-4bb9-55a7-993c-d52aa8ff6164 | note | METHOD: Document review
4e36cfe8-d030-5204-85bd-bf05433b7791 | note | FREQUENCY: Where applicable
14762df4-109d-543f-bec9-2107ad471727 | note | CATEGORY: HP*
f525d005-1897-570b-ae2d-2f19061d3dd9 | note | RESPONSIBILITY: PE
5ce77b55-f76c-53eb-b519-22beacc60719 | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
| section | Pre-installation Activities
| checkpoint | 4.1 IFC Drawings
bd8bf7dd-0108-529d-b1ea-fe3b18377164 | note | REFERENCE: MRPA Quality Management Plan
326894f0-e287-566f-b77b-8241c28dbb9c | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
84ec7ff2-c84f-51bf-8358-3fb30dcbfc9a | note | METHOD: Document Review
0b41deeb-9a44-5494-8689-cb230feadfea | note | FREQUENCY: Prior to starting Works and at regular intervals
7e21b593-3e88-5795-99f5-08ba52173054 | note | CATEGORY: HP*
5a93877e-267d-555d-990e-9ff9da3d327d | note | RESPONSIBILITY: All
31d9fe70-e088-526f-b7bb-660e97d7d4f1 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.2 Materials Inspection Checklist
ff338218-b53b-5a87-9c4d-85183b30ce65 | note | REFERENCE: 620.06, 620.07 MRPA Quality Management Plan
44b3dfa7-cd2f-51d0-9e18-5b5dc0de043a | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
8bf9842a-09e5-5745-aab5-7e4bd47aa871 | note | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
63a7a6fa-f6d9-5905-a2e0-de13fdd4bc86 | note | ○ Elements shall have unique identification and orientation marked (if applicable).
60c5099e-0a6b-5141-991b-ee4e1a0e296c | note | Complete: Materials Inspection Checklist in ConQA
2452448c-ca5b-586d-860c-bbf4edcdc3bf | note | METHOD: Measure, Visual
6c377621-481a-5e49-a117-45a3244eeca5 | note | FREQUENCY: Each element
b09f9fe4-e990-5f3c-9aec-797724f13341 | note | CATEGORY: HP*
a2ca0135-afa2-5edb-89fe-9760c1f13976 | note | RESPONSIBILITY: SE/PE
5e7062b5-f5d8-5d19-a8ac-38a8c7aec091 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.3 Survey Set-out of Precast Elements
d2f132e7-e836-5d8d-9c22-762b7cc6241d | note | REFERENCE: IFC Drawings
853d4c03-d0c4-55e4-b6c8-6ec80653e95a | note | ○ 610.46 (a), Table 610.462
dfb0e255-763e-517f-b17d-289e6199872c | note | ○ 610.47 (a), Table 610.472
9ae6bac6-4fac-594b-a5f9-d8ff6e537c16 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
5ece0cae-cd1d-5da3-aea3-9f0b56da8a58 | note | ○ Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
f56ce814-0b81-5c85-83e2-2397007586cb | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
1d637b79-9573-540f-a33c-36b2ca03d224 | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
de028222-8771-5473-98e5-8753e518e643 | note | METHOD: Measure, Visual
db8fdb18-7dc0-5242-9628-14ee95151225 | note | FREQUENCY: Each element
1b82920b-c31c-5799-b5b3-e92060a97b24 | note | CATEGORY: HP*
96b12b42-4c8d-58d4-9f75-f90c099c7742 | note | RESPONSIBILITY: Surveyor, SE/PE
44d0f986-4b5d-530a-a653-e168d7221665 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.4 Shims Placement
33074599-1e8d-57f6-81c5-9d0d17330752 | note | REFERENCE: IFC Drawings AS 3850.3
8268976a-de7f-52af-bcc7-428852c71a1f | note | ACCEPTANCE CRITERIA: Place the shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
67cdf639-dc25-5028-9e84-68cacf822cf7 | note | ○ Shimming should be a maximum height of 40mm, a minimum length of 150mm and a minimum width of 100mm.
91105e1c-4f7e-5b3c-b38f-295b9cee9585 | note | ○ Shims should be located at least 200mm in from the ends of the concrete element and bearing support.
18fa5d6a-8c4e-50be-ac0d-2170c44ec1df | note | METHOD: Measure, Visual
9f314e24-f682-54e0-a092-af676d602740 | note | FREQUENCY: Each element
814e39c9-7ebc-5779-8b54-a5f5444fb2fc | note | CATEGORY: HP*
fa5fbc71-c372-5d68-8320-9f7131b86f55 | note | RESPONSIBILITY: Surveyor, SE/PE
0407e5aa-21ad-564c-bcb2-849cc671d625 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 4.5 Survey Set-out-Concrete Slab
a8a67d5c-f4bb-5fb1-9181-9349707d2020 | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472
e82cf7ff-06f4-5fe6-8938-a73a3fe29eb6 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
8fa8a095-9448-5510-812e-d13119150082 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
884e6de5-527d-5372-a626-350ff08b89af | note | METHOD: Measure, Visual
fb881f9d-0e34-5828-85ed-a214420dfd4e | note | FREQUENCY: Each element
72103a6b-96c3-5526-94d3-db187955fc50 | note | CATEGORY: IP
ffe64f18-3101-58fb-bd36-f16d612f2a66 | note | RESPONSIBILITY: Surveyor, SE/PE
65d4f0e7-966e-590d-b52e-d2d43fc95364 | note | VERIFYING DOCUMENTS: This ITP
| section | Installation Activities
| checkpoint | 5.1 Precast Handling
9a75c69b-d039-56b2-8118-ba2eff8890d5 | note | REFERENCE: 620.07 Crane Lift Study
f34fef1a-68ae-551b-817e-46bcb142608c | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
b97c551f-4fd2-5438-bd27-02c40f846c0c | note | METHOD: Visual
90340610-ed33-5129-b4e6-e0375689eb31 | note | FREQUENCY: Each element
9bdfc2a7-2974-5297-b17e-88c2d9de24d6 | note | CATEGORY: SP
c2bc57d5-e9b5-5a64-80cd-dd2057f29b2f | note | RESPONSIBILITY: SE/PE
6d528d69-e4f0-5e6d-ac7c-008224ca2742 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.2 Precast Placement
38f55b3a-d671-5c51-911f-3ebe8ce2314a | note | REFERENCE: IFC Drawings, Temporary Works Design 610.27
6a25abc3-d6da-55c0-bbe6-d1e61a7170f0 | note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location and not released from the crane until any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
1e836bda-39d6-5da2-9bf1-78600e563472 | note | ○ The nominal gap between elements is 10mm as per the IFC Drawings.
7486589e-af24-566f-8017-4416a0a56629 | note | METHOD: Measure, Visual
26fc9d2b-558d-5678-9a63-65bae2a2c1e4 | note | FREQUENCY: Each element
e8ae9360-2f18-5c90-9e7b-aaf487916f4f | note | CATEGORY: SP
9878b46a-97c2-5171-8893-340412eb21d6 | note | RESPONSIBILITY: Surveyor, SE/PE
523b190f-45a2-5eb7-a292-11e83e1a80b0 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.3 Formwork Design and Construction
bb4b95ac-9883-56ce-ad92-e36927e81f40 | note | REFERENCE: IFC Drawings
29c7bc99-ab25-5b9d-aa31-c2e46e6d5510 | note | ○ 614.04
eeefafec-412f-576b-ac52-0fb1ca4d9a1a | note | ○ 614.05
58fb0155-b28a-5c72-a869-c22262f60b76 | note | ○ 614.06
90c20500-dd09-510b-b10d-7a2583c9efcc | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
ded32145-44a3-58b1-a2e2-12b7a4fabdec | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
ff7f6ba6-ae3a-5c34-bcbb-5710c4c7ce0d | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
bfc778cb-614b-5af4-b540-e51806df0ec8 | note | METHOD: Document Review, Visual, Measure
08f2fbb2-384e-5544-8000-af723bd6708e | note | FREQUENCY: Each type of element
4d3deada-35ad-5085-b3f9-1d93d72eb4cb | note | CATEGORY: IP
15caf62f-bf8d-59b3-bd63-a6904911dc66 | note | RESPONSIBILITY: SE/PE/SPE
dc29a4c4-4203-5181-af6d-526b66dee8fa | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.4 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
6caa7593-fae1-5348-8a56-3878e54f9aa4 | note | REFERENCE: 614.08
42a39835-df3b-5bad-bea1-a1de182b375d | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
df66ae22-d178-581f-9540-33e95892570e | note | Walls with heights less than 2.0 metres
ba26192e-3f11-502a-8894-63a4aa1b1fce | note | Attach: Attachment C
e40fb7fa-fee5-53a4-a0a0-b11dcd22ee5c | note | METHOD: Document Review, Visual, Measure
a8630825-9aea-55e3-ad0a-aa801d03acc8 | note | FREQUENCY: Each element (where 2m or less)
de51566b-0353-59ee-bbeb-3079ff051fca | note | CATEGORY: HP
cda9f5ab-4383-5b83-9e42-36e9db96c9ac | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
6df8e3d5-156b-52b9-8d88-def37e4a38a9 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.5 Pre-pour Survey
29fc3647-7cbc-53d8-a8d8-858675b89576 | note | REFERENCE: 610.47 (a), Table 610.472
37838b33-7d4c-53e6-9462-ebf116946092 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
e5e6ed10-404c-5218-8b81-8f160e72f05d | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
af7b9b6e-852a-548e-b557-715873f09d91 | note | METHOD: Measure, Visual
265c16d4-e3d4-5ce9-bb38-37d1e6fc621b | note | FREQUENCY: Each element
57a12102-09db-5212-821f-1cf34030b694 | note | CATEGORY: HP*
b1a5e961-02fc-54b9-ac91-383533c941a5 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
fb555d8c-cedf-5b77-96ae-14e1f8bcf024 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.6 Reinforcement Placement
9850fff6-a30d-5cfe-a3db-5bda6ff68588 | note | REFERENCE: IFC Drawings
6408e30d-378c-53d5-85af-fb1102f16ed8 | note | ○ 611.06
782f3579-14c1-5637-ab7a-e40be8035c6b | note | ○ 611.09
0530d512-8d75-548e-987e-b63bbbc4d801 | note | ○ 611.10
abf4e2ff-4c49-5119-8cbb-c843caac109a | note | ○ 611.11
fc90e846-7739-56ed-91c9-36411ccd4db8 | note | ○ 611.12
70d35b06-ba18-5200-87f4-9c9eeb1a0f20 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
a01166aa-c373-57e0-9961-439d9e7d0396 | note | ○ Projecting reinforcement is the correct length and location.
ef313ef8-0dd0-5467-aba3-6f058226b3a9 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
10b2d77d-01cf-55a9-b43c-235d1902996a | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
77552212-b85e-5b6d-94c6-da256758f136 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
6e17d000-36b1-5e9c-bce5-5418781d9dae | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
2328373b-469b-5b78-b57d-af9c12d76478 | note | METHOD: Measure, Visual
6d9fa6f6-2da1-5661-bc56-9f6f4434bf27 | note | FREQUENCY: Each element
0606129d-76df-5b8d-a81c-7c8c9c9fc9a6 | note | CATEGORY: IP
7e265d31-5029-5098-9d82-b3e9bf039168 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
1b861620-8f02-5d45-b44e-f31385dba0cc | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.7 Thermal Differential Monitoring
3080fcd6-1758-5bc7-a20d-c63522458b14 | note | REFERENCE: 610.22
f7e50544-a78d-583b-ae45-2d97024a794c | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
a224da08-1007-5b12-b5f6-4cf154ad10a0 | note | Only applicable if the element has:
6c7aa133-befe-54d4-81cc-e442160cf03e | note | i. the smallest sectional dimension exceeding 500mm
452d2f0d-62c6-5646-8e37-ae57f2faa78b | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
1baab0ac-1986-5501-b65b-2c6893551330 | note | METHOD: Measure
d473933c-aba4-5adf-888f-9438ce21484b | note | FREQUENCY: Where applicable, each element
26aeee73-2ab1-55eb-bcab-644b913618f6 | note | CATEGORY: IP
e970b924-7268-5e93-93d1-aac08c25abc8 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5291841b-e3a1-5649-b66e-9621532ff306 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.8 Pre-pour Inspection
9861079a-2452-52e7-a1c8-efef68300325 | note | REFERENCE: IFC Drawings 610.18 (a) (ii) & (iii)
47d36d06-7e66-5bf6-9742-6fbf19927c43 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
a4046043-2ac1-589c-8980-d8e0c71e5622 | note | ○ All foreign material has been completely removed from the forms.
bd53dcd0-7732-5aa8-9452-6476a3e14490 | note | ATTACH: Pre-Pour Checklist
100b7917-b744-5554-8534-0163f4344b92 | note | METHOD: Measure, Visual
80665e2e-2a80-5f6f-8c5c-2220553472a3 | note | FREQUENCY: Each element
5ba773b2-f755-5f92-a34e-74b86ad9b70c | note | CATEGORY: HP
99172c8d-051a-5100-b22a-b4891fc9cc9b | note | RESPONSIBILITY: Nominated Authority
ef8cc2c8-4e53-5485-861d-5684dbfa7ed3 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
d28879e7-52e9-5548-9d03-695ea5d61d0d | note | REFERENCE: 610.17
995fdbb8-8e08-5e16-bcc2-74fc1a66500c | note | ○ 610.17 (a) & (e), Table 610.171
16df630a-f6da-5828-bdf9-d991784c5fbf | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
57b74732-d56c-557d-9377-f981a1781b18 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8f419055-6a46-521a-892c-4ec0d0f52d50 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
fc1ab646-2b76-5a40-811c-f84d77dfd8ff | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
2fec83da-0da0-54a1-8af5-43a231f649e3 | note | Record: Required information on the Concrete Pour Record.
9b0d7712-48fa-5682-9a9c-ee9510818266 | note | METHOD: Measure, Visual
1f499720-5e55-5653-ab45-412b0b49951c | note | FREQUENCY: Each element
2dcea773-5eeb-559f-993e-ebd7e19d0529 | note | CATEGORY: IP
99f275b2-37b4-598d-b81d-2a7e9940fc6a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c648ddfa-a597-52b1-ad29-c5f007d9e643 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
4de8a207-7b4b-52fb-ad3a-d2d536899d9d | note | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
4fbc0576-bb2b-555a-b6c0-d52c1aa43120 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
68a351ff-61c6-5a04-ba12-29bc10de1b1d | note | 0m³ to 10m³ = 1 sample
cc5655a5-66cd-5b30-8763-7bdcba937a75 | note | 10m³ to 25m³ = 2 samples
75e1e649-18d1-5474-83ed-ec2f15838882 | note | 25m³ to 50m³ = 3 samples
ea0e2afd-0edd-5b35-a227-6fc919c89c00 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
f0c9d278-b39e-5bf0-a55f-4491a1c08179 | note | ○ For each additional 50m³ and additional sample shall be taken.
ac01b7a7-9bf8-5a7c-ae67-80d104aec9e6 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
54878148-16b8-595c-8681-e006a20b3381 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
4d1f162e-9f1b-5387-8d28-ce45e724a250 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
f6c47bfd-940e-5ae9-87ca-5b8c993e29b3 | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
9eb502a7-95c7-535b-aa5e-72ca1a7116b7 | note | Record: Required information on the Concrete Pour Record.
3da7f067-dd44-5a2d-93fc-eeacf067b522 | note | METHOD: Test
30f272bb-50c7-5b42-b5a5-044cdb6b069a | note | FREQUENCY: Each element
2549e5a8-a60f-5c7b-9647-f7670ed7a215 | note | CATEGORY: IP
dadd6e9c-3bc1-5cc0-8063-1e1fc1982264 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
fcffea19-0f7d-5ecd-8280-3c9599dc3f2b | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.11 Concrete Testing - Slump
108fc7c7-40fa-52f1-989a-bd67d7d116cf | note | REFERENCE: 610.16 (c)
39cd4665-5ae4-5748-a58d-914744e7a83a | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
14d5bc14-5cd2-55bf-b9d5-80ef01472e8e | note | <60mm = ±10mm
7d931846-31f4-5665-8b47-a853d55f9340 | note | ≥60mm to ≤80mm = ±15mm
60abccab-3a09-570c-9b10-65e233bbe9a6 | note | >80mm to ≤110mm = ±20mm
983a6ddb-5fc2-5012-878e-9e9fef27123d | note | >110mm to ≤150mm = ±30mm
8d8f5d5e-9dfc-53b4-a0db-73285942cae8 | note | >150mm = ±40mm
7ed6fc2a-33b1-5469-956b-8061b7a85006 | note | Record: Required information on the Concrete Pour Record.
d17a6ddf-f519-543a-893e-7cd7c1e91347 | note | METHOD: Test
9ef1ae3f-b5ee-551c-8b01-fdcb6dbaf9e3 | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
cc28c16e-a2ff-57d1-a9a8-42ede4149d98 | note | CATEGORY: IP
a92a9e88-113e-595d-a8b2-bf028f810ac3 | note | RESPONSIBILITY: Concrete Tester
4da44a6c-9ad6-5ca9-aabc-5349e92c07d0 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.12 Supply & Discharge Rates
78f84258-3681-5014-9e62-d6bcc3cec2c7 | note | REFERENCE: 610.13 (a) & (f)
48461064-c98f-57b0-ab60-74062e252b3b | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
3746ec2a-2b80-5dde-bb6d-ed8b2fcf30a5 | note | ○ No water is to be added once discharge commences.
ade78490-2ff8-5ce2-89c1-05029e28106a | note | ○ Maximum time between batching trucks is 25 minutes.
705b3726-9526-56ec-9d8b-9666f8ced8fa | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
1a1ae5cc-b376-50f3-a835-c2a2dba31c00 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
2b289ea1-6a38-544f-b5a3-5210d1fd1fac | note | Record: Required information on the Concrete Pour Record.
d1aed3e4-fb1c-5bf6-818d-758936a146f9 | note | METHOD: Measure, Visual
18b48fc8-7dfe-5291-8bac-f62f4f64da3d | note | FREQUENCY: Each load
137aa153-6581-53f4-aa98-3ba75b6af1cf | note | CATEGORY: IP
a1cef4c2-71e6-5504-9886-3c203bef7f28 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
992d5004-381b-5fa1-8c61-4d5644c89638 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.13 Placement & Compaction
6ffb6676-4068-5468-a76e-c3e06b928b44 | note | REFERENCE: Placement & Compaction Work Procedure
49b3aab7-8965-50ed-874f-d1f7fa327844 | note | ○ 610.18 (a) & (b)
051e0b20-0ea2-5d77-9ce5-31a0959b50a1 | note | ○ 610.18 (d) (i)
5ec89ace-5915-5575-8745-f92b622c0e66 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
7cdb3009-6554-58bc-ba6b-6c1fb1694a3f | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
8a98c8e8-9193-596e-a981-c995e8f6f2ac | note | ○ Concrete is not dropped freely from a height exceeding 2m.
df78abe7-1df0-5a81-a34a-552b4799766c | note | ○ Concrete is not moved horizontally by use of vibrators.
ae4a830a-d784-5cad-86fd-1873aae85318 | note | ○ Adequate compaction is ensured
1a50e83d-1578-53f9-b906-bd2c7b06e25b | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
9fa32df3-2bb7-5b12-b536-906e787aa669 | note | ○ Concrete layers are not more than 350mm
166bc120-ec57-5644-8649-6652c8c92957 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
f359a2b2-2878-54ec-aa07-f8698daf9c66 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
087a8e6a-3801-5517-8501-4a9c6d754a83 | note | Record: Required information on the Concrete Pour Record.
ebcd5c72-43a2-58ca-9a79-bea589d8ad8d | note | Attach: Concrete Pour Record
7a8f48a4-50ca-5883-aed2-448c86a65f54 | note | Attach: Concrete Dockets
59953b00-1214-5bf6-9552-6e34a9b970d3 | note | METHOD: Visual
75809f91-1e44-5197-960a-0009fd246d0b | note | FREQUENCY: Each load
3604e98b-1f15-5ed0-b218-d92fb17894c9 | note | CATEGORY: SP
8f75b1ad-deeb-5e1e-bc7b-ae30e141e5ba | note | RESPONSIBILITY: Foreman, SE/PE/SPE
88938d36-e023-5ad0-943b-b98f59199c35 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
| checkpoint | 5.14 Surface Finishes
1e03c37f-1cc4-5b87-9296-112280189419 | note | REFERENCE: IFC Drawings 610.31, 610.20
55a24a06-d905-5692-add5-f78aa13e3a0e | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
10438160-740f-5c50-988d-e149c87dd889 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
7e41b32c-d38d-5c51-9394-6d31ad84ed1a | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
2228b12e-7de4-5ac9-a49f-2e87c1f6479d | note | METHOD: Visual
a791c494-59a4-561c-9fe4-eec730d505ef | note | FREQUENCY: Each element
6f7945b2-cf0b-5cb1-8809-5a850a335692 | note | CATEGORY: IP
d4d1aafa-ea74-5a4e-9ebf-4102ee70f310 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
c90d069f-38c7-5f37-a81a-031168558e8e | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.15 Curing
1848e935-d850-5529-a96f-879b0c400b88 | note | REFERENCE: IFC Drawings 610.23
fbfeb442-96ea-54d0-91c2-47d408637d21 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location.
42e945e4-4c5c-5693-855b-d34b506f3773 | note | ○ Where formwork is removed prior to the completion of the curing period, curing shall recommence within half an hour.
c93ffd26-6e5b-5f33-81ad-0f477229e201 | note | METHOD: Visual
ee917485-51a4-5840-98be-54cb21b4dad7 | note | FREQUENCY: Each element
0673c774-a719-5eca-a216-c006253f06d9 | note | CATEGORY: IP
55750aa3-8876-58fd-a632-62ba58f656af | note | RESPONSIBILITY: Foreman, SE/PE/SPE
bf7d10e4-ff13-5795-af18-93df23d74b1d | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.16 Geocomposite Drainage Mat - RW 3 & 4 (Type 1,2,3)
dae18659-faa3-569f-bfac-5f4e6661b412 | note | REFERENCE: IFC Drawings, Product TDS
82b7a67e-812d-5a18-b13e-63123c9f797a | note | ACCEPTANCE CRITERIA: Geosheet CS15F or approved equivalent to be installed over retained area of upstand as per IFC drawings.
3d42d6d4-f0b5-503d-8397-d3b4e8191ead | note | ○ Geosheet CS15F to terminate 300mm from finished surface level
88a1038f-e1f8-5a71-a8c4-3041452afe64 | note | METHOD: Measure, Visual
b77e12f4-a7c3-5993-8190-e3ec9221d4a2 | note | FREQUENCY: Where applicable, each installation location
a689cf26-78f9-511e-b133-dc0a07fb3439 | note | CATEGORY: IP
b2b73bac-7ce5-5371-a411-3b046768d9c0 | note | RESPONSIBILITY: Surveyor, SE/PE
7b5e8ee4-edd0-583c-951e-1ed6073cf288 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.17 Subsurface Drainage - Granular Backfill - RW 3 & 4 (Type 4,5)
60b57fbb-df31-5262-9283-290dfa342c57 | note | REFERENCE: IFC Drawings
052aa33f-a1b1-5443-bcea-e05d19b91d55 | note | ○ 702.03
7c98aad9-0ea1-53a4-bc35-1932685c7865 | note | ○ 702.06
218a8e14-ce32-55f7-b3f4-f3295915913a | note | ○ 702.07
7e5e337f-0b73-5fe3-b7ef-f79a6d3ab0c0 | note | ○ 702.09 (g)
93f12c10-8261-5382-ad16-fd98f663fe4a | note | ACCEPTANCE CRITERIA: Megaflow 170 overlayed with filtration geotextile geosheet. Backfill with 300 wide free draining gravel surrounded by geotextile A64 to VR702.
a2ad77b6-dfde-54a4-ba01-0f3a25194187 | note | METHOD: Measure, Visual
715a1e4d-d42a-554a-bf79-d4b268e0d90b | note | FREQUENCY: Where applicable, each installation location
c43aa163-648b-5c5e-9308-916fdb0cff4d | note | CATEGORY: IP
d939fd90-a8f4-5f2b-a9df-8f290fea068b | note | RESPONSIBILITY: SE/PE
674d4935-5ad0-505b-a824-7f5542bc2ddb | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.18 Subsurface Drainage & Permeable Fill Material - No Fines Backfill - RW 1, 2 & 5
1bcc38ff-9109-5154-b0a2-c9997f5b7b60 | note | REFERENCE: IFC Drawings
8f19b8ed-cfa5-59c2-af31-4867bd081b26 | note | ○ 702.03
e3196f82-7874-5be2-bc53-77e16835f7de | note | ○ 702.06
db78c339-356f-5c23-8591-335563fc1401 | note | ○ 702.07
d668e48c-cd92-5db6-9f6a-ee29a996d3ec | note | ○ 702.09 (g)
c7801823-9d88-5d90-9e44-5298aa332452 | note | ACCEPTANCE CRITERIA: SN20 Class 1000 slotted socked subsurface drainage pipe backfilled with 300mm wide no fines to VR702.
0cce621e-379f-5666-8275-e59baaecc71d | note | ○ No fines to terminate at underside of pavement subbase layer.
8841e401-0ed3-5f7a-ad16-e3f136ccbcbd | note | METHOD: Measure, Visual
0a81966c-4d5a-5dee-9a25-e779790cfe08 | note | FREQUENCY: Where applicable, each installation location
4ca03d5e-de3f-5b4a-8035-43a16b7c4105 | note | CATEGORY: IP
fe5b428a-5607-5c0e-93cd-2d54815345ff | note | RESPONSIBILITY: SE/PE
07971449-32cd-5997-b153-56ca52f6766c | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.19 Joint Sealant Application
219cb5c1-34ff-58c9-9d20-6900f7095ac2 | note | REFERENCE: IFC Drawings
a75f8e93-0d7e-5499-b1bd-182eab67b02d | note | ACCEPTANCE CRITERIA: Backing rod and approved sealant to be installed on external faces
813c202d-058d-5b81-80f7-7b483f5e7018 | note | METHOD: Visual
81b98a1e-ac23-506a-811f-595932eda799 | note | FREQUENCY: Where applicable, each element
052c8ef3-9b9b-5d99-83ac-ec0ff4d4add1 | note | CATEGORY: IP
ae61e751-5af4-5359-a7eb-0a4a1d67c2c6 | note | RESPONSIBILITY: SE/PE
ad68d948-fc53-5c7a-b7bb-e05cf92642b4 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 5.20 Flowable Grout Pour
1f221982-565a-5462-9abe-9dc4a9281ff6 | note | REFERENCE: IFC Drawings, Product TDS
cfb8633d-e427-5e0c-ace1-a27cbf045cdd | note | ACCEPTANCE CRITERIA: Grout shall be poured in the gap between the bottom of the precast element and blinding layer below.
714c36e8-2ad5-5575-809c-05cde3b7baca | note | ○ Grout to be mixed and poured in accordance with manufacturer specification.
0bf817f6-c29c-5ba4-9d59-c59a39f282d3 | note | METHOD: Visual
f148839d-3fea-501d-a52c-42f049d7953f | note | FREQUENCY: Where applicable, each element
af3df47e-9f13-59ea-8bd6-fa6068eb73b2 | note | CATEGORY: IP
d3d3bb4a-eb7e-52e5-8e2a-f7886fb98bb6 | note | RESPONSIBILITY: SE/PE
e6ce0c54-e0f5-5951-8f8d-0cc4f2ebbd54 | note | VERIFYING DOCUMENTS: This ITP
| section | Post-installation Activities
| checkpoint | 6.1 Thermal Differential Monitoring
7465d2de-c876-5b1a-9315-d3f6a7a63d85 | note | REFERENCE: 610.22
92cb2c2a-33f4-50d5-b9e2-44e7fcd0b853 | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
ba492ff7-6847-5970-a2b9-789993432fad | note | Only applicable if the element has:
9de530d4-1572-5411-821e-81ece319d768 | note | i. the smallest sectional dimension exceeding 500mm
670bb6e1-5f05-5d45-bc82-4a7a5a815ea9 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
f0a9a864-5bf8-58eb-8407-f975953dc056 | note | Attach: Thermal Monitoring Report
85de1639-6989-584f-a856-ef6901a921ff | note | METHOD: Document Review
9cb7af54-6537-5896-800f-523c7cef9976 | note | FREQUENCY: Where applicable, each element
779bb186-c001-58b5-a36b-d1478b29020c | note | CATEGORY: IP
b1120c91-df43-5e50-9bab-345b9a466640 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
3ad7edf0-9451-509f-91df-0db1a9936fa6 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.2 Removal of Formwork
7f2c23cc-90d3-5c83-bca3-b0f1448c9bdc | note | REFERENCE: 610.25
0c9000a3-437c-5fe8-bec1-b919e10973f5 | note | ACCEPTANCE CRITERIA: Formwork and formwork supports shall not be disturbed or adjusted during the concreting operation and shall remain in position and undisturbed until the minimum removal times given in Table 610.251 have elapsed, after completion of the placing of concrete.
f4a60f73-87e0-5598-8de3-04856c24257b | note | METHOD: Document Review
a548a2b5-d01c-59ae-871f-30da9880576f | note | FREQUENCY: Where applicable, each element
f2af5e79-0c35-5a98-9e1f-63047e4b81c0 | note | CATEGORY: IP
3e7446fa-3583-5160-af05-0d5b488a183a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
26d556c7-6f82-5d23-91b5-7225660aee85 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.3 Surface Inspection - Cracks
72de5909-2c8c-5ada-af26-2ac71374169c | note | REFERENCE: 610.24
3e156eba-71d2-5f36-9545-610c4684cf29 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
0b3a28a3-a5d0-5306-b491-6bb989c3921c | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
90ef3d10-c64f-5680-b131-b789cf60f194 | note | METHOD: Visual, Measure
d6236244-7183-59a3-a817-0ae0d1f822b7 | note | FREQUENCY: Each element
6503813f-5e31-5667-967e-3ee85cb16375 | note | CATEGORY: IP
b8245c6d-36f6-541d-8c66-9a41be12bb69 | note | RESPONSIBILITY: SE/PE/SPE
5d66f32f-fbae-5564-83fc-0c93ffb4778b | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.4 Surface Inspection - Surface Finish
b05bc106-028f-5b43-a7f0-124db00ec155 | note | REFERENCE: IFC Drawings 610.31 (a) - (n), 610.32
aed64fcb-93ed-58e6-b382-ee64fcd4a2e1 | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
3291f2ed-4284-5a28-afb2-a509db835717 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
f6ad303c-d0ac-550e-8f0d-de76a3f94a34 | note | METHOD: Visual
d10d4612-eb9d-533e-90d9-532489319434 | note | FREQUENCY: Each element
166a671d-063e-57fd-9070-c7d7ca33aa88 | note | CATEGORY: IP
891f5aad-5e8b-5c96-b5fc-a8ab5babc85e | note | RESPONSIBILITY: SE/PE/SPE
90f5a1b5-8aa6-57ee-9eed-2a8ad0a9ea03 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.5 Measurement of Concrete Cover
c2cecd41-a49b-5336-a68b-14872ce6be40 | note | REFERENCE: 610.34
83efc323-2913-5ff9-915a-f5aae4b0bca2 | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
6c801545-1188-5334-8428-d4b668e6ef3f | note | ○ Minimum 10 no. measurements recorded in each area.
755ee8e6-ec98-5b87-8f43-09f622dd30f9 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
19a88507-aff8-5a77-8a7e-c04f6dbeaf16 | note | Attach: Covermeter Check Record
44fa2d6c-fec4-5023-9397-f763ee0d331e | note | METHOD: Measure
90f03408-9845-5f26-92ff-b90ca4e277c6 | note | FREQUENCY: Each element
091966bb-2ede-569b-9882-872860598b06 | note | CATEGORY: IP
7fa1ff3e-233f-5e5c-8dae-cc9583288dc6 | note | RESPONSIBILITY: SE/PE/SPE
60821077-01f4-555f-b84f-1d7ca3c95a2f | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
1ac44533-0a23-5ef7-bd55-9d472488f35c | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
1a516a7d-d9b9-5bd3-b27f-bc999e2e023c | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
99fb6d08-a4e1-56eb-9c76-56f83bb298bf | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
ca997d1f-6ef8-5d19-8666-866667c415ab | note | Attach: Concrete Test Results or Maturity Test Results
ff43fd9b-5777-58e8-b054-a3e749b82d37 | note | METHOD: Document Review
0e12884c-9e78-569b-a9c8-eb606e02edf9 | note | FREQUENCY: Where applicable, each substructure element
32633eb1-2f41-5793-bf04-3e5713503cff | note | CATEGORY: SP
2cab1ce2-c5f5-5c9f-9e4b-247dd0eef8a6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
d7b6a6c6-fe0c-5830-a75b-65b7f3ad5976 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.7 Compressive Strength Test Results
fcb99494-3a81-5789-9aab-62089efcce79 | note | REFERENCE: IFC Drawings Table 610.05.051, 610.16 (g)
f32a457d-0390-550a-954c-ff621407e306 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
a04e4018-50e9-50a9-9923-4c2f380e0259 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
8aef81bb-20a6-5b89-8195-88ef47df7142 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
699b3ac9-8bdf-5a39-9787-8e33590b8a52 | note | Attach: Compressive Strength Test Results
f60a960d-d8b0-519a-934d-20937453e9d1 | note | METHOD: Document Review
722cd1e3-54cb-5d7e-a580-557c0e5cd978 | note | FREQUENCY: Each cylinder
987ba138-f3dc-5dc8-9834-9bc926c0f6c6 | note | CATEGORY: IP
32b26a5c-3fe8-5821-939d-26d0a07a8acf | note | RESPONSIBILITY: SE/PE/SPE
c8ff633f-f13c-5e28-aa03-a5a186087ac7 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.8 As-built Survey
3c62810c-f0e7-58e3-b7d6-2e6db07f8861 | note | REFERENCE: IFC Drawings 620.09
ecc3e51f-41e5-5492-86de-706f39dbd0a3 | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
8b974d9d-dde0-5c59-86d3-1abdc257e910 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
1ad90f39-a3d9-5274-b561-2548d980b332 | note | Attach: Survey As-builts / Survey Report
b7732aac-9521-55b1-8e0f-b14667042830 | note | METHOD: Measure, Visual
28b8d854-f8ff-574a-ad9a-7585813be4fb | note | FREQUENCY: Each element
49914ef7-4da5-5eac-a319-0efe823756c9 | note | CATEGORY: HP*
4003f243-7b57-5476-aedb-44d041b594d1 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
5de2ec23-f3a5-5b11-9433-24b92b243c83 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
d9b3995e-b2d3-5728-bc20-09caae2548f1 | note | REFERENCE: MRPA Quality Management Plan
cd4fb5ae-cf32-5e53-ac59-4f86566c3b99 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
516306fb-b9df-5d3f-aaf3-da3575938d1b | note | METHOD: Document Review
88bace12-7c87-5dd4-9706-4be0b5a9c517 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
66c6d5e4-fe62-5bfb-be34-38e964dc1c04 | note | CATEGORY: HP*
71fd8561-b38e-5d26-9d2b-ac9173446d6d | note | RESPONSIBILITY: SE/PE/SPE
666448db-37ed-5754-97e2-3c3c5df63af2 | note | VERIFYING DOCUMENTS: This ITP
| checkpoint | Final Inspection
372f4b3d-53d5-579e-b85c-2ee4eff68fee | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
46535c53-b0f3-559a-bdc8-0403f470eb29 | textbox | Name:
9acb2a4d-260d-5779-9ec3-6ad6c5ee3349 | textbox | Position:
8f7e12e7-b617-51e6-9390-9f30e2dcd92b | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-189-STR-PSDS-Precast Material Inspection Rev 0 | itp | ITP-189-STR-PSDS-Precast Material Inspection |  | 6b27e16d-5b35-485b-84ed-469e69968ed5
| section | Referenced Documentation
| checkpoint | Referenced Documentation
21240b2f-95b9-5c18-93b2-2d689f5f3004 | note | Document Title: ITP-189-STR-PSDS - Precast Material Inspection
5f12e791-a82a-5861-93fe-6563621d76f5 | note | ITP Description: PSDS - Precast Material Inspection
d64cd2ba-c346-5c81-9b16-0fce6eb0d157 | note | Discipline (e.g. CIV/STR/RAIL): 189-STR
e97b0398-4a42-50ab-94d1-e62b81ca1093 | note | Revision Number: 0
a58acf79-280c-5d83-b815-3ec7c2ca3633 | note | Revision Date: 30/07/2024
13187314-8a4a-5bdd-8a51-a1f77ddf7c85 | note | ITP created by: Dan O'Brien
a77208c3-3f50-5e2c-b58b-491de4244062 | note | ITP approved for use by: Victor Mira
| section | Precast Deliveries
| checkpoint | 1 - Delivery Details
d72775b0-4ed1-59ae-b672-b43ba98b94d3 | textbox | Enter: Delivery Docket Number:
6cf28017-3264-5e5d-a4bd-d7176290b98a | textbox | Enter: Delivery Date:
96c4e7db-15f5-54f8-8737-106bd0d5dc24 | textbox | Enter: Element ID (s):
0987e110-1232-5419-aa63-b33384f88474 | note | Attach: Delivery Docket and packaging Slip
3f757197-4dc4-5ae9-9674-5cd30b65b1b9 | note | METHOD: Document Review, Visual
94132db6-2751-52a2-88b8-637e62ac4211 | note | FREQUENCY: Each Delivery
d7318641-d6db-5c18-a0b4-4304dc7c3622 | note | CATEGORY: IP
23ce25ab-8f84-5748-85d7-9b48885468d0 | note | RESPONSIBILITY: PE/SE
57b87e25-8625-5127-a39f-2adfa5b4306f | note | VERIFYING DOCUMENTS: This Checklist
9ca0d62f-87f2-56e9-bc77-d9f1cece5b73 | date | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
d9e2a4ba-a4f5-5e6e-8c58-6366e3cea556 | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
d3d5ff4d-424b-5826-b69e-34c72c76f25d | note | METHOD: Visual
21ebe4ea-ddc1-53f4-ab50-77b526b085da | note | FREQUENCY: Each Delivery
2ffe76a6-1dc8-5828-b8cf-6eea30c3b9d1 | note | CATEGORY: IP
ab6d4e51-a22f-5edd-bcd5-9d24325e7dbd | note | RESPONSIBILITY: PE/SE
ddf88671-c52b-5f12-a6c8-912787151966 | note | VERIFYING DOCUMENTS: This Checklist
986e576a-f256-5e2f-8188-9b15db3d09ee | date | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
f46ba2f5-273e-5176-95e2-765e5f2edf40 | note | ACCEPTANCE CRITERIA: Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
eb9d92bc-d7cf-58f4-8846-1c20a7652fde | note | METHOD: Document Review, Visual
c3e86c64-f9bc-51e3-87ed-7fd1fdfc55dc | note | FREQUENCY: Each Delivery
4ce142b3-7894-598b-8236-dfd6f20bb6a5 | note | CATEGORY: IP
af8be1e9-a2ec-5a3a-ba57-77617194942c | note | RESPONSIBILITY: PE/SE
cb9a8941-3d8f-57c7-989c-d59b21beb0d2 | note | VERIFYING DOCUMENTS: This Checklist
97f17146-4e9c-55fc-81de-89b103f91782 | date | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
962d1529-ac65-57ee-8679-06ed7e60bfdf | note | ACCEPTANCE CRITERIA: Is the delivery accompanied by Precast items Birth Certificates?
a3acf6a6-5b60-5ed7-8916-fc300f76ff43 | note | ○ Precast components are to be marked on the birth certificate.
3a7a71b4-588d-5346-af4b-87d5123eecce | note | ○ Cast date and lot are to be marked on the birth certificate.
dbcddd0b-8267-5210-840f-d7b0f7e2adb7 | note | ATTACH: BIRTH CERTIFICATES
81d6ad28-f188-5b61-9ebe-510e19319bf6 | note | METHOD: Document Review
1b129adc-e9ea-5486-8d1c-c4fee9e6219c | note | FREQUENCY: Each Precast item
c766ae0e-06a4-525c-ac81-e5c055f0a13c | note | CATEGORY: IP
ef9858fa-5ef6-5896-925e-d110a19d9c78 | note | RESPONSIBILITY: PE/SE
47eb3e78-7861-5e6b-8e8c-76a2832548d5 | note | VERIFYING DOCUMENTS: This Checklist
c6c1cea0-5a23-5d9c-b83a-41fa74ddd0e7 | date | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
dbeb2b58-abfc-5190-84c3-f74a31ad292a | note | ACCEPTANCE CRITERIA: Is the condition of packaging acceptable.
4edbc1bf-b180-556c-8905-2def5d2e5c8e | note | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
335e879e-14ad-541b-a3b0-e120df2b8108 | note | METHOD: Visual
34c15742-7022-5428-bf65-55ae4bcf1702 | note | FREQUENCY: Each Precast item
37ddea7b-2d00-5a45-9d2f-5a5d5a3cb58d | note | CATEGORY: IP
6e0efc46-5ebb-5ff3-a3bc-8df256ed16f8 | note | RESPONSIBILITY: PE/SE
17f8a7c6-68cf-567f-95d9-6bfe0ef81f42 | note | VERIFYING DOCUMENTS: This Checklist
7336f639-7eae-5758-ad0f-a90a7893b152 | date | Date Completed:
| checkpoint | 6 - Pre-Lift Inspection-Transport
e6b13f13-70ac-509e-a2a3-eb6bf489d03a | note | ACCEPTANCE CRITERIA: Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
4da66055-10dd-5068-89a4-c19111685d0d | note | METHOD: Visual
c64d73a4-f827-5ce1-96b3-e6345240697f | note | FREQUENCY: Each Precast item
db44afab-c522-54b2-9657-07c4c28629a0 | note | CATEGORY: IP
b01ca7e6-eb7f-5b31-ab02-495c6da066bb | note | RESPONSIBILITY: PE/SE
aea73164-7292-5c18-8a6d-3eb5747c94c0 | note | VERIFYING DOCUMENTS: This Checklist
086332ee-3898-5fea-8334-326b2e2005fb | date | Date Completed:
| checkpoint | 7 - Fault IDs:
a7bed699-18ca-57aa-b716-fe9ec74be33b | note | ACCEPTANCE CRITERIA: For each precast type delivered, check for the following:
5428f64e-0f74-514d-bce2-83e06de1c9d9 | note | 1 - Identification markings match the panel type
62f3e846-2703-566d-9082-e23d7c1b5399 | note | 2 - Element fabricated as per drawings
bd13a5ce-33a9-5ede-bd64-509084d226df | note | 3 - Cracks
eef10400-3a24-5a32-98ab-80c8be06eb69 | note | 4 - Spalling/Damage to concrete surface
f5c80004-26e6-5a9d-a443-818db8a60d58 | note | 5 - Exposed Reinforcement
733a849c-0c84-5b1d-bb5e-8b7d39e8902b | note | 6 - Damage to Anti-Graffiti coating
35752331-4322-5506-b74b-2aaa9b0cae7e | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
4d634913-3b3c-5dc4-ada3-928eeec41b1d | note | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
5adcd7f0-da3d-5874-acbc-0df07b098649 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 1
cde624ee-158c-537b-9c6a-0b315e5d4cae | note | REFERENCE: Item 7 on this Checklist
d93093c1-a243-5b9d-996c-acbd0760f9ee | note | METHOD: Visual, Measure
248de7d6-1bd0-59dd-ba8f-a1c28b76369f | note | FREQUENCY: Each precast type delivered
e7ef58f2-2e51-588f-a597-03fbefe0b6a2 | textbox | Enter: Panel Identification:
16482f26-b545-5d73-999c-c23bd8028e60 | textbox | Enter: Quantity:
3e2d57f8-d27d-5830-8a15-086f7f73fb5a | textbox | Enter: Fault ID if any:
d9f21e76-5d1d-5484-ac41-5ab6b1a85038 | note | CATEGORY: IP
c5292ff3-ff08-5fdc-8f7e-52da87cf9db7 | note | RESPONSIBILITY: PE/SE
a99be7eb-9404-528c-bb00-8f8ccf821881 | note | VERIFYING DOCUMENTS: This Checklist
a5f39df6-655f-57c2-9af9-43bc957e9434 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 2
a31b0fd1-7442-5596-b44d-bb05818ac543 | note | REFERENCE: Item 7 on this Checklist
08036d6c-b5ac-573d-96c0-36b3ea1f1062 | note | METHOD: Visual, Measure
ac24f5ce-f182-5eb4-bad5-23deacee6f95 | note | FREQUENCY: Each precast type delivered
4788a5c0-ce07-5498-8f0b-346880a055de | textbox | Enter: Identification:
09d148ed-d18b-5dac-a1ca-013d0213b4d6 | textbox | Enter: Quantity:
60ba0ff9-284c-5915-8eb2-02d21a484662 | textbox | Enter: Fault ID if any:
fe6bc140-d109-50cc-b5ab-d1d13f6767e1 | note | CATEGORY: IP
2cda33ac-e792-5ceb-b2c2-4c5cc100d61f | note | RESPONSIBILITY: PE/SE
297108af-abbd-574a-a082-288b3a3ab4d9 | note | VERIFYING DOCUMENTS: This Checklist
c6a7ffb4-bd7e-5502-9b54-143ffeb9c090 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 3
36f6cab9-790c-59a8-997a-4151cf189f6a | note | REFERENCE: Item 7 on this Checklist
ff1f693d-43c4-5e91-9dd8-1c4551152041 | note | METHOD: Visual, Measure
75f5e346-dcb8-5243-91b4-9ab220b1c672 | note | FREQUENCY: Each precast type delivered
6766e638-c595-5fb9-8fa5-4a9d23f21e82 | textbox | Enter: Identification:
6c04b5ec-0067-5ac5-915f-bfb688fe775e | textbox | Enter: Quantity:
a7eb8466-14ca-5ae4-a6e8-4a38b4bf0f98 | textbox | Enter: Fault ID if any:
c4c7cbd6-f3ff-56f9-9884-786e779dae32 | note | CATEGORY: IP
6182fd19-bffb-52b9-a309-1ecd100027a4 | note | RESPONSIBILITY: PE/SE
16d42569-26ea-5423-b8e7-7a940a250c47 | note | VERIFYING DOCUMENTS: This Checklist
45967293-28e5-5704-b002-07affbefc3d8 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 4
a49ea4fe-17ad-5c9a-aafa-eab0ab24ed17 | note | REFERENCE: Item 7 on this Checklist
e72dc907-0664-5809-a93d-b43b6621b452 | note | METHOD: Visual, Measure
27e45c97-2415-5043-80e9-f227c8f5ac05 | note | FREQUENCY: Each precast type delivered
5ed78bc8-8198-5473-b68a-dd8ee2600552 | textbox | Enter: Identification:
01ed344b-0a0b-5563-a671-e40c849137f2 | textbox | Enter: Quantity:
d767d68e-8c4f-5188-b6d4-be49a99e9379 | textbox | Enter: Fault ID if any:
f8a7101c-f615-5b96-b04a-b3bb16ac975d | note | CATEGORY: IP
7a1a1182-da53-55fe-ac91-9f3caf78f81a | note | RESPONSIBILITY: PE/SE
52721031-3d51-51c0-914f-4b466b2981bd | note | VERIFYING DOCUMENTS: This Checklist
24c1ca53-0a0e-5fbc-a27b-8fe1fdfac1c4 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 5
777d49f7-f439-572d-8889-1a9e1bbd048e | note | REFERENCE: Item 7 on this Checklist
d94eb18a-b9a1-53ae-8973-cd8e1fed0b37 | note | METHOD: Visual, Measure
1bb0540c-729f-5a97-8cf7-f98421b20230 | note | FREQUENCY: Each precast type delivered
b4fc22d0-c900-5e51-a1c4-236508dd40c0 | textbox | Enter: Identification:
01df8d7e-5352-5c12-a0ed-2d61849d3deb | textbox | Enter: Quantity:
3b63b169-b228-57d4-8bb6-4d174f76b65b | textbox | Enter: Fault ID if any:
982919ca-0f35-5933-ae2d-0bfb0c8dd236 | note | CATEGORY: IP
0da72fc3-9f67-5146-a30b-7239f9bd62f9 | note | RESPONSIBILITY: PE/SE
819a60e8-1528-5a6d-b8aa-02c3c2493ac1 | note | VERIFYING DOCUMENTS: This Checklist
8776d337-b65e-55e5-b59d-d81fee59dbc4 | date | Date Completed:
| checkpoint | 8 - Check for Faults - 6
e8fbc205-2bb0-51e4-8792-0e1479ec8cf5 | note | REFERENCE: Item 7 on this Checklist
21496691-dbfc-5b77-8741-e6dc15e8749a | note | METHOD: Visual, Measure
b3b353fd-f9b6-5b27-aeb8-c6260e4da01f | note | FREQUENCY: Each precast type delivered
c0391a83-cd2e-5b52-a952-5d97d929ced2 | textbox | Enter: Identification:
c07011bd-e323-5782-92cc-514b3fbc22a4 | textbox | Enter: Quantity:
3f5556de-99f3-587b-a29f-5b422245efab | textbox | Enter: Fault ID if any:
3aee875a-b1b2-5504-bd7f-dc8d6d89b8dc | note | CATEGORY: IP
54b98852-6827-56da-8a1a-d5a73452aff1 | note | RESPONSIBILITY: PE/SE
ecb04a71-1afd-5c8d-b244-3da4687ed3f7 | note | VERIFYING DOCUMENTS: This Checklist
caf19843-6c37-54e4-8b83-8e6b9e98e6dd | date | Date Completed:
| checkpoint | Final Inspection
e7df45cc-ea5d-5b13-b86f-1aa46e6ea731 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3569de51-ec11-50f5-bff3-e62dee3113f4 | textbox | Name:
273d0a0e-ed4a-51dc-b138-e6fa15288c47 | textbox | Position:
4da40dc0-5905-52df-abc9-8c36febcbd20 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-213-CIV-PSDS-Cement Treated Crushed Rock CTCR-Scale B Rev 0 | itp | ITP-213-CIV-PSDS-Cement Treated Crushed Rock CTCR-Scale B |  | 2f341019-b1a0-45dd-8ba9-8549348b24a9
| section | Referenced Documentation
| checkpoint | Referenced Documentation
d8e425b2-f0f3-5280-861f-65f416e740f7 | note | Document Title: ITP-213-CIV-PSDS-Cement Treated Crushed Rock CTCR-Scale B
5859796c-3b2b-56b1-abe2-eaf5ca7a73cc | note | ITP Description: PSDS-Cement Treated Crushed Rock CTCR-Roads
3f955d68-9ef9-5c45-a1fe-3ecee1b9bc92 | note | Discipline (e.g. CIV/STR/RAIL): 213-CIV
b9e11e07-08fe-5bb4-8152-e7a694ffd9b9 | note | Revision Number: 0
71319a78-9f3c-5bca-af10-5495fd52923e | note | Revision Date: 30/10/2024
5f4ce81d-cad5-51b8-b68d-c6914287610d | note | ITP created by: Jadan Halkett
a747bd77-3f2c-56cb-b79e-560282783219 | note | ITP approved for use by: VM
c521e9e1-d975-57fb-9563-a7da2d379b76 | note | 1.1 Non Dependent
42300980-514c-5fb7-a9a6-eb1c966ddc8a | note | Reference: VicRoads Section 306 Oct '19
b98d7473-08bd-58f8-a6d1-2889f63aaee6 | note | 1.2 Non Dependent
5c3d56f7-a169-5077-945e-a48aa949b6c2 | note | Reference: IFC Drawings
02771d96-db82-5a80-a2ad-7abf2abf3dcd | note | 1.3 Non Dependent
3243bc59-ce7a-533e-8c74-31d7475ed5b0 | note | Reference: VicRoads Spec. Code of Pratice 500.02
9e36327e-5f6c-53fc-8381-114f6ba4cf58 | note | 1.4 Non Dependent
45d812b9-8c55-5195-9480-a3758eb08e06 | note | Reference: VicRoads Spec. TN 107
a921050b-0665-5d4e-a4c4-bb7f4c62811f | note | 1.5 Non Dependent
bda6cae7-9962-501e-acac-7fdc83840ad1 | note | Reference: VicRoads Section 815 July '16
| section | Preliminaries - Materials
| checkpoint | 2.1 Submit Mix Design - Cement treated crushed rock (CTCR) mix
a56aa9ed-e991-51bd-90e3-33c2adc127f8 | note | REFERENCE: VicRoads Spec. Cl. 815.05
d1b55771-09e1-567a-a0b8-f97899ca6838 | note | ○ VicRoads Spec. Cl.306.04
d9f49160-97a8-5e61-a027-21fec3f7bc0b | note | ○ VicRoads Spec. TN 107
f7e970ad-d3e1-5607-a6e5-6c2fe4369798 | note | ○ VicRoads Spec. CoC 500.02
754ffa54-cfed-5f85-aa42-9ac98ea291c4 | note | ○ IFC Drawings
40678283-683e-55de-9ee5-19e6e0972ad6 | note | ACCEPTANCE CRITERIA: Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
d850a891-1aa5-5a0f-98fd-771c422a1d41 | note | ○ CTCR shall comply with Section 815 & 821, TN107 & CoC 500.02
e5438efc-2e65-55b9-9ea7-e6d40100e28a | textbox | Enter: Teambinder Material Approval number
21cd3353-cf15-56e7-8bac-1890b146487c | note | METHOD: Document Review
3e399946-85a9-5bb3-9646-ddf67225af27 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
bfae6aa6-d96e-5435-afca-9d47a05048f8 | note | CATEGORY: HP
9585a43f-3675-5c7c-b4a7-a97023cb8017 | note | RESPONSIBILITY: SE & Nominated Authority
8398fc3b-6ac1-59a9-ac96-c147f409b689 | note | VERIFYING DOCUMENTS: Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
69ad59dc-ca95-564c-bd28-ae7ece9b0813 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Hold Point - Alternate Binder (if applicable)
28131e0e-da5f-5fc8-b978-ce60ffbf28b5 | note | REFERENCE: VicRoads Spec. Cl.306.09(a)
4abe042a-4e37-5201-80f0-ab58de845153 | note | ACCEPTANCE CRITERIA: If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method.
d3f8cea3-a704-529e-83ce-d5efba4b97eb | textbox | Enter: Teambinder Material Approval number
8b944413-bcbb-5637-ab91-8e47d0606545 | note | METHOD: Document Review
7f559c2c-f809-5212-8749-08e7c852f82c | note | FREQUENCY: Once per material type, prior to commencement of works
df807393-35f8-5c46-b62b-81441ea2347a | note | CATEGORY: HP
c0ebad79-47d6-5233-8751-9e6ca8cdda93 | note | RESPONSIBILITY: SE & Nominated Authority
eb6102e3-3711-5d51-b4ed-337d2aa01648 | note | VERIFYING DOCUMENTS: Issue to TeamBinder: Test Records
cfb8222e-7499-5f64-9636-ed535940784e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documentation
| checkpoint | 3.1 Check that current revision drawings are being used
df651ee7-25a2-5e54-a29c-c7432fda86de | note | REFERENCE: Project Drawings / Drawing Register
f90cdc20-3293-5804-bf36-ec3fad64c757 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
26ba533f-d241-514a-9451-b51fa8549b20 | note | METHOD: Document review
411543f7-23e9-5602-a1d2-23b1991b9a22 | note | FREQUENCY: Each Lot
7b8d5010-610e-5f03-9e6a-524d39b7d1ce | note | CATEGORY: HP*
94d88394-6ed5-536f-9118-6f5790400931 | note | RESPONSIBILITY: SE / Site Foreman
7c1dc243-2034-594f-a99b-e17c515da481 | note | VERIFYING DOCUMENTS: This ITP
9391cb69-5768-5c57-a1a0-77165c092440 | date | Date Completed:
| checkpoint | 3.2 Previous Layer Conformance
3a20466d-03e0-5eba-93ab-54de353abd05 | note | REFERENCE: IFC Drawings for Previous Layer Type
7d508846-fed0-589c-aa25-fc4306925b9f | note | ACCEPTANCE CRITERIA: Confirm previous layer (prior to CTCR layer placemen) conforms to IFC drawing and specification requirements.
031ff158-c40b-5658-811c-3630cbad4196 | note | ○ Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved
b02eba56-d037-5e83-9904-180fb0828428 | textbox | Enter: Previous Layer Lot number [Free text box]
b7510b6e-3c8c-58b8-8248-a92ff44c748b | note | METHOD: Document Review
e3683ba0-aedd-580f-8b8b-76efbe551a50 | note | FREQUENCY: Each Lot
7a639ef3-c537-5d55-9d01-b02f031a382c | note | CATEGORY: HP*
a3139f3a-343a-53a7-8c16-17ba5affbad6 | note | RESPONSIBILITY: SE
fdd658e1-4866-56e9-ad6b-289da28946f2 | note | VERIFYING DOCUMENTS: This ITP, Previous Lot Number
943cb90f-87e0-56d0-a72d-cd3661ffde8c | date | Date Completed:
| section | Preconstruction
| checkpoint | 4.1 Lot Size
d5547244-202d-5890-bfb6-ab31fea2e00e | note | REFERENCE: VicRoads Spec. Cl.306.03(b)
38f6d6a8-4207-5c7b-9652-8546a8894544 | note | ACCEPTANCE CRITERIA: The maximum size for a single lot shall be considered a single layer of 4000m²
a2d1e5a9-c29c-5d8e-a5a8-043d2f3fe4e8 | note | ○ A lot shall consist of a single layer of pavement material placed on the same day
36c73aa9-368e-561f-a3e3-09a73521fd23 | note | METHOD: Visual, Measure
e0d81486-58da-5fec-b8db-4e4d01dec39b | note | FREQUENCY: Each lot
9ffb850c-a6a8-5e19-aa46-54ab7f8666dd | note | CATEGORY: IP
3545f489-3681-571d-9525-195acd40f088 | note | RESPONSIBILITY: SE
775004f5-8046-5be9-9636-0a2a7a95dd36 | note | VERIFYING DOCUMENTS: Signed ITP
de371363-ec81-5f3e-8317-d9d128a93350 | note | ○ Attach: Lot Map
2be4db03-8385-5a6e-97b7-719f6b33b7f0 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
e239117c-9eb8-55a7-8dd9-f313adbfdf96 | note | REFERENCE: IFC Drawings
0a1ce0f8-4719-5e97-be9a-8d101bf935e7 | note | ACCEPTANCE CRITERIA: Survey to set out works in accordance with IFC Drawings
bc9fbf54-69fc-5a0f-a27f-dcea44b4f897 | note | ○ ATTACH: Lot Map
57e6fb8c-32fa-51a8-b8eb-bc7a2dbac760 | note | METHOD: Measure, Visual
9ca779f7-eef5-53cb-b859-700c1740c163 | note | FREQUENCY: Each lot prior to commencement
77e6cedd-40bb-5431-a0b2-c3f68b004307 | note | CATEGORY: IP
ccae5bec-cfec-5511-ae2d-02d3e2187e3f | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
11717a75-0ec2-5a1f-a395-774714b82ac8 | note | VERIFYING DOCUMENTS: This ITP
e3bd28ae-b33d-59e0-b6a5-90b64e060adc | note | ○ Attach: Lot Map
8aaaa0b5-5b19-500a-80e1-77a9dda11094 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Delivery
1cc42b3a-d313-5ab4-9115-a8fa4558e4c2 | note | REFERENCE: VicRoads Spec. Cl.306.07
c9449478-4332-5274-8845-b08d9e04d75a | note | ACCEPTANCE CRITERIA: Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specificaiton requirements.
14f2c074-31d1-5ff1-af75-038f3de071ff | note | ○ Attach: Delivery Dockets
a2f8aea3-db0d-5d5c-b213-d4e15bc19f86 | note | METHOD: Document Review
3c802012-d8f4-53b7-97aa-1bffdb14a665 | note | FREQUENCY: Each Lot
e62bd566-7259-5fa0-a32f-4c2e02e2d8d8 | note | CATEGORY: IP
826ffd1d-90b7-57d5-820d-bf1af34a17af | note | RESPONSIBILITY: SE
e97009a9-a91b-53ae-aa5f-79fc3cf7518b | note | VERIFYING DOCUMENTS: This ITP
a9259875-6c59-5eaa-923e-a311ddd0ca9e | note | ○ Attach: Delivery Dockets
f9ca6f07-ab89-5312-8ba7-4f6c18c04923 | note | ○ Attach: pour records
8c402a67-8056-5b3d-8686-904f6b53d565 | date | Date Completed:
| checkpoint | 5.2 Placement - Transverse Joints
42c1af53-721c-5c78-b231-302904b8e5d4 | note | REFERENCE: VicRoads Spec. Cl.306.08(a)(c)
d33c8d34-cb63-5e23-8d0b-4ff2ec8de1e5 | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
b0b63c70-f825-5f2e-8df6-ba7edb536e9a | note | ○ In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m
cdef5ad9-50f1-5445-a5d0-37c4bf006048 | note | ○ Transverse joints offset from one layer to next by not less than 2 metres
0d3cad29-68cd-552c-bcc4-1ba7b5d087a3 | note | METHOD: Visual, Measure
07c161d0-09ba-552e-a892-cb51fc85dc6d | note | FREQUENCY: Each Lot
cf8de6dc-dc90-5f35-bc17-5ade749f9841 | note | CATEGORY: IP
92f2f17b-4e68-5902-a806-0ee6d5d93481 | note | RESPONSIBILITY: SE
451d87eb-e18e-5d09-b9c2-0de42b721420 | note | VERIFYING DOCUMENTS: This ITP
62a33e15-9ba2-5486-9a9e-6537bd034c31 | date | Date Completed:
| checkpoint | 5.3 Placement - Longitudinal Joints
1a282bd8-3d48-50bc-9d4b-1654adef1148 | note | REFERENCE: VicRoads Spec. Cl.306.08(a)(d)(e)
017037fd-e77e-5e68-ac41-837e53ba217f | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
d4ec8361-8b38-532d-8160-336fdf2e39eb | note | ○ Longitudinal joints offset from one layer to next by not less than 150mm
b8c321de-e12c-5c7d-8ca5-a3421c4dfab0 | note | ○ Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
6f770aa5-9231-5277-9a82-9cce97f57b68 | note | METHOD: Visual, Measure
8354dbeb-e9f7-5936-b367-56adcd6fe8f4 | note | FREQUENCY: Each Lot
72330259-ee9b-5ec5-a10a-2ee33f895aba | note | CATEGORY: IP
5aa9babc-452b-5990-969b-2bdf004847ad | note | RESPONSIBILITY: SE
e2ae5ce0-c3a4-5585-bf70-284341ef6790 | note | VERIFYING DOCUMENTS: This ITP
c478f8c1-2089-5071-9fd5-cf0cb1f7a1a7 | date | Date Completed:
| checkpoint | 5.4 Placement - Layer Thickness
5c09ac79-a7ff-5a32-abeb-2850a523b319 | note | REFERENCE: VicRoads Spec. Cl.306.11
257d2b01-9629-512c-a757-db343355d14f | note | ACCEPTANCE CRITERIA: Compacted layer thickness should be not less than 100mm and not greater than 180mm.
597ddae4-4e44-5d58-aa4e-294e4e53329b | note | METHOD: Visual, Measure
0d320ba1-5278-5fb3-8319-31d0c068a2a7 | note | FREQUENCY: Each Lot
a36db9b2-4b63-5028-a900-aa7098ce3432 | note | CATEGORY: IP
a89176cf-698e-5322-a871-0a7038d054b2 | note | RESPONSIBILITY: SE
1ecfb5e4-a5cc-560a-8b97-c714e1e3d06c | note | VERIFYING DOCUMENTS: This ITP
cba795fb-3613-5767-8cf4-5d4a5e18535b | date | Date Completed:
| checkpoint | 5.5 Placement - Working Time
4029bed4-6df6-5509-a990-7a3be7c12147 | note | REFERENCE: VicRoads Spec. Cl.306.07, VicRoads Spec. Cl.306.09 Table 306.091
49849163-6d5e-57d9-acdf-781bba13194f | note | ACCEPTANCE CRITERIA: Working Shall Not be more than specified for each binder:
05475513-a995-5d2d-8ded-bcfad81caaa5 | note | ○ Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept)
e4150129-ad06-5056-a142-869ad5f06475 | note | ○ Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept)
7a3ae620-2673-550b-8c04-ba4969b6ef21 | note | ○ Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept)
59e97630-398c-5801-a8b5-6b542f514a07 | note | ○ If the ambient temperature within the period from October to April on any day is less than 15°C, the May to September maximum allowable working times may be applied.
a96c0039-37a8-5f0d-bc8e-7a502783114a | note | ○ Attach: Delivery Dockets
6bacbc14-d2a7-578e-8073-4a40b4e27b19 | note | ○ Attach: Pour record
9d6140df-ccfa-586e-8539-246b3f030252 | note | METHOD: Measure, Document Review
0656cd10-a633-54a7-931d-307e169da77d | note | FREQUENCY: Each Lot
cea1e71f-b34c-5034-aab8-e827f8c459a3 | note | CATEGORY: IP
ae8f4fc7-b3fa-50aa-b1ef-1f666a747801 | note | RESPONSIBILITY: SE
0ffde2a6-de25-534e-9078-aad96e08b166 | note | VERIFYING DOCUMENTS: This ITP, Delivery Dockets
7243deb8-7dc0-5217-b10f-310f78d12a05 | note | ○ Attach: pour records
19bde724-c873-52cb-b9a7-c775421b6342 | date | Date Completed:
| checkpoint | 5.6 Water
14caf3d5-954e-5e2a-b2a7-ef7c03c63219 | note | REFERENCE: VicRoads Spec. Cl.306.06
01be0d6f-a4fb-50ef-9e7d-d0f046e58369 | note | ACCEPTANCE CRITERIA: Except for the purpose of curing, no water shall be added to the cementitious treated material.
7007edba-0984-55d9-960c-2faf1e408402 | note | ○ Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
2c21819b-d779-597b-8142-9f4af8712d34 | note | METHOD: Visual
47498da4-222b-5ca7-9241-2b03d4c85fd8 | note | FREQUENCY: Each Lot
4b6e6d70-f1d8-5c50-9fef-e6f54a959527 | note | CATEGORY: IP
f248f199-1177-5ea4-9c33-2eea60517779 | note | RESPONSIBILITY: SE
a872e489-aa9e-5913-828e-5b764c86be76 | note | VERIFYING DOCUMENTS: This ITP
b7fd58ae-75c3-52b6-8b6f-c1844a7433ff | date | Date Completed:
| checkpoint | 5.7 Cementious binder content & UCS requirements
d9c36354-0435-54ed-8276-34f9ff8f4ba6 | note | REFERENCE: VicRoads Spec. 815.10
610b5fb1-1ce3-5c58-97f0-97269d371cd3 | note | ACCEPTANCE CRITERIA: Contractor shall carry out the UCS Testing to determine the cemenetious binder meet the minimum 7days
2796a49f-0f4d-52c5-abcb-0f59235bcd56 | note | ○ Attach: test results
6f9fe560-ab85-51c1-97dc-b9b53fa61ed2 | note | METHOD: Document Review
c3f9eb8c-8952-5f48-8093-535dfa4ba4d3 | note | FREQUENCY: Each Lot
a002df47-c682-530b-99de-8272efdc7a57 | note | CATEGORY: IP
eec4c1a0-82a7-551d-bef9-96ada86b4898 | note | RESPONSIBILITY: SE
35fa0858-6d85-5eb7-9958-97dacf4a77cd | note | VERIFYING DOCUMENTS: Test report
35572e48-5b53-5f75-813e-c05b6e2d3cff | date | Date Completed:
| checkpoint | 5.8 Compaction - Modified Compactive Effort
96d50281-6bb6-5dcf-a6f8-a47ae5763e45 | note | REFERENCE: VicRoads Spec. Cl.306.05, VicRoads Spec. Cl.306.09(a)(b)
598e76c6-186a-5324-9141-10d17d8f541b | note | ACCEPTANCE CRITERIA: Moisture content at time of spreading and compactions is within +0.5% and –1.0% of optimum moisture content
54362ba0-0f98-5758-8a1b-fddf49288322 | note | ○ Scale B:
f04498c6-c9ad-507a-b6bd-5d93a02525d7 | note | – No. of tests per lot shall be 3
002e3c3d-636f-5d92-a514-bb805d86976b | note | – Mean density ratio > 96%
7d0e86ce-bbf7-5c1f-94b6-5b654cd6335f | note | METHOD: Document review
8d02aec2-2d9b-5909-8909-a91914422e4b | note | FREQUENCY: Each Lot
f07e0aaf-93e8-54c3-a305-2597e6da515b | note | CATEGORY: IP
e396a669-3392-56bc-ba13-5df52315f005 | note | RESPONSIBILITY: SE
9e5a409e-feaa-5e69-aa91-63f95d4d53a9 | note | VERIFYING DOCUMENTS: Attach: Test Report
39d97aea-5d78-5674-b5dc-6f44b69234c7 | date | Date Completed:
| checkpoint | 5.9 Test Rolling
7077fb79-f19b-5dae-827f-70554ac21a97 | note | REFERENCE: VicRoads Spec. Cl.306.10 Table 306.091
4863a30b-8238-580b-9e15-582588225455 | note | ACCEPTANCE CRITERIA: Test rolling to be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
4f47e4b8-0801-58ec-9826-96ee8f93b6b8 | note | METHOD: Visual
b97d4376-64d8-513f-9afc-ec0f473924f6 | note | FREQUENCY: Each Lot
fa4ef196-5980-5f55-b747-9deef335f9b3 | note | CATEGORY: HP
9cd47bfa-a7df-5ef0-b009-b7b38c70f2ad | note | RESPONSIBILITY: SE, NA
299f6cf4-873c-50f6-9b72-94ab596b9842 | note | VERIFYING DOCUMENTS: This ITP
3805a4e1-1122-59ac-8417-cfdd3db20cba | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Post Construction
| checkpoint | 6.1 Curing
79646335-83c3-5b72-a203-f3cec40e2420 | note | REFERENCE: Vicroads Spec 306.11
a4747b5e-c7db-5a9d-bd06-a8f5c3a2cd09 | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane
c0c97b05-2194-5288-a5c0-28ef409f6b85 | note | METHOD: Visual
db746fd7-b3d0-51fe-a70e-531eb52e0633 | note | FREQUENCY: Each Lot
79e0e36b-c16f-5610-9eb8-c3f3314b3b53 | note | CATEGORY: IP
237c4804-21a7-557b-84d3-9dd0452a41a7 | note | RESPONSIBILITY: SE/PE
0d2e3589-4b69-5ec8-8b1e-7a19e11448a1 | note | VERIFYING DOCUMENTS: This ITP
a30f9297-ea75-5810-b04b-222620241708 | date | Date Completed:
| checkpoint | 6.2 Protection
53c08bbf-cd79-5538-ad1e-3a8bca1cec36 | note | REFERENCE: Vicroads Spec 306.11
427e588a-7c51-5b74-9e6b-dc38cffbc172 | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa: Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
19b1b9b0-4c97-547a-9a93-2be5d749c003 | note | METHOD: Visual
fe0e294e-a7c2-5991-9a45-06ea845dde77 | note | FREQUENCY: Each Lot
9c9c1bbd-88f2-53d4-9ecb-d96418627412 | note | CATEGORY: IP
96b6a282-23d6-584b-8198-4c606d457301 | note | RESPONSIBILITY: SE/PE
d87bd039-acfa-5c52-87a9-c08909cbc0bd | note | VERIFYING DOCUMENTS: This ITP
51993c08-ab21-5747-b024-4b653c119651 | date | Date Completed:
| checkpoint | 6.3 Surface level
9fb6d3b2-1cae-5cc2-b2e1-1b41dfab417d | note | REFERENCE: VicRoads Spec. Cl.306.03(c)
7d76c526-c7e0-5774-8c3c-94a047fbdd20 | note | ACCEPTANCE CRITERIA: No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
3a184fd6-2458-5d35-adb9-9682abd9f9d2 | note | METHOD: Document review
61c904b3-f74c-542a-8f7b-d00921359eb9 | note | FREQUENCY: Each Lot
42e56689-d700-54b3-aff6-ebe896eb0d9e | note | CATEGORY: IP
2bb44ff2-9f2e-5bdb-a944-a6a575854469 | note | RESPONSIBILITY: SE/PE
f6a0566a-2ca1-5bd4-8b7b-144c35b71129 | note | VERIFYING DOCUMENTS: This ITP
4dea3282-f7fb-595d-a2df-c8ae114d1054 | date | Date Completed:
| checkpoint | 6.4 Conformity with drawings-Width and alignment
d4a14b63-a709-54bd-a7ca-162df0d9dd9d | note | REFERENCE: VicRoads Spec. Cl.306.03(b) Table 306.032
c2a743dc-71fe-5664-8f5a-6591ac3a9939 | note | ACCEPTANCE CRITERIA: Width and Alignment: The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
6ed629cc-0a8f-5b63-81df-96f055543c84 | note | METHOD: Document Review
9bd86f09-858b-545a-aeeb-be2aecb080e4 | note | FREQUENCY: Each Lot
52551b2f-8594-5cb5-8429-0af1b482bc7f | note | CATEGORY: IP
f28f96f0-2115-52f7-b1f6-52a69527ede3 | note | RESPONSIBILITY: SE/PE
83f09c79-1ea5-53b1-8644-31bd80a84b21 | note | VERIFYING DOCUMENTS: Attach: Survey Report
6586a395-cce4-5fdb-b884-d617dea573d4 | date | Date Completed:
| checkpoint | 6.5 Conformity with drawings-Survey Level
ee886e55-89b8-5957-975f-a65ed77cf907 | note | REFERENCE: VicRoads Spec. Cl.306.03(b) Table 306.032
cc2e7e22-c0ce-50f3-bb32-112fcf1d2b97 | note | ACCEPTANCE CRITERIA: Scale B: Measurements per Lot: 40
44288232-1f7e-534f-ae0d-6b9debe441cb | note | ○ Subgrade:
c921c06d-fefe-5d9d-8f42-99a2bfb1e672 | note | – Mean value of all level readings to range between +5/-25
a09760e8-e70d-5f0a-b189-6422d641dd58 | note | – Standard deviation of all level readings to be less than or equal to 15
741282ac-7b48-587c-97d9-b55363459364 | note | ○ Subbase:
fb504036-2339-55dd-80cf-2d31fbe51d6a | note | – Mean value of all level readings to range between +6/-12
196f85cb-f05d-5e5b-bb5b-c6637d7c882a | note | – Standard deviation of all level readings to be less than or equal to 13
8758f83c-1727-541d-8f02-6b68267c4b47 | note | METHOD: Document Review
d41f5415-8cce-5774-b19b-a41cdebe1a94 | note | FREQUENCY: Each Lot, Scale B: 40 points per lot
7be07053-dfc9-5eae-bd13-26824d132d60 | note | CATEGORY: IP
cd1b9c5d-83ce-5349-af19-e44ba71b5cbf | note | RESPONSIBILITY: SE/PE
87268288-19ce-5e50-b71c-c763ecb3bea5 | note | VERIFYING DOCUMENTS: Attach: Survey Report
f3c4839e-de12-5715-a8b1-238644eb3f8a | date | Date Completed:
| checkpoint | 6.6 Non-conformance Report (NCR) Closure
2a0fb465-ea39-591b-af13-e3bea45a0d28 | note | REFERENCE: MRPA Quality Management Plan
ef3599db-0e30-544b-9e6a-a476824d5f3a | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Team Binder.
6a876652-1818-5a1f-9220-712799df2e5e | note | METHOD: Document Review
9612a42d-348d-5d92-b4a6-666a7defda86 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
8311e47f-0c56-518c-b3b1-e40cabd0d2be | note | CATEGORY: HP*
1e1d5d4f-601e-58ca-86e5-55c01fcdc89b | note | RESPONSIBILITY: PE/SPE
f85f3904-753f-5309-8ea9-10e28a9a3add | note | VERIFYING DOCUMENTS: This ITP
3d745df3-c7e5-5a66-b203-4c0e5c75b18f | date | Date Completed:
| checkpoint | Final Inspection
390f1e36-b07f-5295-9230-a521f5f6d578 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
956ee7ee-6a80-5649-8a91-014a3736a9e8 | textbox | Name:
33db29b8-00da-5580-ae76-cc0c9ddbe955 | textbox | Position:
af7b811a-32e8-5734-a8c5-bbdae0ce98f9 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-223-CIV-PSDS-Sprayed Seal Rev 0 | itp | ITP-223-CIV-PSDS-Sprayed Seal |  | 58eaaca2-9190-48bf-8bfc-0db794528e7b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
4b378dbb-2dbb-54bb-8f0b-90b9bfdc6630 | note | Document Title: ITP-223-CIV-PSDS-Sprayed seal
b8086a27-8401-5f2f-a55b-4de95aa4f525 | note | ITP Description: PSDS-Sprayed seal
acc3f067-1a37-5cf8-8783-8ccf8ac201b3 | note | Discipline (e.g. CIV/STR/RAIL): 223-CIV
4f727b9b-4355-5824-9d8c-01800b4b3107 | note | Revision Number: 0
65398982-373d-5986-9fe3-57d821f437f7 | note | Revision Date: 27/11/2024
f7873f65-18d5-57a8-80cf-7e44a0497f5e | note | ITP created by: Victor Mira
8da14e96-bb94-5189-9662-9a91a8e06d26 | note | ITP approved for use by: Victor Mira
f2ff941a-25f9-59be-84a3-ec6d3802e9cc | note | 1.1 Non Dependent
30c2673c-a55c-5c34-bde1-ab0e375cb096 | note | Reference: VR 407 - July 2022
ec993a8a-374c-592c-a4fb-35be26ba1e4d | note | 1.2 Non Dependent
e7476514-a6a7-5e76-8f40-37195a10968a | note | Reference: VR 173 - Oct 2008
| section | Preliminaries - Materials
| checkpoint | 2.1 Aggregate
0d489a53-be18-5195-a1b5-1a8382b4551b | note | REFERENCE: VR 408.11 (a), VR 831.05 (c)
54432a96-7ad9-5796-9318-6608b42c297e | note | ACCEPTANCE CRITERIA: Aggregate shall comply with VR 831 - Aggregate for Sprayed Seal Bituminous Surfacing.
cc248ec0-7728-5b5d-8f4f-fa930d44b06b | textbox | Enter: Teambinder Approval number
01a9c6a0-03cd-5353-ac0d-1c7a518c7384 | note | METHOD: Document Review
a3e5326f-261c-5def-9dd8-7ee6b482214d | note | FREQUENCY: Each Material
165d924f-3975-5eae-a5c7-feb013d3c5bc | note | CATEGORY: HP
14dc62e8-c6da-5656-a67e-23f4652d9d18 | note | RESPONSIBILITY: PE/Nominated authority
5ef9c553-2de9-5982-a8aa-e513921ac054 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
45a2e04c-adff-58a0-9fdc-ee569865ff6a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bitumen Emulsion
b4580e16-22bc-5154-83a2-afbefa2b4b2c | note | REFERENCE: VR 408.08
0bcfd13b-5fd8-53f6-8c39-09e62f7221b4 | note | ACCEPTANCE CRITERIA: Bitumen emulsion shall comply with the requirements of AS 1160.
20dd568f-e962-5c64-95e6-4c9c97df1a59 | note | ○ The use of any non standard proprietary classes of bitumen emulsion shall be subject to the Contractor providing evidence that the product has demonstrated satisfactory field performance for a period of at least three years.
1dfe5b4d-e40c-582f-af34-cb58142b9569 | note | ○ The primer shall be cutback bitumen.
719325ca-ba40-5be1-b865-57c80bebbb2f | note | ○ Cutback bitumen shall comply with the requirements of AS 2157. An equivalent product may be used subject to the Contractor providing evidence satisfactory to the Superintendent that the proprietary product has demonstrated acceptable field performance for a period of at least three years.
7e109cc0-f784-59dc-87ff-dab252a7aff1 | textbox | Enter: Teambinder Approval number
05056961-109d-5722-89fb-64b4592df379 | note | METHOD: Document Review
06f45966-7d1a-5950-b977-32a0ebff51dc | note | FREQUENCY: Each Material
1fbc6b08-ddce-520f-bd1e-6ace440fdd36 | note | CATEGORY: HP
1d9dd1a6-13a2-5db2-9c50-47fec10191b4 | note | RESPONSIBILITY: PE/Nominated authority
4a3a77ad-d113-5c1f-a3f0-f9fdc46b1664 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
d874b1b0-6aa0-5cd0-9ad0-77d43b776f86 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Application of bituminous material and aggregate
9deb216b-0eef-57cc-95c4-68eb7447b00f | note | REFERENCE: VR 408.13 (a)
2d6b730c-9692-5b43-a87a-94df765a0246 | note | ACCEPTANCE CRITERIA: At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent.
2f17e505-b66c-557e-a463-ae8806b5160b | textbox | Enter: Teambinder Approval number
4826edeb-e562-5160-ab76-fc0551f0541e | note | METHOD: Document Review
ab6c3497-9fd2-5003-8fa5-c666232b629f | note | FREQUENCY: Each Lot
45d26485-5239-5173-99ca-775913cdb019 | note | CATEGORY: HP
69e034e0-ee4a-5d21-9c12-7bb5de618f9e | note | RESPONSIBILITY: PE/Nominated authority
760b9cf9-440e-542a-8ae2-80511e773a4c | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
0f36510f-3262-5708-84ee-b90f4e141cca | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Application of bituminous material and aggregate
e7d6848d-1bc3-54dc-9709-76c1a346e1f6 | note | REFERENCE: VR 408.13 (f)
a9c5af3b-799e-5d66-9ee1-141f071aa5db | note | ACCEPTANCE CRITERIA: Where the Contractor proposes to use forward aggregate spreading plant, written approval is required from the Superintendent prior to use, unless written approval has been previously provided by the Department of Transport.
af21b35f-afaa-5ac1-ac8d-d23b1f1a7c38 | textbox | Enter: Teambinder Approval number
c45db6b7-65a0-5b4a-8632-4395172cc21e | note | METHOD: Document Review
eecdbf20-c633-5475-b1af-7fe8c8d25a25 | note | FREQUENCY: Each Lot
86154166-605f-5d21-b61f-6f0f6850abaf | note | CATEGORY: HP
034635b9-b06b-54b1-a276-121a3ecef1c4 | note | RESPONSIBILITY: PE/Nominated authority
31a242cc-55f4-5139-a0ca-b7b52c2b3835 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
421bcb3a-bd79-5071-a44e-2430573bdd0b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Claibration of Bitumen Sprayer
9165c715-327a-5c91-af2d-552cbaccd94d | note | REFERENCE: VR 408.07
7c31210c-ba74-5a6a-abc8-94ec98f22f7a | note | ACCEPTANCE CRITERIA: All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads test methods AGPT T530 through to AGPT T536. The Certificate of Calibration shall be renewed every 12 months. If any sprayer has its spray equipment overhauled or replaced, it shall be calibrated and issued with a new Certificate of Calibration prior to use.
094521ba-d0f3-57db-8900-cb903b7b02e6 | textbox | Enter: Teambinder Approval number
5787accf-b133-5528-a2f2-a0d63d0f0b62 | note | METHOD: Document Review
025b6cc5-26f3-51e9-9fe3-186dedcae064 | note | FREQUENCY: Each Lot
b07de64a-53dc-5ca8-9d55-27bfa803ff33 | note | CATEGORY: HP
f4004ba8-697b-5ae1-8a38-c0000dee8f6f | note | RESPONSIBILITY: PE/Nominated authority
5cab3ddb-f9ec-504e-b822-ff3c4a9c476e | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
53f5b8dd-87c1-5918-8e03-8e5a25fe3499 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
22569cad-2b79-593d-88ae-304607387c6d | note | REFERENCE: MRPA Quality Management Plan
b2545337-852c-5504-9e38-ce3e8841c740 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
c08fab89-08da-5a75-8f1c-69a9735c43c5 | note | METHOD: Document Review
a865f74e-80bf-56d1-974a-93fc5a0a520c | note | FREQUENCY: Prior to starting Works and at regular intervals
8d4528e2-cc49-5d74-a81b-c941705d815c | note | CATEGORY: HP*
dd8fa37b-5df7-5810-90c4-aeed3140eba3 | note | RESPONSIBILITY: PE/SE
ec46b3c6-eb03-5766-9449-3d3a8f8ee455 | note | VERIFYING DOCUMENTS: This ITP
39a63f41-00d4-53da-9f1a-08e68d3f258c | date | Date Completed:
| checkpoint | 4.2 Survey set out - Lot Map-and Lot size
8f57ddd8-7aed-5804-bd8f-cde31990cff9 | note | REFERENCE: 408.05
3caa46a2-57df-5b67-afb4-84b57f06c1f7 | note | ACCEPTANCE CRITERIA: Limits of work at the start and finish chainages plus the limit in any side road have been marked on the pavement surface.
cca2ef40-310f-533c-91da-edbeb884e1c0 | note | ○ The Works shall include all existing tapers, bell mouths at intersecting roads, pavement widenings (turn lanes), traffic lanes and sealed shoulders, unless otherwise specified.
5dfbf0d6-908e-5ce6-8196-c066f984c30d | note | ○ ATTACH: Lot Map with planned location of Joints
50428179-d884-5e5d-be3f-b3aa82fe23b5 | note | METHOD: Document review
31b86c13-a814-5df2-8947-5419b055cb7e | note | FREQUENCY: Each Lot
6031cefb-fd54-5b88-a833-84950f36ac07 | note | CATEGORY: HP*
99d377bc-42ae-568b-8912-e57222c83fd5 | note | RESPONSIBILITY: PE/SE
69022ce4-6141-5813-b645-0d1a94856a09 | note | VERIFYING DOCUMENTS: attached Lot Map
91743637-f9e1-52ad-bc3f-07c764b1f577 | date | Date Completed:
| checkpoint | 4.3 Pavement Preparation
05670859-c312-557f-9b10-35535e6f70bc | note | REFERENCE: VR 310.02
dcf8eaae-80a2-55e8-941d-948de192c9bd | note | ACCEPTANCE CRITERIA: The pavement shall be prepared to produce a surface that is:
30fdc0f8-f66c-51fd-9aa2-07b380f9ae4f | note | (a) constructed to meet specified shape and level requirements
341f30f6-ca8b-5e5b-9dfb-7c15dad66cfb | note | (b) homogenous and consistent with the material in the pavement base layer
64bee32d-b499-5b04-abe6-94ec24234fcf | note | (c) uniform in texture
fba2c831-353b-5817-92e3-133bb634e3f4 | note | (d) free of tearing and scabbing
aadf04af-049c-5cdd-9ead-4b949eb5e7fa | note | (e) free of lamination on or within 75 mm of the finished surface
7f2266ce-ade2-50c2-8a7a-6866d510c5ed | note | (f) level with adjacent sealed areas and edgings at the joints
048088a0-cd10-5dca-b628-e2ab7dd43eb4 | note | (g) a hard dense and tight surface capable of being swept with a rotary road broom or similar
80230f1c-99dd-5868-a01f-7f61579e381e | note | (h) free of loose and foreign materials
026421c4-15fc-54e4-847c-df2cd7c0d2c1 | note | METHOD: Visual
3c33c23a-23c2-5de5-bd7c-21c8a5cf3de2 | note | FREQUENCY: Each Lot
48771f22-5f31-5fa6-bcb4-7391de51e700 | note | CATEGORY: HP*
2783f88f-4b5a-5a7c-b118-3765c601b163 | note | RESPONSIBILITY: PE/SE
5eeac913-fb44-5de5-a973-4bcb8c03dbdb | note | VERIFYING DOCUMENTS: This ITP
8dddd5ae-f8e8-57d6-88c4-850104fc5819 | date | Date Completed:
| checkpoint | 4.4 Dry back of Pavement
bb1161a8-7586-5436-982c-4127ae7aed76 | note | REFERENCE: VR 310.03
2817203c-283a-5579-a168-86cfe873f2d6 | note | ACCEPTANCE CRITERIA: The mean Moisture Ratio shall be determined from six randomly selected sites as a percentage of the optimum moisture content based on Modified compactive effort, and determined in accordance with VicRoads Test Method RC 316.14
b3b8ac61-0120-58cf-8265-ddea49591a63 | note | ○ Scale B: Mean Moisture Ratio Less than 60%
7549067e-3dc1-50f4-a76e-7980d18777e9 | note | ○ Scale C: mean Moisture Ratio Less than 65%
bdd52476-ac4b-5495-be8f-029894a463d7 | note | ○ No individual result more than 70%
6df87bda-13c8-5dc3-bc3f-dc7066a31cb3 | note | ○ Attach: test results:
d445fcf4-8c3b-506f-b502-11e50cd78c03 | note | METHOD: Measure
0bac98ad-944d-5ecb-8ff7-a57e3fc03c7d | note | FREQUENCY: Each Lot
00e9ed8a-ce10-5bb8-ba2d-05da377f909a | note | CATEGORY: IP
bd5118e6-06e2-55d8-93d6-f4501936a510 | note | RESPONSIBILITY: PE/SE, Tester
94012627-fffa-5362-a76d-9f977a924c01 | note | VERIFYING DOCUMENTS: This ITP, Attched results
5a7aa7d9-05ba-5df6-bfae-5ccbda54e514 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Acceptance of work - Rate of binder application
8c24ef9e-ffec-55e9-8adc-11f80071b8a0 | note | REFERENCE: VR 408.15 (a)
236de560-4a66-5bd6-bd58-e9fc1475081d | note | ACCEPTANCE CRITERIA: Attach: evidence to show actual rate of application <0.1 L/m2 below design rate of application.
5d380c80-9b6c-587e-9242-85ed1b31a73a | note | METHOD: Document Review
22520ea2-be81-55f5-8cd4-70d7b2c7e8d1 | note | FREQUENCY: Each Lot
82bbdb3e-dd98-5eae-ac99-901ead0eaab3 | note | CATEGORY: IP
5ab299a6-7227-57d9-a55f-dc829835478c | note | RESPONSIBILITY: PE
03bc4467-8297-5f7b-a140-a69b8e3d1dcb | note | VERIFYING DOCUMENTS: This ITP, Attached evidence
8eb0e232-5c33-5eda-a41b-73fb097ee4df | date | Date Completed:
| checkpoint | 5.2 Acceptace of work - Surface texture
fd9a0ce4-2056-54c1-8d53-89a80476f1ee | note | REFERENCE: VR 408.15 (b)
6c6612e8-7e35-5f48-a29f-fc9a6a0cb0ed | note | ACCEPTANCE CRITERIA: Acceptance of work for surface texture and surface enrichment shall be based on visual assessment. However, in marginal cases the Superintendent may request that nominated areas be tested in accordance with VicRoads Test Method RC 317.01
dc877eda-d99e-5d6c-bc9a-129c4e276e17 | note | METHOD: Visual, Document Review
d47439d6-246f-5156-a94a-f12674e88ee5 | note | FREQUENCY: Each Lot
72ead45f-10e6-5594-9888-edc988a25d7d | note | CATEGORY: IP
42600eee-612a-5052-afc6-2fdc5d174511 | note | RESPONSIBILITY: PE
01b4d620-a876-5e2e-8990-bb68baf75b98 | note | VERIFYING DOCUMENTS: This ITP
3dbfd987-1719-561a-922e-86f3339204ad | date | Date Completed:
| checkpoint | 5.3 Acceptance of work - aggregate retention
91e1653a-7cd5-5da8-aaec-7979a526588b | note | REFERENCE: VR 408.15 (c)
0c4684b9-223f-5df9-9958-03d53f7a84a8 | note | ACCEPTANCE CRITERIA: Acceptance of work for aggregate retention shall be based on visual assessment. However, in marginal cases the Superintendent may request that nominated areas be tested in accordance with the VicRoads Test Method RC 317.03
f5549dec-eb58-5bdc-9112-d9899a7f6c8a | note | METHOD: Visual, Document Review
98850fa5-fa9b-5a46-a497-8ce69f9c4416 | note | FREQUENCY: Each Lot
53d7fe4a-45b3-5647-9a15-f07d4ae479ed | note | CATEGORY: IP
040797c3-e7f1-51a7-9ca2-3e10f8f1cdb1 | note | RESPONSIBILITY: PE
2f9ed06c-627a-5850-a70e-1227d3be16cd | note | VERIFYING DOCUMENTS: This ITP
ac700f2f-4ce6-50e8-867d-5da9c80d4cf6 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Removal of loose aggregate
82e8c813-1dcf-54e4-b45e-545244e61d6d | note | REFERENCE: VR 408.14
67dfb7f8-6b0b-5506-b3ff-3f6613b9433c | note | ACCEPTANCE CRITERIA: After the completion of a sprayed seal treatment, the Contractor shall remove and dispose of all loose aggregate within the maximum time limits as specified in Table 408.141. This includes loose aggregate on all trafficked areas, and areas where loose aggregate has been swept, or moved by traffic onto sealed shoulders or non trafficked areas, or into other areas such as concrete channels, traffic islands, medians, open drains, drainage pits, footpaths, nature strips, or verges. For seals of nominal size 7 mm and under,no more than 60 loose stones in any square metre of pavement shall remain.
ed579f17-a93b-5bf6-83c2-a9bff8002e07 | note | METHOD: Visual
f7dc3026-c411-5f82-870a-9f7b63e1d1b1 | note | FREQUENCY: Each Lot
49d9eebf-c19d-563e-9f4c-7f6c9bba462e | note | CATEGORY: IP
2c44f05c-ace4-5307-b1a0-16467a8a5fd4 | note | RESPONSIBILITY: SE/PE
1ef7f83b-90dd-553a-a1d7-1aa8fdd62fe5 | note | VERIFYING DOCUMENTS: This ITP
dce7b0de-a7d8-5bc5-ac60-b8197a9640c6 | date | Date Completed:
| checkpoint | 6.2 Records
8bf9ece4-1751-5fd8-a516-ed480e3a4bcb | note | REFERENCE: VR 408.17
e2eefacc-af2b-5d69-9903-c4208fb8b348 | note | ACCEPTANCE CRITERIA: The Contractor shall forward to the Superintendent a Job Completion Report (Sealing) using the proforma included as Attachment A to Section 408
d695a875-5a30-58d0-a725-20ddb4be0073 | note | ○ Attach: Job Completion Report (Sealing)
f73b33fb-6de3-561b-a8f0-3f0b43807231 | note | METHOD: Document Review
296cd030-3a73-5543-92ca-95b5130818a1 | note | FREQUENCY: Each Lot
b987520c-3cba-54b8-884c-5cba0fe74b3c | note | CATEGORY: IP
1b4d14d5-941b-54b1-a8a0-f67ce4bf016c | note | RESPONSIBILITY: Nominated authority
0df486a9-aa66-5444-bd09-a31c412d769d | note | VERIFYING DOCUMENTS: Attached records
d0464e6a-a4cc-5c38-83c5-d18611909cb0 | date | Date Completed:
| checkpoint | Final Inspection
e25928f9-f3e1-52be-a446-959f5b390155 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aca68ab4-7c49-5cf4-8784-5de249f5836b | textbox | Name:
f9aa7dae-d35c-5c07-88df-d31e13d79c0a | textbox | Position:
9657d242-99d0-5a9f-98a4-81aba8ca3ae5 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-224-CIV-PSDS Hot mix Asphalt Rev 0 | itp | ITP-224-CIV-PSDS Hot mix Asphalt |  | 3cde8a5c-5e2f-40df-8925-b3f4dcaeddb4
| section | Referenced Documentation
| checkpoint | Referenced Documentation
410bbdf3-d82c-5f16-b030-e8de04ba626a | note | Document Title: ITP-224-CIV-PSDS- Hot Mix Asphalt
d352266a-7178-5864-9c74-91cd6822d9dd | note | ITP Description: PSDS- Hot Mix Asphalt
8932b9e4-1646-5399-9d5e-e3531538938b | note | Discipline (e.g. CIV/STR/RAIL): 224-CIV
b103d77e-fa2e-5bfb-aba8-cfcdf6214b74 | note | Revision Number: 0
f88fded6-01e2-5012-b02d-faafc1a3d07a | note | Revision Date: 27/11/2024
b07fa595-81e4-5749-bdd6-788d09477d1f | note | ITP created by: Victor Mira
985c567f-5de2-52e3-9023-166fcfdc4cb5 | note | ITP approved for use by: Victor Mira
410515a9-7219-54ae-a36b-90cd64be74be | note | 1.1 Non Dependent
b7e8cc05-e1ab-56cd-8ddd-a3f9d39b2602 | note | Reference: VR 407 - July 2022
b9a983d1-f42c-5a6e-bc4f-c1e7135fb932 | note | 1.2 Non Dependent
0a0a354b-f1bd-57de-ab6b-f4427cbd35e0 | note | Reference: VR 173 - Oct 2008
| section | Preliminaries - Materials
| checkpoint | 2.1 Mix Design
06b04b1f-7d3c-50dc-b4ca-f8fcaf04578b | note | REFERENCE: VR 407.09
62755f5d-f738-5c11-978e-6008dd19585f | note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
b487dcd2-6862-5715-a401-5e7d2ec6ca0b | textbox | Enter: Teambinder Approval number
a52ff62c-d130-546e-ac69-093bd80cd949 | note | METHOD: Document Review
e43e261d-d21e-5958-a59d-d18565f00e5f | note | FREQUENCY: Each Mix
c00df339-be14-53d4-b5d9-cbc97b36be1d | note | CATEGORY: HP
e46d19f6-bb5a-5c2a-b540-f1ac3f3a7a20 | note | RESPONSIBILITY: PE/Nominated authority
429093da-56f4-5ae7-8cf6-bb6e4cdf7ceb | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
394d13c8-c4fb-5a48-91a5-7cc5e0382b41 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bituminous Materials-Tack Coat
c1f02553-ad3f-59c9-b827-a70ccea00ff5 | note | REFERENCE: VR 407.08 (d)
eec46c28-eef0-58b8-8bcf-a59cf45b47d0 | note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder.
5b020237-2061-5c92-9798-7c5abd447331 | note | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
560c475a-939f-5bc6-9e84-a60bdfc04a67 | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
efe878cb-96e6-564f-afd6-3859b2956764 | textbox | Enter: Teambinder Approval number
111af58a-89f0-557b-8aad-ef9f9d2a3afa | note | METHOD: Document Review
32657480-fe80-5002-a6ff-ebf179880a93 | note | FREQUENCY: Each Material
d5682984-160d-5334-9194-5d62ac3546c9 | note | CATEGORY: HP
ddca1783-c0b0-501f-86fd-c12e9de4aa52 | note | RESPONSIBILITY: PE/Nominated authority
3993a5a2-812b-5b7b-b459-67197230e0dc | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
5214d0a8-45b3-5ece-a973-289dfa81f435 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Asphalt Quality Plan
f5ce6cb3-380d-5545-8e66-a5547c4e4345 | note | REFERENCE: VR 407.04, VR 407.11
d4315fc1-94ba-5149-9aba-687409a65111 | note | ACCEPTANCE CRITERIA: the Contractor shall provide an asphalt quality plan that addresses the following requirements:
39f3388d-2117-546e-a9d7-22fa5370a745 | note | ○ RAP Management plan (Approved by DTP)
48d5284f-4038-56b0-a810-cac71c402a11 | note | ○ asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
f5ec4eb3-c7d2-5977-b796-aac4fd068ce7 | note | ○ measuring and recording of pavement temperature, wind speed and weather conditions
be366eb2-855c-5ccb-9691-96893c92c86d | note | ○ achieving a uniform application of tack coat
5e21d61b-6643-5888-a752-6c62962bad93 | note | ○ achieving uniform asphalt placement including determination of paving speed and paving plans
ed1472bf-2bc3-5cb5-95b1-08fcd9425468 | note | ○ determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
cc6e8514-b791-52ba-8807-37d53589a110 | note | ○ procedures to maximise density at joints.
07befba8-48b7-5708-bf50-604bd2e46b7a | note | ○ Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
f43fba14-130c-5029-9492-e3cb51e6c0ad | textbox | Enter: Teambinder Approval number
b8430b85-b628-586d-b98b-e16208c369b3 | note | METHOD: Document Review
ca5e0085-1349-57cf-8bc7-24a12e06605b | note | FREQUENCY: Each Lot
24743bcf-9353-5e05-aa39-06b50bc8079c | note | CATEGORY: HP
4856d846-c1e2-56db-ab8e-ae88da6cec77 | note | RESPONSIBILITY: PE/Nominated authority
8801d9f0-7af8-52f7-9c6f-fffec41dc094 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
49b2c12c-0695-5a45-ab50-b7019a866c91 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 RAP Management Plan
4bd870b8-6b5e-5d9d-9418-4bfc6cedd9a9 | note | REFERENCE: VR 407.13 (f)
c33f9707-976c-5fa0-b37c-9a166b80a88d | note | ACCEPTANCE CRITERIA: No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
61f0ceb9-0f6e-56f4-a675-0fe5dcec45a4 | textbox | Enter: Teambinder Approval number
67e05f25-4bc1-5fde-b374-ad5cef0bf412 | note | METHOD: Document Review
7186c381-a3c7-5fba-87d6-75debbdffdfa | note | FREQUENCY: Each Lot
38ef2339-8026-5513-88b5-6a62e3ddd300 | note | CATEGORY: HP
1908da9c-5de1-563d-bcd2-1911ef42bb06 | note | RESPONSIBILITY: PE/Nominated authority
e7a0e9cb-63ae-5061-a8a7-6c5feecb8336 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
1d9209eb-6a52-5469-9b32-defc2bd233a1 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Cold weather placement
a6e2ddcd-bbdf-5745-aabd-44663e4178a8 | note | REFERENCE: VR 407.17 (b)
cf936833-6c7a-5a43-9d1b-9a232a0d25a5 | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
14508983-2590-55d8-ac23-fe65f9ff4df6 | note | ○ Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
82ef1ba3-b79b-502e-96ec-749f585fc8dc | textbox | Enter: Teambinder Approval number
5cb47080-728c-5c35-b11a-c7c9e293d9e9 | note | METHOD: Document Review
716c5549-d2ce-55f2-9b51-8f435a40e880 | note | FREQUENCY: Each Lot
8751d2b9-44f4-535a-85dd-e3cb3120c5a6 | note | CATEGORY: HP
a31a1fe6-bcab-5b4d-820a-9bcca3be17af | note | RESPONSIBILITY: PE/Nominated authority
925fac07-1a1f-567e-88b9-3010466a0fb5 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
75e50707-f64d-5a9a-9c1a-bb6046d6b269 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
59b8d325-c0eb-552a-9c5e-fdea33fc3483 | note | REFERENCE: MRPA Quality Management Plan
a455f15f-30a6-5734-ba2a-89962d5ef690 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
aa99d3a5-4c34-526f-b0fc-bbe9504789ba | note | METHOD: Document Review
edd2c29c-7a8a-5527-94a3-1af167cb58b0 | note | FREQUENCY: Prior to starting Works and at regular intervals
41343059-c92f-5f47-b8f1-21987cfb27ea | note | CATEGORY: HP*
c500dcd6-202a-520b-9aef-c3e5c45474e1 | note | RESPONSIBILITY: PE/SE
9b76c87f-ee67-5c52-b30e-965fea512442 | note | VERIFYING DOCUMENTS: This ITP
55aa8e1c-6bfb-5e4b-b1b6-9dafa667034f | date | Date Completed:
| checkpoint | 4.2 Lot Map-and Lot size
03b93a2c-802d-57db-838e-32077396674a | note | REFERENCE: VR 407.21 (a), VR 407.27 (b) (i)
5325bdd0-e2fa-5a82-bdbf-87f2b6fdf737 | note | ACCEPTANCE CRITERIA: A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
a3da97b0-3a3a-5859-96e2-642a620c773a | note | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
59544a74-3071-5a02-8c11-e9c0bc8fae93 | note | ○ ATTACH: Lot Map with planned location of Joints
900aab73-3f11-5648-8e10-bdf12ba73855 | note | METHOD: Document review
2912301f-51cf-5fd2-b076-8b0795dce7b5 | note | FREQUENCY: Each Lot
018158a2-8acf-55b2-b32c-606210935fbd | note | CATEGORY: HP*
48687b5e-a649-5ad9-b38f-b2f7f9cbd22c | note | RESPONSIBILITY: PE/SE
377a348c-ebd8-5011-8b1f-27e0a0477df5 | note | VERIFYING DOCUMENTS: attached Lot Map
5e889ae0-c218-5ff1-897b-c67c4bdfa114 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Ambient Conditions-Surface conditions
530d0a05-c4e9-5784-9586-cd4fc199be59 | note | REFERENCE: VR 407.17 (a), VR 407.18
11824369-d2c2-508c-bd69-642b865383c8 | note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent. The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
72955640-cf61-5686-8cde-36a814bc53e1 | note | METHOD: Visual
0149982c-a329-5a41-bcd8-448e380dedfb | note | FREQUENCY: Each Lot
24e822b9-cb4e-5bc7-8c17-c833fa15c200 | note | CATEGORY: IP
8755086b-b3f6-561e-9801-cf4c4fbfa859 | note | RESPONSIBILITY: PE/SE
2388c502-d4b4-5e14-9de2-cc5b237746de | note | VERIFYING DOCUMENTS: This ITP
36b09d6e-a51e-53ac-a26e-0d1af6f02565 | date | Date Completed:
| checkpoint | 5.2 Ambient Conditions-Surface Temperature
4cfbcad2-ccfa-5180-b4e7-e98e5d72dc55 | note | REFERENCE: VR 407.17 (a)
4b7874bc-2f9b-5897-a58a-f379aeea1e8e | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
5336d22b-8b80-5f4a-b15e-3a27b20fc12d | note | ○ Specified binder class of C170 or C320:
0adfb017-f745-50bf-855d-435b4004fa81 | note | – Wearing course: 10°C
5c2d5087-6d94-5c34-9cd1-60b3b5d928c2 | note | – Other courses: 5°C
ef5f6f4a-3cc4-53d4-91cf-ab7021905b8c | note | ○ Specified binder class of C600 or containing a PMB:
374b30b7-4c52-59fa-a38f-8bced7247b8d | note | – Wearing Course 15°C
bc510173-8b93-5d92-802f-d26c54e2e461 | note | – Other courses 10°C
655a11c0-7977-567f-a724-212acea695e3 | note | METHOD: Measure
02cc8ea7-41f7-59ab-9d79-497970eed7c6 | note | FREQUENCY: Each Lot
45858ce5-efce-551e-8cfa-cae73d901e4d | note | CATEGORY: IP
29e615e4-f3c2-5b26-a3e0-a3fea01e0e6b | note | RESPONSIBILITY: PE/SE
a063fd27-319d-5848-8548-1cab972c0cf2 | note | VERIFYING DOCUMENTS: This ITP
1f3d2202-95c0-5565-b0a4-40ca22f71756 | date | Date Completed:
| checkpoint | 5.3 Joints and Junctions-Layer by Layer-Transverse Joints
3ae3fb28-eb33-57af-88f1-f82336e77e30 | note | REFERENCE: VR 407.21 (b)
8f6c3082-9657-56de-a144-d3bb6259c668 | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
59bfed7a-7074-53e1-b712-93ac6da84bf8 | note | ○ All transverse joints shall be offset from layer to layer by not less than 2 m.
3c10aacc-215f-5869-b2e7-b61c39e47eca | note | METHOD: Visual, Measure
ba9be9b4-d6e1-5908-b03e-164daaa84de9 | note | FREQUENCY: Each Lot
8f132115-7200-5b43-a5b8-7e840da09d69 | note | CATEGORY: IP
288fa91d-f576-5dbb-9215-26dae3da9456 | note | RESPONSIBILITY: PE/SE
6bf592f3-ed06-52f1-b160-20a342f91032 | note | VERIFYING DOCUMENTS: This ITP
f9018d99-e852-5574-88cc-882a249b7868 | date | Date Completed:
| checkpoint | 5.4 Joints and Junctions-Layer by Layer-Longitudinal Joints
943b30d9-8347-5ec9-a574-1a373f1170e0 | note | REFERENCE: VR 407.21 (c)
3df1a73c-5d71-57e4-ba2a-beaa4de0bcb0 | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
ea19da68-553b-5110-bb6d-f1f23c23df84 | note | ○ Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
cd98adc1-e48d-53df-99e1-762a6300fe26 | note | ○ Longitudinal joints shall be parallel to the traffic lanes.
cc5e509f-dc27-501b-b2f3-e267f933ad39 | note | ○ Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
aaf80a22-c5c2-5a70-8bae-518b9dfcbbd4 | note | METHOD: Visual, Measure
a4a6a5ae-140c-5831-9335-0b2da53ec5db | note | FREQUENCY: Each Lot
d56d62d2-9f73-5ea0-8b43-261ed902344f | note | CATEGORY: IP
845514f9-b01f-58ef-b33f-eb243f5bad1d | note | RESPONSIBILITY: PE/SE
fa64653e-43db-50f4-a32b-0100c477e237 | note | VERIFYING DOCUMENTS: This ITP
40c52f4f-d9b5-5ccd-bd02-b9412aa85e0d | date | Date Completed:
| checkpoint | 5.5 Joints and Junctions-Abutting existing pavement
5e77b61d-2d21-5457-a49a-3e71599eb5fa | note | REFERENCE: VR 407.21 (c)
8920fdd6-9d64-58b4-a896-8bc1178d81f7 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
2d56c6ac-c260-54ab-bb60-381d20777d1a | note | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
db3a11a2-6df0-536a-8058-655ef77e6fd1 | note | METHOD: Visual, Measure
adff33dd-5080-5260-bf6d-4a82d4a4904e | note | FREQUENCY: Where applicable
81e73e48-2f13-54d9-84ae-95efde653be4 | note | CATEGORY: IP
4a787d7f-57d8-51f4-b0d1-70ad697c72d6 | note | RESPONSIBILITY: PE/SE
e86171c9-9959-52cd-bb9f-33359616852f | note | VERIFYING DOCUMENTS: This ITP
e69e6b3a-b9ac-5690-9993-bbffdc071490 | date | Date Completed:
| checkpoint | 5.6 Joints and Junctions-Junctions at limits of works
2d025638-b027-50ea-bf0f-f67c4aa0c628 | note | REFERENCE: VR 407.21 (d), VR 402
45be491a-a568-5767-9799-30ca05bc8e16 | note | ACCEPTANCE CRITERIA: At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
9bbac3dc-4fee-5d9f-b709-b7f7b2c0b115 | note | ○ The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
575dc0a0-6551-5de8-8c0b-d2beb091ae9f | note | (i) at side streets and median openings – 600 mm
13d34b9e-4ee9-54c5-9fef-d02dc2b54930 | note | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
0e26b847-5845-5ab8-943f-d6e1f20941c3 | note | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
e14b010a-98b9-5316-9731-1cec199cd60f | note | METHOD: Visual, Measure
3bf16058-5e07-5983-aff9-946cbc12801c | note | FREQUENCY: Where applicable
7a990100-ef00-58c6-a474-0f95a0a71cb7 | note | CATEGORY: IP
80538580-90f0-5120-a1da-aa906cdc94fe | note | RESPONSIBILITY: PE/SE
66f8b40d-f668-5b87-bb57-e153f0d6b81a | note | VERIFYING DOCUMENTS: This ITP
080a9826-14da-589f-ab0a-4c68b85bfddc | date | Date Completed:
| checkpoint | 5.7 Application of Tack Coat
0d0843df-ea7d-55cc-8ebb-d27e1c7eab5e | note | REFERENCE: VR 407.19
907004a5-e49b-55a9-b4c1-1bedc73c3841 | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
e9970263-7f99-5cce-b2b3-39b9c8ef5682 | note | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen for joints and chases rates shall be doubled.
8bc6ec91-f7dd-54d8-8975-db8db1e583a1 | note | ○ The Contractor may omit the tack coat where asphalt is to be spread over
f3c44261-c22c-5fbd-b605-8bfd8ad56751 | note | – A clean, un-trafficked, freshly laid asphalt, or
c038e671-265c-5613-8987-b41e9f7952f8 | note | – A clean primed surface, or
b78488a7-5271-571e-82ca-057ba9eca4da | note | – Granular material where the overall asphalt depth is 150mm or greater.
dbb81450-64a5-5740-87ce-617ae97ce5a7 | note | ○ PHOTOGRAPHIC EVIDENCE shall be supplied to show that tack has been applied.
2252ced9-987d-5e09-9887-ad39505ef9a7 | note | ○ ATTACH: Photographic Evidence
69c625ef-96fe-5d8b-b410-4cc540ce47e8 | note | METHOD: Visual
db24d9ee-a476-5145-91de-eb55b7ca1086 | note | FREQUENCY: Where applicable
14e25fa3-28a3-5419-8f21-4f121cb0b81c | note | CATEGORY: SP
db4bb20e-326d-5ecf-b6ea-933263a91c20 | note | RESPONSIBILITY: PE/SE
a1c10dfe-718f-5ead-bb12-b43c84952102 | note | VERIFYING DOCUMENTS: This ITP
dab852fa-5909-55fa-82a3-573beabb2c06 | date | Date Completed:
| checkpoint | 5.8 Joints and Junctions
c67b56dc-f2b0-57db-bb72-c480d1f69fb8 | note | REFERENCE: VR 407.21 (a)
c6898f44-8d7c-5576-9252-21be26e82d80 | note | ACCEPTANCE CRITERIA: All joints shall be well bonded and sealed
11ef1f4c-cefe-5975-a442-f535bbb643c3 | note | ○ All cold joints and abutting concrete edges shall be tack coated
091b866c-8761-580e-bd30-39de535ad9cb | note | METHOD: Visual
6d39a0dc-eec2-576f-8605-021fd86dff23 | note | FREQUENCY: Where applicable
c09336ff-7e3f-5d79-a29c-5ff568f0cc57 | note | CATEGORY: SP
d6fa9abb-6978-5e4f-9a8c-71795fff9687 | note | RESPONSIBILITY: PE/SE
22ceb691-5fb4-5f5c-8282-88febe84a7f0 | note | VERIFYING DOCUMENTS: This ITP
d78102c3-3e4a-529e-a7b7-0363ecefdce4 | date | Date Completed:
| checkpoint | 5.9 Delivery Dockets
847bc522-76e3-53fe-8915-723a82ed1ceb | note | REFERENCE: VR 407.20
1510ef20-6dc6-5a86-b9ab-e48f2d42d49f | note | ACCEPTANCE CRITERIA: Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
b53e60c4-435b-5bb6-a3cc-b12f8726e730 | note | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
e1fa17a3-7e78-5640-93de-f74a52e96caf | note | ○ ATTACH: Mix Delivery Docket
f1a979fc-64a1-5667-b39c-7f95ce5640c8 | note | METHOD: Document review
3c80cfa3-16d8-56b2-8433-311ba1acc9ec | note | FREQUENCY: Each Lot
c19236c0-b52b-5fdc-bc02-a081755c7a74 | note | CATEGORY: IP
3d7fa152-057e-57b9-8343-4e6386115108 | note | RESPONSIBILITY: PE/SE
2ea2ba7e-bd8a-5e12-b4a8-b354f2136d40 | note | VERIFYING DOCUMENTS: This ITP
e59d386b-7ec1-54cc-93f7-9ad45866ae8b | date | Date Completed:
| checkpoint | 5.10 Commencement of Placement
a30432c1-e0ae-5a61-9b71-03077dcbaa94 | note | REFERENCE: VR 407.23
f80dc527-075c-58e7-8b93-c560cd2dfdb2 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
11e432af-d5a6-5e70-a97f-885a70012670 | note | METHOD: Visual
46bc6890-6dc9-5a2d-a1fa-0037e85d7f4a | note | FREQUENCY: Each Lot
5f1fcba7-37d3-5bf9-aa1e-536e9ffdfebb | note | CATEGORY: HP
3b07972e-aeeb-5ae2-be0a-dc20c5320cc3 | note | RESPONSIBILITY: SE/Nominated authority
d1bbc5bd-8416-5b35-b768-4a1b09c62853 | note | VERIFYING DOCUMENTS: This ITP
208fef4e-54f2-51e0-98c7-48e437104985 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.11 Paving of Asphalt
bd8a7e71-7039-5315-95b5-9839345a28d8 | note | REFERENCE: VR 407.25
6da370c6-b075-59b9-a561-80e9bfd3144e | note | ACCEPTANCE CRITERIA: Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
30857e1f-13e8-5072-8346-a317f13ac51b | note | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
df27bcf1-80e4-5240-8a53-b35282ec8cfe | note | METHOD: Visual
537ad7b8-ffc5-5b53-8357-f37006243d3d | note | FREQUENCY: Each Lot
0923cfe9-677d-53ec-9397-22b91c1fe2ab | note | CATEGORY: SP
91560775-46d3-55e4-816f-aa34a8e2723e | note | RESPONSIBILITY: SE/PE
8f0694a4-ba4a-50ea-aea4-a364fc3d3b8c | note | VERIFYING DOCUMENTS: This ITP
47d8c269-29ab-5853-99de-be84e8b9dfe6 | date | Date Completed:
| checkpoint | 5.12 Paving of Asphalt
70c6de62-2e9d-59eb-9454-813b4c109415 | note | REFERENCE: VR 407.25
6e912c8b-f725-587d-8e6a-23d0f4212888 | note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
3ffdb93a-51b8-5d5e-86b4-86cabdeaa8c4 | note | METHOD: Measure
e6533c94-6382-523b-97fc-8a897adf47be | note | FREQUENCY: Where applicable
642b957a-aa15-5f43-a55f-0dfb6727a8ef | note | CATEGORY: IP
cd1cb4b7-e1be-5ec6-a272-175960aa517c | note | RESPONSIBILITY: SE
75c4de01-e158-5c6e-b535-0c834d4a0229 | note | VERIFYING DOCUMENTS: This ITP
2de63454-d3b0-55c0-a74c-e38fc3f1a948 | date | Date Completed:
| checkpoint | 5.13 Compaction
ab0174e2-921c-5010-9448-07ac311a59f2 | note | REFERENCE: VR 407.26
0d5a326f-2e0b-5e21-bdfa-460255cd5873 | note | ACCEPTANCE CRITERIA: Asphalt shall be uniformly. Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
40ee2869-b751-59d5-ae2b-63b773b435ed | note | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
b2a41c65-e77a-5af7-923c-2ff9c59c5745 | note | METHOD: Visual
e12c783b-c3a4-5fbd-a356-3e1871c45fbf | note | FREQUENCY: Each Lot
0bbb1163-8128-5e46-b5be-5d1eac37248a | note | CATEGORY: SP
5c048b71-e10b-5369-adc5-ab893051d6e8 | note | RESPONSIBILITY: SE
3b1ced6a-7e54-5f82-b773-a484d9d7792f | note | VERIFYING DOCUMENTS: This ITP
4bd6ac1b-aa73-519e-8f4a-e8ec8cc56817 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Compaction test-Lots larger than 500 sqm
3621a8d3-6d66-5b0f-bdc6-aba966dff68a | note | REFERENCE: VR 407.27 (b) (i)
5f05b342-9bd9-586a-bafe-0cb59ef3e1c1 | note | ACCEPTANCE CRITERIA: The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
47ea1509-f3c9-5ea0-a4cb-6faed80a1709 | note | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
3d255986-e9cc-5d21-870f-faca025455bb | note | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
6ae8f717-3a72-534e-982e-86f7d1b5eeb1 | note | ○ ATTACH: Compaction test report
953ebe41-f329-52ab-b817-dc5be41c1d21 | note | ○ ATTACH: Wearing course joint strip compaction test results
612c931c-a8d3-585a-957a-953b94f98cc3 | note | METHOD: Document Review
9d01ee5a-8ec9-54f5-9dd2-f3fd4bda3d0c | note | FREQUENCY: Each Lot Where Applicable
8280b3d0-5f62-5bfd-b31a-1b0f1e4753ca | note | CATEGORY: HP
d0d5a89b-4cb0-5c66-b250-5580d8543e38 | note | RESPONSIBILITY: Nominated authority
c63f0c32-fddd-51aa-b6f7-de9529e20663 | note | VERIFYING DOCUMENTS: This ITP
337cbd67-2aab-5e96-94db-7b5a14af56dc | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.2 Compaction test frequency-Lots smaller than 500 sqm
63f73498-f57c-5396-a85b-e98828725be6 | note | REFERENCE: VR 407.27 (b) (ii), VR 173.04 (d)
b54d1646-f175-5253-9611-424ced474c24 | note | ACCEPTANCE CRITERIA: acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
f3ba6748-c71e-5a59-aa33-1debc82978c3 | note | ○ ATTACH: Compaction test results
6fe5b715-9fea-5a5e-9345-82e3e052e1d3 | note | METHOD: Document Review
31132424-2225-5ddb-8104-b66ccfd863b6 | note | FREQUENCY: Each Lot Where Applicable
e4c92c47-3193-57fd-8b0c-f11801a9fd44 | note | CATEGORY: HP
45d0bd11-9138-5bb2-9a2b-6ee7cae0c819 | note | RESPONSIBILITY: Nominated authority
6811309a-9252-5b39-b3f6-6fdf90759718 | note | VERIFYING DOCUMENTS: This ITP
28b9196c-4132-5170-ae8a-066da254f822 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.3 Surface finish and conformity with drawings-Surface Finish and shape
64d6034a-dbc1-5675-a7f4-625853945dec | note | REFERENCE: VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
db23d482-6a7e-509c-aaa1-c1c53d359989 | note | ACCEPTANCE CRITERIA: The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
ae5e3814-4e39-5745-8b2d-fb07ab3c1d98 | note | ○ No point on the finished surface of the wearing course: Shall lie more than 4 mm below a 3 m straight edge
860606b6-e1ca-5829-859d-8bef5bfce477 | note | ○ For intermediate and base course layers: The distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
c19b160f-456b-57e0-91d2-aa6598a0150c | note | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
5ec7da63-780b-5f93-8b37-12c1d4a5e9ca | note | METHOD: Measure
faf7c6e1-bd50-5e51-88a9-53fc5735e425 | note | FREQUENCY: Each Lot Where Applicable
9209b6a2-635e-5f8e-863a-0391e0775e73 | note | CATEGORY: IP
0d4ccb4c-08db-5e3c-9353-0a3a16c45d08 | note | RESPONSIBILITY: SE/PE
c8abd0da-d9ee-5280-bf70-8291bcbfda6a | note | VERIFYING DOCUMENTS: This ITP
c1fe4593-b3fb-57e4-a0e6-0c59ab38bb6e | date | Date Completed:
| checkpoint | 6.4 Surface finish and conformity with drawings-Alignment and width
0910d9c8-223e-55a5-b1ca-ee9cf3bb16d0 | note | REFERENCE: VR 407.29 (a) (iv), VR 407.29 (a) (v)
9335169f-324e-5b3f-8f1f-e1782430c381 | note | ACCEPTANCE CRITERIA: Where asphalt pavement is not placed against a concrete edging:
ce756228-b133-559a-ad4c-a23880027307 | note | ○ The edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
887d3d0b-7c06-5d35-9ba0-9e0d29a25696 | note | ○ The width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
29c65edf-de16-5301-8234-f7d3f48577c3 | note | METHOD: Measure
312ffeb9-c821-5391-80e9-cfd145ac2853 | note | FREQUENCY: Each Lot Where Applicable
4dcecab3-5c05-522e-b448-20b23ebf5b54 | note | CATEGORY: IP
111aed71-8303-5466-9675-aaaa8e24d91c | note | RESPONSIBILITY: Surveyor/SE/PE
f171315c-dc89-5372-9984-4928f3aabafc | note | VERIFYING DOCUMENTS: This ITP
e182bc7a-5e28-5650-a777-af3d4d739588 | date | Date Completed:
| checkpoint | 6.5 Conformity with drawings-Scale A and Scale B
012e758a-ce5d-55b9-9ef9-505c191c22bf | note | REFERENCE: VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
f0b3031f-eb6d-597d-a2d9-305060a5688a | note | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
7c87c1a7-c84a-5f4b-b0a8-2c8fa62eb6cd | note | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
f8085427-8902-55b4-89f2-6ad6f4ad4be8 | note | METHOD: Measure
104a39fa-e708-55cb-b3bf-b2b73b015c36 | note | FREQUENCY: Each Lot Where Applicable
062159c2-08a0-5267-80df-7ef9d23eaa4b | note | CATEGORY: IP
ba75e7a4-a4f7-52c5-9f24-8776173cadb5 | note | RESPONSIBILITY: Surveyor/SE/PE
3be5e35f-865e-5bba-95e4-184dcf48a362 | note | VERIFYING DOCUMENTS: This ITP
fb991bbe-cc14-58c8-a9d5-a6c5cac45801 | date | Date Completed:
| checkpoint | 6.6 Conformity with drawings-Scale C
44aadb04-4048-536f-b243-0b7f6730383a | note | REFERENCE: VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
ac25cc6c-ab1c-5f21-a1cb-625e76aab427 | note | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
355548ea-4574-5595-8f1d-a0987880c415 | note | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
7ef67d9c-1401-5c3b-b4d0-ab101ed2531c | note | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
4ed1af7f-e3e4-5fd3-9316-0f5693452a33 | note | METHOD: Measure
4c31c50e-0497-592b-9cad-0489473ba7e7 | note | FREQUENCY: Each Lot Where Applicable
132225cb-dea3-56a6-bbc9-56954d3dc6d1 | note | CATEGORY: IP
3c26b819-fdb4-5763-9856-1ee239364122 | note | RESPONSIBILITY: Surveyor/SE/PE
14033cf7-5f20-5529-8aae-f58b0d497c4a | note | VERIFYING DOCUMENTS: This ITP
45cda97f-a956-5b0d-9d5c-f358e567819d | date | Date Completed:
| checkpoint | Final Inspection
28c95c74-dfe9-5ece-96e7-356552c5f521 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7ec00682-5b87-55ba-954c-3e7681b97c76 | textbox | Name:
1ce88543-f67a-5e50-864a-561df86a98d9 | textbox | Position:
d9936933-137c-5cb6-9422-85b7a2e80ca0 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-232-STR-PSDS-Concrete Coating-Protective and Decorative Rev 0 | itp | ITP-232-STR-PSDS-Concrete Coating-Protective and Decorative |  | 9d2bd48c-9edb-4228-8f5c-b84f70187cad
| section | Referenced Documentation
| checkpoint | Referenced Documentation
c9918b28-5793-5be0-a148-56d6663d1eb5 | note | Document Title: ITP-232-STR-PSDS-Concrete Coatings (Protective &/or Decorative)
5de36756-827c-5964-9bce-dfde4d01f8da | note | ITP Description: PSDS-Concrete Coatings (Protective &/or Decorative)
ef1c8091-9f2a-5e6d-ac05-ab9b3dfe352a | note | Discipline (e.g. CIV/STR/RAIL): 232-STR
86a906ea-3a62-5588-b751-ef36db90425b | note | Revision Number: 0
74975159-2a9c-5f6c-9ab4-51eda8913777 | note | Revision Date: 6/12/2024
90e952ab-bf9c-518e-99f2-f4f291a4a199 | note | ITP created by: Mike Freeman
829b7226-aad1-5eba-9bda-9af048835362 | note | ITP approved for use by: VM
3d543420-baa5-5ccd-81dc-9db7421dcbdb | note | 1.1 Non Dependent
ab034162-740e-5972-ad9a-2878698d3b11 | note | Reference: VicRoads Section 685 November 2018
7e20225d-fd4f-5496-a99b-06485dd55fdc | note | 1.2 Non Dependent
7555944e-3796-5032-892c-9757cdc79265 | note | Reference: VicRoads Section 686 November 2018
| section | Preliminaries
| checkpoint | 2.1 Anti-graffiti System Selection
a8464183-0e25-50a4-bd9e-0ac94c8039bf | note | REFERENCE: IFC Drawings
5fa699e9-539c-5f8a-bd93-b52a1f2f5240 | note | ○ Coating System TDS
738b694c-9273-5d92-8ee1-aca07a6d0632 | note | ○ Surface Cleaner TDS
013742e6-c484-52db-a43f-9812f4b4c8dc | note | ○ 685.04
00e946ec-b786-5585-9c30-8365bdfa76b0 | note | ○ 685.06 (a) & (b)
20ba32dc-779c-50d8-b739-5d6bdeaf7d67 | note | ○ 686.04
68409f9e-be2e-50ce-8554-24311bcf72b6 | note | ○ 686.05 (a) & (e)
181c187d-3b7e-58c7-b2bf-dfeffd804354 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
090f0113-21ad-5e2e-8acd-a5946edb0837 | note | i. be either a film-forming or a penetrant system
a0d14343-7844-547d-a2d6-b1a6e9125c16 | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
5550ccbe-5c3f-535e-9009-4b3a87f23bf1 | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
9bfac307-71f1-5f65-807f-2e8d9219a4e8 | note | iv. be non-yellowing, colour-fast and not subject to fading
91f4f4c5-a923-53cf-b581-77d6adc2c4e0 | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
7491276f-e0f6-5f3d-96a6-ea80463ed5c3 | note | vi. application thicknesses (film-forming):
8f0cbf63-3606-56c5-8b9b-8844bcc75e14 | note | ○ WFT total = 175µm min. OR
e1329944-deae-513b-a105-dcc361a83be8 | note | ○ WTF per coat = 88µm min.
1e5bed08-1f35-5aa9-bef7-2e6aa12a2086 | note | ○ DFT total = 100µm min.
534c0ec0-dad3-5c08-bdce-4a1d99920a78 | note | vii. adhesion to substrate (film-forming): 0.75MPa min.
3cc797a1-0ef5-5198-9e7a-8511304acc3b | note | viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
c2377704-5086-5c52-b519-3075d067ed91 | textbox | Enter: Teambinder Material Approval number
88bbf316-4306-5215-a623-e21a32664afd | note | METHOD: Document Review
94e4f88f-54af-55a5-82c7-e91032d0e222 | note | FREQUENCY: Once, for each coating system, 14 days prior to application
b4c530c2-ac67-50cb-9b2f-2ea9c59500eb | note | CATEGORY: HP
11d827ad-c899-556a-810c-797b56d2b318 | note | RESPONSIBILITY: Nominated Authority
eccb7826-ad1f-565b-973f-ca3c9af0501a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ec65b11b-5378-5eb5-b896-9f5e4a601da6 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Decorative & Anti-carbonation System Selection
00eec245-6829-5d80-9289-04a05478025c | note | REFERENCE: IFC Drawings
ca156f20-b2ec-5a53-a941-4fb90f234f42 | note | ○ Coating System TDS
d0c6ef84-6890-5b0f-aed5-97dcc3742788 | note | ○ Surface Cleaner TDS
b18c902a-f02e-54d9-931c-75ec98c20490 | note | ○ 686.04
e04a77f4-5592-5fe3-9bda-4e2c0ad0f162 | note | ○ 686.05 (a) & (b)
2540c256-1c0d-57b0-b314-4f7081e43e04 | note | ○ Table 686.051
aec18107-7a3e-5444-8c19-315fb03e20fa | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
e47a8670-4f5a-569d-8d31-24accbe22cfa | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
33f3263d-aca2-583f-8d75-6470adf80cb7 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
ef9774f2-d74e-506d-9f3e-bcffb27b4ed7 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
7b32cf2e-b43b-5864-ac7f-2224285931e2 | note | iv. be non-yellowing, colour-fast and not subject to fading
1c3b214c-c06a-5cee-b6a4-9ff777602a9a | note | v. be guaranteed to last for 10 years of outdoor exposure
c21c8e24-61cf-5672-b0e7-77007d879230 | note | vi. application thicknesses:
1d82ac66-3680-5f93-86b2-fd7d1a341c84 | note | ○ WFT per coat = enough to achieve the total DFT
353ebd4e-ea42-5c05-8d7e-5461995316ab | note | ○ DFT total = 150µm min.
b71afd58-be19-550f-bb47-c77cf031bc8f | note | vii. adhesion to substrate: 0.75MPa min.
65f4316e-c588-5ddb-ae71-e19dbca68dc3 | note | viii. able to bridge cracks up to 0.3mm wide
9235f6cf-85f9-51aa-9962-b0ae82a7e5e8 | note | ix. able to be re-coated within 24 hours
29fd138c-ea56-5f71-8740-d1a7f3d031e1 | note | x. have a minimum pot life of 1 hour
376e5d78-42d5-5d08-b6f7-6d9574c67d84 | note | xi. compatibility to an alkaline surface
aca8d218-6673-51c9-85fe-a08a8f058700 | note | xii. equivalent air thickness >150m
00582d5b-f467-5f24-b130-6d1d6f33481b | note | xiii. equivalent concrete thickness >450mm
999ab160-0e0b-511d-bd94-4759e26f55ca | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
b868f67d-5483-50eb-b0b5-ec3905e3e6bf | note | xv. Water vapour equivalent air layer <4m
ef6022c1-d863-5ced-8bac-eb5f90fb4a17 | textbox | Enter: Teambinder Material Approval number
5204048d-6a66-5dd2-9790-0f0148ec8e9c | note | METHOD: Document Review
c8329f1d-30eb-5287-907b-7e07a1ccfcab | note | FREQUENCY: Once, for each coating system, 21 days prior to application
cd10d572-5592-550e-8542-e6922b0756fa | note | CATEGORY: HP
726234cf-f58e-5b4f-a369-f19975e76b80 | note | RESPONSIBILITY: Nominated Authority
ecba3ddb-72d3-5319-a345-f18ebc4a782c | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
18bc2247-460a-5142-be63-23953811a2df | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Decorative, Anti-carbonation & Anti-graffiti System Selection
1813812a-b2e7-5df5-b1e0-6e3870a67d44 | note | REFERENCE: IFC Drawings
2d92527d-d074-5530-a225-fb6d30fe4a9d | note | ○ Coating System TDS
b0669d88-6a82-5aef-92e7-3a150673c853 | note | ○ Surface Cleaner TDS
06939a44-be22-575f-8515-9de141a053c3 | note | ○ 685.04
a8c52034-3fe2-5565-8cc3-54ea033da4fd | note | ○ 685.06 (a) & (b)
b15098f9-55e2-505d-b5bf-b0ec5adbfe13 | note | ○ 686.04
a7c0c912-5925-5cc1-b30e-1584aa4c6714 | note | ○ 686.05 (a) & (b)
26a83fc1-9864-5b3b-9adf-9b55e9f881da | note | ○ Table 686.051
c7c22ad3-43de-555e-964b-ffde24e07c8b | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
f196505a-6538-57d0-86ff-0d3ada0cf043 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
9ae59efb-a71f-510d-b87c-a7184c83afbd | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
619e6e86-14f9-5022-8fba-ea1b527fc139 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
16d2800d-190b-5141-9fce-42e51bce04c0 | note | iv. be non-yellowing, colour-fast and not subject to fading
4dfa71ef-a1fd-531f-9687-1c9e00e97fa6 | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
50e3deb3-6704-54b7-99f5-dfc792a5f2b9 | note | vi. application thicknesses:
d4f8dd22-7795-5629-9dcb-a7a26a941046 | note | ○ WFT per coat = enough to achieve the total DFT
46afe0a1-07c8-5560-8ba5-6046d16d565a | note | ○ DFT total = 150µm min.
b189462f-dae2-5abb-9864-b12cfc0eec48 | note | vii. adhesion to substrate: 0.75MPa min.
49ba34f6-46ea-54e9-ae07-3265674d1bfb | note | viii. able to bridge cracks up to 0.3mm wide
4ba2ed7e-7892-5bfa-8735-aed37a4cc1a2 | note | ix. able to be re-coated within 24 hours
8fc725a5-b6a1-5e73-b655-2313b28d7486 | note | x. have a minimum pot life of 1 hour
7f400c2f-9bc1-5c5f-b7c1-2ae0bfb2f27e | note | xi. compatibility to an alkaline surface
7653be90-7dde-5bd5-bdc7-d368aed6bd08 | note | xii. equivalent air thickness >150m
c2783aa0-575c-5ac2-ae85-176004680ccd | note | xiii. equivalent concrete thickness >450mm
7769d0c3-6343-5b8b-bc71-275bc2435a5b | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
86debaa6-d155-591b-9ef0-88443f5b68d6 | note | xv. Water vapour equivalent air layer <4m
8ade1807-fa13-52b4-8637-d4309ba5a163 | textbox | Enter: Teambinder Material Approval number
244968d9-83aa-583c-b469-4c9797c6ed6d | note | METHOD: Document Review
53d20a63-ab11-590e-9f7c-2bda09f2f373 | note | FREQUENCY: Once, for each coating system, 21 days prior to application
0a79f528-ebbf-59c7-b855-45579a50e040 | note | CATEGORY: HP
1df1fff8-0d62-594a-8811-2b23763a8f28 | note | RESPONSIBILITY: Nominated Authority
852ba30d-7597-55f8-a526-1860fc6624b8 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
107ecf38-04e3-5479-a9ed-8ca7b8ecc755 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Atmospheric & Splash Zone (Dual Protective) System Selection
a576a30c-104f-5259-a544-c9227f6f2796 | note | REFERENCE: IFC Drawings
101ce3a4-20f6-50db-814e-6a56c854bc51 | note | ○ Coating System TDS
732f6342-f633-5ce3-ae6f-cc9386ae9375 | note | ○ Surface Cleaner TDS
68c5144a-9a60-522c-b84b-dc0e49675558 | note | ○ 685.04
d9e98fc3-a04b-5d80-b27d-8ac4806ecc81 | note | ○ 685.06 (a) & (b)
f1d87aa8-f4ee-5b7a-9970-a1ea4b043ee6 | note | ○ 686.04
d8a7ccd1-317e-5e14-88b3-8ed8634ab24f | note | ○ 686.05 (a) & (b)
b3e714fb-49f8-565a-bbf1-bd75c442b2df | note | ○ Table 686.051
6dbfaa54-7b80-5461-800a-c74bbfddb548 | note | ○ 686.05 (c) (i) & (iii)
4a25c05a-1736-5540-90b6-ea835e9c0a39 | note | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
17b3a63b-991f-564d-ac84-d4a171c386c8 | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
cc550671-c4cd-5a77-b00a-e3e469723ea7 | note | ii. all coats to be compatible with each other
d79c3966-900e-5ef8-a642-ca0e84b74b06 | note | Penetrants:
b5ada1fb-3690-5e0a-a9bd-e3356cc185d0 | note | iii. active ingredients:
c21c9db1-e493-53e8-8484-5cf817163360 | note | ○ Silane = at least 95%
3dd45f79-c470-53e2-a93c-9a4675023967 | note | ○ Solid silane & silane cream = at least 80%
8950272c-cb16-5d15-9e88-19d9780d4d60 | note | ○ Silane-siloxane & siloxane = not specified
41b4adbb-95bf-5caa-a4a0-ea5c0091c007 | note | iv. application rates:
cb6f57b8-eb8d-59cb-88e9-6288bd0da556 | note | ○ Silane = 2 applications of 0.3L/m² min.
e1f8e2e2-38bc-56f4-919e-b2fd68df0919 | note | ○ Solid silane & silane cream = 1 application of 0.4L/m² min.
c487fea4-6759-56c9-bcf8-52602642e3bc | note | ○ Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
3a6d70ab-d272-5895-b5a9-c308f9d281da | note | Film-forming coat:
ce065eef-bd65-5d52-812f-83d96dbb6577 | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
a03f9890-b9b0-58b6-9451-99359e8ba07e | note | vi. to be water or acrylic based, solvent-free
8cab5efa-1ecf-5ecc-84e6-8c4742e6a19d | note | vii. to be non-yellowing, colour-fast and not subject to fading
d98df9b7-e30e-5ae1-ab7d-e7e3ab2e0594 | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
b846915e-69b7-592f-88d0-225156b401d9 | note | ix. application thicknesses:
f6bdcbb6-b9c3-5184-ad9f-cda473ac476a | note | ○ WFT per coat = enough to achieve the total DFT
37190acd-97d6-5507-8eab-ead8cc23ed18 | note | ○ DFT total = 200µm min.
b76318cb-f5fb-5a80-bf8a-206fb9cd6472 | note | x. adhesion to substrate: 0.75MPa min.
3041f450-eaa1-54e7-a923-0b99bc1c2c2b | note | xi. able to bridge cracks up to 0.3mm wide
7c5d3910-75d4-5df9-a5dc-75397fba23a2 | note | xii. able to be re-coated within 24 hours
9a5e613f-5989-56f0-bbfe-203648b1612a | note | xiii. have a minimum pot life of 1 hour
24c807f8-6138-5648-828a-820235c2b332 | note | xiv. compatibility to an alkaline surface
67dc6c35-de35-5196-aff9-fec61eafa673 | note | xv. equivalent air thickness >150m
5906df29-8a2b-59ca-878e-6d36d29eacd8 | note | xvi. equivalent concrete thickness >450mm
70e47a3b-fbf0-5489-9c9a-d8159dd95f4c | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
8599423c-a815-5449-a645-ca9c9aaa583d | note | xviii. Water vapour equivalent air layer <4m
557f1900-4146-5cbe-8a9e-cab9ef40627f | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
3b15218a-9f8b-51ab-8a6e-231fa145efdb | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
08a2441a-456e-5ffb-816f-ca6cb8b04bb2 | textbox | Enter: Teambinder Material Approval number
c556983c-d133-5a11-a405-f3fae9e8a77b | note | METHOD: Document Review
1029dc4b-4e9d-5ad4-a84b-3ea5e6729c35 | note | FREQUENCY: Once, for each coating system, 21 days prior to application
aed75467-e76b-5b5c-bf73-34340d699fdd | note | CATEGORY: HP
bd82140c-2d89-5d60-9ee6-3bc443a87c66 | note | RESPONSIBILITY: Nominated Authority
e6a6de61-07aa-5f40-8fbd-0d6df40808e1 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9fd6df56-cad6-5f35-8fd1-63192cc39601 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Work Procedures
fed2a0c9-4b11-51cb-92b5-a2fbc625f7fc | note | REFERENCE: 685.05, 686.04
41c4c647-e38d-5419-90a6-13d5a77e28bd | note | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
b6159b3a-1bdd-5315-a3b1-287be12b1446 | textbox | Enter: Teambinder Hold Point number
8800342b-4b2c-54a5-8091-473ea3548fd9 | note | METHOD: Document Review
5e1e1dda-da90-5663-a9c0-b5f79698ae1e | note | FREQUENCY: Once, for each coating system, 21 days prior to application
10b4a8dc-e88a-5c32-9ad9-1ce230491f2a | note | CATEGORY: HP
8ed4ec8b-dc4e-5bea-a862-859af5b1d4e8 | note | RESPONSIBILITY: Nominated Authority
ef8b880b-27bf-5257-bde3-c148a518dc52 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f8ab845d-666b-5a5a-9436-b08feed0e9e9 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.6 Coating Personnel & Equipment
e31f4774-41b7-5daf-acf0-32d3ef19c0cd | note | REFERENCE: Coating System TDS
e5c83939-6bc0-5fb9-8322-a4c2e215dcda | note | ○ Surface Cleaner TDS
a7780fbe-72d5-59b9-936e-2a6c1ffbaf89 | note | ○ 685.16
115cff05-18c2-5f98-b7fd-fdd3c561058c | note | ○ 686.18
96f54ba6-20ca-5ad5-a5a7-add236bf2bee | note | ACCEPTANCE CRITERIA: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
ca9e3ee7-d934-5f2b-af95-460d9e9208d8 | note | ○ Application personnel require 2 years minimum experience.
da0b9944-2d0f-5b9f-a46e-6d3bf4527321 | note | ○ The supervisor shall remain present at all times.
8f22fac3-8cc6-5601-bee4-b049b10d3cca | note | ○ Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
2c9fbbfe-0aa1-5949-8a7e-baa0df2b1e01 | note | METHOD: Document Review
f8999471-cde7-55eb-9c03-663f391dd5ae | note | FREQUENCY: Once, prior to application.
d8a684dc-9922-5190-b84f-59cf4e2ac261 | note | CATEGORY: IP
7aa686f5-2b68-57d1-aefb-9b278e479573 | note | RESPONSIBILITY: SE/PE/SPE
8990c0d1-8bc6-51a1-a02d-ad8462008e2d | note | VERIFYING DOCUMENTS: This ITP
aa4d1149-e5c7-567b-9d23-960661a84ff0 | date | Date Completed:
| checkpoint | 2.7 Protection of Adjacent Works & Property
d6e97360-43ed-5150-a17e-9f1054471e56 | note | REFERENCE: 685.17, 686.10
9d13f5a9-79b2-5ff3-91af-b01b133e6f70 | note | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
f701a7af-3836-55ff-8668-32141d89e654 | note | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
87a93db7-b84b-50bd-97c2-8cd48b95cae0 | note | ○ Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
29fe467b-b3ca-523d-b99f-64fd00fe7852 | note | METHOD: Visual, Document Review
13f04d46-a039-50a4-b84d-6ebe14933a3e | note | FREQUENCY: Where applicable, 2 days prior to application.
9f1f38d9-ef43-57da-8fa8-c8b5c43ef830 | note | CATEGORY: HP
c85894ab-c833-5a30-8489-9cdc625c4698 | note | RESPONSIBILITY: Nominated Authority
c388e0e6-687e-5ae2-858d-209a5e685f67 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
36954eca-d826-5e07-8d6f-9151e6f1eebc | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.8 Minimum Concrete Curing Period
168cb6d1-61e7-503f-b0cf-af96b9e1fec2 | note | REFERENCE: 685.08, 686.16
33e9a33d-b04b-5e0d-a9ff-dea1de12e17a | note | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
a45484c4-f406-527a-bde5-38c3130cb5b8 | note | ○ Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
9afd2c29-f31a-55a2-a432-5fd54b1c76da | note | ○ Accelerated cured concrete = 14 days
ccde30e6-6cba-57e7-9303-6fcb07652421 | note | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
3b2d898f-9c05-52c8-be1e-26807151c4d4 | note | METHOD: Visual, Document Review
a3e008bb-cc4b-5aa9-a101-1a82bb974787 | note | FREQUENCY: Once, prior to application.
d2714b45-96e5-5ece-8178-05908316b29f | note | CATEGORY: IP
afc9cd70-98ee-5cae-b7a6-6f6894b18ef2 | note | RESPONSIBILITY: SE/PE/SPE
7638a3b1-a740-580e-9a69-9a134dfa699e | note | VERIFYING DOCUMENTS: This ITP
d2e69ab0-1cac-5232-aa2d-deada1eb0baa | date | Date Completed:
| checkpoint | 2.9 Trial Application (or Past Performance) Inspection
03d77baa-60a5-57b9-9263-e7e42a9d6402 | note | REFERENCE: 685.11, 686.13
d1ce1588-c22f-52fb-9a80-f1c282140d3e | note | ACCEPTANCE CRITERIA: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
0f468753-ed33-5c64-8d01-cfc518527bd9 | note | ○ Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
9dcd95b9-fa15-55ca-b5cb-a122714bb561 | note | ○ Attach: Inspection Photographs OR
e917cf6c-92b2-5b92-9edb-299bf7b64c05 | textbox | Enter: Teambinder Hold Point number
56d550df-5914-5a8c-be64-67157e8f6d26 | note | METHOD: Document Review
79ea2e96-46eb-5526-9e9a-5c471af33417 | note | FREQUENCY: Once, for each coating system, 7 days prior to full coating application
bc344ccf-2720-52d8-b5e9-d1f5f7fe0f00 | note | CATEGORY: HP
b04ffb24-5c48-5a35-a228-39287fb04e35 | note | RESPONSIBILITY: Nominated Authority
f59a0e39-3b80-569d-bafe-77e7f6c4bc9f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ebdbec8c-4776-571a-8584-8060056d12e2 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-application Activities
| checkpoint | 3.1 Material Records
d95d4bbf-69b1-5c90-85c7-77ea1d7a159a | note | REFERENCE: Coating System TDS
a5537d6a-96e1-5912-97ce-ba5b5c244805 | note | ○ Surface Cleaner TDS
f5374d98-ef3f-517d-b964-5f354ccf4c4b | note | ○ 685.10
56dedba5-4b19-592b-990e-b07f4997621f | note | ○ 685.12
79621cea-d283-5106-9ef0-054d0d5699f9 | note | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
1a6f6419-3591-5f84-83fe-6f1acebbed01 | note | – the manufacturer's name & address
ec79181f-d23b-5354-b28a-5e8cf78451f8 | note | – product reference
006b70a9-c775-5197-80f3-2e56f1d9c6b8 | note | – batch number
8f7c600e-534e-5ae2-b071-d326945c5337 | note | – quantity manufactured in the batch
857741ee-1726-5536-8fc6-a120177138db | note | – date of manufacture
919d9db8-ee0c-5812-9728-e7a470c2d7da | note | ○ Product beyond the manufacturer's shelf life shall not be used.
140561cd-976f-52a0-b5d3-4fe3b61f0fd9 | note | ○ Each product shall be traced to final location.
be3643dc-f930-5c9b-bc4a-0ff34707b7fe | note | METHOD: Visual
89bffed1-9e9e-53c3-860b-5a95f2ca1d3f | note | FREQUENCY: Prior to application
fd452f65-b0f6-5bf2-bbae-cc74c54dd676 | note | CATEGORY: IP
f70d58e7-204d-5cee-8e3c-c8cc28d49c9b | note | RESPONSIBILITY: SE/PE/SPE
fd0f21ec-ec5a-5818-aa75-eda32e5c81ca | note | VERIFYING DOCUMENTS: This ITP
68e5f95d-1862-5b25-815f-07e1a2d15947 | date | Date Completed:
| checkpoint | 3.2 Weather Conditions
25048e9a-de41-59e1-87d6-4f6ec110dcdd | note | REFERENCE: Coating System TDS
573e1d23-444a-5cad-b930-258db6b05ae8 | note | ○ Surface Cleaner TDS
29d8dbb7-4152-53dc-b3c3-fd345a220601 | note | ○ 685.09
ed73a620-601a-5350-8fec-92e63b9df67b | note | ○ 685.12 (a)
698296a3-893b-5f66-92ad-fd8f929d80ac | note | ○ 686.11
0dc4ed92-9b94-5529-824e-3d5c278fdff7 | note | ○ 686.14 (a) (iii)
8ff51185-4591-580b-a3dc-a1e71b4054be | note | ACCEPTANCE CRITERIA: Coating systems shall not be applied under any of the following conditions:
ffe2732b-be3b-5157-8c0e-9b6bff087973 | note | i. windy conditions where spray/splatter may be generated
f19e5c6c-c228-5708-99f1-c7618d3abfa6 | note | ii. when wind-borne debris is likely to contaminate the uncured surface
80d03841-9fb1-597c-ab58-a0393e40dc4a | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
0a8ffc88-4ed3-54c9-a830-1231b3d2ad17 | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
61fb25cb-d058-5b4f-b1d5-70135f3b81bc | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
dcd84b8d-5d5b-52ea-9b65-29de5a1e7618 | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
bb4316ff-3389-5a10-bd8b-87994ecfb671 | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
9dfa9101-3826-52fb-be81-8e447c8c6881 | note | ○ Weather conditions are to be recorded.
2ef83a4d-cfa6-5253-82fe-e8361ad332ee | note | METHOD: Visual, Measure
f9bfec7d-2724-581c-b12d-5d7619a8c6fe | note | FREQUENCY: Prior to application and every 4 hours per shift
12cdf1f1-1129-5962-b21f-53f57a0c7609 | note | CATEGORY: IP
965e1a9c-ac39-5312-bd9c-edfe28d4af55 | note | RESPONSIBILITY: SE/PE/SPE
8979bb2f-9d61-5a8b-8606-adb187894f87 | note | VERIFYING DOCUMENTS: This ITP
7a956432-7aad-5983-8a68-703d5917ac74 | date | Date Completed:
| checkpoint | 3.3 Surface Preparation
31be042c-b037-52ff-9339-33fdcc3dd0ac | note | REFERENCE: Surface Cleaner TDS
c4232555-456d-57f5-bfce-97bdd91d7738 | note | ○ Coating System TDS
1bbb0cc3-feb6-5d7b-869b-441915bd5072 | note | ○ 685.05
12d3fb05-1842-52af-87ec-af050bfceb0f | note | ○ 686.06
c622f8fc-6d49-5878-8e4e-54166476587a | note | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
9adccaf4-03af-5e0b-919e-b889b8284adc | note | ○ The surface shall then be flushed with water.
dd01fde0-2b82-54b2-9352-77a2c157af2e | note | ○ Any concrete defects exposed during the surface preparation shall be repaired accordingly.
a008a98b-c019-578a-ba62-d5c6f9ec6484 | note | METHOD: Visual
433477f8-e85b-57aa-b94a-d37576040e3a | note | FREQUENCY: Once, prior to application.
e797a876-b953-5b28-beb5-ae271bc139c0 | note | CATEGORY: IP
7b615675-870c-5247-b90f-73b7d35bc2bd | note | RESPONSIBILITY: SE/PE/SPE
04c6aa72-b1e3-5a6c-b620-78638ffae874 | note | VERIFYING DOCUMENTS: This ITP
1e4d51fd-b0c4-505f-b9ac-df4f546d0996 | date | Date Completed:
| checkpoint | 3.4 Surface Moisture Testing
b76472ca-4e1e-5875-81b3-976f314ca1e7 | note | REFERENCE: 685.12 (a), 686.14 (a) (iii)
85e290c7-5901-5013-aa7b-b97cfa5620db | note | ACCEPTANCE CRITERIA: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
18fc0f9e-0e5f-57ef-b957-a6835b7f4c2e | note | ○ Surface moisture conditions are to be recorded.
e1e10fc1-5d67-516e-bc6f-74677017a57f | note | METHOD: Test
fe19beb5-e22b-5935-9265-a8ba01a79fc1 | note | FREQUENCY: Immediately prior to application, 1 no. test every 50m²
86348ab6-bfae-5cfb-b900-a7f6eee22b0e | note | CATEGORY: IP
aac66924-8de9-5686-a16b-d36d89f3d872 | note | RESPONSIBILITY: SE/PE/SPE
adbe5fff-e446-59ae-a3e3-57a707b6bac2 | note | VERIFYING DOCUMENTS: This ITP
ea1f2a96-7ed1-5b62-abeb-2776d0e79284 | date | Date Completed:
| section | Application Activities
| checkpoint | 4.1 Method of Application
ddafd2e8-07aa-5926-874e-c4ae881ce766 | note | REFERENCE: Coating System TDS
5408df97-099b-5ef8-a2e8-c04d7f4c379a | note | ○ 685.07
b560aeae-da08-5178-bbae-22307eaf2510 | note | ○ 686.07
6c0ebf89-6f13-5862-bc21-c96bc9b1c135 | note | ○ 686.09
bdd71c6e-b866-5cb0-ab80-44815f13de16 | note | ACCEPTANCE CRITERIA: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
487f0370-0d2f-5496-8909-80203599b63c | note | ○ Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
140298e4-9b18-5e77-b993-a5f92ebdf9af | note | ○ For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
acfc0f75-1fbc-511b-aa60-457460753292 | note | ○ Times of coating(s), material names, locations coated and volumes used shall be recorded.
552cbd4e-cd66-5955-b2b8-52c35650085c | note | ○ Attach: Coating Application Record
006dd404-52dd-5ffd-b942-fe92933aff66 | note | METHOD: Visual, Measure
b5284b00-7f83-5f6f-8a86-4274902698a7 | note | FREQUENCY: Each coat
865690c4-4ed2-5fdb-aec8-0a8a652629fa | note | CATEGORY: IP
28ef6b94-803c-5d09-9af6-74cc4f02b381 | note | RESPONSIBILITY: SE/PE/SPE
a473251f-eb3c-5ddc-914d-59be4749bb34 | note | VERIFYING DOCUMENTS: This ITP
aee03200-07b8-5c9c-b969-68af6d834aed | date | Date Completed:
| checkpoint | 4.2 Wet Film Thickness (WFT) Testing
96899acd-fa68-50d5-a326-6d88f44c7d95 | note | REFERENCE: Coating System TDS
79660231-4c0c-56b2-9f80-15bf58804818 | note | ○ 685.12 (b) (ii)
4efa8424-8c02-5981-ba7e-17679cd65895 | note | ○ 686.14 (b) (ii)
e5abdcb5-b160-5ce2-9b80-e59c7509dfc7 | note | ACCEPTANCE CRITERIA: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
1ec16061-c3af-548b-a9bb-8a6fd69e8f6c | note | ○ Attach: WFT Test Results
9064e21d-9f50-5736-9b4f-dd99b1be4346 | note | METHOD: Test
ecb432c4-e3a8-5f61-ae02-fa826ab42ac7 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
723607ac-30ad-5713-9526-a5dd6f77e635 | note | CATEGORY: IP
a9539447-e6bf-500f-8988-77980badd807 | note | RESPONSIBILITY: SE/PE/SPE
9c60444c-8b90-5b07-bcd9-ad87884d8492 | note | VERIFYING DOCUMENTS: This ITP
e2c80bbc-6166-5506-8405-de303c24202c | date | Date Completed:
| checkpoint | 4.3 Inspection & Defect Identification
95397afb-9117-5565-b5fa-f829514748dd | note | REFERENCE: 685.07
f651572c-958e-505c-95ce-609f00d34c07 | note | ○ 685.13 (d)
eeb0b426-9acb-5ef2-b4db-aa3240b439c4 | note | ○ 686.07
fa1d7ab0-0ff2-5770-b805-da97f11affd5 | note | ○ 686.15
99e8c97e-9798-5717-97b1-96ccd0f68c20 | note | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
ac1a0abb-c609-5331-924c-99003d1b4316 | note | ○ Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
0139a21e-0126-5002-89c7-92b9f581837c | note | METHOD: Visual
706552c5-969c-5bf2-9d1e-0928578cf95b | note | FREQUENCY: After each coat
4e903038-0d30-5805-9c4b-37949e7b8121 | note | CATEGORY: IP
bcd5b906-3665-57cd-a88b-f508c4a702be | note | RESPONSIBILITY: SE/PE/SPE
9adad8d6-223c-514e-b6e7-a8ab487fd859 | note | VERIFYING DOCUMENTS: This ITP
288f5ee7-e4b5-5ac9-80bd-bf065b2558f6 | date | Date Completed:
| checkpoint | 4.4 Drying and Curing
d5f1f5b7-3ac5-57de-9785-8144ea0cd0a6 | note | REFERENCE: Coating System TDS
6ba1e800-db4c-53b2-9f18-7b01d59c21b8 | note | ○ 685.17
58814b2a-ea08-5771-b318-adb678a8ca1e | note | ○ 686.10
5fabefdb-a630-5917-bed2-dbe413f5a380 | note | ACCEPTANCE CRITERIA: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
4d5de15f-94a3-5dc5-a60b-962a6f2ec906 | note | METHOD: Visual
28e8eeb9-0bc6-57c1-b0ae-52709a5538d5 | note | FREQUENCY: After each coat
3d9327b9-119a-51b2-a81c-8ffcad1ca845 | note | CATEGORY: IP
f485df33-f331-55ef-a9e0-8124741e216d | note | RESPONSIBILITY: SE/PE/SPE
556420fe-408c-59b0-8887-da4640c6cdf1 | note | VERIFYING DOCUMENTS: This ITP
3ef86432-cc11-5c19-93cc-ca3fd0ee5bd0 | date | Date Completed:
| section | Post-application Activities
| checkpoint | 5.1 Clean-up & Waste Disposal
b8edabcb-de20-5be8-b3e1-6c892c32cd48 | note | REFERENCE: 685.09 (c), 686.10
e9d6204a-9d75-5127-9cfb-29ae4128de7e | note | ACCEPTANCE CRITERIA: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
db6096ac-1ef9-5033-acd3-e382b4720268 | note | ○ All rubbish and remaining coating products shall be removed from site.
a379af37-37ed-5e13-8205-d7e370e19ccd | note | METHOD: Visual
758e424c-fbaa-549f-9735-cca2bd0df474 | note | FREQUENCY: At completion of Works
64b63234-3a50-54e7-9c5c-27ae089b7455 | note | CATEGORY: IP
0fe245e8-d67e-5ad3-9f83-3b06e777aa6a | note | RESPONSIBILITY: SE/PE/SPE
02325670-4425-5f7d-9cf7-a90a2404274e | note | VERIFYING DOCUMENTS: This ITP
ef694603-5b4f-530b-9b57-df3c59ba6897 | date | Date Completed:
| checkpoint | 5.2 Dry Film Thickness (DFT) Testing
17b9f09b-ab9f-5e09-b6c5-52cbb515ce9a | note | REFERENCE: 685.12 (b) (iii), 686.14 (b) (iii)
dd34d173-9e42-5ee8-8323-164f950fa65a | note | ACCEPTANCE CRITERIA: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
9e48b88c-73bb-5df3-9e4a-cb3acffc8cf9 | note | i. Anti-graffiti system = 100µm
59f3a648-3e1c-537c-9363-bf20d5cfa2bf | note | Ii. Decorative & anti-carbonation = 150µm
bd5adb48-7840-50a4-968d-0aef7e021a80 | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
61c1479d-811c-5415-98c0-981b5db08108 | note | iv. Atmospheric & splash zone (dual protective) = 200µm
65bbdcfd-6456-5895-973f-831769f790db | note | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
4b69bb4b-4c00-5878-995c-394fcb14a15a | note | ○ Attach: DFT Test Results
b5ae0f86-305a-5477-8ad8-8c5c52e3edc3 | note | METHOD: Test
9271fcaa-2af5-55a0-bd7c-d305a9d0924d | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
e84b157d-0070-5e43-abdd-dd234ee824c3 | note | CATEGORY: IP
2439794a-84f4-551e-a133-f75d5fb88f53 | note | RESPONSIBILITY: SE/PE/SPE
deb81abc-7928-5832-aee9-ad58f186f2d6 | note | VERIFYING DOCUMENTS: This ITP
f5145463-c7fa-589d-be2e-02504072779f | date | Date Completed:
| checkpoint | 5.3 Adhesion Bond Strength Testing
82e385a4-f90a-5e3c-b303-882fe0121604 | note | REFERENCE: 685.12 (b) (i), 686.14 (b) (i)
05c24c98-fde2-54a5-8926-6cd2ab18fadb | note | ACCEPTANCE CRITERIA: A minimum of 14 days after application, the bond-strengths between:
506c94b5-24a2-551d-a7a8-b796843ca3c2 | note | i. the coating system to the substrate, and
26f1108c-aaa8-5951-a020-7db882837b52 | note | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
bc32ff51-2f86-56cd-8220-d3a9a11f649b | note | ○ The subsequent results shall be greater than 0.75kPa.
edc2aebc-9626-56ac-aeec-297f23859286 | note | ○ Attach: Adhesive Bond Strength Testing Results
a2c20672-6e9f-57c1-a6b6-293e56452ea0 | note | METHOD: Test
48a87f22-b4ab-55cc-bc53-92b626708aca | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
be4ee65a-be2b-5ba1-97e9-bebb445497f0 | note | CATEGORY: IP
0a4f300f-c0e9-5af5-9730-100578e0645c | note | RESPONSIBILITY: SE/PE/SPE
8322b70c-4857-592e-a7f1-60c42b7bfb67 | note | VERIFYING DOCUMENTS: This ITP
e4e58f14-8afb-5b58-a8e0-16f3594ebc9c | date | Date Completed:
| checkpoint | 5.4 Penetration Depth Testing
e10f4e23-c131-5ea8-bd18-cd7c935a6cd6 | note | REFERENCE: 685.12 (b) (v), 686.14 (b) (v)
66443e80-54e9-551b-879a-003564023f09 | note | ACCEPTANCE CRITERIA: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
3db5adfa-163c-50a7-b312-f3648b8cd57f | note | ○ The subsequent results shall be:
a9376bdc-16fe-503d-af12-442814d17fb9 | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
1c8a48c1-5edd-5faa-b962-8c0f6fbf1ac2 | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
223a628d-c296-5bc4-b8eb-4e19fd299757 | note | iii. Silane-Siloxane or Siloxane = 3mm min.
28c381f1-0701-5eab-adb3-59cfa7cb7499 | note | ○ Attach: Penetration Depth Testing Results
eb40ff6b-67f4-5d9a-9bb2-4da9a4177267 | note | METHOD: Test
0ba0d52b-48d8-5528-928b-dd51983c5999 | note | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
5316e744-4375-5b3e-936c-fb8cd84aebfd | note | CATEGORY: IP
17ed8ad4-bb1b-57a3-8f32-e1f130254f13 | note | RESPONSIBILITY: SE/PE/SPE
50dcaaa5-47b8-52c0-9685-34e3ff1a43c6 | note | VERIFYING DOCUMENTS: This ITP
ee3910ef-5d56-5c45-8502-a5e62c2315be | date | Date Completed:
| checkpoint | 5.5 Non-conforming Coatings
df784437-dda5-5d7c-a661-f84fa46d6b4c | note | REFERENCE: 685.14, 686.17
2291f203-c886-5522-9315-dd7968707a4a | note | ACCEPTANCE CRITERIA: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
63af4f37-12a2-5642-b012-056f4036a492 | note | ○ Such Work may include removal of the coating, surface preparation and re-application.
00db00b3-077e-570a-abec-b224c9f5c027 | note | ○ Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
fb6b26d3-c0cc-5f91-b498-cabdec31faaf | note | METHOD: Visual
4e1bc953-6844-515a-ac6f-8df8885ac6fc | note | FREQUENCY: Where required
4c6b7846-be7f-51de-b66a-f94e3e6ca964 | note | CATEGORY: IP
b672ccfe-7174-55e0-bd06-c4e2b52b08bb | note | RESPONSIBILITY: SE/PE/SPE
8be5bc6f-2025-5f7e-a8c1-724f18b97b4b | note | VERIFYING DOCUMENTS: This ITP
826decb1-1211-59d5-837f-dfaaba12cbbf | date | Date Completed:
| checkpoint | 5.6 Coating Application Guarantee
84017998-6480-5e8e-9074-6b087bce1a5a | note | REFERENCE: 685.06 (b), 686.05 (a)
d0a9cc5e-43b5-5153-8161-6dca909c6e4a | note | ACCEPTANCE CRITERIA: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
5ac0af03-9d86-5805-8b00-6d0991ccbab4 | note | ○ Attach: Coating Application Guarantee
82df8a01-8825-5052-b85f-f3bc7659d6e9 | note | METHOD: Document Review
d1765c08-3bfb-53f2-a1e7-1b185a6a36f1 | note | FREQUENCY: At completion of Works
811d188c-18e0-5484-ac52-4c7860a77cb6 | note | CATEGORY: SP
dc2991aa-0a8d-5f15-93a5-1f62b0f4163b | note | RESPONSIBILITY: SE/PE/SPE
dcbbb18a-9f93-52e8-8aa7-a6444b2bce68 | note | VERIFYING DOCUMENTS: This ITP
ec41507d-5341-5720-a9b8-1c8130a69381 | date | Date Completed:
| checkpoint | 5.7 Repair to Damaged Coating
f6234adb-9bff-5abc-a358-5c27ee8aa450 | note | REFERENCE: 686.17
31352c6a-92e8-5308-a374-ab6576780c32 | note | ACCEPTANCE CRITERIA: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
ec5c7b88-5108-5133-8dc7-0601cd7c190b | note | METHOD: Visual
e54172a0-089d-569f-9d49-c14a092be02c | note | FREQUENCY: Where required
99f0ddfc-fbdc-5fa9-b16d-ca3cb3635d5c | note | CATEGORY: IP
0c07f234-733c-562c-89dd-e9ea49f8b389 | note | RESPONSIBILITY: SE/PE/SPE
0aea9c8a-cc77-58ce-ae09-a31d1e79fe10 | note | VERIFYING DOCUMENTS: This ITP
3cb4e4af-6a0b-5652-8d9c-cbd1c260c309 | date | Date Completed:
| checkpoint | 5.8 Non-conformance Report (NCR) Closure
d624e6bd-1e7c-539c-94b4-f672309bbabf | note | REFERENCE: MRPA Quality Management Plan
8bf4bee5-b55c-5d66-b588-8f492a482299 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
bf311e8d-077d-5dba-b51e-913ecd86ad40 | note | METHOD: Document Review
22d03719-952b-5c9a-9a10-3987edce972b | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
8413557d-10c4-5420-9530-16b417ff63e6 | note | CATEGORY: HP*
2262422c-e418-59a0-97e0-7daa7f94c042 | note | RESPONSIBILITY: SE/PE/SPE
4cc99e1b-65f6-5d44-8be8-9a316304b3e9 | note | VERIFYING DOCUMENTS: This ITP
c3dc6ad2-301a-5968-9481-774256a9f1da | date | Date Completed:
| checkpoint | Final Inspection
190879d0-27ac-5555-9bcd-d695f32d63f3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
346339f6-3160-52de-97f8-c6462726cbe2 | textbox | Name:
3bd745c6-2839-5101-946b-0e9f92e1db73 | textbox | Position:
7c5798df-eef0-5c77-a073-3c778f645281 | date | Date Completed:
| signoff | Sign ITP