## Sheet1
ConQA Team Notes:
Document Title: |  | CHK-CIV-SSO-Stormwater Drainage Pits Installation
CHK Description: |  | SSO-Stormwater Drainage Pits Installation
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2024-10-22
CHK created by: |  | Sandy Escalona
CHK approved for use by: |  | Sandy Escalona
Special Notes to ConQA Team : |  | This ITP Should be used in Conjunction with ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
Checklist - Stormwater Drainage Pits Installation
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-10-22
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads, Section 701 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Main ITP | ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation | This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0 Enter: Lot Number | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Bedding | VicrRoads: Cl 701.09 (d) | Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP. | Document Review | Each Lot | HP* | SE | Material Delivery Docket
2.2 | Backfill Material | VicrRoads: Cl 701.09 (d) | Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP. ATTACH: Backfill Material Delivery Docket | Document Review | Each Lot | HP* | SE | Material Delivery Docket
3 | Preliminaries - Procedures & Documentation
3.1 | Subcontractor QA Submissions and ITP | ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation | Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP. ATTACH: Subcontractor Signed ITP | Document Review | Each Lot (in case undertaken by subcontractor) | HP* | SE | ConQA Hold Point Release
4 | Pre-Construction Activities
4.1 | Survey Set Out | VicRoads, Cl 710.10 | Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10 MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP | Visual inspection | Each Lot | HP* | SE | This ITP
5 | Construction Activities
5.1 | Pit Excavation | VicRoads, Cl 705.05 | Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit. | Visual inspection | Each Lot | IP | SE | This ITP
5.2 | Excavation Foundation | VicRoads, Cl 705.05 | Bedding conforming to to 710.09 shall be supplied, placed and compacted to a thickness: > 80mm for clay foundations > 150mm for rock foundations | Visual inspection | Each Lot | IP | SE | This ITP
5.3 | Placement of Pit-Conformity with drawings | VicRoads, Cl 701.10 | The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250 ATTACH: Survey Report | Measure | Each Lot | HP* | SE | Survey Report
5.4 | Jointing | VicRoads, Cl 705.11 & 705.15 | All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter. Exposed reinforcement shall be coated with an approved epoxy treatment | Visual inspection | Each Lot | IP | SE | This ITP
5.5 | Shaping of Floor | VicRoads, Cl 705.13 | Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe with cementitious mortar, which shall comply with requirements of Clause 610.33 | Visual inspection | Each Lot | IP | SE | This ITP
5.6 | Step Irons | VicRoads, Cl 705.12 | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder shall not obstruct openings and that water does not discharge on them. Ladder rungs shall be located directly below the opening in the cover and set into a wall which has no openings, or beside an opening, or across a corner of the pit. | Visual inspection | Each Lot | IP | SE | This ITP
5.7 | Fitting of Covers | VicRoads, Cl 705.17 | Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement. The level at every point of the perimeter shall be within 10 mm of the design level for that point, and the line of the cover shall be within 10 mm of the design kerb line. | Visual inspection | Each Lot | IP | SE | This ITP
5.8 | Backfilling Around Drainage Pits | VicRoads, Cl 705.18 | Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal using hand held mechanical equipment | Visual inspection | Each Lot | IP | SE | This ITP
6 | Post-construction Activities
6.1 | Compaction and Moisture content tests | VicRoads, Cl 701.20 | Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested. ATTACH: Compaction and Moisture content test results: | Document Review | Each Lot | IP | SE/PE | Test Results
6.2 | CCTV Inspection | VicRoads, Cl 701.30 | All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. ATTACH: CCTV Report (PDF) | Document Review | Each Lot | HP | Nominated Authority | CCTV Reports
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /