## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CHK-015-CIV-SSO-Stormwater Drainage Pipes installation | itp |  |  |  |  | CHK-015-CIV-SSO-Stormwater Drainage Pipes installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: CHK-CIV-SSO-Stormwater Drainage Pipes Installation
label | Checklist Description: SSO-Stormwater Drainage Pipes Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 22/10/2024
label | ITP created by: Sandy Escalona
label | ITP approved for use by: Sandy Escalona
label | 1.1 Non Dependent
label | Reference: VicRoads, Sec 701
label | 1.2 Main ITP
label | Reference: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
label | Acceptance Criteria: This checklist should be used in Conjunction with ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
textbox | Enter: Lot Number
section | Preliminaries - Materials
checkpoint | 2.1 Bedding
label | REFERENCE: VicRoads, Sec 701
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | ○ ATTACH: Bedding Material Delivery Docket
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Material Delivery Docket
date | Date Completed:
checkpoint | 2.2 Backfill Material
label | REFERENCE: VicRoads, Sec 701
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | ○ ATTACH: Backfill Material Delivery Docket
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Material Delivery Docket
date | Date Completed:
checkpoint | 2.3 Stabilized Sand
label | REFERENCE: VicRoads, Sec 701
label | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
label | ○ ATTACH: Selected Backfill Material Delivery Docket
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Material Delivery Docket
date | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Subcontractor QA Submissions and ITP
label | REFERENCE: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
label | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | ○ ATTACH: Subcontractor Signed ITP
label | METHOD: Document Review
label | FREQUENCY: Each Lot (in case undertaken by subcontractor)
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 Survey Set-Out
label | REFERENCE: VicRoads, Cl 710.10
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ○ The culverts constructed shall be constructed true to line and level.
label | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | METHOD: Survey, Measure
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP, Main Lot Map
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Trench Excavation
label | REFERENCE: VicRoads, Cl 701.15
label | ACCEPTANCE CRITERIA: For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
label | ○ Horizontal Clearance from the outside of pipe to the wall of trench to be within the limits:
label | – Corrugated metal culvert: >300mm to <1000mm
label | – Other pipe culverts: >300mm to <600mm
label | ○ Box Culverts: clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Trench Base
label | REFERENCE: VicRoads, Cl 701.16
label | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Bedding-Placement and compaction
label | REFERENCE: VicRoads, Cl 701.16 & 701.20 (a)
label | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | – 100 mm where D < 1500 mm
label | – 200 mm where D ≥ 1500 mm
label | ○ Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
label | METHOD: Visual, Measure
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Laying pipes-Bedding conformity
label | REFERENCE: VicRoads, Cl 701.17
label | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
label | ○ Laying of pipes or box culverts shall commence from the downstream end.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Pipe Laying
label | REFERENCE: VicRoads, Cl 701.16 & 701.17
label | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall commence from the downstream end.
label | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
label | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
label | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
label | METHOD: Visual
label | FREQUENCY: Each Pipe
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Pipe Joints and rotation
label | REFERENCE: VicRoads, Cl 701.18
label | ACCEPTANCE CRITERIA: All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
label | METHOD: Visual
label | FREQUENCY: Each Pipe
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Conformity with drawings
label | REFERENCE: VicRoads, Cl 701.10
label | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ○ ATTACH: Survey Report
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Survey Report
date | Date Completed:
checkpoint | 5.8 Backfill-Under area to be paved
label | REFERENCE: VicRoads, Cl 701.19 (a) i
label | ACCEPTANCE CRITERIA: Culvert under area to be paved
label | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
label | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Backfill-Under area not to be paved
label | REFERENCE: VicRoads, Cl 701.19 (a) ii
label | ACCEPTANCE CRITERIA: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Backfilling with cement stabilised sand
label | REFERENCE: VicRoads, Cl 701.19 (c)
label | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
label | ○ ATTACH: Selected Backfill Material Delivery Docket
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Material Delivery Docket
date | Date Completed:
checkpoint | 5.11 Backfill Placement
label | REFERENCE: VicRoads, Cl 701.20
label | ACCEPTANCE CRITERIA: backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: SP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.12 Backfill Compaction
label | REFERENCE: VicRoads, Cl 701.20 (b) (i)
label | ACCEPTANCE CRITERIA: 20% of all bedding/Backfill layers for each culvert shall be tested.
label | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
label | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | METHOD: Test
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Compaction and Moisture content tests
label | REFERENCE: VicRoads, Cl 701.20
label | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
label | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | ○ ATTACH: Compaction and Moisture content test results
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: Test Results
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP
checklist | CHK-016-CIV-SSO-Stormwater Drainage Pits Installation | itp |  |  |  |  | CHK-016-CIV-SSO-Stormwater Drainage Pits Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: CHK-CIV-SSO-Stormwater Drainage Pipes Installation
label | Checklist Description: SSO-Stormwater Drainage Pipes Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 22/10/2024
label | ITP created by: Sandy Escalona
label | ITP approved for use by: Sandy Escalona
label | 1.1 Non Dependent
label | Reference: VicRoads, Section 701
label | 1.2 Main ITP
label | Reference: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
label | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
textbox | Enter: Lot Number
section | Preliminaries - Materials
checkpoint | 2.1 Bedding
label | REFERENCE: VicRoads: Cl 701.09 (d)
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Material Delivery Docket
date | Date Completed:
checkpoint | 2.2 Backfill Material
label | REFERENCE: VicRoads: Cl 701.09 (d)
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
label | ○ ATTACH: Backfill Material Delivery Docket
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Material Delivery Docket
date | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Subcontractor QA Submissions and ITP
label | REFERENCE: ITP-208-CIV-SSO-Stormwater Drainage Supply & Installation
label | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
label | ○ ATTACH: Subcontractor Signed ITP
label | METHOD: Document Review
label | FREQUENCY: Each Lot (in case undertaken by subcontractor)
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Survey Set Out
label | REFERENCE: VicRoads, Cl 710.10
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
label | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Pit Excavation
label | REFERENCE: VicRoads, Cl 705.05
label | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Excavation Foundation
label | REFERENCE: VicRoads, Cl 705.05
label | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shall be supplied, placed and compacted to a thickness:
label | ○ > 80mm for clay foundations
label | ○ > 150mm for rock foundations
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Placement of Pit-Conformity with drawings
label | REFERENCE: VicRoads, Cl 701.10
label | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ○ ATTACH: Survey Report
label | METHOD: Measure
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: Survey Report
date | Date Completed:
checkpoint | 5.4 Jointing
label | REFERENCE: VicRoads, Cl 705.11 & 705.15
label | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Shaping of Floor
label | REFERENCE: VicRoads, Cl 705.13
label | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe with cementitious mortar, which shall comply with requirements of Clause 610.33
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Step Irons
label | REFERENCE: VicRoads, Cl 705.12
label | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder shall not obstruct openings and that water does not discharge on them. Ladder rungs shall be located directly below the opening in the cover and set into a wall which has no openings, or beside an opening, or across a corner of the pit.
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Fitting of Covers
label | REFERENCE: VicRoads, Cl 705.17
label | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | ○ The level at every point of the perimeter shall be within 10 mm of the design level for that point, and the line of the cover shall be within 10 mm of the design kerb line.
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Backfilling Around Drainage Pits
label | REFERENCE: VicRoads, Cl 705.18
label | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal using hand held mechanical equipment
label | METHOD: Visual inspection
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Compaction and Moisture content tests
label | REFERENCE: VicRoads, Cl 701.20
label | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
label | ○ Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
label | ○ ATTACH: Compaction and Moisture content test results:
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: Test Results
date | Date Completed:
checkpoint | 6.2 CCTV Inspection
label | REFERENCE: VicRoads, Cl 701.30
label | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | ○ ATTACH: CCTV Report (PDF)
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: CCTV Reports
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP