## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | INF-HSEQ CC0375-ITP-006 Kerb and Channel & Checklist- Rev.5 | itp | INF-HSEQ CC0375-ITP-006 Kerb and Channel & Checklist- Rev.5 |  | 422d5cbd-0911-401f-8a4b-6b4b5f38d37c
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Determine lot size
23ea0b50-77b5-5c36-a330-9f9dec534cb7 | note | Ref docs - Spec. 0161 Quality [Cl 7.3]
bf4552b6-5f5e-547b-a658-3b91c4a12d7c | note | Acceptance Criteria - Lots to be broken up accordingly and outlined on a lot map
dbd59763-1149-51b8-874e-d93885ac1474 | button | Acceptance | Yes,No,N/A
6d112e99-e523-57bf-a1de-fc365598b2bf | note | Key - S
8ab1b5a5-23ba-551c-9936-7df42f7d5c26 | note | UGL Key - S
21be28a7-26f7-5a0d-bafb-6a360373a43c | note | SHL Key - S
3326b6ce-6937-53c6-afa1-accc83a7260b | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
83fa7cff-54c5-57a8-86d1-ede15aab5be2 | tickbox | Lot map
| checkpoint | 1.2 - Concrete Mix Design
83b8110f-5c7b-5050-94be-ec03f1917cf7 | note | Ref docs - Spec. 1121 Open Drains [Cl 3.1]
2407ff25-909a-5c2f-b194-52226b4d21b6 | note | Acceptance Criteria - Submission of Mix Design and compliance certificates for concrete constituents
818245e8-c747-5c13-a510-6da7ddac521d | note | HOLD POINT
d81e9743-cf6a-57c8-8b12-d61629348187 | button | Acceptance | Yes,No,N/A
92113e45-14b9-5e16-a026-c0d9b2c79594 | note | Key - H
0ca1712e-4eb4-5496-a250-a08433e010e5 | note | UGL Key - H
aa0597ba-42c4-58fa-b461-e688a0c71495 | note | SHL Key - H
7cbb6f73-13fd-5f54-a663-c305ddb6f748 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
ae6978c0-77fd-54f9-bd59-fea3718ba871 | tickbox | Material conformance certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Joint Fillers & Sealants
cd06b79e-8038-5bd3-8131-ee241899aa34 | note | Ref docs - Spec. 1121 Open Drains [Cl 3.2]
8e307295-83e9-5cfe-8786-c616626b4831 | note | Acceptance Criteria - Submission of Compliance Certificate for joint fillers and sealants
ac5b3ce6-91a4-5686-9011-1dc3f9e4d24c | note | HOLD POINT
8ed8321a-6c06-5db1-bfae-bb2b4eb35423 | button | Acceptance | Yes,No,N/A
2e89feb4-5321-5f04-b6bc-a48bb51e203c | note | Key - H
e329f753-b3e0-582c-999b-b5b90a9021d7 | note | UGL Key - H
61b370bd-a1a6-51fe-ae98-120ab2a2519d | note | SHL Key - H
70d4d324-4b50-5e5d-88f0-9e1ab4c87c49 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
c56c580d-2afe-52b4-9425-1a92cb21c1ba | tickbox | Material conformance certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Kerb & Gutter Methodology
2caa9e64-6524-55c7-a3fb-ab4bfc7baa50 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
50b36497-e570-5cfb-92de-1eaad8091b85 | note | Acceptance Criteria - Construct kerb and channel in fixed forms, by extrusion or by slip forming to AS2876.
a1f8ba27-9b5a-5e11-a201-6aa67f5de930 | note | ○ Submit details of method proposed including type of extrusion or slipform, concrete properties, equipment and finish.
7d7f5dbb-7663-52c0-9ba3-13ba692f576b | note | HOLD POINT
6e727449-e18f-5e1d-8d3f-6e7da7f1ebc8 | note | Notice: 14 working days prior to commencement on site
be09df0c-e116-53c8-b8b1-281bc50260ab | button | Acceptance | Yes,No,N/A
a6c811dd-1474-5e19-944c-ed6788968865 | note | Key - H
48676d81-2510-5a0d-bf2f-0fe2013a9c75 | note | UGL Key - H
6f1e5d4d-2cf0-55c3-ad92-e768a75b997a | note | SHL Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Underlying Lot Conformance
f4fea250-d06c-5167-b81c-f9c3f216097f | note | Ref docs - Underlying Lot ITP
646f62ea-e06a-5445-9fd2-ee3f45685908 | note | Acceptance Criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
42d23c79-4e3a-5767-83c8-16ba1185a139 | note | ○ Refer underlying lot ITP(s)
6c5b9bdd-eaeb-5239-9759-8e62da0a3a13 | button | Acceptance | Yes,No,N/A
04480635-2f43-578e-a13f-baefdb86d8be | note | Key - S
0a3971e7-272f-5ba6-b924-2ed25d73e1d9 | note | UGL Key - S
dee5b9b7-2191-5e48-96c8-e3c88b13331b | note | SHL Key - S
| checkpoint | 1.6 - Survey set out
77abcd3a-40c7-57c9-99ae-38ffe3f200fe | note | Ref docs - Drawings
90edc993-5b78-5c9c-a17a-53d22f3a31bf | note | Acceptance Criteria - Set out the alignment and level of the kerb
d0ea18b2-a1a5-511d-974a-6b0e92e94d48 | button | Acceptance | Yes,No,N/A
a52b960c-fb88-5c40-9cd0-17707e89b74c | note | Key - S
102abc9c-d4d1-57ab-99fc-d5c4746cbb8f | note | UGL Key - S
53dcbdbe-1de7-5ecd-8dc6-2f4d1fcf43c8 | note | SHL Key - S
| section | 2.0 Kerb and channel placement
| checkpoint | 2.1 - Foundation
33a63628-28fb-5d3a-b586-1b620df210bc | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
63d2795c-dac3-5061-a292-f561326173bf | note | Acceptance Criteria - Shape and compact foundation material to the requirements of the respective pavement course
719cb626-5cd5-53b3-8107-f6124dcaa2c3 | note | HOLD POINT
c653fc30-322b-593a-97c8-c5800c785a76 | note | Notice: 1 working day before forming
f1a849c0-6749-5a9f-823e-27e3cf2c2d00 | button | Acceptance | Yes,No,N/A
14fd45c0-8818-5a48-8966-1c98f18df920 | note | Key - H
05d45c9a-9802-5ee2-a3eb-44978f7d3539 | note | UGL Key - H
7c25a614-81d5-5116-bf78-b618f771c6f7 | note | SHL Key - H
33306e45-55b3-58aa-984b-b08a7b8bcbc0 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
65d5c97a-b9a2-590a-9f22-d8fb5e7b060e | tickbox | Test reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Trial section
1ada370d-8446-589a-80e8-cc102a3d0302 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
26b8b368-3bcb-5f64-9516-f48d5912c317 | note | Acceptance Criteria - Construct trial section to demonstrate the Contractors capability of forming equipment.
48d6fd31-c229-530b-b2b1-922fda532728 | note | HOLD POINT
23b2e091-ac36-58ed-9611-ace02f7c8327 | note | Notice: To be completed on 1st section of kerb,
451548e3-dde0-50bc-b639-c2f03e1361a8 | note | 3 days prior to commencing next section
1ad99bfb-a3e6-5705-a95f-026a1a8f181f | button | Acceptance | Yes,No,N/A
f4f87e73-c47e-5dac-8cb2-dc49b5316c19 | note | Key - H
4e275058-8f0d-52c2-857e-52cfd89ecc2f | note | UGL Key - H
298ef5c2-2ae3-598c-afd0-172f7e06424f | note | SHL Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Concrete supply and placement
6099a512-0efc-5168-8916-ee9a0d5929f1 | note | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11] Drawings
a98a0acf-5d60-554e-b419-bc3872a869de | note | Acceptance Criteria - Check docket to ensure strength and slump is as per design requirements
384f623e-a70f-5ecc-81f9-c278296ab75e | note | ○ Ensure the temperature of freshly mixed concrete is maintained in between 5°C and 35°C. Ensure elapsed time between batching and discharge of the mix complies with the below table.
ef6f7f8f-c3e3-52ee-906e-634d257f68ee | note | – – – – – – – – – – – – – – – –
aa951040-7ab7-53f8-a06a-e7ee4c9c0d63 | note | Concrete temperature at time of discharge (C) ¦¦ Maximum elapsed time (hours)
e2561c21-9663-51d1-8d85-dcfddb52003f | note | – – – – – – – – – – – – – – – –
de080aa2-af0b-58a3-a9fe-96f42be61153 | note | 10 - 24 ¦¦ 2.00
dfef807b-df7a-59c1-864f-1f704815d66d | note | 24 - 27 ¦¦ 1.50
4987f7aa-d964-57f1-bc4d-afebd4958fe6 | note | 27 - 30 ¦¦ 1.00
dbeb0c66-b74d-5843-b3c8-00752defc128 | note | 30 - 32 ¦¦ 0.75
ad708570-4d65-5318-ae09-3366756a11d3 | note | – – – – – – – – – – – – – – – –
d07fc7e4-6d9a-50df-8a73-642d62790c71 | button | Acceptance | Yes,No,N/A
8212656c-6b1c-59d1-91e6-95bbb88dbdc2 | note | Key - S
501f781a-e86b-5f99-978d-954a171793f8 | note | UGL Key - S
ba9306c7-f1c3-58ed-b74b-356d9af40ebf | note | SHL Key - S
71d3fffe-840a-5970-b76e-7666239b443b | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
30fa5370-6220-5269-9957-9a72678f54d7 | tickbox | Delivery dockets
| checkpoint | 2.4 - Concrete sampling
972a3878-27b4-5bed-a96b-df9d32dc3db9 | note | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.2]
7f65886a-c3fb-5eba-8232-ad3306f53766 | note | Acceptance Criteria - The nominal rate of sampling shall be taken as:
322636c0-f9c7-5d85-bf7b-2cb26efdd3d0 | note | (a) Compressive strength: See table below
cb5f28b8-0172-54c6-bf9d-ac0f341f8acc | note | – – – – – – – – – – – – – – – –
fe1e0e03-44a4-58b8-a0ec-a1f1c3b3f367 | note | Number of batches for each type and grade of concrete per day ¦¦ Minimum number of samples
92b1f8a1-fb27-5323-a047-80e7019f702c | note | – – – – – – – – – – – – – – – –
05869597-a5fa-5696-ba3f-4d6cbf0971f4 | note | 1 ¦¦ 1
75030b7a-9d53-5292-a2c9-4a6243e750fc | note | 2-5 ¦¦ 2
55d680fc-aa4b-572e-a1ec-31cabd965549 | note | 6-10 ¦¦ 3
7d4f0c7d-8997-5f92-afad-c005916ebd34 | note | 11-20 ¦¦ 4
5982802d-e046-5ed2-ad97-02f0189088ac | note | each additional 10 ¦¦ 1 additional
956dfb24-9854-531d-8dba-f3ee36d2ee93 | note | – – – – – – – – – – – – – – – –
973d37ca-2095-5887-9ef5-67ef14bf2ed3 | note | (b) Slump: One per batch of concrete
f9f7e46c-cd14-5ce9-bae9-7e0a8af4866e | button | Acceptance | Yes,No,N/A
cceb2992-5576-5235-bcc1-03f9f903bc1a | note | Key - S
78c9a28e-9975-548b-a28c-525b5cfc0022 | note | UGL Key - S
e8aefd4f-2b15-582a-bdde-00511421a5e1 | note | SHL Key - S
a8edbf9e-95bc-52b0-9291-698633c6768b | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
834f1182-e975-5e9a-b66b-5971c9c845d6 | tickbox | Concrete pour record
| checkpoint | 2.5 - Concrete testing
428d0f33-aa8a-5907-b56c-79e0e04fd683 | note | Ref docs - Drawings
d1402de4-d388-5599-951c-7873d7992be3 | note | Acceptance Criteria - Average compressive strength at 28 days meets minimum design requirements
b850ce4b-9651-5978-8cab-23f51615a807 | note | Slump within tolerances specified in AS 1379
3d940112-e77d-5dc0-a06a-b0c6c60fddde | note | – – – – – – – – – – – – – – – –
4ff66f1c-2ed8-5051-a179-3053a58cb4f7 | note | Table 5.1 Permissible Tolerance on Slump
f863eea6-6d3b-59b3-b626-a3c5beb984ab | note | – – – – – – – – – – – – – – – –
c618414e-37d4-52f1-aa88-30676b33c984 | note | Specified slump, mm ¦¦ Tolerance, mm
9eb0fc28-06a6-5504-8d15-d01775ad831b | note | – – – – – – – – – – – – – – – –
c7bec765-8f13-5b3f-a9a7-28c3a2b4c800 | note | <60 ¦¦ ±10
28739fc6-3010-564b-88a0-f585e8fda8f1 | note | ≥60 ≤80 ¦¦ ±15
34fea913-774b-5538-9f18-35b511af98cc | note | >80 ≤110 ¦¦ ±20
d41cf3ff-b8ed-52cc-b56b-adc1b30ee0ec | note | >110 ≤150 ¦¦ ±30
fbd562ee-e237-550c-b6a5-ae0417ab9f39 | note | >150 ¦¦ ±40
cf123a84-6859-5ddd-91e4-e0e9eafe6cf3 | note | – – – – – – – – – – – – – – – –
e702f67d-19a4-5923-9f4f-f4f145b1e0dd | button | Acceptance | Yes,No,N/A
b8e24fc4-fa96-559f-a38f-f9ebfa7da4bc | note | Key - S
23125f5d-20b2-51a1-a638-04064a4d5ee6 | note | UGL Key - S
09ee832b-4b01-59e4-8a6d-55bece884774 | note | SHL Key - S
6ae1fe41-188a-52af-abe0-14c133f04590 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
60c7433d-ca22-5502-8b4b-f38df2e02df7 | tickbox | Test reports
| checkpoint | 2.6 - Finish
1a5490d7-2b7b-5385-a990-3eae7076d974 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
9d6a7ef6-e9a8-53c5-bbc8-d1fcd9594a0d | note | Acceptance Criteria - Finish true to line: The top and face of the finished kerb and channel.
98a60b8d-4142-51e8-b7c2-65a2ae91751f | note | Top surface: Uniform width, free from humps, sags and other irregularities.
2acf4b50-70aa-5e5b-b803-d070e8c3b8cc | note | Type: Steel float finish or as otherwise shown on drawings.
e80b9b2e-f2ee-5922-95bb-aec9497f0f64 | button | Acceptance | Yes,No,N/A
f6bfd661-ce00-5e7a-8ebd-1e40ef0db7ed | note | Key - S
ff3a4aae-8342-5efe-82f4-0d004e635c21 | note | UGL Key - S
016019c4-e03a-5532-918a-b792782454c4 | note | SHL Key - S
| checkpoint | 2.7 - Joints - Contraction
42a7eb96-0708-5a6a-9a5c-e3cf5447fbb3 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
11fc12f5-8533-5525-9431-33d4d7422409 | note | Acceptance Criteria - Contraction joints to conform to the following:
ab3d3907-a593-5d7b-adfe-68e768f75193 | note | – Width: 5mm min.
715edca4-25f0-593f-9ca8-421eb49089d3 | note | – Depth: 20mm
120ccc2c-145d-55f2-8e9c-a2430583acbb | note | – Intervals: every 3m for a min of 50% cross sectional area
268bb8d4-26bc-51ab-a19c-a6b592156839 | note | – Tooling: 20mm depth / 5mm width
873644a5-a92a-58b2-abb3-05dea1eadad6 | button | Acceptance | Yes,No,N/A
f1dca3d3-92fc-56e4-be6a-ea3326108d2c | note | Key - S
94d86eef-9fdd-5c84-bd18-bc1074729ffd | note | UGL Key - S
c4fde604-3358-5359-97fb-d2c429a664f7 | note | SHL Key - S
| checkpoint | 2.8 - Joints – Expansion
0c3397c9-8d12-5753-9c18-e55a3fe26141 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
f4ff86c5-9a5a-58d0-a6aa-9c899089f40e | note | Acceptance Criteria - Expansion joints to conform to the following:
9932a94e-1dac-5a21-a84e-6e51b341d9dc | note | – Width: 15mm
c2f9b354-145e-5c04-97a1-07e306d5d330 | note | – Depth: Full depth of kerb/channel
c223ced1-75d5-5f32-a097-50f9090271a9 | note | – Intervals: Max interval 15m
f97a127d-fb17-5347-9704-cd5110dd9f5e | note | ○ To be provided where channel/gutter abuts against pits, retaining walls, overbridges and both sides of kerb laybacks unless otherwise shown on drawings.
52bcbef1-51fc-51b1-a634-4a5eed97ade6 | button | Acceptance | Yes,No,N/A
cdc9e428-849a-5573-b646-7fc23e91929c | note | Key - S
3ce33a93-4232-5811-9164-9bb2428d833a | note | UGL Key - S
d8f4eaf9-4bd4-5c67-99ab-dd684d9b8da7 | note | SHL Key - S
| checkpoint | 2.9 - Backfill
4b7ba6dd-4e1a-5507-9e83-098203af3eff | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
1fd07d26-dfc0-5c9e-baf2-2a8c393e5290 | note | Acceptance Criteria - Timing: Backfill behind kerb no earlier than 3 days after concreting.
3f1f73a1-2efc-52e0-876d-dbe5ba141443 | note | Material: Granular material, free of organic material, clay and rock in excess of 50mm or approval material
d2e72fb4-7004-5849-8815-0b87f9beca82 | note | Layers: Compact in layers not greater than150mm
ddc25e45-bd59-50f4-97c0-ccd4b3eedb74 | note | WITNESS POINT
ea8fe023-fe9b-5080-b8a6-c8c301503618 | note | ○ 1 Working days before backfilling behind kerb
7ebb9358-7d59-59f2-947f-bc285dc89217 | note | ○ 3 Working days before to backfilling gutter pavement
12b37733-ba2c-5e82-85e4-a590b0bd82a4 | button | Acceptance | Yes,No,N/A
c95924a7-c561-5766-8cb6-f610974f6857 | note | Key - W
0f1a0b01-f7a0-5b27-b0f7-30b8e13b7832 | note | UGL Key - W
ad44044b-31ac-5fd6-9ea6-8874d9b436f2 | note | SHL Key - W
| checkpoint | 2.10 - Backfill Compaction
83ca36ff-91bc-5538-a776-cad6dd424233 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
544b48e9-56de-51f7-9f79-25836937bc74 | note | Acceptance Criteria - Compaction: As per pavement design drawings or otherwise 95% relative compaction in conformance with AS 1289.5.4.1
3e1d5c0f-099c-5484-b940-5b2cdbb99958 | button | Acceptance | Yes,No,N/A
21e47768-75db-5dd5-bca1-b7985b78d7d4 | note | Key - S
e0319f1e-b7a3-525e-9fff-0a7e048d3bac | note | UGL Key - S
5480c889-45e6-53cd-8607-4df0a1354fd6 | note | SHL Key - S
c8be9ec4-593b-5f9d-951c-c6b6e2aab6d1 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
e26cf7c4-b0f4-5b1d-a8a1-14c324b510a7 | tickbox | Test reports
| checkpoint | 2.11 - Gully Pit Tie Ins
34d95e1c-73b3-5282-bec1-d03600cd298c | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
1a0c9023-6245-5810-a98b-d37c3627d426 | note | Acceptance Criteria - Adjust gully pits or precast units to suit the new kerb and gutter profile without reducing hydraulic capacity of the pit.
3e09c2fa-858f-5336-8346-d7c6d623b99d | button | Acceptance | Yes,No,N/A
17c6f77c-4254-5ed5-bae0-1ae7cc99b6d9 | note | Key - S
69cc825d-b3b7-5487-95af-59df96935f84 | note | UGL Key - S
10049363-7b77-50d5-82d5-a6d45129828c | note | SHL Key - S
b9db0955-8138-5b5e-a908-4c3d1311abc1 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
6ae6be90-fbe0-5310-8cd1-ec09d7ccb77a | tickbox | Test reports
| section | 3.0 Conformance Check
| checkpoint | 3.1 - Survey Report
2c44dc5e-4c60-5e7d-906a-cd85c4197521 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.0]
e947a803-ddef-560e-9d8f-12b24c1d3847 | note | Acceptance Criteria - Survey report verifying kerb and gutter has been constructed within tolerance:
039c677e-702e-592d-adc3-752b837a86fa | note | ○ Finish levels of channel/gutter surface: within ± 10mm of design level
f879bd76-5645-58dd-ac58-fb6d5579e7d8 | note | ○ Surface deviation of kerb face and channel surface: ±5 mm from edge of a 3m straight edge, except at laybacks, grade changes or curves, or at gully pits requiring channel/gutter depression.
84b05d44-9cc4-5b55-a76b-b6148b1ce9a0 | button | Acceptance | Yes,No,N/A
ec81a7c3-3ba1-5972-b0a1-a61086d9b06c | note | Key - S
5c0b86e3-6e80-5663-a5da-d90d5ddb717f | note | UGL Key - S
4dabb84d-be00-51ef-bd18-9cc0f76fa965 | note | SHL Key - S
905d8661-4faf-559b-8585-3110f3e8019d | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
e47a40db-8119-52cc-9fa6-a87b7729543e | tickbox | Survey report
| checkpoint | 3.2 - Acceptance and closure of non-conforming items
c22eca06-6982-55a5-97e6-9b384a1a062d | note | Ref docs - Spec. 0161 Quality [Cl 3.8]
3a2a7c71-416a-5c7f-b493-d815302c9f58 | note | Acceptance Criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
ef584c52-1766-51c0-99a9-d72bebfa7bca | note | HOLD POINT
f79b3de3-7f39-59bf-bd4f-410617543579 | button | Acceptance | Yes,No,N/A
0520858a-01cb-508c-a6e7-0eb5b7004b77 | note | Key - H
182a516b-46d4-53e0-a3cc-b88e707ba279 | note | UGL Key - H
3a0fb9b8-ca02-5e42-8704-96d5b6bc772a | note | SHL Key - H
| signoff | AUTHORITY HOLDPOINT
| checklist | HPP-UGL-CIV-GN-GEN-ITP-007 Kerb and Channel - Rev.0 | itp | HPP-UGL-CIV-GN-GEN-ITP-007 Kerb and Channel - Rev.0 |  | a210baf5-28a3-4406-a75a-02ae19006958
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Determine lot size
05a708af-2209-5170-abf5-7b5bf7176ac5 | note | Ref docs - Spec. 0161 Quality [Cl 7.3]
2d3909a9-3546-5616-bfe7-837c58de07dd | note | Acceptance criteria - Lots to be broken up accordingly and outlined on a lot map
754929b1-bc94-5149-8d70-6422ae29ba72 | button | Acceptance | Yes,No,N/A
3df4333f-48bd-5d61-b590-87ed1aa86b9e | note | HPP Con Key - S
dee18c35-4a46-5be7-89f2-b450aec12292 | note | HPP QA Key - S
| checkpoint | 1.2 - Concrete Mix Design
c3ad3dad-4a09-5aa3-a112-c73fac37372f | note | Ref docs - Spec. 1121 Open Drains [Cl 3.1]
e58aad63-603a-51d0-86d7-84fb13b57258 | note | Acceptance criteria - Submission of Mix Design and compliance certificates for concrete constituents
b896d57a-e1ca-530d-b0de-fe5ad345bf2c | note | ○ HOLD POINT
22ec8f9d-385e-562e-8daa-fdfc3f1bced5 | button | Acceptance | Yes,No,N/A
76b87e87-0f92-5f70-8481-b9bfa0c919e0 | note | HPP Con Key - H
968dc8eb-ff01-52f8-9025-0fc118d8a599 | note | HPP QA Key - H
476e5a84-8581-525a-b973-43eaa2b86e8a | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
49411e48-2ffa-5c85-b47c-b462bf32954e | tickbox | Lot map
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Underlying Lot Conformance
161c9ac9-8095-569f-bd39-8e7ef7709589 | note | Ref docs - Underlying Lot ITP
e3efdbc3-a226-5897-bbda-308597010079 | note | Acceptance criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
efe322aa-a1ff-5d07-b29a-31828f39942c | note | ○ Refer underlying lot ITP(s)
ccd88253-aafc-594f-a62a-1c6a87cb3b2d | button | Acceptance | Yes,No,N/A
bacbc040-89f5-5a05-8c0a-ada4c3189b6e | note | HPP Con Key - S
6959b408-f0ab-56c8-9a62-8f31d70fe9e9 | note | HPP QA Key - S
| checkpoint | 1.4 - Survey set out
48f998d5-5caa-5eea-afd5-1583e192aef8 | note | Ref docs - Drawings
3f24b69b-0940-55e1-9a26-aedebd580223 | note | Acceptance criteria - Set out the alignment and level of the kerb
506d5162-8c24-54e2-9774-2868f03a2346 | button | Acceptance | Yes,No,N/A
ccb5f311-b7d2-50e2-b373-63ad53fa9147 | note | HPP Con Key - S
f3a2c9b1-fa04-5124-96eb-751008bd715a | note | HPP QA Key - S
82d3ec17-1712-56b2-9245-eaf89cd1cb11 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
84050827-0eb8-5379-832a-f25775ccd4f7 | tickbox | Material Test Reports
| section | 2.0 Kerb and channel placement
| checkpoint | 2.1 - Foundation
7f36ac1c-8564-564d-ae9a-9522c38bd593 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
6eb77abb-6171-5671-ae77-6b9c3f5860a9 | note | Acceptance criteria - Shape and compact foundation material to the requirements of the respective pavement course
521037ff-1485-5027-8aaf-fa45c73c2b0a | note | ○ HOLD POINT
3a674660-0d5f-5fb9-9832-44a1858cabf9 | note | ○ Notice: 1 working day before forming
0c334ddb-02b7-54bb-9e61-25eed5dae996 | button | Acceptance | Yes,No,N/A
f22b4fea-6010-5eb1-b4ae-4f42ea279706 | note | HPP Con Key - H
9bb09a4b-3f11-5cc4-81af-d3bad3ab4265 | note | HPP QA Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete supply and placement
a5bb7b72-a90e-5922-8fd7-8d12da102ff6 | note | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11]
22953404-f1d9-51e5-aacc-803a23a52be9 | note | ○ Drawings
de9a949a-7c8b-51b7-b8a2-d25e6ffae43c | note | Acceptance criteria - Check docket to ensure strength and slump is as per design requirements
d8262f8a-f886-5197-8166-5c6ff90067fb | button | Acceptance | Yes,No,N/A
51e53a6c-9ce2-5f47-9b7e-106c57b27805 | note | HPP Con Key - S
2fb244c0-1410-58a4-bfcc-e7555ad24572 | note | HPP QA Key - S
| checkpoint | 2.3 - Finish
302a6fcc-8feb-58f1-8557-f07c2f840e56 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
8008674b-36cb-587c-b02d-6ded6f17dac6 | note | Acceptance criteria - Finish true to line: The top and face of the finished kerb and channel.
df56c61c-098e-5296-af3b-8e1943194cfc | note | ○ Top surface: Uniform width, free from humps, sags and other irregularities.
f784476a-2b44-5422-9d79-f380165ae84f | note | ○ Type: Steel float finish or as otherwise shown on drawings.
132600c2-b367-5bce-a729-9512a338de16 | button | Acceptance | Yes,No,N/A
1bba824a-66db-5db1-a008-7b4e788bf9b7 | note | HPP Con Key - H
2f604bcc-5f00-5b08-ba88-bdd68769a8b3 | note | HPP QA Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Joints - Contraction
00d84ca0-cecd-5aa9-9563-bcfb1f2eb58c | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
1fab8c2a-e5b8-5041-905a-ad8892ddbbea | note | Acceptance criteria - Contraction joints to conform to the following:
59ae2521-99f4-534f-b935-665d99954120 | note | ○ Width: 5mm min.
9859f4bf-0017-5201-a56e-9add46ebaf2a | note | ○ Depth: 20mm
54b883d1-d0dc-5757-a712-870bd97bb12b | note | ○ Intervals: every 3m for a min of 50% cross sectional area
c3c2d10b-4f8c-5752-b7bd-1d4bf09b7174 | note | ○ Tooling: 20mm depth / 5mm width
f5036449-adad-56ab-8936-bde2ff9716b3 | button | Acceptance | Yes,No,N/A
89c3881c-74e2-5077-a7b5-a88b9c0895c2 | note | HPP Con Key - S
4309eded-ee3f-56f1-affa-e25e42c87bc0 | note | HPP QA Key - S
5809fefe-799a-51c7-ab6e-f346fdbfa89f | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
e4505f18-3fc0-5920-af2c-00588b2f76a6 | tickbox | Test reports
| checkpoint | 2.5 - Joints – Expansion
1fef62cf-accb-5955-9ef9-ff623eef3021 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
5300ec22-0354-5acc-9b5d-38f003ee24a8 | note | Acceptance criteria - Expansion joints to conform to the following:
8ed6fe3a-f12f-5fc7-a38d-791bf09ff09d | note | ○ Width: 15mm
9ed0adb7-01a9-56d7-b1ca-af0f873ded01 | note | ○ Depth: Full depth of kerb/channel
426c1c2a-634e-5775-9a76-e8af83958015 | note | ○ Intervals: Max interval 15m
e176f4ef-61ce-5d96-9ce1-5b3d48b9c493 | note | ○ To be provided where channel/gutter abuts against pits, retaining walls, overbridges and both sides of kerb laybacks unless otherwise shown on drawings.
736e02a8-41b8-5191-b9eb-69c30cbbf388 | button | Acceptance | Yes,No,N/A
2179cad8-05c3-5c49-ad58-d4577bbfe209 | note | HPP Con Key - S
bcb98c8a-9cec-596c-bdd1-3d7e4a185f9f | note | HPP QA Key - S
| checkpoint | 2.6 - Backfill
88ecd8eb-c16b-5190-928a-1c30eb914d9a | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
19101681-9e0b-5223-96dc-66d12ae5e302 | note | Acceptance criteria - Timing: Backfill behind kerb no earlier than 3 days after concreting.
4a9266bd-19a6-5923-9d5a-fc6c9a1b683f | note | ○ Material: Granular material, free of organic material, clay and rock in excess of 50mm or approval material
19cba5b4-42c6-58e1-95eb-de72eeb52a5a | note | ○ Layers: Compact in layers not greater than150mm
5b52428c-5dfc-5205-b22c-ad9e9a0d2556 | note | ○ WITNESS POINT
2e6c90ce-5465-5a80-bfe3-2836b667258a | note | ○ 1 Working days before backfilling behind kerb
e01bc4c5-97c3-5549-affe-d9c2c6fb3836 | note | ○ 3 Working days before to backfilling gutter pavement
d3a5322d-f641-52c2-8459-8a01d4eefaa7 | button | Acceptance | Yes,No,N/A
6a2897d3-bfa8-5bfa-8845-55fda2e1997b | note | HPP Con Key - S
9dbf545d-a5f7-54f3-b7f0-40c027d2ed61 | note | HPP QA Key - S
05f18001-5633-540e-a1e7-ec05119a26f7 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
b68d7a4b-b12e-577d-ab5e-eac4872f442a | tickbox | Test reports
| section | 3.0 Conformance check
| checkpoint | 3.1 - Survey Report
9cf506ee-8cea-5c21-a46f-37b725d4e476 | note | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.0]
59e8edc4-a1e9-5bb1-b1ef-12fce040c84a | note | Acceptance criteria - Survey report verifying kerb and gutter has been constructed within tolerance:
d0dba125-609c-5b35-80c1-e87f97f21ece | note | ○ Finish levels of channel/gutter surface: within ± 10mm of design level
5a16bbd5-903e-5a7a-bbcb-90bb905d08d0 | note | ○ Surface deviation of kerb face and channel surface: ±5 mm from edge of a 3m straight edge, except at laybacks, grade changes or curves, or at gully pits requiring channel/gutter depression.
4c61bc4b-dbb7-5500-b260-8677ea871cee | button | Acceptance | Yes,No,N/A
1f9d5cb2-b0b7-5181-b173-eacbfeb8de18 | note | HPP Con Key - S
01bffd8a-71e6-55c8-93ce-98c74767a5be | note | HPP QA Key - S
| checkpoint | 3.2 - Acceptance and closure of non-conforming items
47aec7aa-6487-54f8-9e29-0cd5ba431e90 | note | Ref docs - Spec. 0161 Quality [Cl 3.8]
5fed2cc8-c79b-5116-a2fa-b6afae75fc38 | note | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
046ebc9f-f223-5f79-a864-080f28584364 | note | ○ HOLD POINT
5f961807-f902-5502-b057-25c8e557497c | button | Acceptance | Yes,No,N/A
6edea8e1-941e-55ab-af94-e3a251de745b | note | HPP Con Key - H
10a6a9d8-a81a-50ef-beb1-556864e0d04e | note | HPP QA Key - H
| signoff | AUTHORITY HOLDPOINT