## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Prefix | Postfix | Resource Id
| checklist | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing | itp | 1630-P200-SYM-QAC-ITP-0001 Site Clearing and Grubbing |  |  | a073e436-6148-4f4e-a1cf-0ac516489764
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Define Lot
1aeaacd4-4230-5865-95c7-c87b67f2f725 | note | Ref docs - 1200.15 (b) (i) (B)
3051c949-737e-5f17-91d2-d04bc948cd17 | note | Acceptance criteria - Clearly mark out lot and extents.
25f3fbd6-318a-5d65-a217-61e8af37ca55 | note | • All No-Go Zones must be protected by temporary fencing and signage visible.
e9c9eb16-22e5-521a-bc5f-0ef130232142 | note | • All fencing of No-Go Zones must be:
ecddb32e-7a18-5e98-9fa4-a7143532f8b8 | note | a. erected a minimum of 1 metre beyond the boundary of the habitat to be protected, at the Tree Protection Zone or as directed by the Superintendent;
99495e62-1c44-50e3-a545-ba563cb4783e | note | b. at minimum, constructed of star picket and paraweb with two wire supports. The star pickets must be 1.3m in height, installed to a height of 1m above ground level and the paraweb must be installed to ensure a minimum 30cm gap is available between the bottom of the fence and existing ground to allow for fauna movement;
a255df34-f2a2-559a-b045-2a60203e192a | note | c. communicated by signage installed on the temporary fencing at intervals no less than 10 metres apart stating ‘Environmental No-Go Zone – no unauthorised access’;
ab6a4518-209c-5efe-a7cc-1e738598fe04 | note | d. installed prior to commencement of works in the immediate area, in accordance with the relevant approved SEP; and
568faa27-ea5e-5522-bef7-dc75982fd353 | note | e. retained in place for the duration of construction activities.
a2ec6a87-7d84-5ed9-bab7-5201a648016d | button | Has all of the above been completed? | Yes, No, N/A
7f7c9a1b-c030-5997-9f37-8956a46d8830 | note | Freq - Prior to start of works
9c7638ba-17e3-58a3-af91-d967e4e51e98 | note | Key - R
067a77d9-060a-5143-8e55-8390c0ede22c | note | Resp - SE
6ecb996b-d7d5-50ae-833b-4a296f144f2e | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
b489b33a-e894-50f7-8c1c-b138239e478a | button | Lot map | Yes,No,N/A
613ac238-8319-5ae0-baa9-1f3b3f5eeabc | date | Inspection Date:
| checkpoint | 1.2 - Works required inside a No-Go Zone
688d3eca-247d-5a7a-b7b8-acf90a952cce | note | Ref docs - 1200.15 (b) (i) (B)
fde1cadf-b659-5684-bfc1-d3340246aa53 | note | Acceptance criteria - No works are to occur inside any No-Go Zones, except for where the following process is followed:
f732ba0c-e9fd-5929-8e92-7c4091da8c37 | note | • Before commencement, where works have potential to impact flora and fauna protected by a No Go Zone, the Superintendent has been provided a report to the requirements of 1200.15 (b) (i) (B) for approval 5 days before the proposed Delivery Activities and it has been approved by the Superintendent.
f04de08a-0d34-5f7f-9f75-010c0a684c1a | button | Has all of the above been completed? | Yes, No, N/A
28124040-ea02-55df-9758-54259c361318 | note | Freq - Prior to start of works
4164726a-ef54-5049-9e7b-ce07d6c2dd95 | note | Key - H
e12ed4c0-a438-59c1-86cf-80df686a891c | note | Resp - SE
fe262d40-665f-5cc2-aaec-2754e0e61847 | date | Inspection Date:
| checkpoint | 1.3 - MRPV Vegetation Removal Permit
7a32c4b3-012d-5891-8c3f-6e4e4dcc2985 | note | Ref docs - Vegetation Removal Permit / PS3020.07 (a) (ii)
8eada7fd-3d79-5a74-9c08-5df5768ef2a7 | note | Acceptance criteria - Sign off by the Project and MRPV Environmental Representatives. This is to be reviewed by the Superintendent prior to removal and provided to Environmental team
91c9385b-5359-5c43-a9da-ef3460a5a3a4 | button | Has all of the above been completed? | Yes, No, N/A
1e81eec6-8f15-5f5c-96a7-05ff41dfdfab | note | Freq - Prior to start of works
134cdc22-d059-503f-95b4-726cd717a2f7 | note | Key - H
949dfb55-f788-516a-bea0-33cd437f9916 | note | Resp - SE
930838fc-ee73-52da-a4f3-110030ccbd87 | note | SI Key - H
49215191-82bf-5cc2-a396-a1097e7b6353 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint-no-value | 1.3.1 - Environmental Permit
367059b9-87d4-5293-8214-cc1b1896b2e4 | button | Environmental permit | Yes,No,N/A
7cb6d97e-008a-5996-ae1c-4ac9c740634b | date | Inspection Date:
| checkpoint | 1.4 - Design Documents Required
ddb00bbb-e7ab-57f2-81b0-8425fbb29e82 | note | Ref docs - 1170.11
59a61109-20b6-57de-aeff-cf5e1ccbd714 | note | Acceptance criteria - For site clearing and grubbing, the documents needed are:
2b330eb7-feb5-564a-9a12-44a4d86574ad | note | (1) marked up drawings that relate to the design Documents and clearly define the scope of the Enabling Works;
81920bc8-2e13-5fb5-9d30-f6bf93d12b48 | note | (2) any relevant Construction Specification for the Enabling Works.
491ba839-26c1-582a-abab-fc2dba44b97b | note | (3) a drawing showing environmental approval boundaries, activity areas and no-go zones.
ce172a45-eb29-594e-a08d-0831f91bdb8b | note | (4) evidence that any required design related Approvals have been obtained; and
184d644a-afa8-5878-babb-4a2dfde0aa17 | note | (5) a list of all required Approvals.
b6acb5f8-f07e-5526-a319-55cdf6a7dae6 | button | Has all of the above been completed? | Yes, No, N/A
669666cd-7ee5-5476-942d-038f2b53a010 | note | Freq - Prior to start of works
f94b0a48-3c1f-59dc-886f-d98f14684e4d | note | Key - R
c7ab6282-e9f6-5eb6-bc94-0886ca02e57d | note | Resp - SE
d97e5a42-3ba5-5920-b111-2a0b0f162084 | date | Inspection Date:
| checkpoint | 1.5 - Site Environmental Protection Plan
19b113f9-f428-575a-a795-80ceb50f031a | note | Acceptance criteria - Site Environmental Protection Plans and Site Erosion Control Plans have been reviewed and approved for works.
e6a5fa35-acb7-55af-ac19-2539536068d7 | button | Has all of the above been completed? | Yes, No, N/A
49d20439-dafe-5eee-916f-3a2959737bc2 | note | Freq - Prior to start of works
74f9980d-823b-549b-bae0-1f0f015353e4 | note | Key - R
bbf7fb5b-40d0-5ab0-9c52-2712c4822e9e | note | Resp - ENV REP
c7e89c08-4d17-5bd2-8087-c7015a470469 | date | Inspection Date:
| section | 2.0 Pre-Clearing activities
| checkpoint | 2.1 - Pre-Clearing Identification
f66c08f7-26a3-517d-ae71-f8951f49cea7 | note | Ref docs - 1200.15 (b)(i)(C)
9c6418f7-b248-5d60-b799-c0428e265a01 | note | Acceptance criteria - No less than 7 days prior clearing, an ecologist has certified that all habitat trees are clearly identified and marked with flagging tape or survey, consistent with the Design Documents and permits and approvals.
406073f9-3636-543a-87ce-c92a9517220b | note | • Any salvageable timber suitable for reuse to be identified and marked for stockpiling, for it to be reused after clearing.
5caee50c-1dbc-59b4-9134-0420fc38c384 | button | Has all of the above been completed? | Yes, No, N/A
304ca1c1-bddc-51d7-8579-614c4c345df5 | note | Freq - 7 days prior to proposed clearing
330062aa-d495-5ed1-879e-a331e5e98d40 | note | Key - H
5529ab32-761a-5984-9cda-c5b862cf7d98 | note | Resp - SE
467af375-8c6b-57cf-ad47-1bd287e4d596 | date | Inspection Date:
| checkpoint | 2.2 - On-site inspection
cea5e880-ea3b-5e8b-a0cf-4ef27cdbeaca | note | Ref docs - 1200.15 (b)(i)(C) (4)
92af811b-f0a9-5f25-80f6-2041775eaec1 | note | Acceptance criteria - Prior to removal of vegetation, site inspection to be arranged with the Superintendent and other authorities to confirm the requirements of Sections 1200.15(b)(i)(C)(1) and 1200.15(b)(i)(C)(2) have been achieved.
ad722b5e-4838-5ef2-9c69-15b7464a267b | note | • All Approvals are in place and the ecologist is always on site, ready to perform further inspections in accordance with Sections 1200.15(b)(i)(C)(3) and 200.15(b)(i)(C)(5).
f703935d-b0ce-532b-bf92-62ede504562d | button | Has all of the above been completed? | Yes, No, N/A
36b866cc-9670-5900-8449-ff775a11fea8 | note | Freq - Prior to clearing
4b0be976-fa55-5a73-bd16-9cb2a8040ce4 | note | Key - H
a5b589a5-762b-54c6-bece-ffe2e79061d1 | note | Resp - SE
0ffbca66-b115-56c7-a6a8-344f4fafb2bd | note | SI Key - H
284869ae-1d41-5de2-ae9e-b10f520e701a | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Onsite Clearing and Grubbing
| checkpoint | 3.1 - Clearing
8134fbe5-5f9c-51f4-bd1e-2285ba293755 | note | Ref docs - VR201.04 1200.15 (b)(i)(C) (5)
d1885acc-e2cf-5908-b8a8-3421c18841c4 | note | Acceptance criteria - Only non-habitat trees can be removed during the first stage of clearing. Habitat trees can then be removed after approvals have been received and a minimum of 24 hours after the removal of non-habitat trees.
594387f3-cff1-5e29-a205-8c94f69f8f87 | note | • Prior to commencing of clearing each day, the ecologist appointed should inspect the area for signs of wildlife.
a62414e5-2aa4-57ef-9f46-a24733e6905f | button | Has all of the above been completed? | Yes, No, N/A
4aa2dad0-7550-59a2-9b40-919a3fc12b34 | note | Freq - Each lot
071f9452-f9ef-53f3-99c2-8969f5ddbef9 | note | Key - H
ac43cedc-ca20-5277-a6c4-84b94bf60f88 | note | Resp - SE
91dbf2b5-9a5d-50f1-8eb0-76ac45015a66 | date | Inspection Date:
| checkpoint | 3.2 - Grubbing
765705e2-d463-523b-bf79-b23f0f2c2dc1 | note | Ref docs - VR201.05
3810f854-6779-5953-ab9d-554d9449e3f9 | note | Acceptance criteria - In areas where excavation will be undertaken, all vegetation shall be grubbed as per the requirements of VR 201.05 and early works – subgrade improvement design package
dd370420-f1e0-525b-9fb0-3482980c504d | note | • Holes resulting from grubbing shall be backfilled with similar material and compacted to same degree as surrounding material.
43af75e3-6205-5bef-b9c0-c92da9f71132 | note | Freq - Each Lot
a32fc915-ab09-535b-88b4-4d9f9083db34 | note | Key - R
942823a9-3770-57c2-8ed8-76b6d4c64c91 | note | Resp - SE
9369dfc7-f86c-5902-b865-d9c2e1a85d82 | date | Inspection Date:
| checkpoint | 3.3 - Clearing at Culvert Sites
17166604-6bf8-5a47-9f4b-549277092086 | note | Ref docs - VR201.06
38cd2420-f39d-52ff-880b-d69a58f4dc70 | note | Acceptance criteria - Any trees or stumps with 10m of any portion of a proposed culvert having a waterway area greater than 6m^2 shall be cleared and grubbed in accordance with the requirements of VR201.
81f3b80b-3665-5499-8b7d-4b029a1c3143 | button | Has all of the above been completed? | Yes, No, N/A
b7364ca5-7ef3-5fd9-a367-9c26af473400 | note | Freq - Each lot
1c9aa83b-f83f-567a-92a7-7302c41c5b5d | note | Key - R
b3d7b60a-53ce-548d-9229-0c85a8d738dd | note | Resp - SE
3ece8513-7dab-599e-ae32-5aab7ee6679b | date | Inspection Date:
| checkpoint | 3.4 - Flora and fauna handling and removal
0c8b1649-bc7c-5328-a8c4-e66f8b8cd5af | note | Ref docs - 1200.15 (b)(i)(F)
20c690c6-6455-580f-83a5-255e8110b13d | note | Acceptance criteria - The Superintendent must be notified if any significant flora and fauna is found, and an ecologist must identify and provide advice on what to do with the found flora or fauna.
41c59073-a4f0-542b-b774-185ac0f50271 | note | • The Superintendent must notify Environmental representative of any flora and fauna found.
6558365f-04f5-5525-b8ca-9e3ada2a8c59 | button | Has all of the above been completed? | Yes, No, N/A
b015d1ac-2a3a-56ce-a752-5179739c3397 | note | Freq - Each lot
6666619e-77af-539b-9be1-17089105176c | note | Key - I
b4508b45-159e-50f2-807f-3125fb7945ff | note | Resp - SE
90f3ce84-c1bd-5525-81ca-d103f46ccb52 | date | Inspection Date:
| checkpoint | 3.5 - Identified habitat
a3eaf210-473b-532b-9b97-c7d2ffb028de | note | Ref docs - VR201.10 1200.15
db02926b-aa92-5b12-a5c3-e8b948bf7818 | note | Acceptance criteria - Trees with hollows can only be removed during initial clearing, if hollow is occupied, the section is to be left and cut after clearance from the ecologist and a minimum of 24 hours after removal of non-habitat trees in the area.
4eaa7fc3-187b-5524-8023-442f29334217 | button | Has all of the above been completed? | Yes, No, N/A
50ba95ab-ea75-5cd3-8271-fe53b2ea3dd8 | note | Freq - Each lot
0fe09c78-873c-5e1c-b893-7946aa42f93f | note | Key - I
9529233f-363e-52e5-a5d0-61fbf76aed4f | note | Resp - SE
d10bac38-3616-5137-bf68-8ca5bb9cf264 | date | Inspection Date:
| checkpoint | 3.6 - Reuse of Material
5ed6226d-b06c-5add-a9fe-05feddd7d5e0 | note | Ref docs - 1200.15 (b)(i)(G)
19593e4e-2458-5263-8699-2530c500b7fb | note | Acceptance criteria - Seek and adopt where practical reuse opportunities for vegetation felled during the vegetation clearing operations. Reuse may include:
9bb6ebc9-c4d7-59ad-b1e7-68d766c755b3 | note | a. retention of sections of a branch/trunk with hollows;
2b188504-37fe-5e54-bc82-0af88263820c | note | b. habitat logs on the ground in revegetation sites;
66b7bdcf-916b-57de-a73f-48746ce61f44 | note | c. placement as in-stream habitat with the appropriate approval of the relevant Catchment Management Authority; or
63009fc2-485d-513a-97c2-645a99b9c12f | note | d. timber for furniture construction
d25265f3-e945-5cd5-8707-e2d067632433 | note | e. Mulch provided to Council, local schools, or to landscaping facilities
e9746773-2157-53de-9d93-5ee8925d70ab | note | Update tree removal/retention register
c0c4fd5b-50cf-5eee-9858-233bc7904da5 | button | Has all of the above been completed? | Yes, No, N/A
f25cfa97-395d-5c6a-938e-144f2ff692ce | note | Freq - Each lot
51b7f521-36ee-53b7-9930-8dfb665e33b3 | note | Key - R
c1c1495d-0590-541c-b1c1-16d8fa3d64cc | note | Resp - SE
242a1718-aafc-5f0b-a045-0536637fdc39 | date | Inspection Date:
| checkpoint | 3.7 - Disposal of Material
22ab1f51-be06-59d3-8723-6a067c3cd4de | note | Ref docs - VR201.07 VR177.I2 PS3020.07 (a)
5c8edeb8-5436-5716-b9ad-7eec55c24b3d | note | Acceptance criteria - No removal of noxious weeds from the site. Identify and undertake treatment of declared noxious weeds prior to the commencement of any ground disturbing activities.
8ad52fd6-9afe-5a69-8a56-b25741efabe5 | note | • The disposal of these materials shall be in accordance with the CEMP and its sub plans
15f8667e-f158-5a0e-b0b5-bb8f79ea6243 | button | Has all of the above been completed? | Yes, No, N/A
b9bbbd28-46a5-55c2-90e6-b420a0b67e94 | note | Freq - Each lot
e67357d3-d70a-5557-a6c5-0724d4b43a7b | note | Key - R
91f63033-9c44-5f27-99e0-db12236e6a7d | note | Resp - SE
7c6b496d-5674-5bf0-b0a5-d20d47a1387c | date | Inspection Date:
| checkpoint | 3.8 - Salvage of Vegetation
23549aac-89ad-5bee-b6eb-0969e80f2ae1 | note | Ref docs - VR201.11
72147322-28e1-51bc-b978-03f241399063 | note | Acceptance criteria - Salvaging any plants as well as collecting cuttings and available seed from areas of native vegetation on site to be completed where applicable
e2ce4a55-26c2-5287-aa10-7edb1b48adf0 | button | Has all of the above been completed? | Yes, No, N/A
ec6acecb-2efe-5060-8553-6bc607710bf8 | note | Freq - Each Lot
41cb47bd-0387-50d8-bf7b-8cc6dc6e4fb5 | note | Key - R
5e022082-44cf-5f79-8775-0d23395d8ead | note | Resp - SE
6863f7ea-39df-5592-a3ef-0a9814484ac5 | date | Inspection Date:
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Product Non-Conformance
19c26434-6dc1-59af-bc98-36adc0c0cfcc | note | Ref docs - CQMP
9518b3f4-350e-5fcf-84bb-20dc7d9bfd0a | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
414be1e4-dd58-514e-9aa9-3aa236908911 | note | Freq - Each lot
95c40cbe-2f04-5cfb-9ea7-46afacf4e933 | note | Key - R
346b6282-08c5-5e82-b865-5a52190fbf88 | note | Resp - SE
1de4e1b9-6e81-5c1e-937e-83f3b62d4ca2 | textbox | NCR No:
3d042604-f802-5c13-9d3a-f5a67dd771c1 | tickbox | NCR reports
379973d5-60a8-5adb-8248-a277533eac6d | date | Inspection Date:
| checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
ffc76c0f-2b8b-558d-b0d7-dae9d6812bed | note | Ref docs - CQMP Lot Records
e10d2619-880b-51f6-88de-945be30924e0 | note | Acceptance criteria - All above criteria met, and records identified attached.
b2e3f48d-5616-5f85-8bbf-b937b6eacd62 | note | Freq - Each lot
a5c3681d-7870-5675-a7cf-b69ac24a35a6 | note | Key - R
d049f055-3bb5-56ce-a1ed-2ee1e25ae8ea | note | Resp - SE
7f5d42cd-6f2a-5cfd-8273-f23af83651c5 | tickbox | Completed Checklist (if applicable) and reports and other compliance records attached.
28a22383-1679-51db-93b6-fd88f726cb54 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping | itp | 1630-P200-SYM-QAC-ITP-0002 Cut Floor/Topsoil Stripping |  |  | e9007ad5-8686-4cfd-9689-41b829945f13
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Commencement of Work
354d4795-24bc-5065-8ceb-48d5e3a49155 | note | Ref docs - VR Clause 160.C1 General condition of Contract
3604b9c5-db0f-5d37-a313-662a65afb029 | note | Acceptance criteria - Works shall not commence on site before the following documents have been submitted:
a2f3cb45-2f2e-558f-87ca-453e0f657632 | note | a. Evidence of public liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
b51d1b8c-0fe0-5d99-988d-5917794f9d27 | note | b. Third party property damage insurance in accordance with Clause 160.G1
3cbaafe7-b65f-5a84-bc10-df42fc0ce6fd | note | c. Health and Safety Management Plan
a8777f84-cd15-5f8b-8fed-a7c578cf98ab | note | d. Construction Environmental Management Plan
cf0d5e50-678a-5153-8ffd-8e63e15a55b2 | note | e. Traffic Management Strategy and Traffic Management Plans for the initial works
746ebbb4-4050-5c7c-8aab-a3fcc36b41fc | textbox | CHAINAGE FROM
e8c3a184-a8f4-5272-82a3-11f5dea72b87 | textbox | CHAINAGE TO
845c6684-e4f9-5b0f-96c7-708a92b78f54 | button | Has all of the above been completed and approved? | Yes, No, N/A
20dac91e-ef6e-5e5e-8ffa-37400f1d0c16 | note | Freq - Once (Pre-Start)
fe244820-2108-5934-ab99-c1a8cb1ff05d | note | Key - H
3d7c06fa-ab1a-5a17-a992-73a2cc6cb403 | note | Resp - SE
af5aa3dd-5878-5b85-98ec-fd59f4ceab0c | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
7a23205e-ea04-5fa3-a339-47099e0014fe | button | Lot map | Yes,No,N/A
506daf4b-2b5b-5461-b76e-2deb8d233501 | date | Inspection Date:
| checkpoint | 1.2 - Safety
ab550148-a0da-5865-99b3-d3e81ed2fbb7 | note | Ensure that the following items have been actioned:
858b8e46-6323-5fe7-a78a-8195315895fa | note | – SWMS if applicable
802b698e-9f4f-585f-b64c-44224b503f97 | note | – Plant Pre-start Inspection
aee3ad6f-2789-54a5-beb7-2ae34e363e63 | note | – Service locations identified
d6d6148a-cec1-5c75-b757-64ca8569ac01 | note | – Traffic Management Plans (if required)
53102884-5190-5c72-a305-f4f39aa0d7eb | note | – All staff inducted
467d9bbd-b7af-54df-a720-1e52b06a19a2 | note | Ref docs - SMP
6813e853-7c23-5fad-a934-c334791f559b | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
e8eaa971-6a14-516e-a927-f2a9f7730503 | note | • Plant inspections completed and entered.
13dfd283-88d5-5589-b85c-87703defbfb2 | note | • TSA training completed. Pre-work briefings completed.
9e6322b5-8a22-5416-8f48-9187111411cd | note | • Service Diagrams available and services located.
3401e531-3b6a-53c1-844e-9a977d104998 | button | Has all of the above been completed and approved? | Yes, No, N/A
7dd98b5c-d093-5144-b283-b8ac082aefc0 | note | Freq - Once (Pre-Start)
38691c0e-e2fa-509d-b301-d94c743604b2 | note | Key - H
eb6f0e05-79c8-54f9-b15f-8ae740922568 | note | Resp - SE
e2511b9c-4776-565f-b999-720c9cd48dbe | date | Inspection Date:
| checkpoint | 1.3 - Survey Set-out and TBM’s
c34585a1-238d-5da7-8dfd-537d2b57c11b | note | Ref docs - IFC Drawing
f913eb0e-f647-5bba-9aa8-9446a18c6acc | note | Acceptance criteria - Record existing and established TBMs. Survey set out including frame, benchmark, and recovery points in place.
3af33cda-3a1b-5e28-a1fd-4225d5b71fd7 | button | Has all of the above been completed? | Yes, No, N/A
6519fc63-0e60-5cff-af9b-3840ea887760 | note | Freq - Prior to start of Works
66258eb7-fd9d-5092-9b65-23c89f706a84 | note | Key - H
f3c38956-1ef6-5604-a24c-1983d15461ab | note | Resp - SE SV
22faa7db-d081-5679-bf8c-52ed8096cef1 | date | Inspection Date:
| checkpoint-no-value | 1.3.1 - Surveyor Report Reference
09f688dd-aa34-5f4f-8cbc-ac625aef672f | button | Surveyor report reference | Yes,No,N/A
a19e0ee5-cfaf-5b63-b16c-3a8abf9d72ef | date | Inspection Date:
| section | 2.0 Construction
| checkpoint-no-value | 2.0.1 - Incoming Material Docket
03a4e44f-00e7-590a-964e-4a5cf4e4d3b4 | button | Incoming material docket | Yes,No,N/A
3f3044d0-c5aa-5ac0-b809-7b89e63c19ef | date | Inspection Date:
| checkpoint | 2.1 - Topsoil Stripping
b78056f9-eb0a-5953-b395-d43fab4429df | note | Ref docs - VR Clause 204.05
d4271cca-3256-59a3-a32d-4c9a5f196de4 | note | Acceptance criteria - Topsoil is to be stripped to an appropriate depth removing surface topsoil in a way to leave the surface evenly graded and free draining.
4f018ea4-fbff-5c2f-a722-eb4288acda14 | note | • Topsoil to be reused onsite is to be stockpiled in an agreed location. All stockpiles shall be maintained in a neat, well-shaped state capable of shedding water.
45a75409-28f4-56a0-99fb-520c552a9c37 | button | Has all of the above been completed? | Yes, No, N/A
7e4bce7f-f710-50ec-9fac-f027c0f60c90 | note | Freq - Each Lot
8fda29b4-19e6-5859-b55b-dfa2005a36f1 | note | Key - R
d01857fa-f4df-5ae3-a305-843bef5f790e | note | Resp - SE
aaceb6b1-ca28-551b-b1aa-5769126f56df | date | Inspection Date:
| checkpoint | 2.2 - Site Excavation
3dbca08e-003d-5324-adf5-0c8ea834c548 | note | Ref docs - VR Clause 204.06
26145cf0-a388-5b28-bb51-e7b5aca2fa02 | note | Acceptance criteria - Prior and during excavation work, the Superintendent will be notified to inspect all material encountered for material classification, subject to verification by laboratory testing.
4da4d0d2-4596-5db3-88a2-de1794556e17 | note | • The areas of rock subgrade shall be presented to the Superintendent for acceptance.
11ff03e0-5769-5659-8555-fa91069a1d5c | button | Has all of the above been completed? | Yes, No, N/A
8bbcd9ee-fac7-5547-851c-99d46787a713 | note | Freq - Each lot & Each possession
c9c30a26-d7ea-5272-8bdf-6dcc3c20cb89 | note | Key - H I S
69ab45c6-0d80-5d75-914b-74d5750af34a | note | Resp - SE
2ca9c33b-0b10-5043-a676-00b29b77b27a | note | SI Key - H
f140015f-9544-5a17-acbf-c61c6962d731 | button | NATA Test Reports (as required): | Yes, No
1eeb59c8-7cb9-5cb0-b222-fad81728a2b3 | note | – CBR and Swell
3e19371f-2051-5b89-8b7d-b5c082dc5e72 | note | – PI
b547beb7-6f63-5981-ace3-f27a7017d5f5 | note | – Permeability
e02f7690-097e-511a-8e42-6a228417995a | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Groundwater / Seepage (if applicable)
71e5f216-2ecc-5d84-842c-f6a2ac75ff92 | note | Ref docs - VR Clause 204.06 (h)
d7503594-bcb2-5ad7-a828-3b3fd3b71809 | note | Acceptance criteria - If groundwater or seepage is encountered, notify the Superintendent, and create a course of proposed action.
4d8cc251-9c73-5622-bbc3-5c2224d5b4ce | note | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
8fbc0d1b-cea8-58ca-a282-ffd65476b0e3 | button | Has all of the above been completed? | Yes, No, N/A
43e8fa9a-3acb-52d6-9c1c-d09bec99a386 | note | Freq - Each lot & Each possession
8dde038c-78af-589e-843f-02cfcbd813a7 | note | Key - H I S
7d8fb756-d231-5a81-8cc0-11f22a3054a0 | note | Resp - SE
1d4e1dea-25a1-55fc-b1f5-75b147ced990 | note | SI Key - H
71f126af-dbb5-5d0e-a81e-c4bae4b69a51 | textbox | Dewatering Permit No.:
36b9c9ca-1e9e-5fd6-97cd-f50e04e32803 | button | Written Approval from Authorities | Yes,No
643389a5-8775-51e4-b8c5-da1963a46b17 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Treatment of Unsuitable Materials (if applicable)
6e5ebc13-ebdb-5975-b7f3-c00e48e4fb90 | note | Ref docs - VR Clause 204.07 (d)
4c386842-4811-5f84-82fc-1a56ee50cf06 | note | Acceptance criteria - If unsuitable material is encountered, submit proposal for in-situ treatment or excavation and replacement with conforming material.
c999ed12-ea6d-51b4-b60f-583d0bd2e54e | button | Has all of the above been completed? | Yes, No, N/A
00e7c125-26f5-5fbf-9ca4-c1acf6226440 | note | Freq - Each lot & Each possession
94792577-2bb8-5a86-b8ec-3e497604eabb | note | Key - H
8aad049c-99a1-51fb-b5a9-1b74159378d4 | note | Resp - SE
b589bb22-544c-5af5-b12e-1530b0e05944 | note | SI Key - H
91fc756b-208f-594d-a1ad-c52a8b917225 | button | Survey Report (Extent of Area) | Yes,No
650b2b09-f4fc-5afb-859d-d4374d4978e5 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Treatment of Cut / Rock Subgrade
| checkpoint | 3.1 - Treatment of Rock Subgrade
dc46f4b8-3f7f-50a3-96fb-35a3211330b0 | note | Ref docs - VR Clause 204.06 (f)
cfd6d02c-6f33-5584-a11f-7ace2d67d67b | note | Acceptance criteria - Where rock exists in a cut below subgrade level but within the designed capping or selected material layer:
c2df1d1f-3a42-5db2-96ea-162d40546085 | note | • Excavate minimum 150 mm below subgrade level in all areas on which pavement is to be placed.
8c02cdf2-f17c-502a-be42-aed6f00afbbc | note | • Remove loose material and soil from the rock floor.
674927fe-90ce-524f-8824-85cfb305ffa4 | note | • Any resulting depressions lower than 150 mm below subgrade level shall be cleaned of loose material and backfilled with 20 mm Class 3, 3% cement treated crushed rock and compacted as specified.
719f4a96-b270-510c-9f4f-d35d8b04f122 | note | ○ Present the above to Superintendent for inspection.
b5bcad0f-4589-5ff7-8f23-0b4282dc02bc | note | ○ Contractor is to submit details of any necessary adjustments to the subsurface drainage design, including transverse subsurface drainage at all interfaces to the Superintendent for inspection and review.
73479a87-bdf1-52bb-857d-d3c85d9c1426 | button | Has all of the above been completed? | Yes, No, N/A
f425aa4b-24b9-5544-a64a-9a5784477d35 | note | Freq - Each lot & Each possession
e7a44e25-8613-5538-a8b7-f99f4214f978 | note | Key - H W S
45af8726-8d29-58ba-966a-713b42c2caa0 | note | Resp - SE
13aca8c9-2d27-50df-8239-4077197e6400 | note | SI Key - H
defeafc4-308c-58f0-9355-502284218a09 | button | Evidence of VicRoads Registered Mix | Yes,No
a04b5e9c-55e7-5571-be53-98d640a71176 | button | NATA Test Report: Compaction and Moisture Content | Yes,No
3116e02d-2d87-513f-8257-2198d1212b42 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Regulating Layer for Rock Subgrade
e53644c0-6d45-5e79-861b-0b04ee49d2b9 | note | Ref docs - VR Clause 204.06
e2bd0d62-8680-552e-a466-bf615aa7814e | note | Acceptance criteria - Following inspection of rock subgrade by Superintendent, place 150 mm regulating layer of Class 4, 20 mm Crushed to subgrade level in lieu of the specified capping or selected material.
d0c31cfb-3e79-58f4-901d-21b3e64bc8b1 | button | Has all of the above been completed? | Yes, No, N/A
e7c25b1e-c2d2-5f8a-a416-663bb3fcd878 | note | Freq - Each lot & Each possession
a8085c19-1495-599b-8707-612a219a19aa | note | Key - W S
abf77ff0-fb0c-5b8a-b6f8-bf1fb1404819 | note | Resp - SE
e74dfb76-bfac-5a95-9f1d-e178756c5065 | button | NATA Test Report: Compaction and Moisture Content | Yes,No
68f684a0-8171-5573-914a-fd46a1f7c6c3 | date | Inspection Date:
| checkpoint | 3.3 - Testing In-situ Material in Cuts
d19e9362-2436-5eda-ae14-ede3d36d21d7 | note | Ref docs - VR Clause 204.07 PS3020.05 (c)
95eb85db-9635-5592-9cc1-d069d0d51eaa | note | Acceptance criteria - Undertake 1 Lot test initially to determine Assigned CBR and % swell for in-situ material in cuts within 400 mm below capping layer.
52b3800a-aa7b-5ee2-aa3a-c7f196ed4b55 | note | • Where the assigned CBR and % swell conform to the requirements of Cl. 204.04, seek the Superintendents ’s approval for minimum frequency of testing.
f1f02e00-9f19-5fc3-8c4f-c1bd673cddad | note | • Assigned CBR must be equal to or greater than 2.5% and must be no more than 10%.
e053a484-9e84-5867-8c77-46baf3f19112 | note | • Assigned percent swell must be less than 2.5%
121ff1b6-5ce9-5c25-92fc-2f4e85cdb1fb | note | • Where Superintendent approves minimum testing frequency, proceed to conduct 1 single CBR and % swell test to confirm Assigned CBR and swell every 4 lots.
8f7e6ba2-7a09-5f72-a268-279d9c46ed42 | note | • Where unsuitable material is encountered on site, the contractor shall submit proposed treatment plan to the superintendent for evaluation.
1f310865-f0a2-52a5-b9ed-5efd69f1e4de | button | Has all of the above been completed? | Yes, No, N/A
dd19ff20-4c7e-5d4a-823c-347e77f704d1 | note | Freq - Each lot & Each possession
f170c8e9-9499-5195-9231-865b5afabea1 | note | Key - W S
8eef8029-68cd-56b8-ba0d-9eba64294b96 | note | Resp - SE
bb76e712-5fea-51b3-8e86-c3431ca52423 | button | NATA Test Report: CBR and Swell | Yes,No
a7763117-158d-5bfe-a74d-81f3728440ae | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Treatment of Cut (if applicable)
13c7d6eb-566e-5ef5-bb11-40514a98c06b | note | Ref docs - VR Clause 204.06 (e)(ii) 204.10 (b) 204.12
263ff6d1-d670-512e-8edf-ef5704dd79f2 | note | Acceptance criteria - The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm.
188662a4-b8b1-5771-90ee-cea6ff90ca0f | note | • Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with Type B material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
f41ef56a-f579-5fc9-8fb5-67f5e62d5d07 | button | Has all of the above been completed? | Yes, No, N/A
419ed413-bd9e-513b-9b3c-2991b7a7eb06 | note | Freq - Each lot & Each possession
4c934a84-3d28-534b-a5e5-0d3bfdfc260e | note | Key - W S
7c0c504e-9ce1-5648-a1f2-2d83830fa3e5 | note | Resp - SE
f3deb7c8-f10d-5ce9-885b-ccee5e9365bf | date | Inspection Date:
| checkpoint | 3.5 - Compaction and Moisture Requirements (material of nominal size < 40 mm)
4c0558d5-2dbf-5e33-ab3f-9e01534fef0c | note | Ref docs - VR Clause 204.13 (para 1) 204.13 (b) 204.15
3702e6a1-eeee-50c3-a15a-d8364f238983 | note | Acceptance criteria - Undertake 6 tests per lot (except for small lots).
309dbdf3-8fbd-55b6-a17d-f48bc67df3b5 | note | • Ripped and re-compacted material below CFL: minimum CDR 99% (Scale A)
3667c525-8d48-50ab-8bf2-e05dea9f1d10 | note | • Top 150 mm of areas where fill is to be constructed: minimum CDR 97% (Scale A)
9b2aa876-1447-5483-8302-1e4033166390 | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer above.
ba086768-31c2-586b-ab0c-c1a2512ae333 | note | • The moisture ratio shall be determined using the material which passes the 37.5 mm sieve, where the material contains less than 20% oversize material. If the material contains more than 20% oversize material, the moisture ratio shall be determined using an alternative method in accordance with the appropriate test method or Code of Practice.
a00c3d9c-a330-5e2d-8552-a6a903d9b73e | button | Has all of the above been completed? | Yes, No, N/A
6d090dd2-21ba-5777-bd0d-ac8bd55d2bbf | note | Freq - Each lot & Each possession
c96f9750-b33f-5913-b71c-aa56b3318804 | note | Key - W S
fc8c429f-b71a-5759-a225-a5e156c3bfe1 | note | Resp - SE
a7baaf89-94d3-5839-bb11-92b0bb04e593 | button | NATA Test Report: Compaction and Moisture Content | Yes,No
aa06e39a-1217-5a83-ad2a-d136cfe787fd | date | Inspection Date:
| checkpoint | 3.6 - Compaction and Moisture Requirements (material of nominal size > 40 mm)
e5713da6-0202-59df-af38-1c0a212b7f4d | note | Ref docs - VR Clause 204.13 204.15
6cf35207-f719-54ef-b24b-3f022973a7d6 | note | Acceptance criteria - All fill material and material below the Cut Floor Level shall be compacted at minimum moisture ratio of 80%. Place and compact material in accordance with approved procedure.
534cd735-9926-5ca2-9608-4c4c2083f12a | note | • Any unstable areas detected by test rolling shall be rectified. Where unstable areas exceed 20% of the area being test rolled, the whole of the area shall be ripped, re compacted as specified above, and re-presented for test rolling.
81f8a26a-fe89-5a8b-a9ca-f2341f7935fa | button | Has all of the above been completed? | Yes, No, N/A
2e18ad7f-1650-55a5-b7f3-65dd92bf69db | note | Freq - Each lot & Each possession
f4e77a1f-07b9-52c0-9e3b-423c7293c460 | note | Key - W S
158c3fef-8bbc-5cc5-a262-e3092516f966 | note | Resp - SE
eb565063-19a5-53a9-ae69-f182c7d900de | date | Inspection Date:
| checkpoint | 3.7 - Surface Level Conformity – Fills and Prepared Surfaces
517b58a4-cd13-5202-8843-6f3b7574a963 | note | Ref docs - VR Clause 204.03 (a),(b),(c),(d),(e),(f),(g),(i),(j) & (K)204.15
02c6bd54-5239-5c37-aad6-a14a6cb8337e | note | • VR Clause 204.12
cfb65c17-b056-5982-829b-cc270e587283 | note | Acceptance criteria - Where capping and/or selected material is to be placed above the Cut Floor Level to subgrade level, the level at any point on the surface of the Cut Floor Level immediately below capping and/or selected material shall not differ by more than 15 mm above or 30 mm below the specified level.
fbf2949c-b9e7-54dd-af5e-7e3808610224 | note | • Where capping and/or selected material is not required, the Cut Floor Level shall be prepared to the appropriate tolerance for the subgrade. (See figure 1)
f016296c-c9bd-5b5d-81ef-1bec01e06269 | button | Has all of the above been completed? | Yes, No, N/A
caa8cc8a-1fdb-5daa-8da8-9452cc75dd47 | note | Freq - Each lot & Each possession
7564ccc7-b44d-5cfe-b858-b2ac681a997b | note | Key - I S
bbbfc94f-2aab-592f-b3c8-54ee7d519da1 | note | Resp - SE
35b12cf9-d6c0-5325-b11e-3655abe375c3 | button | Survey Conformance Report | Yes,No
20ebf3e3-187e-5847-8a80-e4664a75c3f0 | note | – – – – – – – – – – – – – – – – – – – – – –
ff889095-5a80-596a-a74b-79eb81ad4af3 | note | Figure 1.
6a8f1ba9-79e5-5c88-895c-c9da96f415b2 | note | Table 204.031 Minimum Number of Level Measurements and Tolerances
10a3701e-7be7-5be0-90e7-afaaf9e3788b | note | – – – – – – – – – – – – – – – – – – – – – –
6ad71462-cf0c-5bc3-a17c-90ab6eee099c | note | Scale of Surface Level Measurement ¦¦ Minimum Number of Measurements per Lot ¦¦ Tolerance: x̄ Range (mm) ¦¦ Tolerance: Maximum S (mm)
4d49f4e8-d7cf-5442-9426-aecb66c4a12a | note | – – – – – – – – – – – – – – – – – – – – – –
ac3dd7ba-e12c-5f27-9962-f711f8795fcf | note | Scale A ¦¦ 80 ¦¦ +5 to -15 ¦¦ 12
e5d5aea4-adcf-5f14-bc61-7f0cf0f51121 | note | Scale B ¦¦ 40 ¦¦ +5 to -25 ¦¦ 15
3f744d3b-386b-5cea-811d-03e65d832e8f | note | – – – – – – – – – – – – – – – – – – – – – –
c05453e2-8510-56b5-a1eb-923c899e0ef1 | note | Notes:
33378fdf-1b0e-5fd7-8cdb-a743c5ed8561 | note | 1. x̄ is the mean value of all level readings taken in the lot
16c761b7-d084-5b00-9c03-a81db5facd61 | note | 2. S is the standard deviation of all level readings taken in the lot
1c6d8b14-6eb4-5370-82d4-acb374136121 | note | 3. A negative value designates a measured departure below the design level and positive value designates a surface level above the design level
d68dba6b-ee3d-50dd-ad99-33d3dafa1986 | date | Inspection Date:
| checkpoint | 3.8 - Test Rolling
2df1ed7a-3f9e-58de-b541-ecf8f1e8736a | note | Ref docs - VR Clause 204.12
faa97184-a15a-5b06-8759-5d9da28419c4 | note | Acceptance criteria - Test Roll in accordance with Section 173.
ed057fd5-5646-5b6a-9feb-760dff8e743f | note | • The Contractor shall provide for the Superintendent to be present during all test rolling.
6ae69317-d944-5705-8af1-20894256f4a4 | note | • Surface shall withstand test rolling without visible deformation or springing.
eef470b0-9d49-5204-8b25-964221af9fb7 | button | Has all of the above been completed? | Yes, No, N/A
97ded3ae-34a4-5064-88ae-58153bfec0cf | note | Freq - Each lot & Each possession
74e0d21d-c552-5dd5-8465-4f0fecfcd990 | note | Key - W S
e140ed56-b79d-53b2-af93-0280d4428121 | note | Resp - SE
d6c70eda-971c-5781-873d-f941dc7d37e5 | note | SI Key - H
b931b56b-168d-5bc5-9b39-66a33171675c | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint-no-value | 3.8.1 - Proof roll if applicable
9af9148c-76ed-5486-a207-1cac2fa80380 | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
d8a339f5-31c1-52e8-8467-959132686604 | textbox | Chainage
f255f7c2-6ec4-5ab2-8b00-7fba0f541756 | date | Inspection Date:
| checkpoint | 3.9 - Maintenance of Cut Floor Level
7759a58f-fb5b-5c17-a11a-775b50759477 | note | Ref docs - VR Clause 204.15
9c3afb80-a414-5352-8f93-ea14a15ec8c4 | note | Acceptance criteria - Visual inspection to confirm that surface is produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
50431e93-6315-5693-893f-b29e79663935 | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
75d270ab-b993-55cd-9ce6-4d9a0ba6fd7a | button | Has all of the above been completed? | Yes, No, N/A
939d98dd-c561-5ca7-8265-ec96bf4ad7fc | note | Freq - Each lot & Each possession
2891a4a3-aaee-5713-80c0-1d501857cb12 | note | Key - W S
331b886e-9a67-5851-bce8-308e774caabe | note | Resp - SE
df1cc46b-ff17-54aa-a7be-bfe093369446 | date | Inspection Date:
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Test Reports
b190ccef-1ea1-5964-b59e-b33ae19a291e | note | Ref docs - VIC Roads Specifications
34232b75-da6c-53e2-aa25-51ae3844ab67 | button | Acceptance criteria - All Test reports received and Reviewed. | Yes, No, N/A
530678c3-b60d-5b84-9051-7a5f5e02cf74 | note | Freq - Each lot
81302774-d031-5f9e-a3af-dfadc79a9982 | note | Key - R
43cb3c08-fa9a-598c-948a-863187ae379b | note | Resp - SE
34b18927-742a-556e-a974-7efc3474d1ce | button | NATA Endorsed Test Reports | Yes,No
2cc51b6c-37c4-584d-b5c2-180fe37846b9 | date | Inspection Date:
| checkpoint | 4.2 - Product Non-Conformance
440ede72-b716-5c21-b481-e8ce125fb51d | note | Ref docs - CQMP
544e2d5c-6070-56a9-b017-a94410256f62 | button | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable) | Yes, No, N/A
d272dd55-8d73-5999-b921-4232ad0bd0ae | note | Freq - Each lot
f12d9070-98c4-5e5e-a9e5-d393f6675078 | note | Key - R
a2764a93-086b-5613-9770-d9e227ba285c | note | Resp - SE
406a12de-d985-508a-acf6-f29296fe8f43 | textbox | NCR No:
25b65892-8b52-5646-87e1-0abb1a91f2ce | button | NCR reports | Yes,No
f9a0dc43-43d6-5f73-bbe1-e392c4d92243 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B REV01 | itp | 1630-P200-SYM-QAC-ITP-0007 Fill Earthworks Type B REV01 |  |  | 3111f2df-fd4d-4607-ba81-ecbd85e8df1e
| section | ITP Details
| checkpoint | ITP Details
f8fa8744-13b2-595c-98cc-5859150f61f7 | note | ITP No. - 0007
d1ea8105-ee7f-591a-8a11-cf1e60ef4236 | note | Rev No. - 01
39a8c9d4-027d-5918-a9d9-4f96876e37ba | note | Date of Issue - 15/11/2023
f7650654-fefc-5b5e-bfb4-1486c27d2111 | note | ITP Type - Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Define Work Lot
118def92-7ae8-52bd-b7c1-ea6f3cef4ac3 | note | Ref docs - 173.02, 204.03 (h) Table 204.142 Quality Management Plan Lot Diagram
083d1f38-9c86-5175-acba-f078f9465f9c | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works.
a87b551f-99f5-5e2e-9c83-fffacbde0053 | note | ○ Lot diagram to be provided clearly marking up extents of lot area.
df6f0577-1631-5a38-b0c9-16f6c114cbaf | note | ○ Work Lot open on TeamBinder.
2407d0e7-d52d-5181-b4d3-0a9dfcebc940 | note | ○ Lot size with no more than one day’s production or a maximum of 10000m² for Type B Material.
81be863e-484c-5078-a26c-f7cc0949fd96 | note | ○ In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
46a738c1-b9ef-55d1-ad30-b8cea37b6831 | note | Freq - Prior to start of works
8f1df7ae-9e76-5ce3-b3e0-e1d5bce4f776 | note | Key - R, S
0ba70a13-fda1-519f-ae37-ba8ef254c996 | note | Resp - SE
b3cf9eb1-9901-5b64-b816-f43b702379a1 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
1c438892-d470-59a2-8974-5505d6f7e239 | tickbox | Lot Map
| section | 2.0 Set Out
| checkpoint | 2.1 - Set Out Survey Completed
b966ac30-4021-58e8-9e25-53ac22743838 | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
ba0c806a-d3c7-541e-84c9-293c5fbc20e7 | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
c2e911ac-2517-550e-b6cf-2ee6d603ead6 | note | Freq - Each Lot
ce35b749-8589-5479-aaaa-09f337926ce6 | note | Key - R
3ae8b7f8-b3ce-5e26-a4ea-1591f1f2da2a | note | Resp - SE
| section | 3.0 Placement of Type B Material
| checkpoint | 3.1 - Underlying Layer Conformance
91bfb728-5fdd-56b5-9e6b-ac3930a0339c | note | Ref docs - VR Clause 204.10(b) Construction Document
98ae63c7-d3ea-549d-a559-f013517b318d | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
ac9f9e30-d565-5a74-9fdf-c652b63fbf0f | note | Freq - Each Lot
40712dda-c500-5516-a3be-ee59d7a2ffb7 | note | Key - H, W
c8fd70c5-d39f-5296-8304-b8ba47b10ce4 | note | Resp - SE
74cdb9ed-6770-53e7-b2a8-6609f5dccd6f | note | SI Key - H
62941524-c285-5027-9c3c-e3c947cef67d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7c85ecca-e400-55e4-9984-6aa85352f368 | textbox | Ref
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Placing Geotextiles (if applicable)
7c0ba699-a638-5e26-b8a7-5e1c5d91cb62 | note | Ref docs - VR Clause 210.05 Table PS3020.071 IFC Drawing
365f91d9-d18a-5119-932e-47785f1bf2d3 | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent.
212572ac-70c5-508f-b9ca-53060fd99d7a | note | ○ Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with imperfections shall not be used.
7ee65017-459d-559c-b479-746fda37da19 | note | ○ All joints shall be overlapped or sewn in accordance with the Geotextile Record.
2f174dd1-5828-59a2-b6eb-a3fb2d21dade | note | ○ Geotextiles shall be covered by filling within 48 hours of placement.
63df42a2-8de3-5d69-a0f4-cb1441ceb73b | button | Has all of the above been completed per standard and approved? | Yes,No
12c0681f-8950-55a5-af8d-bed53a51f43f | note | Freq - Each Lot
c17b1b5c-307a-5be3-b77d-618e417bcd29 | note | Key - H, W
1c49a7b5-13e6-5104-9d8c-e51023541254 | note | Resp - SE
4c4325f5-a2eb-595c-aeb8-4fa5fa196f09 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Placing Subsurface Drainage
44b65fdc-6368-5473-9181-924946fa2b1c | note | Ref docs - 1630-P200-SYM-TPW-RPT-0001 Appendix B – Table 5
4379448b-b6d0-523c-895a-3a8037cefebd | note | Acceptance criteria - Subsurface drainage mat to be prepared in accordance with drawings.
e93b3fa0-8dfe-5d84-97ec-8c2e52a68c6c | note | ○ Superintendent to review and approve prior to placement of any fill on top of subsurface drainage mat.
2114a86e-059c-513d-8ac6-c29e058925f5 | button | Approval to proceed granted? | Yes,No
f1bf0faf-db49-5dfa-aa54-d6a4039fe6f3 | note | Freq - Each Lot
c6f2522f-598b-54ce-9292-02bb59549387 | note | Key - H
bf83510c-aecf-5606-ae1d-5cbe088eac04 | note | Resp - SE
cf84b35b-dc02-502a-9975-c6156c2d6943 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Placing of Fill
d76fb0de-d97d-5ad8-bb27-d9cad57deddc | note | Ref docs - VR Clause 204.10(d)
b43e6d06-8615-5fbf-9c35-94e547b16dad | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm.
2d8a3c83-32fb-5e62-945e-811f84c8e672 | note | ○ Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material.
8a87e1fc-e8f2-5058-b430-c4a92ab6be0a | note | ○ Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
a074bc31-e9e7-5db8-9466-23e5ee89dbed | note | ○ Material shall be compacted at minimum moisture ratio of 80%
a1a2e96e-f8cb-5c9f-8320-4dd0eb3b590d | note | Freq - Once, Each Lot
5e59158b-3225-586c-ba9a-0f1a244dfb02 | note | Key - W
fde104fc-9b01-55a7-9108-bff43d4c61a3 | note | Resp - SE
61ec8746-302a-5135-891f-a68558192f9e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
374ff45d-b49b-5649-ad56-cfa2f559d5c8 | button | Verification Records: Layer Thickness at least every three layers | Yes,No
c69e008c-db4f-59c7-b64b-71ca6339d486 | button | Material Compliance Certificates | Yes,No
3d23b559-82fa-5f67-b168-277a84afb85c | button | VicRoads registration of recycled material blend (if applicable) | Yes,No
| checkpoint | 3.5 - Keyed Fill Layers
c1479262-f6af-5c15-8091-aea0aeeec38f | note | Ref docs - VR Clause 204.10(c), 204.10(d) Construction Document
6ca61033-2d69-5dfe-b061-4ac3da306207 | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
6a5f862d-a29f-5c5d-8c92-8c70cd03c944 | note | ○ Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
3dc0e1e8-ee11-519d-9fd4-64846fc3338b | note | Freq - Once, Each Lot
8e90521c-245d-5507-83d5-0d8399de7d38 | note | Key - W
c146e570-2dc6-55a0-aa24-a0e65def17fa | note | Resp - SE
| checkpoint | 3.6 - Test Roll of Type B fill layer
792691a1-50d9-549a-ad9e-d71d1fcad8dd | note | Ref docs - VR Clause 204.12, 173.03 Construction Document (Test roll Procedure in specification 173.03), 1630-P200-SYM-GEO-DPK-0001 Table 43
e30ea70d-d291-56f5-b3bd-5d448e5de12f | note | Acceptance criteria - Test Roll in accordance with Section 173.
c40976ab-bee8-5fdf-8bba-601ee35a8157 | note | ○ Surface shall withstand test rolling without visible deformation or springing.
9081e08e-8d5a-5a8b-aa9a-79ce66d10adf | note | ○ Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass.
6c01a1c9-acd3-5c73-a51f-c90873cd4759 | note | ○ Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted.
e321340a-98e7-589d-b9de-1295739e3bac | note | ○ The Contractor shall provide for the Superintendent to be present during all test rolling.
53efaa4a-f6f6-509a-9433-a0b7012c9411 | note | Freq - Each Lot
450be4c5-4be5-5b61-b0b9-bbfb0cb0c6e4 | note | Key - H
047c9a27-cddc-529a-b6d4-afbb635459a7 | note | Resp - SE
b2ec52bf-c276-54d6-9e06-15bef1fc0923 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Geotechnical Analysis
| checkpoint | 4.1 - CBR/Swell – Initial Testing
d1345fae-145b-5b0d-af14-74c5227c0a94 | note | Ref docs - VR Clause 204.04(c) PS3020.05 (c)(v)
e7ab7d81-c896-592e-a99b-d0cc763d63c6 | note | Acceptance criteria - First lot tested to determine assigned CBR and Swell:
af2cb4d9-359c-50dd-a958-2d376315462b | note | ○ CBR ≥ 3%
e697266b-9e3a-583d-a9ca-703f6478ac6e | note | ○ Swell < 2.5%
57eed39e-620e-516e-b12b-e8601eb7111f | note | – If swell exceeds 2.5%, the material shall be classified as expansive. Raise RFI and request approval from the Superintendent to use material.
7e3734b0-d44c-5430-8d10-c4df18b361a7 | note | – If both assigned CBR and swell meet the requirements and are approved by the Superintendent, the material will be considered conforming and single CBR and single Swell testing can be performed for future lots at reduced frequency.
ffd92195-084d-576a-8f26-dcf60131aafc | note | Freq - Each Lot
5ef8ba29-032e-54b5-8b18-6f3446dd71a6 | note | Key - R
a234cb9e-7b87-58d2-8d45-8074d4c05cd1 | note | Resp - SE
ec104c8b-2e5e-56e4-82a6-23627efb418d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7c8d6a5c-c7d5-520c-9187-98ae116d19ce | tickbox | NATA Test Report: CBR and Swell
| checkpoint | 4.2 - Compaction Testing / Moisture Testing
02eb49a0-3f89-5637-8bf6-d42b2315dec8 | note | Ref docs - VR Clause Table 204.131, Table 204.141, Table 204.142, 173.04(d) Table PS3020.072
6a9e98f9-e1dd-5121-9cbe-fa3007557e1c | note | Acceptance criteria - All areas of the job will be considered as scale A.
a5e66414-f1c3-501d-b611-fd5fb5a245dd | note | ○ Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
acd96646-20c0-58e3-a7d7-c8045e83f782 | note | ○ Scale B Testing: All other local roads, SUP.
b8d92a8d-0ee1-5320-a7f5-11f9adcbe01a | note | ○ Type B material placed within 400 mm of top of Type B material: 99% (Scale A)
23697983-92a5-572a-bc45-af87969c195b | note | ○ Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A)
b58f0636-5780-500d-b5bf-0f358a1ecf94 | note | ○ Type B material placed within 400 mm of top of Type B material: 98% (Scale B)
21888d3c-e248-521b-90f5-42b79710c920 | note | ○ Type B Material placed more than 400 mm below top of Type B Material: 95% (Scale B)
2d0d494d-5b7c-5382-9e08-7a6a411c9ed1 | note | ○ Type B material is to be tested as per table 201.142. And should meet the moisture content requirements as per VR204.
4aa6d56d-beb9-57e6-88a0-3570fa8a21b1 | note | ○ >70% for any material within 150mm of subgrade.
b2b98428-dd97-5811-a64b-fb707106ce6b | note | ○ >80% for all material below cut floor level.
41c50492-c07b-5a69-a60f-d2a87f8d85d2 | note | Freq - Each Lot
154a462e-4fd9-5e99-bc44-0e3146799eee | note | Key - R
fecfee67-19b2-520a-9fb9-f2baf4385319 | note | Resp - SE
75f2b313-f5d9-54dc-97db-1300381855e3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
3e5eaec9-e150-5e56-bfca-8a30bd2bf364 | tickbox | NATA Test Report: Compaction
| checkpoint | 4.3 - Material Requirements
91711516-3eb4-5285-9027-22158c6e5307 | note | Ref docs - VR Clause Table 204.041
656dd772-c3eb-5a92-a94c-e7a301184e09 | note | Acceptance criteria - Maximum Particle Distribution (MPD) ≤ 150 mm within 400 mm of Top of Type B.
075c9a22-068a-5855-b168-d0f66f2902e8 | note | or
6238986b-343b-5366-ab65-536ab7c8632b | note | ○ MPD ≤ 40mm at depths greater than 400 mm below the top of Type B material.
8da5bbde-fa2f-5469-83f9-0cd1c2c60b65 | button | Have the results been achieved? | Yes,No
0fb5aac0-f2e9-5efe-a460-8085aab74b73 | note | Freq - Each Lot
32510abe-9c73-5d8f-b2b6-fc525f107f26 | note | Key - R
ab7cdec8-1751-5d26-a82f-483b4e2718f7 | note | Resp - SE
| checkpoint | 4.4 - LL and PI Testing
2b11534b-dd36-5037-9ff3-f1139fdc5f81 | note | Ref docs - VR Clause Table 204.141, Table 204.142, 173.04(d)
07b2c680-494b-5073-8655-4f019fb63932 | note | Acceptance criteria - LL and comparison of PI against LL, (identification of silt) is required for Type B Material.
a8d88f85-4863-52ab-a4db-12521899c195 | note | ○ Initial testing is 1 Test per 2 lots.
d2ee1e31-d5db-5692-a5e0-ba24fe40c869 | button | Have the results been achieved? | Yes,No
083e75ba-6f20-51a7-94de-dd8fa834ff0a | note | Freq - Each Lot
25bafed0-1397-5dfd-b81c-13b9050eeda7 | note | Key - R
b734e5dd-56d9-57f1-99b3-6db74c0a4ed4 | note | Resp - SE
8f5c47e6-5054-5fab-ba26-2f4a7634a95e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
8e37c05c-ef25-5030-a7f7-aa705efdfd96 | button | NATA Test Report: LL, PI | Yes,No
| checkpoint | 4.5 - Reduced Frequency - Post compaction testing of initial lots.
b137ed08-3237-5c5e-a85e-de1121d00b89 | note | Ref docs - VR Clause 204.14 – Table 204.141 PS3020.07 (f)
9d76839c-4653-57f7-a334-1876ca64e170 | note | Acceptance criteria - Test initial lot for CBR/Swell.
c930093b-5ebf-54cc-b786-3629569ec4be | note | ○ Test initial 3 lots for compaction.
0c80c9c4-7d1e-5885-bf59-fb003fe99908 | note | ○ Once material and work have achieved the specified requirements in the first test. And;
73a8dd25-f4e8-58a7-b496-ad8351214f7a | note | ○ Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142
9bf9fa44-b1da-5bac-a1b6-4c0abfb8a830 | note | ○ If Reduced frequency has been granted, the testing can be conducted at the following frequency.
a98110f6-eb50-5b93-89a6-4a84044640cc | note | ○ 1 test per every 8 lots for CBR/Swell
5db306f0-c662-574b-a15e-cd77ae2651ed | note | ○ 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing.
8141576a-3dd3-5a52-aaae-c68707239af5 | note | ○ 1 test per 4 lots of LL and comparison of PI against LL.
9cdd27f3-6254-56f7-823f-61f0d0991ccf | button | Has the criteria been achieved? | Yes,No
c09cc300-ed80-5e9b-9e27-4db76bcf005a | note | Freq - Each Lot
ce154a6e-d65e-5c66-8f02-e1956ea32400 | note | Key - R
cba402e4-102d-5d67-81e2-93a583832ba8 | note | Resp - SE
cb9591e2-3ca6-5649-93fd-5bbcea44f37a | note | SI Key - R
db87910b-9d05-571a-beb5-d3ae7e15c897 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
0f9d1667-8309-5197-a370-888356d16187 | button | NATA Test Report: CBR/Swell, Compaction, LL, PI | Yes,No
| section | 5.0 Completion
| checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
1c5e28cd-b7a9-5172-831f-e6eeb8f870fb | note | Ref docs - VR Clause 204.03 Table 204.031
9825c7b4-8b07-5800-a59a-a24f61edc366 | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
e650331a-449c-5697-a402-dd04edaeca4b | note | ○ Scale A: 80 measurements per lot
0a39f398-8347-5ff8-91c6-4028ececdb48 | note | ○ Mean +5 / -15 mm Max Std Dev. 12 mm
a835032b-54f1-5e3d-9bc4-434f31806b21 | note | Freq - Each Lot
301e79f9-cc24-5399-b011-84686b184546 | note | Key - R
14434944-eedb-5e51-8bfd-22f0a0aea0b3 | note | Resp - SE
0dbf9f0a-6b38-5582-ad71-138f1c12aabb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a934f5c7-b50a-5b29-85aa-fad0b05bf9f7 | tickbox | Survey Conformance Report
| checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
7e067f12-75f7-5cb1-998c-30bec7510d73 | note | Ref docs - VR Clause 204.15
87a3287c-1139-5a79-9f05-8820e0e93eb5 | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
4fb2e3d3-112c-5769-a2e0-0987651e0f94 | note | ○ Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
a4f426b2-0b77-53c9-b298-95adbd8fcf6a | button | Does the final product conform to the above criterial? | Yes,No
5948400e-70e1-5ca6-a1ff-bc0bb4eed080 | note | Freq - Each Lot
922db5e6-793c-5502-a517-9305dd6a331e | note | Key - R
3393f966-3760-542d-8d15-4d556b915d5d | note | Resp - SE
| section | 6.0 Work Lot Close Out
| checkpoint | 6.1 - Test Reports
ce82807c-299f-5c13-829c-c5b0eff3a33a | note | Ref docs - DoT Specs
49d8515b-b265-562f-b8e6-91d6c74f91c3 | note | Acceptance criteria - All Test reports received and reviewed
3bf27e6d-f43b-59b4-9907-5e8bed83dcc3 | note | Freq - Each Lot
e697a152-8577-5980-a70d-37375ed5c5a1 | note | Key - R
9cd13a5f-4795-5350-9a28-42e8fcfaa595 | note | Resp - PE
71915dcb-dda2-5fda-999e-98ebbd51f80f | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NATA Endorsed Test Reports
| checkpoint | 6.2 - Product Non-Conformance
1ec5af06-9821-5af1-89b5-593b83f4006e | note | Ref docs - QMP
eb570275-0d0b-5f5c-a1d8-e83ccdd9b69f | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
476bead5-0d47-5aef-a4e9-13a5a8d9041c | note | Freq - Each Lot
713c98bb-7a85-5ff8-9f23-f65a86e0fe92 | note | Key - R
b71c0627-47d9-5241-b70f-d6a32e73a481 | note | Resp - PE
420a6801-3c86-5eeb-8d0e-551023b30772 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NCR reports
| checklist | 1630-P200-SYM-QAC-ITP-0008 Fill Earthworks (Bridge Embankments) REV01 | itp | 16300-P200-SYM-QAC-ITP-0008 Fill Earthworks (Bridge Embankments) REV01 |  |  | b094fd79-7a4e-4ff1-a18e-026a46e28aa8
| section | ITP Details
| checkpoint | ITP Details
baeeddcf-41a7-5da4-b323-515ea44a97d1 | note | ITP No. - 1630-SYM-QAC-ITP-0008
b3500013-706f-51e8-b9ff-dbed333d62a0 | note | Rev No. - 01
fb295979-421c-5e90-87e6-50c14546f08f | note | Date of Issue - 21/01/24
d10c24f3-0daf-5cd5-9f2a-70c4ec4c9bcc | note | ITP Type - Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Define Work Lot
baeeddcf-41a7-5da4-b323-515ea44a97d1 | note | Ref docs - 173.02 204.03 (h) Table 204.142 Quality Management Plan Lot Diagram 1630-P200-SYM-GEO-DPK-0001 5.2.1.4 (Table 43a)
b3500013-706f-51e8-b9ff-dbed333d62a0 | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type B Construction works.
c03d677a-d30d-54ce-822f-39f905a76d9d | note | ○ Lot diagram to be provided clearly marking up extents of lot area.
7aa7fa3d-6444-51d5-ba40-abb020f773c1 | note | ○ Work Lot open on Teambinder.
b8eb5b82-a77b-5511-aeed-48134aa4281e | note | ○ Lot size with no more than one day’s production or a maximum of 10,000m² for Type B Material.
9f49ba8a-a6cd-5773-a460-6388e7422f0a | note | ○ Lot size with no more than one days production or a maximum of 5000m2 for Type A1 & A2 Material.
3a8af651-6667-52fb-9231-f6de886c176e | note | ○ In case of Random level assessments of the surface measurements, the lot size shall be a maximum of 4000m².
fb295979-421c-5e90-87e6-50c14546f08f | button | Has all of the above been completed and approved? | Yes, No
d10c24f3-0daf-5cd5-9f2a-70c4ec4c9bcc | note | Freq - Prior to start of works
1bbd20c9-f001-55d2-b354-22bd94d63a3e | note | Key - R
cafcbf63-9daf-59d0-98cd-260f2ded237d | note | Resp - SE
e7df7c1f-b67a-50c2-a5ce-5fb1fcc5b988 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
0b566460-90fd-54eb-8493-9e9c9b41c365 | button | Lot map | Yes,No,N/A
40027081-9e42-5463-907c-2bdb3d2922b0 | date | Inspection Date:
| checkpoint | 1.2 - Fill at Structures
dc8f5842-0f0f-53f9-bb3b-d473167933dc | note | Ref docs - 1630-P200-SYM-GEO-DRG-1103 to 1105
73979f6f-8f03-510d-a7c3-ea6a1ee6f340 | note | Acceptance criteria - Material type is determined by reviewing the proximity of the fill layer to the future bridge abutment. As per the relevant drawings, fill may be Type B, A1 or A2 materials.
b9e1939c-0136-55ac-baa3-262980ecec34 | button | Material type determined: | Type B, Type A1, Type A2
eee5a9dc-7780-5380-8c99-cba687033fae | note | Freq - Each Lot
611f72f9-f7fb-5334-841f-7233bbbc7ec5 | note | Key - H
943e6a6d-f1b4-5078-8f27-aae28847a6ea | note | Resp - SE
f09828e9-d0dc-55b3-99b2-e1f133707d74 | date | Inspection Date:
| section | 2.0 Set Out
| checkpoint | 2.1 - Set Out Survey Completed
85782c57-ed78-52c6-a981-6830a30f2bb7 | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
185fad8d-707c-5d61-bd03-1ef38c3a12b5 | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
c03d677a-d30d-54ce-822f-39f905a76d9d | button | Has all of the above been completed and approved? | Yes, No
7aa7fa3d-6444-51d5-ba40-abb020f773c1 | note | Freq - Each Lot
b8eb5b82-a77b-5511-aeed-48134aa4281e | note | Key - R
9f49ba8a-a6cd-5773-a460-6388e7422f0a | note | Resp - SE
3a8af651-6667-52fb-9231-f6de886c176e | date | Inspection Date:
| checkpoint-no-value | 2.1.1 - Surveyor Report Reference
30872b16-bc4b-587d-a099-ce2b4ae2d25e | button | Surveyor report reference | Yes,No,N/A
be0952d5-9630-5d63-85c3-702255f515b3 | date | Inspection Date:
| section | 3.0 Placement of Type B Material
| checkpoint | 3.1 - Initial Testing
037f499f-1e0a-5f82-b085-3fd6ba07f48c | note | Ref docs - 1630-P200-SYM-GEO-DRG-1004 VR Clause 204.04(c)
4aa87a10-b419-541e-8585-9fe6bec3b6b9 | note | Acceptance criteria - Type B: The material is to be meet the following requirements:
28201014-63b6-5197-ab93-862b4e07f680 | note | CBR ≥ 3%
30fbd676-4db2-5490-b4b5-ceef330e1565 | note | Swell < 2.5%
d1e3299e-aff9-5b95-a13b-b9952c999494 | note | Friction Angle ≥ 28°
0db61536-930d-56d8-b8d0-ad13e4a0af70 | note | Drained Cohesion ≥ 4kPa
5ac35f56-e773-51f8-863a-5e1e8b137da2 | note | Liquid Limit < 50%
93da59bf-d892-576f-9364-ffd9109856cf | note | ○ If swell exceeds 2.5%, material shall be classified as expansive. Raise RFI and request approval from Superintendent to use material.
691a64f7-1e01-56c2-9656-9009e5301ad4 | note | ○ Type B fill need to be tested to confirm they are able to meet the adopted shear strength parameters.
096c0754-3b46-5492-90ee-1c762cbecbf9 | note | Freq - Each Lot
0f9a3470-853c-5e2f-bfc3-e4a3f7308e9d | note | Key - R
7fd80c6a-456f-5921-a294-4c8fb827f75c | note | Resp - SE
1d440773-bdf0-5e44-8a90-361a259c005b | button | Remarks/record - NATA Test Report: CBR and Swell | Yes, No
3613270f-c4db-5c51-ae14-14182d16f1b7 | date | Inspection Date:
| checkpoint | 3.2 - Underlying Layer Conformance
fb6a3b0b-1703-5ba8-9741-ccee7516ebd0 | note | Ref docs - VR Clause 204.10(b) Construction Document
d3c26377-277a-5521-998e-f7dc906de206 | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
779aa915-8b99-574b-8830-72b2d47727eb | note | ○ Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor, Any unstable areas detected by test rolling shall be rectified.
03917bb0-d9c3-56b2-97ab-8450c6e2dd17 | note | Note for 1st layer:
8f0dbc6d-177c-5594-8b9c-c5220655a0eb | note | ○ After subgrade cut to the depths (or after in-situ stabilisation) nominated in Drawing Nos. 1630-P200-SYM-GEO-1102 to 1105 in Appendix A, or as required by DoT document Section 204, perform subgrade proof roll to assess stability. Results of proof roll to be provided to the Superintendent for review and approval in accordance with the requirements of DoT Section 204.
59e344ce-49a8-52b2-be28-56f6ad046968 | button | Approval to proceed granted? | Yes, No
65bddd2f-798c-5da5-a5c7-8904c6829506 | note | Freq - Each Lot
1a8b7091-9e2d-5bb6-a1d6-1e1155004c84 | note | Key - H
daf4fe1b-9a29-58f3-badb-814d465e620b | note | Resp - SE
923d331b-a583-5487-96e6-00cab7f76071 | note | SI Key - H
f94877ea-f5e8-5ea9-8e5b-3a94f2bfbbf8 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Placing Geotextiles (if applicable)
dccbc20a-0b74-5104-adbe-d683e4728622 | note | Ref docs - VR Clause 210.05 IFC Drawing
9d3303a0-e76e-5261-939c-89d1a9d81653 | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval of the Superintendent.
e7e1c75e-f3bd-5b68-a226-0d8ea3ef5d1c | note | ○ Geotextile shall be placed to the limits as shown on drawings or specified. The geotextile shall be placed without punctures or tears and, if these occur, they shall be rectified or the entire roll of geotextile replaced prior to covering. Any rolls with imperfections shall not be used.
82e1ee0e-1b9b-5289-8a09-708823adf3cc | note | ○ All joints shall be overlapped or sewn in accordance with the Geotextile Record.
0bd8b0ff-7a10-5a43-8a87-aa821d3a1d28 | note | ○ Geotextiles shall be covered by filling within 48 hours of placement.
09fdc6e4-bf00-54bf-b27c-88738cb3f3eb | button | Has all of the above been completed per standard and approved? | Yes, No
086edbbc-46fc-5c59-bb4d-c6acfd60509c | note | Freq - Each Lot
38a2ad61-1109-53f8-bdcf-0693a50afe21 | note | Key - H
8b74504f-ac42-591d-99a0-bc82486410d3 | note | Resp - SE
b7376ac5-18f9-5ec3-90a9-53c56b0738e4 | note | SI Key - H
b7346628-13c1-5c88-a4a5-8629b0ce7775 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Placing of Fill
68e79fd0-82b2-560b-bd30-cb3289737342 | note | Ref docs - VR Clause 204.10(d) 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.4
325aab88-f6c3-5c41-978f-dbd47b06a92c | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm.
95715c8d-3654-5e9e-ac45-a41b803a05a0 | note | ○ No more than 20% of total volume of each fill layer may exceed 37.5mm particle size
c7f137cd-d4a6-5460-919f-67a55374c0c0 | note | ○ Where Type B material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 200 mm thick layer, the loose thickness of each layer may equal 125% of the typical maximum particle dimension of the rock up to a maximum layer thickness of 500 mm. Any rock with a maximum particle dimension greater than 80% of the loose thickness of the layer shall be removed. The material shall be placed and compacted such that voids are completely filled with fine material.
54a0baf6-4a39-5afc-a074-0093a4211f3b | note | ○ Type B material containing rock with a particle dimension greater than 150 mm after compaction shall not be placed within 400 mm of the top of Type B and/or Type C material zones.
5731dcaf-d2ff-5921-b22a-1a324773b184 | note | ○ Placement of fill to full embankment height in lifts of no more than 2.6m per week where monitoring remains within acceptable limits. Hold filling while monitoring settlement and increase in pore pressures. Commence next lift of filling if the measured settlement and excess pore pressures are within acceptable limits.
611c46ff-e0d5-509e-8db4-1a84b8bbccdc | button | Has all of the above been completed per standard and approved? | Yes, No
8ccda2f4-6be2-5b35-b370-d7fadcfc288b | note | Freq - Once, Each Lot
923c9b8c-15cb-5713-be1a-634e77141050 | note | Key - W
c4a1d893-d7d6-5e16-aa04-a772e631aa34 | note | Resp - SE
ad8ffc9d-1fa5-5a29-87c1-aa8aa4eb932e | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
0dc98755-a917-5921-93c4-13dfba029346 | date | Inspection Date:
| checkpoint | 3.5 - Keyed Fill Layers
29f3cc5a-048e-5e9e-9ce7-3274d0389f15 | note | Ref docs - VR Clause 204.10(c) 204.10(d)
ceded3b1-a0d6-5645-b266-f18ee26373ac | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
a7070955-73a4-5528-99a9-03478af814bc | note | ○ Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
f7514e72-2959-5ea5-8d6f-73caa49265d1 | button | Has all of the above been completed per standard and approved? | Yes, No
53e8f420-453a-50f3-b438-438cfd4764cc | note | Freq - Once, Each Lot
4aa30e82-3c78-5310-ac4a-869b0077cec0 | note | Key - W
bdf063e6-5bb2-535d-95e6-2a3a4f4b85f0 | note | Resp - SE
08996005-9398-5568-be80-c5e97fc77390 | date | Inspection Date:
| checkpoint | 3.6 - Test Roll of Type B fill layer
08725ee6-7633-5718-b740-cf0acae5c156 | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
b5729838-e7f3-5c0e-aaee-eccb6e8b4d50 | note | Acceptance criteria - Test Roll in accordance with Section 173.
d74bbc54-5720-5d09-a2fc-2957ec9ad545 | note | ○ Surface shall withstand test rolling without visible deformation or springing.
86d9d439-2ae1-52fa-8864-e4f78d53b7e9 | note | ○ Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass.
3a5da9d3-086f-550c-bd6f-a4d0fbe83d4e | note | ○ Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted.
56a9f366-2230-5c38-a1dd-80ccfc9c6571 | note | ○ The Contractor shall provide for the Superintendent to be present during all test rolling.
0d71b7eb-b99b-5089-8e4b-899d5f98e13e | button | Has all of the above been completed per standard and approved? | Yes, No
0e9c01f3-8e9c-5970-96cf-d0af81e59ac9 | note | Freq - Each Lot
1ce41327-ffbb-5a6d-85f2-244c079a0de1 | note | Key - H
8303747e-fe17-5bac-88d9-289a9646466c | note | Resp - SE
f3577c9b-dd67-54a0-ad51-39aa94cdd8be | note | SI Key - H
6acef1c7-5520-56db-a3ff-83e9daf0fc16 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Compaction Testing
ea2267a2-316c-5ef4-86ca-9ee183e6aaba | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) 1630-P200-SYM-GEO-DRG-0004 (table 3).
4def999c-126d-5c5c-8300-93661d11c62c | note | Acceptance criteria - Type B:
2896cca6-b5ce-5509-84d0-d929a0bbc259 | note | ○ Type B material placed within 400 mm of top of Type B material: 99% (Scale A)
9182a054-3f48-5bf0-ac41-ac010fb90930 | note | ○ Type B Material placed more than 400 mm below top of Type B Material: 97% (Scale A)
08111cc2-16c0-50e6-b0dd-21457dd004e0 | note | ○ All areas of the job will be considered as scale A.
5047887f-45b4-5bb9-832c-88691aed8c05 | note | ○ Type B material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204.
01d1d298-622e-5099-ba2b-24f4ddc43136 | note | ○ >70% for any material within 150mm of subgrade.
b15bef84-73de-5096-afae-2dcd34b2b741 | note | ○ >80% for all material below cut floor level.
7565e91e-8c12-503f-a7ca-951750bafcd3 | note | ○ For testing small areas, which can be for lots where surface area < 500m2. The test requirements are based on the mean of 3 individual tests where the results must exceed 2% or more than would be required for a 6 lot test.
7c425cac-2e51-5297-8383-7ac61c5f99a2 | button | Have the results been achieved? | Yes, No
cbb3fc50-3680-5fb4-bc2f-a97b57b97437 | note | Freq - Each Lot
c6141978-9092-5d98-ba11-9f221fdc2870 | note | Key - R
98038a81-f071-580d-b1f6-ffba6ff405de | note | Resp - SE
faf46499-12d1-50a4-b5aa-adfd9390f599 | button | Remarks/record - ATA Test Report: Compaction | Yes, No
e05a8d6f-615d-5530-bf53-a05ed121f24d | date | Inspection Date:
| checkpoint | 3.8 - Monitoring of Settlement
eb5a928e-1bfb-5263-9bec-daa05fe20882 | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33 5.4.2.2.10 Table 34b
8c56ba21-d1ff-5432-8e70-54e6366643eb | note | Acceptance criteria - The rate of filling lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored.
2310cec2-619d-5253-9a52-e7af482ba99c | note | ○ The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift.
4bd5fb2d-cc78-5583-9312-91cd3adf8150 | note | ○ A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 1m of fill after. During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached.
e0763b59-94b9-50a0-b6f9-345398b11a47 | note | ○ Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals.
4d69a58a-34c3-53fb-8b88-d4ab50ba894f | note | ○ Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached.
00c4c0c2-e395-5927-8ad7-4e2b638ed17d | note | ○ Are monitoring results within the allowable limits stipulated in Table 34b (where applicable for this lot)?
5b3138c6-52b2-5095-a2dd-6ca87387607d | button | Approval to proceed granted? | Yes, No
8fd94d0b-dee7-5341-92a4-c01dfe9c6fc0 | note | Freq - Each Lot
fc9ae3c8-47df-50c6-98bd-3f0d67263249 | note | Key - R
73916675-a39c-5c46-b5fa-8b586be9905a | note | Resp - SE
25fa1044-b75c-5141-aaf0-b89713f2d3a8 | note | SI Key - H
a300aefa-c3b7-559c-86df-3223448fe3a1 | button | Remarks/record - Monitoring Checklist | Yes, No
f1d4e071-77f0-548f-a399-011304f87f28 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Placement of Type A material (Type A1 and A2)
| checkpoint-no-value | 4.0.1 - Incoming Material Docket
8042dd2c-0d34-5eaa-b1ab-cb433bc3479a | button | Incoming material docket | Yes,No,N/A
65889f87-e196-51b3-b0e2-6642f8b2cd2e | date | Inspection Date:
| checkpoint | 4.1 - Initial Testing
fbd21e7e-4028-5f79-844e-f1b84bc15e7b | note | Ref docs - 1630-P200-SYM-GEO-DRG-1004 VR Clause 204.04(c)
f2e2113d-1c22-545f-a26a-9f0d028b6261 | note | Acceptance criteria - Type A1:
6d55f089-e699-5eed-9c3b-f5c64a074e1b | note | The material is to be meet the following requirements:
91b56f81-c7af-59b7-8514-a0dd616effab | note | ○ CBR ≥ 6%
e264b5cd-c50e-5b45-a1f0-b038fbf1de91 | note | ○ Swell < 1.5% (1.0% for verge material)
ee0b7b0f-54ec-5c01-a975-3ac88abf4e01 | note | ○ Friction Angle ≥ 37°
fe436c03-06ca-5403-9bb5-d713999dd30b | note | ○ Permeability < 5 x 10^-9 (capping/verge material only)
4ac5ee9c-6f26-5196-b38b-3bcfa2483174 | note | Type A2:
61e0b1f2-bed3-5e95-be22-1b98c2af9831 | note | ○ The material is to be meet the following requirements:
003b96c1-b733-542c-817b-dba63f85fe7c | note | ○ CBR ≥6% - Assigned CBR testing for new material.
2f6985ff-ca9e-59c3-b385-816713825ecd | note | ○ Swell < 1.5% (1.0% for verge material) – Assigned swell testing for new material
6450467e-6ea3-5ef8-9506-27ae3532480a | note | ○ Friction Angle ≥ 32°
373358f9-3bcb-5cbe-bcb5-65e449cfe170 | note | ○ Drained Cohesion ≥ 6KPA
2b90866e-faa9-5d87-a8db-c9eb2ff139c9 | note | – Type A structural fill and Type B fill need to be tested to confirm they are able to meet the adopted shear strength parameters.
779aa915-8b99-574b-8830-72b2d47727eb | note | Freq - Each Lot
03917bb0-d9c3-56b2-97ab-8450c6e2dd17 | note | Key - R
8f0dbc6d-177c-5594-8b9c-c5220655a0eb | note | Resp - SE
0693a0b4-7e53-53ad-a398-2a8072fc8e86 | button | Remarks/record - NATA Test Report: CBR and Swell | Yes, No
39554bec-2ab1-5bac-977e-b2e1a4d8bf1d | date | Inspection Date:
| checkpoint | 4.2 - Underlying Layer Conformance
99a782de-c684-51e0-82de-fb70a3e90de0 | note | Ref docs - VR Clause 204.10(b) Construction Work Pack (Placement of fill material)
63a8fe1d-3c60-55b3-a1b6-99c8516dde04 | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
fe494730-7214-5c10-afcd-23e1f2c2f655 | note | ○ Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor, Any unstable areas detected by test rolling shall be rectified.
531ee94f-379d-5b41-a7f0-b2f1b937988f | note | Note for 1st layer:
94d4ce8a-f708-593e-bd6e-f9c3a86d5eff | note | ○ After subgrade cut to the depths (or after in-situ stabilisation) nominated in Drawing Nos. 1630-P200-SYM-GEO-1102 to 1105 in Appendix A, or as required by DoT document Section 204 dated December 2015, perform subgrade proof roll to assess stability. Results of proof roll to be provided to the Superintendent for review and approval in accordance with the requirements of DoT Section 204.
e7e1c75e-f3bd-5b68-a226-0d8ea3ef5d1c | button | Approval to proceed granted? | Yes, No
82e1ee0e-1b9b-5289-8a09-708823adf3cc | note | Freq - Each lot
0bd8b0ff-7a10-5a43-8a87-aa821d3a1d28 | note | Key - H
e9d91340-2688-5d1f-a648-80111df275c3 | note | Resp - SE
d6e6613c-e108-5d27-8243-257236843719 | note | SI Key - H
deaa99b3-15c6-5cdb-8bd0-48d734f4b6e6 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Placing Subsurface Drainage
8865d1c2-3b8c-53a7-9180-952c6031c1df | note | Ref docs - 1630-P200-SYM-GEO-DRG-1102
768a8d68-9454-59cb-b33e-47804b79b1b7 | note | Acceptance criteria - Have specified drainage materials been placed at the base of excavation as per drawing 1630-P200-SYM-GEO-1102?
95715c8d-3654-5e9e-ac45-a41b803a05a0 | button | Has all of the above been completed per standard and approved? | Yes, No
c7f137cd-d4a6-5460-919f-67a55374c0c0 | note | Freq - Each Lot
54a0baf6-4a39-5afc-a074-0093a4211f3b | note | Key - H
5731dcaf-d2ff-5921-b22a-1a324773b184 | note | Resp - SE
6f5361bc-7356-5c09-b784-531c857690fc | note | SI Key - H
76df183b-c98c-5731-a261-2605b490c5c5 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Placing of Geotextiles (If applicable)
5beb25b3-6dff-5144-a1af-d36b135bfd6c | note | Ref docs - VR Clause 210.05 IFC Drawing
d922261b-1b13-5972-86e3-7135459d194e | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer.
a10accf3-119c-5a91-8cfe-9eeb83ee88eb | note | ○ Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering.
c0690a73-096b-5484-9c0c-2bd1dacb8578 | note | ○ Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material.
1d8d557a-c11b-534f-8f57-0162db25996d | note | ○ All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
a7070955-73a4-5528-99a9-03478af814bc | button | Has all of the above been completed per standard and approved? | Yes, No
34a82f5d-f281-5fbc-a0d2-94b2458a0239 | note | Freq - Each lot
7bbfce29-d517-5044-aa96-d6ca32e9aca5 | note | Key - H
e25819d6-383c-5e61-b85a-80dc8f93b180 | note | Resp - SE
df9c7beb-f521-5461-b5d9-5ea553a05917 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6 - Placing of Fill
576dad6d-ed75-5e02-ad80-e94abc4c8672 | note | Ref docs - VR Clause 204.10(d) 1630-P200-SYM-GEO-RPT-0001 5.2.1.3.1 Table 43
ad84aad3-37e5-5d3b-b153-4bee28826990 | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 200 mm.
3b4db3dd-c9da-5b2b-a8f8-fa8b13dd2d69 | note | ○ Visual Inspection for maximum particle dimension
33403138-d118-5efb-96da-e6d8fd1c7652 | note | ○ Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than H3:1V, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be not less than 1 m.
2eb11b5c-0f65-5cb7-ba2c-e3a6f71474e9 | note | ○ Placement of fill to full embankment height in lifts of no more than 2.6m per week where monitoring remains within acceptable limits. Hold filling while monitoring settlement and increase in pore pressures. Commence next lift of filling if the measured settlement and excess pore pressures are within acceptable limits.
d74bbc54-5720-5d09-a2fc-2957ec9ad545 | button | Has all the above been completed per standard and approved? | Yes, No
86d9d439-2ae1-52fa-8864-e4f78d53b7e9 | note | Freq - Each lot
3a5da9d3-086f-550c-bd6f-a4d0fbe83d4e | note | Key - R
56a9f366-2230-5c38-a1dd-80ccfc9c6571 | note | Resp - SE
8532109c-e70a-58ff-a180-63e585a15633 | button | Remarks/record - Verification Records: Layer Thickness at least every three layers | Yes, No
2401f632-0b85-5495-b7a4-40a6ecc0ec91 | date | Inspection Date:
| checkpoint | 4.7 - Keyed Fill Layers
1b7c88b9-2e90-56d1-9668-32bad8f1e2d1 | note | Ref docs - VR Clause 204.10(c) 204.10(d)
a62a8e96-7b87-5ab1-b290-0864810f9c6f | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
2aac232d-92e2-5e70-b90b-e07c46c57376 | note | ○ Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill. The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
2896cca6-b5ce-5509-84d0-d929a0bbc259 | button | Has all of the above been completed per standard and approved? | Yes, No
9182a054-3f48-5bf0-ac41-ac010fb90930 | note | Freq - Once, Each Lot
08111cc2-16c0-50e6-b0dd-21457dd004e0 | note | Key - W
5047887f-45b4-5bb9-832c-88691aed8c05 | note | Resp - SE
01d1d298-622e-5099-ba2b-24f4ddc43136 | date | Inspection Date:
| checkpoint | 4.8 - Test Roll of Type A fill layer
26cab5da-18ef-5103-b4d2-e65cb7eef4be | note | Ref docs - VR Clause 204.12 173.03 Construction Document (Test roll Procedure in specification 173.03) 1630-P200-SYM-GEO-DPK-0001 Table 43
fbc3b14d-715a-55e6-9b1f-d8f6ea5a5dba | note | Acceptance criteria - Test Roll in accordance with Section 173.
bd32a4c2-3267-5b74-abd6-cc75ab1a31a2 | note | ○ Surface shall withstand test rolling without visible deformation or springing.
cb07097f-d1ea-581f-9ba2-b1b59e04b248 | note | ○ Test roll to be completed using at least a fully loaded water cart with 8 tonne axle load or 20 tonne gross vehicle mass.
ea7ac573-92a5-5115-be0a-51fb7c9622fa | note | ○ Where unstable areas exceed 20% of the area being considered by proof roll the whole area should be ripped and recompacted.
101648b8-9b82-5d05-9763-e8a50b242c5f | note | ○ The Contractor shall provide for the Superintendent to be present during all test rolling.
57efeebc-e897-52bd-93b6-5f672739a5fb | button | Has all of the above been completed per standard and approved? | Yes, No
4bd5fb2d-cc78-5583-9312-91cd3adf8150 | note | Freq - Each lot
e0763b59-94b9-50a0-b6f9-345398b11a47 | note | Key - H
4d69a58a-34c3-53fb-8b88-d4ab50ba894f | note | Resp - SE
00c4c0c2-e395-5927-8ad7-4e2b638ed17d | note | SI Key - H
b6fb6af0-5a63-5081-8d61-1d1fcc6e82dc | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint-no-value | 4.8.1 - Proof roll if applicable
11a93d5f-0e31-5a34-81a0-601433075af3 | button | Proof roll if applicable - comment reasoning if N/A | Yes, No, N/A
f35f30c1-c3b2-572b-85c2-b9f453adea2a | textbox | Chainage
57a66303-f254-55e7-a0c7-7543903b468a | date | Inspection Date:
| checkpoint | 4.9 - Compaction Testing
be975b40-af83-5fa2-8e7e-13966a145243 | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) 1630-P200-SYM-GEO-DRG-0004 (table 3).
ef950e19-77e9-5b6c-b0ae-d2e0a7126171 | note | Acceptance criteria - Type A1:
1dec87fb-5c4d-5adf-8d97-4be55c06b20e | note | ○ All Type A material: 99% (Scale A)
6ff021ab-13ef-5fb8-b4cb-91ce4f67b695 | note | – All areas of the job will be considered as scale A
c9e4c791-f15a-568c-8f1b-143ffe0480b2 | note | ○ Type A1 material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204.
f560060f-431c-5e51-b19d-01588c88259c | note | Type A2:
74244344-dd2d-5750-93b4-88bba2aa0b7f | note | ○ All Type A material: 99% (Scale A)
300f30d9-1922-559f-a8df-2973cfb44575 | note | – All areas of the job will be considered as scale A
f3c2a874-1f4e-56ae-8c73-91de075702ea | note | ○ Type A2 material is to be tested as per 1630-P200-SYM-GEO-DRG-0004 (table 3). And should meet the moisture content requirements as per VR204.
034bd641-7283-5ef6-b471-5a428558edbd | note | ○ For testing small areas, which can be for lots where surface area < 500m2. The test requirements are based on the mean of 3 individual tests where the results must exceed 2% or more than would be required for a 6-lot test.
e77b42ab-b468-591a-b449-0809f1fd0742 | note | Freq - Each Lot
5031f8e7-0c7e-5262-b8b1-02094c074457 | note | Key - R
f494d407-dbf9-53a1-ab94-ef67aeaddc15 | note | Resp - SE
ffc5132c-f7ef-56d5-bc64-264ebe9e67b9 | button | Remarks/record - NATA Test Report: Compaction | Yes, No
b8324918-b2f1-5d32-a241-4426e37eb72e | date | Inspection Date:
| checkpoint | 4.10 - Fill at Structures (if applicable)
6831449e-3d14-5504-8104-22249941fa9d | note | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
01662495-eddc-5af6-84b7-f3d8b55b391b | note | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer. | Yes, No
1b3377e1-48da-511e-b6b1-c5806332be12 | note | ○ Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
1664bd7d-79b0-51f9-87dc-eef8d5d052fa | button | Has all of the above been completed per standard and approved? | Yes, No
16fffd0c-c5a9-57e7-8c6e-d48850c6c870 | note | Freq - Each Lot
9cc0edf5-d5f3-5c86-bc3f-c307379ec5ce | note | Key - H
59a3d26d-e5a9-5618-a5b5-05f9b0d2521d | note | Resp - SE
7d2e113a-00bb-565a-84d4-746d8ea118fa | note | SI Key - H
e6226276-073c-5073-9b19-0f7d4f194b79 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.11 - Fill within 300 mm of structures (if applicable)
1fbcc455-8d70-51d9-b875-0fae6a5048a3 | note | Ref docs - VR Clause 204.11 Construction Work Pack
2fdc0347-b9be-52ed-976d-1acf013e4a7e | note | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f).
0a4115db-8828-5922-bef7-a06a7644a645 | note | ○ Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111.
c06baa38-c354-5998-a89a-76dea6c4e2fd | note | ○ The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
bfa24cf1-f626-568a-a856-d9edbd35d513 | button | Has all of the above been completed per standard and approved? | Yes, No
43377108-b5fc-5708-ac2a-79804ca9076b | note | Freq - Each Lot
c47b2ec7-1c97-564e-baf0-4c13a29c8a99 | note | Key - R
51e47b72-12b6-5987-b224-7fb39c82104e | note | Resp - SE
6bb2b794-eabd-5109-bc69-9bf494106e25 | date | Inspection Date:
| checkpoint | 4.12 - Fill Material against Concrete Structures (if applicable)
3c0ca7c4-82c7-5d3c-82f1-54091f2cfa64 | note | Ref docs - VR Clause 204.11 Construction Work Pack
c7e606c0-067d-511a-b5f3-c2928b953a8d | note | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
3a44c6eb-98d0-5af8-862a-ea7033481081 | note | Has all of the above been completed per standard?
dd3c5264-5e3d-50b3-b166-848fee617c0e | note | Freq - Each Lot
c5017994-257b-5094-b320-5662a9199c9f | note | Key - R
46cbb0ad-8246-50a7-8fdd-877be25878f9 | note | Resp - SE
490f3ef5-8204-5e6c-b1af-7a0a6b449ed6 | button | Remarks/record - Concrete Pour Recorded | Yes, No
e59d747c-3149-5a2e-b1b5-b6d02c01d1e1 | button | NATA Test Reports: Compressive Strength | Yes, No
289b9754-d91e-5f96-9471-8d6a880897ad | date | Inspection Date:
| checkpoint | Monitoring of Settlement
629f9a01-f70c-519c-baa7-b685cf28cf27 | note | Ref docs - 1630-P200-SYM-GEO-DPK-0001 5.4.2.2.10 Table 33 5.4.2.2.10 Table 34b
32ad9037-9bbe-5160-bc9a-fd25f6fed795 | note | Acceptance criteria - The rate of filling lifts and effect on settlement, lateral displacement and excess pore water pressure to be monitored.
b4015614-6468-51f0-be44-601807054371 | note | ○ The ratio of change in maximum lateral movement to change in maximum settlement should be calculate at the competition of each lift.
0a6e794a-4690-5fae-8edb-a9f1022a671b | note | ○ A minimum of two readings are to be taken immediately post installation and immediately prior to the commencement of embankment construction from the settlement plates, extensometers, survey prisms on culverts, inclinometers, and standpipes. During the construction phase measurements are to be taken when the fill height reaches 1.0m and then every 1m of fill after. During the hold period measurements are to be taken twice weekly and monthly until practical completion is reached.
9fb39d59-f7c1-5f8d-bcf7-90361a0a6416 | note | ○ Vibrating Wire Piezometers readings are to be taken for at least one week prior to commencement of construction. Continuous readings are to be taken during the construction stages with data sent to the logger on 6 hourly intervals.
5fc53012-f8b2-520e-9545-215e4cec8826 | note | ○ Survey prisms installed on bridge abutments are to have baseline readings taken immediately post installation. Following that readings are to be taken weekly for two months, two weekly for the following six months and monthly following that until practical completion is reached.
4c45890c-488e-5329-8965-4d864f078284 | note | ○ Are monitoring results within the allowable limits stipulated in Table 34b (where applicable for this lot)?
bea09a98-752c-5bfb-9959-175460ed24cc | button | Approval to proceed granted? | Yes, No
7ad3d2be-c211-5910-affc-7d2b10fc8b5b | note | Freq - Each Lot
3ffb358d-02f4-5251-b178-10a3e69a1eb3 | note | Key - R
3b775001-0951-5995-b0ad-13df7e431563 | note | Resp - SE
faff4b79-09d3-5b0d-9d5e-f73aa01be478 | note | SI Key - H
c6b8c84f-bbf9-5f1d-9d06-5154e952e703 | button | Remarks/record - Monitoring Checklist | Yes, No
b354d1c1-b15b-5414-b439-40a25a75192d | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 5.0 Geotechnical Analysis (and Material Testing)
| checkpoint | 5.1 - Post Compaction Grading/Maximum Particle Dimension
3c0a14ff-108f-5151-abc8-c4f61d8525d1 | note | Ref docs - VR Clause Table 204.041 PS3020.05 (b), (c)
048abbed-a911-577f-9094-ebada79344f8 | note | Acceptance criteria - Type A:
a137cb3d-90ff-5000-828d-26f0565dcf54 | note | ○ Sieve 75.0mm – 100% passing by mass,
c6c8aa5b-44c9-5d5c-827a-5c22ff621c41 | note | ○ Sieve 4.75mm – 40 - 80% passing by mass,
33ff35bb-f5d7-5e3b-bd0a-139461b1bada | note | ○ Sieve 0.075mm – 10 - 40% passing by mass.
869f5576-2195-53cf-90e9-278d0349e38e | note | Type B:
4a005891-8b19-524c-830a-8500778160df | note | ○ No more than 20% of total volume of each fill layer may exceed 37.5mm particle size
007a9ca8-d729-5afc-beab-6af7c7e0e2fe | note | – Maximum Particle Dimension (MPD) ≤ 150 mm within 400 mm of Top of Type B.
d73f287d-fed5-5594-8534-cbdabf94986a | note | or
8df47f14-240b-56e4-b2ce-0404c2d6210b | note | – MPD ≤ 400mm at depths greater than 400 mm below the top of Type B material.
c879ab91-29f5-52a8-8633-4e35933de44e | button | Have the results been achieved? | Yes, No
07061943-5d0d-524f-9bd5-56e0f0c37792 | note | Freq - Each Lot
d801191e-8de7-5333-a3f3-0d5a863090fa | note | Key - R
3d2f15f3-e996-5513-98fc-4638527613de | note | Resp - SE
62c497d0-260d-5202-9273-578fbda236f1 | note | Remarks/record - NATA Test Report: Grading Visual Inspections for Maximum Particle Dimension
64bebdb3-0995-5306-8395-d4cbd8aeacb0 | date | Inspection Date:
| checkpoint | 5.2 - LL and PI Testing
a6b76dd0-6a0a-5750-9120-0342ab149f2a | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d)
4a32a77e-b144-5c3e-bc70-38c598201db2 | note | Acceptance criteria -
ec249345-1ad8-5cc5-a415-7a95ef9a746c | tickbox | Type A:
3dabf341-8c3d-5eb9-a30a-24adb77cef84 | note | PI: 6 - 25,
9d8f779c-a933-530e-ab2d-15bff7a5774c | note | PI x % Passing 0.425mm: 1000 Max.
c6982f69-adb0-5d50-b124-e874ca3c2077 | note | LL and comparison of PI against LL, (identification of silt) is required for Type A2 Material.
b663b567-252b-5d19-a614-a79855578506 | tickbox | Type B:
7b670f59-21cf-576c-a039-3941e96bd329 | note | LL and comparison of PI against LL, (identification of silt) is required for Type B Material.
bb5bf6a4-18f1-5df0-a8f2-78c9dd1de8b4 | note | Initial testing is 1 Test per 2 lots.
6d55f089-e699-5eed-9c3b-f5c64a074e1b | button | Have the results been achieved? | Yes, No
91b56f81-c7af-59b7-8514-a0dd616effab | note | Freq - Each Lot
e264b5cd-c50e-5b45-a1f0-b038fbf1de91 | note | Key - R
ee0b7b0f-54ec-5c01-a975-3ac88abf4e01 | note | Resp - SE
fe436c03-06ca-5403-9bb5-d713999dd30b | button | Remarks/record - NATA Test Report: LL, PI | Yes, No
4ac5ee9c-6f26-5196-b38b-3bcfa2483174 | date | Inspection Date:
| checkpoint | 5.3 - Reduced Frequency Post compaction testing of initial lots.
400d6a2f-5679-56f3-836e-c342f63256bf | note | Ref docs - VR Clause 204.14 – Table 204.141 RC 500.20
937c3cb2-dea7-5e4a-84bc-af949f28cb74 | note | Acceptance criteria - Test initial lot for assigned CBR/Swell.
b0deeb31-317a-5ab5-95b4-d4ba569136c3 | note | ○ Test initial 3 lots for compaction.
48157eca-4d0f-55ee-b5ce-7afde4acbd1e | note | ○ Once material and work have achieved the specified requirements in the first test. And;
5dcbd21d-3347-54ca-a0e0-e2db2e98c361 | note | ○ Established a compaction procedure to the satisfaction of the Superintendent’s. Symal can reduce the frequency of testing of subsequent lots to the minimum requirements specified in Table 204.142.
18cd747a-8aeb-530e-97f7-1929548a498e | note | – If Reduced frequency has been granted, the testing can be conducted at the following frequency.
4d7897ab-362c-5a73-9023-036b51536e4e | note | ○ 1 test per every 8 lots for CBR/Swell
81f54333-c26e-5dd1-8140-b1bc577caf1a | note | ○ 1 every 2 lots OR every 3rd lot if placed >400 mm below top of type B for Compaction Testing.
fb62e3d3-63d6-50c8-b3d0-8a2d0b696d43 | note | ○ 1 test per 4 lots of LL and comparison of PI against LL.
fe494730-7214-5c10-afcd-23e1f2c2f655 | button | Has the criteria been achieved? | Yes, No
531ee94f-379d-5b41-a7f0-b2f1b937988f | note | Freq - Each Lot
94d4ce8a-f708-593e-bd6e-f9c3a86d5eff | note | Key - R
94e5b8e8-86e7-5975-9b35-7114da3fa858 | note | Resp - SE
0b66f1de-b3bb-5099-8d0d-c9d91f67ffa8 | note | SI Key - R
5adf570c-9cfc-5dff-8c75-804d1693d0aa | date | Inspection Date:
| section | 6.0 Completion
| checkpoint | 6.1 - Conformity with IFC Drawings and Construction Tolerances
737c0b0d-c5de-571d-9be0-99a46701c6f3 | note | Ref docs - VR Clause 204.03 Table 204.031
1f6e8487-94cd-598b-84ec-128216bac7ae | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
44e2374e-cda0-5cf1-bd5b-239af1969b3b | note | ○ Scale A: 80 measurements per lot
635d1e25-3f41-56a6-a5e4-cf6196756f76 | note | ○ Mean +5 / -15 mm Max Std Dev. 12 mm
a137cb3d-90ff-5000-828d-26f0565dcf54 | button | Does the final product conform to the above criteria? | Yes, No
c6c8aa5b-44c9-5d5c-827a-5c22ff621c41 | note | Freq - Each Lot
33ff35bb-f5d7-5e3b-bd0a-139461b1bada | note | Key - R
869f5576-2195-53cf-90e9-278d0349e38e | note | Resp - SE
4a005891-8b19-524c-830a-8500778160df | date | Inspection Date:
| checkpoint | 6.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
3b197c80-e2da-5e6b-a1fe-87e654aca5b5 | note | Ref docs - VR Clause 204.15
b228fc07-8c7d-5ebd-af73-04aa4eb7d0dc | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
68401126-7f25-5fa6-a8d8-2c6ffec79ddd | note | ○ Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
ec249345-1ad8-5cc5-a415-7a95ef9a746c | button | Does the final product conform to the above criteria? | Yes, No
3dabf341-8c3d-5eb9-a30a-24adb77cef84 | note | Freq - Each Lot
9d8f779c-a933-530e-ab2d-15bff7a5774c | note | Key - R
c6982f69-adb0-5d50-b124-e874ca3c2077 | note | Resp - SE
b663b567-252b-5d19-a614-a79855578506 | date | Inspection Date:
| section | 7.0 Work Lot Close Out
| checkpoint | 7.1 - Test Reports
71d9ea9b-319b-51fc-a33d-afa159828aaf | note | Ref docs - DoT Specs
625e9e14-3917-5b1d-905b-0a6e9542d411 | note | Acceptance criteria - All Test reports received and reviewed
44e2374e-cda0-5cf1-bd5b-239af1969b3b | note | Freq - Each Lot
635d1e25-3f41-56a6-a5e4-cf6196756f76 | note | Key - R
28b11944-9860-5341-b674-f06fb0696c01 | note | Resp - PE
9df17621-a5ef-545a-9f8d-dcfdbe9a8448 | note | Remarks/record - NATA Endorsed Test Reports
6f896df5-ec8e-5d8c-88af-8419ed3241fe | date | Inspection Date:
| checkpoint | 7.2 - Product Non-Conformance
65fb0df3-3755-5975-8723-de50dc8cb571 | note | Ref docs - QMP
8e03c6e3-68ba-5630-bc1d-2aa9c5e58523 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
68401126-7f25-5fa6-a8d8-2c6ffec79ddd | note | Freq - Each Lot
6662df44-853f-5879-bf61-87123c081173 | note | Key - R
37ff0ed3-9f40-525d-9884-64a29a3f51af | note | Resp - PE
23aedcba-3e90-5043-a530-8eb9d697ee13 | note | Remarks/record - NCR reports
49f53ce0-3244-5e45-aa04-4c3142917314 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0011 Stormwater Drainage Installation REV01 | itp | 1630-P200-SYM-QAC-ITP-0011 Stormwater Drainage Installation REV01 |  |  | ccc57c69-be54-489e-a816-5f790a03cd1b
| section | ITP Details
| checkpoint | ITP Details
3e3ce95f-8bf8-5295-bc59-4cc85cbd240b | note | ITP No. - 0011
c336aa15-5a15-5e79-bd8e-d8a82bfa0b4b | note | Rev No. - 01
7e103913-b86b-55de-9ff4-e67c042b47b5 | note | Date of Issue - 15/11/2023
0abf54bc-0745-51a4-9ac4-f18f5eeccdac | note | ITP Type - Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Define Work Lot
16fd4093-fa6d-5e73-b618-56fff83fe2fd | note | Ref docs - VR Clause 173.02, 701.20, 701.10, 701.26 IFC Drawings QMP
95e04f64-ceba-5896-8314-cb5bcf3e8008 | note | Acceptance criteria - Survey boundaries clearly define the Underground Drainage Construction works. Lot shall be defined from pit to pit (or end wall, where applicable).
1fd0fc04-214d-5c05-b134-169e09c663f0 | note | ○ Where required; guideposts should be installed at the edges of formations on the side of the culvert nearer approaching traffic.
d7ab89eb-f776-51c7-97fc-fe9a20a5d3ab | textbox | Upstream Pit:
f2067392-be01-5f32-a700-fd8613719e7b | textbox | Downstream Pit:
ab159ed6-7a21-5783-a11e-604bc5bec22a | textbox | Culvert Type / Size / Material:
89307b3d-77ea-51ad-898b-27aba95fcd97 | note | Freq - Prior to start of works
c0163f5a-31c2-54db-885c-e2bba21768b0 | note | Key - R
4c9a7b21-6eae-5c2a-bb2a-702bf8798708 | note | Resp - SE
5aa107b2-bb4a-5b8d-83fb-49f5a1231c76 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Lot Map
| checkpoint | 1.2 - Conformity with Drawings
080dc252-2e49-5831-ad09-d672de136867 | note | Ref docs - VR Clause 701.10
866c5ad9-293c-5f87-95f1-4a8198ef7a29 | note | Acceptance criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
20c50273-24d8-5624-9d41-c60f27f78211 | note | ○ Survey set-out of pegs, line, and height.
036ed14b-3cdb-5675-8907-c09a2d28ba5b | textbox | Drawing No. & Rev:
48b85194-0be2-5bbd-8e07-cd483f8a29a2 | note | Freq - Prior to start of works
4d3baf9b-586e-56cd-8eb4-eb5fa8162838 | note | Key - H
bd5051dc-f932-526a-a366-9cba8bfe003f | note | Resp - SE
3dda4d70-325d-5dca-bfd8-8f764b83696e | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Acceptance of Box Culverts
93e5d39a-79d3-546b-90ee-07b2a486d306 | note | Ref docs - VR Clause 619.22 IFC Drawings
6ebba2b7-98dc-5f82-8243-c347400937cd | note | Acceptance criteria - Complies with specified requirements and free of defects and to drawing dimensions.
f2456663-8bb9-5a61-818b-cfeaecf298b9 | note | ○ Box culverts shall be accepted on the basis of full compliance with the requirements of this section and AS 1597.1.
8f309fae-5d2d-5f40-9de5-b34023a7dee5 | note | ○ Documentation supporting the following quality requirements shall be submitted for review by the Superintendent upon transport and delivery of units to site:
277cb64c-d393-5e89-a628-8001f25d02b4 | note | (a) visual inspection.
6ade5ec2-9f6d-5c40-bd8d-5443aad0ca11 | note | (b) dimensional measurements.
83a8c5e0-ee6f-5d68-a306-3f360950449d | note | (c) measurements of clear cover to steel reinforcement.
7723a69d-e93d-508d-9e27-84cb51154c73 | note | (d) concrete compressive strength test results.
0069b1f7-971a-5bad-b739-e59fa3b77e4f | note | (e) proof load test results.
4768ea23-6396-59a7-8fb2-68d845996930 | note | (f) ultimate load test results.
0129b5ac-e6c0-52d9-9aea-ca6bd67afd2e | note | Freq - Prior to start of works
3b43428c-d809-53b7-bf67-348c54d9e5e9 | note | Key - I
42d16b73-477a-5b3c-a644-e7394e0e9959 | note | Resp - SE
2dddbdcc-d944-504f-b0e3-73b3cbc66282 | note | SI Key - R
cc4a451c-e798-5d8e-ac40-9757abaad1d9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
ff95817d-21ce-5fa4-8ca8-406bf0a2633a | tickbox | Incoming Material Checklist
1307d7b0-b2ea-5936-9148-a6f2caacffcf | tickbox | Manufacturing QA Records
6b28bc90-07dc-55e6-addb-d20d90f3a9d2 | tickbox | Manufactures Compliance Certificate
| checkpoint | 1.4 - Acceptance of Precast Reinforced Concrete Pipes
f3760645-9632-5eac-a0c3-680811e66dc1 | note | Ref docs - VR Clause 701.05, VR 610 IFC Drawing
daa68a87-51bf-56ec-96bf-1bd6f5b25ee8 | note | Acceptance criteria - Precast reinforced concrete shall be of the required sizes and load classes as shown on the drawings.
83b6e420-5b24-5f50-bfe9-c101a685ba26 | note | ○ Rubber ring joints shall comply with the requirements of AS 1646.
6e818570-08dd-5f71-8026-9de123444cee | note | ○ Aggregates for precast reinforced concrete pipes shall comply with the requirements of Section 610
bc4f4ff7-27f4-5ded-b20f-253b27a8b315 | note | ○ Any steel reinforced concrete pipes that have cracks wider than 0.2 mm or are damaged prior to laying and backfilling shall be rejected.
d14a29f6-afe3-5346-9725-13203858b3e5 | note | ○ Documentation supporting the following quality requirements shall be submitted for review by the Superintendent upon transport and delivery of pipes to site:
1ad1220e-1a58-5834-b637-40165faafad3 | note | (i) visual inspection
b2fc190e-9725-5851-89da-2a0fd9571637 | note | (ii) proof load test results
613abef1-1fd5-5c8a-8199-516f579db8d8 | note | (iii) ultimate load test results
0a8895e9-ae2a-57f0-82ac-bcc231369789 | note | (iv) dimensional measurements
dc998a7c-b79d-5ad5-9f34-34748a466407 | note | (v) measurements of clear cover to steel reinforcement
a81315e1-754f-5976-8a96-d25213d5d595 | note | (vi) joint assembly.
0e3bd016-72cd-5f6b-9797-8fa46ca2112d | note | Freq - Prior to start of works
f8dae984-aa41-51fb-a73f-42eb1d471f1f | note | Key - I
5ea6b0f3-9aec-50f0-a7e4-17ea1dbe7af8 | note | Resp - SE
c72c3246-2deb-54b1-889c-1883b16b4d48 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
542d0ce9-48b8-50c2-9fcb-8b7b21c1070a | tickbox | Incoming Material Checklist
c7329e0a-961d-5414-b491-cfe74eb5d452 | tickbox | Manufacturing QA Records
2e05ae16-ed54-5c1e-84e4-862b22319997 | tickbox | Manufactures Compliance Certificate
| checkpoint | 1.5 - Bedding and Backfill Materials
e9971492-c6a4-532a-9b39-de422211eb87 | note | Ref docs - VR Clause 701.09(d) Table 701.091, Table 701.092
1ff60e60-4947-5e17-9275-e3afacc303dc | note | Acceptance criteria - Materials used for bedding and selected/ordinary backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
5d042735-887b-54d1-81ce-e0f7cdefabdf | note | Freq - Prior to start of works
74444e5b-da0b-5a10-bead-cbdd6daf80c2 | note | Key - R
9c72fb1c-ffa6-5c08-8e1b-e21eeed9b739 | note | Resp - SE
23c6a43a-d6ce-5aa5-be7c-6572b8dd485b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
55a6fb20-75d9-57ae-a614-fbb2b53fb548 | button | Bedding and Backfill Material Conformance | Yes,No,N/A
1167504a-8ed7-533d-bdbd-8534874ecf95 | tickbox | Dockets
19e59e9d-26a9-50fe-96e7-5290cf5a70f1 | tickbox | NATA Test Report: Grading and PI.
| section | 2.0 Excavation
| checkpoint | 2.1 - Excavation of Trench
9ff8cca5-1d22-5c02-90e0-9ebd5e7aa40d | note | Ref docs - VR Clause 701.15 Table 701.151, 701.08
e04600b9-ee12-51cd-983c-0fea97b63b9f | note | Acceptance criteria - Excavate to required depth which shall also include excavation necessary to prepare the culvert/pit foundation & provide the full specified depth of culvert/ pit bedding. Maintain trench width clearances as per table 701.151.
a649dc24-9c03-5052-9116-2b2d1a6ec62d | note | Freq - Each lot
66811e2c-d66e-5d83-9d74-1fa57d6d878e | note | Key - I
671db894-c338-5a21-929d-bd466a7a367e | note | Resp - SE
| section | 3.0 Bedding
| checkpoint | 3.1 - Bedding – Layer Thickness
70eaa458-1ed8-562c-87c3-0ca08b6c3964 | note | Ref docs - VR Clause 701.16
30d24b65-e6f0-5499-83da-5e75604bb075 | note | Acceptance criteria - Bedding material shall be provided and placed for the full width of the trench or where the pipe/culvert is to be placed without trenching to a width 0.8 m greater than the overall width of the culvert or pipe. Bedding to be the compacted thickness of
d605a5e8-ed54-5cc0-83d2-1511436d4a35 | tickbox | 100 mm where D < 1500 mm
84163be0-15a0-5c2a-832f-9ba519bf26de | tickbox | 200 mm where D ≥ 1500 mm
8512786e-39a8-5f59-94ed-f851c88b27fe | note | (D = Pipe Diameter/Culvert Width)
b2ee439a-c08e-5267-9776-e59fbfc3167c | note | Freq - Each lot
b030ec9e-519b-5c8d-82db-b56bde38fe01 | note | Key - R
f381fefe-527f-5bb5-ac4e-7bb8098b60d6 | note | Resp - SE
| checkpoint | 3.2 - Bedding Material - Compaction
6e12c65b-5ddf-576c-9314-05cc301bc800 | note | Ref docs - VR Clause 701.20
2c897431-7284-50e3-9237-56e591900c3a | note | Acceptance criteria - Compact bedding to refusal using handheld mechanical equipment.
77921ba9-68a7-539b-8279-605f95af3eb3 | note | ○ If expansive (Swell greater than 2.5%) material is utilised as bedding material, then it shall be tested for its swell properties and have the following criteria met.
328d684f-32ec-59f0-aa27-46c6664f1257 | note | – Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
7640bd2a-db5f-545d-9de8-1ba89ddc5e68 | note | Freq - Each lot
48604a72-b4c7-58b5-bc0c-9a9d74c646bd | note | Key - I
4bf43727-044e-5157-af6f-950f8d5407da | note | Resp - SE
e5112387-7ffb-5050-bd15-74ae2f22c794 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d1d34e5d-e164-5ce1-9502-5f2a013a91fb | button | NATA Test Report: Swell | Yes,No,N/A
| section | 4.0 Installation of Pipes
| checkpoint | 4.1 - Laying of Pipes
c69de127-104a-5c88-b77f-185ce33ffdb7 | note | Ref docs - VR Clause 701.17 (a) (b) AS2566
bba0f3e4-e937-546b-9068-e49f13f9066d | note | Acceptance criteria - Laying of Pipes shall not commence until it is verified that pipe bedding complies with the specified lines and levels and compaction requirements.
81a35443-0121-55ae-8cbc-53704d0c2c6f | tickbox | Approval to proceed?
5a14df36-f74a-54e5-9b34-e8a74ce03560 | note | ○ Laying of pipes shall commence from the downstream end. Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered. The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
9a341a59-0cc5-50fb-9b57-b520513d0e37 | note | ○ All conduits’ joints formed by the spigot and socket ends complying with AS2566
1da8659f-ea0a-5b1e-be25-e426415029ae | note | Freq - Each lot
70f7f238-24bc-5aec-83e6-4e1c9e525056 | note | Key - R
295f00ed-9e6e-5e5e-8385-7f9702d1fc99 | note | Resp - SE
ee9d23f0-ff7e-51a9-a1ab-3822de64c253 | note | SI Key - I
724f7ebc-b334-5974-b78d-e4c802648e79 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
45a39c26-4529-5bd6-bdc5-b46141fb5bd7 | button | NATA Test Report: Compaction | Yes,No,N/A
33a5df16-2d14-51cb-bb38-9b90f1473b8b | tickbox | Survey Conformance Report
| checkpoint | 4.2 - As-built Survey
1967c5a8-dc31-5b26-a8f1-51ad72c705d9 | note | Ref docs - VR Clause 701.10
28915878-94fd-513e-9aac-5ed79b3dab29 | note | Acceptance criteria - The location and grade of each run of underground drainage shall be verified by a survey certificate prior to backfilling the underground drainage.
c6b1d890-da5f-5fe2-a505-e5041ae7cc36 | note | ○ Invert level of pipes at pits ±50 mm
853dabe2-5567-583c-920c-08d22493d437 | note | ○ Departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250.
566f126a-2626-5a28-84a1-49bb978da407 | note | Freq - Each lot
59726324-ddd6-5662-a710-1583466a0d0b | note | Key - R, I
832c10df-9dbd-5f7b-b2f6-054a9b20b60e | note | Resp - SE
c18d9560-4d45-50d1-a3ed-74fd73737a0a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
1ab8311d-709e-5330-9183-ac6f84714241 | tickbox | Survey Conformance Report
| checkpoint | 4.3 - Jointing and Lifting Holes
692616b7-b38b-5579-be76-75b579fe07dd | note | Ref docs - VR Clause 701.18
8b544e13-2a85-5806-b382-d2d884324a84 | note | Acceptance criteria - All interlocking joint reinforced concrete pipes shall be mortar jointed or wrapped with a 200 mm wide external joint rubber band.
e65e3303-6f3f-5039-8dd4-2489b63b78ab | note | ○ External rubber bands shall be manufactured from natural rubber and have a minimum tensile strength of 18 MPa and a minimum elongation of 400% at break.
b2a8a6cf-2708-52fb-82a3-f77e1878ac15 | note | ○ Rubber ring joint pipes shall be jointed with rubber rings. Ensure rubber rings are clean prior to installation.
914bf32e-0357-59a0-838c-1e0589e88f26 | note | ○ Verify joints by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket against the values specified by the manufacturer.
0dfe6c4e-7f98-5409-ad20-c2060d3cac9b | note | ○ Where lifting holes are provided, the pipes shall be laid with the hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
c7e70851-6108-56b7-9761-1893b4a3671b | note | Freq - Each lot
070ac2b2-c7a5-50ea-b14b-c97cfc508bd4 | note | Key - W
1ed411f4-0c3a-5e9b-888d-5ec65c31de5c | note | Resp - SE
3e475d12-fceb-5247-9359-5610acd30e2b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Visual Inspection: Joint Overlap
| section | 5.0 Installation of Box Culverts
| checkpoint | 5.1 - Laying Box Culverts
1ac722dd-1787-5dce-8eb5-21f0e3f442be | note | Ref docs - VR Clause 701.17 (a) (c) (d)
93a60095-9f2b-51c1-b968-f38d39960304 | note | Acceptance criteria - Consecutive sections of box culverts shall be firmly butted together. The top sections shall match to the bottom sections and shall not be lapped over adjoining bottom section. The contact areas between the top and bottom sections shall be mortared.
e44ace2a-cc18-58ea-a48d-b6e07e09cc0e | note | Freq - Each lot
8e2b3b88-1c67-56cf-9997-b8e07ce20ce6 | note | Key - R
f71855bf-2828-5499-aa33-333118453646 | note | Resp - SE
| checkpoint | 5.2 - Mortar
9a277b18-0627-5097-ba58-153324320713 | note | Ref docs - VR Clause 701.09(f), VR610.32
2564b59f-a640-5c35-b8d1-feb169dbf727 | note | Acceptance criteria - Mortar used in the laying of box culverts sections shall comply with the following requirements:
d5dc4df8-cdae-5d81-985f-d21be2f8cdb3 | note | ○ Shrinkage compensating proprietary product.
437bf655-cc9a-5421-9971-4fe700f082cf | note | ○ Min 28-day compressive strength not less than 40 MPa.
1fac3d64-5433-5235-b55e-5ed59645b84e | note | ○ Cementitious grouts shall be min Type C Class dual shrinkage compensating.
4b6759fb-8fda-54b4-a08c-7424f33403ae | note | Testing requirements:
722ffcfa-5d66-5600-90c1-c3c755ae6b70 | note | ○ Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Following (2 x 7-day cubes, 1 x 28-day cube).
205b58fe-e842-5356-aa07-96abcc3dd2ea | note | Freq - Each lot
4f0de09f-e7a7-5b51-94ed-d61c7eb528d9 | note | Key - R
0362f12c-dfdf-54eb-b410-2727a7ea3a41 | note | Resp - SE
93a841d6-92b3-5054-b2d2-98f5819e378d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
60169e5c-0496-5de6-8c74-ae81377ae805 | button | Technical Data Sheet | Yes,No
5620dcae-1f5e-5870-a3fc-19ca4d47b44d | tickbox | Delivery Dockets of Mortar
a7670edd-a5a3-5c96-b7b8-b455a623c25b | tickbox | Compressive strength Report
| section | 6.0 Completion of Works and Backfilling
| checkpoint | 6.1 - Backfill Underground Drainage
ae5e8e2a-8c9e-551d-b72d-55ea41210bbc | note | Ref docs - VR Clause 701.19
01e310d2-804e-5c4d-9f7f-8999aa9d5309 | note | Acceptance criteria - Place and compact backfill material in max loose layer thickness of 150 mm.
7dc6c953-a2b8-5993-bd12-0b02b7227787 | tickbox | (i) Under area to be paved:
c59e6fea-a63b-514c-b798-b2d016d3773a | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
ea993db2-a585-57bc-8b21-0c23de5b24a0 | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
c6079cb4-9fbc-5c60-8776-5eea44e9fa2d | tickbox | (ii) Under area not to be paved:
7fc0a553-2bb3-5e0a-9cb7-6cd1bd2b8303 | note | ○ The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
ff1259b0-e827-5271-a5d7-b392fff7ae40 | note | Freq - Each lot
3f138954-9ea5-5942-b02e-466c6f1580f8 | note | Key - R, I
50369688-9d06-58c2-b606-aead6e387c8d | note | Resp - SE
| checkpoint | 6.2 - Backfill with Cement Stabilised Sand
ad92ef92-0c27-54cf-bc74-e38737df25a8 | note | Ref docs - VR Clause 701.19 (c)
a4318a47-dd46-57a5-9084-c571f819b501 | note | Acceptance criteria - Culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
88f92d79-2cad-5341-92c5-30c13f834b32 | note | Freq - Each lot
7c6091af-8aa0-5f42-a29a-6334aed66aa9 | note | Key - H
ee909513-f5ce-597d-98b3-f3f5b9a8e892 | note | Resp - SE
b73746b1-adfc-503c-81bc-9b7b18ea9b30 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
13b14f83-ee64-512d-aec0-dc3490214796 | tickbox | Delivery Dockets
| checkpoint | 6.3 - Testing – Backfill Material
74d8a171-f66b-53fc-bf90-d590bff6af61 | note | Ref docs - VR Clause 701.29
8a6a1a10-e5b6-5e83-816f-fb2992e388f4 | note | Acceptance criteria - Grading and Plasticity Index– one test per 1000 tonnes or part thereof.
53687fb8-c622-5e58-88cf-664c3b647873 | note | Freq - Each lot
ec378c0c-a587-514e-9ec3-d379afe9b1ec | note | Key - R
83c8edb3-f86b-5450-ad90-384f739ac113 | note | Resp - SE
094b45f0-982f-5aaf-9314-d16ac70cfc5c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
622184ad-a528-5444-ac0b-5240bad47051 | tickbox | NATA Test Report: Grading and PI
| checkpoint | 6.4 - Compaction: Backfill
ba1a4cb8-1f35-5e1b-b01d-8332b9555ca5 | note | Ref docs - VR Clause 701.20
aac7dd7f-c034-517b-a860-5be822930d99 | note | Acceptance criteria - One lot is to be raised for backfill for a culvert length (between adjacent pits or end-walls). 3 tests required per layer and a minimum of 20% of all layers for each culvert shall be tested.
96889c9d-088e-578d-bbfe-b546faaa823e | note | ○ Mean density ratio:
93feb362-9f75-5190-8153-66e4de6d29ae | tickbox | Material nominal size 40 mm or less after compaction: Mean density ratio not less than 97%.
5b81a884-f493-54f1-a7ea-243d61e69813 | tickbox | Material nominal size greater than 40 mm after compaction: Submit RFI compacted using a grading, mixing, watering, and rolling procedure that has been trialled, tested and proven.
fb326c15-acbf-570e-a250-81fcdb3e07bd | note | Freq - Each lot
c40a996b-4955-51f9-84a3-5f447a354192 | note | Key - R
3fb146fa-557f-57b1-8686-2c06713dbb06 | note | Resp - SE
61369b41-9db6-52b8-bf8d-0e68cf829715 | note | SI Key - R
765e03f4-9d76-51dc-bba6-1b0fb3b966ef | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
1f0e545d-4186-5593-ad29-e253e8351070 | textbox | Total number of layers:
7cffae84-0f74-58ed-9a91-bdba7ac94c2b | textbox | Layers Tested:
281dd646-801a-5c05-8ad5-6dbc99a5f3e2 | tickbox | NATA Test Report: Compaction and Moisture Content
| checkpoint | 6.5 - Flushing of culverts
912ca9c1-7801-544d-8545-31d0d15008e0 | note | Ref docs - 701.28
f085ded4-c489-5a20-b6e8-1af7228e1510 | note | Acceptance criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
521351b8-9586-5c59-9905-dfc75d664c18 | note | Freq - Each lot
e71c6fd1-d58a-58cc-8453-73564e5273c8 | note | Key - W
5b975ee3-64a5-5404-9126-21e5b38f18a0 | note | Resp - SE
d0e73ee5-9c80-58f4-842d-f7c8f094a0bb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
e6929ec9-2b1a-58f0-b71a-62f61cfec666 | tickbox | Flush out Checklist
| checkpoint | 6.6 - Existing Pipes Inspection
4cef7833-6210-5399-bb73-cbe47abdf904 | note | Ref docs - 1630-P200-SYM-CVD-DRG-0003
fc8ca1c6-d9f2-5ff1-86db-5b73cfc0cc2d | note | Acceptance criteria - Where existing pipes are to be retained, Symal are to undertake CCTV to confirm that pipes are in a satisfactory condition and clear of silt and debris.
8f85c360-f3fa-52de-8221-1f235029996c | note | ○ If necessary, the existing pipe and culverts are to be replaced.
6bb74065-d44f-59a3-989b-ad74f8089d30 | note | Freq - Each lot
fe51b4d2-0af2-5212-85f5-734048cd0ac0 | note | Key - R
3a3b5b6f-239f-5cb0-82c9-95865d106c50 | note | Resp - SE
| checkpoint | 6.7 - CCTV Inspection
51ce5e30-6631-5a08-bf93-33feee353eb4 | note | Ref docs - 701.30
6d548bef-445b-5ef2-a6b9-7d55f009fad6 | note | Acceptance criteria - All drainage lines constructed shall be visually inspected using CCTV by an independent testing organization for the full length between pits after completion of earthworks to subgrade level and before commencement of pavement construction.
f2f14873-2a05-50e8-b892-0db84951994e | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
19e2a54b-4f6b-5ccf-a416-02dea0c685b5 | note | ○ Upload to the work lot, the report and the CCTV footage. The report shall include a summary of the location of any defects detected by the survey.
a0ae5802-babd-51a3-8500-b5a0d9df3c26 | note | ○ The lot diagram shall clearly identify the length of drainage pipes for which the CCTV footage was inspected.
13412566-05d8-5439-8879-74aff6ffdc0a | note | Freq - Each lot
9bbe85a6-e470-580d-b1d7-67dcfe37ba6f | note | Key - H
7b371bc5-dc36-5edf-8a0c-c63d785662e9 | note | Resp - SE
13acd388-f755-557e-b71c-7fae5476fa6e | note | SI Key - H
abdcd66e-3785-55f5-947e-3762f70e5f3c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
504b2db5-ba77-590f-892f-4361ab468915 | tickbox | CCTV Inspection Report & Footage
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.8 - Repairs to damaged pipes and box culverts
39eb7cce-569a-559d-8b02-b94bcdd8f494 | note | Ref docs - VR Clause 701.31
36fc2b3a-bd55-55a6-b564-b33d18cbbd06 | note | Acceptance criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
1543dca2-8a57-5c4a-807a-383509db6ece | note | ○ cracks wider than 0.5 mm
1d7f8a81-34f3-53e4-8e26-d8ca52deef29 | note | ○ spalling of concrete
742b1b34-1556-5a22-9e1a-4cf19fdccd25 | note | ○ exposed reinforcement
aef16b2d-67db-58ab-a0b9-6edf77d7ce91 | note | ○ joints that are not fully engaged.
b3d14151-ef5a-5997-847f-4762f4c7281d | note | Any pipes with defects greater than the following limits shall be removed and replaced:
20b2bdd6-2aa8-5784-8c23-4c6a2407ee0e | note | ○ longitudinal cracks greater than 2 mm
8fb11054-de76-5dcc-a2d9-7e4cb18a43ce | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
d469ed0d-f9f5-5831-9526-d4015475e243 | note | ○ circumferential cracks around part of the circumference with width greater than 4 mm
7f854e49-6168-50b3-96b8-9f7d64e7064d | note | ○ penetrations with area greater than 400 mm2
b589d879-c61c-56fa-9f06-4d2c5e19e450 | note | ○ pipe joints that are separated.
e2bcb32b-0f80-5afe-86ac-974af0f21891 | note | – Other types of pipes which exhibit defects or are otherwise damaged prior to laying and backfilling shall be rejected.
69e98764-33b7-534e-9aac-b128124d67bb | note | – Box culverts which do not comply with the requirements of clause 619.14 prior to laying and backfilling shall be rejected and removed from the site.
c75d34cd-01d2-5a51-85bf-3436fe820d1a | note | – The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
967305ae-2582-5777-88ba-0738b3fcb862 | note | – No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
39777a74-e38a-54a6-9dfb-34dec45e6c8f | note | Freq - Each lot
18284e39-0fe9-5e19-a3fc-b8974af4a513 | note | Key - H
c9ab4cf7-bfa9-56f9-b9b0-bb87d29ff453 | note | Resp - SE
2f5eaf6b-e132-5250-940b-9f942cfa8b53 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 7.0 Close-Out
| checkpoint | 7.1 - Test Reports
2311a136-2589-5e70-a180-436d1c81d6aa | note | Acceptance criteria - All Test reports received and reviewed
eba56654-932f-54bd-bb78-77d6793a5edb | note | Freq - Each lot
2d6b3d3d-665d-5152-8576-d99cacff51a0 | note | Key - R
2b1afde1-548d-5d90-ab92-9f878ca60bfa | note | Resp - SE
ca18dc2e-5d28-53b6-b2ad-34abfb87c255 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
fe72cfd9-9c04-5a9d-8539-e5c2620ada92 | tickbox | NATA Endorsed Test Reports
| checkpoint | 7.2 - Product Non-Conformance
b9d5f221-0844-51e1-9de1-b7aa9da63625 | note | Ref docs - QMP
13f4479b-6375-5f33-af3f-17a9ea6637e2 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
03e9432f-53c8-52de-9d97-b7465cc02437 | note | Freq - Each lot
3118f282-5953-532d-b8c4-ce1d1d66a834 | note | Key - R
e50b3bf0-4a1b-517c-afa5-9e617469f50e | note | Resp - SE
d29dd7e6-7cb0-5fed-8e93-ef2ddafbfc65 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
82439afd-94fb-5a6b-a166-1a4ce9a9ef2f | textbox | NCR No
fbf85cf0-992c-5b88-b2b7-656fe22bafb2 | note | ○ NCR reports
| checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
e1c91825-eefa-5f48-8354-a57d0aadc5ef | note | Ref docs - CQMP Lot Records
38306f29-5dd2-5303-a65f-2cf12c7eaebf | note | Acceptance criteria - All above criteria met, and records identified attached.
098aa522-9a6f-529c-a844-2850c271edb2 | note | Freq - Each lot
dd1e9391-bc35-59cd-883d-2f5a44b1f846 | note | Key - R
83ac7ba2-8748-5af9-a3a0-54e3c8f37374 | note | Resp - SE
15fc356c-0f7e-5c59-ad4d-539af8f2270d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A REV01 | itp | 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A REV01 |  |  | 7c815c14-dd38-4c3e-885f-4d0e050c79e6
| section | ITP Details
| checkpoint | ITP Details
4899ce53-c870-5fbe-aba0-fbc8647ecbe3 | note | ITP No. 1630-P200-SYM-QAC-ITP-0012 Earthworks Type A
74386f2a-0e78-52c9-a725-726f91b15b15 | note | Rev No. 01
9f6ba596-8d3d-5477-a677-ce80a731e6d7 | note | Date of Issue 01/11/2023
b05f62c2-84ba-586c-ab0a-9f5cdd7384b7 | note | ITP Type - Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Site excavation and Material classification and supply (Site only)
c55496ea-53fd-5c32-90ed-3e941dc6ff68 | note | Ref docs - VR Clause 204.06 (c), 204.04 (b)
8d5cd10f-6bc3-55f1-9b56-3b2a58dedf52 | note | Acceptance criteria - For site-won material: Prior to commencing excavation in any area and during excavation work, the Surveillance Officer and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
68172d3f-14e1-5015-b5d3-aebf0f8c6921 | note | ○ Material classified as silt prior to compaction shall not be used as Type A material without stabilisation to the satisfaction of the Surveillance Officer.
95312752-fd59-5177-97cc-8e2155c957ff | note | Freq - Each Lot
e66e8784-3ba2-5e89-a187-c4498a844e62 | note | Key - H
499f7f2e-ad9a-5a49-871f-d3e324b1f758 | note | Resp - SE
bd7ac52f-5caf-58ba-ae7c-e32f1ea58bdb | note | SI Key - H
7a017d04-486c-5cab-b1b3-60daca10601b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
8e8dfc60-abed-57f0-940b-39499fca5d30 | button | Compliance Certificates/ Test Reports | Yes,No
9976401f-715c-5e10-b5ac-90902b4eccc7 | button | NATA Test Reports: CBR, Swell, Permeability, Grading, PI | Yes,No
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Set out
| checkpoint | 2.1 - Set out and survey land appropriately for intended works.
b453ce4b-5e3f-53af-b716-cfbc1ad5aad5 | note | Ref docs - VR Clause 204.03 (a), VR Clause 204.14 Table 204.142
485ecb09-e2f9-5418-9adc-0a5865b956c6 | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per design IFC drawings. Lot size to be one day's production or 5,000 m2, whichever is the lesser.
a6b1b539-962e-580c-ade7-263e28bb8311 | button | Has all of the above been completed per standard? | Yes,N/A
e4d25c49-d015-57ab-8a44-9f127d524482 | note | Freq - Each lot
fbba7f81-4305-5d82-9428-fde4635d7b73 | note | Key - R
a4135598-bd83-583f-b3d1-c7d959d2709a | note | Resp - SE
| section | 3.0 Placement of Type A Material
| checkpoint | 3.1 - Underlying Layer Conformance
de53b4d7-42b2-5e6b-a835-c495f3eaa7d5 | note | Ref docs - VR Clause 204.10(b) 204.06
2e71621e-01d4-5aa0-8736-08e99a87d343 | note | Acceptance criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. Any unstable areas detected by test rolling shall be rectified.
c958215b-a34f-53ab-ad01-6ff13f3575e3 | note | ○ Where ground water or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
29939a0a-e62b-582f-add8-c783a089a0d8 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
c517dd61-af63-543a-9002-fe5e697a2a84 | note | ○ The Contractor shall not commence playing any fill on the prepared areas until the area has been reviewed by the Superintendent.
e6ff0a67-45c3-56f7-98d7-ad1befb5574c | button | Approval to proceed granted? | Yes,No
a7727933-9ffe-5ce3-8386-aeef7a1d459d | note | Freq - Each lot
323aa496-0845-5cfa-8dc4-118c81a8a12e | note | Key - H
fbae6f05-6144-5ebf-b2b6-c6a603eca7f7 | note | Resp - SE
ee9017cf-507c-5af6-9481-9338b808573f | note | SI Key - H
e93ff2ea-71db-5c3b-a386-8e37c1cec407 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7616017a-f552-548c-814b-651ffa78f71d | textbox | Ref
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Placing of Geotextiles (If applicable)
517683b8-140c-515b-9dc4-c2eb651618b6 | note | Ref docs - VR Clause 210.05 IFC Drawing
6c528777-71db-5fce-9572-166fec6941b0 | note | Acceptance criteria - The placement of geotextile is not permitted without the written approval from the relevant Surveillance Officer.
9026adc5-7043-53c1-b6b0-b6506991f6d4 | note | ○ Geotextile shall be placed to the limits as shown on IFC Drawings without punctures or tears. If these occur, they shall be rectified, or the entire roll of geotextile replaced prior to covering.
ca6e2599-2c17-501b-a898-03d217a165f6 | note | ○ Geotextiles in subsurface drains shall be placed to conform to the approximate shape of the excavation and fully envelop the drainage material.
b34f22b9-fb7e-5000-834b-461b8854a4d4 | note | ○ All joints shall be overlapped or sewn in accordance with the Geotextile Record. Geotextiles shall be covered by filling within 48 hours of placement.
9071ce16-e3e9-5c7d-a8be-f4e2b203975d | note | Freq - Each lot
860492a3-a25e-546f-8519-8057fa576f41 | note | Key - H
8d5ca5ef-72a3-513b-b944-9ad78164baa5 | note | Resp - SE
44019ccd-f545-53e7-9f2b-bc49618d7519 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Placing of Fill
491730d0-800b-5504-870b-1da5d5e32186 | note | Ref docs - VR Clause 204.10(d)
d14d52d0-da24-5e4a-b30f-353b2e4ddadd | note | Acceptance criteria - Spread and compact in uniform layers not exceeding a compacted thickness of 200 mm.
f9d6b7df-4775-5d8b-9080-297cb7deab3d | note | ○ Visual Inspection for maximum particle dimension.
34b5672f-c9d8-5d88-a8cc-f2067f7a2446 | note | ○ Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4H:1V, benches shall be progressively cut
e879b056-4aa9-5f35-a05b-5370c7cc415c | note | Freq - Each lot
573a220e-e621-5d68-a508-1852c38b3344 | note | Key - R
97cc3f8d-9844-587e-b1c7-68f7c8993793 | note | Resp - SE
c306390a-ee5d-5b38-86cd-a4c152f038e0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
71a6fdcd-cea2-563f-b52e-4d060f7f0029 | button | Verification Records: Layer Thickness at least every three layers | Yes,No
| checkpoint | 3.4 - Keyed Fill Layers
844cfb8b-0fd3-537c-bfa3-e08ec72b6405 | note | Ref docs - VR Clause 204.10(d) Construction Work Pack
624850d0-be2c-54fb-a047-7dccfaa0a41a | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
ce5be331-73d3-550b-a5bb-4be0a605bed3 | note | Freq - Each lot
28847810-fc67-5410-8113-25b736b308e6 | note | Key - R
76c2b7dc-3689-5b8f-80fd-4a2d97ac6d8b | note | Resp - SE
| checkpoint | 3.5 - Test Roll of Type A fill layer.
5b680f9d-00ec-5e49-89ba-c0c84e67682c | note | Ref docs - VR Clause 204.12 173.03 Construction Work Pack (Test roll procedure in specification 173.03)
2a81a371-0149-59be-b302-5e41b0d20cf6 | note | Acceptance criteria - Each layer should be test rolled immediately following completion of compaction but if test rolling is carried out at a later time the surface of the layer shall be watered and given a minimum of three passes with the test roller prior to commencement of test rolling.
c3c95374-84e0-5591-9202-7edf12b25977 | note | ○ Surface shall withstand test rolling without visible deformation or springing.
7d736c5a-6fd1-59f8-9f6d-c0b8833a6ed1 | note | Freq - Each lot
91f3743a-5aa2-5a36-85ca-61069548c53d | note | Key - H
d5024776-0401-586b-81a0-0ddefd057ed7 | note | Resp - SE
550d1ab2-2499-5a8c-b0ec-398164519437 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Fill at Structures (if applicable)
4a15c94e-89d5-5102-8dd4-0eb2c8df9785 | note | Ref docs - VR Clause 204.11 (b) Table 204.111 Construction Work Pack
f78852ab-8bb0-5afe-9fcb-dc850bbd6249 | note | Acceptance criteria - No Fill to be placed within 3 m of structure until the foundation is reviewed by the relevant Surveillance Officer.
7b6c43d6-f0e6-5d85-9ab5-58bac61d2c0b | note | ○ Culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
bb538ba0-e24b-5fb3-a439-5ecc164f2744 | note | Freq - Each Lot
9c84ded7-3dac-5e9f-9478-c07fdac94353 | note | Key - H
be3a3b5f-eb01-505f-b982-4c9a1f3bbaa9 | note | Resp - SE
e2f3690f-effc-5c3d-97a4-bd03f683676d | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Fill within 300 mm of structures
55d9a68c-9377-5729-9f65-ce505be01654 | note | Ref docs - VR Clause 204.11 Construction Work Pack
92b37372-2f5d-58a5-9cc4-f46f0abe7e62 | note | Acceptance criteria - Use of geo-composite drainage material or Permeable Fill in accordance with 204.04(f).
52a35d68-0503-5be6-a89e-dd56807c2f77 | note | ○ Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111.
b7991812-4084-5cf5-bb9d-ad72e5a3e014 | note | ○ The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
2005eb48-7c23-53f3-97f3-f62bad10a64e | note | Freq - Each Lot
8d5d077c-19a8-563b-a508-596c2627be43 | note | Key - R
6a27d4e2-8cf1-542c-aff6-b84704b2598a | note | Resp - SE
| checkpoint | 3.8 - Fill Material against Concrete Structures
fb127a0e-ee1e-5a99-bf4a-66c86797149d | note | Ref docs - VR Clause 204.11 Construction Work Pack
b86bb90d-0172-5e7a-90c8-6382aafb469f | note | Acceptance criteria - No material shall be placed against concrete within 14 days of casting.
1ea63c1a-a90b-5b30-925f-d818ee966b66 | button | Has all of the above been completed per standard? | Yes,N/A
ddbaf68f-f205-553b-ab30-8f739d19a8df | note | Freq - Each Lot
d89df0a5-a2a9-52a6-8b82-491c94b6367b | note | Key - R
59c05abb-2e3c-5683-90e7-283cdd44b205 | note | Resp - SE
a469b20e-3ea3-5546-bf30-ced93e4afed9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c9fb92f7-e0e1-50b8-83f5-2503cd3e82fe | button | Concrete Pour Recorded | Yes,No
7cf77dd9-5130-5523-b1eb-f7ad6d466f0c | button | NATA Compressive Strength | Yes,No
| section | 4.0 Geotechnical Testing
| checkpoint | 4.1 - CBR / Swell
e4e2bb80-bb5b-5839-9927-9d757372f611 | note | Ref docs - VR Clause Table 204.041, 204.141 Table PS3020.051
2c6cecff-e831-592d-b071-c3a039666011 | note | Acceptance criteria - Unless otherwise specified:
384cf521-0d80-5d30-b217-20fa4948015f | note | ○ CBR: ≥ 6%, Swell: ≤ 1.5% (1.0% for Verge Material).
64fb6347-cf20-55f6-a48c-ee1e76e2159b | note | ○ Initial testing frequency: 1 Lot test to determine Assigned CBR and swell.
097bc6ab-f57b-5bb2-897f-b7f82051fda3 | note | ○ Continued acceptance of the material will be assessed against the Assigned CBR and percentage swell values of a single CBR and single percentage swell test.
5a532c9c-98d6-56d1-885b-20e0e6608e3b | note | ○ However, if the material fails single CBR, swell testing then another assigned CBR to be conducted.
fdb0b4b2-8f1b-598f-a526-942a4088dcc3 | button | Have the ideal results been achieved? | Yes,No
d55c4578-9cf9-52bf-81a9-7f386f459d94 | note | Freq - Each Lot
0ca1eaff-cba9-5df0-9801-674d53303fc5 | note | Key - R
f0a79d01-b9fc-5ee6-8c9a-42f334ea1ef4 | note | Resp - SE
37b70c7c-d602-56fb-896c-8f38c1ad7d2d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bfde03e9-d161-5c20-9b9c-5d98df25dfba | button | NATA Test Report: Assigned CBR, Swell | Yes,N/A
9dd004d9-eb2c-59b0-9569-bdf80144e3b9 | button | NATA Test Report: Single CBR, Swell | Yes,No
| checkpoint | 4.2 - Post Compaction Grading
c04d6b9a-291a-569e-b9c0-dde17178aab1 | note | Ref docs - VR Clause Table 204.041
6bf075e7-48aa-5650-9b3b-57906bee5db6 | note | Acceptance criteria - Sieve 75.0 mm – 100% passing by mass, Sieve 4.75 mm – 40 - 80% passing by mass, Sieve 0.075 mm – 10 - 40% passing by mass.
86ffd096-ffcd-5d57-8511-2c2e1f91377e | note | ○ Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
233e309a-7324-5979-ad22-1f2f97486b10 | button | Have the ideal results been achieved? | Yes,No
2edf02e2-f682-5830-9d40-e546c1fe024e | note | Freq - Each Lot
0cdb54af-aebf-53e3-a569-cc42d8dfc039 | note | Key - R
80c0462d-e94a-57cf-93fa-7aacac5f9aa8 | note | Resp - SE
6e36a9c1-0550-5f01-bf74-623432e0d184 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
da81bb8f-b912-5f83-a33f-aba39ccc98e5 | button | NATA Test Report: Grading | Yes,No
4f921d43-819a-5adf-b701-fa5a0b308fd9 | button | Visual Inspections for Maximum Particle Dimension | Yes,No
| checkpoint | 4.3 - Plasticity Index
02a5c7d3-7e98-5822-90e6-2185ae28e484 | note | Ref docs - VR Clause Table 204.041
cb67eb90-f1c3-5da0-bb27-c9c51dd35947 | note | Acceptance criteria - PI: 6 - 25, PI x % Passing 0.425mm: 1000 Max.
6565bd8d-71a6-5b42-9b13-2bf2f5ebfe8b | note | ○ Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
d6e43935-a479-52ff-a86f-d7bf04fe3ac8 | button | Have the ideal results been achieved? | Yes,No
dc8abee3-e319-5863-92f0-9b5d640eee60 | note | Freq - Each Lot
f2eb5c2a-3265-5c75-9654-d8efaf836d95 | note | Key - R
6cad01b9-3fd0-5149-a365-6029b0cfddd8 | note | Resp - SE
b2d67e5b-4bca-5b58-9c11-d9a9eb9a99a4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9fc6d8de-851e-5a65-9a92-64e224c3eb5f | button | NATA Test Report: Atterberg Limits | Yes,No
| checkpoint | 4.4 - Permeability (Capping & Verge Material only)
4361c771-3c87-5971-b017-a4a652362271 | note | Ref docs - VR Clause Table 204.041
f506c5a9-0c59-5459-8f36-12a177cfae2a | note | Acceptance criteria - Permeability: 5E-9 m/s
381402e1-8fa5-548c-a4b7-66e0ba13e56b | note | ○ Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
2fb8427f-ef46-51d2-a393-c2c6eb628e98 | button | Have the ideal results been achieved? | Yes,No
37b2dc22-1f73-56d2-8edd-793b3d261b69 | note | Freq - Each Lot
0b355fba-ab49-5c73-a437-cccba626610a | note | Key - R
175826c1-67be-5800-9205-f316537b4f34 | note | Resp - SE
4cbd428e-f765-5f1c-a9a7-cda1c5024323 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bd5abf8d-9e1a-573d-a1e4-17aa3abb461d | button | NATA Test Report: Permeability | Yes,No
| checkpoint | 4.5 - Compaction Testing
3bb93d5c-4278-55a0-ade5-e34cd4815c1e | note | Ref docs - VR Clause Table 204.131, 173.04(d)
4394a7a6-2843-5d6d-867c-b72a35adf1b3 | note | Acceptance criteria - Minimum Characteristic Value of Density Ratio: 99% (Scale A), 98% (Scale B).
66367898-9ad9-5ed5-b415-135a9849fdd0 | note | ○ For small areas (<500 m2): Mean value of density ratio: 101% (Scale A), 100% (Scale B).
ed9a9627-345b-5ac7-911d-e20e7ad3ddf4 | note | ○ Initial testing frequency: Each lot until 3 consecutive lots meet compaction requirements.
036fea84-e1bb-5064-a34b-cada55aff1c1 | button | Have the ideal results been achieved? | Yes,No
5b1169f9-6c3f-5add-b828-febcbce4bd51 | note | Freq - Each Lot
51cc4b1d-6809-5c90-9e96-38e7532d9b7d | note | Key - R
2bb7b8f9-6fef-50c4-ae19-b52333a8e265 | note | Resp - SE
949dc06a-19a3-501d-93bf-3d0c39594601 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
0517d04e-2b24-511c-897b-aeb529a4f49f | button | NATA Test Report: Compaction and Moisture Content | Yes,No
| checkpoint | 4.6 - Reduced Frequency of Testing
18b16e37-f576-500f-91e5-2bbf125518ae | note | Ref docs - VR Clause 204.14 – Table 204.141
30b35df1-b429-557e-8efb-033d1fd5bef9 | note | Acceptance criteria - Unless otherwise specified:
75a9f66d-a45d-50dd-a5f3-839975ca4e78 | note | ○ Material properties (Scale A): Test at the initial testing frequency, if compliant, seek approval from Surveillance Officer for minimum testing frequency.
d2c37334-b878-5436-abf5-411b4b28c727 | note | ○ Material Properties (Scale A): CBR/Swell: 1 test every 2 lots. Grading: 1 Test for every 2nd lot PI: 1 test every 4 lots
57587ab3-1fbf-5157-98b9-6e871d7a7c61 | note | ○ Permeability: 1 test every 4 lots
3dc7dc17-3997-564a-bd25-1717d74f1053 | note | ○ Material properties (Scale B): Test initial lot and no further testing required until changes in physical property/material source are observed.
33ac273f-7fbd-597c-8cc4-ceee6094d8f8 | note | ○ Compaction / Moisture Content:
0c6a668f-72eb-5b9b-84b3-3c8c340808a9 | note | ○ Reduced frequency: Test every 2nd lot.
54ab2914-e902-5a8e-93b3-073829ebd1f3 | button | Have the ideal results been achieved? | Yes,No
b484ce44-83b6-5fe2-8a13-cf501fce6726 | note | Freq - Each Lot
dbc0ad55-5325-5778-8ac1-b44f1aa701be | note | Key - R
7f058a0e-e373-5a07-a95d-5927fd68e41b | note | Resp - SE
3fe40537-ccc6-5183-b500-431a045e03cf | note | SI Key - R
0559c0d8-8056-5f7c-9ad2-34fcc821cfca | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
94ab9934-0e0c-5f5c-9583-03e30d679de3 | button | NATA Test Reports: CBR / Swell Grading PI (Atterberg Limits) Permeability Compaction | Yes,No
| section | 5.0 Completion
| checkpoint | 5.1 - Conformity with Drawings
625cbc8f-1289-5cfb-ac58-a5023f4822ed | note | Ref docs - VR Clause 204.03 Table 204.031
2791355a-cc34-5ff3-b9e0-8ca73c1bc53c | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings with the following requirements.
bddca4c4-7de7-5378-994c-0e01957c64e5 | note | ○ Scale A: mean +5 / -15 mm Max S 12 mm.
b4765b0c-7925-5180-a7da-b710a298cba1 | note | ○ Scale B: mean +5 / -25 mm Max S 15 mm.
3eb74f90-1dd6-5a22-ae18-f68634536a7b | note | ○ Alignment: ±50 mm.
28b307ef-dcf9-5fa6-b27d-35a7e96b0609 | note | ○ Scale C - random levelling not required, no point > +10 / - 30 mm.
ea8d827a-6e8f-5fbc-b7f3-3955c19156e1 | button | Does the final product conform to the above criterial? | Yes,No
bb074275-82c8-596a-98f7-bdc8a5cdfda9 | note | Freq - Each Lot
5a4ce6ed-fe29-5100-899f-5fef431f7d54 | note | Key - R
2342d557-944e-5e6f-8f8a-fdc5cbb21645 | note | Resp - SE
| checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
9573e644-2c84-5796-bb0e-d0ae9f888e40 | note | Ref docs - VR Clause 204.15
84c83fc4-3b37-5db4-96cc-3c368767e759 | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
acde3ba7-960a-55cb-8260-1b9ebfb50eba | note | ○ Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
fbbfb24c-b075-56ec-8f42-80e04337c89d | button | Does the final product conform to the above criterial? | Yes,No
fa67be75-3bec-522d-bf9f-810942ca5262 | note | Freq - Each Lot
57573743-0620-5b0f-a432-e53eec370f66 | note | Key - R
3d72a598-6180-50af-825b-d4a4fad49ee7 | note | Resp - SE
| section | 6.0 Work Lot Close Out
| checkpoint | 6.1 - Test Reports
ac51daff-1b14-5c19-9c75-cf30f09f6da2 | note | Ref docs - VicRoads Specifications
8400ef24-63dc-5394-9210-0696a7ffb93b | note | Acceptance criteria - All Test reports received and Reviewed
c03e5b29-c83f-593b-8e62-aa205c44f072 | note | Freq - Each Lot
bc1e1520-00be-5cfa-ba1d-0b8b2b6425fc | note | Key - R
8c1ab3aa-2579-524d-b969-c0500f4e4af8 | note | Resp - SE
083af6a6-3b65-5bc0-95c6-21ffe0fa3253 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d35f31fa-2596-5eb6-8651-db3126ced243 | button | NATA Endorsed Test Reports | Yes,No
| checkpoint | 6.2 - Product Non-Conformance
8aa81ef9-fb99-53bb-9e4b-6c5655e7ea92 | note | Ref docs - CQMP
4e485263-54e8-5db5-b104-bd64e1e7aaa8 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
09e44aec-113e-54e4-a5de-bc16de19f09a | note | Freq - Each Lot
43847dff-4992-542c-90e2-70a02fe5d2c0 | note | Key - R
1804ba8c-f424-544a-a7ef-c63d6eab25a5 | note | Resp - SE
e36df632-a082-5914-8a9f-3984d64d2907 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7ade5e9b-3bf0-531c-a97d-b302a6a3e48b | button | NCR reports | Yes,No
| checkpoint | 6.3 - Quality Representative to check the above criteria and records to confirm
fe374904-5a69-57e2-b370-d4f56b72facc | note | Ref docs - CQMP Lot Records
c93199b2-2b4b-5eae-af20-bff84ae38688 | note | Acceptance criteria - All above criteria met, and records identified attached.
2c557fae-5377-5383-800b-41f3c53699bb | note | Freq - Each Lot
bb021243-1cee-5860-902c-574fb7c16984 | note | Key - R
c129bc26-8282-5237-b661-bf96fa0aceb9 | note | Resp - SE
189897c5-c529-53a0-91d8-014a5d7ada9c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0013 Subsurface Drainage | itp | 1630-P200-SYM-QAC-ITP-0013 Subsurface Drainage |  |  | f2d3d3ba-04aa-4fb7-88d1-d230b4fdf57e
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Procedure for method of compaction and placement of no fines concrete filter material
f91c4160-0901-5ff0-84dc-a01402165585 | note | Ref docs - VR702.09
baf26de6-f23c-5528-ab0f-0aeb0cb4c2fe | note | Acceptance criteria - The method of compaction shall be in accordance with the Contractor’s quality procedures and shall be submitted for review by the Superintendent.
7c40b4fa-1629-59a8-96a7-88137761989f | note | Freq - Prior to start of works
a819febb-b549-5ecc-bdf0-1472f4aed0fd | note | Key - H
f51c384c-1295-527c-94f7-74760bb6bc44 | note | Resp - SE
c7f819e0-781f-53a1-b6b5-003f52b7bf2c | note | SI Key - R
8580071f-66d5-53ab-9a24-aefce84bfb87 | note | Remarks/record - As per approved Construction Document
94ebb247-6372-532a-bacb-12916f3e8d67 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
47ea718a-9139-5084-860d-d61fe2a4b303 | button | Lot map | Yes,No,N/A
59291681-34b5-54fc-97c2-46050f528754 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
c6c85b1f-bd88-5b7d-ab61-320bb0242f3a | button | Environmental permit | Yes,No,N/A
67223c57-d86a-530a-ace3-8846eb9a43ba | date | Inspection Date:
| section | 2.0 Materials
| checkpoint | 2.1 - Supply of Pipes & Geocomposite Drains
8f7feb94-1e20-503f-80a9-464aabb7aa7a | note | Ref docs - VR702.04 PS3030.05 IFC Drawings
cf4f7680-b046-5462-bd22-538d537a9831 | note | Acceptance criteria - All subsurface drainage pipes supplied shall be Category 1 (Class 1000)
273d6d78-1063-5fbf-bbbb-59ed1dfbdce5 | note | • Perforation size must be a maximum width of 1.5 mm and a minimum length of 150 mm per m2
ac1cebec-1090-5106-8541-42a4bd3543c0 | note | • Plastic pipes and geocomposite drains shall be handled appropriately to reduce sunlight exposure during delivery, storage, and installation.
614cbcd9-5e0e-5a02-aaf7-ed818f827c33 | note | Freq - Each Lot
ce6a6110-e5a7-5ad4-8143-0e600ede901a | note | Key - R I
0b5476dc-1756-5c17-b07a-6565e21cdd00 | note | Resp - SE
97e5a096-2c3a-5d9c-a980-ccc89c03ee38 | button | Remarks/record - Manufactures Compliance Certificates (AS2439) | Yes,No
eeab3f9c-cfbf-5131-bcbe-d01fa4e73256 | date | Inspection Date:
| checkpoint | 2.2 - Supply of Pits & Flushout Risers
ec9d882f-aaaa-579c-a3f6-e5370a651b6d | note | Ref docs - SD1631 SD1611 PS3030.5 IFC Drawings
151e6603-94c4-5a87-8b11-ba064be9a25f | note | Acceptance criteria - Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
3ae307c4-e1e8-5a40-8e2d-9760a3071c98 | note | • Flushout risers shall have surface fittings as shown on the drawings.
77b32c0c-1d36-5a2d-9a66-e5198ee404f7 | note | • Pits shall be supplied in accordance to SD1611.
38168700-4b13-534f-affe-b942331ae85d | note | Freq - Each Lot
114cc5da-9d61-51c0-94d4-65f9a4d2e2c8 | note | Key - R
683e20dc-f300-5288-82a7-d63a2f4e6daa | note | Resp - SE
07491c3d-4a88-5428-a91a-5330a038a49c | button | Remarks/record - Supplier Compliance Certificate | Yes,No
59a57c73-f745-5b0a-bcbf-0ae0d9c6138f | date | Inspection Date:
| checkpoint | 2.3 - Granular Filter Material – Sand
3811133f-0710-5ad4-9f62-2440cd05d933 | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
1a2aaf02-1b0c-534a-ac5f-b810c5b7abcf | note | Acceptance criteria - Granular filter material must meet the below requirements:
971b6d87-a765-5b8a-8084-12ad0e12e63f | note | • Grading: As per Table 702.051,
f3242474-0e4c-52cb-91c3-a2b386631e93 | note | • pH: 6.0 – 10.0.
3c9df138-e52c-5e6d-918c-b33d8a3e3c2f | note | • For glass fines: be thoroughly washed and retested prior to use, where the measured Total Dissolved Solids (TDS) of the granular filter material exceeds 1500 mg/L.
af0da553-1d01-5b9f-8e68-f87b83693fa3 | note | ○ pH and total dissolved solids (glass fines only) must be tested at a rate of one test per 5000 tonnes of product.
88af118c-2df4-5ab4-81ac-6b8df59be9ef | note | Freq - Each Lot
d358e849-b700-59e5-940e-36d5c7a3096b | note | Key - R
9567219c-eff3-5084-8596-0b2350b26097 | note | Resp - SE
07528748-56e8-59fc-b9c0-24769d992cb7 | note | SI Key - R
60df4f2c-a2a9-5302-91dd-4b443ad6ca57 | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
d68c2f31-bd15-5a6c-bbf2-8ab7b63b93ec | button | Remarks/record - NATA Test Report: Grading | Yes,No
555a2d59-268f-55ff-b64e-c0e294652989 | date | Inspection Date:
| checkpoint | 2.4 - Granular Filter Material – Crushed Rock
09176e86-dd31-58a6-91c3-638a86822827 | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
2f29afd7-ab07-5300-9835-e5cb85f0166f | note | Acceptance criteria - Granular filter material must meet the below requirements:
faa1e1c3-dc3c-5a53-a82b-ec80e7a4ab5b | note | • Grading: As per Table 702.051,
3d822aad-c10d-511e-9cc2-274c2598bb03 | note | • Unsound Rock Content: < 5% by mass,
558bc1b8-7c21-5d47-8b37-b6471d434a2c | note | • pH: 6.0 – 10.0.
e2a27c78-4276-55c8-823a-9933b4caae98 | note | ○ Crushed Rock Components: The percentage by mass of unsound and marginal rock in that fraction of an aggregate retained on a 4.75 mm AS sieve shall not exceed the values specified in Table 702.052.
85cc2d29-e21b-5167-91d2-0d6dda96d518 | note | ○ Granular filter material must be tested for grading, unsound rock content on each production day or at a rate of one test per 500 tonnes of material as per Table 702.131.
52502764-001a-5415-874c-a6c4c2d4d3a9 | note | Freq - Each Lot
c58d5326-9211-5273-b4e8-bd72094ec365 | note | Key - R
3bacf34b-b730-5897-a716-4c4f7810985d | note | Resp - SE
145d03e5-0484-5c17-b0ff-b3338c8d3351 | note | SI Key - R
5dae040e-c748-5b49-99f6-49b0ffba19df | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
904bb841-333b-5335-a8f5-b6c3dfd0a15d | button | Remarks/record - NATA Test Report: Grading | Yes,No
72bd4e05-e7b8-5d86-b992-37502a20eda0 | date | Inspection Date:
| checkpoint | 2.5 - Granular Filter Material – No Fines
c8221dc3-b527-5ab6-b679-6fa0e0e68227 | note | Ref docs - VR702.05 VR702.13 Table 702.051 Table 702.131
f645cf26-faf8-5e49-bf10-24b898b5aa57 | note | Acceptance criteria - Granular filter material must meet the below requirements:
655ae7c5-03c0-5013-a36a-a14518988859 | note | • Grading: As per Table 702.051,
4369bf76-c723-591f-92f6-5b460a1ca42c | note | • Unsound Rock Content: < 5% by mass,
36e349d0-ad0b-50cd-887a-1b7dc700bb8c | note | • pH: 6.0 – 10.0.
7fdf8164-4230-5e22-8547-2fc64c48c1f1 | note | ○ No fines concrete shall consist of B4 filter as defined in Table 702.051 and mixed with 4.0% by mass of cement and 3.5% by mass of water in a mixing plant.
a37d3119-0e1e-5974-9442-1b2c46224f1d | note | ○ Granular filter material must be tested for grading, unsound rock content on each production day or at a rate of one test per 500 tonnes of material as per Table 702.131.
992b1f2a-8a17-56df-9683-7fddad9acbe1 | note | Freq - Each Lot
d91f44ec-dd2c-5517-92b7-1e2f3d9e3df8 | note | Key - R
3c49ec8e-2bd4-5adf-9fbf-f24783c33ba0 | note | Resp - SE
d69c2e96-659a-5b1c-ac6a-c1525d4f4661 | note | SI Key - R
e4a24350-e40f-5bc5-88a1-63111416f486 | button | Remarks/record - Material Compliance Data/ Delivery Docket | Yes,No
5c8c87f9-545c-542d-bee3-679123d090a9 | button | Remarks/record - NATA Test Report: Grading | Yes,No
5d2b4e78-05c3-5fc9-bd5c-b08eb2bc44a9 | date | Inspection Date:
| checkpoint | 2.6 - Geotextile Filters
c3a6be97-0579-50bd-9b72-d47682cca111 | note | Ref docs - VR702.06 Table 702.061
ac0ef425-9491-543e-9d83-3c542cb681a4 | note | Acceptance criteria - Geotextile filter shall consist of a fabric manufactured from synthetic fibres of a long-chain polymer such as polypropylene, polyethylene, polyester or similar material and shall be stabilised against deterioration due to ultraviolet light.
f2df2df4-f8c1-55eb-811e-28a56c7309c0 | note | • The geotextile shall be free from defects or flaws which significantly affect its physical and/or filtering properties.
580ad5ff-e4bf-58c0-84cb-b3d39b75265f | note | • A geotextile filter may be non-woven or knitted fabric and shall comply with the requirements of Table 702.061 relevant to the geotextile filter type specified in clause 702.12.
efda487c-7a9e-5e78-8490-521fc56b2282 | note | Freq - Each Lot
5c522407-8aab-5258-ad15-4176c21becc4 | note | Key - R
fb8d4874-42d2-5c63-9286-4bb92c7ca5ab | note | Resp - SE
69e30fae-1e79-5946-bca0-9deba2d8acf1 | button | Remarks/record - Manufactures Compliance Certificates | Yes,No
19d4a568-60e9-5112-b47c-ea803ee7c83a | date | Inspection Date:
| section | 3.0 Installation of Subsoil Drainage
| checkpoint | 3.1 - Excavation of Trench
7bd9f9d0-c738-50b6-8134-ea48c0b64d18 | note | Ref docs - VR702.08 VR702.09
59693f08-14d9-52b7-b868-f19c105e1005 | note | Acceptance criteria - Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile
b7a0263d-0c14-5c12-84ec-85e544ae7a6e | note | • Trench base shall not be more than 50mm below the specified level of invert of the pipe.
5ae1fde6-c02b-59dd-ab3d-add57cf912ae | note | • The base of the trench shall be inspected to verify compliance with the requirements in this clause prior to placing bedding in completed excavations.
fd41dc9b-8f15-5e81-9a58-9a0423cb30f5 | note | • Subsurface drainage pipes or geocomposite drains shall be laid to the depths or levels shown on the drawings. The top of any subsurface drainage pipe shall be at least 200 mm below subgrade.
6d91e3cf-9858-5531-8866-57e3e859ea0f | note | Freq - Each Lot
89749f10-a14e-5114-a627-c63c8e6758ea | note | Key - S
e6b1b70e-b0bf-586d-ac3c-a74a7af0de38 | note | Resp - SE
1a0fa295-08a4-5441-856d-f331b8dd4004 | note | SI Key - I
0bcaf511-1b10-5055-978a-2dd8498ad739 | date | Inspection Date:
| checkpoint | 3.2 - Excavation of Trench in Expansive Material
36ebc5e6-44e5-57f7-89c6-85aef457d46c | note | Ref docs - PS3030.07 (b)
2539ff39-cf33-541e-84fc-c43a021c6e18 | note | Acceptance criteria - Subsurface drainages laid in expansive materials with swell ≥2.5% shall conform to the following requirements:
e86ed7cd-919a-5968-b417-0a185f2eedaa | note | • Pipes shall not come into contact with material.
357e4d7c-199d-51d8-9df5-078839accc88 | note | • At least 100mm of capping materials provided below the floor of the subsurface drainage trench.
0ec4b5a0-d9d2-5018-9ccb-f79e7a778fc9 | note | Freq - Each Lot
4944e6d4-903e-5d2a-8b80-87b35bbb86df | note | Key - I
83ea4b76-4cbc-5e61-b7ac-d1ff492d4c11 | note | Resp - SE
a99cf87a-5d09-590c-a9b1-5fb74a8d3576 | date | Inspection Date:
| checkpoint | 3.3 - Placement of Bedding
4619c392-f4f4-563e-ad61-13b47e6888be | note | Ref docs - VR702.09
71b8d399-22b2-5b59-bb6c-50cd521898d4 | note | Acceptance criteria - A bedding of granular filter material of thickness between 25 mm and 50 mm shall be placed across the bottom of the trench. The bedding shall be tamped and screeded or graded to level. Bedding is not required for geocomposite drains.
1aea52bf-ab14-5a51-bb08-174f980f4833 | note | Freq - Each Lot
d1fd14e3-15cf-556f-b21d-603e33490153 | note | Key - H
56718f78-4ed8-5b98-b388-0cc39341615a | note | Resp - SE
4aed806a-ed52-535f-a5fc-59a38b754fa2 | date | Inspection Date:
| checkpoint | 3.4 - Construction – Pipe and Geocomposite Installation
640b623a-18fe-5036-9a3c-d79a417332c1 | note | Ref docs - VR702.09 702.03
22d4f3a1-7df1-5571-8dc4-58da82d3367a | note | Acceptance criteria - The grade of pipes or geocomposite drains shall be not flatter than 1 in 250.
92d3920d-1ef9-536b-a744-3bdc643e2bd9 | note | • Pipes shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the openings in the lower half of the pipe.
4a3a04dc-9119-5826-a93d-18a3b2d33fc2 | note | • The minimum width of geotextile used for wrapping shall be 450 mm.
3a18cfc0-2363-53e0-9039-65ed15fc4d98 | note | • Lap joints in geotextile used as first stage filters shall consist of an overlap of not less than 900 mm longitudinally and 150 mm transversely. Lap joints in geotextile used as second stage filters shall consist of an overlap of not less than 300 mm.
5dc695c8-7277-5219-88d8-601bedec6f21 | note | Freq - Each Lot
e5977556-0fed-5fa6-89f2-7edfca848cf1 | note | Key - S
960f5792-99fb-52c9-84cf-7aa09d35a30d | note | Resp - SE
b9abaf08-5f31-50bd-a7e2-dbf232e2e2ef | date | Inspection Date:
| checkpoint | 3.5 - Construction – Access points and Inspection Openings
88c7d12c-694d-5bad-9137-47d947e7f75f | note | Ref docs - VR702.10 IFC Drawing
03ab2281-19a2-5318-9168-08142fa539e5 | note | Acceptance criteria - Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located minimum 100 mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100 m and 150 m intervals unless noted otherwise on drawings.
9434db44-af8a-5f1c-91c0-d365c259d7a1 | note | Freq - Each Lot
c0bc77e5-0398-571e-a636-95651ff05829 | note | Key - R I
6434209d-949a-5dd4-a3a8-ff001f141861 | note | Resp - SE
2f3949f6-688a-5cd0-b669-8ce26a2be45a | date | Inspection Date:
| checkpoint | 3.6 - Construction – S1 Pit, Batter Outlet & Flush Out Riser Installation
97e6b5ce-212c-50b0-851d-b0a8cb219cdd | note | Ref docs - VR702.10 SD1611 IFC Drawings PS3030.05
83acf61d-16ac-5572-bbb6-ff8fc03b21b7 | note | Acceptance criteria - Flushout risers for drainage pipes shall have the same diameter as the pipe.
b67903ae-0ce6-5e72-94d3-4a4c74742166 | note | • Flushout risers for geocomposite drains shall consist of a preformed riser fitting, or a pipe of diameter not less than 100 mm.
644b19b8-00f0-5050-bb83-ef8f9158b8ab | note | • Flushout risers shall be installed in accordance to SD1631.
3ed2cc6c-620c-5c52-ba33-91534094a228 | note | • Pits shall be installed in accordance to SD1611.
a45d8c32-220a-56c9-99a7-b74e9e97b207 | note | • Pits deeper than 1m shall be fitted with step irons.
80c5a124-76f6-56de-b599-bc0f5d89d843 | note | • Batter outlets into a swale must maintain min. 200mm clearance to the invert of the swale.
a59eb6cc-7c95-5ad9-8a17-88405ba259d4 | note | Freq - Each Lot
12742cf6-a07f-58d5-9155-00a8e8293a0e | note | Key - R I
db61ae89-269d-56b8-b13c-ee11e102599c | note | Resp - SE
09868bfa-09c1-51a3-a729-e9ca00aed51e | date | Inspection Date:
| checkpoint | 3.7 - Inspection of Drainage Lines & Pits
55f7f2c5-a08b-5dfc-ac6e-3df9c9df9df9 | note | Ref docs - PS3030.07 (iv)
f953710e-fca7-519d-8e21-97f6c2730cfa | note | Acceptance criteria - The superintendent must inspect subsoil drainage trenches, subsoil drainage lines, and associated pits, endwalls and risers, prior to the commencement of backfilling
86832d77-623b-5f6b-87a9-b6677a4b12ab | note | Freq - Each Lot
eb506233-9ac2-5b02-be31-28c3bc7815f9 | note | Key - H
fc4e10fd-e8d6-570d-a34b-c364965e2fa0 | note | Resp - SE
7627a78c-0f51-52e5-935f-dcf76510f065 | note | SI Key - H
0e35589a-ec1d-5472-9ff2-1c05f0a42140 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Construction – Granular Filter Backfill
d173159f-d06b-5b96-92b7-ea83a8ce2f2e | note | Ref docs - VR702.09(g), Approved procedure in Construction Document - Drainage
442dd08f-a2f3-5796-85c3-b30d6e0bb83e | note | Acceptance criteria - Material shall be placed moist and compacted in layers not exceeding 300 mm. Material shall be compacted with minimal disturbance to pipes, geocomposite drains, geotextiles and trench walls.
a9148e6e-3beb-5399-9e15-70c6acf1fa10 | note | • The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Superintendent.
2dcf837b-3bde-5dc2-bbfa-3d2de5159829 | note | Freq - Each Lot
89bc7873-f56b-5872-b69b-1153b18a7268 | note | Key - H
eeeecb47-e895-5d1e-99ae-adab1babf10f | note | Resp - SE
c1cb9778-e45f-563d-a042-5b8b07155991 | note | SI Key - H
334c723f-53c5-511f-a33e-b3c7cc5c3ae3 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Construction – Granular Filter Backfill (No Fines)
2072a448-e3f9-5a31-b5ca-9e19c2b26ca9 | note | Ref docs - VR702.09(g), Approved procedure in Construction Document – Drainage
0f1b448f-0228-511f-84a7-837ff37ff37b | note | Acceptance criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
7fcd070c-39ea-56a6-b0ef-2274a6ffa241 | note | • Contractor shall submit quality procedures for review by the Superintendent which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
8b131465-ab7c-5e4d-83fb-f063837f51eb | note | Freq - Each Lot
215b8604-b8db-5534-b02e-ebb68e963a48 | note | Key - H
1bdafb71-abb4-5d6d-818a-300a60a66cb9 | note | Resp - SE
a81da753-6320-52da-a355-de68779ffc02 | note | SI Key - H
d6cc53ee-ba9d-5f10-8aae-a3eb48f1f21e | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Flushing of Subsoil Lines Flushed after Completion of Flushers, Outlets
953a5cbb-8349-5e39-9042-4d803aa17ab1 | note | Ref docs - VR Clause 702.09 (h)
07b39d41-7e5f-56dd-bffb-b34e313c7c1a | note | Acceptance criteria - Subsoil Lines Flushed to ensure Drainage Lines are free from obstruction.
698100be-8a9d-5139-8767-864369e947b6 | note | • Location, Date & Time for subsoil line recorded on lot map.
d0c1e9e7-5fa9-5b34-a298-8f2d86f1a17b | note | • The flushing test shall be witnessed by a representative nominated by the Superintendent.
b85f5998-6ec3-570f-b3c5-4fc19aca9ab0 | note | Freq - Each Lot
92bed01e-f772-55bc-85b8-ebe282a07b51 | note | Key - R
3604ea2a-9d1a-591d-93f9-10c32b0c6e20 | note | Resp - SE
184ce42a-684e-5459-a54e-52926cb989b6 | note | SI Key - W
7ec27c17-99a6-5402-a6b6-178ece75c28b | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Inspection of Subsurface Drainage Lines
b7e3b1ce-a873-5bba-8162-8e666cf7e7e9 | note | Ref docs - DoT Clause 702.09(i)
9536df01-d8fc-58fc-a61e-0770a774c8b9 | note | Acceptance criteria - All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television
bfc087df-b2d0-50f6-8b10-2ad780631d49 | note | • (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
f93d71b7-43ac-5dad-8932-55f49d2612eb | note | • The report shall be provided to the Superintendent, with a copy of the CCTV record including any video recordings and a summary of the location of any waste construction materials, obstructions and defects detected by the survey.
c1d7a9b8-efba-5b26-8a2f-71501b79c513 | note | • Any sections of damaged or deformed subsurface drainage pipe shall be removed and replaced. A further CCTV survey shall be undertaken to verify that the damaged or deformed subsurface drainage pipes have been replaced and are defects free.
58c2ad75-7e0a-53a6-988f-665f8e88ebea | note | • Placement of Asphalt shall not proceed until the CCTV inspection and flushing test has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage line has been verified by the superintendent.
e02bb468-4e29-5d0e-83c0-50e27df55e59 | note | Freq - Each Lot
82078bef-9e64-5ede-bc2c-333011a712ab | note | Key - H
be6019c5-5539-5af0-b230-cd9e0d33f962 | note | Resp - SE
255aa015-f272-53c8-b41e-e21c1295692f | note | SI Key - H
88650c06-b6cd-523a-a9a1-601929b9c4bd | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - As built
14911955-1a54-575f-a05f-1141b5e948f1 | note | Ref docs - DoT Clause 702.03
aee2fc8c-9e05-5d50-8de2-6ff808ddc91f | note | Acceptance criteria - Subsurface drains to be constructed true to line, level and depth, as shown on the drawings.
f16a35b3-b8d9-5d02-934a-e59a1efac3f5 | note | • The invert of the subsurface drainage to be < 25 mm from the specified level and not more than 50 mm from the specified line.
e581257d-15d3-5db1-bd84-8a4b38636448 | note | • Grade < 10mm in any 3m length or lead to ponding of water within the drainage pipe.
935a5baa-5625-5e37-b445-b57fb147ff2e | note | • Changes to design shall be recorded.
daaac9b5-5f46-55bb-878f-50a727c980b6 | note | Freq - Each Lot
8bdb13ba-d1da-5ce5-809a-b4fc7f060842 | note | Key - H
ec629d6f-8558-5e66-b944-1e1b07e0709b | note | Resp - SE
ac36f896-7cf6-5857-b3b9-ef1a9f7ade0a | date | Inspection Date:
| checkpoint | 4.4 - Product Non-Conformance
e2a54873-2016-5acb-ac85-a68fc99f48a4 | note | Ref docs - CQMP
d20b3537-49c2-507a-a9ac-3d6dde75ea5b | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
19a0207c-729a-5575-a06b-ef1d9ba76281 | note | Freq - Each Lot
903bf4b5-fa73-5e5b-a424-50f307c39790 | note | Key - R
7e5a2076-fabd-55e2-a470-b22c6ab8c33c | note | Resp - SE
dc40bfc9-fa82-51da-bea9-4fc996016e04 | button | Remarks/record - NCR | Yes,No
fe1dabd7-951f-53a8-b600-7784d85088aa | textbox | NCR No:
7eb1b486-dc2e-5165-b763-681df0fba6e1 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0014 Structural Steelwork and Fabrication | itp | 1630-P200-SYM-QAC-ITP-0014 Structural Steelwork and Fabrication |  |  | 338ba1d3-a8aa-4820-9cfb-38b4fa41182b
| section | ITP Details
| checkpoint | ITP Details
ff21051d-54d0-57a8-a0fc-e9f7da7ce53f | note | ITP No. - 0014
5e05091a-d136-5b6a-a02e-c6115537c50b | note | Rev No. - 00
7776f0c9-f931-5e9a-a7ed-8579f0684f30 | note | Date of Issue - 13/08/2024
ce0736ab-8a29-58e4-9db9-db25d231382e | note | ITP Type - New
| section | 1.0 Approval and preliminary requirements
| checkpoint | 1.01 - Quality Management System of the Fabricator
9876d2c1-5ae4-5593-a0dd-19433bb5b3ca | note | Ref docs - AS/NZS 5131.
d8028378-faf0-506e-9b3f-3c6bbb6be822 | note | Acceptance criteria - The fabricator has a quality management system conforming to Appendix D requirements of AS/NZS 5131.
a59e8600-ee7a-5b13-903a-e03cbfe321b8 | note | Freq - Each lot
782d3696-a646-57af-9697-410beaa1a4ae | note | CIGFAB Key - I
830052b2-4143-5b7c-a7ad-571343bf50dc | note | CIGFAB Resp - SE
2e3c356f-0efb-5981-a645-3e999255e011 | note | Symal Key -
ae8cee5a-b058-5a04-bfff-14f68197b04b | note | SI Key -
| checkpoint | 1.02 - Quality Management System of the Manufacturer
9188977d-72b9-5a29-866e-0f0b6de0b8be | note | Ref docs - AS/NZS ISO 9001
ee7721a9-c224-584f-8e06-2fdb2eb21668 | note | Acceptance criteria - The manufacturer of all structural steel associated components and welding consumables has a AS/NZS ISO 9001 certified or equivalent quality management system.
536a5638-e15f-5f52-93c9-93b55143c16a | note | Freq - Each lot
e81a1bbf-eb87-5819-8733-cf1aedbcb632 | note | CIGFAB Key - I
fd56b1ce-d927-56f5-806e-4b39bf4d8387 | note | CIGFAB Resp - SE
5fda826e-c0ca-5934-955f-b979c53485bb | note | Symal Key -
bbc621cc-a99b-5f21-a018-951be29557e8 | note | SI Key -
| checkpoint | 1.03 - Quality Plan
c50a9244-d15a-592b-a924-f43cd8d0fa6e | note | Ref docs - D of AS/NZS 5131.
946e1dd4-9e1f-54e1-89b0-867543e30fcd | note | Acceptance criteria - I) The fabricator has a quality plan covering the requirements of Appendix D of AS/NZS 5131.
d9730d4e-f1e9-5f9d-bc41-32360a636f3c | note | ii) The quality plan includes responsibilities, names and qualifications of all persons involved including welding Supervisors, welding inspectors and NDT technicians.
113d579c-730c-5073-9181-d7508b294872 | note | Freq - Each lot
833b1219-6c73-5226-bfe7-c3def327fd29 | note | CIGFAB Key - I
5ad78664-83b0-5760-a25e-b415cfaac3fd | note | CIGFAB Resp - SE
5ff40974-0dc4-57fc-bebc-dd6f150a8379 | note | Symal Key -
1964eca2-c09b-5413-9ecb-4e2d33ff2711 | note | SI Key -
| checkpoint | 1.04 - Drawing review
df559cb9-70c2-50ce-91a0-4e3415325712 | note | Ref docs - 630.05 HP 4
b730adf3-6d52-506e-b9d9-c0201fd7a3d8 | note | Acceptance criteria - I) Shop drawings are reviewed by a competent Structural Steel Designer.
dc8d23b3-4427-581c-ae16-fbb0d74128b7 | note | ii) Evidence of review and competency of the Designer have been submitted to the Superintendent prior to fabrication.
f5913acc-a3cf-5f59-89ce-ea730b397d49 | note | Freq - Each lot
71b7adc5-54a7-5d00-8282-1dd6ae460168 | note | CIGFAB Key - H
7af6928c-28b5-56d2-9108-0d77c2741815 | note | CIGFAB Resp - SE
969f2314-736b-5b46-a3fe-662ede1b6852 | note | Symal Key - H
bd395a54-8a97-5fc4-ae36-0faaf4dc6535 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.05 - Certification of Fabricator (from 1 Jan 2024) to construction category
6ba2b887-138d-55e7-881b-9a60eaaf7b7c | note | Ref docs - AS/NZS 5131, and AS/NZS 3834 HP 2.
f42e4660-b47a-52e3-a02b-f02c2ba143f1 | note | Acceptance criteria - I) The contractor shall be certified to CC2, CC3 or CC4 of AS/NZS 5131 as required.
aaceba2d-2eef-5283-b449-4647f50be24c | note | II)The fabricator shall be certified to AS/NZS 3834.2, or to AS/NZS 3834.3 as required.
f2533a3a-2ccc-5837-b9dd-1ee0305cb8f6 | note | Freq - Each lot
58d45b7f-9ea1-5726-b84f-178ea558492d | note | CIGFAB Key - H
604c2469-f230-5f13-92c1-aaa160149710 | note | CIGFAB Resp - SE
763b47cf-5e6f-516e-9b32-2993d169d7af | note | Symal Key - H
129a423d-f60f-52f8-b68f-bf5bd251aea5 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.06 - Fabricator & Sub-contractor details
4aec2a05-344d-59ff-8cc2-e73ddc9b6932 | note | Ref docs - N/A
17c321d4-c3a2-57cd-aa94-94a3181fa3cd | note | Acceptance criteria - Fabricator & sub-contractor details have been submitted to the Superintendent at least 14 days prior to commencement of steelwork.
30a3cde9-3600-5461-aebf-790902566acf | note | Freq - Each lot
4d3dbc54-8ecb-5b0c-a6ee-38bc8f3d8223 | note | CIGFAB Key - H
ad7cf728-d5e3-5c5d-a97e-b7ff1f7ef089 | note | CIGFAB Resp - SE
f127d343-0452-5d31-8ce2-2ae98445d14d | note | Symal Key - H
76b4634e-e600-5fab-8ae0-6849213be090 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.07 - Evidence of certification to construction categories
f86e0d19-c580-5f1f-b216-cf9493b1c292 | note | Ref docs - 630.03a
b9ee0e6b-fcb9-5278-91df-e7f2c1a2b737 | note | Acceptance criteria - Evidence of certifications of the fabricator to construction categories has been submitted to the Superintendent.
be7b26b8-236c-58cc-98fc-1f3b30cf467e | note | Freq - Each lot
c83a3b9a-fd81-5e60-bdad-5b27c4aa69aa | note | CIGFAB Key - H
63bf0c32-ea2e-5fa5-be63-e0448fbad68e | note | CIGFAB Resp - SE
e5b51245-c538-5365-a9b7-7eb49b57bd85 | note | Symal Key - H
9d792540-b864-5135-92d4-a7de38ee90bf | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.08 - TB 46 Surveillance
f0c98fba-24b0-5321-a215-50bb9d767043 | note | Ref docs - AS/NZS ISO/IEC 17020
1b4ff563-0d68-5243-9876-53f60f2a4b1a | note | Acceptance criteria - Surveillance of the steel work as per Technical Bulletin 46 by a Surveillance Officer from an organisation certified by AS/NZS ISO/IEC 17020 has been scheduled prior to commencing the fabrication works.
1019eb09-caa7-5012-86ce-b655cfd73486 | note | Freq - Each lot
4a81573f-9e3e-5079-8c37-abc0c6a5c81d | note | CIGFAB Key - I
91c7bb04-1416-58fd-9c14-e8d435eae424 | note | CIGFAB Resp - SE
5cc3e7cb-9674-5a48-82fc-384fd9febbae | note | Symal Key -
9c0e0ecf-df6f-5f29-87c1-038649de2387 | note | SI Key -
| checkpoint | 1.09 - Qualifications
f842513b-5451-5fe5-909c-75607c602b12 | note | Ref docs - Clause 1.12.1 of AS/NZS 1554.1.
7359d8da-fe40-5857-ab14-c78c6ec8dfab | note | Acceptance criteria - i) Welding Supervisors are qualified in accordance with clause 1.12.1 of AS/NZS 1554.1.
c9e2ce1f-d598-51dc-b25c-211518751ccb | note | ii) Welding Inspectors are qualified in accordance with clause 7.2 of AS/NZS 1554.1.
3ccf3b4d-bf6b-5e4b-ab5b-bf7d1e134e3d | note | iii) Certified technicians for NDT testing are qualified in accordance with clause 7.4 of AS/NZS 1554.1.
ab019a24-e480-5d78-8e56-5ddf81eb16be | note | Freq - Each lot
c76911ba-6cf7-57a0-a579-9dc0d0b01487 | note | CIGFAB Key - I
f75a76d7-c3bc-5a8a-845a-c339234be081 | note | CIGFAB Resp - SE
12c893f0-39cd-5e83-8677-0e4e9b7592d1 | note | Symal Key -
21534c91-1028-5a1e-b51c-f829f7270d60 | note | SI Key -
| checkpoint | 1.10 - Testing Laboratory accreditation
64b579dd-f077-51b3-8d17-c229020d4be4 | note | Ref docs - AS ISO/IEC
8125d847-7c0b-5e9e-85fb-80ae6af255f2 | note | Acceptance criteria - Testing laboratories are accredited to AS ISO/IEC 17025 by a signatory to the International Laboratories Accreditation Cooperation (ILAC) through their Mutual Recognition Agreement (MRA) which includes NATA.
8f420fae-344b-5b4b-9220-0497123c6e9f | note | Freq - Each lot
ef7c6b60-0697-56f0-b8bd-d3e62e6d8084 | note | CIGFAB Key - I
8b4cc826-b3c1-529b-ae05-b3cf4c729f74 | note | CIGFAB Resp - SE
16bbfa2f-b498-5b66-9277-4f4a43acc339 | note | Symal Key -
2f0cbbcb-16da-5cb8-b816-d07666407c33 | note | SI Key -
| checkpoint | 1.11 - Procedures & ITP submission
5e3c1ebe-9f9f-5f3b-81e6-f2324c2da6fc | note | Ref docs - 630.03D HP 3
8631b670-09a3-5bc6-8dad-0c4e92b9871c | note | Acceptance criteria - The fabrication, welding and installation procedures, and ITPs have been submitted to the Superintendent one month prior to fabrication.
9ce6b10e-48df-5ff7-acd9-1ab3039e28fc | note | Freq - Each lot
4af279d8-9caf-55a9-b028-be61e3c8b7e4 | note | CIGFAB Key - H
25338a4f-1039-5a7d-94c0-c30bf03038f3 | note | CIGFAB Resp - SE
dd4c8db6-ea91-5b7c-93c3-492d86aba8da | note | Symal Key - H
b61adb50-8b1a-5fbd-9134-e48e95122056 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.12 - Welding procedures qualification
45e345c3-1064-5297-b224-79ca30da1c3d | note | Ref docs - 639.14 HP 9, 10 & 11
f1f8a62d-56a0-5dc8-8805-0fddb0a1b717 | note | Acceptance criteria - All welding procedures are qualified through a Welding Procedure Specification (WPS) as follows:
05eb4850-b9b2-5a88-9dde-cfc3ff7744e0 | note | i) Category SP welds using one of methods (b), (c) or (d) of Clause 4.2 of AS/NZS 1554.1;
096f5494-0bf4-5794-9e76-07dd3cfb1ecc | note | ii) stud welding in accordance with Section 4 of AS/NZS 1554.2;
48433fc4-472e-5b96-a1be-03e85048e35e | note | iii) Category FP welds using one of methods (b), (c) or (d) of Clause 4.2 of AS/NZS 1554.5;
605850d4-025f-54ac-a68b-5572dbcf9b92 | note | iv) Category GP or any other welds in accordance with Clause 4.2 of AS/NZS 1554.1.
02190339-615a-572e-9bca-1aa1717bfb64 | note | ○ The welding of all test pieces required for qualification using method (c) or (d) of Clause 4.2 of AS/NZS 1554.1 is done under the direct supervision of the Welding Supervisor, and optionally witnessed by the Surveillance Officer.
75adff9e-f5ae-593b-80a7-edabecd477cf | note | Welding procedures previously qualified and used on other works are certified by relevant documentary evidence by the NATA accredited Surveillance Officer, provided that:
484d9d1b-df56-5357-b4d4-d02dd5daf81b | note | i) the procedure is being used within the limits of changes in essential variables permitted by AS/NZS 1554.1 and within the limits of the Welding Procedure Specification; and
7a9e2cbc-f3da-5631-af6f-eab4807a169d | note | ii) all qualification documents as required by AS/NZS 1554.1 are available to support the procedure qualification record; and
4f5e7a00-e71a-5d1f-a77e-21aa2172b2c1 | note | iii) non-destructive examination records are available to demonstrate successful use of that procedure.
a5028e0b-8d8e-5f08-a8fa-97ae9aca2c4f | note | ○ Documentary evidence of the results of welding procedure testing, assessment against the acceptance criteria, and an approved Welding Procedure Specification (WPS and PQR) for each of the weld procedures to be used in the welding of the steelwork have been submitted to the Superintendent for review at least five working days prior to commencement of welding.
9d915660-6236-5a6a-9e55-115dc161b400 | note | ○ A photograph of the etched surface of all weld macro tests, to AS 2205.5.1, at a magnification of x1, or greater, is submitted to the Superintendent with the test results.
3d7fac2e-ce63-51bc-8592-3856eb15d85b | note | ○ Documentary evidence of welding operator qualification through testing or assessment for each of the welding procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding.
f11f5295-ae01-5221-8ab3-781a3fcbf610 | note | Freq - Each lot
c5c60a41-2ef6-5f8e-8b27-aaa5be2a7e3c | note | CIGFAB Key - H
28c690df-d5b2-5fc3-b893-35bd91a74b28 | note | CIGFAB Resp - SE
a9309b3d-a0ae-57ca-b0d5-fc77df9ad35c | note | Symal Key - H
bc5b4701-d7bb-5771-93ab-66ca6b752a82 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.13 - Welding operator qualification
3b925103-6365-530e-9fad-436d6b32f320 | note | Ref docs - AS/NZS 5131
3e6cc9b6-9c45-54cc-91c2-a6940410f8f8 | note | Acceptance criteria - Documentary evidence of welding operator qualifications through testing or assessment for each of the welding procedures to be used in the welding of the steelwork are submitted to the Superintendent for review at least five working days prior to commencement of welding.
48ec0f4f-ab06-571e-885c-26d3bd4c1877 | note | Freq - Each lot
7ac9dd04-c113-5db5-b971-7c6de1c01b0f | note | CIGFAB Key - H
a7e34a40-c5db-556b-b66f-f0a73be1d8d0 | note | CIGFAB Resp - SE
82d20830-4e0d-5b60-995e-01a028cb752c | note | Symal Key - H
9997125f-80a4-5f37-a5a0-4ddfc203e520 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.14 - Dispensation/changes
c41d78b9-d86e-574c-9ae7-7406b67e029f | note | Ref docs - QMP
441a70e2-8d21-552c-8ec2-50066ba0ec10 | note | Acceptance criteria - Any dispensations or design/drawing changes applicable to this lot have been tool boxed with all involved.
38270f16-1b7f-59ba-b478-ac7e279baa79 | note | Freq - Each lot
ce03fa56-1fb6-5062-b95d-801355364ced | note | CIGFAB Key - I
d1d3b466-ca1b-5558-9466-377f8e718d0b | note | CIGFAB Resp - SE
0c4517a6-9d04-5a22-bc82-ea8b382411e4 | note | Symal Key -
06aa0563-e622-5b8f-9939-7e8e725f0c3b | note | SI Key -
| checkpoint | 1.15 - Inspection of Welding Qualifications
4c7100f2-269e-5f28-8464-e156e93b10ec | note | Ref docs - VR630.03
ba809a46-a337-5cd2-81f0-a15bc89f2ac3 | note | Acceptance criteria - Welders qualifications to be inspected by independent surveillance officer
afaa2394-5bcd-58ab-9dbe-aeddd8a74820 | note | Freq - Each Lot
27ce29b8-4f5d-57b5-b12f-d2dc0761e6d2 | note | CIGFAB Key - H
383dc0ea-492c-5592-bad7-bbe86e88f158 | note | CIGFAB Resp - SE
42074bde-2188-51bb-a0af-ad0ef3068efe | note | Symal Key - H
bc798f43-e3d7-5630-aac8-de29c3335656 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Materials
| checkpoint | 2.01 - Certificate of Product Compliance
3b0bca30-f18c-5444-b0de-16ffc522c656 | note | Ref docs - Table 630.071 HP 5
1aab1ec9-be28-5a1e-b456-8710adb1aefd | note | Acceptance criteria - The steel manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance to the relevant steel product standards listed in Table 630.071 have been submitted to the Superintendent.
6c1b75c5-e53d-54d2-ada2-a7629c52646f | note | Freq - Each lot
af3edf4e-8a28-514e-a9e4-df01fefe8f4c | note | CIGFAB Key - H
e099077a-4b87-57dc-b422-fa023589511d | note | CIGFAB Resp - SE
7298e717-543b-565b-ae1f-5228f6a29eb7 | note | Symal Key - H
e603a0b2-e667-56a4-b582-caca231f70c6 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.02 - Traceability and Marking
424789c5-fd5f-5455-be07-919f7960d472 | note | Ref docs - 630.07
4f016603-7ff4-5f8a-89a7-51c529d7d3e0 | note | Acceptance criteria - All steel are traceable from the point of manufacture to its final location in the structure in accordance with the marking requirements of the relative Australian Standards as applicable.
33b304e5-97f8-5c2a-a415-6cb50369bfec | note | Length marking:
4ab9c7b0-89f4-5713-a786-b4f782ee1dee | note | i) The manufacturer’s name or mark, or both;
0f4655c9-13f4-5783-8f3a-d6fe9f60bc4e | note | ii) The manufacturer’s site or mill identification, or both
5bdbf762-7955-52e5-b27a-490d147e20fb | note | iii) The grade of the steel;
53eb9c28-9262-5fa8-9ded-40229b32f70e | note | iv) The heat number;
0cc82ba7-0130-5a17-b23e-3438f005b6e6 | note | v) A mark (e.g. plate number) allowing it to be traced to a test certificate;
599e1a6e-4ebe-5c67-ba49-19a0ae884b77 | note | vi) The nominal size and shape;
74587350-48aa-5d0f-89ab-26b64c4758bd | note | vii) Batch identification number;
938f8b76-ae6a-5740-83ed-9d6f68b20d34 | note | viii) Name of the Australian Standard
47e7d08f-72e5-561f-8b22-c09878c781b9 | note | Bundle/pack marking:
6d0e6af1-cf60-5bef-af40-b485cbb7978c | note | i) The manufacturer’s name or mark, or both;
09eedef0-3b92-5a0a-98b9-c1596e6ed5b2 | note | ii) Name of the Australian Standard;
51daad5d-1f55-5ec2-b84b-260f5b400ce6 | note | iii) The grade of steel;
d15ae93b-883a-57be-b51f-f1d12e2c5a4c | note | iv) The heat number;
1b58649f-a57d-5810-b944-3d4eb3004d1c | note | v) The nominal size and shape
94d9cbde-046d-5e13-8eb9-50416cdc6876 | note | Freq - Each lot
c54d82bd-a2ed-571f-a4c3-0e6aa0667d7e | note | CIGFAB Key - I
c8ecc587-05ab-561a-8d37-74f46b4e0d15 | note | CIGFAB Resp - SE
a2c88cf6-9b78-5c70-97b5-00eb7306da51 | note | Symal Key -
e314c26a-949b-5a90-9e5c-fa8b94da67a1 | note | SI Key -
| checkpoint | 2.03 - Freedom from defects
46ebd160-315e-50aa-a54a-57ad84772b96 | note | Ref docs - Clause 8 of AS/NZS 1163
14ead0c2-95d4-5279-af7d-756a8ce85ee4 | note | ○ Clause 2.4 of AS/NZS 1594
4c97effe-b5fc-505d-af48-211f78a5eb12 | note | ○ Clause 8 of AS/NZS 3678
81b5c8c5-20f3-5673-9f5c-6450063f52c1 | note | ○ Clause 8 of AS/NZS 3679.2
ae1599d6-2d4a-5f1c-98f7-db39c8323a8e | note | Acceptance criteria - Steel has no defects as per the below before fabrication.
dfb01235-8cc3-5c33-9c28-510f52ae19c2 | note | i) Clause 8 of AS/NZS 1163 - For Cold-formed structural steel hollow sections;
cfab9ce5-3785-56e1-85c0-05ef58f7d13f | note | ii) Clause 2.4 of AS/NZS 1594 - For Hot-rolled steel flat products
5b1b6b40-85c9-51b1-a1a4-b02803b24993 | note | iii) Clause 9 of AS 3597 - For Structural and pressure vessel steel - Quenched and tempered plate
e33122a0-08a3-5495-81c1-18dfbdd660d4 | note | iv) Clause 8 of AS/NZS 3678 - For Structural steel - Hot-rolled plates, floorplates and slabs
2443992a-f46c-5e35-81ff-34d3b275a04a | note | v) Clause 8 of AS/NZS 3679.1 - For Structural steel - Hot-rolled bars and sections
b49da2ef-4670-5a0b-9cf2-22ee1375b028 | note | vi) Clause 8 of AS/NZS 3679.2 - For Structural steel - Welded I sections
1a5d1494-4db7-5282-aab8-f01f63402b71 | note | Freq - Each lot
4a9c5e4e-522e-5b6f-9ef8-8fd14337d30a | note | CIGFAB Key - I
b674f270-745e-5500-8bbf-1bb5d501f426 | note | CIGFAB Resp - SE
58d969b8-d171-5bf2-850f-37d230e125ae | note | Symal Key -
5b7a70c9-3ae0-52dc-bcb9-e4c0a1bb4d89 | note | SI Key -
| checkpoint | 2.04 - Use of weld repaired steel
af3d5102-716f-5bad-9d54-aa7a9457c84c | note | Ref docs - 630.07 HP 6
ce6fb39a-f12f-5dc1-9637-ad3ccb916045 | note | Acceptance criteria - Approval to proceed has been given by the Superintendent for using any weld repaired steel including welding to make up member length. Submissions are made at least 5 working days prior.
2a29e3ed-08d0-5f75-b6db-64c3b17f87cc | note | Freq - Each lot
c3282103-4191-5b68-8f5b-d56c79d26d37 | note | CIGFAB Key - H
b1e814b4-3646-5baa-9c81-9a0d8a43f060 | note | CIGFAB Resp - SE
c861bf55-3692-5aeb-b64f-b3f39f2ce09f | note | Symal Key - H
1cdd47fe-1643-54e5-bc99-965c7ce05b0c | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.05 - Storage of materials
172a6df4-08d8-5502-a56f-0f95d1327af1 | note | Ref docs - 630.07
70d1e57d-b80b-5921-bc67-faa212ad434f | note | Acceptance criteria - All steel, whether fabricated or not, are stored above the ground and adequately protected against corrosion and damage.
741d82ab-2972-5dd8-ab75-b54032f3682c | note | Freq - Each lot
42b2ba87-a3bb-5fc2-9015-85b64248817e | note | CIGFAB Key - I
4ddc5151-312f-5dcd-95ee-5c71cf29d0fe | note | CIGFAB Resp - SE
70bfd682-b18d-5a57-a787-dd6ee0fe599c | note | Symal Key -
f46d4402-c6c6-5c05-8b6d-0faae2a57c96 | note | SI Key -
| checkpoint | 2.06 - Material change
7b477aff-fad7-535b-9cac-888c11283c49 | note | Ref docs - 1170.12
ce476e4e-1cfc-5b25-8900-119788a0ce29 | note | Acceptance criteria - i) The Superintendent and/or Designer have reviewed and agreed to any material change request.
389b4882-e636-55bb-84d6-d2866c161e8a | note | ii) Design Change Request (DCR) has been raised (if applicable).
59332bca-372b-5a07-827c-37ae9e4edbff | note | Freq - Each lot
5f99ffaa-c6e4-509e-988d-0502245ad081 | note | CIGFAB Key - I
0ef5fb74-e0ad-5690-8692-5c2e1b660572 | note | CIGFAB Resp - SE
3e4cdca7-2df4-58fe-beb1-04bb8981adfe | note | Symal Key -
54d41217-57d8-5389-9253-bf02c8ce240e | note | SI Key -
| section | 3.0 Construction
| checkpoint | 3.01 - Safety
d9ec5b54-36e3-566c-a08e-a8650a37e6a1 | note | Ref docs - 630.04
e19dc414-9056-56bf-8691-15389a6eebeb | note | Acceptance criteria - Adequate safety precautions (control of exposure to arc radiation, hot metal, and welding fumes as well as the prevention of electric shock and fire) have been taken for all persons.
42bf4fc7-270c-5548-b86e-1fba7763ceeb | note | Freq - Each lot
e412a7a3-6d7a-5c9b-8dfd-3f1b5664fd36 | note | CIGFAB Key - I
b5ac7c12-bc05-59a8-859b-e277d0bf4efb | note | CIGFAB Resp - SE
9b7da5d6-252e-5ff6-96fc-abc3ca2513fd | note | Symal Key -
cdcdcb79-70e5-5775-9808-e1e46be55c7f | note | SI Key -
| checkpoint | 3.02 - Cutting
589c411f-aead-53dd-9d28-e505ae91c637 | note | Ref docs - Table 630.101.
a3d79fde-7274-5a6f-ad49-de98b6d98316 | note | Acceptance criteria - i) Hand held or hand guided cutting is only done if no other alternative is available.
34a3f61a-5dd1-5dcf-987b-09c6a86c4335 | note | ii) Shearing or cropping has not been used for main plates, reinforcing plates, main gussets, splice plates, rolled sections and shapes or any steel thicker than 16 mm. Distortions caused by shearing is removed.
fe36b53e-16c2-5858-9005-d3c86c64825a | note | iii) Cut surfaces to be incorporated in a weld are free from fins, tears, cracks, lose or thick scale, slag, rust, grease, paint or other foreign matter or any other defect or foreign matter that impacts quality, strength and proper welding.
d06f9f2b-3b4f-5738-a171-d091aaf0a89b | note | iv) Cut surface not to be incorporated in a weld has a surface roughness not greater than the values given in Table 630.101. Surfaces with higher roughness values are grinded parallel to the direction of cut to reduce roughness.
2913980b-7f68-5d8c-9435-a3904bd31dd6 | note | v) Notches, gouges or other imperfections on the cut surface with a depth of 2 mm or greater are repaired by welding.
0a5a3ff8-d369-5bce-9d23-b8172dd8b9df | note | vi) Notches, gouges or other imperfections on the cut surface with a depth of less than 2 mm are removed by machining or grinding, and the depression is tapered out smoothly for a distance of at least 75 mm on both sides of the defect.
420307cc-a3ea-57bd-a007-7c2bf6406061 | note | vii) Notches, gouges or other imperfections are not closer than 20 times the thickness of the component.
a7f732a5-81cd-53c6-bba2-2a99e0a0411c | note | viii) All edges of steelwork to be protective coated are ground or machined to a smooth even surface finish with a minimum radius of 2 mm.
216c60c5-4994-546b-ada9-42852a976ba5 | note | ix) Corners of rolled edges are rounded, and edges are square and straight.
9604dbc1-9788-553a-a6bf-4f5cf08a0145 | note | x) Re-entrant corners have a radius of min. 20 mm and are shaped to be smooth and without notches.
107a8475-e7b1-54ae-a82b-fb91bf045f49 | note | Freq - Each lot
78437847-c8e3-598e-bcfd-f9b7152682e3 | note | CIGFAB Key - I
8b443fd7-81a6-5760-8e46-327df4698c48 | note | CIGFAB Resp - SE
8db07b8d-e2b9-5cc5-8b7c-395ad205de19 | note | Symal Key -
6d4c9dae-0971-5bb0-a632-b058ba1b5fa2 | note | SI Key -
| checkpoint | 3.03 - Cambering, straightening, or forming
d6eec0d7-b827-5107-8f3a-4484cb7d25c9 | note | Ref docs - 630.11 HP 8
b10f4568-047e-5b37-9888-eb806e09e663 | note | Acceptance criteria - The work instruction for cambering, straightening or forming, as appropriate shall be submitted to the Superintendent for review at least seven working days prior to commencement of these activities.
a5531971-5efb-54ab-b49d-3bdf0d911abc | note | i) Allowance for the deflection due to self-weight in the measurement of camber is calculated by an experienced structural design engineer who is eligible for Corporate Membership of Engineers Australia or who hold a Registered Engineer certificate.
d4e6e4fb-5c4a-5b2a-846c-7cf84bc6b7f7 | note | ii) Cold forming (forming at temperatures below 250°C) has been carried out within the deformation range recommended by the steel manufacturer.
d377fb29-b025-5b20-90a1-36012dd259c3 | note | iii) The temperature of steel did not exceed 600°C during these operations.
1517ee5b-5f0a-54aa-8742-5f650d40e7f7 | note | iv) Forced cooling by water or other fluids is not done until the temperature of the steel is below 200°C.
e68dfd8e-7a10-574e-8c19-497fe6d732bb | note | Freq - Each lot
89bbd1c3-33f6-5890-91e4-f17f153bce7c | note | CIGFAB Key - H
cc5e74de-801e-5858-9f7d-89fab6ea4d66 | note | CIGFAB Resp - SE
8c7e4bfc-c959-5798-8e6b-89331b9141a5 | note | Symal Key - H
3b1bb1f4-dc6d-54d9-8eff-1ab133f02192 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.04 - Holing
6ef60505-8b9c-58bb-a68a-e3448e6282d8 | note | Ref docs - 630.12
517f69ed-1b20-583c-827f-853040c0d1c2 | note | Acceptance criteria - i) Holes are not formed by hand thermal cutting or by punching to full size, or by sub-punching (Grade 250 L15 or for any higher grade of steel).
53ba9f8c-b190-5290-83f3-3c167c59fb65 | note | ii) Round holes are formed by either drilled full size or reamed to full size after sub drilling or sub punching at least 3 mm undersize or machine thermal cut to full size, and pierced within the removed material.
e71525fb-b79e-5de6-9868-a2433f1c2dbd | note | iii) Slotted holes are formed by either machine thermal cut, and pierced within the removed material or formed by drilling two adjacent holes and completed by machine flame or plasma cutting.
3001be06-1d5b-571b-a157-ed0b2b9dd6bc | note | iv) Holes are formed by sub-punching in grade 250 steel and only in material less than 20 mm in thickness.
5a03d1ba-38d9-5c84-8765-230fd5b1ad00 | note | v) Holes are cylindrical and perpendicular to the face of the member.
23d4c183-3a5a-5bba-af1f-d37114c48189 | note | vi) 85% of the holes in any group are showing no offset greater than 1 mm between adjacent thicknesses of metal after reaming or drilling holes.
053ae8c5-64f3-5e2a-b640-7620d176ba25 | note | vii) All burrs are removed after drilling or reaming.
b5201006-ba12-59dc-8e4f-a15c6607bc38 | note | Freq - Each lot
80966883-1019-5ac9-9f79-67066b4b438a | note | CIGFAB Key - I
f8befd26-24a3-5cc2-aa92-6decbaf4d10e | note | CIGFAB Resp - SE
86a21ad3-d31b-58c0-9c58-062b35ebfb6a | note | Symal Key -
7f857d71-3e5d-5e6c-93f1-9b94c2523963 | note | SI Key -
| checkpoint | 3.05 - Oversized and slotted holes
943aa503-e731-5ff1-b0d0-3bb091c04328 | note | Ref docs - to AS 4100, AS 5100.6 or NZS 3404
cb730503-7382-50f2-886f-f03493773d1b | note | Acceptance criteria - i) Oversized hole of steel members designed to AS 4100, AS 5100.6 or NZS 3404 did not exceed the greater of 1.25d or (d + 8) mm in diameter where d = nominal Dia of the bolt in mm.
07945d7e-936b-5e05-af6b-689a3d0c09e2 | note | ii) Short slotted hole of steel members designed to AS 4100, AS 5100.6 or NZS 3404 did not exceed the nominal diameter in width and 1.33(d + 10) in length where d = nominal Dia of the bolt in mm.
3e8addfd-07e7-5da7-a074-79d2e97b23c1 | note | iii) Long slotted hole of steel members designed to AS 4100, AS 5100.6 or NZS 3404 did not exceed the nominal diameter in width and 2.5d in length where d = nominal Dia of the bolt in mm.
1bee24ed-a2d4-50a6-814b-311932417a12 | note | iv) Oversized and slotted holes of steel members designed to AS 4600 conform to Table 5.3.1 requirements of AS 4600, all bolts are loaded in shear and
68a1f58e-c478-52c0-bfaa-ee02c1236070 | note | – a) for slotted holes:
dd112c77-ca05-5ad9-ab86-ddc5d86809d7 | note | ○ A) The length of long-slotted holes are normal to the direction of the shear hole.
9ccc037d-7ef7-56f7-ae62-33c6b98fbd8a | note | ○ B) Short-slotted holes have the force either perpendicular or parallel to the hole.
bb029189-4473-54cc-afe7-b0810e664f38 | note | – b) for lapping and nesting of sections for purlins and girts:
e3e57209-4820-5cdc-8803-53c54699398f | note | ○ A) integral washers are used with the bolt head and nut.
49234b42-bced-5707-a602-90dc4c5ef5a2 | note | ○ B) all bolts are loaded in shear.
7151e045-1287-5e82-95ec-6be4464016fe | note | ○ C) the length of slotted holes are normal to the direction of the shear force.
d3bd5275-d1c8-5bd6-bedd-6493e7c8b9aa | note | ○ D) in shear and the length of slotted holes are normal to the direction of the shear force.
6bf3dab2-aa25-5b67-a612-3fcf3caf1e58 | note | ○ E) The dimension of oversized-slotted holes is (d + 6.0) mm by (d + 10.0) mm where d is the nominal diameter of the bolt.
a4fcb129-8831-57be-8c96-472911afadce | note | v) Hardened or plate washers are installed over the oversize/short, slotted holes under both the bolt head and the nut where oversize/short slotted holes are used in any or all plies of bearing-type or friction-type tensioned connections. The plate washer is completely covering the hole such that the minimum distance from the edge of the hole to the edge of the plate washer is 0.5 times the hole’s diameter.
870c73d3-6e3a-5a16-93c8-cdf81decb22e | note | vi) A plate washer not less than 8 mm thick is installed to completely cover the long-slotted hole under both the bolt head and the nut where a long-slotted hole is used only in alternate plies of bearing- type or friction- type tensioned connections. The plate washer is completely covering the hole such that the minimum distance from the edge of the hole to the edge of the plate washer is 0.5 times the hole’s diameter.
3c876ee8-d5a2-5143-8630-c5e941a3ddda | note | vii) Slotted holes are only used as per IFC drawing.
a05c2217-6754-5afa-a980-a46d19a88c1e | note | viii) Approval from the Superintendent has been taken to use slotted holes where not shown on the IFC drawing.
6176c379-bbbb-5bd8-8fd2-337bf18b882e | note | Freq - Each lot
92a20d53-dacc-5603-9e83-346cd0f834b0 | note | CIGFAB Key - I
f08c359f-4fa0-517b-8966-031b6d042e45 | note | CIGFAB Resp - SE
b6cd38ff-3ddc-56f1-b378-aca61c843530 | note | Symal Key -
eaa18734-1158-52f3-9d05-0762cbdfe179 | note | SI Key -
| checkpoint | 3.06 - Preheating weld rods
b8395910-a71b-5146-ac92-baca11c76531 | note | Ref docs - 630.16
434ca0b9-0d66-5d3e-85ea-023a05470c09 | note | Acceptance criteria - All welding consumables shall be stored, handled and used in accordance with AS/NZS 1554.1 and in accordance with the recommendations of the manufacturer.
77f33cef-4d87-510b-9694-f27195e3b883 | note | Preparation, assembly, preheating and welding shall be carried out in accordance with the relevant sections of AS/NZS 1554.1, as specified, and the following requirements:
1c8cb021-be15-531c-90b2-48a57a2e62e2 | note | (a) Hydrogen-controlled welding processes, as defined in AS/NZS 1554.1, shall be used for all butt welds for flange and web splices in main girders, gantry beams and columns, for splices in bridge barrier railing, for T- butt welds, and for extending members when permitted at clause 630.07.
be44353d-58de-598d-b64c-38a895435427 | note | (b) Hydrogen-controlled electrodes shall be used for all manual metal arc butt welds, in accordance with the selected manufacturer’s requirements.
2944c87d-84cd-5921-9142-c280d091b7fe | note | (c) Preheat temperatures shall be confirmed by contact thermometers, non-contact thermometers or temperature indicating crayons. Preheat temperatures shall be confirmed if welding is suspended for more than 20 minutes, and if necessary further preheating shall be applied.
13725ae1-7e91-505a-9acc-ea3cebce1433 | note | Freq -
ea49cdca-e70b-5c88-874e-e42905562628 | note | CIGFAB Key - H
0d60c46b-9530-5e26-b28e-4455c4d81bfb | note | CIGFAB Resp -
aaa1ed84-d2cb-5b57-baf0-89865d175a27 | note | Symal Key - H
ce7eb6cc-12db-54ca-9cfa-979c509f1ac4 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.07 - Welding
3a4ba87a-456d-53be-9667-2d9a0fb1e078 | note | Ref docs - AS/NZS 1554.1
97375e17-1cbe-543f-a413-318a1f8dc42b | note | Acceptance criteria - a) Minimum length of tack weld is 50 mm for a 5 mm fillet weld or 80 mm for a 4 mm fillet weld.
9962136a-dae5-5f30-a0ab-b1b4f721ae7b | note | b) Any and all tack welds and all fit-up or aligning or temporary attachment welds are made using a qualified welding procedure. Tack welds are made within the weld joint and consumed by the production welding of the joint.
04ba9bff-784b-5d0d-bdd3-9735552a76d7 | note | ci) Suitable run on and run off tabs have been used for all butt welds and web to flange fillet welds. Each weld pass has been terminated on the run on/run off tabs at least 20 mm beyond the edge of the parts to be joined.
22bce867-4f49-5b7a-93b4-61c41eb1a098 | note | d) When required by the WPS, root runs of double-sided butt welds have been back-gouged sufficient to ensure full penetration. A 20% sample of back-gouged preparations has been visually inspected for the absence of unsound metal and reported.
6964bd5f-d15c-58f9-8c18-14f35ae0d01e | note | e) The maximum size of electrode is 5 mm. Use of more than one electrode simultaneously in the weld pool has been validated by the welding procedure qualification.
b9eb2a41-f54a-50b7-8d68-21dba1a6d67f | note | f) The maximum size of fillet weld to be made in one pass has been validated by the welding procedure qualification.
1985736f-e684-598d-8731-a40114d4b6cc | note | g) The suitability of the deposited thickness of a single layer of weld metal, whether deposited in one pass or made up of several parallel beads, has been validated by the welding procedure qualification.
fc433687-c801-55ca-a25c-8234206867d7 | note | h) The direction of welding for all passes are upward during vertical welding. The width of the deposited weld metal did not exceed 12mm for all vertical up welding.
d0e5f778-b119-5645-b310-9d5d03f4d7d3 | note | i) Exposed faces of welds have been made reasonably smooth and regular and comply to ISO 8501.3, Treatment Grade P3, where protective coating is to be applied, unless weld quality as in Table 6.2.2 allow otherwise.
5503b391-82a3-51b9-aefc-969164ec2c75 | note | j) Weld sizes conform as closely as practicable to specified dimensions and is not less than the specified dimensions at any place.
e9f77c45-6914-5b56-aa7a-5cbcc07484f2 | note | k) Butt weld run on and run off tabs have been removed after the joint has cooled and the ends of the weld have been finished smooth and flush with the faces of the abutting parts.
35291e6b-982a-5140-bbf0-43b444460f9e | note | l) Butt welds have been finished smooth and flush with abutting surfaces where required for assembly, or where specified on the drawings, or where the welds are on the exterior faces of exterior girders.
c668ab04-b6f9-51c7-b5f7-433ae04154c7 | note | m) All welds not specified on the drawings, including tack welds, welds for temporary attachments, arc strikes and similar have been made using a qualified welding procedure (WPS). Any defects such as arc strikes on external or accessible surfaces have been addressed flush with the surrounding steel, without under-flushing. Magnetic particle inspection or liquid penetrant inspection has been carried out on the repaired areas in accordance with Table 630.182. Welds containing imperfections exceeding the limits in Table 6.2.2 of AS/NZS 1554.1 have been repaired.
15217835-b554-5865-a623-02fdcffb866d | note | n) All weld spatters have been removed from the surfaces of the weld and the parent metal.
cb166171-7cb7-50f2-a9da-000b48bcebaf | note | o) Stud welding and stud shear connectors comply with the requirements of AS/NZS 1554.2.
9d6a2812-a626-5508-bbca-b1a8f1bf0244 | note | p) Ground or earth clamps have been connected directly to the work piece being welded.
8b99c690-f8f2-5218-9763-5ec30732662e | note | Freq - Each lot
83d45c86-5e7c-5619-98fe-9045526c3fa3 | note | CIGFAB Key - H
e3842b7d-a65e-5edb-959c-aa0059a3f5d7 | note | CIGFAB Resp - SE
28883e3e-4c8b-5bbb-b1d9-a557b88b878f | note | Symal Key - H
73dcf8fc-62dd-5c38-a3c2-3f1da7c4bfd6 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.08 - Pre-closure inspection
560ff047-2ec4-5849-b62c-3e40876b2977 | note | Ref docs - 630.20 HP 13
2b8c554d-6038-5e16-9f6c-d88f4bdb92ef | note | Acceptance criteria - All sub-components that form the internal components of a gantry (ie fixing plates, diaphragms, gussets, stiffeners, conduits for cabling, etc) shall be checked and verified for location and dimensions as a pre- closure inspection, prior to attaching and welding the last plate to a fabricated box section (column or beam). This inspection shall be carried out by a person (the Surveillance Officer) accredited for surveillance of structural steelwork to VicRoads Technical Bulletin TB 46 by an organisation certified to AS/NZS ISO/IEC 17020.
e378e6b1-444d-5044-b0d1-10837150a4c1 | note | The below were undertaken as a minimum during the pre-closure inspection:
21d94d2b-c618-5da9-b0fc-192ae8977b6a | note | i) Live stream video, as a non-stop recording (ie no edit cuts), of the beam box internal sections prior to the fitting of the last plate showing the exact location of all gussets, diaphragms and stiffeners including covering welds;
27ff6b91-37d5-570f-9a3f-4f713e14f391 | note | ii) Detailed photos of the measured location of all components such as internal gussets, stiffeners and diaphragms;
f91e8260-232d-5357-92fa-032949fd47e0 | note | iii) The video stream and the photos are showing gantry identifiers and accurately time/date stamped;
752b9810-9dc6-5d81-bfbc-a17637b646e9 | note | iv) Any non-conformance to drawings are notified to the contractor for resolution.
48e2563f-4802-5ab3-bc6c-a96379a184f0 | note | v) Pre-closure details for each gantry is reported separately. Report for inspections on different days clearly identify what portions were inspected on each day; and
552a21a9-77f1-5fdc-bec0-9423fe39accd | note | vi) This information forms part of the Fabricator’s Data Report.
20bd52f3-a5c2-5d44-b6ca-25841c7e443f | note | Freq - Each lot
4cfb6b3b-2542-59b3-bc9c-18e62175acda | note | CIGFAB Key - H
f3e95c47-b808-5b1c-9b97-abe88c1e25f1 | note | CIGFAB Resp - SE
a5e30432-31ab-5ebd-a2c2-0141fa501161 | note | Symal Key - H
3d8d19c3-da05-58c6-a482-8d35ed165f2e | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.09 - Surface preparation for installing fasteners
4348e795-dc12-57f4-ad4b-489f40d1e357 | note | Ref docs - 630.21C
e20f8f96-e483-5c60-938d-c096a96ecd16 | note | Acceptance criteria - i) Any defect or foreign material has been removed from the contact surface and made "as rolled".
6d8380ce-544c-5dda-8bd2-e7a1d3df6433 | note | ii) Burrs larger than 1.5 mm have been removed or reduced to 1.5 mm or less by grinding.
34dd7490-872d-52e9-a235-e2b74f7d7d14 | note | iii) Applied finish for corrosion protection has been tested to establish the friction coefficient or slip factor for friction-type connection.
421bd5de-85a2-54c5-a8fd-adf50748c9c3 | note | iv) If applied coating is to be kept out of the contact surface area for friction-type connection, the coating including overspray has been excluded from areas closer than one bolt diameter to any holes of the contact surfaces of high friction joints.
f14718a4-9078-526b-895d-e61ccc1007e1 | note | v) Galvanized contact surfaces have been roughened by means of hand wire brushing if required by friction co-efficient testing for friction-type connections.
5939ad8f-7b0f-585b-a784-fcee6a508a0a | note | Freq - Each lot
71b2a019-9027-560b-b879-f1b15021a125 | note | CIGFAB Key - I
c7394d4b-88c9-5db9-afc6-f6537098f9f5 | note | CIGFAB Resp - SE
a4ca14f4-fbb6-51ca-8c47-4ee22360e826 | note | Symal Key -
c0df8eff-291c-51fa-9c86-407d147afebb | note | SI Key -
| checkpoint | 3.10 - Freedom from defects
fcae8e7a-ba81-52f2-8ef7-027630c4eb98 | note | Ref docs - 630.07
cf5dd07d-5ffc-53d4-ab36-536779ae4749 | note | Acceptance criteria - Steel has no defects as per the below at any stages of fabrication.
e1cb77a3-d5bb-5c0d-9c27-3fc1f77103d3 | note | i) Clause 8 of AS/NZS 1163 - For Cold-formed structural steel hollow sections;
b1ab299e-a3a2-541b-ad6d-1ee6ad56730e | note | ii) Clause 2.4 of AS/NZS 1594 - For Hot-rolled steel flat products
b1921740-83d5-57e4-905b-58cddec24edb | note | iii) Clause 9 of AS 3597 - For Structural and pressure vessel steel - Quenched and tempered plate
398a7e5c-dae3-557f-9e19-1b9b3b4e9f75 | note | iv) Clause 8 of AS/NZS 3678 - For Structural steel - Hot-rolled plates, floorplates and slabs
65e5242a-4346-54a4-bbe0-7d4a0047e13b | note | v) Clause 8 of AS/NZS 3679.1 - For Structural steel - Hot-rolled bars and sections
1d306f24-b60e-547d-b003-b6b3cb4067e9 | note | vi) Clause 8 of AS/NZS 3679.2 - For Structural steel - Welded I sections
b14deea0-181b-5b2a-8153-a5de7ec0c1b4 | note | Freq - Each lot
295b12b1-f6ec-53d5-807c-495fd55d1199 | note | CIGFAB Key - I
39967d56-c7fb-5ecf-aff8-5533a7e75ec1 | note | CIGFAB Resp - SE
784c35e0-31b3-5957-b1e9-96d8ea9d5ac8 | note | Symal Key -
d7c18909-f265-5e88-9721-a6e8e726a83f | note | SI Key -
| checkpoint | 3.11 - Tolerances
403dad52-93f0-5987-b22a-1a712b8d3724 | note | Ref docs - AS/NZS 5131
d9effa84-4891-541d-b521-4279ce08911d | note | Acceptance criteria - Geometrical tolerances are within the limits of Appendix F of AS/NZS 5131.
f56c1cfa-0ef6-5e12-b0eb-2708869cc5cf | note | Freq - Each lot
b205ff88-9172-560f-ae92-1cb5fce32c67 | note | CIGFAB Key - I
18639b60-aa41-5ccd-ac46-037b8a2dabc8 | note | CIGFAB Resp - SE
f7f35cbc-4477-5c34-ab30-38825982d28b | note | Symal Key -
dad0dc2b-abc2-507f-88d3-4fdfa88bc8c8 | note | SI Key -
| checkpoint | 3.12 - Testing
89d75a4a-f018-57fd-ae50-a855649fd1ac | note | Ref docs - 630.18
d811417c-8476-5a6c-9100-392ff03656eb | note | Acceptance criteria - All other testing is -complete.
1ea48acb-fd2f-5cf7-80aa-0d833bc80f08 | note | ○ Frequency of testing has been checked for all testing in the testing tab.
f8813bd1-118e-5a54-9c4b-6ff1a09950f8 | note | ○ Test certificates for all non-destructive inspections and dimension inspections have been submitted to the Superintendent for review at least two days prior to the steelwork being transported for protective treatment.
10633bdb-4e76-5e34-97aa-2bbaef194698 | note | Freq - Each lot
a90dd144-a56c-56d2-8cce-a21caef95071 | note | CIGFAB Key - H
248682a8-d91c-5974-90cf-89b0c9d62db1 | note | CIGFAB Resp - SE
ba17fdc1-7f74-536c-98eb-270f54bba269 | note | Symal Key - H
1c960fbf-3aa8-5316-af29-db8c813685ae | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Repair of non-conforming welds
3a6afd06-ee4d-5395-8795-671d08910611 | note | Ref docs - 630.17, 630.18
b465e92a-4b79-58ab-a37e-d633bcafb180 | note | Acceptance criteria - Repair procedure for non-conforming welds identified in visual or NDT inspections has been submitted to the Superintendent 5 days and 3 days prior to the repair commences respectively.
575bf6fd-e6db-589d-87fd-aa5391a5b971 | note | Freq - Each lot
76cdc073-53e7-5307-b041-669c45e2be05 | note | CIGFAB Key - R
c9d1e0e6-261f-5d92-93af-0b3bca017dcd | note | CIGFAB Resp - SE
11081061-dddb-5815-94c8-bed3a45ec46a | note | Symal Key -
437b227f-de49-5eca-b14b-8f2d4058ec25 | note | SI Key -
| checkpoint | 3.14 - Re-inspection
6883814d-fec0-50f0-bc7d-dd67ae4211aa | note | Ref docs - 630.18
bafd03cb-78ac-5d23-b3ca-72e44362261e | note | Acceptance criteria - The full length of repaired weld has been re-inspected by NDT methods.
02a0d941-bec9-58ba-9126-63452bab1204 | note | Freq - Each lot
0e1d02b1-05e5-5d27-b0ad-af36ec6eab4e | note | CIGFAB Key - I
2b0c1d3a-dd54-5e3b-83a6-74d1006c4891 | note | CIGFAB Resp - SE
7e11aa26-dad9-5c12-85b8-8e13079a354b | note | Symal Key -
c3446294-e433-53ce-976b-fce38652feca | note | SI Key -
| checkpoint | 3.15 - Handling, transport, and erection
561365d7-5740-5b1c-bdee-046d22f6279c | note | Ref docs - 630.09 HP 12
a1163958-8163-54d0-ba50-0a7e23706edf | note | Acceptance criteria - i) Steel members are not stressed or deformed beyond the design limit.
f04167cd-3743-51a8-8192-1ff29d639fcb | note | ii) Protective coating is not damaged due to handling, transportation, and erection.
1cb05402-8ea5-58dc-97ce-cd6bcf294ea9 | note | ○ The Contractor shall submit test certificates for all non- destructive inspections and dimension inspections to the Superintendent for review at least two days prior to the steelwork being transported for protective treatment.
61b0ba85-e37a-5c16-9c43-b8bc3acfeff7 | note | Freq - Each lot
9baa34e6-ddc1-5ae5-addf-e4d8522aba2f | note | CIGFAB Key - H
6460d807-1fc0-50a5-a669-cb733aea45b2 | note | CIGFAB Resp - SE
5b4abd55-0083-5f96-ac62-19f63a584397 | note | Symal Key - H
b5681484-a4c5-5e19-bcfc-0b2e88b04204 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.16 - Fabricator’s Data Report (FDR)
1bd1232d-0e38-50c9-b17b-e9978db6874b | note | Ref docs - 630.22
7d00e2cf-5926-5bf6-8aed-3eb25a971220 | note | Acceptance criteria - Up to date technical details and record of activities are recorded in the Fabricator's Data Report (FDR)/Manufacturer’s Data Pack, indexed to Section 630, in English, SI units and legible, including but not limited to the below.
bac901f6-f685-5532-b86e-f87fb8d018f5 | note | i) Structure or component name, identification and intended location for erection;
61c3cce7-b4df-5677-ae85-a4a5749438c7 | note | ii) Name and address of fabricator;
c6e4e873-6e20-593e-9be4-f688f5cc66b4 | note | iii) Relevant drawings approved for construction
59da8b73-1598-53f1-a94f-d401e91379b4 | note | iv) Fabrication specific procedures included in the QUALITY PLAN;
bca3db11-673b-5df6-8513-199364dc3fa9 | note | v) Inspection and test plans (ITPs) and documents detailed within the ITP
97f76451-969a-54b6-8e2e-ac0a9ff0862b | note | vi) Qualification of relevant fabrication personnel (Welding Coordinator, Welding Supervisor, Welding Inspector, NDT operator and welders);
7fa570c0-9c29-5abe-8879-73a39e3c3f1a | note | vii) Any deviations from the Specification and the corresponding approval for the deviation;
170ec86f-cb7e-50fa-b823-b34455ca0539 | note | viii) Material test certificates, including for steel supplied to the Works, and for bolts, nuts and washers;
6b920076-4298-5aed-8093-978f361ea99f | note | ix) Welding records, including weld maps, welding procedure specifications, welding procedure qualification records and relevant test certificates, welder qualification records, and welding consumable certificates;
a1b7f10e-c656-5868-9fa7-bee79717847a | note | x) Non-Destructive Examination reports;
ebe1c3c9-9fe4-58a0-9163-f5b9bb567df3 | note | xi) “As constructed” drawings of the fabricated members;
54ce760e-e3d7-5dbb-8be4-77339497d4f2 | note | xii) Nonconformity reports and outcomes of corrective actions;
38665952-ea9e-5758-8c13-f963c0d968f4 | note | xiii) Trial assembly records;
326ba153-df13-5df9-bda6-715cf6b8b681 | note | xiv) Instrument calibration certificates;
89aa85f3-b9c7-5815-a8c9-4c6d90c40518 | note | xv) Inspection and testing records, including measurements of dimensions compared with relevant tolerances;
86daa9b6-c25d-5477-ac7a-78e0b1b595f9 | note | xvi) Pre-closure inspection records, when appropriate;
84305f16-5bf9-514f-82d2-2af7693e9dc7 | note | xvii) Delivery/dispatch records.
7fd1031e-8898-5094-b334-7e96b46cc29a | note | Freq - Each lot
4789ae53-3b5a-54c9-9122-997972cde6c2 | note | CIGFAB Key - R, I
15fcabe5-65f0-5247-b040-15b32024095b | note | CIGFAB Resp - SE, SE
64a6c74f-a22f-5064-a06f-5caab290819e | note | Symal Key -
7c94a232-3dbf-5637-ace7-cbec2f4ec667 | note | SI Key -
| checkpoint | 3.17 - Fabricator’s Data Report (FDR)
c9d0f82e-12a7-579c-9e1e-adc8df2b8f04 | note | Ref docs - 630.22
534bf1ad-7c4c-5924-a2c7-dc07ef80a482 | note | Acceptance criteria - The FDR is submitted to the Superintendent in digital format within 4 weeks of completion of the fabrication work, including any detailed table of contents if requested.
f61d36a1-d936-5d89-88eb-73172285cfa4 | note | Freq - Each lot
60437c82-39e8-565f-a335-2dfa138568cd | note | CIGFAB Key - H
ea1e2d3e-68bb-5229-99ca-d79cd306436d | note | CIGFAB Resp - SE
e5fa563d-1af5-5270-b141-90eea74a97dd | note | Symal Key - H
0f136c3f-65c4-58e6-8290-179ee4c352b1 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Post construction activities
| checkpoint | 4.01 - NCR
cc611eb8-8002-5ee9-944f-567bb88ee5a9 | note | Ref docs - 160.A6
db1dc42d-aaab-5c3f-8731-acf7095274ed | note | Acceptance criteria - NCR (s) has been raised for all non-conformances.
1aa1a279-65f0-5e03-a05c-e2938dbfb72f | note | Freq - Each lot
197d4ec0-db32-576d-9cf0-03e68ec11b33 | note | CIGFAB Key - H
c37cd65c-08d1-5dbb-9ca0-bd0be7166335 | note | CIGFAB Resp - SE
246e1c22-aa37-530d-be46-3779cf420f68 | note | Symal Key - H
ce05aec7-ea4c-5af8-ba65-c7f4aad02c72 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.02 - REWORK
cbea0a5b-9438-533c-8d1d-dd2c080d7acc | note | Ref docs - QMP 630.17, 630.18
a535b6d0-2440-5986-aed5-d4a81b4b9a43 | note | Acceptance criteria - Lot has been reworked if did not comply with specified requirements.
1f8d1faf-c761-5c93-aa61-19946e0013f6 | note | Freq - Each lot
7f5faa7f-28f5-5067-a6da-c47ca97ac8db | note | CIGFAB Key - H
5d89b8aa-6e2f-53bf-b11d-df747e50bef9 | note | CIGFAB Resp - SE
db1f099a-5c0d-5043-aeb3-83beafb3f202 | note | Symal Key - H
02d355a3-0f3d-5f34-a2b3-9fdca90a78c4 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.03 - RFI
11a0674e-acbb-579f-a8cf-11787f90c6a4 | note | Ref docs - 2010.07 d(v)D
5cf3231d-5751-5b34-9406-9107decdd10b | note | Acceptance criteria - All RFIs related to the lot have been closed.
24036cf3-351b-5495-9513-92fc4b093dff | note | Freq - Each lot
632f4477-b880-5c43-adb8-8f1fd68ab5b0 | note | CIGFAB Key - H
4d42424b-2bb2-5fef-98dc-851ddf9df5f7 | note | CIGFAB Resp - SE
94f1168c-1954-5c7b-98c6-6059fac814ef | note | Symal Key - H
d24522a8-6ac3-5b0c-a088-a93dc4f73fc9 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 5.0 Work lot closure
| checkpoint | 5.01 - Lot verification
f453ac81-61c6-5459-a268-738b16b146b7 | note | Ref docs - QMP
9584dc36-0219-538c-a8b9-4178c9115cde | note | Acceptance criteria - Quality documents have been received, verified, completed, and signed off.
6795eb5c-ce28-5579-a5d0-f1cf780ec775 | note | Freq - Each lot
a8d8b72d-fb89-5907-8b9e-ae61fc57f67f | note | CIGFAB Key - I
e2eccebe-4b2f-507b-b037-47c420a8f580 | note | CIGFAB Resp - SE
1bbf3486-d8f7-5d29-96ff-774e077f693d | note | Symal Key -
7df596f7-9f69-5ce6-b108-192da08024b8 | note | SI Key -
| checkpoint | 5.02 - Lot Submission
21200a7e-85d5-5d1a-a7dc-8dacfeb222cf | note | Ref docs - QMP
3d0b5c22-75e3-5241-8670-fa3fa734cdd7 | note | Acceptance criteria - Quality documents have been uploaded to team binder.
294e8ca4-6ee2-52cd-9deb-cb205e1c177e | note | Freq - Each lot
3eb410a1-a6b6-5437-998a-a6f20f13b852 | note | CIGFAB Key - I
9ecf1973-e0a4-59af-b30c-5f0b859e25c7 | note | CIGFAB Resp - SE
032738a6-27c8-515a-83a5-28dca776a832 | note | Symal Key -
e637c75d-6f0a-5f44-9320-12998acd6305 | note | SI Key -
| section | 6.0 Completion
| checkpoint | 6.01 - Conformity with IFC Drawings and Construction Tolerances
697dc83c-d42a-5f8c-8db7-7bd2cd35a3bf | note | Ref docs - VR Clause 610.47, Table 610.474
e590cee2-e73c-5634-afba-28c645822fc5 | note | Acceptance criteria - Precast elements shall be landed to confirm to the levels, grades and cross sectional specified or shown on the drawings with the following requirements.
f2f135fa-1e13-56d2-9c80-cc60195b4c24 | note | Freq - Each Lot
0d179188-a985-55aa-807c-17e8a4720f75 | note | CIGFAB Key - R
f08f4a3f-9070-5183-8d4b-3a1d2897ede7 | note | CIGFAB Resp - SE
535b385a-6f52-5704-b8d8-ac087e410e53 | note | Symal Key -
2586878d-00d5-5bdd-9dcb-08c8b3d91787 | note | SI Key -
| checkpoint | 7.01 - Product Non-Conformance
125a0bf8-1da2-5327-9042-7622e511bdb8 | note | Ref docs - QMP
8a223cff-201a-5faa-a2e4-fdffcb2284c9 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
b5bce64d-4ad8-5e1f-a85d-604dbbd0395b | note | Freq - Each Lot
4a78f520-6b07-50ff-85d3-21b65155cce0 | note | CIGFAB Key - R
57ab71cd-a75c-5b37-95ff-f5c2c4ccf0ce | note | CIGFAB Resp - PE
73676731-de88-5b91-84a6-186c3ed15d02 | note | Symal Key -
1c54e5ad-54cb-5b8b-aa32-86a97ebdbd35 | note | SI Key -
| checklist | 1630-P200-SYM-QAC-ITP-0015 Precast Stormwater Drainage Pits | itp | 1630-P200-SYM-QAC-ITP-0015 Precast Stormwater Drainage Pits |  |  | 2451c140-96d4-4351-8545-ddea0bf57254
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Design
c4c87fb5-dadc-5fe0-8fb1-23433361b853 | note | Ref docs - 705.08(a)
6f9eedff-44c6-5b20-b875-f052e88c6b57 | note | Acceptance criteria - Design has been provided, including Proof Engineering (by prequalified VicRoads engineer) to confirm that all requirements of AS5100 and additional loading requirements have been met.
8546f544-06ab-5f1e-b7e5-aa40d016a218 | note | Freq - Each Lot
bb8a192a-bdc9-5f57-b651-90d4fc7121a3 | note | Key - R
43e84a19-35f5-56f2-be1a-0ec2cd82b619 | note | Resp - SE
3f8d9ad8-413a-52e5-9392-fd19310191b6 | note | Remarks/record - Design
0a97706d-d509-5ad5-be28-88e4d7c1abdb | note | Remarks/record - Proof Engineer Certificate
8ea5b34d-fca2-5cfd-a4dd-48ec23766f70 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
c8065e8c-5a49-5248-98bc-4377752c814a | button | Lot map | Yes,No,N/A
5d0f6f46-c5ea-529e-b913-ff747475163c | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
5532ea74-bd2d-5797-9fe9-37ecc7c3c48f | button | Environmental permit | Yes,No,N/A
c6da9d80-b82b-58a5-ac41-78f7e87b7790 | date | Inspection Date:
| checkpoint | 1.2 - Concrete Mix Design
36aaf60a-d80c-555e-acae-8d8cf4db3631 | note | Ref docs - 705.04(b)
86532d9c-cdbe-5dba-887b-27195e9c6ac7 | note | Acceptance criteria - The concrete mix design used by the pre-cast supplier is approved and current in accordance with the requirements of VR610.
2a72d99d-4d92-59e3-8bb3-bce0e607e23a | note | Freq - Each Lot
deb4eb81-72bd-54c2-9a6f-37065e07af7c | note | Key - R
33b29f07-d8f2-597b-a5c6-56fb2bb2d6db | note | Resp - SE
2ec4ab79-6ac9-53e8-ad4b-a52a01aae0ed | note | Remarks/record - Concrete mix design
532bcb68-0ff7-570f-bb01-7cd53ca0752d | date | Inspection Date:
| checkpoint | 1.3 - Concrete Supply
76fcdcd9-7888-5377-88ab-814568f0bdc1 | note | Ref docs - 705.04(a)
cc637b2f-5e20-5e4f-84c9-ecf33259bdc0 | note | Acceptance criteria - Concrete has been provided in accordance with VR610 and VR705. The minimum grade of concrete is VR450/50.
9e7e34c0-d4aa-51d6-9f49-b69d46419ab0 | note | Freq - Each Lot
e088742b-cd12-554b-a6c6-0fe70fdf2fd6 | note | Key - R
f04c4339-cb43-5019-8721-be0755198138 | note | Resp - SE
45263553-b465-5297-a99c-c2319419de56 | note | Remarks/record - Compliance Certificates or Dockets by Supplier
bf0bfad6-e1a2-568b-a90a-ec2cd11a8076 | date | Inspection Date:
| checkpoint | 1.4 - Fibres
606cbb8c-8f13-5c33-b361-d495329a1fc8 | note | Ref docs - 705.04(f) 705.08(d)
42d05a32-2a33-5e46-aaf1-d53251894381 | note | Acceptance criteria - Fibres comply with the requirements of ASTM C1116 and have been supported with documentary evidence confirming their long term resistance to deterioration when in contact with the moisture and alkalis present in cementitious paste or the substances present in chemical admixtures.
3d3d5c4a-36e5-591d-bdb9-8e691d54fc47 | note | • Fibres have been tested to the requirements of ASTM C1609 (flexural toughness) and ASTM C1399 (average residual strength of fibre reinforced concrete) and comply with the requirements of AS 5100.
4eb3e1d2-2320-52bb-976a-827e519ce465 | note | • Evidence has been provided by the supplier than the minimum fibre content has been achieved.
80fb8845-42cb-5b05-936f-4f8439b2abac | note | • The worksheet and/or report for determination of fibre content shall be submitted to review by the Superintendent.
b51b0a92-22d4-5ec3-9987-1adb363f02b7 | note | Freq - Each Lot
90b8b4d1-4e44-5299-a7ec-e5272288c4b6 | note | Key - R
71102c05-8ebf-5180-8d21-95a79aadec81 | note | Resp - SE
ef7ec0e2-aae8-54f0-9e96-aa8a3792d5d0 | note | SI Key - R
0cf4ef8f-0da9-55ae-b271-8c05573d4a14 | note | Remarks/record - Compliance Certificates and/or Test Reports
fddf9b45-a119-5067-b796-d098b61b2203 | note | Remarks/record - Worksheet for determination of fibre content
654dee8d-eecc-5746-a5e3-8dca00593e58 | date | Inspection Date:
| checkpoint | 1.5 - Wall thickness
8285db7d-c6cb-549f-b202-2b7a06f08640 | note | Ref docs - BTN033
655bfb2d-93aa-5f51-bde9-4b81d36b2e22 | note | Acceptance criteria - For concrete drainage pits up to 2 m deep, the minimum wall and base thickness must be 100 mm. For concrete drainage pits more than 2 m deep, the minimum wall and base thickness must be 150 mm or thicker if required.
6389ff46-f1d0-58b3-80cd-2ca65cc94195 | note | • Where the depth of the concrete drainage pit exceeds 2 m there may be a need to adopt two different wall thicknesses in the construction of the complete pit. The wall thickness at the bottom will need to be a minimum of 150 mm thick whilst the wall thickness of the riser must be a minimum of 100 mm thick.
7505c325-18a2-5bab-869f-b5b0101dd5c2 | note | • The depth of drainage pit must be measured from the bottom of the pit towards the surface. The bottom 2 m must have 150 mm minimum wall thickness.
6c570f0a-d3fc-51af-9439-269e305883aa | note | • Where the depth of the drainage pit is over 2 m in height then it is acceptable to construct the complete pit as one section with 150 mm wall thickness.
ef4bf2c2-e3cf-5c7e-9d5b-6ca742bb7d36 | note | • Where the depth of the drainage pit is greater than 4 m, the wall thickness and reinforcement requirements must be structurally designed and Proof Engineered, but not less what has been specified under Section 5 for unhaunched concrete drainage pits up to 4 m in depth.
6faed019-5117-59a6-aea8-4f9682db958f | note | Freq - Each Lot
b4872027-28c0-57aa-a47b-93a97fb5aa90 | note | Key - R
b612ccda-6801-5b9a-ad08-a0c5e8d860e3 | note | Resp - SE
5e86f124-3e4e-5656-91d0-4b64a59b1ccd | date | Inspection Date:
| checkpoint | 1.6 - Supply Precast Covers, Grates, Lids
5026090b-8741-57c0-badf-2cfe4e49dd92 | note | Ref docs - 705.04(c)
8dc4b6c8-98b9-532e-8b51-e46da0e0dc80 | note | Acceptance criteria - Pit covers and grates have been designed in accordance with AS 3996 and table 7 from BTN 033.
d80cd302-27b1-5c46-aada-95b91079cfe4 | note | Freq - Each Lot
13a9da6c-4ccf-5c6c-9188-d22f2b941c6b | note | Key - R
fd1d3b95-acdf-50dc-b91f-9d0cb9d36c16 | note | Resp - SE
ad39a473-2698-5361-b991-a79c64d4b1db | date | Inspection Date:
| checkpoint | 1.7 - Step Irons (pits greater than 1.0m)
e21df7ad-b9f9-5131-a2bf-4eff23926249 | note | Ref docs - 705.04(d)
8e122a32-a2aa-5678-a2c6-dfe3522cd375 | note | Acceptance criteria - Ensure step irons are manufactured from steel AS/NZS 3679.1 grade 250. Step irons are hot dip galvanised as per AS/NZS 4680 or 13 mm steel bar covered with polypropylene shall be approved by design.
ab8c49ae-4162-50ca-9c2d-5f73e2be925a | note | Freq - Each Lot
13634822-1dde-5801-8b7b-374c374b3e16 | note | Key - R
f6c38933-927e-5648-8830-76456b1f8ae9 | note | Resp - SE
d158241f-6bdc-5251-8f46-9b6ea75ffec5 | note | Remarks/record - Compliance Certificates Superintendent Approval (for polypropylene step irons)
d1cfc2d4-5723-5e24-97ec-d7241b3128f4 | date | Inspection Date:
| checkpoint | 1.8 - Weep Holes
2d8e3d98-08ea-5cc1-ad09-9cb13e17e254 | note | Ref docs - 705.09(c)
fd84f395-1ad4-5706-8523-f6ba786d26f2 | note | Acceptance criteria - Weepholes of 50 mm diameter shall be provided in all precast pits and shall be placed between the midpoint and top of the stormwater drain in those walls which have openings for drains.
1fc2162e-0411-581c-8063-0c5b13a96658 | note | Freq - Each Lot
ad94d417-b8bf-58b7-bdb9-42acb85fa003 | note | Key - R
56b2a246-81a2-5bfa-9169-32f044938856 | note | Resp - SE
736fe747-dc5c-5ea2-bce2-081bb1f3f8c4 | date | Inspection Date:
| checkpoint | 1.9 - Segments
407c67f2-fd65-5076-8dc6-9234b71cb0fe | note | Ref docs - 705.09(b)
42a21176-1180-50bc-bc5f-b8cb046d42b0 | note | Acceptance criteria - If a precast drainage pit is cast in segments, each section of the drainage pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15 mm shall be used.
59140a36-ff4c-5364-ac16-f9b164153e64 | note | Freq - Each Lot
f60749d7-6c17-54ba-83d2-f40bf358cb8d | note | Key - R
5ec00a63-a4fd-5d7f-8918-d3b3d59d2ed0 | note | Resp - SE
2ab53413-cc32-55fe-bc38-55f2cc2d4738 | date | Inspection Date:
| checkpoint | 1.10 - Repair to Defective Pits (if applicable)
2e18e2dd-2386-5590-b3fa-1a767a3c4c36 | note | Ref docs - VR Clause 689 687
fe81a189-2980-5c9b-b031-576ad5328d27 | note | Acceptance criteria - Any Pits damaged due to handling onsite post acceptance at delivery of non-defective product are to be repaired as per the approved Cracks and/or Patch repair procedure. A Non-conformance to be raised for the defects identified and issued to the State and IR for information and refer it to the Designer for assessment.
04ae2a45-b271-5af5-9eb0-a19b0e109a6f | note | • Prior to any patch repair of concrete, Symal shall assess the damaged pit to determine the influence of spalled, deteriorated, damaged or honeycombed concrete on load bearing capacity, serviceability and durability, and submit the assessment to the Superintendent for review.
78248d72-e392-52af-b0f4-73a3e4617aae | note | • The Designer and the Engineering team to agree upon an appropriate repair treatment(s) and materials, consistent with the requirements of VR Spec. Section 687 and 689.
bf74d206-c2a4-518c-ab6c-fab6f7ed5189 | note | • Complete ITP for either crack repair or patch repair.
75a072d8-d133-556b-a595-1b7aeb9034f9 | note | • Measure, document and photograph the dimensions and condition of the defects.
1a858ce3-f08c-5fab-ae55-6b11b9bba182 | button | Has all of the above been completed and approved? | Yes,No,N/A
2b1cea1d-f65a-570d-bbbd-52e8888fae39 | note | Freq - Prior to start of works. Each Lot
2a8f29cd-8740-5c2c-b36b-c81fdee2f9cb | note | Key - H W
b5297e82-0e09-5839-82a3-8c28c478bbb0 | note | Resp - SE
960a2d8e-0847-5bde-a478-eaabec297737 | note | SI Key - H
25ec1ea1-2e19-54b8-88f4-03f4d5146f24 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Excavation
| checkpoint | 2.1 - Conformity with Drawings
6ff3e672-dc1e-51d3-839a-57d5c2c49c21 | note | Acceptance criteria - Prior to commencement of excavation for the pits the Contractor shall confirm the position of all pits with the Superintendent.
22bd148e-8817-5e83-8022-7fa25806cf24 | note | • The location of each pit may be altered to suit site constraints ±1m with both the approval of Survey and the superintendent.
294b791a-8c5d-56d5-b8c7-13e239a1009d | button | Approval to proceed? | Yes,No,N/A
546fc7d1-3707-5ac2-b17a-f816c99dafc9 | note | Freq - Prior to start of works
12246ffa-3cc2-5084-8c4f-b8e457a66305 | note | Key - H
66363737-2869-5605-93a2-a168528211bc | note | Resp - SE
c0d04504-59dc-5b9c-88b4-c8c287dd27b2 | note | SI Key - H
1ac7cae7-13eb-581f-a703-94ed873a91b7 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Excavation for Pits
f6c62df3-3e71-50dc-bf6b-485a37755901 | note | Ref docs - VR Clause 705.05
8a0b79b2-60b8-5fc8-a1d3-b00bcdb74ec8 | note | Acceptance criteria - Excavate to required depth which shall also include excavation necessary to prepare the pit foundation & provide the full specified depth of pit bedding. Maintain excavation width clearance. Excavation for pits shall not be less than 400 mm from external wall to side of excavation.
998a6ba7-fbd6-5bc3-81de-bdba76e2b4b5 | button | Has all of the above been completed? | Yes,No,N/A
c0b679ad-708d-57df-9b4a-96c8662b80c3 | note | Freq - Each Lot
afdde096-ed4c-5df4-b3e4-af54084a16c5 | note | Key - S
9da36e9b-394c-57bc-b2eb-e40e0e919cee | note | Resp - SE
3cb3a2e7-7895-5224-8073-d6df85dcd5d6 | date | Inspection Date:
| section | 3.0 Bedding
| checkpoint | 3.1 - Bedding
80dfbdfa-5416-56e5-838a-4d754f9d759b | note | Ref docs - VR Clause 705.05 Table 701.091 & 701.092
d6e76c0f-aa15-5044-a8dc-b37e5f25aae4 | note | Acceptance criteria - Bedding placed and compacted to a thickness not less than 80 mm on clay foundation or 150 mm on rock foundation.
6211ed6b-b214-5a38-9751-e56c5f1f36c8 | note | • Bedding needs to conform to Table 701.091 & Table 701.092.
e9099129-2c15-5739-b10f-ee7625000ac8 | button | Has all of the above been completed? | Yes,No,N/A
54be929e-efc1-5026-9ddc-83036dcdbecf | note | Freq - Each Lot
272ce974-a9e7-5e4a-9c98-0388cf857725 | note | Key - S
f7aad43f-57e8-5d9b-8a8b-3744961ea0f8 | note | Resp - SE
712eaff3-cba6-568b-9531-f7f925d3f37e | button | Remarks/record - Bedding and Backfill Material Conformance | Yes,No,N/A
9dbaa96f-02c1-5396-870a-c2853bef5ab8 | date | Inspection Date:
| section | 4.0 Installation of Pits
| checkpoint | 4.1 - Installation of Pits
4bb3c86c-52b0-59bb-9869-dd77557520c2 | note | Ref docs - VR Clause 705.07 705.08 705.09 705.11
2161dce2-efd1-55bf-98b0-1b4d2e32393c | note | Acceptance criteria - Precast pits shall be installed at the locations and to the dimensions shown on the drawings.
4f86518d-5044-584f-bdb2-e7a0875ba54f | note | • Subsurface Drainage Connections – Holes for subsurface drainage shall be 150 mm diameter (cored not broken), unless specified on the drawings.
86881686-c6a4-52bf-9c0f-222eb4b10dc5 | note | • Segments – If a precast pit is cast in segments, each section of the pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15 mm shall be used.
99b38b3a-b8eb-5d35-8eb1-6b9ef8785c45 | button | Has all of the above been completed? | Yes,No,N/A
42a50711-2ad9-5055-aecc-ee36e8fac32a | note | Freq - Each Lot
c157ad8c-09c7-5b9c-9304-e33cf570bfad | note | Key - I
1853a7a0-ad4e-5afa-a4d3-3abf33ed543d | note | Resp - SE
3100447a-3dfc-5668-8938-f36265c2c12e | button | Remarks/record - Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier) | Yes,No,N/A
f083a874-a0e2-57a4-9dea-d2ffa5bdba09 | date | Inspection Date:
| checkpoint | 4.2 - Pits with Risers
e66fab0c-14c8-5306-b989-41ad4db3380e | note | Ref docs - BTN033
98b54c3f-3c2f-53bb-9908-5e5884d43802 | note | Acceptance criteria - Where a drainage pit is manufactured in multiple sections with different wall thicknesses, the internal wall face must be vertically aligned, and the step in the wall thickness is to be located on the outside face of the pit. Joints must be sealed with cement mortar to provide watertight joints. No bonded anchors to be used for the construction of the drainage pits.
0fd37816-a118-5c18-a672-f530a2160263 | note | Freq - Each Lot
1cce5e35-2405-5596-bd78-8e0494f4c8ab | note | Key - R
15cdcaed-65a8-554e-9370-61d34d495d2a | note | Resp - SE
81d27583-79f0-5289-9180-38f23bbc1417 | date | Inspection Date:
| checkpoint | 4.3 - Step Iron Fitting
330e83fc-a66f-5e70-a5fa-41c96ed0b54a | note | Ref docs - VR Clause 705.12
0db24bcc-25cb-5914-9420-635f6f2f3d10 | note | Acceptance criteria - Pits greater than 1.0 meter shall be fitted with step irons. Step irons shall not obstruct openings or be fitted to a wall which has openings.
07046fd7-2e46-557b-a6d2-05a052b108a1 | note | • Step Irons shall be installed in accordance with the manufacturer’s instructions and shall be an approved proprietary type.
dbcfa8d0-f534-5465-956d-ae7a997c14c6 | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
02973095-82e0-513c-880c-192879c20473 | note | Freq - Each Lot
8c2130d6-8099-5511-913b-676adf831b21 | note | Key - S
d048ce73-3db9-5aab-a75e-9bbf3c87d373 | note | Resp - SE
aea4fe7f-a6a5-5769-a42e-150491ea5ca1 | button | Remarks/record - Material Conformance Certificates | Yes,No,N/A
9fda0814-496f-5fd8-a4bf-9bb8d38bff58 | date | Inspection Date:
| checkpoint | 4.4 - Shaping the floor
10402814-f54a-5b38-88d3-14e1ce923387 | note | Ref docs - VR Clause 705.13
583f9cf1-46dd-549a-bdc9-9f4c0539326b | note | Acceptance criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar, to provide a profile that will ensure smooth flow conditions between inlet and outlet pipes and prevent any snagging of debris. The cementitious mortar shall comply with the requirements of clause 610.33
80f67807-0d95-54ef-97fe-58cd2e6ae20a | button | Has all of the above been completed? | Yes,No,N/A
c00e04a3-b4e9-5b24-976d-cafba102a0ce | note | Freq - Each Lot
1516c909-ff92-5d5f-8f2d-8af4c7e73c93 | note | Key - S
ac8ff956-d6dc-59fe-a3a8-13aa5de72e40 | note | Resp - SE
f4b65c11-10ac-5bb8-838e-01d47790205e | date | Inspection Date:
| checkpoint | 4.5 - Jointing
480e23bd-37f1-58a4-bf7e-9ca797bf7851 | note | Ref docs - VR Clause 705.14 705.16 610.33
9fedef23-a59c-52f7-8a7f-2ebe265a178a | note | Acceptance criteria - The joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
df1cc141-09d0-5302-b62a-72230a37aaad | note | • Mortared joints and recesses shall be cured for a period of not less than 48 hours with no backfilling until the curing period is finished.
31d7b099-62e1-5098-b72e-64426e190386 | button | Has all of the above been completed? | Yes,No,N/A
3f843ed2-cc9e-5cb0-888a-3a3a4f8d0061 | note | Freq - Each Lot
4020d288-9af9-5c7a-8506-987bf9287c21 | note | Key - W
dd31c1a2-2d50-5232-b03a-21108eba248b | note | Resp - SE
117dee00-1258-5585-a34b-6856d089bf4d | date | Inspection Date:
| section | 5.0 Backfilling
| checkpoint | 5.1 - Survey Location Confirmation.
5581731b-f62f-5e81-98f5-037bd6160559 | note | Acceptance criteria - The location of each drainage pit shall be verified by a survey certificate prior to backfilling the drainage pit.
925be89f-6b2b-5dfa-8c7a-1937d946edb6 | note | • Offset of entry pits required to match lines of kerbs or barriers ±20 mm.
1bfe2c6d-bf7c-553f-9587-f7e99ef4417e | note | • Plan location of pits other than offsets to kerb lines or barriers ±100 mm.
0d96c718-ac02-5ba1-b5f5-c6d40aec099d | note | Freq - Each Lot
bebe0b16-97d4-5109-b92e-21279c9f1890 | note | Key - R
018c7694-befe-54fb-ae45-78dbc18fd884 | note | Resp - SE SV
43740099-8fc6-5c9c-99a5-0ed666b71d46 | button | Remarks/record - Survey Conformance Report | Yes,No
e903d022-15bb-5862-9527-6cf9039e2a3c | date | Inspection Date:
| checkpoint | 5.2 - Backfill Material
49478161-53c6-52e7-bafb-7f6498323610 | note | Ref docs - PS3030.07 (a)
25ca2e77-26ec-5e78-a160-e4f55396c5f3 | note | Acceptance criteria - Backfill material shall conform to the requirements for type A material.
fe6207c7-04ed-57e0-ab61-0fcb0b18be0f | button | Has all of the above been completed? | Yes,No,N/A
86445d82-ee5b-5aa0-9a5f-28c2f442a074 | note | Freq - Each Lot
22954d0b-4e3d-5c06-a719-ec05000e091c | note | Key - R
bf48ebc0-7bf1-595e-b35d-9f877c8f954a | note | Resp - SE
7e2a4df7-2b06-5dab-a4f9-2fdc1edce1a6 | button | Remarks/record - NATA Test Report: Grading/PI | Yes,No
1f162f4e-5489-522e-b9ab-2aa16cc0c964 | date | Inspection Date:
| checkpoint | 5.3 - Backfill Pits
13df0a99-e537-5da3-8f8f-3ad46de7d60f | note | Ref docs - VR Clause 705.18 PS3030.07 (b. iv)
244b7901-1650-593e-8218-aaa65e43aff8 | note | Acceptance criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment.
49dbc2f5-c993-58fd-b649-99ff149453b2 | note | • Superintendent must inspect before backfilling as indicated in PS3030.07 (b. iv).
8eb1e5a4-cd31-5e5a-832d-a45dafcc5bed | button | Has all of the above been completed? | Yes,No,N/A
97cea43f-d210-5a58-93f1-fe826212d3b1 | note | Freq - Each Lot
8295f170-8edf-583e-ba53-cac56f7b30c8 | note | Key - S
16762890-e62f-5718-9336-04e21716cf9a | note | Resp - SE
bbb02d9a-8879-5c96-bacd-8a9b2db3aeb3 | note | SI Key - H
7822d4cb-4902-53d7-9683-6dbb828b8a91 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 6.0 Completion
| checkpoint | 6.1 - As-built Survey
c51a6fb7-0841-59af-be76-fc11b90861c6 | note | Ref docs - VR Clause 705.19 610.46
dd9f64e4-1955-59e8-b0ad-506fd0e1bcb2 | note | Acceptance criteria - Survey complies with specified requirements.
fee2296c-6f68-516b-9619-a319c59948fc | note | • The level at every point of the pit covers perimeter shall be within 10 mm of the design level. The line of the cover shall be within 10mm of the design kerb line
a9438fa6-30d0-5027-9635-4eb5a4f0627d | note | • Offset of entry pits required to match lines of kerbs or barriers ±20 mm.
fa1137a2-3e5f-5d61-b510-8ee5d08baa37 | note | • Plan location of pits other than offsets to kerb lines or barriers ±100 mm.
12bb5b9f-0886-5a57-9021-4ec9e9a821e9 | note | • The tolerance listed in Clause 610.46 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
83d35d06-d9e4-508b-852e-ed6f8d1fe9b2 | button | Has all of the above been proven and meets requirements? | Yes,No,N/A
70eec5f7-ae7f-59ca-8208-12c2a2ba7550 | note | Freq - Each Lot
94a02cc0-a402-5bc5-bad6-4c1b5f470c19 | note | Key - R
503a9e0a-9e8f-51cc-82d4-286ec078c5a5 | note | Resp - SE
d7c0d839-d107-5fa7-8a3e-62405d9ffa37 | button | Remarks/record - Survey Conformance Certificate | Yes,No
8addc9b6-2dff-5b0f-8cfa-5127286a87c4 | date | Inspection Date:
| section | 7.0 Work Lot Close Out
| checkpoint | 7.1 - Test Reports
b73bb617-abc9-5251-a087-1b07f5cd8489 | note | Ref docs - DoT Specs
6da64a56-f07b-5238-b82c-873b9b3bcfaa | note | Acceptance criteria - All Test reports received and Reviewed
a5914969-4062-5b29-a66e-ccab8c952025 | note | Freq - Each Lot
d633c025-2c29-545a-a57f-442376e1610f | note | Key - R
24dae65c-83ac-5c80-a63e-f2c9edf0be16 | note | Resp - SE
bdbdf54f-cca3-501f-9e95-087a8a60cc7f | button | Remarks/record - NATA Endorsed Test Reports | Yes,No
2f061b42-8426-50e4-85c3-19fefa8b40ae | date | Inspection Date:
| checkpoint | 7.2 - Product Non-Conformance
f83d11a8-0eae-5c7f-a49c-fb9635bc9768 | note | Ref docs - CQMP
868968b4-1562-5541-b80e-735c72c16428 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
6a01f8dc-f357-5976-99b4-dd093f586ce2 | note | Freq - Each Lot
0fd9aa62-7902-5ad2-b1df-b6dc4f0e97dd | note | Key - R
ecc3daa5-6dde-534c-a03f-f899df71ff9c | note | Resp - SE
b8bff080-8173-5851-bbfe-2bf8e1d3d213 | button | Remarks/record - NCR reports | Yes,No,N/A
69eb6a38-3564-567b-9bcf-eb39acf86704 | date | Inspection Date:
| checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
7ef4b7c4-c025-572b-830f-102ffa85c31e | note | Ref docs - CQMP Lot Records
0c0e7dab-9134-532b-982a-d409a27da34e | note | Acceptance criteria - All above criteria met, and records identified attached.
06315200-038d-5202-a000-479298df02a7 | note | Freq - Each Lot
77ceacb6-1c6d-5f49-b1d6-3098866afe22 | note | Key - R
75c028a4-83dc-5f2f-b65d-3ecf09549573 | note | Resp - SE
cf15468c-f60c-5001-b8fc-aa7cdcdef22c | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
4aa91d87-ae8c-5368-8dfb-687547642f32 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0016 Power Relocation | itp | 1630-P200-SYM-QAC-ITP-0016 Power Relocation |  |  | db6b2744-14b2-4fe4-b033-e2e7cc9e5ed7
| section | ITP Details
| checkpoint | ITP Details
95210441-b164-567c-896f-624dbcdde91d | note | ITP No. - 1630-P200-SYM-QAC-ITP-0016
7038d5c5-58d5-53ca-b014-833c9fbc57cf | note | Rev No. - 00
39ca7af5-3270-547f-af95-b40de5db64dc | note | Date of Issue - 15/12/2023
67a0133e-db3e-5376-b437-0bfcfc42fb7e | note | ITP Type - New/Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out
417115f2-d152-56ce-8acc-ead3b689ee1b | note | Ref docs - IFC Drawings
2f7a0027-5331-5b7b-94b6-11c71c424024 | note | Acceptance criteria - Ensure alignment setout has been completed and pegged.
5a58df63-ebb3-51ce-8975-31e4f3ff7a01 | button | Has all of the above been completed? | Yes,No
ec8ffc7c-6d26-503a-a2bc-85181c4efdd2 | note | Freq - Prior to start of works
aacc925e-da7c-5315-845f-5fcba0f15785 | note | Key - H
fa00412f-7b2f-5db2-8690-21064f0da626 | note | Resp - SE/SS
| checkpoint | 1.2 - Boring under Carriageways
9b9eb54e-1c40-57ad-818d-0c3cdb886c5b | note | Ref docs - VR Clause 706.04
5c05f98c-d04d-5025-b90f-61bebeff95d4 | note | Acceptance criteria - Boring by water jet not permitted.
eab9eb24-df92-5eeb-8d2b-88d1cff475e3 | note | ○ Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
ba045a44-4a2e-5033-a62d-9c4ba9a03ccc | button | Approval to proceed? | Yes,No,N/A
81e1a410-1f6d-5e3a-9cf3-5363841ce32b | note | Freq - Prior to start of works
15080e74-01dc-5d88-a6d1-260226a6419d | note | Key - H
45c65af0-a77e-52e6-b116-95918a93f86c | note | Resp - SE
9c5d5968-1e85-5a76-a8ce-6d608eb8dca8 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Conduit Covers
| checkpoint | 2.1 - Excavation and Cover Requirements
ef8c171f-2976-55a1-9201-9edad084e6e1 | note | Ref docs - VR Clause 706.03
a265b562-3578-5330-8455-7eccbed8cdf1 | note | Acceptance criteria - Cover requirements for electrical assets shall be:
0163e148-0ad4-5aa3-8cb4-9ac6a0400f54 | note | ○ Pavement surface to top of conduit minimum 1200 mm.
a08b279d-5762-58e0-af8c-606c3cbeb019 | note | ○ Invert of open drain to top of conduit minimum 750 mm.
7f668964-86e1-50fe-9250-62cce9bf033a | note | ○ Unpaved areas to top of conduit minimum 600 mm.
614156a3-df6c-5a62-b449-34268cb7880e | note | ○ As per asset authority requirement for cover to other assets
e2244b86-9cc2-546f-a826-3fa5ec950d8b | note | Or else as specified on design drawings in accordance with asset owner requirements.
5762d72e-c184-5223-8f76-f827d7718d14 | button | Has all of the above been completed and approved? | Yes,No,N/A
c9a61372-3f8c-5938-ae61-e3cb1a8aee69 | note | Freq - Each Lot & Each possession
b9d6d7d4-291f-5fe5-8a8d-7a4b804f39ca | note | Key - S
4cfcd628-9765-5ed6-b72b-c1655b6ff948 | note | Resp - SE/SS
| section | 3.0 Backfill and Compaction
| checkpoint | 3.1 - Backfilling/Compaction (Areas not being paved)
aefeb1df-200f-5656-8b1d-84dc6159f938 | note | Ref docs - Ausnet Tech Spec
53bff178-7c79-57fa-8039-c0554875cef8 | note | Acceptance criteria - Works outside road: As per Power Authority
e2bebde4-283e-5181-b6e4-db4ced035fcf | note | Freq - Each Lot
c2d3f345-5991-57ea-97a1-91295f89993c | note | Key - R
daf3a9cf-0500-5267-8670-6f20bc384a8c | note | Resp - SE/SS
| checkpoint | 3.2 - Backfilling/Compaction (Under areas to be paved included shoulders and verges)
ce38365e-86bc-5f27-a663-cb7247e9f8b6 | note | Ref docs - VR Clause 706.08, 706.09
16f43444-fc70-5e92-a704-603814f736c6 | note | Acceptance criteria - Unless backfilling requirements are specified by the Asset Owner Authority, backfill material properties as per VR706.061:
55e13ab9-ccc7-58fc-85b8-91858b733d70 | note | – trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness, and above that level with common backfill material.
c292d09d-5bed-56f7-b71d-73009a651d15 | note | – The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97% based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
e53a4d40-fa91-5270-8069-5f030b580545 | note | – Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
77f62186-81c2-5e9b-9438-2fdcf03cdee1 | button | Has all of the above been completed and approved by the relevant authority? | Yes,No,N/A
e3336715-7ab9-5a80-8c7d-1d4f9c5def5c | note | Freq - Each Lot
a8160cf9-7b35-5312-9b10-720e7241fb23 | note | Key - R
77a5f36b-941a-57d5-8f2d-3d09ef4aa749 | note | Resp - SE/SS
265f68da-c897-5b4a-b23f-9bbf3c9c84a2 | button | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NATA Test Report (if applicable) | Yes,No,N/A
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Test Reports
6711c160-8bf5-5ab8-8cf3-5bd42b5d20e6 | note | Ref docs - VR706
e83eecba-ba46-57dd-8c74-404bc76486b0 | note | Acceptance criteria - All Test reports received and reviewed.
4726cbfd-c0e1-516d-b51c-2c4627492adc | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
9055332b-ae93-5746-83ca-f1796162c931 | note | Freq - Each Lot
05dbc484-bae7-53e3-bbf1-1b63cfb904cb | note | Key - R, I
fc4f29b7-17fa-50df-a51f-12d1d1dbd7be | note | Resp - SE
| checkpoint | 4.2 - As-built Information
def9eac6-a1f8-5a6c-8f7d-6a54d0118acc | note | Acceptance criteria - Where applicable, as built pickup or as constructed drawing been provided by authority.
9065ee03-65de-59f2-aa99-e77e88402b41 | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
3240e4f6-8031-50ad-b0ee-b6271fe56d54 | note | Freq - Each Lot
40034185-5b92-5185-a0c6-b73a4b9d5134 | note | Key - R
cf8e53f2-6603-5e30-b63d-29ce8ab05a39 | note | Resp - SE
| checkpoint | 4.3 - Audits, checklists, and approvals
d71570cd-5f87-5627-96df-f223c41e3f50 | note | Ref docs - Ausnet Tech Spec
7aa85fde-79f4-58cd-8dd8-3f2ba50fb046 | note | Acceptance criteria - Civil Audits for all trenches (If applicable).
262a4a85-4dd7-5b79-8cfb-7b698796c2f9 | note | ○ Cable Hauling audits (If applicable).
ccde1079-a470-57c8-b7ef-33039740156d | note | ○ Trench inspection and detailing of all conduits and cables (If applicable).
ca4517bb-a7d7-51f3-b2c9-cf8ee219c24a | note | ○ Pre-commissioning audit with all non-conformances rectified (If applicable).
7cea3b41-a5e0-5ddd-8cca-eddfd878c8ef | note | Freq - Each lot
da58ce25-5e06-50e8-af13-67e61f028bb1 | note | Key - R
eaf56b5f-0021-5a5c-8433-83f686b0808b | note | Resp - SE
8d7e4cbe-a8dc-5d89-bb28-9262791ace4a | button | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Conformance Report | Yes,No,N/A
| checkpoint | 4.4 - Product Non-Conformance
55c4ea1f-aeea-5517-af46-ad0a0b39422b | note | Ref docs - CQMP
67ee24ee-8c63-53cf-b6ec-775e09e638af | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
289e5a0d-9f62-5638-9941-3a0068326eb7 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
0f9d43f1-eeea-5c0e-af60-8a056531ff21 | note | Freq - Each Lot
d84b5886-14f7-5ed0-aa34-da0829940e45 | note | Key - R
e84a075d-3a6b-5331-922a-dd123c0b8768 | note | Resp - SE
de76d55d-0bd7-5bb3-b7b6-8f7d92e70e3c | button | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NCR reports | Yes,No,N/A
| checklist | 1630-P200-SYM-QAC-ITP-0017 Water Relocation | itp | 1630-P200-SYM-QAC-ITP-0017 Water Relocation |  |  | c9bea6da-ee4b-424d-a5c4-7dfcb71781f6
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out
5c37ec68-e1b5-5ef8-831e-ba40edb5c3bc | note | Ref docs - IFC Drawings
fdf725a0-5dd8-50df-af08-abe94a24f236 | note | Acceptance criteria - Ensure alignment setout has been completed and pegged.
a7ebfbb3-dd6c-5723-9422-df1a34d13698 | button | Has all of the above been completed? | Yes,No
1534840c-68f4-5b0c-a02e-f86e8ff89e88 | note | Freq - Prior to start of works
1aa8ceb6-a135-5d36-be14-0c2ba90733cc | note | Key - H
61c9df7a-3fe2-52ea-80ff-42ceaa4dd7cd | note | Resp - SE
3ef396a2-774f-57bd-a0c3-fd8553b704e4 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
1cdc1255-fe76-56ae-8290-9626fff6e145 | button | Lot map | Yes,No,N/A
8c6d788c-d9bc-5a6f-863c-179b21de01d1 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
97d0d0f7-4932-52f3-9815-0c67cd6426d2 | button | Environmental permit | Yes,No,N/A
70a1118c-fd50-5f5b-ae8e-40021c1a5b3f | date | Inspection Date:
| section | 2.0 Materials
| checkpoint | 2.1 - Material Conformance
97c8ed84-c213-58e6-9417-a05e82ee5d63 | note | Ref docs - AS4130
01b51e89-a3fc-5ffb-83b2-bfb484137f45 | note | Acceptance criteria - Assets installed are correct type, class & diameter and comply with AS4130 (as relevant) unless noted otherwise.
021b32a3-985c-570e-86fe-11fe6f388b4a | note | Freq - Each Lot
94293c92-cab3-57a2-b3f2-2065d56b0ced | note | Key - R
f8b46672-4bfc-594e-996e-a5319d132cd5 | note | Resp - SE
82b2d7ee-ee1c-5fee-9add-b07c402f7e45 | button | Remarks/record | Yes,No,N/A
6ef506d2-8398-50d3-9d56-8c4551d9c400 | date | Inspection Date:
| section | 3.0 Depth of Cover
| checkpoint | 3.1 - Depth of Cover Requirements
181a976e-ab35-5be1-a2bb-81a7b9c6907b | note | Ref docs - VR Clause 706.03
d18354ed-95da-539a-949e-72d16a346b5e | note | Acceptance criteria - Cover requirements for water assets shall be:
3089d800-710a-55e6-a837-32453a18534d | note | • Pavement surface to top of conduit minimum 1200 mm.
76cceaf8-0ec9-59f5-9e28-210d3d63385d | note | • Invert of open drain to top of conduit minimum 750 mm.
14933dab-9753-55c2-afa4-7c25b5f2fba9 | note | • Unpaved areas to top of conduit minimum 600 mm.
520f34e6-5f04-5f45-82c8-dc50b6709620 | note | • As per asset authority requirement for cover to other assets
3eb1f525-677a-5ed8-9f70-c442f8c0c66e | note | Freq - Each Lot
cb76b358-4484-5f0c-b95a-235c46bfbf6f | note | Key - S
f94d81a4-69c0-522b-8ce0-34dad6184e9f | note | Resp - SE
dedd1621-d686-5988-9dcc-170d050ccee9 | button | Remarks/record | Yes,No,N/A
fc8dbdb3-3a6f-5520-bb08-88f0251feb69 | date | Inspection Date:
| section | 4.0 Backfill of Excavated Trenches
| checkpoint | 4.1 - Bedding / Embedment Material Properties
58f831da-cc95-5cd2-b808-80561223b4ab | note | Ref docs - VR Clause 706.06 Table 706.061
5c8c9a63-2531-5fb2-aef7-f3f2cc115012 | note | • VR Clause 706.07
595024d1-b5a6-5c39-8330-c596ec83abb6 | note | • VR Clause 706.09
dd395429-3fee-54df-866b-1ea5935b2252 | note | Acceptance criteria - Bedding / embedment requirements are to be as specified by VR706 and VR Table 706.061.
f9e93ab9-d25d-58dc-a0a8-3153dda1766a | note | Freq - Each Lot
75a3804a-5452-558b-8c57-76a9374506fc | note | Key - R
8803825f-6317-5323-9226-0d4991ccf09d | note | Resp - SE
f43c6948-81f6-51d2-9d6d-05d944f67be9 | note | Remarks/record -
b2ead47f-45f5-5df7-b30e-e2ba878d0095 | button | • Test Report (if applicable) | Yes,No,N/A
d50fa01f-8385-51c9-8d83-111143ad26d9 | date | Inspection Date:
| checkpoint | 4.2 - Bedding / Embedment Placement
5b89141a-31c1-5c78-9069-9cdb5684b8b4 | note | Ref docs - VR Clause 706.07
b36c8235-9d11-598f-8a28-699fd7d4859e | note | Acceptance criteria - Placement of bedding / embedment is to be as per VR 706.07.
607c841d-17ea-5e08-9f7f-7c20d5bbbeae | note | Freq - Each Lot
86bdaf50-762f-506e-9118-dead22738d53 | note | Key - R
3ea15c82-0b62-5f67-a305-eae99f233e4a | note | Resp - SE
43dc06d7-e749-5e6a-86ae-f8323ad9d1b1 | date | Inspection Date:
| checkpoint | 4.3 - Backfill Material Properties (under paved areas)
43610fe3-6804-5dcc-ad68-34de47b51b0e | note | Ref docs - VR Clause Table 706.061
5781045e-3920-54ad-bf97-ed792f38df10 | note | Acceptance criteria - Backfill material properties to be as per Table 706.061 (See figure 1).
837f580d-a55d-577d-9a96-9766819336e9 | note | Freq - Each Lot
cb4b7be2-b0cb-5a6c-9191-5de0e2b0a746 | note | Key - R
614b7a6b-c4c4-52f6-9f20-babd90fbcb81 | note | Resp - SE
0097b327-a16d-5bd2-a37b-a333e685fde0 | note | Remarks/record -
1a3743db-da78-5afc-a232-856d9cf4ef57 | button | • NATA Test Report (if applicable) | Yes,No,N/A
82084a36-886a-546b-874b-0ebb991f05c0 | date | Inspection Date:
| checkpoint | 4.4 - Backfilling (under paved areas)
6853bcd0-ca63-5f79-bb33-6e979957386c | note | Ref docs - VR Clause 706.06, 706.08, 706.09
ceb50a80-34c0-5212-9eaf-94eec08a63a7 | note | Acceptance criteria - Backfilling requirements and placement to be as per VR706.08 and VR706.09:
89df92e8-786e-5ea4-9889-636f7a7240cf | note | – Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness, and above that level with common backfill material.
2e9e2b97-1be4-54f5-8677-97ec35bb461e | note | – Moisture Content between 85-115% as determined in the Modified compactive effort.
615cd5a0-4d0b-57c5-86d7-694b56683956 | note | – The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97% based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
a6252f8b-448b-5595-8a7e-c5645770b2ce | note | – Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
71ace6ee-bb27-5734-8d81-342608e43d53 | note | – Detailed proposals for compaction of backfill materials of nominal size greater than 40mm shall be submitted to the Superintendent for review before commencing work
4c69c822-0257-52db-8f10-58d80e8b5edb | note | Freq - Each Lot
587bfbf1-09f7-501a-ba47-d6fa7bd398c8 | note | Key - R
ca5d97cc-30cc-5f0b-ad6d-9d7a1c85c9f9 | note | Resp - SE
88c0d166-72c3-52ec-a1a9-a71906147bfc | note | SI Key - H
7aa53b1f-e8c6-5b55-8ea9-3a987ce21374 | note | Remarks/record -
48f3f04d-3060-54f8-bd71-050b2ca59b69 | button | • NATA Test Report (if applicable) | Yes,No,N/A
00e19fb1-4616-5f5c-a8cc-0f91b8e6dd29 | date | Inspection Date:
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Test Reports
87103499-947b-507d-a579-035f92ac1827 | note | Ref docs - VIC Roads Specifications
c0755c01-a383-5158-8711-cd94c5dc9280 | note | Acceptance criteria - All Test reports received and reviewed.
2ef97ba1-2c1f-5e6c-8f0b-b133e8095d80 | note | Any specific asset owner QA documents available to be submitted attached.
1bfcb786-66fa-52f0-97a1-b737c12c1770 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
dab4390a-b40e-587f-8d3b-fa32d11bc09e | note | Freq - Each Lot
345ac42a-c520-5291-b1c8-16cd4fbe622a | note | Key - R
883a4b5c-fbea-5239-9edf-b1aca23fedf4 | note | Resp - SE
b045ee02-acf9-55a3-a16b-abddca504703 | date | Inspection Date:
| checkpoint | 5.2 - As-built Information
ca30e46f-90fc-54b8-94a7-74f1cd5ed600 | note | Acceptance criteria - Where applicable, as-built pickup or as constructed drawing been provided to the authority.
8ce72f20-c8ec-5625-8bca-fb3c518f7ddf | button | Has all of the above been completed correctly | Yes,No,N/A
c5f2498d-a397-5b1c-a95a-b0e1727eefc5 | note | Freq - Each Lot
b38b161a-54f0-5edf-ab8f-68576f678512 | note | Key - R
c19e7065-6db9-5836-8757-6593f2785a3a | note | Resp - SE
0cc2287e-c1ae-5168-a519-ed50c082bbde | note | Remarks/record -
227e9692-0787-58f2-bb4e-961b47c2db30 | button | • Survey Conformance Report or as-built drawings to authority | Yes,No,N/A
8ca70d04-d385-586a-a7de-c4a4b1084d51 | date | Inspection Date:
| checkpoint | 5.3 - Product Non-Conformance
7f3e57a7-5b1d-54b2-88fc-2dbe8f4e316e | note | Ref docs - CQMP
5318d2ef-1644-5cf6-8fab-a99155eb2aa0 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
354bcc64-4db7-587b-a928-5e37e7894845 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
102f9edf-0f3e-574f-9ead-13857ebd60ea | note | Freq - Each Lot
03534d69-9ddb-51fa-86ab-ea056510067a | note | Key - R
29a9362e-4c84-5f0d-878b-db3e5983065b | note | Resp - SE
d402e5d1-5ff3-5f9e-9eed-13df18084d14 | note | Remarks/record -
a6e16a2b-29ec-5521-b515-1fba4277a98e | button | • NCR reports | Yes,No,N/A
4468bf4a-b4d2-5380-bd23-d4d23914d969 | date | Inspection Date:
| checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
380eeed4-3db3-5801-8d6a-ad4f546d46a1 | note | Ref docs - CQMP Lot Records
b8b30523-ceaf-56b3-88c7-e8f592c20ba1 | note | Acceptance criteria - All above criteria met, and records identified attached.
b47d150a-51ef-5d79-886b-9b3f654f4fef | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
ab959837-0d81-5ef5-a82c-60832f4d9463 | note | Freq - Each Lot
aafa4b40-6fb8-54ec-86ef-2769a4bbcbd6 | note | Key - R
e38de800-2379-552c-b4e5-668e58dad2be | note | Resp - SE
63c16381-020e-54ae-9806-0fddfde1dad7 | note | Remarks/record -
717ff71e-1839-5030-b6a2-1fc48043140b | button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No,N/A
ec2aa53a-2ec7-5e33-94cf-972ccc979e32 | date | Inspection Date:
| checkpoint | 5.5 - Authority Asset Install Acceptance
93d71fe4-b318-53bc-9f71-76bfcc903357 | note | Acceptance criteria - Audit and approval received from accredited SEW consultant.
c144a07f-bbaa-5d56-955a-50659bb868a7 | note | Freq - Each Lot
99d06fd5-2918-5353-99e9-41c8d03d0799 | note | Key - R
e2479f30-1897-5a03-9f2b-99e91c77d6ad | note | Resp - SE
092aabd0-8573-50e2-9a0f-c0b5c40debfa | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0017 Water Relocation REV01 | itp | 1630-P200-SYM-QAC-ITP-0017 Water Relocation REV01 |  |  | a02f733d-b5ac-4a1a-b4f0-3e4a415e85c9
| section | ITP Details
| checkpoint | ITP Details
340f3777-4b79-52fe-8f29-7340166f3946 | note | ITP No. 1630-P200-SYM-QAC-ITP-0017 Water Relocation
c991e78a-cc83-5da0-8523-d774550e6b36 | note | Rev No. 01
776c277b-a0fe-5380-91e7-0d4452bdda5e | note | Date of Issue 27/10/2023
e57f5eb0-b7e7-5e73-8db0-e119919ac2bf | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out
485806a1-ab58-52ef-9b31-56f2d60f572c | note | Ref docs - IFC Drawings
141d91d0-c992-50e7-9bb5-d54faadcde8f | note | Acceptance criteria - Ensure alignment set out has been completed and pegged or sprayed painted.
1f6f17fe-8262-5cc1-aaa2-7e527f1a112f | button | Has all of the above been completed? | Yes,No
2cd85bdf-28e8-5df7-8fab-79db5b4bc5c6 | note | Freq - Prior to start of works
15c56038-3052-56e8-8ba0-360be5c62314 | note | Key - H
316e1da7-3fa7-52d1-beb7-9bfc480a8829 | note | Resp - SE
| section | 2.0 Materials
| checkpoint | 2.1 - Material Conformance
476ddab0-a013-56f7-9e20-502403c1fa8d | note | Ref docs - AS4130
58725d6c-3b27-5127-9c74-3fb2133e2c7c | note | Acceptance criteria - Assets installed are correct type, class & diameter as per design. Procured asset complies with AS4130 – Polyethylene pipes for pressure applications (as relevant) unless noted otherwise.
e84302b5-b887-5e06-9f98-3229afebe8b8 | note | Freq - Each Lot
7a1280d8-75df-59c7-9f15-c570ae19872f | note | Key - R
2811f892-70ac-58e4-b4c5-25700d0ad722 | note | Resp - SE
| section | 3.0 Depth of Cover
| checkpoint | 3.1 - Depth of Cover Requirements – Design Check
d6021e99-f52a-5d74-92b1-b58b28d8b649 | note | Ref docs - VR Clause 706.03
dfd5183c-cc20-5dcd-8623-7f4ea8eabb2b | note | Acceptance criteria - Cover requirements for water assets design comply with the following:
dc7acee1-e2ce-576b-abc8-ab4b699244ca | note | ○ Pavement surface to top of conduit minimum 1200 mm.
3a1d3272-f257-5c2c-92e4-567837bf880e | note | ○ Invert of open drain to top of conduit minimum 750 mm.
f5b02b45-71f1-5180-9c42-18c3dce73ead | note | ○ Unpaved areas to top of conduit minimum 600 mm.
c7df676d-3523-5b76-b0ad-dbcb84c9922a | note | ○ As per asset authority requirement for cover to other assets
d1ecf0eb-c84a-5aed-aa3b-6a7e82e580cd | note | Freq - Each Lot
80c8ccf7-cf8d-554c-acef-b03f226f7cb1 | note | Key - S
7bfcd7c4-96b4-5100-95f8-5fbf7308cceb | note | Resp - SE
| section | 4.0 Backfill of Excavated Trenches
| checkpoint | 4.1 - Bedding / Embedment Material Properties
6d5018ac-1dcd-593c-b772-e8908834ce0b | note | Ref docs - VR Clause 706.06 Table 706.061
c6a24476-4ba6-58db-a967-1261210f0b0b | note | Acceptance criteria - Bedding / embedment materials are to be uniform in composition and free from perishable matter. Further the size and plasticity index must comply with VR Table 706.061 (Figure 1 on page 4).
56ff933f-dfad-5a57-8f79-b04d43706568 | note | Freq - Each Lot
b0dcae52-3e20-52d6-a69b-dcb3be146722 | note | Key - R
0132a5e8-fe82-562c-be56-d1eca3c27f95 | note | Resp - SE
| checkpoint | 4.2 - Bedding / Embedment Placement
5beb48a4-90f4-52ea-90a5-183e74654c9f | note | Ref docs - VR Clause 706.07
7ec54dd3-98be-50ec-96e6-48529396a040 | note | Acceptance criteria - Placement of bedding / embedment is to be as per VR 706.07 requirements below:
6e54914d-e2cc-5fdb-98cd-6587dd266711 | note | ○ No less than 25mm of compacted depth shall be placed below
707edffe-16a8-5652-afe7-c496ae8c7215 | note | ○ Bedding shall be placed below, around, and above pipe
eceaa2a5-13f8-5ff9-a0fc-5e9169c80287 | note | ○ No less than 150mm of bedding shall be placed above
f51ba112-815f-58e8-af56-89ea67c553b0 | note | Freq - Each Lot
c5e0a42a-0c43-5f45-b12a-f27f887761b8 | note | Key - R
c8e7b30c-014a-5568-9e87-60b2074307ba | note | Resp - SE
| checkpoint | 4.3 - Backfill Material Properties (under paved areas)
451005f6-f745-5682-8253-88809741353e | note | Ref docs - VR Clause Table 706.061, VR Clause 706.08
ea1194c9-95b9-57e1-aa0b-da96be48b590 | note | Acceptance criteria - Backfill materials are to be uniform in composition and free from perishable matter. Further the size and plasticity index must comply with VR Table 706.061 (See Figure 1 on page 4).
2c150c4a-efad-5eee-99c5-cdb73933a0cd | note | Freq - Each Lot
9d45c18d-18d5-5964-812e-f9321509dfe6 | note | Key - R
c761611b-5570-5ee8-b45e-2757f642e0e3 | note | Resp - SE
| checkpoint | 4.4 - Backfilling placement and compaction (under paved areas)
973f9cca-cd4c-5562-b911-a0a5a266c281 | note | Ref docs - VR Clause 706.08 & 706.09
728737d4-feb3-583b-b14a-2f6206b850d5 | note | Acceptance criteria - Backfilling placement and compaction is as per VR706.08 and VR706.09:
1037073c-dbf8-5d07-8728-997bd0f60479 | note | ○ Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness
0b32c837-c679-5dd2-b726-85dac31ba42f | note | ○ Optimum Moisture Content between 85-115% as determined in the Modified compactive effort.
c6d4e6a6-5c58-5e15-961b-cfcc2253af0a | note | ○ The number of tests per lot shall be three.
396f26b6-aabc-5643-919e-99f81377b124 | note | ○ Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97%
221caa8d-ea7e-5eda-b4d2-4dd4709862d3 | note | ○ Noting density ratio shall be based on Standard compactive effort.
31992f11-0e78-5bb2-b786-74f379156825 | note | ○ Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
5767a9f6-04c1-5a2f-aa0b-79f7ea1d0990 | note | Freq - Each Lot
f31c338b-0b60-5408-9385-985bbec819ed | note | Key - R
cfc1dbeb-081c-5684-8b10-e302707fee8e | note | Resp - SE
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Test Reports & Other QA Documents
2d7fea30-51a2-5d7c-9180-9ad790d76ac1 | note | Ref docs - VicRoads Specifications 706
976c68fd-e2d8-5b2f-8800-a0285dfcef98 | note | Acceptance criteria - All Test reports received and reviewed. All required material dockets has been received and reviewed.
d14d2b9c-6814-5486-9550-875947e33f8a | note | ○ Any specific asset owner QA documents available to be submitted attached.
5d345cff-930a-55a2-a241-05960aa9d3ec | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
ec2320bf-bede-5813-8475-6de4bd7a25a9 | note | Freq - Each Lot
01c4beff-aa8b-5894-9228-037ac271a0fb | note | Key - R
5d6226fe-cf47-55ec-97f4-c9101c3d9924 | note | Resp - SE
| checkpoint | 5.2 - As-built Information
e026c25c-5cac-58d5-a92c-0cb67d3c7528 | note | Acceptance criteria - Where applicable, as-built pickup or as constructed drawing been provided to the authority.
723a07fa-3de7-5569-9921-0a4d590a4575 | button | Has all of the above been completed correctly | Yes,No,N/A
19f86d89-380d-5299-860a-259f9220295d | note | Freq - Each Lot
cf8eb04c-1b93-5490-8d81-819e679809c0 | note | Key - R
7b2fbd91-69c3-58f9-b759-d2a98df26f6c | note | Resp - SE
5e26f9da-03cb-5e35-b3da-08a670836276 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
5dba7fc0-dcff-56eb-9afd-09fc4749e36e | button | Survey Conformance Report or as-built drawings to authority | Yes,No,N/A
| checkpoint | 5.3 - Product Non-Conformance
73a5ff28-a864-5b7a-b28a-ba8b28a7f1b9 | note | Ref docs - CQMP
78e31d6a-47ad-52cc-8ac9-21ac3acabadd | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
7c65b1a7-ace6-522f-9184-0b0dffb27bfc | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
700c6ff6-3620-5590-a048-187c076ed602 | note | Freq - Each Lot
1d442064-8c4c-5f11-b551-5d5f43b52629 | note | Key - R
3f6a5386-009d-523d-9434-e30d7ac2092a | note | Resp - SE
0832ac1a-9c78-5b9d-a4f1-c63a6ca62eb9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
75ab43af-c014-5162-8b05-2a35a0235a00 | button | NCR reports | Yes,No,N/A
| checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
8b2f6e56-1839-5cb1-a402-ea0071852c5e | note | Ref docs - CQMP, Lot Records
0afeb110-d5fe-51d5-854e-8ffb7f4ad429 | note | Acceptance criteria - All above criteria met, and records identified attached.
53d41953-d0d9-5670-bc69-aae212d29871 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
d8ba87e4-7d21-5fae-9131-cb1aedb11f82 | note | Freq - Each Lot
d59ca183-6318-5c4a-bb51-c86e2c736820 | note | Key - R
bf7a378c-5566-59f0-ba4a-98818ba9247b | note | Resp - SE
667d81c9-a902-5ed9-bd6b-e39c2eb40603 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7f394896-a70b-595c-aa89-9817817f8e38 | button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No,N/A
| checkpoint | 5.5 - Authority Asset Install Acceptance
87171084-5332-574d-8c7a-f65bc5354dd8 | note | Acceptance criteria - Audit and approval received from accredited SEW consultant.
23b759d3-6c14-5846-b63a-360e16925528 | note | Freq - Each Lot
94c25e9d-152a-5687-84e8-4e5cb715aa9e | note | Key - R
3b0e9586-a0fe-58ca-bc49-90d8c08e2782 | note | Resp - SE
| checklist | 1630-P200-SYM-QAC-ITP-0019 Lower Subbase Layers | itp | 1630-P200-SYM-QAC-ITP-0019 Lower Subbase Layers |  |  | 3526fc3e-f635-4689-99f3-f7af02eba99f
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out and TCM’s
b99e4d74-7856-5dad-92c3-a78c2d07213e | note | Acceptance criteria - Record existing TCM’s on TCM offset sheet. Survey set out including frame, benchmark, and recovery points in place.
07a641cc-9de2-56c7-9ca8-56b7d62939b7 | note | Freq - Prior to start of Works
559f184a-50bf-53b4-beb1-69c10045e48c | note | Key - H
8c5c8bae-02b5-5f26-b6a3-941d751d9508 | note | Resp - SE
08f94f57-66a8-5f53-9636-9a38334992f5 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
8dea6dc8-3b70-5aa9-99cf-2aa6bd2e4ade | button | Lot map | Yes,No,N/A
e44a8763-d941-5791-8aaf-5d3077a4f6e8 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
4afa04ca-c2e4-59ef-a235-195718fc4045 | button | Environmental permit | Yes,No,N/A
9c3c6d19-5007-530b-8724-bf3b7b11e5d0 | date | Inspection Date:
| checkpoint | 1.2 - Subgrade preparation
928bef34-6dca-5390-a922-9a93985a9a88 | note | Ref docs - DoT Clause 304.04
cab27010-71b9-537a-9368-671d59f969e2 | note | Acceptance criteria - The subgrade should conform to the requirements (compaction and levels) of Section 204 before the lower subbase can be placed.
e8cc7b87-f06c-5e63-9a72-be11c7190e01 | note | Freq - Prior to start of works
00c3ac6a-e1ca-5844-a922-53a0dca990aa | note | Key - H
00022e9d-9e78-538c-bed2-7bb830bcfb84 | note | Resp - SE
8b7a02af-e1dc-5457-82cc-52b736a5d4a2 | note | SI Key - R
9a377d97-e484-53da-aa1a-31b72e481c77 | note | Remarks/record -
8f80b867-9d91-5510-a6a9-24cfb671b338 | button | • Survey Conformance Certificate | Yes,No
38e04c9a-2cbf-5631-b6de-7a49f382b886 | button | • Test Reports | Yes,No
d504a524-a2b9-540e-830a-aa5da356ef91 | date | Inspection Date:
| checkpoint | 1.3 - Material procurement for construction
9deb86ac-fb0c-5781-9781-3320e40094d2 | note | Ref docs - DoT Clause 304.03, 812, 204.04
4e5f9488-d476-5ee3-aa4c-c467a5653eba | note | Acceptance criteria - HP: All crushed rock proposed for use on VicRoads funded works shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
7c52698a-13d9-55e5-bbbc-cc50129794c6 | note | • The Contractor shall be responsible for the procurement of sufficient specified material to complete the work. The Contractor shall supply details demonstrating compliance of the materials with Section 801.
1d9d6343-5e7f-5bf7-a71e-74aa089cd861 | note | • Water added to the pavement will be clean and suitable for construction and substantially free from detrimental impurities such as oils, salts, acids, alkalis, and vegetable substances, and have no more 1000 mg/L of suspended solids.
417b795c-37c4-54f7-a938-e03a753dc5d4 | note | Freq - Prior to start of works
87da74e8-cacd-5dc0-be33-9c206a372fbd | note | Key - H W I
7d5b9f60-dd4d-556a-82fe-9ec8094604a5 | note | Resp - SE
1d5843bf-6eba-5ddd-82ae-ffaa17b2e224 | note | SI Key - H
a9ea14e3-28c8-5904-b211-63335f7a7efa | note | Remarks/record -
8c3c9034-6854-57c7-978e-0d902ed35612 | button | • Crushed Rock Mix Registration | Yes,No
af01d87f-f1c7-512c-9c69-95c3bde76f9b | button | • Delivery docket and material compliance checklist | Yes,No
6123e4f5-b36c-549c-8b90-c59b0c1849b7 | button | • VicRoads Materials conformance | Yes,No
7e25a1ed-2bf8-5ce4-beeb-81d185b0e21d | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Installation of Lower Subbase Layer
| checkpoint | 2.1 - Construction - Jointing
78900972-6ba4-5a01-9e32-4f0d48f26b49 | note | Ref docs - DoT Clause 304.07
30130d8c-00aa-5acc-bd93-8bbb7fda5992 | note | Acceptance criteria - Transverse - Offset by not less than 2 m to any underlying pavement layers.
275f9e27-36bc-59bd-9eec-1d17a862e22f | note | • Longitudinal - Offset by not less than 150 mm to any underlying pavement layers. Located within 300 mm of the traffic lane lines or within 300 mm of the centre of a traffic lane.
6fd2b3f9-492c-5746-aa9d-cf65798f7c9e | note | • The exposed end of each lot and the exposed edges of any part width construction shall be kept moist until spreading and compaction has been completed over the entire layer.
46f30bdc-e10b-5e7a-b334-c58a7366880f | note | Freq - Each Lot
01861c8a-ecb8-56eb-ad70-e0ec498427bb | note | Key - S I
7979ffe7-3c84-5086-885e-05c397e0787d | note | Resp - SE
120ca43d-a406-5553-9564-94d520000ac2 | date | Inspection Date:
| checkpoint | 2.2 - Placement of Material & Testing Compaction
dd955adb-2c72-59e7-a6f1-5cc6f08bef5b | note | Ref docs - DoT Clause
4b5ffe9e-476b-543e-aea3-73c14b7bc1a6 | note | • 304.06
1313efe3-2520-5c18-9229-ac055b53c2cf | note | • 304.06 (b)
f04cfa67-6402-5be0-8f76-50c83db28258 | note | • 304.06 (c)(i)
36174cc9-6fc6-5790-9fcc-37e1ee05a164 | note | • 304.06 (d)
d966b78d-1fd5-595b-b7e4-2c8baef071c7 | note | • 304.08(a)
29b69ee5-667c-586d-83d7-9887b7f27bd5 | note | • IFC Drawings
bc55cd16-16a6-55b5-bb4f-9e721c480c34 | note | • Construction Work Pack
577642c7-4777-592e-9a9b-b875bd2a32c1 | note | Acceptance criteria - Place and compact layers so that the surface finish is smooth and uniform.
2f9311a1-87a4-5ffc-bc4b-41e2220fcb71 | note | • HP: Any material that has been compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without the approval of the Superintendent.
3eea983c-2e2a-52ad-b5f4-d25a9f5f79c1 | note | • The width of each side of the pavement shall not be less than the specified offset width or more than 50 mm outside the specified offset width when measured at right angles from the centre line or design line.
f911cf37-83db-54b0-bbfb-3a49cb17f311 | note | • The subbase course shall be not less than the specified thickness by more than 15 mm.
7b62a0fa-f09c-5207-8c08-a57c2cba6cad | note | • No point > 8 mm below a 3 m straight edge in any direction
d90793b4-dac7-58c6-940f-dabd6177673f | note | • No point >10 mm below a 6 m straight edge in any direction
397849d2-1ea5-5efd-8d6c-b0d1ea9ce12b | note | • No Ponding of Water.
775f7d64-d09b-56f8-8305-0db9c4303561 | note | ○ For material of nominal size > 40mm:
5fc00657-ac1d-59db-bfab-cf9111c25fbd | note | • The first lot shall be placed as a trial section. Following acceptance of the trial section, the Contractor shall then confirm the moisture control and compaction procedure and submit the procedure to the Superintendent for review and record.
bc0dfdac-b01b-52cb-bddc-4f1f4ae62d85 | note | ○ For material of nominal size < 40mm:
a76dbbda-b70a-5385-b531-7b8a630f426f | note | • No trial sections needed.
3f3c5324-02db-551f-b88a-a12295b4efc2 | note | Freq - Each Lot
84135121-b28b-55ae-9347-aec9e1906f36 | note | Key - H I W
e9085903-830d-5e25-886a-1371b6ccab4c | note | Resp - SE
cea73a5c-2786-5329-8742-b473915284a7 | note | SI Key - H R
356b02ec-d241-52ea-8a3d-17c9f1755373 | note | Remarks/record -
49898788-ff7b-515d-ad99-c1936bf76db1 | button | • NATA Test for Compaction | Yes,No
1eb745d5-492c-5234-933b-3fa78db037be | button | • NATA Test Report for Material | Yes,No
7e922665-6479-5865-afb4-0ba1f3de488e | date | Inspection Date:
| checkpoint | 2.3 - Testing – Stability (Proof Roll)
abb749de-297e-59f1-98fc-f85ab0add235 | note | Ref docs - DoT Clause 304.08(b)
431e7726-69f8-54df-a8b5-36ace7c613b8 | note | Acceptance criteria - Test rolling of the subbase layer, irrespective of material size, shall be in accordance with the test rolling procedure that was submitted to, and approved by, the Superintendent.
61537bf4-3a01-5296-a5bb-3834e8c8155c | note | • Area shall withstand test rolling without visible deformation or springing.
f94f5eb7-bbf5-59b1-a2ba-be419b06461d | note | Freq - Each Lot
d8721f56-2e85-57af-a2a9-502fac353ff2 | note | Key - H W
955d2626-a43c-5aec-8d69-809d0d48a486 | note | Resp - SE
330383b7-ef04-5e51-a201-d7533ec92b4c | note | SI Key - H
ae119e49-c3e1-59a1-9cc8-f218a7c81669 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Protection of compacted layer
6fc04e0b-e0a8-5b18-922d-64b0a3bfe29a | note | Ref docs - DoT Clause 304.09 Construction Work Pack
e0ffd55a-75b3-5e20-b623-30deea323680 | note | Acceptance criteria - Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
b97285c4-9630-57c7-9159-0a69ee6ec003 | note | Freq - Each Lot
2527abfe-8635-519f-af47-0a0870756ba4 | note | Key - I
1289f08d-81c4-5df6-8926-0c6f95aea369 | note | Resp - SE
522e4f7b-b10c-550f-beb8-ae0eb3769a5e | date | Inspection Date:
| section | 3.0 Testing
| checkpoint | 3.1 - Testing – Compaction
71cb93ea-2e8b-54fd-a021-dbab1f515a21 | note | Ref docs - DoT Clause 304.08(b) 304.10 304.11 Table 304.111
72a2548b-4971-5497-8e34-042c6c3d26fc | note | Acceptance criteria - Characteristic Density Ratio % (six tests): Not less than 98.0% Modified
b0565aab-5cba-51ff-8cdc-9157f61b6080 | note | Freq - As required by section 3.2
61b8cf09-5efe-5338-86fd-b0af3fab6256 | note | Key - R
83d894a2-eb50-59dd-8ef6-6d54da2f126d | note | Resp - SE
439c9d50-31be-5b83-ae88-9e3c963087a6 | note | SI Key - R
2441d932-081f-5ef9-88e4-61bb85a16893 | note | Remarks/record -
b253cbe6-a430-5884-85e7-6fb8599f03d0 | button | • NATA Test Report | Yes,No
d450ac2c-11ab-5032-9595-e2a81369cf42 | date | Inspection Date:
| checkpoint | 3.2 - Scale A Requirements for Post Compaction Grading and PI Testing
693f8002-ac4b-5e7f-a407-435743e14913 | note | Ref docs - DoT Clause 304.11 (c) (i)
2a32281a-aa94-569c-a690-bb64d40e8bed | note | Acceptance criteria - Where testing is specified in Clause 304.10(c) or (d) and Clause 304.12 requires it to be Scale A, all pavement layers shall be tested for post-compaction grading and PI at the frequency specified in Table 304.111.
a182f3d5-906a-5843-86ea-07187fe59d5d | note | • The first lot of each pavement layer shall be tested for post-compaction grading and PI.
95d30c17-b67e-5835-8845-9f81066cca73 | note | • The Contractor shall immediately notify the Superintendent of any lot that does not meet the specified requirements and any subsequent lot shall be tested as if it were the initial lot.
609053d8-25a1-52f5-a77b-a5b74777e9fe | note | • If any lot meets the specified requirements but is reworked to comply with the specified compaction requirements, it shall be retested for compliance with specified requirements.
d69dda11-2519-50ef-8f43-de6fc8c8fe80 | note | Freq - Each Lot
5a8cbc8a-98aa-5f7c-8bdf-18fc7a659e5b | note | Key - H
cdb4da61-392c-5ad3-9481-a3665913cc93 | note | Resp - SE
e6a2e5a7-7dd4-5932-ac2d-d8bfa5b42e4d | note | SI Key - H
cd4e7bfa-2c0b-5fe8-bb3e-62e6dc95ff93 | note | Remarks/record -
96d78990-e3dc-5a92-a363-94c77effcd30 | button | • NATA Test Report | Yes,No
1988579a-915e-5bac-a444-0ae957ff9408 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Post Compaction Grading (Nominal Size = 20mm)
d81a2dcf-fd84-5e48-9803-e1fd1cfe315a | note | Ref docs - VR Clause 304.10 (a)
9f7e93fe-1ead-5b14-84b7-c5bc16076892 | note | Acceptance criteria - Sieve 26.5 mm – 100% passing by mass,
7d1c6e73-a3f8-5f74-94e5-6b23760797cd | note | • Sieve 19.0 mm – 95 - 100% passing by mass,
c0a6ed53-61c7-5850-9575-f0076ebe9230 | note | • Sieve 13.2 mm – 75 – 95% passing by mass,
d90bb3c0-20d7-5a0b-935b-216022449248 | note | • Sieve 9.5 mm – 60 - 90% passing by mass,
4c9370d0-767a-59c1-95b6-5ed9e069ccaa | note | • Sieve 4.75 mm – 42 - 76% passing by mass,
e8bc41ce-8be3-583c-8516-1b7757f9a4ee | note | • Sieve 2.36 mm – 28 - 61% passing by mass,
fd7ed6b8-9c1b-59e9-9d1e-1e8ce341f89f | note | • Sieve 0.425 mm – 14 - 29% passing by mass,
63424bb2-38ea-55bd-98b9-a693efd5131d | note | • Sieve 0.075 mm – 6 - 14% passing by mass.
c8a065b2-563c-5198-b89a-39005e641ce2 | note | • Initial testing frequency: 1 test for each lot tested for compaction until 3 consecutive lots achieve specified requirements.
f462c67b-c35d-5ce1-9be5-738abe842228 | note | Freq - Each Lot
45d43ea0-2286-5d53-8211-86ec27e5b648 | note | Key - R
dbc9bc92-fcc0-5b01-a683-7eaa35c7a1d7 | note | Resp - SE
a6110f33-7dc5-552d-b9a7-40f723681180 | note | Remarks/record -
09d54dcc-ed10-5489-92e7-2281d4c7c170 | button | • NATA Test Report: Grading | Yes,No
54bb9329-97ea-5c2b-965f-f09d6d98d093 | button | • Visual Inspections for Maximum Particle Dimension | Yes,No
b0b46c81-4ebb-564c-a3f7-4370f8d011ce | date | Inspection Date:
| checkpoint | 3.4 - Plasticity Index
8d702aa9-4981-5cbc-bf80-1000612986b3 | note | Ref docs - VR Clause 304.10 (b)
7371eb74-9e9f-51a1-a727-54deabb4c3f0 | note | Acceptance criteria - PI: 0 – 10%, Initial testing frequency: 1 test per 2 lots until 3 consecutive lots achieve specified requirements.
d62d3c2b-743c-5e61-8e3b-0b511a041645 | note | Freq - Each Lot
662eb067-bc98-56c4-bb7e-6123fd230b47 | note | Key - R
84d5c91f-b1a5-5975-99ba-cb27c33d1eae | note | Resp - SE
4be01b32-5af9-5016-a3b1-e882b9da6962 | note | Remarks/record -
8f643088-d301-5e90-a5fe-a8f01dd34c6c | button | NATA Test Report: Atterberg Limits | Yes,No
ac6c3bbe-bfd5-5ae2-87e3-4884f08b2e86 | date | Inspection Date:
| checkpoint | 3.5 - Testing – Reduced Frequency
faa7e5a7-8e06-5a69-b1c3-f1801d20b31a | note | Ref docs - DoT Clause 304.11 Table 304.111 Table PS3040.061
e2cb4b68-a4a4-5cc2-b329-3eee0bcc0f20 | note | Acceptance criteria - Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
a8f6f1d1-785a-5f38-aad3-45618a18b75a | note | • Testing may then be completed at the minimum frequency outlined in Table 304.111 and Table PS3040.061.
d9c93473-3917-5321-89bd-da8c995ec3e3 | note | • For Subbase, one Characteristic Density Ratio % (six tests) will be completed for every second lot.
4624fb76-e2ca-5538-b0e2-0f01a149d614 | note | • Testing will be completed at the minimum frequency until such time as a lot fails to achieve the specified requirements. After a failed result, all subsequent lots will be tested until three consecutive lots of like material and work have achieved the specified standard, at which time the frequency of testing may revert to the minimum frequency.
a0e1a91b-769c-5958-b068-fb0956002c78 | note | Freq - Each lot
f00ae2e2-23e4-5c50-bb41-2b16f914abe1 | note | Key - R
32f87c21-d203-503e-a1d6-ce7fe23ca9a7 | note | Resp - SE
0819bcf7-26b3-5ddf-8d44-2414e7be275e | note | SI Key - R
3f1c9a48-4c12-5a33-b4df-c14227c6d08c | note | Remarks/record -
5cc30595-ce03-5d8a-aa26-f196568b35ab | textbox | • If using reduced frequency, provide lot number of previous lot tested:
e33a088d-909f-5ad7-86a4-a6ba94c04d7e | date | Inspection Date:
| section | 4.0 Completion
| checkpoint | 4.1 - Survey as built
40516cd4-e82b-52ee-bb5f-87b36832c897 | note | Ref docs - DoT Clause 304.06 Table 304.061 Table 304.062
3b3f18dc-0d20-51dd-80e5-5a05105c855b | note | Acceptance criteria - Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
cb35fb57-7ea7-5800-9b8b-229cd131e105 | note | ○ Surface level checked for compliance with 304.06:
da2a24c8-fdd0-5d4a-a918-a7c8ee6982a7 | note | • Mean +6 mm to -10 mm with a max std deviation of 10 mm (Scale A)
c8e79556-b99c-572b-8895-dda6329e153f | note | • Min 80 measurements per lot (Scale A)
782e2166-1ee6-5fe9-9e3a-89db758ee1c0 | note | ○ Number of survey points to be at random locations in accordance with VicRoads test method with minimum number in accordance with Table 304.061.
898c2fad-d45c-57d1-ab32-4cf4b871ce77 | note | Freq - Each Lot
ad21d2e1-0c08-56f1-87a9-621e26e86b4d | note | Key - R I
b0293030-f8ad-5795-b2a6-62c48a1347af | note | Resp - SE
d873418c-2963-5853-95f4-78c29e97d23f | note | Remarks/record -
c24bd7d2-b4b7-503d-b52f-b50af1f89832 | button | Survey Conformance Certificate | Yes,No
06c0ee22-c56c-515c-b9a4-23fc42d8af1a | date | Inspection Date:
| checkpoint | 4.2 - Thickness of Pavement Layers
00592ccf-6db4-546c-a304-c75cd20b9464 | note | Ref docs - VR Clause 304.06 (c)
76421ecd-4a40-5dcc-b7b9-fbcf0a16e21b | note | Acceptance criteria - The following tolerances shall apply to the thickness of any pavement layer:
9562c98d-2635-5a0f-aebf-a37e1f1eb6f6 | note | • The subbase course shall be not less than the specified thickness by more than 15 mm;
dfa5820d-c96d-5d8f-9074-6398428e7638 | note | • The base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
1257b284-6902-590f-9edc-2ab8079c0296 | note | • The combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
6110d383-d99f-59dd-8d1d-fecc83618153 | note | Freq - Each Lot
0f929b1e-ec48-5c0d-8f77-716d125a532e | note | Key - R I
42e02618-d257-53ac-9c80-2952bdd09af8 | note | Resp - SE
9c71bc51-4efb-5ee2-a601-0834151af502 | note | Remarks/record -
cda87787-52b3-5a62-94f7-580fdfa240c3 | button | • Survey Conformance Certificate | Yes,No
df4cb55d-220d-57cc-a967-ce1295de10fe | date | Inspection Date:
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Test Reports
f380ea94-538c-527f-a9c2-b95eb7c802a6 | note | Ref docs - VIC Roads Specifications
db73627c-167c-5a50-8786-624d6225b4c5 | note | Acceptance criteria - All Test reports received and Reviewed.
37927a82-e42a-5284-8b8b-25559fafaf03 | note | Freq - Each Lot
868846d0-3248-593d-a394-4a92d13bff4b | note | Key - R
e6ce1c12-3a38-5b60-b495-a457c75bb730 | note | Resp - SE
73c0e856-8f89-5766-aca4-b1c24e6a6089 | note | Remarks/record -
a2ada059-7c23-5066-9db6-51d2e5bfc4dd | button | • NATA Endorsed Test Reports | Yes,No
5f1d1d54-fa46-5623-9f1c-a04e6287143a | date | Inspection Date:
| checkpoint | 5.2 - Product Non-Conformance
22c854ba-0ff1-575e-a995-e2f17a09a5f4 | note | Ref docs - CQMP
dfea45df-ecbe-5148-bf0f-f6c0ab0a3deb | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
d41d9b3e-0402-54d1-af1e-ccc41844b23f | note | Freq - Each Lot
e982308e-7ad0-594f-8195-33ec793f9694 | note | Key - R
fde1d45d-f03d-5655-8e77-f8da714d2910 | note | Resp - SE
b9505a46-1304-5c69-bea9-8e83ba3b2bc7 | note | Remarks/record -
f980fd33-2799-502e-90fa-9655afa1ffc4 | button | • NCR reports | Yes,No
ec1564b1-e241-541d-99c7-23986263cbc8 | date | Inspection Date:
| checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
1381efa3-d1e5-5822-bcd4-1ddd02867e82 | note | Ref docs - CQMP Lot Records
73ed2239-6812-58c6-954c-4c966a71f679 | note | Acceptance criteria - All above criteria met, and records identified attached.
23b243a8-ae1d-5f11-aaa0-ed5a4abee708 | note | Freq - Each Lot
cc3d85e0-fad7-5b6f-ad13-0e71b4a82841 | note | Key - R
c1bbf8a5-77f5-571d-8de0-5467b0cd9723 | note | Resp - SE
75ae5bea-294a-5cf9-9bbb-7ce6f6458267 | note | Remarks/record -
7aa62367-e24e-5204-b89b-07dcd9631157 | button | Completed Checklist (if applicable) and reports and other compliance records attached. | Yes,No
c7e58678-9875-5a3d-9d7f-3603c6084688 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0020 Cementitious Treated Pavement Subbase (CTCR) | itp | 1630-P200-SYM-QAC-ITP-0020 Cementitious Treated Pavement Subbase (CTCR) |  |  | 6db86d5b-0f1e-4c91-9683-55948d8e4f29
| section | ITP Details
| checkpoint | ITP Details
1424c75a-ff50-5ff1-a42f-8516cb290fc3 | note | ITP No. - 1630-P200-SYM-QAC-ITP-0020
f9349525-0793-5ce7-abbc-09457c825aee | note | Rev No. - 00
88476ef5-f555-51c8-bad8-a94071762e57 | note | Date of Issue - 09/01/2024
df495e26-8d89-5c07-aaa4-c36020d7421d | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Source Rock
a202abfc-3d5b-5068-90ea-3f68a8e4a34d | note | Ref docs - VR815.03
21bf0303-71de-521f-b378-91e7f8b470c9 | note | Acceptance criteria - Source rock complies with the requirements specified in Section 801 Source Rock for the Production of Crushed Rock and Aggregates and has been obtained from an accredited VicRoads source.
8c84a0f4-c510-50db-b787-ee6f1f75a033 | note | Freq - Prior to start of works
8254e99b-0d69-5632-a559-aecfba17edd4 | note | Key - H
ad0bb76b-2789-5923-98b3-d5cc4b8a8e1f | note | Resp - SE
2b68f273-18eb-53e6-8f8b-f6cd90df4df7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test results demonstrating compliance of the source rock being used for the production of crushed rock and aggregate
| checkpoint | 1.2 - Coarse and Fine Aggregates (Source Rock)
24fbd97c-b266-53a4-98f6-b430982116ec | note | Ref docs - VR815.04
8e7a6637-d95e-5254-a9ef-73150b3a9841 | note | Acceptance criteria - Coarse and fine aggregates are clean, hard, durable, angular rock fragments of uniform quality. The durability, soundness and degradation factor requirements specified in Clause 815.03, Table 815.051 and Table 815.141 are met.
1ce6b767-8471-5dac-bdf6-a2a9c5f7aca7 | note | ○ Note that degradation factor is only required where the supplier uses fines from a different bench or location to that of the coarse aggregate source.
926df45f-c9f5-5d28-8334-f26889d5a62b | note | Freq - Prior to start of works
4a3bd6fc-768b-57d3-a897-233c57138055 | note | Key - H
3090196f-c047-5e93-8271-f1b661931f79 | note | Resp - SE
653ee8f6-8a30-5ac1-9ec9-a2bae80a317e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
5c174bc2-4a4c-5b22-8c43-3ec2d89a2663 | note | ○ Test results demonstrating compliance of durability, soundness
940f8b0c-2147-54de-94be-36741dc1e602 | button | Test results demonstrating compliance of degradation factor | Yes,N/A
| checkpoint | 1.3 - Coarse and Fine Aggregates (Imported or manufactured)
b6aa83f8-ec01-5e68-9b81-0f1839427681 | note | Ref docs - VR815.04(b),(d)
364116f1-39b9-5bc3-b0d3-48690be97118 | note | Acceptance criteria - Coarse and fine aggregate is not imported from a different source or manufactured from a different rock type to that of the coarse aggregate.
578acb7a-6b11-54ee-9b34-86dbba2fbd1e | note | Freq - Prior to start of works
73267dca-72c3-5488-adef-963e678e03ce | note | Key - H
b6fe701c-6f08-5459-94c1-d4a8d203d9e5 | note | Resp - SE
052eccbd-e89e-5bac-97fd-27abab799bd2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Confirmation from supplier that fine aggregate is not imported or manufactured from a different rock type
| checkpoint | 1.4 - Additives
257e80e5-d135-526c-9cd2-46aaa4996303 | note | Ref docs - VR815.04(c)
18c2b950-3a06-5957-afb3-546caac9e701 | note | Acceptance criteria - Additives are not used in the production of crushed rock.
050923a3-c2fe-55d0-9037-a8d895525e2c | note | Freq - Prior to start of works
994b310b-8fbd-522d-9e53-96198703c012 | note | Key - H
83af0930-3441-5975-b356-f9a862a8d6b6 | note | Resp - SE
995c94c6-c4c5-5bc8-b291-6aed4c231e0f | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Confirmation from supplier that additives are not used in the production of crushed rock
| checkpoint | 1.5 - Crushed Rock Mix Registration
07bacae8-15ff-534b-82d4-d7a8e72dcf71 | note | Ref docs - VR815.05
f2b655f3-af46-5a03-8152-418d0cd304e8 | note | Acceptance criteria - Cement treated crushed rock proposed for use on VicRoads funded works are be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
52913db3-bccd-5416-aec0-8534d0f057d4 | note | Freq - Prior to start of works
dd8e8f74-df55-52e6-adbe-1b161a261d30 | note | Key - H
a570d3dd-0fe9-58b3-b00e-1f28dc6d3cd6 | note | Resp - SE
14f3109a-e048-5d4a-8b48-e50797fbd8d5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - VicRoads Registered Crushed Rock Mix Design, Test results demonstrating compliance of the supplied CTCR (From supplier)
| checkpoint | 1.6 - Cement
de06f2fa-7e4b-5de5-afbb-8ba427f4904f | note | Ref docs - VR815.06
d0b8855e-be07-5c78-8928-f35ec2220e50 | note | Acceptance criteria - Portland and blended cements are Type GP (rapid setting binder) and comply with the requirements of the current Australian Standard for General purpose and blended cements as listed in Section 175.
c3b388c7-4b48-51d9-b777-18dd90bc4962 | note | ○ Cement is stored in weatherproof structures, and no cement has been damaged by moisture.
a48de7c0-887a-552c-9df4-f03454cbf628 | note | Freq - Prior to start of works
6c32948a-7e06-5b96-b910-62d40dd55f34 | note | Key - H
fecd92d6-bb5a-59fa-96fe-9c655f8c2250 | note | Resp - SE
129db294-c14c-5893-9aac-c146623b258c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Confirmation from supplier that cement is Type GP and stored in a weatherproof structure
| checkpoint | 1.7 - Water
b22ed209-51c9-5191-a94f-c3a139705d96 | note | Ref docs - VR815.07
b70b124a-0169-53a4-acf9-1e4c3ca5003a | note | Acceptance criteria - Water added to the crushed rock is clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
6a908bc8-978d-5f48-8810-eaa2fdf512ec | note | ○ Water sources have been tested prior to use for electrical conductivity and pH, in accordance with the current Australian Standards as listed in Section 175.
782095ff-36b5-5a2b-9489-543b80f824bb | note | ○ The electrical conductivity is not be more than 3500 µS/cm and pH is within the range of 6 to 10.
cf89bfcd-db4a-58f2-9bb0-ab74c861d2b3 | note | Freq - Prior to start of works
b5a4f95b-f757-5eb4-b3c9-a4db49be4d44 | note | Key - H
f36083c7-1ebf-525e-9c0d-9087864e8aa1 | note | Resp - SE
2e8cd4dc-76cf-5e66-9eee-74de1caef60c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test results from the supplier (maximum of 12 month intervals) demonstrating that requirements have been met
| checkpoint | 1.8 - Mixing
b997345a-1d46-5453-b81a-449542e63d71 | note | Ref docs - VR815.08
5ca12250-48ca-5a14-ad39-37f999a22ac7 | note | Acceptance criteria - The crushed rock, additive (if any), cementitious binder and water has been mixed by continuous pugmill or batch mixing.
d3fbb27e-1f5e-5080-ad40-7dcdead36e20 | note | ○ The mixing period and the time of addition of water is such as to produce a uniform mixture of the components.
cda156b6-b19c-5d9a-b0a3-8fac606dc794 | note | Freq - Prior to start of works
6eaa7b4b-1c85-5000-9e0b-8702547d58d7 | note | Key - H
60eaf443-9f12-5fc3-b538-8bb774ca3d75 | note | Resp - SE
87d5cb60-221a-594e-96c0-1d376d85c063 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Confirmation from supplier that mixing is undertaken by pugmill
| checkpoint | 1.9 - Cementitious Binder Content
3abad9c8-768b-5a0a-8a05-ac2fd1146cba | note | Ref docs - VR815.10
5aec4007-5fe9-5d01-b873-82604165fbad | note | Acceptance criteria - The content of cementitious binder has been determined to meet the minimum 7 day UCS specified in Table 815.101 using modified compaction.
23a1ec6e-b1da-52c1-bd9d-a07a41d35f61 | note | Freq - Prior to start of works
cedda8fe-05da-5d32-a8f4-010baf2fd4b5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Test results demonstrating the specified cement content achieves the required UCS
| checkpoint | 1.10 - Underlying lots
76e7dcb7-050f-56fc-bd8d-5b316b468cd2 | note | Ref docs - VR304.04
3b4f4a00-7807-5e4e-9200-fefabc6923c6 | note | Acceptance criteria - The lots on which the subbase is to be placed conform with Section 204 and 304. Underlying layer lot status are conforming or non-conformances resolved prior to placement of subbase layers.
cb626332-151a-5b61-b480-19bc474eac53 | note | Freq - Each Lot
4c57abde-a9e4-5a0d-9516-9634e696e884 | note | Key - R
15f3c1e8-1c0f-5e34-aba0-f283ef2a45eb | note | Resp - SE
| section | 2.0 Installation of Cementitious Treated Pavement Subbase (CTCR) Layer
| checkpoint | 2.1 - Delivery
e28b0fcc-6274-595e-9c30-013edcd8d707 | note | Ref docs - VR306.07
f1b477a2-0550-50bb-9304-fb0491ffb06d | note | Acceptance criteria - Delivery dockets will be produced for each CTCR Lot.
f7f71a3e-c00b-5d76-a8ec-8372d4d966f7 | note | Delivery dockets show the below and are for the correct product:
410e0bb8-f63e-5362-8144-946dd348b2a1 | note | (i) name of the supplier, and location of plant;
29fe6a63-3f59-5e39-bbcd-d5ea2731134c | note | (ii) docket number;
0bd868c4-d493-5e3e-b944-6ba6bd8f3472 | note | (iii) name of user;
1c329650-5a41-586b-b96f-4cb438081511 | note | (iv) project name and location (or contract number);
91e7da39-967c-520f-87ee-ebfcaa79ca86 | note | (v) registered number or fleet number of the vehicle;
770eaf81-54f3-5f68-8986-f56898a6455c | note | (vi) date and time of loading;
f44a4ebd-e853-5588-be13-d8eb1ecf4ca5 | note | (vii) nature and source of material;
5c19e923-df0a-5116-8886-c6fe9dfaa38e | note | (viii) empty and loaded masses of the vehicle (where material is scheduled for measurement by mass);
c5f5b628-cf6c-5429-a3e1-736bed62b107 | note | (ix) loose volume in delivery vehicle.
1dd5f457-afc2-53d3-9de3-62fbfc9e53de | note | Freq - Each lot
612ec38f-dbd0-5cf5-a920-e646743f69f0 | note | Key - R
26c7a177-8f3d-5eb3-be23-e892aec5a0dc | note | Resp - SE
7ab7c7f9-f3ad-532b-baac-76e05e55613b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Delivery Dockets
| checkpoint | 2.2 - Moisture Content
63a6ace0-625b-5932-8c2b-e9e80224070c | note | Ref docs - VR306.05
22fc1021-b311-599c-864e-6a097905cff3 | note | Acceptance criteria - At the time of spreading and compaction, Moisture Content (MC) is within plus + 0.5% and minus -1.0 % from the Modified optimum moisture content. Except for the purpose of curing, no water has been added to the cementitious treated material.
58cd05f5-be99-5807-96c0-8fbfb09c812a | note | Freq - Each lot
060ec8d4-e408-5dc9-a465-0ae05f2826b5 | note | Key - S
9613a5d5-f067-5437-954d-83d77a70edb7 | note | Resp - SE
| checkpoint | 2.3 - Construction Jointing
005b66b0-7d38-56e4-b852-a328cb7b94f6 | note | Ref docs - VR306.08
f43419aa-9aa0-53fa-8798-f4ea25c7801d | note | Acceptance criteria - All jointing conforms to VR306.08.
f633fb81-c089-5b49-932e-a06861fb7941 | note | ○ Longitudinal joints are located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
9035b241-433a-59d8-bba9-787b16687143 | note | ○ Joints have been prepared immediately prior to the recommencement of spreading operations by cutting back the edge of previously laid material to a clean vertical face in compacted material for the full specified layer thickness.
40e39f22-ceb3-53f8-993f-202b8a073913 | note | ○ The faces of all joints are thoroughly wetted immediately before spreading new material.
2176704a-c79e-5a60-9274-2192a98e9e75 | note | ○ The level and shape of the surface at all joints shall be within the limits specified in Clause 306.03.
cf61e6da-b1b8-5167-ac82-e72b9e78c28e | note | Freq - Each lot
23612953-3e6c-54a1-9db2-e742bce25cc6 | note | Key - I
6cf31e68-cba7-566a-a56e-aac6e08f6ae9 | note | Resp - SE
| checkpoint | 2.4 - Construction – place, spread and compact CTCR (1)
81741380-e8bf-59de-96a3-6a1d63b4d07a | note | Ref docs - VR306.09 Table 306.091
601a388e-bc0a-5074-bbd2-03c0480943e6 | note | Acceptance criteria - CTCR placed, spread, compacted, and trimmed within the allowable working time. See Figure 1.
6fed6113-81e2-582d-9d2d-a5a73c057593 | note | Freq - Each lot
7ee36af4-1985-5e2a-8763-f47d78956d3e | note | Key - R
dd3d1a63-521a-53df-9353-9c7236d7186c | note | Resp - SE
| checkpoint | 2.4 - Construction – place, spread and compact CTCR (2)
c977be3c-139d-5ce7-8e47-9ad270188e40 | note | Ref docs - VR306.09 Table 306.091
f4e68471-fb5b-5ca4-b18f-867b716091ad | note | Acceptance criteria - The minimum compacted thickness is not less than 100 mm and the maximum compacted thickness is no more than 180 mm.
867c71e5-afcb-5fcc-b69f-fba4070a953b | note | Freq - Each lot
189a4e73-92cc-54ac-a0a9-f354b2e36e2a | note | Key - S
d143117c-66de-56ea-8f95-ae605b47390e | note | Resp - SE
| checkpoint | 2.5 - Testing – Compaction (If alternative binder is used, testing to prove accordance to VR standards is required)
d35e3254-efa9-5fc5-b731-97ee7afc5725 | note | Ref docs - VR306.09 (a)
2139f457-1e0a-5eb6-b2f4-6793942a4b4f | note | Acceptance criteria - Adhere to Scale A compaction requirements. Tested for compliance with 306.09. Mean Density Ratio not less than 96% (Modified).
4476d539-53b6-5038-9a5d-d521d37ff19e | button | Is area considered a small lot (< 500m2)? | Yes,No
04bf7dd5-ea04-5acd-a54d-1a89a8c54aa4 | note | ○ If yes, for earthworks and pavement construction any lot which has a surface area less than 500 m2 may be treated as a small area.
44109f93-f16e-549a-81f6-c49a5950ee92 | note | ○ When testing a small area as a lot and where test requirements are based on characteristic values of density ratio and/or moisture ratio, acceptance of the lot is based on the mean values of 3 individual tests.
0e8bbe21-e8cb-557a-a17b-a5020cf173cb | note | ○ In this case the lot will be accepted as far as compaction is concerned if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
db6b7060-fe3d-5d58-be9a-5d90d62ba1d8 | note | Freq - Each lot
6380f040-5e84-5cb6-b24b-db2901fe1cbd | note | Key - R
bd6743df-f346-549c-a44a-55b43b759a90 | note | Resp - SE
c10c7de2-cb89-5049-b65a-07b27b53cc7a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NATA Test Report: Compaction and Moisture Content
| checkpoint | 2.6 - Test Rolling
d7914bc7-6dfd-54e3-ab71-bd71991a90a0 | note | Ref docs - VR173.03 VR306.10 Table 306.091
13672974-faf7-5c29-a0d9-2f7aff35518e | note | Acceptance criteria - Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of the year as specified in Table 306.091.
cd7e2117-1879-58ff-b31d-f546b6354754 | note | ○ Test rolling was not conducted outside the allowable working times.
b237fdb0-8976-5987-90d3-2b440c3acb8c | note | Freq - Each lot
a5bc6141-cb4c-5326-9f0e-ca2b8e93b118 | note | Key - R
2900571d-cf67-5385-8483-ce14e5ac36fd | note | Resp - SE
21eeb7d1-1951-5187-8642-8b6ffba5ae9c | note | SI Key - W
| checkpoint | 2.7 - Curing and protection of compacted layers
052d6047-db1a-5df6-aa4a-9800e22bacba | note | Ref docs - VR306.11 (a)
bbc65865-45fb-5d64-b319-2f102ebc653c | note | Acceptance criteria - Construction or other traffic has not used compacted layer within 24 hours of placement. Surface has been kept moist for 7 days unless covered by succeeding layer or membrane.
b9528407-ab42-572d-8a9f-8fe003eafdb1 | note | Freq - Each lot
b7f3f6f1-cbf7-5b1b-9c23-79cbe29c09b7 | note | Key - R
f198bb46-2ea0-5154-9ed5-d50bdc32c385 | note | Resp - SE
| section | 3.0 Completion
| checkpoint | 3.1 - Survey Tolerance
de5086c4-e9c6-5732-a3ae-7ae8f4324303 | note | Ref docs - Table 306.032, 306.034
78d74294-c4e2-5aeb-8995-8c509a087bf9 | note | Acceptance criteria - + 4 mm / -8 mm with a maximum Standard Deviation of 8 mm (Scale A)
53d1a3c2-ee03-5654-b686-e1f6e06d77a5 | note | ○ + 6 mm / -12 mm with a maximum Standard Deviation of 13 mm (Scale B)
bb0efed1-9d7d-5f5c-b705-bfebe4b8b505 | note | ○ +10 mm to -25 mm for Scale C.
0ae69db4-f89c-5031-ba8f-75d0b7f2ba6c | note | ○ Minimum of 80 Level measurements for Scale A and 40 for Scale B.
7d4c783f-803e-5df9-a2c4-5a6b500d14e6 | note | Freq - Each lot
665ab003-fd4d-574d-8708-446b5d1765ec | note | Key - R
ee3284dd-f36e-57ce-a841-57298bf3608f | note | Resp - SE
7e27ac33-3384-5a9c-9fbe-2f10be695f3a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Survey report
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Test Reports
1429b705-ce6b-5d3c-809f-597c39843f5f | note | Ref docs - VIC Roads Specifications
27af2742-f4f8-5364-af34-481b859bc592 | note | Acceptance criteria - All Test reports received and reviewed.
45d5a5e8-0f06-5e27-997c-dfb66fff8cbc | note | Freq - Each lot
a4ec6bfb-9a15-5708-91d3-62729d18ae9b | note | Key - R
3ad41514-4e82-57d2-abb0-8fafe22004d7 | note | Resp - SE
7a4b2a06-c935-5d91-be52-8420787278f2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NATA Endorsed Test Reports
| checkpoint | 4.2 - Material Supply Testing
b19d1a69-9a6f-51ca-8729-8c445c0d9419 | note | Ref docs - VR815.14
946eb401-c411-5dca-bf74-8c95206d11c0 | note | Acceptance criteria - Test results have been received and are conforming for cement treated crushed rock at such a frequency to ensure that all material consistently complies with the specified requirements. See Figure 2.
3a3b04ff-d485-5c58-94a5-eb993ab11a2d | note | Freq - Each lot
324ff0e6-3dae-5dea-b7e7-ff66bd4efbb2 | note | Key - R
f2137fee-41bd-5a4c-b2d2-3b149a356482 | note | Resp - SE
1b75f411-cde2-5848-a23f-3a96653b77e0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NATA Endorsed Test Reports
| checkpoint | 4.3 - Product Non-Conformance
6024ad14-2b47-5387-b91c-de16b0831866 | note | Ref docs - CQMP
8c135bbe-6470-57e3-950f-6f42761d2e1a | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
bb545f72-2f9a-5245-8da1-8b481339a630 | note | Freq - Each lot
d8bc0cf7-933c-5289-8f21-4a7681d2b66d | note | Key - R
98d891f9-291b-5b95-a641-48fcf927aed7 | note | Resp - SE
02a33fc5-1f6e-5e33-9471-e57aa70746cf | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
645f93d9-4218-514c-8120-77ca79fc9c2b | textbox | NCR No:
6dd31e54-7088-5965-93fe-aea9efb7426b | note | ○ NCR reports
| checkpoint | 4.4 - Quality Representative to check the above criteria and records to confirm
98a4d8ac-1a7b-5ff2-b8c6-88464a402427 | note | Ref docs - CQMP Lot Records
b3101436-7bc3-5489-8b44-9bed6e588b11 | note | Acceptance criteria - All above criteria met, and records identified attached.
3c6bbb3f-a884-5cf8-ab3c-4daa1d5100d5 | note | Freq - Each lot
5f560668-fbea-55de-8ef4-bfaae407ea49 | note | Key - R
b3b79c01-0039-52cd-b29a-9f3b5d84bb11 | note | Resp - SE
3e2cf73f-285c-5ad3-8e99-3913d4bc0701 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0021 Conduit and Pit Installation REV1 | itp | 1630-P200-SYM-QAC-ITP-0021 Conduit and Pit Installation REV1 |  |  | 5c965879-5d7d-41ee-992c-fdf141116985
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Boring under Carriageways
2f713103-617a-5c3d-923a-76d8a5b2c458 | note | Ref docs - VR Clause 733.05
5df04e79-e95d-542f-8120-eaf9662a1649 | note | Acceptance criteria - Boring by water jet not permitted.
968fd953-5c07-5212-8f51-8c53f5312bc5 | note | • Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
823fffd2-d9ca-5314-8286-2b3c64901d98 | button | Approval to proceed? | Yes,No,N/A
a2b1f52f-d66a-5863-8bf8-bfeab56d79bb | note | Freq - Prior to start of works
24c6c6e4-c0b6-50d1-9f36-5244ef021436 | note | Key - H
07acf559-c7fd-5147-bdb0-09532e014864 | note | Resp - SE/SS
49022b87-db93-5abc-a082-7db45fec5ca8 | note | SI Key - H
61b05b19-3ac9-531e-bffc-e2ddd9684d91 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint-no-value | 1.1.1 - Lot Map
735f5e70-348d-511f-b99a-24bc661a8479 | button | Lot map | Yes,No,N/A
2c978f00-3ea4-5db2-8060-7de1be4a6858 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
15c1828e-c21a-50a5-8209-76b6c7e4154e | button | Environmental permit | Yes,No,N/A
29c0a3ab-7864-594a-b359-9e891d5fe45e | date | Inspection Date:
| section | 2.0 Conduit Materials
| checkpoint | 2.1 - Material Conformance – Conduits and bends
6f482625-6055-5a3f-85bd-02694d3fe93f | note | Ref docs - VR Clause 733.02 Table 733.041
82befed0-7a06-5d20-9dce-7be674937cc7 | note | Acceptance criteria - Conduits are correct type, class & diameter and comply with AS1477, AS2053, AS4130 (as relevant), unless noted otherwise.
2195aa03-fda0-5a4f-82dc-865f1e49f57f | note | • Electrical – Heavy Duty Grade, Rigid orange UPVC conduit to AS/NZS 2053.2.
434942a8-0ab1-56f0-b815-6be9e47308bd | note | • Communications – Heavy Duty Grade, Rigid White UPVC communication conduit to AS/NZS 2053.2.
4bf95e97-b172-5c45-ba17-46abc9680b7e | button | Have all the above materials been approved? | Yes,No
ca44bde3-19fa-5fa6-93f2-8723d3c4e57f | note | Freq - Each Lot & Each possession
768b5955-c3a6-5e67-b80a-a99af822e350 | note | Key - R
3819045d-b995-5514-8891-325d836a9627 | note | Resp - SE/SS
1bba3948-2a89-50cf-9dd4-51b9f6fcfab8 | note | Remarks/record -
4bb8c6c7-a41d-5a2a-a6cc-cd63491482a8 | button | • Supplier Compliance Certificate | Yes,No
5f17cb15-5b65-527d-8d72-01eb2fe50ebc | date | Inspection Date:
| section | 3.0 Conduit Cover
| checkpoint | 3.1 - Excavation and Cover Requirements
2b3f3f1b-5688-5904-b4fb-e35ffc194d77 | note | Ref docs - VR Clause 733.05 Table 733.051
401cf1a4-6a5d-58d5-9944-2b977048a598 | note | Acceptance criteria - Cover requirements for both electrical and communications conduits shall be:
57fb2218-48d5-50f8-baee-855cb4bbb832 | note | • Pavement surface to top of conduit minimum 1200 mm.
782c7cdd-3bea-5a85-8d79-f4874116c1a6 | note | • Invert of open drain to top of conduit minimum 750 mm.
858789b2-6966-512f-bbbd-2f05fbdf066f | note | • Unpaved areas to top of conduit minimum 600 mm.
ea9eac26-a75f-5931-ad30-39d78d030569 | note | ○ Or else as specified on design drawings.
4d627fe2-353b-561d-92d9-e05a21b100d1 | button | Has all the above been completed and approved? | Yes,No
985aec8d-fa47-5ca7-ace0-c93e62539bc9 | note | Freq - Each Lot & Each possession
f9b1dfe5-33e6-5878-90ab-de3918c91cdd | note | Key - S
1566fb7d-8743-52ec-8a26-d7374ecd9d83 | note | Resp - SE/SS
67750df8-cf3e-58b9-9790-16c9ba3fe4da | date | Inspection Date:
| section | 4.0 Installation of Conduits
| checkpoint | 4.1 - General
224f2f7a-982b-58ba-8bd9-399530206724 | note | Ref docs - VR Clause 733.06 Table 733.061 AS/NZS 3000 AS/ACIF S009
899e6132-aa2e-5d86-ad57-6d29fa4bf041 | note | Acceptance criteria - All conduits shall be installed as shown on the VicRoads Standard Drawings and Contract specific drawings, or as otherwise specified.
10d1fd33-3d1e-530a-b575-6a3f1a2c6c64 | note | All conduits for electrical and communications cabling shall be installed to conform to the relevant requirements of controlling legislation, regulations, industry codes and standards, including:
39a65921-46fc-5e64-8709-74e62bf8ac2b | note | • AS/NZS 3000 Electrical installations (Australian/New Zealand Wiring Rules)
39768788-d8dc-5650-ae33-0086e59ec620 | note | • AS/ACIF S009 Installation requirements for customer cabling (Wiring Rules), and any other relevant requirements of the Australian Communications and Media Authority (ACMA) for connections to telecommunication carriers’ network.
26f7637c-60b1-513d-94b5-610214e4aad3 | note | ○ Installation of conduits shall be carried out in accordance with the following:
86c111c9-d771-5bd3-8faa-1d691ade537d | note | • HD UPVC Plain to be Thrust bore or Open Trench.
7437cead-c0d9-5d3a-a0ad-26824570bf92 | note | • HDPE continuous (must have ID not less than that of 100 mm HD UPVC for electrical and 90 mm HD UPVC for communications) to be Directional Bore.
1b4f90fd-7da9-52e2-b629-ccec66191ed6 | note | Freq - Each Lot
f2245e67-04bb-540f-b4b0-f96263914c39 | note | Key - I
fbe0ffeb-a64a-50a4-8992-c098c7087148 | note | Resp - SE/SS
196db6e5-6ecb-55b3-a2d9-eb8b753982e7 | date | Inspection Date:
| checkpoint | 4.2 - Bedding Material/Placement
c1ac7761-6b01-5775-8def-36d010f5af25 | note | Ref docs - VR Clause 733.08
d8c55378-7fa5-597c-ae88-05367fe8ff89 | note | Acceptance criteria - Bedding material does comply with the requirements of Table 733.081.
0d7decc0-4971-571f-8fd5-69ec9c7cdeb3 | note | • Minimum 80 mm bedding below conduits on earth foundation.
3941b85e-975b-52f7-9961-11e15a79d1d0 | note | • Minimum 200 mm bedding below conduits on rock foundation.
ce1114d5-ad70-5f92-a514-295c4c4511c3 | note | • Bedding placed to full width of trench, and between conduits as shown on trench details on latest revision IFC drawings.
7ed90e44-b4df-5d34-906e-df537400f4c2 | note | • Shaped sufficiently to maintain the conduit in line as the sections are placed.
d6d441e5-48f6-5b19-bcd2-db3c398d4a7a | button | Has all the above been completed? | Yes,No
4f362462-c847-5998-909c-0c49929eca72 | note | Freq - Each Lot
830dedc3-a290-54e1-9dd2-8bc83713cb4e | note | Key - I
957ed6b2-7270-53e5-9148-8f91abf0f349 | note | Resp - SE/SS
7317d926-629d-542b-840f-0bea1aad3b50 | note | Remarks/record -
859ec677-aea2-5121-b3d3-cbd93bbdbbe3 | button | • Material Compliance for Bedding/NATA Test Report | Yes,No
03a67da6-924d-5c85-96fe-a314e54716fa | date | Inspection Date:
| checkpoint | 4.3 - Bedding Material/Placement
f1a34b93-19bb-5928-8967-102d621bca7f | note | Ref docs - VR Clause 733.08
703e10b8-20c4-5114-8446-d74194366010 | note | Acceptance criteria - Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by Superintendent.
b96e271a-aca6-5ac4-b920-f6c1bf92a749 | button | Approval to proceed? | Yes,No
d1259096-4fda-5cea-9b41-bc6eb1274294 | note | Freq - Each Lot
a03018af-fd3f-5c1c-a188-1cc14cc36815 | note | Key - H I
8363fd9f-70fc-51e4-87e8-fb4264db6ffa | note | Resp - SE/SS
105f9681-b754-5991-9434-ab791088b820 | note | SI Key - H
f0df05f1-931c-508b-896e-2899809af279 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Bedding Material/Placement
07ce8da0-e9ed-541f-a13d-8492246e2952 | note | Ref docs - VR Clause 733.08
937b6d75-4b34-5bcd-b53e-50717a357535 | note | Acceptance criteria - When conduit sections are in position, additional layers of bedding material shall be placed and compacted to a height 150 mm above the bedding previously placed.
873ef3cf-ed73-5db6-9793-d2133def20e9 | note | • Bedding material must not be the same material excavated for the trench, it shall be clearly identifiable as introduced material.
72996614-1a6b-5ca5-acce-a56654cf11ea | button | Has all the above been completed? | Yes,No
93e078b0-bf1e-59ea-b6d0-b224b5e12fd7 | note | Freq - Each Lot
06672ae7-7068-5bb5-8395-55a15b5a5d36 | note | Key - I
c7d28aa2-a848-5621-82ee-8e4f874061f7 | note | Resp - SE/SS
4b9cbb57-cfd2-5782-af08-ed627f4d03ee | date | Inspection Date:
| checkpoint | 4.5 - Conduits for Traffic Signals/ITS/Public Lighting
388b87c4-6d74-56db-84e1-29a39deab04b | note | Ref docs - VR Clause 733.06
73d62461-e454-5c10-b666-a1cd6b3d027b | note | Acceptance criteria - a) All conduits shall terminate in a pit in accordance with VicRoads Standard Drawing TC 1207, TC-1230 and TC-2200 – TC223.
5a41ff75-4722-545a-9b4f-310b0dbe5c55 | note | b) Only one size conduit shall be used for a complete run between pits; unequal size conduits shall not be joined in the ground.
8e11b10e-4c14-5525-bfdf-2ae6dfe71a5e | note | c) All conduits shall be temporarily sealed prior to cabling to avoid blockage.
e550a327-0aab-547f-810f-e2a9a0fb9476 | note | d) Changes in conduit direction or depth shall be made by natural set or in the case of bottom entry, by means of a swept bend; elbows or tees shall not be used.
bc87a144-c825-5154-8dfc-0fb5037d5dae | note | e) All conduit joints shall be correctly prepared and sealed with approved solvent cement.
aa1f51e9-4251-52c2-960c-61f815135099 | note | f) Conduits for detector cables shall be installed as shown in VicRoads Standard Drawings TC 1207 and TC 1320; and
f4874ab0-1eee-5e93-8482-623b7f1691a5 | note | • A 50 mm electrical (orange) conduit shall be used to convey the detector feeder cable from the detector pit to the cable pit, as shown in VicRoads Standard Drawing TC 1207.
01a5b2ae-6a44-5415-b4b6-ff6dd618915e | button | Has all the above been completed correctly and to a high standard? | Yes,No
1235b95a-73f1-5654-89f4-e8793eec6a24 | note | Freq - Each Lot
f5584f9a-94c1-519d-a017-68eeb10c692a | note | Key - S I
8c2ae869-ad5c-5cd1-a863-2813d83c02e1 | note | Resp - SE/SS
8d437bf9-fedc-5235-9cf9-1c94e8dc13eb | note | Remarks/record -
ab181abc-38d7-5b92-a8b3-b97937dd96d3 | button | • Installation Records from Subcontractor | Yes,No
5965c3f8-8790-55aa-8813-52c5509708bd | date | Inspection Date:
| checkpoint | 4.6 - Draw Cords
5d56464f-d09a-5559-9e36-69493c271704 | note | Ref docs - VR Clause 733.07
46fd5b54-ccc7-5b32-8fa5-40c25aa2bd65 | note | Acceptance criteria - Draw Cords to be 3 mm diameter and with a minimum breaking strain of 1.6 kN.
9c8d12de-4f10-5abd-b89b-5a354e7f267d | note | ○ Where the conduit terminates in a pit
40a6f279-c26d-55f2-a1ed-f5de365d19d7 | note | • Have no less than 500 mm of the draw cord tied to a marker peg 25 mm x 25 mm, no less than 300 mm long, left coiled in the pit for future use.
930bb6d8-7d31-51a3-8cf6-f2f005bfbcf7 | note | ○ Where conduits do not terminate into a pit.
64c70085-b87e-55dd-9d48-9d798be3afd2 | note | • Be tied to a marker peg 100 mm x 100 mm, not less than 400 mm long, driven firmly into the ground with the top 50 mm projecting above finished surface and painted yellow.
798b14ae-b056-50b6-8896-501c534e6c08 | button | Has all the above been completed correctly and to VicRoads standard? | Yes,No,N/A
d303d998-09b6-5960-8828-5142e1aa78d8 | note | Freq - Each Lot
23e9751a-3aa7-5cae-86e7-09fbb5a1529d | note | Key - I
1d728f65-1bd3-5ecf-a0eb-390e472d08ec | note | Resp - SE/SS
00fa2c9f-b196-54a2-830a-1dd0d937f1f0 | note | Remarks/record -
ea61a4f7-5e60-51f8-8498-780d073ed458 | button | • Installation Records from Subcontractor | Yes,No
e514a86e-41f9-509d-ab39-83ab76c919f1 | button | • Material Conformance Certificate | Yes,No
28ed96d4-c6f1-59cc-ab6d-dedae42b1585 | date | Inspection Date:
| section | 5.0 Backfill
| checkpoint | 5.1 - Bore access excavation
e7a840ef-d2fd-59b4-8e70-168a4b0fd721 | note | Ref docs - VR Clause 733.05
685a3020-6e57-5f0a-9073-f58d1b1381c1 | note | Acceptance criteria - Before backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative.
cfd40866-ad28-5b4e-b4a0-6d3cb957c7e8 | button | Has all the above been completed? | Yes,No
8272c4c4-1cb1-56bf-a37d-8d4182000de4 | note | Freq - Each Lot
3edb9183-2ed4-530a-b6bf-7a67150d019e | note | Key - H
f4ceb1fe-fc78-5d0b-8cbe-1d0a53446243 | note | Resp - SE/SS
51554504-036f-595a-80ae-079f456f5068 | note | SI Key - H
2947ce2d-776e-5e9f-a7f6-493ea4766e46 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Material Properties
4d248082-5992-5684-b184-e42777dcc0ad | note | Ref docs - VR Clause Table 733.081
ce7c2973-1e9e-570b-9e52-cfbc02ca1420 | note | Acceptance criteria - Backfill material properties to be as per Table 733.081.
361b1edc-788a-5b0e-a3b7-a92edfb21e8d | note | Freq - Each Lot
c80e1313-b6f2-5e3a-a85d-18c2a7bdd4c5 | note | Key - R
564e566b-227f-5aa6-80fe-27a1d22d3814 | note | Resp - SE/SS
4101b591-eafa-544c-9bb4-65a64be25fc9 | note | Remarks/record -
fd3f3dc2-ee3b-5adc-8190-7bf349b6d5a9 | button | • NATA Test Report (if applicable) | Yes,No
4f84725b-42b5-536a-8153-c0c7e7fd7872 | date | Inspection Date:
| checkpoint | 5.3 - Filling
66f317ea-85b2-5cbf-81be-107d2e540c27 | note | Ref docs - VR Clause 733.08
c24cc143-5f84-5697-ace4-41a03cd633f1 | note | Acceptance criteria - Unless otherwise specified or shown on the drawings, selected and common backfill shall be placed and compacted as follows under, around, and above the conduit after the sections are bedded:
d23ee5c4-902e-5999-b4cc-2ff3499900e7 | note | • Place and compact selected backfill 400 mm above bedding (in non-trafficable areas) remaining fill to be common backfill.
c2cdd5d7-6fb6-51cc-93c4-264f8ff434ac | note | • Place and compact selected backfill to subgrade level (in area’s to be paved)
9afa6fd6-22c8-58ba-bba4-6347ad46752c | note | Freq - Each Lot
85b01c3e-5140-5adf-b8a5-f6beb3d51c6d | note | Key - R
bce7daac-dbe9-51fa-bae7-824c504d3f02 | note | Resp - SE/SS
a4bc9b21-d1ba-5e45-8a6a-dfb665859bec | date | Inspection Date:
| checkpoint | 5.4 - Compaction - Areas not to be paved and below pavement
4a17bec3-51fa-5391-8bf2-a9cbf3a91b82 | note | Ref docs - VR Clause 733.08
3d20e959-f46f-5a3d-88fb-b1655eedad24 | note | Acceptance criteria - All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
36dd9f44-bf4d-549f-808c-485fe3b0fce2 | note | • Compacted to refusal using handheld mechanical equipment.
b0e8e5ea-982a-57f0-80ec-ab3c74ba4fd4 | button | Has all the above been completed? | Yes,No
c6c67d7e-471c-5a8b-a884-2b766286855f | note | Freq - Each Lot
8c6c121e-6a69-575b-b4ae-ec5ad4d62b7c | note | Key - R
e4b41784-aac1-51f6-adcc-9ecb5fc1d6b4 | note | Resp - SE/SS
2d7c7cab-761c-54c1-9dea-ab28355cc0f1 | date | Inspection Date:
| checkpoint | 5.5 - Compaction – Area’s pavement layer
66070f80-1df2-562e-aaa3-bb2f1d881c71 | note | Ref docs - VR Clause 733.08
78ec6b14-bc49-5d69-a773-568a52c6f827 | note | Acceptance criteria - Where specified, pavement material shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three.
74b05730-ab29-5dd6-a87a-67199c0d18e2 | note | • All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
351b23e0-be36-502d-976d-fceb7acf273e | note | • All pavement layers shall be placed and compacted in layers to a density ratio of not less than 98%. The calculation of density ratio shall be based on Modified compactive effort.
5d10baef-d2da-5f6b-9b53-4e8048fc86f6 | note | • Compacted to refusal using handheld mechanical equipment.
648591fd-fe0f-5345-98f0-bb42f639845e | note | Freq - Each Lot
879f0825-2347-51d7-af7d-9c4a7ac788ff | note | Key - R
9d043d10-a87b-5999-a3da-5b6eb6dde889 | note | Resp - SE/SS
ebd61d4a-25ee-5749-8e74-8e6ddab7b4c8 | note | Remarks/record -
ad7e2341-e96a-5471-964c-0be4f94bf4ef | button | • NATA Test Report (if applicable) | Yes,No
afa74d2b-c245-5002-8eb4-65eb5b867571 | date | Inspection Date:
| checkpoint | 5.6 - Warning Tape
a7038d60-b0dc-59fd-b974-c31ea879910c | note | Ref docs - AS/NZS2648.1
ef84ea1f-ee9c-5faa-883b-23a637c99d76 | note | Acceptance criteria - Where marker tapes overlap electrical tape to overlay communications tape:
b5bef862-2b9c-5a2a-9850-3ac38dbb00c0 | note | • Marker tape 100 mm wide complying with AS/NZS2648.1 coloured orange with black lettering “DANGER BURIED ELECTRIC CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits in all trenches where electrical conduits are provided.
e94e3b9e-3ca0-5ed4-a4b7-6effc0b505b6 | note | • Marker tape 100 mm wide with two stainless steel tracer wires coloured white with black lettering “DANGER BURIED COMMUNICATION CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits. In all trenches where communication conduits are provided at least two meters of each tracer wire shall be anchored to and neatly coiled in each communication pit.
3e2b0365-b9a7-554a-8c8d-1470844d0061 | note | • Where both electrical and communication conduits are provided in a trench two marker tapes shall be provided one for electrical and the other for communication conduits.
e07e1649-8060-590a-a66d-1fb530477299 | button | Has all of the above been completed? | Yes,No
6c8ecb60-44db-5ed8-96cc-e0c6c74a107f | note | Freq - Each Lot
57a3c365-b0b7-55d8-914f-7a95501cccf2 | note | Key - S
f3c198d7-e6de-5e16-b882-8c3613d173aa | note | Resp - SE/SS
8de034b7-d82e-5669-9577-66c3ca9413eb | date | Inspection Date:
| section | 6.0 Installation of Pits, Lids and Cables
| checkpoint | 6.1 - Location of Pits
ccc76270-d86c-59ca-926b-76970fb6cd2a | note | Ref docs - VR Clause 733.09
899262eb-8b2a-5433-9c0c-4aecad00cbb7 | note | Acceptance criteria - Pits shall be located in accessible locations for maintenance activities.
3a2107c1-6f82-5cad-8888-f69c94d6a682 | note | • Pits to have a maximum spacing between cable pits of 100m.
3e399717-f832-51ab-8abe-47f8eb5f1bcc | note | Freq - Each Pit
f653ec13-8fa0-546e-b70a-08c150f2f2e3 | note | Key - R
5d47d084-838a-543f-8d52-c1aaebde2963 | note | Resp - SE/SS
b5c82cd1-20bc-5dce-b94d-9a0e99ab5010 | note | SI Key - H I
859c00fe-5062-5215-a524-114805f9c42c | date | Inspection Date:
| checkpoint | 6.2 - Cable Pits & Pit Lids
ce1260f2-aa78-5567-8649-5e7881ef7c58 | note | Ref docs - VR Clause 733.09 TC2200 TC2201 TC2202 TC2203
ef81f1be-81fa-5fc3-9d53-7184b94ad329 | note | Acceptance criteria - Before the pit lid surround or pre-formed collar is cemented into position an inspection by VicRoads Superintendent or representative must be carried out.
911cbbe4-3b46-5110-a90e-eeabb6fe7c7d | note | • Install cable pits in accordance with the design drawings and VicRoads Standard Drawings TC-1210, TC-1220 and TC-1230, TC2200-TC2232.
881beee6-726b-56a3-b13f-9e7ae39efcf2 | note | • Top of pit lid matches the surrounding finished surface level fits neatly without movement.
76a1e091-2f43-5581-948a-4385fe9e7fca | note | • Pits watertight and suitably drained.
92504c3a-18dd-5760-a40b-46e74f1624fd | note | • All conduit connections to cable pits shall be neatly made and the ends of the conduits trimmed off and fitted with a conduit bush. The area between the conduit bush and pit wall shall be stopped with a suitable sealant that bonds to the pit wall and the conduit.
146d0d41-c457-5b2f-b0a8-159d0af4501e | note | • Heavy Duty Pit lids provided for pits in the road pavement.
1aecb02a-53c8-5306-a9d7-da80ffa6ed6b | note | • Entry conduits to be installed at: 80mm +/- 20mm into pit (VicRoads)
1d6a01f5-2c75-58fd-9d93-54b5a0ffa748 | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
b34f2ca1-2bf6-5090-bbbc-0b1d58f557ef | note | Freq - Each Pit & Each possession
cb5b6d0f-3b13-5556-a109-a9626a0c0394 | note | Key - S
a70e830b-e48a-501e-9ee7-a57eec86242f | note | Resp - SE/SS
993ab9d8-906f-5bf7-a298-ca0d4701f310 | note | SI Key - H
f26ab98b-4c46-57d0-8957-40425b82e8dc | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Detector Pits for Traffic Signals
8ea70052-7249-5998-a8df-70d8ca632ceb | note | Ref docs - VR Clause 733.10
6f54bb4c-9e34-50e7-a3fb-b3e63a542ce9 | note | Acceptance criteria - Install detector pits in accordance with the design drawings and VicRoads Standard Drawings TC-1310 and TC-1320.
e6409f5d-ebcc-5a1c-8f4d-abafdcecd6c5 | note | • Fix pit cover securely using the fixing device supplied.
2eeda5fe-4366-5d95-afa6-a7b96b27d6c9 | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
eae4ad79-4b89-5b91-91e9-689d04f49ee0 | note | Freq - Each Lot
48ba33b4-e6e0-50dd-a4f7-7b797e4d1363 | note | Key - S
0d51973b-349f-56c6-a07d-f658a849bea1 | note | Resp - SE/SS
1afd445e-adbe-5cab-a69c-d264b35d1b40 | date | Inspection Date:
| section | 7.0 Foundation
| checkpoint | 7.1 - Location of Foundation
4f936f2a-2e03-542b-b566-aab18d8b3bcb | note | Acceptance criteria - Foundations shall be located in accordance with the drawings and approved at the pre-installation meeting.
7e3a2a9f-8c1b-56d6-b149-3dabc97aa3ed | note | Freq - Each Lot
937c4b94-392a-50fb-8141-5bb6d311c528 | note | Key - R
3bce82db-d1c4-5540-9dce-c4a5997863d2 | note | Resp - SE/SSSE/SS
95b5487c-3d7c-5eb4-b6a0-dc813f03e881 | date | Inspection Date:
| checkpoint | 7.2 - Foundation Type
e8047862-1d5a-5f04-88e6-07fde8cdaabd | note | Ref docs - VR730 Table 730.111
850bc5bb-6cff-53f4-a8df-724eba219f1f | note | Acceptance criteria - Foundations and footings shall be as specified in the VicRoads Standard Drawings for the specific item of equipment they are to support, as listed in Table 730.111
52d0e9a1-1f93-57c9-b9ea-6b8597a89737 | note | • Where alternative foundations are proposed, they shall be approved by the Superintendent prior to the Contractor installing the foundations.
0b1ff44a-6194-5234-8c58-2a6a4d2e5f58 | note | Freq - Each Lot
54e6da90-0fe6-557e-be29-abdd0f36d3da | note | Key - H
d5fc99e3-6929-5e35-88f4-dab2f7b59829 | note | Resp - SE/SS
787124c5-32fc-5dbe-86c6-217ce80f360b | note | SI Key - H
5eff9fea-2c8a-5488-96ce-2e1017f2c0ad | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.3 - Inspection of Foundation
7e546606-e1b6-53de-b535-52e9fdfcb7df | note | Ref docs - VR730.11
f817a353-693e-52f7-b003-6f4352904a62 | note | Acceptance criteria - All foundation works shall be inspected by the Superintendent prior to the Contractor covering the works.
a2d9a895-2a79-52ba-a824-1f3006dcb223 | note | Freq - Each Lot
bab276ac-dc36-5a2c-9d61-5f0545ba5ddc | note | Key - H
15b148c8-b338-5aa2-a3c4-9fb509dffcb2 | note | Resp - SE/SS
d16ab6ea-ac3d-5943-a7d5-fde70ac5c193 | note | SI Key - H
d9af6795-9bb2-555c-ac3e-7a2fc6ae8290 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.4 - Concrete
8ffa414b-272e-5426-ab14-0dbbf7879131 | note | Ref docs - VR610 Table 610.161
4a74daf2-46e7-5a2d-ba3d-f4db53f4e541 | note | Acceptance criteria - Concrete is to be vibrated, and not dropped from a height greater than 2m.
fcd57aab-bacf-59e7-b7fb-8eda0084b58e | note | • Concrete is to be tested as per VR610 and should be a minimum concrete grade of VR330/32.
8ee04247-5fd5-53a4-8683-46987ffbdfff | note | Freq - Each Lot
9371e84f-7749-59f7-9236-99baf3eb4dbf | note | Key - R
b71ff581-76ea-56f5-aa05-7bfbf45620bc | note | Resp - SE/SS
1fad6096-5f7c-51e0-89c7-6bb309fd836e | date | Inspection Date:
| section | 8.0 Completion
| checkpoint | 8.1 - As-built Information
2eac14ce-462c-5233-b133-171e51cf6eb0 | note | Ref docs - VR Clause 733.12
4f93723b-0448-576b-8797-59a15a166b01 | note | Acceptance criteria - Identification and recording as follows:
6ed198c5-ca75-5426-93b9-82a7d62767e2 | note | • All conduit locations not identified by pits immediately installed at the ends shall be marked with pegs 75 x 38 mm stakes projecting 0.4 m above the ground, with the top 150 mm painted yellow, or as otherwise agreed by the Superintendent.
ce602c01-e0bf-5262-96ad-f92d6dfd3120 | note | • Conduits under road pavement shall be marked with stakes clear of the road pavement.
33b59de8-047b-5ff1-964c-6d9018fb4520 | note | • Conduits not under road pavement shall be marked with stakes at the ends, at changes of direction, and at intervals of not more than 30 m.
a515282b-d63d-55a2-932d-70b39a219280 | note | • The actual installed location and depth of conduits on the as-built drawings.
ca9e87a6-834e-51d4-b9ea-e2700deff95a | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
fa619d9d-bc93-591f-9617-ab695457c1b6 | note | Freq - Each Lot
b4b096af-2b9e-5932-af8d-375c19cbcd81 | note | Key - R
a95c7a24-cf16-5574-9d81-cc155bfe0637 | note | Resp - SE/SS
53d1085f-6b2c-5d9b-92ce-e5b113a208d3 | note | Remarks/record -
6fb7b682-61ea-50b7-8979-7b1e085ec6c2 | button | • Survey Conformance Report | Yes,No
d112c83a-1345-5e07-83d5-445c44bfb5d8 | date | Inspection Date:
| section | 9.0 Work Lot Close Out
| checkpoint | 9.1 - Test Reports
2f63ae36-3a7e-52d8-a64f-9fc86f755ffd | note | Ref docs - VIC Roads Specifications
d61770dc-e5fc-537c-89c8-2fe138406851 | note | Acceptance criteria - All Test reports received and reviewed.
52999ed0-8d5a-52e2-963e-b6e05f6e6be1 | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
5b8df7d9-d746-5eab-b172-8da582617a59 | note | Freq - Each Lot
e9e3ebdb-d4cc-5d07-bffb-40f737d1c066 | note | Key - R I
5bed81a5-e033-575c-94ea-dc79ed46c725 | note | Resp - SE/SS
e3de8ea0-994c-59d0-97f9-87306a594c3b | note | Remarks/record -
794073a3-3075-59ef-a40f-423b57688b80 | button | • NATA Endorsed Test Reports | Yes,No
afbee064-28db-5f71-8d26-94d28f28ec5f | date | Inspection Date:
| checkpoint | 9.2 - Product Non-Conformance
b1f7814c-18f0-5f3f-821d-e9515bcc0ca6 | note | Ref docs - CQMP
8c80acb9-33cf-5aee-b013-266c57cd482d | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
188bd4d9-a2b2-5df3-8f2b-80bff7211938 | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
bd39739c-0b56-5ee1-8761-0162d81dc2e4 | note | Freq - Each Lot
ad5ea24e-de9c-529a-8c40-7595472059cc | note | Key - R
ec85e8e9-72c0-5202-a800-700099f3bd0a | note | Resp - SE/SS
b4a17a18-65b4-54bb-8018-c8a3b634dd7c | note | Remarks/record -
981e043a-b02d-536a-833c-c3e2601c43ae | button | • NCR reports | Yes,No
d7ba65c1-d7a8-5880-8e56-c2e3cb07c1ed | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0022 In Situ Kerb and Channel | itp | 1630-P200-SYM-QAC-ITP-0022 In Situ Kerb and Channel |  |  | f731e439-21d3-4a69-b2fe-3724f8031819
| section | ITP Details
| checkpoint | ITP Details
7629a507-9cff-5513-8a31-a3694c2d652f | note | ITP No. - 1630-SYM-QAC-ITP-0022
d612a019-62b6-5ed1-85ac-69a5a279672a | note | Rev No. - 00
926084fb-1fe5-5d89-8bf0-d826273ede3f | note | Date of Issue - 31/10/2023
00adfee9-40de-5257-a94f-0b2aba0932d1 | note | ITP Type -
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Supply of Premixed Concrete for Kerb Extrusion
dc81da47-e46f-52cb-bd8c-550cc9acd7a2 | note | Ref docs - DoT Clause 703.05 (b), 703.11
35f868db-040b-51fa-a63e-31d6aa13b938 | note | Acceptance criteria - Concrete is minimum or equal 320kg cementitious material or geopolymer binder per m3. No slump or compressive strength requirements.
58b4fa04-5c6b-538c-a0f2-e3d25ca9cc78 | note | ○ Where kerb and channel is placed and compacted with internal vibration between previously placed formwork: Concrete is N32 Portland or 32 MPa geopolymer concrete standard strength grade.
4d24f3fa-2ba2-50a0-9556-4d0308045ca9 | note | Freq - Prior to start of works
e88ab888-2ea4-5535-b9f8-32d9b2790f8b | note | Key - R
7fc574f9-68a9-5366-bf1d-b79dea895037 | note | Resp - SE
a0e42845-0804-5c5d-a177-f6f6d9332bdb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Mix Design
| checkpoint | 1.2 - Hot or Cold Weather Concreting
39b0770e-e859-555f-90e6-9a2bc135ab70 | note | Ref docs - DoT 610.17 (a)
56f61315-7ef2-59e1-af02-d6eef0153765 | note | Acceptance criteria - Any proposed hot or cold weathering procedure is submitted at least 2 weeks from placement and approved by the Superintendent.
411aad78-1422-53be-9a14-3eee463cc824 | note | Freq - Prior to start of works
80749fb4-c75b-520a-81fc-7a88b077057f | note | Key - R
be4ff476-3176-537b-9639-ae4d660a6c29 | note | Resp - SE
cfefdbd8-7276-5283-8f39-76a6b8510d6a | note | SI Key - W
3531fe71-b8fa-5810-bdc6-08e68d00b032 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Proposed Procedure
| section | 2.0 Setting Out
| checkpoint | 2.1 - Setting Out
f07567e3-8044-5385-91aa-bb6cdb5610ed | note | Ref docs - DoT Clause 703.17 IFC Design
9b0c55b7-0a8d-5e7f-969c-c682359bd8f0 | note | Acceptance criteria - Superintendent has reviewed and confirmed the set out. Work is constructed as per the set-out line, level, cross-sectional profiles on the drawings.
1c53f006-e7ba-5330-9bd6-42c0bcd5031a | note | Freq - Each lot
2a26241d-d519-5fe1-8834-59ab21c95657 | note | Key - H
8b960b9f-c8fd-585c-acde-ff8b02651917 | note | Resp - SE
0470e1e2-8549-5bf8-8a81-dc7f2504290b | note | SI Key - H
f4a11632-5412-5e97-8ff2-0103e7d3bed6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Survey Set out
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Construction
| checkpoint | 3.1 - Ambient Weather for Concreting
fad2b0c3-f806-5865-a364-a02c7a07aede | note | Ref docs - DoT Clause 703.09, 610.17
015176a4-c92e-50b6-8f1d-ee63a7da09c9 | note | Acceptance criteria - Freshly finished concrete is protected from sun, wind, rain until curing is completed. Further protection is considered for more extreme.
c6546d61-9e6f-5e67-8454-092080acbf7c | note | ○ Concrete temperature right before placing is between 10°C and 32°C.
bf828de0-3797-55de-99c3-37d8a05faac8 | note | ○ Evaporation rate is less than 0.50kg/m2 per hour.
129705c7-f52a-53b0-90b9-db8bb029ce4b | note | Freq - Each lot
54a70239-ccd0-5c43-821b-721a03a7f474 | note | Key - S
5a318aa9-14db-5582-bda4-a18d30208a16 | note | Resp - SE
| checkpoint | 3.2 - Machine extrusion or Slip Form
c4ebe2a5-6aa0-52ee-bcb7-f6167ccc77b5 | note | Ref docs - DoT Clause 703.23
c0df7c20-0199-5dee-aa54-47b3fad41bd3 | note | Acceptance criteria - Datum for grade/alignment is established.
6d9c9426-833e-535c-8b1b-1972e7b4bfd4 | note | ○ Concrete is fed to the machine at a uniform rate, free of surface pitting >5mm and honeycombed patches. And satisfactorily compacted and dense.
d977a989-e0b5-5adc-91a4-401a6f2123e2 | note | ○ When combining fixed forms and extruded work with similar mixes, the concrete in the fixed form section is compacted with internal vibration for a satisfactory compacted mass of concrete.
c3950984-f047-519f-9faa-7d42b9625a54 | note | Freq - Each lot
2278ddca-ba3a-5258-a23d-defb50df038e | note | Key - S
ac695d34-7227-5abd-84e9-f0a05752ff0a | note | Resp - SE
46d8f01e-fe05-5058-8b3e-c4214b55f30a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Delivery Dockets
| checkpoint | 3.3 - Profile transitions and Matching Existing Sections
d88d322e-1208-5535-9653-9906500ca122 | note | Ref docs - DoT Clause 703.24 SD2102
b283dbe9-0b1c-5f10-b839-70bd6a67dfc0 | note | Acceptance criteria - When joining new and existing kerb, profile transitions follow SD2102 and should appear identical to the existing sections.
20e6d335-6353-564f-9740-01071d5a9b93 | note | Freq - Each lot
4e57ba56-a38a-5d64-80c4-ff128fac78c2 | note | Key - I
cba1e6dc-84f6-5827-afce-968d76210ef9 | note | Resp - SE
| checkpoint | 3.4 - Surface Finish (Exposed Surface) Edgings
eae5bb27-4da0-59b2-b986-8b43ee682b40 | note | Ref docs - DoT Clause 703.25
01251717-f8cb-5810-8082-cfd81f6c6e19 | note | Acceptance criteria - Edgings are rendered and have a steel trowel finish.
5ab77237-1f15-5d47-8460-b3c7beba0f36 | note | ○ Rendering applied within 30m of placing/extruding.
2e86ba72-e163-5842-bae9-bfcceca7f776 | note | ○ Mortar used is 2 parts fines, 1 part cement, and sufficient water for a suitable consistency.
f2d3c863-bf67-5bf2-94b5-a9b7be31f1dd | note | ○ Rendering thickness is less than 3mm.
758d6d51-e31c-5e9f-a28a-66d772cdfb03 | note | ○ Exposed surfaces have a steel trowel finish.
b116092f-00de-5632-ac93-f33a0d5fb20c | note | Freq - Each lot
054db5de-3c8e-5331-8ee7-495e2fcc9ac7 | note | Key - S
afb9a362-3740-5dd0-98a9-b78f5556368f | note | Resp - SE
| checkpoint | 3.5 - Surface Finish (Exposed Surface)
5d09b060-72dd-5fe9-8712-7dfe1a9a5a3a | note | Ref docs - DoT Clause 703.25
ba323265-c1dd-5e08-92d4-7c7434c7d353 | note | Acceptance criteria - Finished product is neat and of uniform colour.
5eb2bc9d-9b4b-5b15-9cbf-f0a7944d0b75 | note | ○ Edges are sharp and clean, and bullnoses are regular and of uniform appearance.
62bb4e9e-95e7-5e1f-8ee3-9a0a93ffe5c7 | note | ○ Discoloured concrete is cleaned/replaced.
bc71399e-1f89-53a9-ac73-116b8c9f1def | note | ○ Permanently hidden concrete surfaces including footpaths, edgings, concrete surfacing have a class 4 finish.
3f5913b2-d736-56d3-b604-49da2f9bc123 | note | ○ All other concrete elements have a class 3 finish for external surface and a class 4 finish for permanently hidden surface.
6c3cbf30-8b27-58f6-91af-cfe780fc340c | note | Freq - Each lot
c9652807-1a37-5ab7-8871-2785b75ba1bf | note | Key - I
416ed99f-1e64-5989-b8a8-69c36608e0b5 | note | Resp - SE
| checkpoint | 3.6 - Joints (Edgings-Transverse)
e849653b-13c0-5473-8f48-c340bfc45097 | note | Ref docs - DoT Clause 703.26
755e9d62-af90-50ce-9a21-15f2b1bcec60 | note | Acceptance criteria - Transverse joints are built at right angles to back of edgings at intervals less than 2.5m.
ac8d240f-a512-591a-9fcc-4f0cc131be0a | note | ○ Extruded edging installation does not damage or distort adjacent surfaces.
43c4d8bc-1c11-5fb4-8a8c-38d784ea5c09 | note | ○ Fixed form edgings templates are removed as soon as practicable after finishing placement.
fed1c27f-a554-5f45-a09b-606466585368 | note | ○ The guillotine (extruding) or template (fixed) cuts between 40% to 70% of the are of section. In both cases the resultant slot in the edging shall be tooled to a depth of 20 mm to produce a neat groove not less than 5 mm wide on the exposed surfaces, following which a vertical cut shall be made through the base of the groove to a depth not less than 50 mm from the surface.
8c6a5b96-4365-5468-820a-621ff5a2fcad | note | Freq - Each lot
c496812b-8084-58ee-a11b-1ebbc2dc2cf7 | note | Key - S
954bc9ed-aed4-53e8-ab12-bb2394c56806 | note | Resp - SE
| checkpoint | 3.7 - Joints (Edgings-Expansion)
5e169c1a-9de7-5465-a6e6-b692b98fd4d7 | note | Ref docs - DoT Clause 703.26 (a) (ii)
d800a6e5-3b91-573f-9a55-b68925903bb0 | note | Acceptance criteria - Expansion joints are placed at junctions with bridges and are 15mm wide filled with cork or bituminous impregnated particle board strips extending for the full width/depth of edging.
c42c7134-8d7b-52d4-ba9f-9aea44101bc7 | note | ○ Fillers are placed before concrete is placed and held firmly during placement.
1f531ba2-3dc5-50b7-8b85-aef79f10abdf | note | Freq - Each lot
6e95bb0d-7183-5e4c-91e9-02c3be2cdc5c | note | Key - R
d4ca4cbc-d230-54b1-aaff-fe90a565478f | note | Resp - SE
| checkpoint | 3.8 - Curing & Protection of Concrete
d2d57946-7b5b-5c6b-bb64-fce0d6d088b3 | note | Ref docs - DoT Clause 703.10, 703.27
2b712dbd-95ea-5093-9de7-58aa0e022958 | note | Acceptance criteria - All concrete work is:
9650e81b-4475-56e6-a54c-5ddf6085a66a | note | ○ Cured continuously with either water, wet hessian, or curing compound (AS3799) for at least 7 days. Except concrete edgings which is at least 3 days.
e18fa773-3a01-52a4-b20a-2561bf59d9b1 | note | ○ Protected from early loading (4 days): Pedestrians, animals, vehicles, and rain or other cause.
a8d71d67-6951-5458-900a-55d599032451 | note | Freq - Each lot
1d9ae900-4b0c-5b6e-a96b-2d0fae0d86fe | note | Key - S
e10141b0-ab90-59e7-8645-dc1b5c7af7cc | note | Resp - SE
| checkpoint | 3.9 - Marking of conduit positions
5b59c36b-da34-5e41-bd98-4616131ec4d7 | note | Ref docs - DoT Clause 703.28
fca0056f-ce58-5618-b139-19ec64063e71 | note | Acceptance criteria - Existing conduit under edgings are marked up above the conduit with a suitable identification.
b986592f-0936-58b1-8a23-8453ca618e55 | note | Freq - Each lot
a07707e5-648e-584a-83ea-920ea080ec69 | note | Key - I
1bdf5ca5-749f-5b6c-b471-2c97cd917731 | note | Resp - SE
| checkpoint | 3.10 - Concrete Cracking
165fcae2-9658-567a-9cb6-39f329e36b1e | note | Ref docs - DoT Clause 703.30
b2a787ee-56d6-50a5-a44a-b976eee15cc4 | note | Acceptance criteria - Concrete has no surface crack more than 0.2mm. NCR is raised for cracking more than 0.2mm.
5f129964-8190-59db-b025-d137e3fc2c09 | note | ○ Cracked sections are removed and replaced or repaired as directed by the superintendent.
85d1feed-5fbb-5788-9029-72815052138a | note | Freq - Each lot
734f90f6-7bc5-5693-820d-22f2e1848818 | note | Key - I
542f56c7-0aab-5335-8f4d-de7ef4dff7e7 | note | Resp - SE
| checkpoint | 3.11 - Repair of Damaged Kerb and Channel
53664b53-51b3-5f73-ad2c-1cd2e8ed877e | note | Ref docs - DoT Clause 703.30
362d5d4a-14f7-5d8b-910e-4194228148aa | note | Acceptance criteria - Damaged kerb concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
61a61bb3-9220-5165-8911-eda96bb8b6af | note | Kerb channel and edgings shall have a length at least 1m removed and replaced with a section:
d53dd1f5-48fe-5f9b-a98d-f41f8037ee68 | note | (a) Constructed on compacted bedding.
79d2ae5f-e24c-5e79-82a0-32623b5cd9fb | note | (b) Dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and,
e6942b52-b1d8-50df-9ceb-3e6faf9da70c | note | (c) Shaped and finished with curved trowels to match the profile and surface finish of adjoining sections
5e2373ed-532f-5e96-acdb-ce711a5cb184 | note | Freq - Each lot
9549c9eb-3c22-5c9f-94fb-b7351562ec3c | note | Key - I
da4f1e26-9d36-5bf1-a801-29ee7f20ce6b | note | Resp - SE
26557d3d-02a9-5046-b460-484aef44f7b7 | note | SI Key - R
| checkpoint | 3.12 - Paving
3fac6177-47cd-5b37-8176-22f35d44c69b | note | Ref docs - DoT Clause 703.15
61698a04-2a68-5c3c-a636-83f948d7d5cd | note | Acceptance criteria - Concrete paving including footpaths, edgings, other surfacing’s are shaped to match existing fixtures, e.g., pit covers, edgings and vehicle crossings, within 5 mm.
| section | 4.0 Completion
| checkpoint | 4.1 - As Built Survey
3c6454ad-427c-58e0-ae25-10d01ee1a874 | note | Ref docs - DoT Clause 703.15
28f649e3-ffb8-52c3-b313-96e6d4a02a63 | note | Acceptance criteria - Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm.
f1f72ff3-581f-5021-810c-cdce2cdfa854 | note | ○ Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
3e682bea-1797-51a5-8b59-76f714b5cf8f | note | Freq - Each lot
da174eb9-debc-50e9-aed3-bf0c5ed63172 | note | Key - R, I
caa80234-21e9-5d46-ab80-8bddb71af01e | note | Resp - SE
9413cd90-be74-5143-8385-4cf2465d608a | note | SI Key - R
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Product Non-Conformance
5b994fc5-0adc-5a92-bede-ab94002eedad | note | Ref docs - QMP
16b71d77-9e61-527c-9800-a547c69ddd05 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
a060e8dc-daab-500f-bd82-8872e4a96cbd | note | Freq - Each lot
9abd9580-e6aa-5e43-9f2b-3d4fa546198e | note | Key - R
2ea83a1b-705b-58b1-8bef-22f19771fe22 | note | Resp - SE
592993a2-c265-549c-a260-272f8d34c113 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
0da71d21-1ebb-5f45-b8dd-443bc22c0d00 | textbox | NCR No:
667c81a1-5923-56a5-9b8a-4726204a358a | note | ○ NCR reports
| checkpoint | 5.2 - Quality Representative to check the above criteria and records to confirm
58a3f45b-77ae-55ba-a4b1-4555bbf14be2 | note | Ref docs - QMP Lot Records
9b922800-b2d6-5634-8ad9-27a3b159bf76 | note | Acceptance criteria - All above criteria met, and records identified attached.
f1c610a9-043e-5a5e-8aeb-e2f0ee2a022b | note | Freq - Each lot
7279f0bb-4895-5b15-b6c0-ae097a4752fa | note | Key - R
80f7aaa1-1ac2-5e76-9320-768155750106 | note | Resp - SE
39170ff6-931b-5165-8bb4-8f822018dc7e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0023 General Concrete Paving | itp | 1630-P200-SYM-QAC-ITP-0023 General Concrete Paving |  |  | 05a5a01f-4cd3-482c-ba26-b65504ebd35e
| section | ITP Details
| checkpoint | ITP Details
d722448a-f3e2-5e75-b2f9-544d18609433 | note | ITP No. - 1630-SYM-QAC-ITP-0023
31138c11-c696-562c-9abb-85744f2c74d5 | note | Rev No. - 00
d3688497-27c5-5d78-abe7-f77d81efae2b | note | Date of Issue - 08/01/2024
05a60f8d-fde6-5459-802e-f5769bdb6e2e | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Concrete mix design approval
e7cb300d-ddd1-5472-a050-d7a00b2a3418 | note | Ref docs - VR703.01, VR703.05
d18d9c98-85e7-5899-b951-41fd58bc2081 | note | Acceptance criteria - Concrete mix design is approved by the Superintendent.
80e49c2d-59b0-58cf-ab0e-af6235190be5 | note | Freq - Prior to start of Works
d733e5a6-f76d-5ec2-aa8e-616c811c850b | note | Key - H
38b88d67-1f9f-56a4-bade-f6ddc65a3577 | note | Resp - SE
9710ee8b-18a7-5ccd-88b4-89b66e2f7fdf | note | SI Key - H
1bbb076c-1e28-59cf-97a0-baf8236e5d15 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
6014522d-1e24-52d4-a7ec-08e1b5e74c30 | textbox | TeamBinder Ref No.
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Setting Out
| checkpoint | 2.1 - Setting Out
3a1b4ef1-bc0e-5a7a-814a-376911cb62d7 | note | Ref docs - VR703.15, VR703.17
1498359a-9219-5f5a-86b9-2d28fb8c838f | note | Acceptance criteria - The concrete will be constructed in accordance with the confirmed line, level, grade and cross-sectional profiles as shown on the drawings or as specified in VR703.
cbb5842f-3e61-503a-bb05-822f086b56f6 | note | ○ The Superintendent has reviewed and confirmed the set out.
df9ba9aa-125d-5701-9c22-3eb481f3fb01 | note | Freq - Each Lot
5fc95af1-0222-5dec-8be6-010c53ec2d68 | note | Key - H
66ee0b1d-538a-5942-bee8-0d5948bf1583 | note | Resp - SE
021834ca-87a5-508d-976c-36cba6b9d98a | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Subgrade/Subbase
| checkpoint | 3.1 - Bedding Preparation
ea30a98f-60f1-5122-9ee1-8811ac1dfeed | note | Ref docs - IFC Drawings VR703.21
ffa5ce50-6ac0-5d24-bd0a-2076e3932854 | note | Acceptance criteria - Bedding material conforms to the requirements as stated in the design drawings. Immediately before concrete is placed, the bedding is moist with no free water on the surface.
842fb0aa-a34b-5860-871e-5b6579527bc6 | note | Edgings
89691302-d362-5ff8-8dae-2b07be21b632 | note | ○ Where edgings are constructed over pavement layers, bedding is provided between the pavement layer and the underside of the edging, or the edging is thickened to match the pavement layer.
226df386-3487-5381-a356-ca32bf56c289 | note | ○ Where edgings are not constructed over pavement layers, bedding is 100mm thick unless noted otherwise.
498373c2-bf5f-5e4a-af66-9b6be7907edb | note | Footpath and Other Surfaces
151b1dbd-12f9-5e22-a59b-bdf87db4d44b | note | ○ For footpaths and other surfacing’s, bedding is of 100mm compacted thickness unless noted otherwise.
d3f28f5d-771e-567a-b41c-783a838d5032 | note | Shared User Path
e398efe9-14cf-5125-967f-f723b71de748 | note | ○ For shared user paths, bedding is 150mm thick and compacted in accordance to Section 304 unless noted otherwise.
9f869585-b324-5ff2-8a8f-876610bf62fc | note | Jointed reinforced concrete
1d035d60-dfcb-53ff-b3d3-42e418bbfad6 | note | ○ Bedding is to be as per IFC drawings and compacted in accordance with Vicroads Sec304.
02991230-564f-595a-a392-027ecb0095a6 | note | Freq - Each Lot
9af7ff71-43e5-560f-9cd6-ad6502cd11df | note | Key - R
356d4e4a-4f00-5276-84e5-8ff047af6a35 | note | Resp - SE
| checkpoint | 3.2 - Material Testing for Concrete (if applicable)
839c6a5a-b6cf-5e15-9ba7-f7eab714b2a8 | note | Ref docs - VR304.09
8b022a43-c9c6-5f46-90e1-1e835fd70f32 | note | Acceptance criteria - For shared user paths, scale B testing is completed in accordance with VR304 with the below requirements:
ba4338eb-1919-578a-a7a5-e816aa20db51 | note | – Moisture Content: >85%
fd577ffb-05e7-5687-8d49-51cc045e5654 | note | – Compaction: ≥97%
d4ac9104-7eb3-5f30-9dd1-00d523ffa1ba | note | – Post compaction grading
23cda90d-6c6b-5f46-8de7-6f0054f66c9f | note | ○ For Jointed reinforced concrete, scale B testing is completed in accordance with VR304 for each material of the subbase.
e85e4e68-c8d6-5402-ab9d-10d45da7351b | note | Freq - Each Lot
86647b78-4a31-5104-a044-76a6e0f7d835 | note | Key - H
952345bb-81fe-5cac-b518-d2be368ad31b | note | Resp - SE
de2e6643-04ff-5894-8c5f-73a79aee94f2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Material test results
| section | 4.0 Installation of General Concrete
| checkpoint | 4.1 - Formwork
012e4a60-63ed-54e6-8f38-4e30c1fa584b | note | Ref docs - VR703.12
3ab17c76-c374-56e5-b59e-48154de905d9 | note | Acceptance criteria - Ensure materials, design, construction and stripping of formwork complies with AS 3610. As well as erecting formwork prior to placing concrete so that fresh concrete is not placed directly on the side of the excavation.
a1cf1af6-9b91-57e0-b695-8f4fbaa935a3 | note | Freq - Each Lot
2c8e22cf-b23d-537d-b385-addd4a8e5c7e | note | Key - H
6e98f873-b024-544d-9356-7ad26853a7e8 | note | Resp - SE
| checkpoint | 4.2 - Steel Reinforcement
c98fb3d6-1542-59e6-9400-2a22f8161880 | note | Ref docs - VR703.13
e034e173-be62-5917-91fc-7f2743698da4 | note | Acceptance criteria - Reinforcement complies with AS/NZS 4671, and the minimum cover of reinforcement is 50mm or as per specified in the drawings.
6fb979bd-83ef-50f3-b670-611844433ed0 | note | ○ Reinforcement is supported using either concrete or plastic chairs.
dd1800f5-e76f-5575-8822-eb0990bfb69b | note | Freq - Each Lot
9cbb90f4-8b2d-5106-a6f0-b2fe5e42673d | note | Key - R
fec17b1c-c97c-5228-97e8-93fc8c81e65b | note | Resp - SE
| checkpoint | 4.3 - Thickness and Steel Reinforcement Requirements
3fcaa2a9-dea9-5927-afc0-994fe08787dd | note | Ref docs - VR703.16
3c138c66-c922-5314-af4f-2b26027ebacb | note | Acceptance criteria - The concrete paving thickness and reinforcement is as per the drawings.
faf080fe-7bb2-5866-b1fb-25450e0aa550 | note | SUP's and Commercial Vehicle Crossings
b8816925-0fa8-5462-b315-d6a6e5312ed0 | note | ○ SUP’s and commercial vehicle crossings are reinforced with SL82 mesh and are 150mm and 170mm thick respectively, or as specified in the drawings.
984664d2-aa7e-5034-ad55-b27e8d9fdb8f | note | Medians
43a4dfef-8d72-5e46-9e9e-4e099b475566 | note | ○ Median surfacing within 2m of the edge of the median and bays of footpath, is as per design drawings and reinforced with SL72 steel mesh unless otherwise specified.
65bcd848-179d-5e4e-8119-58228d8ff5d6 | note | Freq - Each Lot
e0b74632-2c28-572b-ae7f-dce8b49cf5f2 | note | Key - R
77f7a8d1-085d-54d0-9cd8-f2076469f1b6 | note | Resp - SE
| checkpoint | 4.4 - Fibre Reinforced Concrete
dcb6e322-4d4a-5007-b8d9-9f0fa3a986c8 | note | Ref docs - VR 703.14
6818b596-e555-51e8-ba67-bd006b0f905f | note | Acceptance criteria - Where fibre reinforced concrete is proposed to replace up to SL82 steel mesh, the fibres are made from virgin polypropylene or copolymer.
33f4a457-b6a4-5266-bebd-7c23704df115 | note | ○ The properties meet the requirements of VR 703.14.
f7f86a2d-3751-5d1a-8b7b-2e294ca3e9b6 | note | ○ The worksheet and/or report for determination of fibre content has been reviewed by the Superintendent.
a316ec87-96ea-5540-86db-0d216fb484e9 | note | Freq - Each Lot
3013fd02-0a83-57b0-a02f-eea34497136d | note | Key - H
697afdc0-d8e7-54b6-b763-8023e1162627 | note | Resp - SE
e9d0b5a7-71f7-5542-83e9-56ee8eaaaa83 | note | SI Key - R
1aa44e31-4302-541d-b68c-345ec5ccf5a3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Worksheet for determination of fibre content
| checkpoint | 4.5 - Placing, compacting and finishing concrete
a7a391ee-7685-5752-81a9-04dbbd39e2c6 | note | Ref docs - VR610.13, VR610.18, VR703.08
f0db1c52-d1f5-5556-b644-39bcfd6542ee | note | Acceptance criteria - Immediately before concrete is placed, the bedding is moist but has no free water on the surface as per VR 703.21.
50a4c72c-2b9b-5846-a794-a12c048b5256 | note | ○ Concrete was not mixed when the air temperature is lower than 5°C or greater than 35°C.
39604de6-5f5f-5344-aae5-41f768393f1f | note | ○ Discharge Time to be 60 minutes unless mix design is approved for 90 minutes.
098a2136-9b4c-5eda-b28a-472c8faf0514 | note | ○ Concrete was thoroughly compacted by means of continuous tamping and internal vibration.
e0f570a7-aa53-5c89-a821-57efb560b286 | note | ○ Fresh concrete was not placed against concrete which has taken its initial set, except at properly formed construction joints.
9b4ded45-1f60-528a-a355-b3c92e5c25d8 | note | Freq - Each Lot
6e6de4e1-0c32-57f5-a3d7-6eec579c470d | note | Key - H
f17338c5-f9f2-5ab1-aae4-5cf5dee01851 | note | Resp - SE
cde484b6-4956-55cd-827a-5e66dd663e54 | note | SI Key - H
e0b89ade-b893-5543-a708-0bfe912e364b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Concrete pour record attached.
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6 - Provision For Permanent Signs
610d0034-fffd-5ee6-89c0-0d3988b6eda0 | note | Ref docs - VR703.22
93d95169-5f8b-5fa2-9564-bed8c5910ac3 | note | Acceptance criteria - Sign post sockets have been supplied and installed to provide for erection of permanent signs in the areas to be paved at locations shown on the drawings.
54d7d515-a849-56b9-99d2-265575ae9ec7 | note | ○ Socket depths, dimensions and installation requirements are in accordance to Section 714.06(d). Any concrete which falls into the sleeve has been removed.
5d881449-ae80-5340-9187-d57dbae64f97 | note | Freq - Each Lot
42a2acd0-48ca-543b-8308-27257c26a241 | note | Key - H
c9f4fb23-872c-58e2-b3e4-b95417ef29b8 | note | Resp - SE
| checkpoint | 4.7 - Conformance Testing
1bdf3ace-efcd-53e6-80f5-6b5cdee3a78e | note | Ref docs - VR703.11 Table 703.111
4d64eae6-6111-56c5-b51b-ca7cb910cc81 | note | Acceptance criteria - The compressive strength of the concrete meets the requirements of table 703.111.
0ccd45a4-fd7d-5f56-bb77-e83f3ef2d6ae | note | ○ The frequency of sampling is once per 50m^3 of each strength grade on each day.
3f8ddadd-6af3-5d65-81a4-1466a8e92a23 | note | ○ The consistency of the concrete is determined by using a slump test of each concrete strength sample in accordance with AS1012.3 and clause 5.2 of AS1379. (Not required for concrete used in kerbs and channels and edgings).
a08a6f99-c633-5729-b20b-3cf1c68298e6 | note | ○ Sampling and testing for concrete used in shared use paths is in accordance with Section 610.
36241b8a-75c8-55a6-aa81-69a6e3d06169 | note | ○ Compressive strength and slump testing is not required for concrete used in extruded kerbs and channels and other edgings.
1e9c61d9-cdd2-5be2-b49a-9d2d80e7e44d | note | Freq - Each Lot
1950f510-c04e-5317-8b10-adfbe368a304 | note | Key - R
26e43144-959b-59ad-97a8-4d61b88c6449 | note | Resp - SE
6c0079a4-bbbb-5b57-97ce-8565088b4e44 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
b1c506f9-bf27-5d90-aad4-326c942c37b1 | button | Concrete test results attached. | Yes,No,N/A
| checkpoint | 4.8 - Surface Finish
bff28e3d-82ec-5e42-be40-5cec7db0b0e9 | note | Ref docs - VR703.25
447afb38-54f0-522e-ac1c-666dcf988ab6 | note | Acceptance criteria - Permanently hidden concrete surfaces including footpaths, edgings and other concrete surfacing have a class 4 surface finish in accordance with AS3610. All other concrete elements have a class 3 surface finish.
3d810cc6-8af4-5ecc-bb6e-23f73c034736 | note | Edgings
68d56293-8104-5b2e-8d73-6067c3d3701f | note | ○ Edgings have been rendered with a steel trowel finish. Rendering to be applied within 30 minutes of placing concrete.
d9e6a3b0-edc6-5678-b2ec-078b873daff0 | note | ○ The mortar used is 2 parts fine aggregate, 1 part cement and mixed with enough water for a suitable consistency.
04c43d87-6fa0-5f59-99a1-d2ad1fe0f503 | note | ○ The thickness of the rendering does not exceed 3mm.
e85ba825-cadf-5587-8c5c-13ec25364781 | note | Footpath, SUP & Other Surfacing's
2a17d3ba-e159-5cb9-ba42-bb5aab485da8 | note | ○ Concrete placed for footpaths, surfacing’s and SUP’s, has been compacted and worked until the coarse aggregate is below the surface and mortar comes to the top. Mortar has been struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
71153c06-bd06-5c8b-9edc-50530fbe97dd | note | Freq - Each Lot
9101f348-a44c-5870-8db6-c5d8a272b168 | note | Key - R
8f108b4f-be76-5304-a10e-15d7371a466c | note | Resp - SE
| checkpoint | 4.9 - Joints
29885262-2f86-55b4-a688-266ca077815d | note | Ref docs - VR703.26 SD2071
aa03bbed-fc3e-55c0-be3c-3a287007acec | note | Acceptance criteria - Expansion Joints
28f9a05d-54d2-5730-8b01-b925e64e9dc6 | note | ○ Expansion joints are 15mm wide and placed at intervals not exceeding 10m, on either side of vehicle crossings, at junctions with existing footpaths and SUPs. Joints are filled with cork or bituminous impregnated particle board strip extending for the full width and full depth of the paving unless noted otherwise in the drawings.
b5c2df52-c24f-5e0c-a9b8-2636e8db50ec | note | Control Joints
f1a58125-e628-5639-afe7-2bf9204d4bf0 | note | ○ Control joints are at least 25% of paving thickness and 5mm wide at 2.5m intervals unless stated otherwise.
83bb8333-0d7c-5fb4-93f5-afa57bcf73ac | note | Extruded Edgings
ae5399c9-d23d-5528-b3bc-5c8f215ffb9a | note | ○ Extruded edgings have transverse joints every 2.5m with a width of 5mm and tooled depth of 20mm.
e33c3c33-af59-526d-b4c6-27330a2a799b | note | Indented bus bay contraction joints
d2e9ba68-fadf-5468-93d8-c7fb608dae20 | note | ○ Indented bus bays have 15mm transverse contraction joints at 3m intervals, and are filled with neoprene compression seal as per SD2071.
b212b903-7bbd-5d34-b10e-b0f9cdf406d2 | note | Freq - Each Lot
e6fed251-16a1-51b7-b02c-2d3c9a0df650 | note | Key - R
3c47e602-c8db-5f63-a445-70a776a7d9e5 | note | Resp - SE
| checkpoint | 4.10 - Curing of Concrete
abab31a7-7e95-5314-b05f-e3a2f7e6eecd | note | Ref docs - VR703.10
3e4ccb61-ec06-5ea3-b4c6-34766207bd8d | note | Acceptance criteria - The curing process has commenced immediately after finishing operations are completed, when using either water or wet hessian or curing compound.
c6c9ecf1-05b8-579f-b712-6e76dbf9a6b8 | note | ○ Curing compounds must comply with AS3799.
4af6ca86-22c6-589a-935d-aab4fe52aba4 | note | ○ The curing process using a curing compound is completed for a constant period of no less 7 days uninterrupted for general concrete purposes and at least 3 days for concrete edgings.
c0a73492-1f08-5485-98af-704f5b4001fe | note | Freq - Each Lot
a095f196-aabb-5e23-bcf4-112925ec27b7 | note | Key - R
28cd72b3-3f78-5510-9edd-d224416db2c3 | note | Resp - SE
| checkpoint | 4.11 - Formwork Stripping
84ffca61-1896-54f7-b374-cb0a5eea6c83 | note | Ref docs - VR703.12
ca00045f-7d38-598d-9be3-9d25763456c3 | note | Acceptance criteria - Formwork has not been removed until:
2c551683-e39f-57a9-8600-a7e8045fc835 | note | ○ 2 days for vertical formwork on external surfaces: and
a45d3950-19c9-524f-84ed-81f1377f8962 | note | ○ 1 day for vertical forms on permanently hidden surfaces.
64a5cc5a-99d5-5080-b49c-3b37122a3a80 | note | Freq - Each Lot
47016425-0218-5437-a51f-3ec62082e65e | note | Key - R
7409b57e-e8e0-5cfe-9c2b-36e43fd653b4 | note | Resp - SE
| checkpoint | 4.12 - Protection of Concrete
1c7cd55f-7cf7-589d-931a-b7dc6c246216 | note | Ref docs - VR703.27
f4755d75-22cd-5908-929e-30711c21a29a | note | Acceptance criteria - All concrete is protected from damage from early loading.
9c90d4f0-959b-5bfe-b81c-3d23261485c7 | note | ○ The contractor has ensured that no vehicles are permitted to cross over private entrance or commercial vehicle crossings a minimum of four days after completion of casting of concrete.
aede5460-f45c-5fe9-82fd-ac8916c504ed | note | ○ Vehicles greater than 1.5t may not be permitted to cross until after 7 days.
395a941d-89dc-5857-949e-8c5e8a3bdc12 | note | Freq - Each Lot
e4c9df0c-13af-5891-ae30-316c1c9a20b1 | note | Key - R
32ae57da-37ce-545e-ac63-f9dcc89fbda1 | note | Resp - SE
| checkpoint | 4.13 - Backfilling
dc4c2915-222d-5553-b9ce-a7629fe99042 | note | Ref docs - VR703.29
31a3da49-bb6b-535a-979b-45951e195b98 | note | Acceptance criteria - Concrete is backfilled no earlier than 3 days after placing. Topsoil material is free from perishable matter and then placed and compacted as specified.
d17a7a02-40a6-561d-b521-a162a22649e5 | note | Freq - Each Lot
5bdcae18-626f-5dd2-8d4e-44fd5aec048b | note | Key - R
1a06b70a-f404-5319-8770-aae4378f26c3 | note | Resp - SE
| checkpoint | 4.14 - Inspection of Concrete Cracking
20483f62-f940-5736-914f-c0f7d9c10c8a | note | Ref docs - VR703.03, VR703.30, VR703.25
a40b5f3e-29d8-5d5b-b386-a956017a6053 | note | Acceptance criteria - Concrete has no surface cracks of width greater than 0.2mm. Where this occurs, this is identified as a non-conformance and repaired in accordance with section 687.
d3b4c350-c947-5060-bfef-2772c47bd10f | note | ○ Any concrete repairs have been carried out using a method and materials accepted by the Superintendent.
e4830a91-dcf9-5f4c-9444-15460fd5d00e | note | Freq - Each Lot
23b57ec9-22d4-5569-ac98-6934ab9cd43a | note | Key - I
67ee4b08-c06a-532b-bb90-25bf89741dd3 | note | Resp - SE
3f3a943c-a73e-58eb-87f5-f2f03bd3d733 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 5.0 Completion
| checkpoint | 5.1 - As Built Survey
f9aaadcc-e1e2-522d-bd31-d00c5e9aada6 | note | Ref docs - VR703.15
9dc2f5b8-d0c1-5e86-b33c-9f2410500764 | note | Acceptance criteria - All surfaces satisfy lines, levels, thicknesses, and cross sections as specified on the drawings within the specified tolerances stated in VR703.15.
cb849330-2c45-503b-88a7-0fdb7dd62c87 | note | ○ Section dimensions as per the design drawings.
8c385a2a-2231-5ec0-9437-903f3be1bff8 | note | Freq - Each Lot
b2005aa1-2caf-5a8a-ba0b-ecc8b22ec680 | note | Key - R
6ba7249e-8dc0-52d9-b646-3044fab7d889 | note | Resp - SE
697ba82c-b1c8-5f6e-a1b5-cccd2af73ce3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
07fb80bf-11cd-544e-bbcf-f60831153aac | button | Survey Conformance Report Attached | Yes,No,N/A
| checkpoint | 5.2 - Test Reports
4f659bb3-70ea-54e0-ba20-e87140a76713 | note | Ref docs - VIC Roads Specifications
0e1ec031-01a7-5e5f-a3ae-07cfc3a87279 | note | Acceptance criteria - All Test reports received and reviewed.
dc91ccb2-1bba-58fd-8237-d772eae4d474 | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
fe048293-6dbd-5052-801a-a1744f7a055d | note | Freq - Each lot
0eb8856e-25f0-5a83-8c1b-0cecdcb01d89 | note | Key - R
4e9a03af-bcd4-5fd0-86bd-0f01097b7435 | note | Resp - SE
| checkpoint | 5.3 - Product Non-Conformance
b1613143-fe44-546c-bcfd-4e34ef394e6d | note | Ref docs - CQMP
a9380aba-4811-5774-86da-caf6ab8cdae7 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
8f9dcca5-e687-5d18-8896-0c27c0270957 | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
391b6ef2-1a76-5ff7-a343-67116768753f | note | Freq - Each lot
b584deed-7dca-59d5-8477-3d43eaf90922 | note | Key - R
e8ac39e6-ded9-53b8-8734-62762955b181 | note | Resp - SE
9410eec1-1b59-54f3-924c-fa2ad93e1d4e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
e6e9d09b-f38a-5d61-8654-5423e1dc814f | textbox | NCR No:
1eae429f-2006-5a38-be51-c1d10f1dd8c3 | button | NCR No | Yes,No
19f89dab-5d47-5365-84ea-cf5edab9a0c9 | note | NCR reports
| checkpoint | 5.4 - Quality Representative to check the above criteria and records to confirm
810d11f1-aa52-5627-b533-e4afcbe98f3c | note | Ref docs - CQMP Lot Records
45de3b9e-cb61-59c1-a54c-382f1f9331ae | note | Acceptance criteria - All above criteria met, and records identified attached.
a229c0eb-9d97-56b3-84a6-e7e4e4a32e9f | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
3492822d-85b0-5dcd-a3ef-96aa2edba57e | note | Freq - Each lot
3817280d-c02c-590f-bab7-30b0d0e543bd | note | Key - R
93d7f707-26da-526c-a706-b87b274e13a4 | note | Resp - SE
7c49a212-fbe0-5760-878d-1801b4557005 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0024 Foam Bitumen Pavement | itp | 1630-P200-SYM-QAC-ITP-0024 Foam Bitumen Pavement |  |  | 5592a156-eec2-4540-a50b-5535a0c575ac
| section | ITP Details
| checkpoint | ITP Details
4cd182b4-85da-5499-92c8-7398648367ec | note | ITP No. - 0024
80bd0b17-6d77-5bb0-acde-95498ee89e28 | note | Rev No. - 00
bf9554e0-0b9f-59d5-b49d-cda817112ee6 | note | Date of Issue - 19/03/2024
491c6e57-8765-51e8-a8fb-5a76fae92ec8 | note | ITP Type - New
| section | 1.0 Pre-Construction Activities
| checkpoint | 1.1 - Safety – SWMS developed and reviewed
3deae076-b263-5f80-b212-e8e430be6eed | note | Ref docs - SWMS
04cf83b2-cbe6-518e-afe3-94afb8ba786d | note | Acceptance criteria - Specific SWMS for work task has been developed and reviewed by all parties involved in the works.
ffad35a4-5572-5604-8e22-213fbbddb024 | note | Freq - Prior to works
dc43870a-41ef-535a-b686-9ff421a9528f | note | Key - R
5c205428-268b-5a73-9d26-f8c602ce07ee | note | Resp - SE
11eb2e84-e499-5857-8daf-629722d9c956 | note | SI Key -
b22aa696-1af5-5669-952c-41324c6cbdfe | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
53ea7813-bc46-59dd-91ba-1fb70bc07af7 | tickbox | SWMS approved and ready for task
| checkpoint | 1.2 - Previous layer conformance
54253c1e-4520-5586-a7bd-03496376fd4e | note | Ref docs - Quality Documents
aa7a939b-e2d2-5383-96cc-01a7b2dfaf4d | note | Acceptance criteria - Previous layer has been signed off and approval for foam bitumen layer is approved by MRPV
3e4c1396-65da-5b5e-9c01-32b844c9a6e8 | note | Freq - Each Lot and prior to works
85832086-ca9a-5e62-8b11-0109da975531 | note | Key - H
2433f06d-8017-5073-9f67-a1d35afce523 | note | Resp - SE
e58e8113-c73f-5310-a02f-9fe1b199351b | note | SI Key - H
850281ab-a993-584d-9304-b636b4dfbd0e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d6b5ca6f-558e-5a5f-a1bb-69781ebd3bee | textbox | Previous lot ref:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Laboratory Testing – PSD Testing of pulverised pavement stockpile
b227a6f4-03da-5d3a-85f5-f88c245c796e | note | Ref docs - Test Reports
23263907-72be-5bc1-bffa-47a6c661c86d | note | Acceptance criteria - Particle size distribution testing has been completed on the pulverised pavement stockpile.
822c873a-591f-5050-afb4-60637a6eb856 | note | ○ Results from testing have been received and passed on to MRPV for review prior to beginning works.
4582a2b4-51f9-5c41-a80b-60c625e4574a | note | Freq - Prior to works
4ee6e3ac-7959-5641-9ec9-ff2086696a8d | note | Key - H
7e21113a-7e96-5bce-a0ca-8e6208fba9d6 | note | SI Key - H
92011ac8-b5fd-5141-8f58-2c6484f9f3ef | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
50974ee2-812c-5873-86f9-50f73127367f | tickbox | PTC PSD and PI Reports (Pre- Construction)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Laboratory Testing – Retained modulus of foamed bitumen volume expansion
53fcf0da-2635-58ea-8fef-c84a900b34f0 | note | Ref docs - PTC Test Reports
1de01372-2aec-56a9-a00b-5d5847e59ae1 | note | Acceptance criteria - Testing for retained modulus has been completed and results received for the foam bitumen volume expansion retained modulus.
35df928e-4864-5f8b-9c2c-72d9d7a7fbc5 | note | ○ Minimum retained modulus value: >0.5
0607eaf7-2708-5976-8d21-5273db5e852c | note | Freq - Prior to works
df67d76e-ae4c-5728-a822-f887f7882f51 | note | Key - H
3981d1e1-974f-53c1-9b5c-1856ef21c9b8 | note | SI Key - H
71b0689f-5654-55cd-bd59-2e5d0c981bf0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
55682809-8fd6-5caa-9483-628e0d7f9fff | tickbox | PTC Retained Modulus Test Reports (Pre- Construction)
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Mix Design Approval
c23f9fc4-6ec9-5908-869f-fbb280e05e3f | note | Ref docs - DTP 308.06 754- MELGE3056 62BV_rev3 DTP 308.05 DTP 308.06 HP
18cc9556-728e-5e54-958d-c1cfc287abdc | note | Acceptance criteria - Mix design has been received and reviewed by Symal, to ensure it complies with VicRoads Standard Section 308.
b438fefb-cf29-5f26-8457-1bb1025b3fbd | note | ○ The Contractor shall not commence work until all mix design details have been presented to the Superintendent showing compliance with the requirements of Clause 308.05 and approval has been given for stabilisation work to proceed.
8a594682-b722-53df-a3a1-d40ed52aa74f | button | Mix Design approved? | Yes,No
849d3d7a-c16d-5921-ab9e-6a3bd5d937d7 | textbox | Mix Design Reference:
e8c5f947-8bc1-5ac6-aa96-b422032aadd6 | note | Freq - Prior to works
20041126-a63b-5497-aa13-9eaa9297f86f | note | Key - H
5963441a-3212-5ae2-a4ed-0423b7ab40a6 | note | SI Key - H
f1ed20b3-436e-546f-9b32-affd27421cf5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
6a024074-b4e9-5a83-be09-376e90cd4bc3 | tickbox | Mix design, Tetra Tech Coffey Design Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Lot Map
c6f85eaa-63be-586a-8af7-85e43985cc88 | note | Ref docs - Design Documents
f17871ea-14e9-500a-ad83-b8d34f7ff99c | note | Acceptance criteria - Lot map and area has been established.
fc984698-0211-59be-911a-f4796a508074 | note | Freq - Each Lot
f8f0df38-4622-5f18-8c20-a3e031cae72d | note | Key - R
9a2d70e7-3921-5209-b962-592aea426a30 | note | Resp - SE
b1297383-2dbb-56e3-9d90-88153fb31349 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bbd63efd-2f6f-5b0c-a0d2-9325ab0f2b2a | tickbox | Lot map
| section | 2.0 Construction Activities
| checkpoint | 2.1 - Pavement Temperature
14b5c9e3-71b1-5e24-8cd9-c9d964d9c298 | note | Ref docs - DTP308.08 (b) Table 308.151
6dbcc0a0-633d-50b8-842e-c0670337bd97 | note | Acceptance criteria - At the commencement of the shift, pavement temperature shall be measured at a minimum of ten random places.
fc9dbc50-a504-5f50-a929-6f174751b3f0 | note | ○ Depth of temperature reading: 50mm
655fd529-8eab-59d7-98c5-1a2a4d248e54 | note | ○ Minimum temperature reading before proceeding: 10 Deg C
b7b24de4-3d20-5dba-9008-126a75e465be | note | ○ Details of procedures for measuring pavement temperature and ceasing operations in the event of rain or strong wind shall be submitted to the Superintendent for review.
b2aa060f-f0e0-5f89-9165-f635dc2aef1f | note | Freq - Prior to works start
452d2038-b262-54f9-a0fb-353bacecb2c1 | note | Key - R
9cf51c83-3dc8-595a-8369-2493b09398f6 | note | Resp - SE
fbb177bb-e26f-5df1-92d3-ca726d427e98 | note | SI Key - W
| checkpoint | 2.2 - Layer placement
5d7a6f48-bf18-5f8c-bf16-d5dad43803e2 | note | Acceptance criteria - Pulverised pavement profilings to be placed in a 190mm thick layer.
76e221b3-843a-5b67-8ad8-8b6220120184 | note | ○ Class 3 crushed rock to be placed in an 80mm thick layer.
921b8532-dad7-5833-916f-acbde1542a96 | note | ○ Layer thickness to be verified during install by survey/GPS.
1383c693-2703-55a8-af8f-b49b7da914bf | note | Freq - During works
36c4a164-b7f7-529a-8a16-6c9cf827aae7 | note | Key - W
d50aaad6-dee1-5cfb-a5d9-329974aac613 | note | Resp - SE
cf35a265-f89d-5c94-8afe-3ab57f5da244 | note | SI Key - W
| checkpoint | 2.3 - Supply of Hydrated Lime
99a38262-8ebc-5381-81f1-f474d8fc3529 | note | Ref docs - DTP 308.04 (b)
4734d2ae-4f11-5a06-a096-64658d2da05d | note | Acceptance criteria - All quicklime and hydrated lime supplied to the job shall be provided with delivery docket showing an assigned ALI at the start of each production week. The assigned ALI shall be determined by averaging the six most recent test results for ALI. A test certificate for determination of the ALI shall be made available on request
fec28be7-1976-5625-bbdf-b8b4655a8b31 | note | Freq - Each Lot
2e229ecb-cc51-53ab-9323-1442b23dc244 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
b943498e-1d30-5ab5-86c0-145be33d7a6e | tickbox | ALI Test Certificate
| checkpoint | 2.3 - Secondary Stabilising Agent
60f1c4b3-2144-53b3-9ce9-5d2d8b1e7a1b | note | Ref docs - DTP 308.14 (a) (c)
dd8bb09d-8b13-51cd-988a-8defee5e4cde | note | Acceptance criteria - Binder (Lime) shall be spread at specified rate on mix design.
9c9a8bc9-6c33-54e7-97f9-e282d9b447dc | textbox | Spread rate:
79e0e13a-1050-562d-8185-89fa67a850bc | note | ○ Mat test shall be completed prior to commencement of spreading secondary stabilising agent.
2f192c9b-9a51-512e-87c7-e5dc1e24d428 | button | Mat Test completed? | Yes,No
2ae115af-f46d-5f4e-8b4d-fd1499cda5ff | textbox | No. tests?
81dce9e2-32b6-51a4-bcc9-63565bbfd382 | note | ○ Lime to be uniformly spread over the unbound pavement material. Mixing to commence as soon as practical
6e5a083b-be16-51d9-aa5a-7b7751e076c2 | note | ○ No trafficking (other than construction traffic) to be allowed after spreading of secondary binder.
12835e6a-33de-5d0e-bc4d-c443fe1c0282 | note | Freq - SE
dd59da3d-a43c-5659-804c-96d2cf6860cf | note | Key - H
958510a1-5a03-5f48-b6d4-e6ea27673775 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Uniformity of spreading of secondary binder
8c724839-0056-51a0-9071-3985c0934462 | note | Ref docs - 754- MELGE3056 62BV_rev3, DTP 308 Table 308.151
fba2b142-4aa0-5433-9db4-da0867bc9075 | note | Acceptance criteria - After the spread rate is confirmed using three trays or mats not less than 1 m2 as per Clause 308.14, three randomly selected supplementary binder spreader runs should be tested per lot as per Clause 308.14 unless the forward speed of travel of spreader or the rate of spread of the spreading unit is changed, then the above process shall be repeated for the new forward speed of travel or new rate of spread.
6f9ed9cf-c910-5a26-abe5-2a01339a7976 | note | ○ Exception: where calibrated load cell computerised spreading devices are fitted with a system to continuously monitor the spread rate every 100 m, recorded on a daily report sheet.
a58f0e9c-6d28-59a0-891a-86cbe838b23a | note | ○ The Contractor shall have a current certificate of calibration for the computerised spreading equipment and shall produce evidence of the actual running spread rate when requested by the Superintendent.
c537d982-ba1e-5774-95c0-7894124a10b5 | note | Freq - Every 100m of spreading
d5eb02a9-f17f-5be3-b81f-a7f216ce326e | note | Key - W
0299cd51-59cd-520c-9a3c-b71fff03c339 | note | Resp - SE
b4a5f833-003f-5964-b44a-8bce30d9abb0 | note | SI Key - W
f086d51e-867c-5a8c-ae52-c925f3077571 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
28b1ab08-0717-5b09-ad81-87361eff4589 | tickbox | Calibration Certificate
99678b2e-08fa-5acf-b1e7-8bceb4deb37c | tickbox | Daily Report Sheet
| checkpoint | 2.5 - Initial blending uniformity
b0d85c32-c31b-521d-8ef5-0d13f6eaca30 | note | Ref docs - DTP 308.08 (d) and (f) and (g)
c5104029-e47d-55be-bbf1-d815579c6765 | note | Acceptance criteria - After lime stabilising has been completed, a small area to be hand-dug to confirm the material has been blended uniformly to full depth.
ed23cae4-fff0-5a5a-b783-bcf603555ec3 | note | ○ The incorporation of the bitumen is to be carried out to the specified thickness in one or more mixing passes.
3a8488f8-5f83-5b36-b190-ab24f8cb3481 | note | ○ Foam bitumen stabilisation should not proceed if the bitumen temperature does not comply with the specified bitumen temperature included in the test certificate required in Clause 308.04(a).
828c8de1-a9b4-5cee-9eae-f94e20dc48b4 | note | ○ Where indicated by visual inspection that the foamed bitumen is not uniformly mixed and/or the moisture distribution throughout the layer is variable, Re-mixing to take place improve the uniformity of material, bitumen and/or moisture.
94ed0a09-5b95-5975-9807-1fb45b2d35e2 | note | ○ Inspection is to be a visual inspection by Symal Supervision.
18049c0f-fc22-513a-abd9-fb294fe37121 | note | ○ Pavement is to be lightly compacted.
8a685f99-f6da-5772-b15a-2446e2fd111c | note | Freq - Prior to foam bitumen
e760af70-fd7a-5302-85d0-0b6d9ac002da | note | Key - W
60bb5ecc-0e9e-56bb-b005-23c527de2584 | note | Resp - SE, LH
b16a77fc-c0f7-5d48-8cbf-2bab7bd0b54b | note | SI Key - H
f00bf853-a149-55ac-9782-7bc071f2eef6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
fdf556a5-e908-5893-8d56-17af7e37dc0d | tickbox | Symal/ MRPV Visual Witness of Hand-Dug Trench
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Relative Moisture Ratio (RMR)
4a74d142-de6e-55cb-9d5b-d013f3750809 | note | Ref docs - 754- MELGE3056 62BV_rev3, DTP 308.08 (g)
af441b02-87c4-569f-8573-8fd1012738b8 | note | Acceptance criteria - Prior to the incorporation of the foam bitumen the Relative Moisture Ratio (RMR) shall satisfy the below:
af672d7e-0e56-5d06-828f-d24d1f4aa03a | note | ○ RMR: Between 55% and 75%
85bcd66a-0139-5fee-b4c1-8d08aa637c59 | note | ○ The RMR is to be taken as the ration of the in situ moisture content prior to the incorporation of foam bitumen, and the material OMC, as a percentage.
a61efd55-d9df-5fdf-a718-c735cbb9ebf3 | note | ○ RMR (%) = In Situ Moisture Content / Material OMC
4d849228-cea9-5897-9b54-a6ea339b7009 | note | ○ The relative moisture ratio (RMR) prior to incorporation of the foamed bitumen shall be not less than 55% or greater than 75% of optimum moisture content (OMC) of the material.
addbbab5-a9aa-5670-9c56-90b35a38dc11 | textbox | OMC:
4c98923f-f58f-5f98-8d61-b6c6750fe8a6 | textbox | Moisture Content:
d601e97f-c088-5221-996b-69aa3e58b19d | textbox | RMR:
0ad1098b-f0c7-52c2-99ba-012a1f66a077 | button | Confirm above RMR is within specifications prior to foam bitumen? | Yes,No
558a91a0-0065-54af-90ce-102be8047bf4 | note | Freq - Prior to Foam Bitumen
c78ea12a-7716-5d87-b5e6-fe0d2a84c3d1 | note | Key - H
87b7bf5a-e6eb-5966-9649-382e5a8e06c7 | note | Resp - SE
8e93e7f2-cbb6-51c5-ab55-2570a90e6167 | note | SI Key - W
| checkpoint | 2.7 - Bitumen Supply
eba5e7a7-aaf6-55fb-833b-e5802e75f2a9 | note | Ref docs - DTP 308.04 (a), 308.08 (e), 308.14 (c)
3b9527be-7682-5a8c-9e82-420ff51fb3c9 | note | Acceptance criteria - Bitumen shall comply with the requirements of Section 175.
e37a0d5d-97b2-56bf-b564-9a96a7d93bc0 | note | The Contractor is permitted to incorporate bitumen foaming additives to the bitumen provided a test certificate is produced confirming that the half-life and expansion ratio as specified in Clause 308.14(c) are met at the bitumen foaming temperature. The test certificate shall include:
7e142c1d-0b56-5d9a-b219-f4b621b9fe5e | note | (i) The form of the foaming additive i.e. a solid, liquid or paste
bedd3e45-3d18-578e-b859-9a5c4338cacf | note | (ii) Chemical and physical properties of the additive
f1c8eed4-fbdf-5c7f-8f7c-e196731f04fe | note | (iii) Method of handling and mixing
62b73ed9-3fe4-5446-98f6-751e6ea0fe79 | note | (iv) Dosage rate for bitumen used
969e7df0-36bb-547a-b055-82399270967a | note | (v) Mixing time and effective life in the bitumen
ca96372b-5b12-5865-905f-93dd703950a8 | note | (vi) Shelf life
e3524ce1-3453-5a8f-96e6-3666b81deb31 | note | (vii) Half-life in seconds and expansion ratio of bitumen with additive and the specified bitumen temperature
06f30f45-4974-56e9-8ae6-053f9fb1b14e | note | (viii) Materials Safety Data Sheet.
da10f35f-a7b4-5a05-9d16-aa7b05b8d5b1 | note | Requirements:
c06b66bf-148d-57d0-a5a3-fd722124b53b | note | ○ Minimum Expansion Ratio: 10
5f909a2c-9164-548c-a145-be522c151178 | note | ○ Minimum Half-Life: 20 Seconds
6f07a79d-18d1-5437-a5f2-e473d3cabf8e | note | Freq - Each Tanker
87f3a863-6c15-5f33-9d36-197a4cd93176 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
eb14eac4-c561-5b48-9a72-682b8d45ac63 | tickbox | Bitumen Test Certificates
| checkpoint | 2.8 - Primary Stabilisation Agent (Foam Bitumen)
7e32f4fd-fa84-5164-8c20-f8caf2dd61ac | note | Ref docs - DTP 308.08 (g)
9129c347-5dfb-5d1d-9724-8b7c0a08a429 | note | Acceptance criteria - The foam bitumen agent shall be incorporated and mixed into the full depth of the pavement material. Ensure supplier bitumen complies with the specified temperature.
0c2e184b-cab6-54d7-a731-b50358270822 | note | ○ Uniformity of mixing is to be completed by way of visual inspection.
775c7426-0002-5904-b389-627d875aae3f | note | ○ Mixing shall cease if streaks or blotches are observed in the material.
d1fc337b-7cd3-5f9e-b7f2-df83bed717d3 | note | ○ Works shall recommence once the Superintendent is satisfied that uniformity of mixing has been achieved.
d176210f-6233-5334-b724-7e2ac070eccf | note | Freq - Each run
892c5e03-56a5-5c43-ad80-f05a30dcab01 | note | Key - W
80bd1546-5fb0-5577-b1d7-e0e1c7be7057 | note | Resp - SE
9b8bb7e7-1ad9-5438-8807-d2290f433b71 | note | SI Key - W
| checkpoint | 2.9 - Bitumen Application Rate
df884a9f-8669-5817-90e1-bb1e6d734c1c | note | Acceptance criteria -
6277e584-5e3b-59d0-8924-e0389d6b3a3f | radio | One test per continuous spraying run ascertaining the quantity of bituminous binder sprayed per m2 by either: | dipping the bituminous binder supply tanker at the start and end of each spraying run; or,a calibrated computerised measuring device which continuously monitors the bitumen spray rate per continuous spray run recorded on a daily report sheet.
236b4d58-e27d-5d49-8d4f-c7036172a6e3 | note | ○ The Contractor shall have a current certificate of calibration for the computerised bituminous spray monitoring device and shall produce evidence of actual running spray rate when requested by the Superintendent.
884297c4-bae5-5c90-a9b9-f92e4ad6845e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
acb3d5be-607d-5587-8d43-8750cac79468 | tickbox | Calibration Certificates
| checkpoint | 2.10 - Testing for Bitumen Foaming Characteristics
8c741db2-71ce-5256-8f1e-dce9900d18dc | note | Ref docs - DTP 308 Table 308.151 Austroads Test Method AGPT/T301 Section 8. ‘Procedure’ 754- MELGE3056 62BV_rev3
08dc9c1e-c742-5ca9-84d6-f30b506df49a | note | Acceptance criteria - Test the half-life and expansion ratio of the bitumen from the test inspection nozzle on the stabilisation machine before the bitumen is used in the mixer and with the tanker connected to the stabilisation machine. Frequency of testing: Every tanker load of Bitumen supplied.
8f239e95-bf1f-5fd2-a3fa-a95d69b44dc9 | note | ○ For foam bitumen, the minimum expansion ration shall be 10 and the minimum half-life shall be 20 seconds. In accordance with AGPT/T301, the following test information shall be reported:
02e0da7f-449e-5b0e-a5fb-ce108e440849 | note | a) Date the test was performed
7ba2d5fb-b62a-543f-bd60-d6662af022d4 | note | b) Reference to this test method
cd99b243-a14e-5579-a251-2b4ab56f961d | note | c) Reference to the foaming unit used
9a51dcf0-a06a-5d41-a1a3-3023aeca186b | note | d) Reference to the dipstick used or the ruler used
4a6b22db-d406-5f12-ba7a-37533cd825df | note | e) Identification of the bitumen used
38fd508b-9aa7-5e92-8696-b38b619fb1c6 | note | f) Identification of any foaming agent used and the amount added
68656fa0-35d8-578f-a1e6-451f2014c75b | note | g) Temperature of the bitumen at the time of foaming
7d717033-fbe0-5f31-a01e-fe73bd739d72 | note | h) For each water injection rate report the following:
3e192bb6-9498-5098-a962-1caa594f8ee4 | note | 1. The water injection rate during the production of the foamed bitumen
cd17e943-8473-5751-912e-e793b7d032e2 | note | 2. The mass of bitumen and condensed moisture discharged
b16894f8-46cb-58c2-8cd4-3ffc3d136b3e | note | 3. The three individual foam expansion rations (to the nearest whole number)
60873e2a-0d62-59e6-8dd6-0b21c0585cfe | note | 4. The three individual half-lives (to the nearest second)
17be8a72-fce6-57a2-8221-2be9a5a68922 | note | 5. The average maximum foam expansion ratio (to the nearest whole number)
3459fba3-bae9-558c-85b4-fb2d9f4a3733 | note | 6. The average half-life (to the nearest second)
c3fe1dfa-c34f-50e5-8661-4b890f804e4b | note | Freq - Every tanker load supplied
| checkpoint | 2.11 - Jointing
16adefaf-7508-5eba-94a9-59b8d98ad4b3 | note | Ref docs - DTP 308.09
af5a37a1-8c58-5000-9bff-8c5230ad3fa0 | note | Acceptance criteria - Longitudinal joints shall be avoided by completing a full carriageway width each day.
25c91d45-a5dc-5ee7-ae2d-c1f7a4ab41b6 | note | ○ Joints shall be formed by cutting back into the fully compacted previously stabilised material by a minimum of 100 mm.
fdbb3546-a537-5bc5-a986-b0b0f8fcf7a4 | note | ○ The level and shape of the surface at all joints shall be within the limits specified in Clause 308.03
1253ecaa-7937-58fd-88d0-d1ae11b280ce | note | Freq - Each run
070c4200-d581-5866-8652-bb5f4a51b7a6 | note | Key - W
73d5ccdf-b1fe-5032-97ff-8bd7ef4fa011 | note | Resp - SE, LH
ac2cfb6a-e30e-5d02-868a-9b26e61f7adf | note | SI Key - W
| checkpoint | 2.12 - Initial Trimming and Compaction
6a00df35-001b-56de-a9da-c3a21bdd8c5e | note | Acceptance criteria - The stabilised area shall be initially compacted as soon as possible after mixing and within the allowable working time.
6c5c778b-1b50-5f3d-bc95-e24a714f57c7 | note | ○ Initial compaction to eliminate height differences through the stabilised area.
93c5ae1d-1f00-5e61-b28f-4c32beed064f | note | ○ The surface is to be trimmed with a grader to the approximate alignment, height and shape.
a3154805-845b-5ac3-91d9-e384c25e7d19 | note | Freq - Prior to conform- ance check
| checkpoint | 2.13 - Conformity with Drawings
7e130d9c-a787-594d-8e84-43df3c535a4c | note | Ref docs - DTP 308.03 (a) – (e) Table 308.031, Table 308.032
ff35d148-b218-5138-8468-494f5c90254e | note | Acceptance criteria - Checking of layer thickness, alignment, and width to be undertaken by surveyor prior to final compaction. This check is to be confirmed by Surveyor and Symal Engineering and Supervision team.
7cc4f5f0-a277-5c9b-8091-0975da6871bd | note | Freq - Prior to final compaction
a3730587-73f0-5ece-a32b-8d735cdbcce0 | note | Key - W
e570b60e-9bc0-5ba1-9ccf-eae02f47103d | note | Resp - SE, LH
ca709f5d-cd45-5d4d-a2aa-6ded5d313c58 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
3c985094-d3f3-5393-870d-0c2a478d8ea8 | tickbox | Survey Report
| checkpoint | 2.14 - Final Trimming and Compaction
4430943b-6599-573c-84b5-82f2004eeb27 | note | Ref docs - DTP 308.08 (i) and (h) 308.03
72d33be0-85df-5cff-bea0-621b7635e7c2 | note | Acceptance criteria - Final compaction to commence as soon as possible after mixing and within the allowable working time.
c68496fb-2ac3-5654-9197-b295df3057b4 | note | ○ Surface shall be free of loose pockets, holes, and bumps. Compaction and trimming shall be carried out in a continuous operation until completed. Finished surface shall be left smooth.
9342288c-1f87-5387-87d6-c09db09b9ca0 | note | Freq - Each lot
26d4a6c0-55b3-506e-8201-9380591b012d | note | Key - PE/SE
72030e25-9ade-56d6-9c71-fd30f8ba8e04 | note | Resp - W
| checkpoint | 2.15 - Proof Roll
a158cae0-bc69-501a-8a3a-0763008af30a | note | Ref docs - DTP 308.10
71c0d885-80d2-5bc3-80a7-b1b40dcd1c33 | note | Acceptance criteria - Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer.
1cedc222-3031-57f5-96c9-6d140339a4a4 | note | ○ Any unstable areas detected by test rolling shall be rectified.
4f44c704-0d55-51e4-aac2-5da532abd409 | note | ○ Proof roll checklist to be attached to lot.
02d10f8a-ef99-51d3-a80a-766b47ac300f | note | Freq - Each lot
ab612f28-b8cc-59c4-b8d6-8480d082124c | note | Key - SE
a3badd86-65af-5ebe-91f0-959c0c86f4b6 | note | Resp - H
8c3ea6ea-80b9-558d-b5f9-a6f1c0ed1876 | note | SI Key - H
2ab90515-bcbd-5dba-953e-de01b33452a0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
dc4c4ee8-76c8-5998-9aec-f7848bc8f578 | tickbox | Proof roll Checklist
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Testing Required
| checkpoint | 3.1 - Compaction Testing and Relative Moisture Ratio (RMR)
d0f6dd40-beb3-57e7-8236-e3af3471232f | note | Ref docs - 754- MELGE3056 62BV_rev3, DTP 308.13 (b)
27b45ea3-795b-52b6-a88a-3b9e02cdf95d | note | Acceptance criteria - Compaction testing
c82fd5f2-c079-5c35-89d0-ae3c2b26b168 | note | ○ Requirement: Scale A, Modified Compactive effort. Characteristic Density Ratio: 98.0%
fc8e6052-befb-5649-9a1f-676058787786 | note | ○ RMR (post compaction): Between 55% and 75% of OMC
f6a8cb12-e7c1-5da3-9747-8ed4d274e95e | note | ○ No. of tests required: 6 tests per lot.
312ecddb-af76-5def-985b-de1cdac7c4a5 | note | ○ Maximum Lot Size: 4,000m2
35c86f4d-0f4d-5293-bf68-229bd4b0870e | note | Determination of reference density
11c508e8-c254-57d6-8346-0299c5c6a2de | note | ○ Sample to be taken from field to lab within 3 hours due to decay factor, to verify assigned values of material.
497c9c20-b92a-5247-b402-60481e4a600d | note | ○ Density ratio to be determined in accordance with VR Section 176.
81427e91-28dd-54bc-87e6-f657f1e29fe8 | note | Determination of Relative moisture Ratio
98f1be43-0229-5d99-8a1f-def721b38f18 | note | ○ RMR (%) = In Situ Moisture Content / Material OMC
0bc5bf40-3044-5a1c-b945-cd347d8ceaf2 | button | Has compaction testing been completed? | Yes,No
a0f19327-3172-5863-9db8-832bc935576d | date | Date of testing:
6cdedd71-7a70-5330-b2a4-7eb7ea37473e | note | Freq - Each Lot
0d6f8a44-4d43-5936-88ac-df6982584bc7 | note | Key - SE
e8204cab-c0bf-5b14-8866-7811638b1351 | note | Resp - R
54b64419-a629-5acd-aa1c-6fce855a61df | note | SI Key - H
f1f534f5-cc9f-5ea9-a594-a4c793449c57 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
5faf8638-38e1-5d84-af9d-484fde704804 | tickbox | Compaction Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Ride Quality Testing
ad851104-7821-54e8-b0f6-e3c8662142e3 | note | Ref docs - DTP Section 180, DTP 308 754- MELGE3056 62BV_rev3 4.3
ed724195-7960-5b02-9bba-1ac40e96acde | note | Acceptance criteria - Ride Quality Testing Requirement: Scale A
891f0e99-450b-5db3-a7a7-a10fa24f3d1f | note | ○ Lot Size: Freeway Ramp
d09bf72b-baf8-5b0e-a34e-5a1e20bce70c | note | ○ Shoulders and turn lanes excluded from testing.
2abf309d-1dca-53bf-bd98-9965debed7c9 | note | ○ The Contractor shall provide 24 hours notice to the Superintendent of when ride quality testing will be undertaken and the limits for each lot.
9d4f314d-d774-55e7-841d-0bd9f136b686 | note | ○ The maximum individual lane roughness for any 100m segment of road and mean lane roughness shall be as per Table 1 in the appendix.
ca8efdcc-8196-5e98-b1a3-66b1a037138a | note | ○ The resulting roughness, after removal of areas of exclusions, shall be processed and reported for each 100 m sub-section.
1aab4d58-f5d8-519c-85d2-fc5623eb101f | note | Freq - Each Lot
19eac779-6c4a-5411-8e98-5e29bf079d91 | note | Key - SE
c3eaa3dc-1f2f-5bff-89f2-6d0d33cc9063 | note | Resp - R
322564de-bfa6-53af-9523-a287b9bfa0d9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
3bdf917f-50df-55e8-9edb-d80504845627 | tickbox | Ride Quality Test Reports
| checkpoint | 3.3 - Ride Quality Testing – Re-testing after rework
6a47803a-7da0-56e4-8d37-5b9aa0d71796 | note | Ref docs - 754- MELGE3056 62BV_rev3 4.3
fb12c6e1-d269-5758-8a2a-269633e09a86 | note | Acceptance criteria -
0fa9c241-f8fb-5a04-9811-74930fb5d21d | button | Is rework required on any sublots tested for Ride Quality Testing? | Yes,No
2ce68e0d-448d-5374-8961-d32a3d60d661 | note | If no, section is N/A.
401f4005-0ebf-57df-bfd9-5e3503984de4 | note | If yes, proceed as per below.
cfec8284-66f9-5d7b-8f1e-d4cd7620ba2d | note | ○ Symal shall re-test the lot following completion of any rectification work and shall re-submit Individual Lane Roughness and Mean Lane Roughness for the lot.
a4146736-3f71-5392-889e-42069297f29b | note | ○ Symal shall comply with the requirements for both the Maximum Individual Lane Roughness and Maximum Mean Lane Roughness for the lot after rectification works have been completed.
2a9b062c-6185-5d9d-bdf5-957b02577491 | note | Freq - Each Lot
7506fb41-1a55-54dc-8045-22d01a3c1ef5 | note | Key - SE
dde36938-de6c-5130-95e8-e260e23eba79 | note | Resp - R
73cbdeaa-d4e0-5245-bc37-90632f1ad6b2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
f9e03356-3b0d-5b45-a158-9578ec6f6d06 | tickbox | Ride Quality Test Reports (if applicable)
| checkpoint | 3.4 - Resilient Modulus Testing
960ab35f-d93a-5eb9-a1ea-ddb8a336f9da | note | Ref docs - 754- MELGE3056 62BV_rev3, DTP Table 308.05 (a), 308.15
5163751e-9e23-53d9-97e6-c246074b0a47 | note | Acceptance criteria - Resilient Modulus testing of core samples is to be taken at the completion of the works each day.
525246ba-d944-5e14-a296-1144e74c3de8 | note | ○ Laboratory testing to show that design modulus has been achieved in the field.
d3a9779d-0752-53f5-8498-1828814b28e2 | note | ○ Retained Modulus > 0.5 (ratio wet modulus to dry modulus)
818e5ca1-2e5b-524e-a99d-9d766d1d5d14 | note | ○ Core samples shall be collected at a minimum of 6 locations per lot for resilient modulus testing and in- situ density testing at each of the three testing stages.
37e49468-647d-5522-b49e-26de4f98ab38 | note | ○ To confirm the stabilised layer has is uniform and consistent, core samples are to be measured in 2 halves: 1 test on the top half and 1 test on the bottom half.
f3a374c8-4831-5d75-adce-db024d8cd991 | button | Has the above testing procedure been completed? | Yes,No
8d184a92-b429-55a5-b432-84fbc51f17e7 | note | Freq - Each Lot
939230ef-96ac-5e8d-8e66-f8be4b8f7bfe | note | Key - SE
f27569e9-792e-5ea6-b768-2be554e97b05 | note | Resp - R
f77950cc-d52b-5177-a50e-3693bce99a4d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
ba085521-7198-5583-b65b-d84679cd7e96 | tickbox | Resilient Modulus Test Reports
| checkpoint | 3.5 - Dryback Test
43ffe4ae-bee6-5cb5-9232-4ed045b3ffc3 | note | Ref docs - DTP Section 310 Table 310.031, 754- MELGE3056 62BV_rev3 4.4.2.1
f91e8d98-5461-501c-9d34-2b1dc922f994 | note | Acceptance criteria - The uppermost pavement layer after preparation of the surface and prior to priming or primer sealing shall be allowed to dry back so the moisture content of the layer shall achieve the following moisture requirements in accordance with Table 310.031 of DTP Section 310 (see appendix):
d9c79a79-cc66-5ea8-bde8-e24ec1b2b470 | note | ○ Requirement: Scale A
e20a5dd8-06bc-583e-b465-a5978e662867 | note | ○ Mean Moisture Ratio: Less than 60%
cbcace47-c464-54e2-a823-28a244cda824 | note | ○ Max of any Individual result: 70%
6c25d5a6-364c-5340-8839-cb6b687a0631 | note | ○ The mean Moisture Ratio shall be determined from six randomly selected sites.
32bae8e1-dbc4-5c48-88d6-a9cb388e6a24 | button | Has the above testing procedure been completed? | Yes,No
b6c43939-1108-55c9-b198-9559c62f9f46 | note | Freq - Each Lot
038bd7ac-a306-5380-8a93-3c377d9b8271 | note | Key - SE
24edbf43-a07d-560a-8ac5-a161e48b269c | note | Resp - R
85a0c756-15dd-5b54-acde-6d99fbfe821c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
93e8a3eb-5e9d-5861-9ff5-5abc91eca70e | tickbox | Dryback Test Reports
| checkpoint | 3.6 - Ball Penetration Test
f3dedc7b-45a8-5914-b665-5f679b605f65 | note | Ref docs - DTP Section 310, 754- MELGE3056 62BV_rev3 4.4.2.2
cb30cc3e-3a50-5cf8-ae0a-dd339c26ffb3 | note | Acceptance criteria - Pavement embedment shall be assessed by Ball Penetration testing when required as detailed in Table 310.031.
6037a910-2331-5b75-9a4e-609a916e5136 | note | ○ Ball Penetration testing shall be undertaken on the prepared surface in accordance with Austroads test method AG:PT/T251 - Ball Penetration Test at six randomly selected sites.
80f2ccf4-f5c4-5d3c-8a85-565d26ddceba | note | ○ No individual test result shall exceed the maximum penetration detailed in Table 310.031.
c1e27423-ee10-5475-b17a-fc66af2e3a84 | note | ○ Requirement: Scale A
96007589-f62d-5002-9179-75ae58524323 | note | ○ Ball Penetration Max Individual Result: 3mm
4ea5a4f4-ecf5-56ed-897d-14de091f6985 | button | Has the above testing procedure been completed? | Yes,No
71746857-fca0-5e92-8581-9b0c71672779 | note | Freq - Each Lot
ad0f6bf5-84cf-5086-aaed-c4a2e932d958 | note | Key - SE
ff1ada68-8abc-57c4-a474-1fb72cafd16b | note | Resp - R
ad45e5e4-bcde-5e6a-94d5-470ce8f9797e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
8d442bf9-6cfd-5d06-9da4-d88259114d88 | tickbox | Ball Penetration Test Reports
| checkpoint | 3.7 - Falling Weight Deflectometer Testing
cf958b6f-4fa0-5568-82c1-f3555892fc0c | note | Ref docs - Austroads Test Method AG: AM/T006
3290855b-99ae-5edf-aa56-8fcd60145bba | note | Acceptance criteria - Falling Weight Deflectometer (FWD) testing should be undertaken in accordance with relevant Australian State Road Authority Standard or Austroads Test Method AG:AM/T006.
a4c72001-6ee3-5293-ac25-af1dec638660 | note | ○ The FWD testing shall be taken at nominal drop stress of 566kPa (40kN nominal drop load) at the following locations:
1ad914ac-10aa-5d8b-80a1-7794c1191237 | note | – All lanes and shoulders on the Ramp; and
69f599a4-bee7-59ef-8bd1-2d4ba06ef672 | note | – At 10m intervals along both wheel paths.
8a89ebd7-6b05-508e-ac31-a0d0f7f742e7 | note | ○ FWD deflections are to be measured with minimum 7 deflection sensors at 0mm, 200mm, 300mm, 400mm, 600mm, 900mm and 1500mm distance from the centre of the applied load.
6cc25904-ad57-5783-8ba9-cdcf14e72ce7 | button | Has the above testing procedure been completed? | Yes,No
024d4511-c4f7-5e49-8d48-59ce23d3ff25 | note | ○ FWD Testing to be reviewed through benchmarking of deflection data and back calculation of layer moduli to assess layer strength. This is to be conducted by pavement designer (Tetra Tech) and MRPV to assess.
47dd6353-7481-5364-977d-e3653b8b50ee | note | Freq - Each Lot
2cd5b51d-884f-5e9d-8e9f-285e91ecc92f | note | Key - SE
8cab42b3-da77-59a2-acef-145c50a7be32 | note | Resp - R
54c0409c-a41e-5178-abd7-fee92bdea90d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
5c79af81-dfeb-57bd-8eb9-414dc77e677b | tickbox | Falling Weight Deflectometer Test Reports
| section | 4.0 Conformance and Approval
| checkpoint | 4.1 - As Built
7fcb84e8-44d1-5395-a9d1-3034282eb77e | note | Ref docs - DTP Section 308.03 Conformity with Drawings Table 308.031, Table 308.032
1de07468-c193-561e-b37e-ad37079459b2 | note | Acceptance criteria - Pavement Tolerances:
1d180011-7848-5cab-912a-1b6f2d487505 | note | – Finished Surface Level –
4442bc4d-2091-5db9-ab80-a9993773a92a | note | ○ For Base layer:
da42d527-46ee-5cd2-ae0d-195ecb78126f | note | ○ Scale A
1d6fd0c0-467a-53fe-abc1-e01b165c57f4 | note | ○ -5mm / +10mm
151cb2c1-baf0-5cc6-ab98-1e41d82c5cfe | note | ○ Table 308.031 (See Appendix)
0066323e-569c-59a2-993b-8c628aad6cda | note | – Thickness –
66834eae-6ac4-56d7-b1d8-2477dc02bf92 | note | ○ Not less than 0mm pavement makeup
ff2c13dc-929b-55cf-abf6-37c6e27f24ad | note | ○ Not more than 15mm over pavement makeup
dfc472ce-a7d5-5ed7-8a92-7eaaa0fc14aa | note | – Alignment –
afc58a0d-5e87-5087-852c-74664b4bf894 | note | ○ 50mm +/- from design line
a9d093bf-04d4-581c-ac70-776325db560c | note | – Width –
266ef81e-96fc-5769-a0bf-90b4f921986a | note | ○ Not less than a max of 50mm
70bcfd85-6b06-59fb-bf39-be8aaa5c35bf | note | ○ Not greater than a max of 100mm
6d4c9050-4b0a-51f9-ab6d-5a1e9587e99f | note | – Shape –
f4219bec-9a8b-5f27-8ac5-b378c8968ae4 | note | ○ For Base layer:
fa2cae1c-4aef-5cd7-9984-4e4642a4a67d | note | ○ Scale A
2b635823-1df8-5acb-b348-f47b95e2d187 | note | ○ Max. +/- 5mm deviation from 3m straight edge placed in any direction along surface
d1fdb0a9-cf22-5d75-8ee4-2b6f07d1bb2f | note | ○ Table 308.032 (See Appendix)
6d1cf459-25cb-5b8d-8c5c-e05e711f0cab | note | Freq - Each Lot
40d62144-1328-53be-a394-88bdd70980cc | note | Key - H
ad266ce3-6251-569e-8a6c-a07337f885df | note | Resp - SE
81c6f1ae-ebf3-58bc-a426-e4ca14aa8af4 | note | SI Key - H
888d176a-2bdb-506f-9006-f57bb351e5e3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
0d48af7f-3c66-5b71-9870-8b70936b9892 | tickbox | Conformance Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Test Reports
3f3db551-9fe1-5b4b-bec3-99d4693dcd8e | note | Acceptance criteria - All test reports conforming and attached to lot
5aa7d1cb-9734-53d4-b02a-8b60ca2968af | note | Freq - Each Lot
24396786-8627-56fe-b369-59eff4f55d42 | note | Key - H
20417c74-44fb-529a-bf5b-4a23943c2b6b | note | Resp - SE
30d7fade-3cd5-52ef-849c-bc18cac50149 | note | SI Key - H
892e1e1f-c33a-5ca4-8e3b-134b40687756 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
2dc2273b-aa65-5bbd-831e-347d042219c2 | tickbox | Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - NCR
e6801cf9-0d02-5d6c-bde4-c1b3422b3872 | note | Ref docs - QMP
027dbcda-6dd7-5596-b79a-ff3a35979826 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed out (if applicable)
08679ba9-929d-5378-b650-8443e4ed2bd5 | note | Freq - Each Lot
5528e6e9-6e3f-5899-bffd-9358b72eab27 | note | Key - R
db5c39db-547c-5815-95a4-4c10254ad052 | note | Resp - SE
72fbd648-823c-5f2f-b39b-f105566e9157 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
39d9974c-db7d-5622-b1d4-05f46e28df67 | tickbox | NCR Attached
| checklist | 1630-P200-SYM-QAC-ITP-0025 Driven Piling | itp | 1630-P200-SYM-QAC-ITP-0025 Driven Piling |  |  | 706fdeca-8299-46f8-b652-6d6496bae618
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Driving System
763c0f24-f36c-538d-b61a-b80bd073e398 | note | Ref docs - VR 605.03
9dd4da99-1285-5351-ba2a-5635ad45a65b | note | Acceptance criteria - Details of the driving system have been provided to the Superintendent including the make, model and rated energy of the hammer, the mass of the helmet, and the proposed cap block and cushion materials. The driving system ensures that the hammer has a height of fall less than 2m.
7040a1f5-e39e-5856-9dab-c7f8445a9c7f | note | ○ The methodology used in determining the pile capacity below the ultimate retention height of the test pile has been provided to the Superintendent for review prior to commencement of pile driving.
944222d4-ac42-5ae6-bcda-e2e0a59b5cd3 | note | ○ These details, including calculations which demonstrate that the proposed driving system has sufficient energy to achieve the specified pile test load, have been submitted to the Superintendent for review not less than 14 days prior to the commencement of pile driving.
bac354c2-d48c-511b-9eaf-c041445326d5 | note | ○ All pile corners are have 25x25mm chamfers except chamfers on the top longitudinal corners.
60ab7240-1bd9-5474-953a-87097a0251d2 | note | Freq - Prior to start of works
d6bb8ec3-58ce-5113-9a7f-47897991a3ef | note | Key - H
3888110c-6c98-5d0c-9d4a-9a053ac4bbac | note | Resp - SE
817caacc-fa6d-554c-8034-519ca2dbd58f | note | SI Key - R
dda028b5-514d-55d2-98b0-3cf2785a49db | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
1a11f781-c5aa-58f9-b317-368c06f26cd1 | button | Lot map | Yes,No,N/A
8220e517-cca2-562f-97e2-df5d0e360564 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
09f6706e-4eed-51d2-b20f-05d7e8fa84ed | button | Environmental permit | Yes,No,N/A
7bbe170a-d0dd-5ae4-854a-666dd013e587 | date | Inspection Date:
| checkpoint | 1.2 - Concrete Pile approval
f5f4e39f-5855-567f-bdf0-c6f73fb3f1ae | note | Ref docs - VR 605.08 AS 5100.3 (6.4.2.1) VR620.03 VR 605.09, Table 1 BTN 023
512033a1-d389-59b9-9e82-cd860f3f3c22 | note | Acceptance criteria - The date of casting is clearly marked on each pile along with 500mm intervals starting from the pile toe clearly marked.
2caaa049-b27f-542a-8254-5493e7e405c6 | note | Precast square piles chamfers comply with requirements of clause 6.4.2.1 of AS 5100.3. Chamfers are only required on 2 out of the 4 corners.
3ee18d38-9d4e-543b-8e73-7a8db89cea66 | note | – The cross-sectional area is not less than 90,000 mm2
c43ec065-36c4-51f5-80b5-75564fafe16e | note | – The head of the reinforced concrete pile is reinforced with a minimum of 6 mm thick and 75 mm wide steel strap
bc11f925-3204-5e2c-ad32-252af8bee4a6 | note | – Longitudinal reinforcement consists of not less than four bars and spaced uniformly around the perimeter of the pile are provided for the full length of the pile.
757de847-9373-5494-a4d2-9c4c9240a5fa | note | The full length of longitudinal reinforcement is enclosed with stirrups or helical reinforcement of not less than 5 mm diameter, and the volume of the stirrups or the helical reinforcement is not less than 0.2% of the gross volume of the pile.
4eb52d10-cbb8-5ffa-8eee-df2116c9d807 | note | – Mechanical joints (if applicable) are only used with the approval of the relevant authority, are not less than 3 m and not more than 20 m long.
a8c8a65c-6e00-5edc-89f6-c50b5ed363d0 | note | – Driving shoes are either iron casting or made up from welded steel plate with no less than 10 mm thickness. Welding is GP in accordance with AS 1554.1. for hard driving, the driving shoe may incorporate a rock point.
a30a3380-c91c-533c-b50a-4b1899f72615 | note | Piles are free from damage, cracks or distortion. shall be inspected by the Contractor in conjunction with the Superintendent.
bfd305f6-fa56-525e-91bf-f90df0751abc | note | Where required, a rectification proposal of any defects has been submitted and agreed by the Superintendent and rectification works have been completed to this proposal.
a45dc7ea-284a-5946-a091-87e900345c13 | note | All piles are confirmed to have the below minimum age before driving:
0382232f-e4a3-5456-96eb-066fab6cbd36 | note | ○ Steam cured = 7 days after the date of casting
75a2b0d6-7c80-5dde-885b-d729ff8e3694 | note | ○ Moist cured = 14 days after the date of casting
36efaf44-9f82-5998-8837-f762170abf9f | note | Precast [piles must achieve the below strength prior to lifting them up at the precast yard
00f2b625-74ea-5869-be3d-772d3e8460f6 | note | i) 10 MPa for piles ≤ 5 tonnes
68620343-83ca-5857-8c15-be4ffb1c34c2 | note | ii) 20 MPa for piles > 5 tonnes
94e9dac3-2bab-59cf-a90c-63b2b78c9a6d | note | Concrete strength & cover of piles are not less than the value given in Table 1 of Bridge Technical Note BTN 023 for the relevant exposure classification.
78154368-1d22-53e4-ae7f-ed8f6f24a09e | note | Freq - Prior to start of works
381b1437-1d74-5189-a0d8-db5c79a411e4 | note | Key - H
e53c9009-bfad-5f2e-8140-585e94d7b7c5 | note | Resp - SE
f196d888-1fc8-5bd8-a77b-635a5794e80e | note | SI Key - R
6b406779-4ff3-5a49-ac3e-1f444a5ccd78 | date | Inspection Date:
| checkpoint | 1.3 - Pile Steel
c57a0895-fbb4-5534-a75a-50caa8961676 | note | Ref docs - VR605.09 BTN 023 (clause 4.3)
6f2aa573-48a1-5e9d-b684-631bd90b3620 | note | Acceptance criteria - Equivalent reinforcement is approved by MRPV (When anchor bars on mechanical joints interfere with longitudinal reinforcement).
d97badf8-f2e7-5c58-b155-67fea14c6da1 | note | ○ Pile driving rings or head bands are fabricated using full penetration butt welds and backing plates.
c4901908-5b09-58f4-94ab-677fed32bd1e | note | ○ Pile protection fittings are made ‘integral with the pile’ by using anchor bars welded to these fittings.
b8c4c61f-7f16-545b-b958-bf9c8adb407b | note | Freq - Prior to start of works
c60a5049-8dd8-5991-a4f8-fcb920efb070 | note | Key - H
df726d30-b4f9-595b-9d93-8e6394e2888b | note | Resp - SE
af081b8c-e969-5c36-b66b-98c3d7dada60 | note | SI Key - R
1f1aa00e-b470-5600-bcc3-d31fed3c400c | date | Inspection Date:
| checkpoint | 1.4 - Prequalified testing consultant
1436959f-cfbb-59a9-9334-c64be7e22392 | note | Ref docs - VR 605.07(b)
c18e082e-67d7-5b86-ba2b-731f460dad54 | note | Acceptance criteria - The consultant undertaking high strain dynamic testing is independent of the piling contractor and advised to the Superintendent at least 2 weeks prior to testing. The Tester needs to be DTP prequalified.
6b962954-a65f-5e1f-bc54-7ebcdcfa64b0 | note | Freq - Prior to start of works
2b71cbc3-24af-5bae-9ec4-42fc7c1a60b7 | note | Key - H
f256c09c-3ed1-52c9-af6c-64482ceceba7 | note | Resp - SE
bac1d8ca-dc2c-5218-9334-809a07cfa95d | note | SI Key - R
a07917d2-505b-5dbe-868d-af04fd84b954 | date | Inspection Date:
| checkpoint | 1.5 - Temporary Works of Piling Pad Design
f55b02a7-7a51-5907-8ea6-9549d3747c29 | note | Ref docs - General Specification 1170.04
6143664f-c158-5b0b-b32b-ce51371bb393 | note | Acceptance criteria - The manufacture, fabrication, erection or construction of any part of the Works of Temporary Works must not commence until the relevant Construction Documents, including the IFC Documents, have been finalised in accordance with the requirements of General Specification 1190.03.
72a05ead-5d43-569f-b343-d1c9212c7982 | note | Freq - Prior to start of works
c0a4da89-9949-5f80-8f58-d4b701fd25f8 | note | Key - H
2826457d-a3c8-54b5-b23b-12ccb7211a77 | note | Resp - SE
0027f98b-f097-5461-849c-05443f6b91ab | note | SI Key - R
1bc2a33c-447c-55d5-98cc-c826aec6dee2 | date | Inspection Date:
| section | 2.0 Installation of Driven Piles
| checkpoint | 2.1 - Survey set out and drilling setup
bdd0f2aa-4c97-5cc2-a116-42c67b7571c8 | note | Ref docs - 1630-P200-SYM-SBR-DRG-0102
22d5310d-5a58-53c5-b38b-505e325d8bb3 | note | Acceptance criteria - The Surveyor has set out the centre of pile prior to installation. There is a minimum of 2 survey offset marks to maintain the centre of the pile.
3687e20d-6715-59d6-9064-092a34799511 | note | Freq - Each pile
083fdf65-9190-5a0f-8be4-4867e31361c6 | note | Key - I
c4e3bf65-314f-59a6-ac29-e1fa55b886b6 | note | Resp - SE
fa7ede16-1704-50b7-8693-8cc34e1dd04d | date | Inspection Date:
| checkpoint | 2.2 - Isolation Sleeves
34329557-65ae-5300-a281-b01358c679ba | note | Ref docs - AMS Activity 6.3
8551d4df-6213-5ecd-a380-09cf50c6310f | note | Acceptance criteria - The pile location is bored to the correct depth and a steel sleeve is inserted into the hole to provide isolation for the pre-cast driven pile.
c6118da1-3b3d-5853-9973-6b47cd3b2990 | note | ○ The voids between the embankment fill material and the outside wall of the sleeves (if any) are grouted using sand grout.
5d8798e9-9022-5523-9221-658c84e84e66 | note | Freq - Each Lot
0aa67ee6-645b-57a3-982f-d9637cea773b | note | Key - R
22c6c9b5-1916-523f-82de-c0fdbca932aa | note | Resp - SE
85135116-0ebb-537b-93ed-b83982f1155c | date | Inspection Date:
| checkpoint | 2.3 - Pile driving records
0ab693fd-5709-5d05-9ee7-401707db0679 | note | Ref docs - VR 605.06
49359d7f-5ab1-56ee-9368-696343b04a25 | note | Acceptance criteria - The following records have been retained for each pile being driven:
b46f5c27-bc43-57cf-b7e8-2a848a49aaf8 | note | (a) manufacturing lot number and date of casting
80785237-21a3-56f8-a82f-c5d3333a6004 | note | (b) location in pile group
2a1176a7-b5e4-51db-96cb-f72824fae68d | note | (c) length prior to driving
a40ad991-536e-5534-a822-5db0bc6da3c8 | note | (d) date of driving
4c985e5b-c8fe-5229-a8df-b794c181ac80 | note | (e) toe level
310658b5-1cc2-53a5-be4c-060104bb7e20 | note | (f) traces of set measurements showing set and temporary compression
8c49aa90-c966-5d74-b85d-38b1cacfd2c7 | note | (g) calculated ultimate pile capacity
c2ee7f38-e440-5c09-9a02-91f540284f1b | note | (h) measured stresses in the pile.
ac45bcbd-65b7-5b72-b2f5-c72a31424414 | note | All records shall be provided to the Superintendent within 72 hours of each pile having been driven into position.
0d3b3a0d-1095-59ba-937f-096442ce05b7 | note | Freq - Each Lot
2f0e92bd-9caa-57a7-ac2a-322d6c573ef7 | note | Key - R
1ee0d219-48b6-5f41-8612-500cdd5e997b | note | Resp - SE
d4e92b57-0a5c-57a2-98ca-1960299ed5ed | note | SI Key - R
88e64ae5-0267-51af-b1e4-6611d3c8c6af | date | Inspection Date:
| checkpoint | 2.4 - Pile driving (1)
e930332a-68c2-596a-8a57-28d0f3fa4895 | note | Ref docs - AMS Activity 2.06
a8df5638-3754-5fab-bc1a-2eb500aee327 | note | Acceptance criteria - The starting position of the pile has been checked against offset marks. piling rig and pile segment shall be lined up parallel to each other prior to piling,
22d5bae7-8eba-5c9c-9ff0-23b8087c27b9 | note | Freq - Each Lot
beb2c2e3-d379-5117-bf55-b38cdb936879 | note | Key - I
d18820f3-b813-538a-b2d4-eaaf478fefba | note | Resp - SE
7b785a6b-3399-53f8-afee-f931b0dfe959 | date | Inspection Date:
| checkpoint | 2.4 - Pile driving (2)
a1e5760a-f04d-5ebd-a320-c74c72df76a8 | note | Ref docs - VR 605.04
88704e0c-2377-56aa-8927-91145617adc2 | note | Acceptance criteria - During driving, the tops of the piles are held and guided by a suitable helmet and protected by cushioning material to avoid damage to the pile.
e2bff5e5-0082-5e22-a349-88846710d8eb | note | ○ Each pile is driven in a continuous operation, if pile needs to be extended, splicing shall be done immediately once section has been completed so driving can re-comment as soon as splice is completed.
a094403b-5cf7-5dba-8c82-c7a6b76ad64b | note | ○ Pile is driven to the design level
0cfb399f-4d3e-5046-8819-a43a8795018a | note | ○ Forced up piles are re-driven to the design level
3c0d938f-0a45-5aee-a747-e9b1c59ee6e7 | note | Freq - Each Lot
7fe2d264-03d0-55f8-9c7e-12c800b4b042 | note | Key - I
3a900581-2b54-51dc-a9f8-f1162cd59b2e | note | Resp - SE
53fc006b-7d20-5c35-b411-753ba83d6ae4 | note | SI Key - I
4464bd3a-54c7-55dd-ac7f-4075e1ecf64c | date | Inspection Date:
| checkpoint | 2.4 - Pile driving (3)
882a5ab5-33d5-5caf-ba8c-fe5d7e444530 | note | Ref docs - AMS Activity 2.06
6f9d5d6a-354d-5ba9-bab8-cf175a75ca75 | note | Acceptance criteria - Once the pile has been driven to a level that will allow for a visual inspection, pile driving is to cease so that the piles can be inspected.
bfafed45-d958-5ccc-bdda-cd4e69b70454 | note | Freq - Each Lot
28a529f2-aa9b-55f3-a6ff-a5ee1066a3c1 | note | Key - I
75e9a2a3-64ea-5248-bf03-8e200f996896 | note | Resp - SE
67de599c-a510-5a08-86ab-7d9fc00c389b | date | Inspection Date:
| checkpoint | 2.4 - Pile driving (4)
7ebe4711-ce81-561d-89a7-9d7b3eb28380 | note | Ref docs - VR 605.05
d7098d47-6087-57cf-8e84-74a1942a9bc1 | note | Acceptance criteria - Pile stress during driving did not exceed the below:
7ff8e90d-cdb2-57d9-b9e4-2db052ec4e72 | note | i) For concrete piles stress ≤ 0.8 fc for compression and 1.1√fc for tension
ba5c1b7c-401e-54c6-b2da-869e24bc6225 | note | ii) For steel piles stress ≤ 0.85Fy
dda6a7f0-235b-514f-b2a5-b8c65fd3c4d2 | note | iii) For exposure classification B2 or C, concrete pile stress≤ 0.5√fc
f736456a-abe3-555f-9d6c-e87683a6c53c | note | Freq - Each Lot
fdca6fc8-1f6d-53c6-b7d7-070d5313b2ad | note | Key - R
13d7473a-9e1b-52cd-8e7e-9e2448b7752d | note | Resp - SE
a11e82ac-4238-5790-b74c-3dedae2711d4 | date | Inspection Date:
| checkpoint | 2.5 - Pile tolerances
09d457a7-76ae-5a12-9dd5-2e40422bbf6c | note | Ref docs - VR 605.04
c77cbb64-3fe4-553c-bcde-52eeaf6670a9 | note | Acceptance criteria - The Contractor shall ensure that piles achieve the specified accuracy of level and position. The following tolerances shall apply to piles after driving:
944261c5-f5ba-5c06-be78-6dda385f927f | note | (a) pile alignment
07948336-217c-5429-9b93-d5df4441bd56 | note | ○ deviation from the vertical or the specified rake shall not exceed 20 mm per metre length of pile
b9155e35-93e2-52ad-8a1a-c1e4e135f66a | note | (b) pile straightness
913a0430-e3e4-5d1b-bd93-0a6994d33123 | note | ○ deviation from vertical shall not exceed 5 mm per meter length of pile.
b0d22b87-c71e-554d-93d3-89ca61eb0d4a | note | (c) pile position for piles in pile caps and the underside of crossheads
3be32bab-3eea-52c1-92d4-67d6ed787235 | note | ○ pile head center, ± 50 mm of the specified position.
e59df1ea-e20d-5100-b895-2e914f3fb92e | note | Freq - Each Lot
68470d63-5e18-5740-bdee-8e47a762db71 | note | Key - R
013b8458-4d70-5f71-9713-fc34a2899838 | note | Resp - SE
940c33aa-0719-5570-b072-7ddf18825640 | date | Inspection Date:
| checkpoint | 2.6 - Extensions to piles
2b82950d-2a42-5953-9fd1-505bb47c71b7 | note | Ref docs - VR 605.10
28cf7b61-3c00-565e-ab66-dd9f2351241f | note | Acceptance criteria - Reinforced concrete piles are extended with either an additional length of precast reinforced concrete pile or with a cast in place reinforced concrete extension subject to the requirements of VR605.09.
f3675722-e516-549a-b3fc-3df97748887e | note | Freq - Each Lot
40f92aa7-a88e-5103-943f-11daf58afd07 | note | Key - R
1a66defb-365a-51d7-859f-c30412bdd5dd | note | Resp - SE
3eba372e-b605-5f97-8a0f-473b5151a589 | date | Inspection Date:
| section | 3.0 Pile Testing
| checkpoint | 3.1 - Pile Testing (1)
34b71c7c-fdca-5d67-9246-a76d9dd69ce0 | note | Ref docs - VR 605.03VR 605.07
15637309-ec30-5577-b85d-2e3e17aa5233 | note | Acceptance criteria - Pile testing has been carried out in the presence of the Superintendent.
e56466e2-74e1-5ca0-9d56-e30c19459e78 | note | ○ The first pile driven in each group is tested (which determined the driving set each pile group) and the ultimate capacity determined in accordance with the formula in clause 605.05(a).
12ff9cbf-4c51-5445-8f6e-76f9956d103d | note | Freq - Each Lot
821db45a-0bbe-553e-8f8b-596c12d63313 | note | Key - H
5c0d7d41-aecb-5852-a665-108a3dd466e5 | note | Resp - SE
75f3fd18-0e7e-5ab8-b821-8cbbc3a02ac8 | note | SI Key - H
1a64726f-607b-59d0-99a7-bd97fb332f6d | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Pile Testing (2)
e13f4520-ca38-5b93-b9d9-8b6f0b3972dc | note | Ref docs - VR 605.04
5e136e7b-22c2-5efe-8cbe-4ae99783994b | note | Acceptance criteria - Set measurements shall be taken to verify capacity of each pile driven, recorded as traces during driving to show the temporary compression of the pile and the permanent set. Traces must be taken relative to a stable hurdle supported securely by posts at least one pile diameter from each side of the pile.
e2c205e8-c7ee-5ea5-92ca-5ea4d71c91e9 | note | Freq - Each Lot
8bc4539c-fa00-501c-980c-465ee8c2ad79 | note | Key - H
8a00e5d1-9d7a-5b17-922f-946be69f5c56 | note | Resp - SE
730f3c3f-eed7-517d-b228-9ac949e12127 | date | Inspection Date:
| checkpoint | 3.1 - Pile Testing (3)
cb31d067-0102-5610-b827-561cdb4f4a48 | note | Ref docs - R 605.07, 605.05(a)
91af5ba2-0c48-5471-9f05-cab676bd217f | note | Acceptance criteria - The first pile in each group has been tested and the ultimate capacity determined in accordance with the formula in clause 605.05(a).
4cfa95f7-f042-54ae-a173-a8a9c670a6d2 | note | ○ The pile test has determined the driving set for each pile group by correlating the set with the driving system and the designer’s requirements for the pile test loads shown on the drawings. All piles within that group have not been driven to a set exceeding the driving set as determined by the pile test for that group.
53b93579-3311-55ef-98e6-53ea60e9d6c9 | note | ○ Nominated testing coefficient will be reviewed by MRPV
e151c368-e216-5a2c-8505-fb8721c9926d | note | Freq - Each Lot
b85f4666-a9af-51f0-be72-a4eede952f40 | note | Key - H
db391dce-311f-574d-b6f5-4e191d822a11 | note | Resp - SE
e3ef54ee-e9f1-5349-b2b5-923f31d0bd36 | note | SI Key - R
477c2231-e999-5b41-bd6d-db40cd48afc9 | date | Inspection Date:
| checkpoint | 3.1 - Pile Testing (4)
082cdbd7-c922-5f11-a8ec-6f7fb706b4d7 | note | Ref docs - VR 605.05(b)
08fc687b-9ecf-5d8a-a16a-7c29f9f3ee89 | note | Acceptance criteria - In addition to VR 605.05(a), pile capacity should be proven using dynamic analysis (PDA with CAPWAP) as per the drawings:
fa38522b-d009-5149-9d42-b8a5add93b6a | note | ○ 2 piles at each abutment
02072d29-e317-53f3-bf5b-480a3c727444 | note | ○ 3 piles at the pier
58f353b8-c646-5fa9-b922-7e9621945872 | note | All high strain dynamic testing has been undertaken by a prequalified consultant and approved by the Superintendent.
6c6e36b9-438c-559e-8c32-7f4b0f6dc86f | note | The pile test has determined the driving set for each pile group by correlating the driving system and design pile capacity. All piles within that group have been driven to a set not exceeding the driving set as determined by the PDA test.
d539e6c3-c361-59c9-be4a-2f9b65e3528b | note | An additional pile test has been conducted where the driving conditions are no longer represented by the initial pile test for that pile group. Additional pile tests are required where:
15551674-6a2b-55b0-9c69-6f096bd2eeeb | note | ○ The design pile toe level of individual piles within a pile group is more than 2 metres, or
7a948d5c-4c3b-54bc-bef3-d1d21969df9a | note | ○ During pile driving pile toe levels vary by more than 2 metres from the test pile, or
d7cdbba4-442b-5b8f-9c94-4d30c83510d4 | note | ○ Pile rake differs by more than 8 degrees from the test pile.
c1471184-8b32-594c-aa3c-5db1257272c7 | note | ○ distance of any pile from the test pile did not exceed 20 metres.
05dcf976-0ecb-5ca2-be1f-03d404a3728f | note | Freq - Each Lot
602a6dcb-5791-51dc-a533-d37ac696bcf3 | note | Key - H
bfc4b75a-184d-50a6-9ac0-72c6010a9e8c | note | Resp - SE
471b03e1-4e13-5386-93f9-92ea9342da6d | date | Inspection Date:
| checkpoint | 3.3 - Restrike Test
48909222-5d60-5bec-a970-90a8e00ec073 | note | Ref docs - VR 605.08
7afd0fa6-033f-5994-a29e-6df01a7bfcd1 | note | Acceptance criteria - If the ultimate load capacity has not been achieved at the specified level or at refusal, restrike testing has not been conducted less than 24 hours after initial driving.
48151eb2-701b-5b9c-85a7-745df63eaae4 | note | ○ If directed by the Superintendent, the pile shall be driven until the specified ultimate load capacity is achieved.
84ca04cb-c7f3-59a8-8080-7ca333fb3c53 | note | ○ Driving resistance must be equal to or greater than the pile test load shown on the drawings.
10c9180c-3440-5661-8a9e-b1c30a268038 | note | Freq - Each Lot
bd3ed88a-1876-57cb-82bb-b720758854a9 | note | Key - R
05fbca8f-7dbb-5453-9953-7bd2a0800e76 | note | Resp - SE
959417d9-faba-51cf-b73a-2bae34799ee6 | date | Inspection Date:
| checkpoint | 3.4 - Defective Piles
2a258c78-27a0-5546-abf6-6d4bbbbdce53 | note | Ref docs - VR 605.13
1ca24708-d2c9-51f6-ac65-8f83e5ee8ba9 | note | Acceptance criteria - Where a pile exceeds the specified tolerances, is damaged or is otherwise defective, the strength, serviceability and durability of the pile shall be reappraised and where found to be unsatisfactory the pile shall be repaired, downgraded or replaced with one or more supplementary piles subject to the approval of the Superintendent.
89b0efd2-1297-5bd3-a4fc-3e2002a3e140 | note | Freq - Each Lot
ec782e56-5972-570a-8dc8-9006314ff6db | note | Key - R
71f037e7-5148-53bb-9f6e-d1572a406424 | note | Resp - SE
19a70481-695e-5487-a8ac-d29fc4582fd6 | date | Inspection Date:
| checkpoint | 3.5 - Joint location
af4d6de3-88f6-524f-afce-25fd6ae7d87d | note | Ref docs - Drawing no. 1630-P200-SYM-SBR-DRG-0105
2130d203-7f30-5772-a2f0-9aef756ab1de | note | Acceptance criteria - All mechanical joints are a minimum of 5m below natural surface level.
fe4ab1ce-6c6e-5e6c-810f-71e592b9960c | note | Freq - Each Lot
0025687f-7d75-55f7-b684-3ad2f7faf9d4 | note | Key - R
99979d16-4d06-5e5f-a813-7f6dd57cf93f | note | Resp - SE
2751218a-7712-5901-8fc7-3a1f5f7f6de9 | date | Inspection Date:
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Test Reports
cab64935-eee6-56ca-a730-d4b9810f6e57 | note | Acceptance criteria - All Test reports received and reviewed.
6a620c93-31f9-5477-a752-7eb26c3d49bd | note | Freq - Each lot
a124be49-47e7-5ed5-b557-13b488b5d944 | note | Key - R
fee0aa13-df1e-53c3-ab9b-03379a7f3292 | note | Resp - SE
6524a50e-f624-5e0a-aa2b-826ac1410b11 | date | Inspection Date:
| checkpoint | 4.2 - Product Non-Conformance
80222a5e-9cac-5c35-8ee0-86e8396158ba | note | Ref docs - CQMP
11d73fb2-53eb-5fc2-a13e-1591779b918e | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
df1ee264-bea8-5b8e-99e9-986cb683b29f | note | Freq - Each lot
e2be2432-07b7-5589-9d57-e539e1815abd | note | Key - R
aff42ac9-22d4-5da1-86c3-66de367d8176 | note | Resp - SE
a59d5633-8077-52a6-8c8c-fc0a16c35298 | textbox | Remarks/records - NCR No:
fa931800-e978-58ca-a607-0612cd41ad75 | button | NCR reports | Yes,No
d6915d4d-bd90-5d8b-b6b7-2c8cb7024f67 | date | Inspection Date:
| checkpoint | 4.3 - Quality Representative to check the above criteria and records to confirm
b8b7d8fb-9f49-547c-9724-75024dd1aea2 | note | Ref docs - CQMP Lot Records
4d1d171d-ba6e-5760-814a-b401a230f0f1 | note | Acceptance criteria - All above criteria met, and records identified attached.
393d8442-97d7-5967-8f69-9bd897b09bc5 | note | Freq - Each lot
c762b298-2b0e-5649-b99f-90e27d106721 | note | Key - R
b2c78048-3ff5-5ac6-9e62-beea97685919 | note | Resp - SE
d271a9df-bc2d-50f6-8bfc-ac1b6fb7359b | note | Remarks/records - Reports and other compliance records attached.
49271890-4f83-5c31-8010-8be3f8eaed1c | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0026 Bored Piling | itp | 1630-P200-SYM-QAC-ITP-0026 Bored Piling |  |  | 4920c700-883f-4f62-91a4-b194949556c6
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Preliminary Approval
1c4f985c-b6ab-5126-aa2b-af3892eb328b | note | Ref docs - VR606.03
b4ce3d8c-8380-5a39-b0e0-bdc99ffeee19 | note | Acceptance criteria - The Contractor shall submit for review by the Superintendent a quality procedure for the construction of the piles not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
b99507c0-d6ed-55b9-8d49-45ba26172ab7 | note | Freq - Prior to start of works
7aa2f610-923a-5540-9678-6cc13ede8464 | note | Key - H
1b8a0113-3a0c-548e-b065-8c3552f6c0b1 | note | Resp - SE
09c92efb-18d6-5357-a552-afe3cd86435c | note | SI Key - H
4acf20c6-3de6-5f0b-bdc9-7e510e47b161 | note | Remarks/record - ACRS certificate from Manufacturers, Suppliers and Processors of Steel Quality Procedure
c8d8a544-a2dd-543e-9877-ab2f9f1ae03a | note | ○ Quality Procedure and checklist
108fb0bb-ae6a-52e1-9ada-317021e76775 | note | ○ VicRoads pre- qualification certificate of pile testing consultant
a5c4aeb3-e2b2-5f2d-817e-ca1569466fd3 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
caaad263-7507-5b66-bbcf-c60615773df4 | button | Lot map | Yes,No,N/A
d290b3d8-159a-5e36-ac75-de7aac5e34d4 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
6e73988f-cf5d-5256-b998-56b8cb26fac2 | button | Environmental permit | Yes,No,N/A
61d80640-59c2-532a-b59d-1d0be7f52e99 | date | Inspection Date:
| checkpoint | 1.2 - Installation of Temporary Casing
ba0c318d-6d79-545d-88a5-0772b565f52b | note | Ref docs - VR606.03
fe19af0e-5e7e-571c-be89-163d95e80019 | note | Acceptance criteria -
9f284f1b-3412-51a2-a7ed-6fbc734155bb | button | Type and thickness of casing has been proof engineered by a Proof-Engineer who is prequalified in accordance with the VicRoads scheme for prequalification. | Yes,N/A
7bc74e10-9945-5480-8989-7dcada18d4fc | note | Freq - Prior to start of works
fd81e653-745a-5740-8f7b-5b33ae5c001f | note | Key - I
efdcc689-7a71-516a-9c6b-9b0b6730d5c3 | note | Resp - SE
483bc0f4-809d-5956-bfaa-50eec972e3ce | note | Remarks/record - Proof engineering certificate (or written advice)
ba4b73ff-ada9-5c7f-ae72-d7dcab8fc574 | date | Inspection Date:
| checkpoint | 1.3 - Concrete Mix Design
c2186916-c075-596a-ae1c-6f456d33319d | note | Ref docs - VR610.07, VR610.13, VR610.18
c52354ee-1b97-5567-ae6c-5e6ad5adf2aa | note | Acceptance criteria - Concrete mix design is a registered mix and approved by the Superintendent.
b7f16bc8-90e1-55e9-9b28-4e6852c1fdc9 | note | ○ Concrete placed under water is self-compacting concrete (SCC) & Concrete placed in the dry is either self-compacting concrete (SCC) or highly workable concrete in accordance with the requirements of clause 610.07, clause 610.13 and clause 610.18(c).
babe9d3e-e43d-5c56-9ca2-f00e50b7b198 | note | Freq - Prior to start of works
396fc65e-5f91-57ae-84fd-468b1b8234bf | note | Key - H
f76b4e90-0c4a-5381-bba1-9d755e5ab147 | note | Resp - SE
3df53faf-c5d1-58cf-9cc5-6b581e5d4a76 | note | SI Key - H
0f9639a4-3962-5f46-b6a9-3be2f5547741 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Reinforcement cages
45518c19-36fc-570c-a771-61b88a433ffe | note | Ref docs - IFC drawings
8823e86a-4aed-589b-96b5-1427a19c3095 | note | Acceptance criteria - Reinforcement details to be as per IFC drawings and shop drawings.
a3ef24eb-d55f-5a7c-868b-5be041cd2850 | note | Freq - Prior to start of works
ac20f855-be85-5bc3-ac1c-54c6ec47c7e2 | note | Key - R
7698c451-0ed4-5522-a510-eea94b606295 | note | Resp - SE
03a19063-b8ac-52ef-80a8-a099744981f4 | note | Remarks/record - Steel Schedule
2b6ec3ed-ca72-5a4b-9f28-f55388564508 | date | Inspection Date:
| checkpoint | 1.5 - Site Toolbox Talks
b687eaa8-8338-53aa-ad6c-6daf75aeb72b | note | Ref docs - VR610.18
cf9d63dd-d8fa-5010-a32d-3733a6daa5de | note | Acceptance criteria - The Contractor has submitted documented evidence of conducting tool box meetings of all concrete construction personnel on all aspects of the WMS, the ITPs, quality control checklist(s) and all specification requirements prior to the placement of concrete
93bf5d60-d0a6-5022-90f7-e6e01a1905d2 | note | Freq - Prior to start of works
61b97a32-0e70-576e-af48-12d725e21ca8 | note | Key - H
eedb8f10-85e8-511f-abe1-5dc514fa14dc | note | Resp - SE
f7aa796a-b9f8-5944-91b2-3d627cde1510 | note | SI Key - R
020a6e6a-5dbe-5f89-b04a-96064acbf990 | date | Inspection Date:
| section | 2.0 Installation of Bored Cast-In-Place Piles
| checkpoint | 2.1 - Survey set out and drilling setup
bc888702-a0b4-5f7b-a210-4f1ae44b8478 | note | Ref docs - IFC Drawings
a68799eb-2f8d-5d22-9e01-3ca64ce2218d | note | Acceptance criteria - Surveyor to set out centre of pile prior to excavation. Minimum of 2 survey offset marks to maintain the centre of the pile during excavation.
2ffd4793-dd00-5b9c-b212-eb09c13a84bb | note | Freq - Prior to drilling, Each pile
249663fc-c9bc-53b2-9d4f-32877893e6e7 | note | Key - I
626e9125-3afd-57dd-a296-79d69ceb08b2 | note | Resp - SE
86a52eb6-c038-514a-97d4-e3fd428eef91 | date | Inspection Date:
| checkpoint | 2.2 - Adjacent Piles – Check Adjacent Pile Strength
c7098946-72d7-5332-a9c3-e39a23c9611c | note | Ref docs - VR606.04
4ae28157-1b75-5ef8-a1db-00af8bb69be7 | note | Acceptance criteria - No pile construction to commence within 2.5 m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15 MPa.
e7994974-3fd9-5aeb-b296-ad8c36f1abd4 | button | Installation of piles resulting in significant vibration was not carried out within 2.5m to 9m until concrete strength has reached 15MPa. | Yes,No,N/A
3dff69dc-d98a-58b5-8a6e-7c731ed8d71f | note | Freq - Each Pile
930811a0-563d-5763-9fb8-3cbf55443908 | note | Key - W
c6a069f6-52f0-51a5-8f35-0b9f4a27e01c | note | Resp - SE
f66f3fa0-a378-5c01-ab87-4816f743a01c | date | Inspection Date:
| checkpoint | 2.3 - Pile Excavation
d8c3f9dc-2258-5810-a724-8d63f2218cb6 | note | Ref docs - VR606.03 VR606.05 IFC Drawings
8a2d2794-adb9-5379-b8b1-a3eb4c54336b | note | Acceptance criteria - Boring to correct size, position and level as shown on the drawings. Auger diameter to be no larger than 25mm of the specified pile diameter.
3b0b394b-530b-5040-a35b-c93abe755982 | note | ○ If the final level of bored pile is above natural ground level, the pile must be formed to the correct level by using temporary liner.
92922eac-1de6-5e36-8b5b-dae14d99bc61 | note | Freq - Each pile
b9d12493-5b27-5e44-8683-4d4f28bb210f | note | Key - I
60c60f1c-0cc2-5427-a044-7966650dae76 | note | Resp - SE
dfde81a9-30e2-5778-847a-6e64ed7a3681 | note | SI Key - H
4ea6ad9c-d19c-56b3-8076-181f40f971a1 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Installation of Temporary Casing
5279811f-026b-5b25-bf75-7285869b6897 | note | Ref docs - VR606.03 VR606.06
eb13f1e9-961f-5c60-a702-a2e00ced59f2 | note | Acceptance criteria - Temporary pile casings have used unless the Contractor can demonstrate to the satisfaction of the Superintendent that an alternative construction method without casings will meet the required tolerances, cover, and durability.
0e428917-1837-501d-8172-c11a59e75117 | note | ○ Type and thickness of casing has been proof engineered by a Proof-Engineer who is prequalified in accordance with the VicRoads scheme for prequalification.
e5c76916-ec0d-5b9f-b983-73c9c266eecd | note | ○ Unless otherwise approved by the Superintendent, temporary casings have been used to prevent the collapse of piles during excavation.
99b87bff-7446-5eaf-8473-8cf74759c295 | button | ○ Temporary casing toes have been driven into solid rock or suitable material as required to seal pile and prevent water and soil from entering from outside the casing. | Yes,N/A
c873e4ab-3f48-591f-b31d-b5e516098066 | note | Key - I
79d85fc8-e616-5b77-a7a8-6b393df3e6a4 | note | Resp - SE
bfb05158-27ff-559b-82da-66e9cde9137c | note | SI Key - R
7d2bd1ca-e594-54bf-b25f-0e855139c5f9 | date | Inspection Date:
| checkpoint | 2.5 - Inspection of Pile Excavation
0b04d162-d0af-55a5-9547-53f869fcfc9b | note | Ref docs - VR606.05
b3078971-dee5-52d1-948b-6302be0b959b | note | Acceptance criteria - Pile hole to be dewatered and cleaned as per the approved methodology prior to inspection by the Superintendent. The dewatered pile walls and base excavation should be inspected and confirmed satisfactory by the Superintendent.
c8dfa6d1-c3c2-5f50-a34b-72d9ba7c7d9a | note | ○ Any temporary casing installed was not removed, and reinforcement and concrete was not placed until such inspection above has taken place, and satisfaction of design assumptions by a geotechnical engineer has been received.
4a8f4bbb-6ea5-5043-90fa-49be027ecdd2 | note | ○ Contractor to Ensure pile toe level has been measured and recorded. Inspection of hole to select either approved dry hole or approved underwater concrete mix.
1a971b63-f32e-517b-82b3-e713f3ac1f5a | note | ○ Method of pile cleaning & inspection in the event the pile was unable to be dewatered has been reviewed by the Geotechnical Consultant and MRPV.
26865d87-6ae9-50ff-a1ca-7c818a4ca561 | note | Freq - Each Pile
2dcf58e3-abe0-563a-ac2f-568cdaaede85 | note | Key - H
a752e697-48fd-5162-8e88-4cfea291d2c8 | note | Resp - SE
7657dc90-b9bb-5010-9031-1a4a0a7b6e63 | note | SI Key - H
539c2a1b-7f91-5dac-b22a-eeaaf2e5200c | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Pile Verticality
ec23c852-a408-5b73-8074-a89c3369c460 | note | Ref docs - VR606.08
f18daf62-f1d4-50b7-b13c-a71c9755213c | note | Acceptance criteria - Once excavation operations are complete, visually inspect the excavation and confirm verticality using a plumb bob, spirit level against mast, piling rig data or other suitable method.
d5061391-8f42-52e6-9eda-a68ad2edfd9b | note | Tolerances as follows:
4b5aed8d-9510-5a51-920a-dd22560ace84 | note | – Variation from the vertical or the specified batter/rake is not more than 1 in 100
7da85f31-46c9-59fc-8a77-db6c814d669b | note | – Where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line does not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths.
22e1ce92-0b9d-5644-8d0c-615ab9bd9264 | note | Freq - Each pile
5cf2a02f-76ad-54b0-b66d-06749359614c | note | Key - I
d933088f-a18d-54f1-9bf9-f71383450a65 | note | Resp - SE
6e6c74a2-84f7-548d-844b-d1738bddcbd3 | date | Inspection Date:
| checkpoint | 2.7 - Pile Excavation Cleaning
fd71a7ef-fe61-51b7-b330-fdda28d261bb | note | Ref docs - VR606.06, 610.18
5a169b95-5e0a-5b9b-a10d-51a9b634035c | note | Acceptance criteria - Piles have been concreted within 24 hours of completion of Pile excavation.
9eaa4072-034d-5f0b-8a06-bf5214a580f3 | note | ○ For delays greater than 24 hours, ream the walls and the base of the pile to remove not less than 25 mm thickness of material, or any other foundation material which has softened in that time.
14d97b17-bbba-58c1-a704-3d9d2a673560 | note | ○ If water is present in the pile, water is to be cleaned out by means of NDD prior to pour.
67a50c1c-a4b8-5583-9adf-d69bcf2702be | note | ○ All foreign materials have been removed from the pile bore.
fb125530-ba4d-588e-aa2d-6359a0f7ebbc | note | Freq - Each Pile
471fd455-e949-59f6-98c4-bdd5bf0d2b61 | note | Key - H
59c24598-b926-54d9-a69b-058774b0390d | note | Resp - SE
939e4a45-72fb-529b-8e2b-31a6cdb7c53e | note | SI Key - H
2f988419-3afa-5e8b-93da-1149f040cf83 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Spacers and Bar Feet
45295de3-3c5e-5f66-88a5-0739c23d2ff4 | note | Ref docs - VR606.06
d20c454b-e243-5fcb-8ee8-4db686e2c3aa | note | Acceptance criteria - Spacers and supports for bored pile steel reinforcement to be placed at intervals of no more than 2 meters along the full length of the steel reinforcement cage.
b1ed10f8-c700-5b4d-bc27-fc2da4e4c0c6 | button | ○ Ensure that spacers are also placed across the diameter of the cage such that even cover is achieved across the diameter of the pile. 75mm spacers must be used to achieve deign cover. | Yes,No,N/A
290f3227-6087-58aa-b66a-eac74054fdca | note | Freq - Each pile
ad54dad6-e7c9-5352-831c-a44505b27262 | note | Key - H
32637826-ad11-59fd-bfad-9c573481b193 | note | Resp - SE
f15eb1eb-330f-5357-a33a-3778f25b916c | date | Inspection Date:
| checkpoint | 2.9 - Installation of Reinforcement Cage
113b89ca-19db-5bf1-a287-a1d3283e4e9e | note | Ref docs - VR606.06, 611.09, 611.10
d6e8ec1a-2e83-5ab4-a051-ca71af5abb2b | note | Acceptance criteria - Ensure cage is vertical and sufficient cover to Reinforcement as per design drawings.
ced8d7c2-8b2d-563c-ad91-106c7c8c5ae8 | note | ○ Ensure that the orientation of the cage is as per the design.
ac7188e8-35cd-537d-bc4d-a28f14d4b0a8 | note | ○ Steel reinforcement is not be fixed to temporary casing.
79e7fbc6-e4fe-5c8a-aab2-fee64f473834 | note | ○ Ensure that starter bar alignment is compatible with the reinforcement and hold down bolt details for the pile cap to avoid clashes with the pile cap reinforcement.
627a4a40-934b-5826-8267-5d9d76f15d38 | note | Freq - Each pile
84b40321-b491-5411-821b-e96beda5cffb | note | Key - R
cf8e07a3-2bc4-56d7-af44-39d98c1223e0 | note | Resp - SE
619d4792-dcab-5a2e-ab05-97bcdcbdc906 | date | Inspection Date:
| checkpoint | 2.10 - On-Site Tack Welding (if required)
b11b0a7a-0c0f-5796-b896-b4201f160ac1 | note | Ref docs - VR611.13(a, VR611.14(b)
a2eebfce-ca66-5b1a-9ce8-2b7e454b0605 | note | Acceptance criteria - Tack welding of steel reinforcement will be permitted for Grade 250N and Grade 500N carbon steel reinforcement bars provided welding is not within 50 mm of the tangent point of a bend in the steel.
f3232156-94ce-5dba-893d-5236fbb05646 | note | ○ Welders have appropriate training in accordance to AS 1554.3.
ee7f2b68-baa5-51a9-b0b2-9912f18e0bfc | button | ○ Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding procedure has been qualified and reviewed by the Superintendent. | Yes,No,N/A
73009ce2-92e9-59b3-aef2-c3732a280dfd | note | Freq - Each Pile
31c237f4-75c1-5199-8911-d32f92f245c2 | note | Key - H
065e95a8-9a75-513d-b919-d1768ebb7704 | note | Resp - SE
9a12c28d-dbec-5ee1-841e-9da3e950cb8c | note | SI Key - H
96513929-5e60-5a1b-8715-a5eb9cd4d21f | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Concrete Delivery
ed391d43-29ff-5a39-8af4-3c62dbcb0e5e | note | Ref docs - VR610.13, 610.16
8d74290f-6485-51e6-8f84-968f69d36440 | note | Acceptance criteria - Concrete to achieve required uniformity and discharge time in accordance with 610.13.
6edc749c-7908-5b0c-b100-3764fc0c12be | note | ○ (60 minutes unless mix design is approved by Proof Engineer and Superintendent to be extended)
b6923f8a-cd67-546e-a563-efc8020866d9 | note | ○ Time between discharge ending and restarting is to be less than 45mins for a continuous pour.
0c5dbddc-31ed-5c89-bc16-e0f262e76915 | note | ○ Concrete docket has been verified to confirm mix, slump and moisture content of aggregates is as per design.
2c22214b-e5ea-53af-b2f3-1fb3c2517ae2 | note | ○ Records of actual amounts of water added into the agitator drum at the slump stand is available for review by the Superintendent.
d1cb2299-bdd1-5af4-9e31-b6cc73bd0315 | note | Freq - Each pile
08e1ae40-eb1f-5b16-bef6-810b848e454e | note | Key - R
bf8503a8-dcd0-57dc-b5f7-38e35f4cbdda | note | Resp - SE
91bdf35c-37d1-540a-aebe-0ca424b2fc1e | note | SI Key - H
fe7bc973-db02-5a34-a357-adf99f9574a0 | note | Remarks/record - Concrete dockets Pour record
afa08696-2340-55d6-bc5f-066241350f56 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.12 - Concrete Placement
33774a70-7d55-5cc7-b0cd-6ef400aa0a4e | note | Ref docs - VR606.06, 610.17, 610.18
2df9e52f-d165-532a-810f-9c972dcf9e82 | note | Acceptance criteria - Piles have been concreted within 24 hours of completion of the pile excavation.
ec491bca-1942-50ef-87bc-c93dbd41be06 | note | ○ Concrete has been placed through a tremie tube and was not dropped from a height greater than 2m through air.
0fe7539c-b80a-596b-bf02-80af9617ec8f | note | ○ Concrete was not mixed when the air temperature is out of the range of 5-35 degrees.
7445f143-d83c-5ee4-b603-99897798c554 | note | ○ Discharge time to be 60 minutes unless an otherwise approved by the Superintendent.
1f424a73-c5f8-54f3-be4d-f8a35a1e7c02 | note | ○ If water is required to be added, it can be done so if no more than 60 minutes has elapsed. Concrete samples including slump test to be taken after adding water.
6b7ddd59-f5a9-586f-97eb-020153ef68ae | note | ○ Any repairs have been carried out using a method and materials as approved by superintendent.
08a58eeb-1541-5710-96dc-891c82952796 | note | ○ Concrete to be placed in dry bores is either (I) Self Compacting Concrete (SCC) with no vibration or (ii) Highly workable concrete which is to be vibrated by using immersion type, high frequency vibrators.
2445586e-ca74-57bf-975c-cc903c1781d7 | note | ○ Where a temporary casing is used, the free surface of the concrete are at least 1.5m above the bottom of the casing.
eba423d6-1e30-57d6-ac4a-69d3562f5981 | note | ○ Piles placed in the dry have been constructed to a minimum of 300 mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile. Unless otherwise approved.
06c0ca06-7f99-52a8-8f54-f81be1ffc9a1 | note | Freq - Each pile
bdb16cb9-29b7-587b-972a-78a70ee33c83 | note | Key - R
2b279863-852e-5255-bbf2-c57b9a8d4066 | note | Resp - SE
72928fda-aa56-5336-b228-6c6ab409aded | date | Inspection Date:
| checkpoint | 2.13 - Concrete Placement – Under Water
c3faf146-eb6f-5286-9c3b-e9bbb5c79687 | note | Ref docs - VR606.06
fff15f9f-8e72-5cfe-b2ec-4a5bffbed565 | note | Acceptance criteria - Concreting using tremie methods is not commenced until the pile hole is filled with such head of water as to equalise the external water pressure from the surrounding ground.
6fbdee69-d5d4-57b6-9a6b-8a0eb357ec7e | note | ○ 2m head of concrete has been maintained above the tremie tube while placing underwater to avoid contamination and mixing.
18e7bbef-7f3d-5cca-8c97-090c373ede71 | button | ○ The rate of withdrawal of the tremie pipe or pump discharge hose versus the volume of concrete placed has been recorded by the Contractor and the records has been submitted to the Superintendent for review. | Yes,N/A
20fcf508-7e6b-54b4-a078-6c7d629ec76e | note | Key - W
73ad22bb-d8d8-545d-9a03-8bc0a45849a8 | note | Resp - SE
dfeec85f-b8c3-534e-a12d-da3ebd5a15cd | note | SI Key - R
54f32548-1ea5-57ce-88ce-2e28bd570212 | note | Remarks/record - Tremie withdrawal record
a1830260-0d71-52b6-976c-21bb55d4bf38 | date | Inspection Date:
| checkpoint | 2.14 - Concrete Sampling
89d1ff70-45de-5485-957e-35d22b14e1a4 | note | Ref docs - VR610.16, Table 610.131
96d7cb81-1944-5bbf-8214-b93c9d234aaa | note | Acceptance criteria - Slump test in accordance with clause 610.16 (c).
d968f6d2-fd6f-51b3-99d4-9b1fb4ffbeb1 | note | The specified slump ranges are:
9d4b5067-7d5e-50d9-b26b-2c2fbec125d4 | note | – – – – – – – – – – – – – – – – – – – – – –
44d8efb7-0b3e-58b8-914a-2e8bf12a895a | note | Specified Slump, mm ¦¦ Tolerance, mm
831a86c1-732b-5d95-952d-c7992d522e21 | note | – – – – – – – – – – – – – – – – – – – – – –
7c9030af-76e1-55aa-8430-d362b208885d | note | <60 ¦¦ ±10
3900986c-592f-514d-bd78-9529ef03895e | note | ≥60 ≤80 ¦¦ ±15
4235a8cd-b2b0-597f-8260-05fe5ab57a14 | note | >80 ≤110 ¦¦ ±20
bfe83c9b-6ea2-54bc-bf56-5dfa70ec6c40 | note | >110 ≤150 ¦¦ ±30
40007054-cdc4-5b3d-8909-c261c863bbff | note | >150 ¦¦ ±40
71505750-5de4-551b-8192-e45b1f650bd9 | note | – – – – – – – – – – – – – – – – – – – – – –
b0a5d430-4023-56e3-aeca-c669f5cb0c3c | note | ○ The consistency of the concrete to be measured by a slump test after the water has been added.
a126c236-a206-5fbf-b3b5-113cf0ec8be8 | note | ○ Tests are to be conducted for volumes cast in one operation as per:
b44eb271-996f-5a68-a2ba-6cc6c8bd7f7d | note | 0 to 10m3 – 1 test
8de0aed0-31b2-5c25-a967-0f87056f0da0 | note | 10 to 25m3 – 2 tests
1643353e-46f3-5fac-be86-7dbf762429c6 | note | 25 to 50m3 – 3 tests
d61a627c-0e83-5711-9b18-c6bbf1f019af | note | 50 to 100m3 – 4 tests
e95e23c8-ed90-572b-8fe9-2f030acba222 | note | ○ One extra test sample has been taken for each additional 50m3.
521503cf-2ff8-5d15-910a-4a073eeb35bf | note | ○ The compressive strength of the concrete has been tested with a minimum of 1 sample being tested at 7 days and 2 samples being tested at 28 days.
31f0d67c-f938-54bd-b4c0-db617ee98cc8 | note | ○ If SCC is used, it meets the requirements as stated per VR 610.16 (c) and (n).
6a35ae0e-4b33-5774-85bf-1621133dc597 | note | Freq - Each pile
dcc01d02-5b0e-5fa1-9d13-3df39de682c7 | note | Key - W
25c4e145-fbd9-5a57-ba33-19106ad1bdb9 | note | Resp - SE
4b928572-c3f5-5668-92e3-e26e5a928f12 | date | Inspection Date:
| section | 3.0 Pile Testing
| checkpoint | 3.1 - Integrity testing
9a8903f0-a1c6-5725-af45-fb5bfba757a8 | note | Ref docs - VR606.07(a) VR606.07(b) AS2159 PS3050.07 (a) (iii)
8184fd0f-d315-5fd2-9d13-f44db29cc2a7 | note | Acceptance criteria - Integrity Testing has been carried out in accordance with integrity test methods specified in A2159. Pile testing consultant is independent of the piling contractor and pre-qualified. Details of the pile testing consultant has been submitted for review by the Superintendent at least 2 weeks prior to testing.
f697ed29-a8ad-52d5-94e7-b032f5e71a2a | note | ○ The measured cross-sectional area of each test pile is not to be less than 5% of the required area. Integrity testing was not carried out until the concrete has achieved a compressive strength of at least 25 MPa and not before 7 days after casting of the pile.
fff9fcc9-8798-5841-ba25-47680a0022d5 | note | ○ The frequency of testing to be as per specification and the submission of raw integrity testing data to be available to the Superintendent within 48 hours.
07baebb8-e7be-506c-bc13-df5064927820 | note | ○ Testing has been carried out on the first 6 piles constructed, and subject to acceptable integrity test results being obtained, 1 in 3 remaining piles have been tested. If any pile fails to meet the acceptance criteria, all piles must be tested. Reduced frequency is to be approved from the Superintendent.
b8211bdc-d6b8-533c-a674-512ae35475f0 | note | ○ Raw data of pile integrity testing has been provided to the Superintendent within 48 hours of request of the Superintendent.
50fb3201-44ea-5ca2-ad97-26c5b42e5198 | note | Freq - Each Pile
ef68ad58-3b1e-58b5-98ea-2d91f40789ac | note | Key - H
dede5fca-081d-5179-9cde-0dbf944396f9 | note | Resp - SE
14c5f34b-7bbc-5cef-824b-0a479b825201 | note | SI Key - H
19b51547-b29e-5eeb-871f-38291da43627 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Static Load Testing
b40feac3-f81d-56c0-bee3-4e2cc0e1e02e | note | Ref docs - VR606.07(b)
23d0a83f-bbeb-53b0-ac42-a60888076742 | button | Acceptance criteria - Static Load Testing – compression, static and lateral load test in accordance with AS 2159 and as specified in drawings and once concrete has achieved 28-day compressive strength. | Yes,N/A
b53f5ea7-422e-5656-9b9d-508b48c31374 | note | Freq - Each Pile
e9b2ab65-704e-5053-9bfa-1c967b125b7b | note | Key - R
1dc061bf-4e3b-5491-b57e-47a61649d9a1 | note | Resp - SE
7b93ff9c-2d0f-5a26-9358-3afdd2bc4f0b | date | Inspection Date:
| checkpoint | 3.3 - Details of the Dynamic Testing Pile Driving Analyser (PDA)
2a45517b-4bd4-5cca-bcab-c0af748804e6 | note | Ref docs - VR606.07(c)
689ff2fc-1245-5d8d-951c-27eb5fca59ef | button | Acceptance criteria - The details of the proposed pile driving rig, hammer size and drop heights have been provided to the Superintendent for review prior to undertaking the testing. | Yes,N/A
401ed7ed-dd3c-56fa-9d5e-82bb26395e30 | note | Freq - Each Pile
595be2d4-538c-5242-b62b-9df31e7f56d7 | note | Key - R
1b38237e-5ed5-5c1e-8a93-a238203f3395 | note | Resp - SE
7319b2f4-f6df-5854-bd5e-b8917eb2dddb | note | SI Key - R
b46977d1-e7fc-5e37-a792-c8e9ee8a19bb | date | Inspection Date:
| checkpoint | 3.4 - Dynamic Testing
ce7f9eed-46ab-515a-ac66-cc8c3e99d27e | note | Ref docs - VR606.07c) VR606.07 (d)
c411ac5e-0a88-57b4-827e-82ed734a1249 | note | Acceptance criteria - At least one (1) load test every 10 piles or, one load test per pile cap or bridge abutment which ever gives the greatest number of piles tested.
fca452cd-8559-595f-a3c1-4deda14f2543 | note | ○ Dynamic testing has also been carried out on piles of which the pile toe levels vary by more than 2 metres from the test pile.
6ed15d1a-b5c0-5033-909f-996cf40aed15 | button | ○ The test procedure and test reports to conform with the requirements of AS 2159. | Yes,N/A
75771e5b-2f83-5672-9e87-dbf69be373cd | note | Freq - 1 in every 10 piles, Piles with varying toe levels > 2 m
dd517411-0e1a-54f6-8adb-644e1ccfc90e | note | Key - R
10f5a8e7-9de2-5414-9d79-d4d5fb94af18 | note | Resp - SE
b6cf346a-f5c5-5b4f-8d0e-eca2c5b370b3 | date | Inspection Date:
| checkpoint | 3.5 - Reporting & Acceptance of Test Results
8e9af600-a96b-5230-906e-f0168907073d | note | Ref docs - VR606.07 (d) & (e)
c8fbe907-afba-5421-955e-bc29b024e844 | note | Acceptance criteria - Two copies of the test report to be provided for the Superintendent.
2a4e3f16-2ea9-5664-ac08-b22429c607c1 | note | ○ The test results to demonstrate acceptance criteria as shown on the Drawings with ultimate capacity equal to or greater than the pile test load.
9e97fcb4-e267-5602-905f-0c1f6f81094c | note | ○ Where confirmation of pile capacity using dynamic pile testing is obtained by re strike, the report includes the results of the initial drive and all subsequent re-strike.
27936b39-b9e6-546d-b2c2-fecbc17dcec7 | note | Freq - Each Pile
b1caed84-090b-591a-b704-0e4f75ec2d78 | note | Key - R
ca55b33f-40a6-5900-af0c-19a84b944012 | note | Resp - SE
1a15711a-33e8-5d18-a2e3-0f16f87de304 | note | SI Key - R
84952121-c49b-55f9-a058-ccb91c5515b7 | note | Remarks/record - Test Results/Reports
5e7eba3f-b183-5003-9759-1e09f5c2c2c2 | date | Inspection Date:
| section | 4.0 Pile Completion
| checkpoint | 4.1 - Tolerance for Pile heads
0a07ce17-54c9-5475-8c4f-abcd619287ba | note | Ref docs - VR606.08
3000e452-63a1-56ba-9b4e-7a60f8c992a4 | note | Acceptance criteria - Pile heads have been cut back to design level no sooner than 24 hours after concrete has been placed.
5f693c6f-1e70-5d0b-bffb-f7b0a908721b | note | ○ Pile head finishes within 75 mm of the specified plan position.
bbc674fd-e627-5d79-b451-d94e329b7829 | note | ○ Pile head reduced level finishes within 25mm of design.
f47b9327-e63e-52c8-80cb-49544fa3c028 | note | Freq - Each pile
7af846c2-5310-5c98-90a1-a0307f618b54 | note | Key - R
5662bb04-65d8-5f63-8670-a5d70b7df1c5 | note | Resp - SE
f6ef6cfa-4d27-5cd7-a8f7-a8901ed5e9b2 | note | Remarks/record - Survey Report
6e31fcf8-c197-58bb-9620-4bc41517fc01 | date | Inspection Date:
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Test Reports
00b565be-1a46-5cda-8847-eafddd92d5e7 | note | Ref docs - VicRoads Specifications
175fdcc2-5e65-578f-b66b-a5de0322a45b | note | Acceptance criteria - All Test reports received and reviewed.
f19e1137-93b1-5d2f-931e-556815e6c8fb | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
278826cc-89bc-5d40-860c-b0a7e280e31e | note | Freq - Each lot
e411eb4d-ac9e-5ece-afd2-418cc49deb76 | note | Key - R
605a6985-a82c-5045-b952-8f6c7bbda946 | note | Resp - SE
c6ba00f4-03c4-5470-acb9-a35e5f960d35 | note | Remarks/record - Pile Test Report, Compressive Strength Test Report
e5b84bb6-95ec-594b-a179-f80c93e9ead7 | date | Inspection Date:
| checkpoint | 5.2 - Product Non-Conformance
c05eb953-c862-5790-a1c1-42b0514ba4c6 | note | Ref docs - CQMP
968815e4-4825-50f0-837e-d3c50f4b0822 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
758b2cd5-a8ae-567f-8775-45df3728d994 | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
712a7f6b-409e-5175-92f4-4f3becaf6453 | note | Freq - Each lot
ca44221b-f948-5cde-b810-326a916d8c18 | note | Key - R
0811f4b4-303f-5abf-ae8b-ee1008605367 | note | Resp - SE
59a25ebe-a0a7-5194-8d1e-df066171241f | textbox | Remarks/record - NCR No:
33447675-a65d-5e50-aa5f-534b5ad29792 | note | ○ NCR reports
b8cc87fe-bbda-59c4-b39d-e973bea62173 | date | Inspection Date:
| checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
d7e7eddd-cba7-5255-a1ee-1ba6bb63dfe8 | note | Ref docs - CQMP, Lot Records
339b5d3f-f59a-5d56-9ebc-ab580b6b4be7 | note | Acceptance criteria - All above criteria met, and records identified attached.
4b21e5f1-34a6-5b73-b631-a9dbd253b78c | button | Have all of the above been tested and proven to pass design requirements? | Yes,No,N/A
a6e76e2b-6265-5de4-a06b-6180b1b7e170 | note | Freq - Each lot
b99bf73b-57f5-5ab7-bce3-24775bccdc8e | note | Key - R
a68d4acf-3406-5aef-a5d7-f4fdb43332a6 | note | Resp - SE
e07eb8e7-7635-5cf8-8ddc-2c93ceb7cbad | note | Remarks/record - Reports and other compliance records attached.
65e6bc12-06d0-500e-95ab-11536307c279 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0027 Structural Concrete | itp | 1630-P200-SYM-QAC-ITP-0027 Structural Concrete |  |  | 95261b41-8ccc-4d88-bd4b-a56a53524af0
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Concrete Grade, Exposure Classification and Cover Requirement
a6a748df-23d8-542b-a6f7-02adb87f0d0d | note | Ref docs - VR 610.04 AS5100.5
2f08f954-3796-54c1-b5f4-6505d8b5238e | note | Acceptance criteria - The concrete grade, exposure classification and cover requirement of the structural element is confirmed and recorded below.
9ab325cc-ca3e-5627-b924-6bc37a1ab362 | textbox | Concrete Grade: |  |  | VR /
179ea50d-3719-5c30-8d1f-8f2e1c4193b9 | textbox | Exposure Classification:
0bb31706-7d05-566c-a1e8-9a2415d0af8d | textbox | Cover Requirement: |  |  |  | mm
c15492d4-5dc3-5e3f-8add-46b39766759a | note | Freq - Prior to start of Works
6007c722-6d4c-52f4-9f6c-a793a462238f | note | Key - H
a8b30873-5b62-541f-96e8-3bac9ef92aff | note | Resp - SE
589e497a-7c27-5673-bfd4-caa62dc1f1a4 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
7bfdf40f-c034-5597-8c29-b6a571fe08d9 | button | Lot map | Yes,No,N/A
d7a0cd9b-e0fc-5e73-8a9e-ea6ac5eaf16a | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
f33aba10-d067-5bef-bfad-5321f9e3a59f | button | Environmental permit | Yes,No,N/A
ca99271a-34cd-55b1-844d-bad4d15f1f94 | date | Inspection Date:
| checkpoint | 1.2 - Concrete mix design approval
fbaa2e36-e156-5553-b90c-ef9a74c25796 | note | Ref docs - VR 610.07 AS 1379
c6d8e10e-c15a-5c4e-b45a-1d9d01dd6159 | note | Acceptance criteria - The concrete mix design for the specified grade has been approved by the Superintendent.
5d15dbd8-1811-5d40-bbe1-d0d9457ce32a | note | ○ The concrete mix design includes details on the cementitious material used in the Works along with CMRS registration number and test certificates endorsed by a AS ISO/IEC 17025 accredited laboratory.
7a5e68a8-da6c-505c-a410-1952cdff8302 | note | Freq - Prior to start of Works
7b12bad8-5f9f-55c2-a8b3-afdccea9ee65 | note | Key - H
6eec47c7-98f4-5bf6-a405-9f4dedb8547d | note | Resp - SE
5ca49461-b423-572a-aa74-37bb820c189a | note | SI Key - H
73dc57e8-5d6c-52f6-8e62-b3a853d53a38 | textbox | Remarks/record - TeamBinder Ref No.
bc0113b7-9c9a-5498-b6bf-e0a6ec2b0b21 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Approval of procedures
0ed398ed-0d3c-5bdd-9e84-c538ab462a9e | note | Ref docs - VR 610.18(a)
fa2517e0-fd3b-55ae-b95f-e06a245b0912 | note | Acceptance criteria - The WMS, ITP’s and quality control checklists have been reviewed by the Superintendent. These documents shall include:
c6adfab9-dacf-51a2-a2fe-503cd24f1e46 | note | ○ Conducted toolbox meetings of all concrete construction personnel on all aspects of the WMS, the ITPs, quality control checklist(s) and all specification requirements.
90f3aa7d-a6b8-54f5-b706-92e161daa454 | note | ○ A site sampling and testing procedure with minimum frequencies of testing requirements.
f23bba4e-aab3-5b6f-9015-df7bb9e72bd5 | note | Freq - Prior to start of Works
167c7a52-efe0-5776-b42d-af2186079b13 | note | Key - H
0085afc6-9aba-523a-9f4e-737d9b67af7b | note | Resp - SE
0000be06-d294-566d-9f54-8fd352a1721e | note | SI Key - H
c64c1a37-df2a-5a3c-93fc-8d00c817907f | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Curing methodology
8d009214-dc03-5c8b-aea1-10bcdbbd1753 | note | Ref docs - VR 610.17(f) VR 610.23
7bdd0838-4a95-5937-a5b0-84f9c980818e | note | Acceptance criteria - Full details of the proposed methods of curing, as part of the concrete mix design submission has been reviewed by the Superintendent.
6263ae8d-569a-5c4a-8c8c-8d9c55ef290d | note | ○ The curing method also includes any details on evaporative retarding compound and its application procedure including minimum application rates.
81ff78ae-309a-5ff6-924e-fdef189f7b12 | note | Freq - Prior to start of works
866e890e-8b40-50fb-9fea-e3e0224ab50d | note | Key - H
8771e630-f2e3-5c37-b030-dcda2d49bdea | note | Resp - SE
e89e36a6-298d-5424-8655-a5861999638a | note | SI Key - H
8ceaf6f6-d2cf-5821-a371-c4dc4d937b74 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Setting Out
| checkpoint | 2.1 - Setting Out
fa506e75-02b4-5745-a860-3c4c720a05e8 | note | Ref docs - IFC Drawings
ed68cc55-072f-501a-8f24-aa1847f95c78 | note | Acceptance criteria - Survey set out as per the IFC drawings.
21a19a19-d6c5-5ff4-bf6f-d92203bd9dd4 | note | ○ The concrete will be constructed in accordance with the confirmed line, level, grade and cross-sectional profiles as shown on the drawings.
9b4590d9-3629-5cb0-bcb9-2de8eba838a3 | note | ○ The extent of the work has to be clearly pegged and underground servicers have been located.
7dde42da-f52e-526e-a8c3-c5ade90bca95 | note | Freq - Each lot
6e9edec1-4fcf-5cda-8764-5b3ce1dd20e1 | note | Key - W
e512843e-46ed-5c49-9c8f-6abfb6487464 | note | Resp - SE
268bb277-c28b-524d-879f-10505c1722b9 | date | Inspection Date:
| section | 3.0 Preliminaries
| checkpoint | 3.1 - Substrate preparation
8d3eb8c3-19cb-54c6-adf3-17c5c09ab665 | note | Ref docs - VR 610.18(a)
7be534d9-4c94-5041-ba35-7db2d2f028e8 | note | Acceptance criteria - Prior to placing concrete any absorbent surfaces including blinding concrete and construction joints shall be thoroughly moistened and excess free water shall be removed.
5eea4970-beef-55b0-b01f-3842aea2e2db | note | Freq - Each lot
1daee159-74c4-5527-ac54-34152489a4a5 | note | Key - R
729117a5-5010-51c2-907e-5aa862868789 | note | Resp - SE
6b04eb49-d743-5f9e-9a8c-d5130fdc48f3 | date | Inspection Date:
| checkpoint | 3.2 - Construction Joints
1fea6952-334b-50c2-b0fe-4d8866ed3adc | note | Ref docs - VR 610.20
b8580366-de41-550c-b18f-fb448687efd6 | note | Acceptance criteria - Existing concrete, against which new concrete shall be placed, shall be roughened by removing all laitance and sufficient mortar to expose the coarse aggregate to a depth of 3 mm. The roughened surface shall be cleaned of foreign matter, laitance and loose or porous material.
e0c88c2e-ba05-54fd-bcbb-40849ffecd2e | note | ○ Permission has been gained, through the RFI process, from the Design Engineer to locate construction joints at locations other than shown on the IFC Drawings and approved by the Superintendent.
4d908d2a-d47f-5d03-8f1a-6d361df1d814 | note | Freq - Each lot
cbc18e5c-e763-51c4-b337-33c53b0ffb66 | note | Key - R
c28e3a3f-a93a-5e66-85ce-06e18f2b780a | note | Resp - SE
f69a28d2-c534-592c-bf34-576c863800e2 | date | Inspection Date:
| checkpoint | 3.3 - Insertions and Greased Joints
47b19435-5554-586f-b1a5-7c5f6ed0f599 | note | Ref docs - VR 610.21
f8df741f-df30-5eb9-8d01-c8aaff0e224c | note | Acceptance criteria - Abutting surfaces of concrete shall be separated by grease or other surface coatings or insertions of bituminous impregnated felt or fibreboard as shown on the drawings, so as to prevent the surfaces from bonding or binding together.
66df9571-370d-50bb-b936-b73ca4d628a4 | note | ○ Dowels shall be placed as shown on the drawings and prior to placing the surrounding concrete.
3cc5e870-6946-5646-a39c-eb6bf1a7d6fb | note | Freq - Each lot
0c26fe5b-bd78-57bf-a029-1b23deb122fe | note | Key - R
a37dac44-3146-54d2-a142-fcede1e8e3d4 | note | Resp - SE
c9e543fc-1a14-5acc-8613-dafeed10a5ae | date | Inspection Date:
| checkpoint | 3.4 - Steel Reinforcement / Embedded Items
0e98feb2-4c25-50d7-82d7-3a1434e7c595 | note | Ref docs - VR 611
d6a18541-ab03-5485-ba09-8e8f4b8e0f09 | note | Acceptance criteria - The evidence that the forms, reinforcement, any stressing materials and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent.
b5eb0e4b-088d-5c9b-8a5b-c8f85506521c | note | ○ Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
5096ebec-b05b-5c5d-827d-81ed69de0e8f | note | ○ Manufacturers and suppliers of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS).
3258fee0-3fd9-51dc-9dbf-341bba3c08c8 | note | ○ Evidence of compliance with this clause shall be submitted to the Superintendent within 14 days of award of the Contract.
d7fc01a6-8e47-5adc-995e-99918723501a | note | Freq - Each lot
b06e67e5-755e-5723-935a-6681f98f15c8 | note | Key - H
66ee680a-0ebe-593e-83e0-4c2c7525256c | note | Resp - SE
0e914781-e422-5e56-9591-32a25fdbae4a | note | SI Key - H
701f0abf-d5df-58c9-af3f-d606f6d2eb0a | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Steel reinforcement supports
c4145157-5d31-5f46-b853-09f99ee329c8 | note | Ref docs - VR 610.26(a)
715c6b38-14cc-5dff-a071-1130c236039a | note | Acceptance criteria - Concrete bar chairs and spacers are manufactured from machine mixed concrete and shall have a minimum 28 day concrete compressive strength of 60 MPa when tested in accordance with AS 1012.9. Notwithstanding the requirements of AS/NZS 2425, concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12% when tested in accordance with AS 1012.21.
cdfce22b-ac2f-5ed5-b4af-9a7c087fa48f | note | ○ A sample consisting of two specimens has been tested for each of compressive strength and VPV, in accordance with the sampling frequency as stated in clause 6.2 of AS/NZS 2425.
0dff63f7-e97b-53df-bca2-027917384524 | note | ○ Each concrete bar chair and spacer mix design has been tested for soluble salts (chloride ion and sulphate ion content) in accordance with AS 1012.20.1 on a 12 monthly basis or earlier if the mix design changes to demonstrate compliance with the requirements of clause 610.07(k) for soluble salts.
56f8be12-236c-5ee5-9e67-39fe925eef5c | note | Freq - Each lot
6163b323-cd41-59e9-ad1a-238db3725b6b | note | Key - H
a4311d5b-8002-5312-b4e6-ca77e5bcd07f | note | Resp - SE
a88b2ac4-1b91-59f2-b625-f5c2efbba696 | date | Inspection Date:
| section | 4.0 Installation of Structural Concrete
| checkpoint | 4.1 - Reinforcement Placement
cd6e2a4a-4588-5452-9f47-f3d2fba7344b | note | Ref docs - VR 610.26(b)
4c3dea55-a434-5355-a5d6-364554a20e0c | note | Acceptance criteria - All steel reinforcement is securely held during placing and compacting of the concrete. Steel reinforcement supports comply with AS/NZS 2425. The supports are made of durable materials strong enough to withstand the imposed loads without movement of the steel reinforcement as specified in this section, shall be positively attached to the steel reinforcement, and of such size as to maintain the specified cover.
3a9c1a50-72df-5cf1-b8d2-f3a5dde50d7e | note | ○ All steel reinforcement is securely held with the correct tie wire during placing and compacting of the concrete.
169c7760-2ede-561a-be42-f373d7f61eb8 | note | ○ The supports shall be positively attached to the steel reinforcement, and of such size as to maintain the specified cover.
e4ef248e-29ac-56f0-85c9-54c839b5a15b | note | ○ Bar chairs and spacers shall be placed sufficiently close together to ensure that the specified cover is maintained before and during concrete placement, compaction and finishing operations, and to prevent any potential deformation, displacement or crushing of the bar chairs and spacers such that deformation or displacement of the steel reinforcement is also prevented.
97910a03-3816-5d1e-871b-0671bc5fd346 | note | Freq - Each Lot
8f90f77d-b31a-5734-9357-e6a6395e8e8f | note | Key - H
faebe67a-8c62-501d-af03-d16b095f5def | note | Resp - SE
3f46d0c9-609b-59b7-90d4-ec7ddc6abee7 | date | Inspection Date:
| checkpoint | 4.2 - Early Age Thermal Cracking / Thermocouplers
f1d24801-cfdd-5d08-a9ce-378ca94cf162 | note | Ref docs - VR610.22
d6f1e085-df9d-5c6d-9bb1-e190831387a9 | note | Acceptance criteria - Measures have been taken to control early age thermal cracking of concrete for large and restrained members including but not be limited to crossheads, diaphragms, columns, abutments, footings and pile caps where:
75d4133e-eb27-553b-8dcc-5e9a208422e9 | note | (a) the least dimension of a member exceeds 500 mm; or
d8c98111-1eb7-57a9-83a9-edc153325857 | note | (b) one or more faces of a concrete member is restrained by previously placed hardened concrete or by other external restraints.
14e1a38f-e610-53fe-a4ec-46ad23f91add | note | ○ Temperature differential monitoring is installed (unless already undertaken on at least one representative member from each type of large and restrained members, provided that any required control measures to reduce the differential temperature within the specified limits is adopted for the subsequent construction of members of the same type).
7da4bbaf-2471-5c5d-aa95-ff0f810368fb | note | Freq - Each Lot
c516091a-3b96-5b79-bb70-51adeacb97cf | note | Key - H
4d8633b9-9edd-5007-b459-88a9fdad0a10 | note | Resp - SE
dc104540-6226-5534-8a62-c8d1d1ac30eb | date | Inspection Date:
| checkpoint | 4.3 - Pre-pour inspection
8ecb6541-1953-51ce-8832-62b898edbb92 | note | Ref docs - VR 610
a0758a19-6aed-5601-b8b8-38325c409554 | note | Acceptance criteria - Pre pour inspection to be conducted prior to placement of concrete.
a6be818e-0b59-5ade-9f4c-52b2eae0fdb0 | note | ○ All formworks shall be erected as per specifications and all reinforcements shall be installed as per specifications.
97ee69fb-ac64-5e52-9382-7910be800337 | note | ○ The specified minimum concrete cover shall be maintained at tie wire positions. Excess tie wire shall be cut off and the twisted ends of wire ties shall project away from the cover zone.
5567f46d-1fe8-524e-ac1c-2919a9bffa81 | note | ○ Contact between carbon steel and galvanised steel reinforcement or carbon steel and stainless-steel reinforcement or other similar metal embedment’s shall not be allowed.
052a8928-a789-50a2-a21d-69d1cc161cd2 | note | Freq - Each Lot
35068514-6e66-55a4-a62e-2166127bbb6f | note | Key - H
e8292509-9871-505d-80ea-0d49e107221f | note | Resp - SE
40099d4c-dabb-503f-be16-ecc9e093791a | note | SI Key - H
9fa2cfcf-1eca-5247-b0b9-07b7237ed543 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Concrete Batching
37837bd9-9baf-5e35-8cf2-c9f0bb920f8f | note | Ref docs - VR 610.14
1c5f7d13-7b8c-565e-a97a-eb794a3e205c | note | Acceptance criteria - Alternative supplies of concrete are available from stand by mixing plant(s) capable of being operated immediately in case of breakdown, together with adequate supplies of cementitious material, fine and coarse aggregates for an approved compatible mix(es).
9e0cfdf2-71fe-5060-ab1a-2153a00557f9 | note | Freq - Each Lot
6189b705-4e8c-5b4d-ac75-0b848b822151 | note | Key - H
1439aaec-d6ae-56eb-a647-bcd1af9ecbfc | note | Resp - SE
cda01dd3-ea14-584a-94f1-c5bb658e837d | date | Inspection Date:
| checkpoint | 4.5 - Placing, compacting and finishing concrete
e81fdf59-7e6d-5804-9b9e-1390912c3948 | note | Ref docs - VR610.13, VR610.18
672849a7-d435-5f4b-ab8c-02a44c040106 | note | Acceptance criteria - Concrete shall not be mixed when the air temperature is lower than 5°C or greater than 35°C.
614db646-dbb5-5b1e-8dac-e87d1d69dc1d | note | ○ Discharge Time to be 60 minutes unless mix design is approved by the Superintendent for 90 minutes.
5a8db276-b827-57b5-88c9-b5d2d7eb6dcd | note | ○ Concrete shall not be dropped from a height exceeding 2m.
9ec0dbc9-200a-5444-9110-46d9b5d50072 | note | ○ In continuous concrete pours, the maximum time lag between truck loads on site shall not exceed 25 minutes.
d988a408-118f-5dc3-9a04-5e5e680aec9f | note | ○ If water is required to be added, it can be done so no more than if 60 minutes have elapsed from the time of adding cement and before commencing discharge. Concrete samples including slump test to be taken after adding water.
d7624502-666a-5ddb-91c1-02d6173768d8 | note | ○ Concrete shall be thoroughly compacted by internal vibrators of appropriate size and supplemented by external form vibrators.
80d274ee-0c1a-5485-870d-1496618c9032 | note | ○ When the value of the rate of evaporation as determined from Figure 610.171 exceeds 0.50 kg/m² per hour precautions to minimise evaporative moisture losses such as the application of an aliphatic alcohol based evaporative retarding compound or controlled fog spray are taken.
0dc41f06-35fd-5212-8d03-a4c0458504ab | note | ○ The evaporative retarding compound, when required, is to be applied immediately after initial screeding. The remaining finishing operations can be carried out after application of the compound.
176671f2-1455-5cbf-bb7b-4f9742d47614 | note | ○ An evaporative retarding compound is used for concrete decks and slabs.
2513fac7-1bee-5ee5-832d-4054b6d957b3 | note | ○ Records of water added to agitator drum are made available for review by the Superintendent.
72be7faa-3f98-5821-ba5b-75d93ab9720a | note | Freq - Each Lot
dcabe075-e7cd-52d5-b2b5-b4514700dc85 | note | Key - H
e7fa6cbd-f26f-5d8f-a64d-fb34777d7755 | note | Resp - SE
11370508-8e52-5d7c-9625-d2c2f3a49877 | button | Remarks/record - Concrete pour record attached | Yes,No
09438a66-c4a4-5aea-a916-c3a1491c2390 | date | Inspection Date:
| checkpoint | 4.6 - Concrete Testing (Compressive Strength, VPV and Slump)
c0106ea7-4461-578c-beca-9d0f086b59d2 | note | Ref docs - VR 610.16, Table 610.161, Table 610.162, Table 610.131
27e8664f-b88a-57f4-9095-9c5b76d8d550 | note | Acceptance criteria - When concrete is being cast into a structural member, it shall be tested with a frequency in accordance with table 610.161.
44ec13ce-f449-582f-8df7-15bfba291f13 | note | ○ For volume casts in one continuous operation:
10af66a3-902c-551f-8e98-8d92dcb53ae6 | note | 0-10m3 : 1 sample must be tested
74a852ca-beb7-53b6-9b01-d11482ab164e | note | 10-25m3: 2 samples must be tested
e78e7bff-5877-588a-9c97-ad6d30088517 | note | 25-50m3: 3 samples must be tested
aa5df1ce-1c5d-5826-b2c7-06d33d9c03f3 | note | 50-100m3:4 samples must be tested.
9e3c4fe7-6f46-5298-bc70-b30e9858de1e | note | ○ For each additional 50m3, one additional sample must be tested.
b3e3ba66-d54a-5f90-94fe-b4c9dbb91fd1 | note | ○ The concrete samples shall conform with the testing requirements of VR 610.16. This includes a slump test being conducted to test the consistency of the concrete. With tolerances to be for specified slump of:
f71f5d57-7c84-5e99-95fa-8befc797b0e1 | note | <60mm: +-10mm
73bf40d7-f004-52da-b2b4-8c31d226084f | note | 60-80mm: +-15mm
b1bc5257-470a-54b1-b61b-0ba745fc23e0 | note | 80-110mm: +-20mm
e4089b09-f2e3-58ab-b7c1-c9ba3c038736 | note | 110-150mm: +-30mm
73381f98-e646-50f2-823f-0ba157152c69 | note | >150mm: +- 40mm
ea9342f2-0d35-5b5a-9d6d-0211f9018e29 | note | ○ The compressive strength of the concrete shall be tested with a minimum of 1 sample being tested at 7 days and 2 samples being tested at 28 days.
a8520321-ee63-55a5-81a3-67162d810f5f | note | Freq - Each Lot
6c26f573-cc2d-5789-9a1b-ec60298b40cf | note | Key - R
e4159907-0d9c-58bb-91de-bf3b10a615d8 | note | Resp - SE
cb44e012-3410-5d4e-8e6d-578f1f3d8ade | date | Inspection Date:
| checkpoint | 4.7 - Surface Finish
be442f5d-ce76-54ee-832d-270175e9e97f | note | Ref docs - VR610.31 IFC drawings
0a9e86a5-86e3-5489-a8f6-bba75cc2e96d | note | Acceptance criteria - The surface finish shall be as per the drawings and VR610.31.
e0306cd2-1814-574f-8594-1280c44861ac | note | ○ Where the surfaces finishes are not specified in the drawings, surface finish shall be class 1,2 or 3.
657f7d2e-5a4c-5821-9e83-4814695c8e9d | note | ○ Class 1 finish shall be a uniform colour and texture with no defects which structurally affect the concrete. Class 2 finish shall achieve a concrete surface of uniform colour and texture and be free from any major surface defect. A class 3 finish shall achieve a concrete surface of uniform colour and texture and free from surface defects.
63017c3d-a200-568d-845c-89c2b740fa72 | note | Freq - Each Lot
c2b3ce02-4a91-5746-a0db-e0414a58f1da | note | Key - R
f2909f9e-1650-534e-963e-5ea7f51df637 | note | Resp - SE
71e81ce9-9af4-5b2b-bd9d-ac343d0d9843 | date | Inspection Date:
| checkpoint | 4.8 - Curing of Concrete
645e0bed-1e30-59a0-9480-8489a86ca57b | note | Ref docs - VR 610.23 AS3799 Table 610.231
1b5b3dcb-c835-5ca1-8448-15feeecabf06 | note | Acceptance criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed at any location and shall continue uninterrupted for not less than the periods specified in Table 610.231. Methods of curing appropriate to job include, and are not limited to;
19506d83-47d0-5f59-9b31-71cab85457a5 | note | ○ Water Curing
4c37d1ad-92d7-53c2-8792-842f5f4c42a2 | note | ○ Curing compound
e76d2323-5a68-5c87-a8fb-f82f01d876a3 | note | ○ Polyethylene Sheet
8f97471d-3d7e-5b02-a59a-50bb8166a970 | note | ○ Maintaining Formwork in Place
c380562f-26b1-5f94-b425-bf503a732655 | note | ○ Steam or Radiant Heat Curing
63395462-3daf-54c7-931f-6522136fbb7b | note | Freq - Each Lot
77fa7443-c144-5229-a232-d15dc3fd8907 | note | Key - R
ac388574-413a-5c43-a1c2-2c0ea1cbed04 | note | Resp - SE
ff3b3964-ed50-5f4e-a860-1659fcbbb4cb | date | Inspection Date:
| checkpoint | 4.9 - Formwork Stripping
adf32654-b64c-505e-b1ce-933e5751c49c | note | Ref docs - VR 610.25 Table 610.251
d7b561b3-4787-54a0-b76b-44a3e1deb226 | note | Acceptance criteria - Formwork shall be removed as per specified in VR 610.25.
da3718e2-ab23-51f4-a335-465f0a11e54c | note | Freq - Each Lot
7c8d8508-8beb-5eb3-a902-3b337c3047c1 | note | Key - R
d9005792-2c74-51bb-8384-27796e836ab6 | note | Resp - SE
3ddfa13d-9f4b-5d25-becd-5f9982051052 | date | Inspection Date:
| checkpoint | 4.10 - Curing of Concrete (after stripping)
dfa3f72f-0bec-551c-9ca9-d68500f8e8e8 | note | Ref docs - VR 610.23 Table 610.231
6e4475ff-ef90-5fff-9b73-5c284b016251 | note | Acceptance criteria - Immediately after stripping any formwork curing has commenced to the approved procedure and minimum durations.
a4ff195f-9e4d-5a5a-a25c-dcf2a49b0f9e | note | Freq - Each Lot
1afd6982-2ff9-50a3-87ad-1865653a6c7b | note | Key - R
b0f8060d-b475-5d07-a918-fcdb4a123dbd | note | Resp - SE
6d3f73db-d0ba-59eb-9b61-de2c3bd53c2b | date | Inspection Date:
| checkpoint | 4.11 - Coating of concrete (if applicable)
57c189ab-7081-5ca0-bb95-f155280971f1 | note | Ref docs - VR 686
0f37df27-ae13-5cfe-9006-ec709d8cb5ae | note | Acceptance criteria - The procedures and surface preparation in accordance with clause 686.06 have been reviewed and accepted by the Superintendent.
76fc2379-c42d-51f2-b432-71757cf38434 | note | ○ Coating of concrete shall be as per VR 686.
af54826b-ac75-5764-a0c6-787eb5be515f | note | ○ Coating has not proceeded without trial coating application with outcomes reviewed and approved by the Superintendent.
916bc5df-66f2-52fd-911c-1b25f473c73d | note | Freq - Each Possession
01332947-c9ec-5982-8bb5-0ba50a569eb6 | note | Key - H
8bb7f3e4-cd9c-538e-a8db-e39dc003c8a6 | note | Resp - SE
03a42d21-21ee-557b-a05b-012e496552ac | note | SI Key - H
cffc37a6-7426-59b1-943f-4e2dbbb4f137 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.12 - Measurement of concrete cover to reinforcement
e76df8d5-f18d-56cf-abf4-91e3925acf60 | note | Ref docs - VR 610.34
a499d9bb-15d6-5b33-a629-509c71603cde | note | Acceptance criteria - A concrete cover measurement survey shall be conducted after construction on a representative and randomly selected number of exterior surface areas, using a concrete cover meter in at least 3 m2 test area for every 25m2.
b0e8f05d-6378-5de8-8233-07e0d2b27903 | note | ○ Records to be available for review by the Superintendent.
4917ac90-0511-5729-bd86-8afd1b8a828c | note | Freq - Each Lot
66ae41b7-4f43-56e0-b6fb-4ff60db6df30 | note | Key - R
fa37cf15-2160-501b-ae61-5cf69064224f | note | Resp - SE
b978299e-0391-5c24-b0d7-282e91015e9c | date | Inspection Date:
| checkpoint | 4.13 - Cracking of Concrete
ddb329e4-a868-5a1f-914f-0b6aff2735fb | note | Ref docs - VR610.24 Table 610.241
92c2f8d1-fd3d-50f3-90e1-05c8a1957204 | note | Acceptance criteria - Cracks may be no wider than 0.1-0.2mm depending on exposure classification in Table 610.241.
ceff0895-a2e6-5c8e-8692-e89dee8d736e | note | ○ Minor surface imperfections are repaired in accordance with VR 689.
9f46a5d4-20af-5d06-9cca-d1f2b077d61a | note | ○ The assessment of cracks has been undertaken by a specialist with at least 5 years’ experience in concrete structures.
8bfe38c8-2352-5d2c-91db-75d7ae097c94 | note | Freq - Each Lot
db67a5b6-19f1-5202-b7d6-7b404f06b95f | note | Key - H
97d6e547-e4c4-526d-97fa-dabf1e58f850 | note | Resp - SE
fa125d79-b93b-5b4e-b2c0-c5d8fb9a4aa0 | note | SI Key - H
f68724d9-a09c-56fc-b7ec-02a3055c6f16 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.14 - Backfilling
2687f90e-dfe6-5c81-aa29-3f9441959e64 | note | Ref docs - VR 610.35
53675bad-9c18-5a94-aa8c-9df043e72665 | note | Acceptance criteria - No fill material is placed against concrete within 14 days of casting in accordance with the requirements of clause 204.11 of Section 204.
5fc8ca5a-d881-58be-87ed-2874a7bff79b | note | ○ Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements of clause 610.16(l) or maturity testing requirements of clause 610.16(m).
2ad6e69b-1492-5d73-a179-325df7beee78 | note | Freq - Each Lot
739b180e-cafb-572f-9a76-c5fcaaa76293 | note | Key - H
f3afa181-e372-5f14-8dd6-02c72ef4cf45 | note | Resp - SE
cce40504-9cb6-5301-8707-518857a36374 | date | Inspection Date:
| section | 5.0 Completion
| checkpoint | 5.1 - As Built Survey
a72988bc-07e2-5216-a141-8281fbd8aaa7 | note | Ref docs - IFC Drawings Table 610.471, Table 610.472, Table 610.473
8275f40f-2788-5adb-b489-0e5b513f4274 | note | Acceptance criteria - Survey as built will consist of:
563a94cc-4b5e-5c29-beb7-e13f310844ae | note | ○ All surfaces satisfy lines, levels, thicknesses and cross sections as specified on the drawings within the specified tolerances.
0b1a9fad-55d8-5cef-9adb-dc7dc587b0bf | note | ○ The tolerances are as per Tables 610.471 610.472 and 610.473
f48eb498-ddeb-5886-976d-935b98a3b5ab | note | ○ For placing of reinforcement and post tensioning sheathing, this is +-5mm. For concrete cover, this is 0 to +5mm.
dbf3f8bc-48d1-5e39-8ff4-5c5ac194b677 | note | ○ Section dimensions shall be as per design drawings
53b609fb-41ef-5f0e-bcd6-73567e47efcd | note | Freq - Each Lot
01688166-abc8-5fde-aef6-1095d4827c82 | note | Key - R
cc359344-8651-5693-b4d1-fb0424faf079 | note | Resp - SE
0d568bf8-c74e-5268-9bac-e8cceeb26de1 | button | Remarks/record - Survey Conformance Report Attached | Yes,No
c219530a-6706-59e6-b13c-ec4701d8d09c | date | Inspection Date:
| checkpoint | 5.2 - Test Reports
dd4132fa-e25a-5197-945b-7e7fb4020c11 | note | Ref docs - VR 610
39bf70ce-139c-5bd7-b9e4-593160197aaf | note | Acceptance criteria - All Test reports received and Reviewed.
7d4db588-751e-5d15-99bd-a652f9eb12d7 | note | Freq - Each lot
c2fd7845-472a-5331-b317-b6adf362037a | note | Key - R
af5e83bb-37e6-5f55-8ece-418fdebf3889 | note | Resp - SE
22399c2c-d928-5b86-aecb-0c9ceab52040 | button | Remarks/record - NATA Endorsed Test Reports | Yes,No
83b41a74-d9e0-54f6-b5e9-0c10115b900a | date | Inspection Date:
| checkpoint | 5.3 - Temperature Data
29437fce-40c8-55ed-8ecb-4644cd4924bc | note | Ref docs - VR 610.22
50fdc6f6-68cb-5374-b622-faf13abaccf6 | note | Acceptance criteria - The maximum internal temperature of all concrete members following concrete placement has not exceeded 75°C.
ed42b632-592a-5b8d-bec5-2374a58016e2 | note | ○ Except where justified by analysis and testing, the temperature differential across the concrete member being constructed shall not exceed 20°C during the period of curing.
07d74b80-98ff-59a2-a627-01f02b0a197f | note | Freq - Each lot
ad1a683e-6ac7-54cf-ab4e-46045a6b2dde | note | Key - R
8b549100-c474-5c79-9143-56dd0f0945a5 | note | Resp - SE
9f42f875-a88b-53b8-a75c-3f7bf3263387 | note | Remarks/record - Thermal Data
bd2f0ca7-012b-5060-b79e-67a717e7363b | date | Inspection Date:
| checkpoint | 5.4 - Product Non-Conformance
b979b209-0d1e-5ec3-934e-290595923452 | note | Ref docs - CQMP
698ea578-8e27-5dc1-9e57-8dc11c232526 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
f53804d0-11bb-5e45-a1d3-ba88753ce76b | note | Freq - Each lot
c582c2a4-f7ed-5000-8417-1c01dc6c80d7 | note | Key - R
a665caac-a2dd-57d5-a28b-b4eca74caeef | note | Resp - SE
5409ef02-2475-5aff-ae94-7a1a35c7a00c | textbox | Remarks/record - NCR No:
39089835-cc9e-5430-93af-71caca14e3af | button | NCR reports | Yes,No
708ccbc2-8784-54b6-900a-cf3f2a24ae39 | date | Inspection Date:
| checkpoint | 5.5 - Quality Representative to check the above criteria and records to confirm
91ca28c0-22a9-5ddd-a0fb-8e61b89ffcbd | note | Ref docs - CQMP Lot Records
c39108bf-ec19-5565-b1aa-d9125a9eae7b | note | Acceptance criteria - All above criteria met, and records identified attached.
4bb45156-350a-5baf-bee2-c8a9a27e6d32 | note | Freq - Each lot
acfc631c-0cde-57a5-8a16-87232feddcfb | note | Key - R
5b2401ff-8139-5d6a-a336-e9dcce4e573d | note | Resp - SE
91d860ab-88bc-5f2d-a982-9ea9eef77a6f | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
ad08c9c5-0b42-5050-931c-271fcf8a108c | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0028 Installation of Precast Elements | itp | 1630-P200-SYM-QAC-ITP-0028 Installation of Precast Elements |  |  | 27fc9f0f-1535-424c-8f26-45eca55b11cc
| section | ITP Details
| checkpoint | ITP Details
c69c81ee-a9ba-5a3b-baa3-2824e363af33 | note | ITP No. - 0028
79c8678f-1b13-55f2-94b9-9bd57b2657d9 | note | Rev No. - 00
54d66f07-fafe-50e5-b615-bbc9f2af63d1 | note | Date of Issue - 06/02/2024
5ed73db3-a9e8-5ca8-866c-7d444fd2bf26 | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Survey & Set out
b661fd9a-2dd5-5644-9238-188ab3de5d28 | note | Ref docs - IFC drawings
0bbc0a77-6dd6-5818-9544-e59cc9543fa8 | note | Acceptance criteria - Limits of work areas / chainage / landing points clearly marked out
8c9d699b-22b2-566b-a3c5-010bcd0eb217 | note | Freq - Prior to start of works
8a78e66a-6e3b-552c-a1e6-27718dae4ace | note | Key - R
589a568a-27cb-5215-ba87-459a5ecf57c0 | note | Resp - SE
| checkpoint | 1.2 - Working Platform (as required)
b93dcda7-d0e7-5009-ac12-0d3b3883c4ed | note | Ref docs - Geotechnical Recommendations
579ca4f3-37f4-5143-8c36-a4e4eed635a2 | note | Acceptance criteria - Working platform prepared in accordance with Geotechnical recommendation
644f0566-104b-581b-9cff-3e0e4bf88fd2 | note | Freq - Prior to start of works
75488afc-8906-5581-857e-1828bd330844 | note | Key - R
8a17e689-093d-54c0-b05c-aefa9dbe17ff | note | Resp - SE
| checkpoint | 1.3 - Completed lift Study / Approved lift plan / Critical lift plan
e371bd81-98a0-51ee-88f3-85d7e6e8865c | note | Ref docs - VR 620.07
b746ba4c-d629-5a23-848a-b7d122f61a7d | note | Acceptance criteria - Lift study / plan to be prepared and approved by 3rd party engineer with relevant state requirements. Min 5 years’ experience.
a5e0320f-afbc-5009-bcf7-d1b6c7a7623f | note | Freq - Prior to start of works
23d04d54-bd3e-5974-a2f5-f4dc2e7c7446 | note | Key - R
56cc8d34-0a0b-5907-a93f-08f6c2a74163 | note | Resp - SE
| checkpoint | 1.4 - Approved Temp works
0eb497aa-2c15-58bb-b7f6-1fd3cf62f022 | note | Ref docs - Design Recommendations
0af77b65-d10f-51aa-bb44-6591d58575db | note | Acceptance criteria - Temp works used in accordance with temp works IFC design
69c13042-3b9e-5e45-8d79-e8ab1fbe2099 | note | Freq - Prior to start of works
46581ca5-4c64-5a35-adb2-171a942293da | note | Key - R
a358b953-9e4d-57ff-ae54-dd3c96f067e8 | note | Resp - SE
| section | 2.0 Element delivery
| checkpoint | 2.1 - Birth certificates
11c4fcf1-23f4-510b-b6a1-e01c6dceef38 | note | Ref docs - Vic roads 620.09
0e2effd4-3335-5d77-89ae-a7f019c7028c | note | Acceptance criteria - All manufactured precast concreate shall be traced from the completion of manufacture to the final location by a unique identification number.
f856dbb8-80a0-5851-bf21-28ba3923e7d0 | note | ○ Precast elements to be supplied with a birth certificate matching to the ID number of the element to ensure traceability.
86854708-79c5-52e5-99aa-4f335618fad3 | note | Freq - Each lot
9e0bbeaa-ca1d-525e-b2b5-e6ee4a87779e | note | Key - R
d273358f-4822-58c2-b7a3-af8a227027dd | note | Resp - SE
| checkpoint | 2.2 - On-site inspection
078b9d60-2996-5a77-923c-70f44e96090b | note | Acceptance criteria - Precast elements are clean and free from defects. Date of manufacture & unique ID numbers marked on units. Units transported after 7 days from casting. Visual inspection for signs of defects/damages during transport.
45aeac71-9b0f-5f96-88bb-ad0f517a974e | note | Freq - Prior to unloading
5f38b718-fe44-5cf5-a869-ae7667de3648 | note | Key - I
dbc4410c-c0ea-5309-9c27-6d55f4eafbbe | note | Resp - SE
| section | 3.0 Installation of precast element
| checkpoint | 3.1 - Handling of precast elements
b1cc6839-a986-59ff-a465-9073d2628e97 | note | Ref docs - VR 620.07
d872c271-f6f7-523e-ab5d-996e8739c8fe | note | Acceptance criteria - Handling of precast elements via designed lifting locations with appropriate lugs/clutches
230032fb-946c-5ba8-8d4a-611db1a94999 | note | Freq - Each unit
be121d81-4a7f-57bc-8143-29e7202822ee | note | Key - I
ab6fe690-103f-5497-88e9-c7ced4e8e104 | note | Resp - SE
| checkpoint | 3.2 - Erection of Beams and other Precast Units on recently poured underlying concrete members
4bc5cd0f-4546-5413-920b-720229fddcdc | note | Ref docs - VR 610.27
7c2829a2-2c10-52d0-bd6f-18ad43620073 | note | Acceptance criteria - Prestressed and reinforced concrete beams and other concrete members shall not be erected and landed until the specified 28 day concrete compressive strength for piers, abutment, deck or pile caps has been achieved.
82ae0b43-504d-5bd3-8f3c-ef05d6b64f9d | note | ○ And not before 14 days after casting or as required by the relevant design package.
d93cde27-13c7-5734-a5d8-87e3f05a9dde | note | ○ Beams shall not be placed until at least seven days after the pedestals have been cast.
67f0e368-a852-5cbb-bc77-249095e8374c | note | ○ Any relaxations from the above requires approved RFI from designers as well as consultation with MRPV to proceed.
bf20e823-bb6e-5535-a34a-6b76e9de8f06 | note | Freq - Each unit
347248e5-d95b-57f3-b7e8-31db55dd64a8 | note | Key - R
d8685209-f98c-5392-b349-52c295dd89d8 | note | Resp - SE
| checkpoint | 3.3 - Lifting of Precast Element into Place
c8850742-3871-5aed-9476-18797b65231b | note | Ref docs - VR 620.07
e9ab79ee-012d-5bda-939a-ce74eb55a1a5 | note | Acceptance criteria - Precast elements placed in accordance with drawings and survey set‐out points. Lifting clutches approved for use
eeca9175-8539-524d-8bce-50251852256c | note | Freq - Each unit
1b990ea1-7026-5702-b05a-4b2f5ae2c98c | note | Key - R
72439fc8-29e3-5135-893f-c44199cf6fa3 | note | Resp - SE
| checkpoint | 3.4 - Propping / Bracing of Precast Element
e11d1a02-c2cd-5c59-918e-dd3ca446e2bd | note | Ref docs - Design Recommendation
60e0d72d-870e-5293-9e47-016300bbd0d7 | note | Acceptance criteria - Propping used in accordance with design recommendation and manufacturers specification – not to be removed till element cast in place with stich pour
f47bbbf1-fcad-5877-aa96-52430a7d2128 | note | Freq - Each unit
c2b1950c-2030-5f64-b974-a5a8551bba64 | note | Key - I
25347dda-85f0-57e6-b382-390e22d4c1a3 | note | Resp - SE
| checkpoint | 3.5 - Secure Precast element against slipping
bfd5dcf3-ddf9-5453-9d2e-06cfe59947f6 | note | Ref docs - Design Recommendation, P
2b216601-bc37-51be-af11-16bede626648 | note | Acceptance criteria - Precast element secured against slipping as per design recommendation – not to be removed till element cast in place with stich pour
51589aaa-839d-5374-beda-b3339bdf1a8e | note | Freq - Each unit
f8adc4bb-186f-5bd3-8a67-c04c2ca06671 | note | Key - I
93470c93-0e17-5c73-8f5b-3458c901c56a | note | Resp - SE
| checkpoint | 3.6 - Grout Infill ﴾where required﴿
b20994bd-fd0e-577b-ad2e-20a0db4f952a | note | Ref docs - Design Recommendation, VR 610.33
79048f7b-c82b-5b53-8244-8138b742be99 | note | Acceptance criteria - Grouting placed in accordance with design recommendation; not to be conducted till element secured in place with stich pour, and sealed against leakage.
204fbd6f-4866-562f-9def-6fd993a54a44 | note | ○ Grout used to be approved & appropriate for use.
b00baccc-6f0d-52bf-ba00-9baeeddc6d71 | note | ○ Test cubes taken in accordance with VR spec
95976361-90c1-57cd-8f66-c221000c1698 | note | Freq - Each unit
f2c6f136-ece0-569f-af73-9b228e629371 | note | Key - R
3edccc54-5dbd-5ecc-b2c6-25a35820939a | note | Resp - SE
| section | 4.0 Work Lot Close Out
| checkpoint | 5.1 - Survey As-built
f62f611a-7b10-57f5-b2e3-119621c6b5cd | note | Acceptance criteria - As‐built survey is within tolerance when compared to design specifications. IFC marked up with redlines.
94a0337e-20ee-52e6-9fe1-961ce97235ce | note | Freq - Each lot
13d3a886-6420-5a73-91a8-cd4d1fee0e20 | note | Key - R
d8475099-a4c5-5262-adbf-80034d13f5b5 | note | Resp - SE
| checkpoint | 5.2 - Concrete Patch Repairs (as required)
a614ecdf-a776-560b-ad8b-66aeca2626ad | note | Ref docs - Design Recommendation, VR 610.31
c1e4c332-5ab6-5af7-a113-7d38a10050a7 | note | Acceptance criteria - Minor imperfections not conforming to the class of surface finish to be repaired
444e73aa-db8a-523c-97af-80649d9c3236 | note | Freq - Each lot
7037d8ac-703f-564d-842b-430fc34b27ea | note | Key - I
ae0e0f37-c498-5808-ae35-e6c2c39cf30c | note | Resp - SE
| checkpoint | 5.3 - Final Inspection with Subcontractor
552f4273-5849-59ee-b5d5-11fd428549b0 | note | Acceptance criteria - Works completed in accordance with approved drawings and any relevant specifications
c3d69bff-6298-5302-8e6a-66fa3360faa2 | note | Freq - Each lot
82f2b4d5-d9d4-5b4c-a91f-029270b04ca7 | note | Key - I
3d422b2e-34e5-5eaa-9fb4-3bf9e21f143a | note | Resp - SE
64617ba8-873b-595c-b5a7-302e7133973b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checkpoint | 5.4 - Product Non-Conformance
d02ea85a-7aac-5015-ae56-c6633099240e | note | Ref docs - QMP
1dbef5be-3e88-5169-b8d7-1f5791e224e4 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
89baf102-9aa3-5a9c-906f-a1178b23ebd6 | note | Freq - Each lot
5c148a0e-6707-5f14-8ff3-f99f08633ada | note | Key - R
a6115cc4-7b3c-5cf8-976d-d323b3c7a45c | note | Resp - SE
0228810e-da2d-5283-acc3-6a36b6e36512 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NCR reports
| checklist | 1630-P200-SYM-QAC-ITP-0029 Manufacturing and supply of precast elements | itp | 1630-P200-SYM-QAC-ITP-0029 Manufacturing and supply of precast elements |  |  | c6580fb4-c5cb-42a5-8d99-e4811d39be0b
| section | ITP Details
| checkpoint | ITP Details
1f87c093-89e2-5e3d-9574-da282fca501f | note | ITP No. - 0029
8c5e8cff-e3dc-5acf-8602-b955aeb8c0ee | note | Rev No. - 00
b6856773-b066-5a0b-8d0b-8c51f43d4a10 | note | Date of Issue - 15/02/2024
b18ffca4-c22b-593d-bebd-5951cf8b8d8d | note | ITP Type - New
| section | 1.0 Pre Construction
| checkpoint | 1.1 - Steel approval
edfde39b-a4c1-5b1f-a18c-436887d6fdf6 | note | Ref docs - Section 611 ‘Steel Reinforcement.
4ee33497-4402-533a-bd22-47ecd79f7f77 | note | Acceptance criteria - Manufacturers and suppliers of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Certificates to be provided prior to use in elements.
66abc449-ff4e-5f4b-84f0-ee896fa05944 | note | Freq - Prior to start of works
5ba151bd-c608-5712-940a-b20143bc66a3 | note | Key - H
83709ee7-692c-5edd-be36-906b7f7e4f04 | note | Resp - SE
4b8df337-4e90-58ad-b3e5-dc0234ea68f2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a90e66bd-4924-589e-8727-cfa9c859d6f1 | textbox | Steel Certs:
| checkpoint | 1.2 - Concrete approval
a5708e16-3fa3-5b3f-aa36-c127e17a1f69 | note | Ref docs - VR610.07, AS 1379
6f8ef0d1-4997-5e6c-ae0b-ec7c5cbd341d | note | Acceptance criteria - Concrete mix design to be approved by the Superintendent.
097ae391-387e-5830-8561-9c1262768585 | note | Freq - Prior to start of works
56776138-0c80-563e-9a5c-d58a05a9d009 | note | Key - H
40b6d58c-ba49-5da6-bbdb-57e9914e01e6 | note | Resp - SE
21976578-f1eb-529f-b82a-14accba68725 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bebbcef7-7455-5e9a-82a6-58c3483ba3b9 | textbox | Mix Design:
| checkpoint | 1.3 - Shop drawing approval
48ce815d-d8d7-5210-8ffd-b15bdf6edb6f | note | Ref docs - IFC drawings
9502778a-9d56-5cf0-b3ab-9715b292a8ee | note | Acceptance criteria - Shop drawings have been revied and approved per IFC design. Shop drawings to be uploaded to Team binder.
c4565268-ad12-5352-a6b1-8792b2ac1ced | note | Freq - Prior to start of works
28582bf4-9ada-5b53-87e2-abfa26f39695 | note | Key - H
0f7a6e23-053f-5344-bd83-c9db5692993a | note | Resp - SE
7f33848f-270a-58b9-8f0f-133db5872f0c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
67e60820-5213-5dd8-8d79-82b286ad22f8 | textbox | RFI Number:
| checkpoint | 1.4 - Curing methodology
59c729b0-766c-5838-a29a-eb5d48c02616 | note | Ref docs - VR610.23
94a4cb56-0e58-53a7-9402-794f7719bd62 | note | Acceptance criteria - The Contractor shall submit to the Superintendent for review, full details of the proposed methods of curing, as part of the concrete mix design submission, not less than four weeks prior to placement of concrete. The Contractor shall not proceed with the placement of concrete until the curing method(s) has been reviewed and approved by the Superintendent.
eb3109bf-922f-5a0e-bec1-c355f169825e | note | Freq - Prior to start of works
a593d7a3-4b91-55d5-944d-de2879f481ea | note | Key - H
8bfa54b7-5570-5a44-b53b-09aaeadf4ca4 | note | Resp - SE
| checkpoint | 1.5 - Birth certificates
e02eb164-f101-500b-801a-9294cda95a68 | note | Ref docs - Vic roads 620.09
a83ed6fd-90fc-5fd0-a369-e24e13822c89 | note | Acceptance criteria - All manufactured precast concreate shall be traced from the completion of manufacture to the final location by a unique identification number. Precast elements to be supplied with a birth certificate matching to the ID number of the element to ensure traceability.
fe97c4c5-ced4-5f26-b0f6-0722d45cad06 | note | Freq - Each lot
7872c488-236f-5aa3-8a66-2df6d9831309 | note | Key - H
d5b3971c-cda7-5cda-8fd2-fb791e5408d0 | note | Resp - SE
dc4fc394-3124-5715-ac43-203d732b3a7b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
84adf0d9-79d5-5ade-97f0-ed4afc7da520 | textbox | Birth Certificate Number:
| section | 2.0 Forms
| checkpoint | 2.1 - Formwork
9e5afcc4-740d-51e7-81f1-452f8ffafbe9 | note | Ref docs - Section 610 ‘Structural Concrete
4c4db1e5-075f-5986-815a-4d6339d645ed | note | Acceptance criteria - The formwork shall be constructed to produce the finished concrete to the shape, lines and dimensions shown on the drawings, and in accordance with the surface finish and tolerances
73ee2f54-511d-549c-809c-492953cf0671 | note | Freq - Each lot
147307d4-73dc-5fcb-8b89-b1d5de5dfa11 | note | Key - I
f294009e-6e1b-547c-84e0-c66285e835ee | note | Resp - SE
| checkpoint | 2.2 - Void formers
c925d73e-511d-5c53-9991-a1270a963efb | note | Ref docs - Section 614
ec25698c-a7cd-5ba0-a21e-50521dea3366 | note | Acceptance criteria - Void formers shall be securely restrained in position vertically against the action of placing concrete and subsequent flotation under vibration. The void former shall likewise be laterally restrained against forces arising from differential pressures during placing of concrete.
e620fde2-5b38-53dd-adc8-10a385a9b50c | note | Freq - Each lot
679e95f3-4ebc-508b-81d8-e653b3306146 | note | Key - W
3bfd325b-17b5-57b6-bf6b-5d22de20f6a2 | note | Resp - SE
| checkpoint | 2.3 - Embedded ties
e1a33971-5818-5e7f-9f99-ba62e34d3bf2 | note | Ref docs - Section 610 surface finish provisions of
b6ef6f04-48dd-5a9c-863c-b1cf947443f8 | note | Acceptance criteria - The use of wires or bolts extended to the surface of the concrete will not be permitted except were shown on the drawings. Any embedded ties shall remain embedded and shall terminate not less than the specified concrete cover.
4df142d2-e588-53c8-a758-c39b86836f98 | note | Freq - Each lot
05d8008e-796c-5ce9-9d75-7c337580670d | note | Key - I
a447118b-dc4e-5cb7-836b-7334aa42609b | note | Resp - SE
| section | 3.0 Removal of units from forms
| checkpoint | 3.1 - Compressive strength
e0c418b8-c15f-5c36-b913-9d170fd73c41 | note | Ref docs - Requirements of clause 610.16(l)
b8b3b1ea-b581-5682-968c-0960845de306 | note | Acceptance criteria - Individual precast units with mass of five tonnes or less shall have a minimum concrete compressive strength of 10 MPa for removal of units from forms. For individual precast units of mass greater that five tonnes, the minimum concrete compressive strength shall be 20 MPa for removal of units from forms.
722ed97e-65af-5aa6-8802-c04070433ebe | note | Freq - Each lot
f1d70a95-1811-5704-9c2c-a50f4c88d971 | note | Key - R
96511f79-6425-58da-956c-5b048b5b39a4 | note | Resp - SE
| checkpoint | 3.2 - Minimum compressive strength
e974a0c6-77b6-5970-b203-ca5db272902d | note | Ref docs - Requirements of clause 610.16(l)
d45ad06d-72db-5baf-b19c-84fd64370325 | note | Acceptance criteria - Lifting of precast units at a minimum concrete compressive strength other than that specified in this clause shall be supported with structural calculations and maturity testing for estimating the in-situ strength of concrete in accordance with the requirements of clause 610.16(l).
4d170c48-3ca0-5a27-93cf-418f032f4111 | note | ○ The structural calculations shall be certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years’ experience in structural design.
681e0617-3f38-58fc-b84d-b6602fe254a5 | note | Freq - Each lot
5509fa2d-4fbb-54df-a108-93d792b19e28 | note | Key - R
3a6141d4-9447-54b7-a3c3-bc0b142ae9f3 | note | Resp - SE
| section | 4.0 Projecting reinforcement
| checkpoint | 4.1 - Projecting reinforcement
32d27e20-3596-5dcb-8db7-37dbccd9e1fd | note | Ref docs - Drawings 610, 611,614
754492c3-c929-559b-ac78-c7e5fefe246a | note | Acceptance criteria - Where shown on the drawings, steel reinforcement shall be left projecting for the purpose of bonding on subsequent work. Care shall be taken to avoid disturbing the bars during the specified period for curing of the concrete. Projecting reinforcement which has been damaged or dislodged or which is loose in the concrete will be cause for rejecting of the units.
ccbe5850-d500-5098-9f0e-7db48bc0da93 | note | Freq - Each lot
d540795f-c226-52f4-a3f2-cd13601b99c2 | note | Key - I
94f7682e-1b09-5edf-9fdd-15433e17ab30 | note | Resp - SE
| checkpoint | 4.2 - Continuity bars
21ed0242-29c6-54d3-87ef-7e867e4246e5 | note | Ref docs - Drawings 610, 611,614
64331e57-be61-5343-b762-ec973792942b | note | Acceptance criteria - Continuity bars shall be positioned within 3 mm of the positions shown on the drawings. The relative deviation of any two bars cross sections, taken at right angles to the longitudinal centreline of the unit over the projecting length of bar, shall be within 3 mm.
a86a775a-e061-5c17-bf7f-f0b537b81bb7 | note | Freq - Each lot
4049f689-06a0-5457-b5ba-a08b080685fa | note | Key - I
20af79eb-c26b-5c70-8ad6-c4fe82b78fc1 | note | Resp - SE
| section | 5.0 Marking
| checkpoint | 5.1 - Individual marking
b6a60553-9e7f-52d7-b480-fcf0a6ddda4b | note | Ref docs - N/A
7bd91ea3-68ff-52a7-bcab-1132c9cb21ae | note | Acceptance criteria - The identification number, date of casting, the manufacturer’s name or registered mark and the maximum mass shall be marked on every precast unit.
45393d4b-2d75-52bf-b4b6-e10f2d6788cf | note | Freq - Each lot
304eb06e-eae0-5d55-a868-6763a886b1fe | note | Key - W
2a65660b-8abf-5dbd-a69b-fb8927e3990d | note | Resp - SE
| checkpoint | 5.2 - Temporary marking
edba8c37-0f98-5a33-aa72-2e37e751c30a | note | Ref docs - N/A
d752c86a-f2c0-5925-97c2-57df463d19da | note | Acceptance criteria - Temporary identification shall be made on the top surface of the unit near an end, except for parapet units. Final marking shall be made by indelible marking material, using letters approximately 40 mm high. For parapet units, temporary identification shall be made on the broomed surface of the parapet as shown on the drawings. Final markings shall be made on one end of each unit.
75f93599-1795-56ab-b66f-21d5c88e843d | note | Freq - Each lot
3ffa3995-7062-536b-91b3-e173f0833281 | note | Key - W
29c3ece1-c65c-54fd-baf9-aa398c6d85cc | note | Resp - SE
| section | 6.0 Handling & storage
| checkpoint | 6.1 - Storage
0bb02d92-9bea-584f-a310-d3a456478d8e | note | Ref docs - Clause 620.07
b03e69e3-f713-591a-b928-c3293faa7436 | note | Acceptance criteria - Units shall not be stored in areas subject to flooding. Units shall not be stored within 10 m of existing or proposed overhead power or telephone lines, or over service conduits, drainage pipes or uncompacted fill.
96ab4fdd-35ef-5506-993c-c2b67ee2138a | note | ○ All beams shall be laterally supported. The lateral bracing shall be designed for 10% of the dead load of the beam at the mid height of the beam. Beams and parapet units shall not be stored in stacks.
5094695a-2bf3-5ad2-8100-0b9c834b254a | note | ○ Slabs, planks, and piles may be stored in separate stacks of identical units up to a maximum height of 2 m, or two units high, whichever is greater. Crown units may be stored in separate stacks of identical units up to a maximum height of 3 m. The upper layers shall be separated from the lower layers by suitable timber bearers in line vertically at the specified supporting points. Timber supports for upper layers shall be placed directly above the supports of the layer below.
2a74fdae-aa8e-5677-adf7-44aef7377c8e | note | Freq - Each lot
42eff167-8054-51fc-a018-7b45cb0cbc91 | note | Key - W
355fb708-8300-5310-9f21-d2385d0b31e7 | note | Resp - SE
| checkpoint | 6.2 - Handling
badfa9f7-a7e7-5078-aacb-fa02344261ef | note | Ref docs - Clause 620.07
7f5d3063-c8a3-56a0-86b0-e3784e19cb8e | note | Acceptance criteria - The units shall be supported on bearers clear of the ground. Bearers shall support the units over their full width and be placed perpendicular to the longitudinal axis of the unit. Unless specified otherwise, bearers shall be placed beneath the specified or approved lifting points clear of any sole plates.
032143c4-6c3e-5601-97e0-bf386ee437e6 | note | ○ The ground or space between the bearers supporting the units shall be carefully cleared and levelled to prevent the unit from being supported other than on the bearers. The bearers shall rest on a firm foundation, and adequate precautions shall be taken to prevent subsidence from occurring and to prevent the units bearing other than at the specified support positions.
8215a531-07ee-55fc-8100-ef503fdac940 | note | ○ Unless otherwise specified, precast units shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. The angle subtended by the slings and the longitudinal axis of the unit shall be not less than 60.
a7302f70-59c5-5e29-8907-dab5f236abc2 | note | Freq - Each lot
f1103ed7-2e40-5ca5-a5de-07b9fcf03fe9 | note | Key - W
42a55a1f-749c-5652-81a0-3a263b25d704 | note | Resp - SE
| section | 7.0 Transporting
| checkpoint | 7.1 - Pre transportation requirements
3f6698e5-ce7f-58f7-975c-a2129f6a623b | note | Ref docs - Clause 620.08
63c248ef-8e12-5044-bcc4-effff4389bf5 | note | Acceptance criteria - Units shall not be transported from the precast yard until specified 7-day concrete compressive strength has been achieved, and not before 7 days after casting.
3e05b91b-d03e-5ffb-b077-4fd7e58cee31 | note | Freq - Each lot
0b6dccc9-1d67-5477-9cac-12046fd7606c | note | Key - H
9af9778f-26b0-508b-9153-12f529ecc19d | note | Resp - SE
| checkpoint | 7.2 - Transportation requirements
f604e9d1-fee4-58b1-8d27-2f68acdc9326 | note | Ref docs - Clause 620.08
1a79a67d-0efb-53f7-9402-0cd92a5f7ecd | note | Acceptance criteria - Units shall be securely fixed to the transporter and provision shall be made to protect the units from damage caused by lashings.
8b5278c0-212f-5e08-a990-826f8c2e37b0 | note | ○ During transport of beam units, the Contractor shall provide end bracing and, if necessary, top flange bracing. Bearings and supports shall allow for longitudinal rotation of the unit in transport and have adequate width and bearing capacity.
450eee1c-22c4-5cd2-a916-79cd1a68d148 | note | Freq - Each Lot
c182672e-350b-5252-8041-250ec86a9d4f | note | Key - H
90a95c0d-5fce-549f-97ba-6ac8dd6ec691 | note | Resp - SE
| section | 8.0 Work Lot Close Out
| checkpoint | 8.1 - Product Non-Conformance
1cd616fe-797c-5adc-abe5-121fe2b1f651 | note | Ref docs - QMP
09d69fb5-8e7f-5f01-a9ac-a28c69bf9257 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
782f7df0-d017-53c6-b9a0-2131b6e13336 | note | Freq - Each Lot
3a6ccded-ae6f-531c-93e7-ce1fa6eed85f | note | Key - R
098b5492-04fd-59bd-a6a8-169988fb01c8 | note | Resp - SE
| checklist | 1630-P200-SYM-QAC-ITP-0031 Installation of Steel Beam Guard Fence REV1 | itp | 1630-P200-SYM-QAC-ITP-0031 Installation of Steel Beam Guard Fence REV1 |  |  | 75249422-f62f-44fb-8a56-a793f7edfbbf
| section | ITP Details
| checkpoint | ITP Details
c4cf6fc7-cd23-5d15-9416-6a149d0ccac6 | note | ITP No. - 0031
a8d9cf65-b2dc-5430-8bb3-384a47aba71e | note | Rev No. - 01
2f02dbb0-2982-55c7-b523-9fb8e8c1f049 | note | Date of Issue - 31/10/24
744f0674-20a1-537a-9e11-0402a7bb1498 | note | ITP Type - Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Safety
b56f74be-5986-5c41-8928-d4f498c544b9 | note | Ensure that the following items have been actioned:
8e7bfdd7-5ae4-53cc-926d-ef06d75919fd | note | – SWMS if applicable
3e91fcf0-a555-5c5c-94f9-5538f8f156de | note | – Plant Pre-start Inspection
f41ceac2-fcc1-5885-ac2a-d914b9969521 | note | – Service locations identified
755ac404-9964-5b2f-80d1-9411e5e50802 | note | – Traffic Management Plans (if req’d)
f124ba43-cd1c-57c0-b2c1-cc3b1125e8d9 | note | – All staff inducted
d8cf4678-220f-5c84-845c-2e6ddec95765 | note | Ref docs - SMP
bae21e01-dad8-59e8-b54d-04489dd4b470 | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
9d7c1369-1fc7-5f04-86d5-09f9146d5b40 | note | ○ Plant inspections completed and entered. TSA training completed. Pre-work briefings completed.
241e54a6-38ab-5bb5-9d79-16c836cdf55b | note | ○ Service Diagrams available and services located
52245dc5-f25a-5376-b43d-d54526bd00bc | note | Freq - Once (Pre-Start)
e30c26fb-5879-548d-a189-03aa9e35488c | note | Key - H
505e349d-ce32-5758-ba46-64bffe921484 | note | Resp - SE
9c720b84-7d74-55d4-972f-4c50e4488863 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
09d2600d-2752-5928-bbe4-ff44407ef36c | tickbox | Service map Attached
| checkpoint | 1.2 - Excavation Permit
126b0ea6-b64d-57a5-ae1c-fdb6bb12b1ea | note | Ref docs - SMP
6857678d-d78a-540e-888b-76d073f644ee | note | Acceptance criteria - All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services.
a1883b36-ea28-5ab0-8a4d-6f583ce81ef7 | note | Freq - Prior to start of works
ab03fd11-558a-5e53-8a36-0f5ff51a3256 | note | Key - H
4bbf1f47-e1ea-5b4c-b0a0-81862d7c6702 | note | Resp - SE
e1468907-dd01-5e62-8b8a-99e9d5d83124 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9dfb7829-4b7b-5d29-8b72-508cf399e52d | textbox | Permit No.
| checkpoint | 1.3 - Material Compliance – Steel
42b34f06-5ae8-5807-b5d2-09c08b36ebe1 | note | Ref docs - DoT Clause 708.05 (a), 708.05 (b), 708.04
113242ff-0420-5165-8e56-7228be2b19ce | note | Acceptance criteria - Submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
9cbc2c31-50c7-5e75-90bf-80cf8ca7f81b | note | ○ All testings shall be endorsed in accordance with the NATA registration for that lab.
53519f29-5c4e-5a07-a033-684082b00330 | note | ○ Only safety barrier products listed in RDN 06-04 shall be used
028c88af-f6af-5d99-ae1d-8ebdd623716d | note | Freq - 14 days Prior to start of works
e69140eb-2f69-521a-a60e-ab7236eeb9ab | note | Key - H
03ab242a-8037-5a57-a577-4473839a215d | note | Resp - SE
dadfa6ea-80d6-5077-9db7-0a57495f56fa | note | SI Key - H
e60ade6a-eb9a-53a2-8bbf-ec12e4d17fb7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
61fb8f46-3f4d-5686-9492-c366e02bb914 | tickbox | Compliance/test certificates
de28acb0-aad4-5117-ab7d-398c91d09b2e | tickbox | Action point & linked
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Material Compliance – W-beam Base Metal Mechanical Properties
02407f29-7a32-5d00-bf8f-b8221cb4f98e | note | Ref docs - DoT Clause 708.05 (a), 708.05 (c) (i)
0a9dc3ec-8c74-5a1d-aad9-6ffe04e14ab9 | note | Acceptance criteria - Below information marked on steel W-beams, posts at both ends and all plastic components:
eb605a67-62de-50b7-8567-f1b001bb9c6c | note | Name of the manufacturer;
a669a062-6190-50f4-b3b8-eeecc0305c0a | note | batch number strength grade and base metal thickness of the steel W-Beams
645efd19-9650-5df9-9997-219910223689 | note | W-beams to meets requirements of AS/NZS 1594 Grade HA350.
58270013-e863-5096-a76c-ed3aece8a715 | note | Mechanical Properties of Base Metal:
65deef76-9c6f-5792-9f79-5b8e6b96e1ab | note | ○ Min. Yield Strength: 350MPa
18b39685-55f7-52ec-bd23-4b91560654bf | note | ○ Min. Elongation in 80 mm: 16%
3b95e089-dee0-5e34-a265-4978ef00de42 | note | ○ Min. Tensile Strength: 430MPa
48dea0c0-ba36-5df0-842f-885aae9bc190 | note | The base metal shall comply with the following tolerances when measured in accordance with the methods of AS/NZS 1365
f0400b2f-6fcc-58ba-90bc-bcfac726c4be | note | ○ Base metal thickness 2.7 mm +0.21 mm or -0.10 mm
001e3327-4bad-5072-8dba-5c381ee5b84c | note | ○ Mill camber tolerance on 2500 mm length 10 mm max
479e36bd-1e61-549b-acc1-43ed33ca2be4 | note | ○ Mill tolerance on strip width +2.5 mm, -0.0
20ad1f11-69b7-5c5b-a1b8-ae1cf987e42a | note | Freq - Prior to start of works
f81c6eb5-b74a-527c-adab-77b344500109 | note | Key - H
6734ff39-dfc1-5068-bb8a-2ccc7fd93e31 | note | Resp - SE
caf16c4e-494e-5496-96f8-5a38b1e9f3fe | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
51a2ebf6-ada2-5460-b011-00210d6760a6 | tickbox | Compliance/test certificates
| checkpoint | 1.5 - Material Compliance – Steel Posts and Blocks
8819b16c-9dbe-5cc5-809d-fbbf50471147 | note | Ref docs - DoT Clause 708.05 (c) (ii)
ec5aec3e-e9e9-5178-b476-17bd9b94c6d5 | note | Acceptance criteria - Manufactured from steel which meets AS/NZS 1594 Grade HA250
39b6c1c4-30a5-5985-aaf6-c430ec428101 | note | ○ Base material thickness shall be 6.0 mm +/-0.27 mm.
a18585d0-241b-538a-a1f7-19cb4575db8a | note | Freq - Prior to start of works
a2d11dbd-bc30-521e-badc-c9b3071069e5 | note | Key - H
8e43dc49-398f-5b71-8e1c-87ad07b88a13 | note | Resp - SE
03881395-0e90-5474-9ef9-0b5af8df3af0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
de822c86-bb56-572f-9778-bcf22fe5b917 | tickbox | Compliance/test certificates
| checkpoint | 1.6 - Material Compliance – Terminal Sections
158e70cc-24a8-5191-871a-2c38eccce367 | note | Ref docs - DoT Clause 708.05 (c) (iii)
f2d1ebd9-54bc-513c-ae97-1daa6069b6b1 | note | Acceptance criteria - Manufactured from steel which meets AS/NZS 1594 Grade HA350
2d82e84f-cffb-5c74-9e3a-e8d5c5d78e00 | note | Freq - Prior to start of works
a8ea9490-cb71-58ab-8f9c-2982b7db9126 | note | Key - H
be4fbfb1-d0ea-5d01-9942-a92c232d4679 | note | Resp - SE
730792a6-de1a-5203-ac37-5aee7fbde2dd | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bb496613-bfab-5bad-ba32-71288b2d9b74 | tickbox | Compliance/test certificates
| checkpoint | 1.7 - Material Compliance – WRSB
e2a66f9b-b321-5cfb-9185-2f284d0fc11e | note | Ref docs - DoT Clause 711.05
8f604a16-40ac-5121-a3ce-fa2ad7ae4401 | note | Acceptance criteria - Submit to the Superintendent for review not less than 14 days prior to the proposed use of materials and components, a signed statement including relevant test reports demonstrating the compliance of the materials and components with the specification for the proprietary WRSB system and VR711
eff89a46-1919-5f92-b54c-d9c019761956 | note | ○ The installation of the WRSB shall not proceed until the signed statement and certificates of compliance have been accepted by the Superintendent.
37775125-06f4-5b6c-841f-c0aa72eeacca | note | Freq - Prior to start of works
c6189d5e-10d8-5cda-b75e-aedc268a942e | note | Key - H
5151186e-a731-51a4-9a21-5334650c31d4 | note | Resp - SE
f9e2ebe4-f9b3-5c1e-937b-c75cf1493bf1 | note | SI Key - H
5cd1b5d8-150d-59cc-a02f-01d7a8082854 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a308e073-0562-5bd8-8575-8845fd0abc52 | tickbox | Compliance/test certificates
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Protective Treatment - Galvanising
19fa5b38-ec83-5483-a498-2b2f98d745fc | note | Ref docs - DoT Clause 708.05 (d)
772c43d6-98df-5e0f-9ef3-89724590554f | note | Acceptance criteria - Treatment should be in accordance with AS 1627 - Parts 1 and 4 and finished by hot-dipped galvanising in accordance with AS/NZS 4680.
3c946d2f-67bb-5799-8335-c8cd463cd19f | note | ○ Hot-dipped galvanised coating on Bolts, Nuts and Washers shall comply with AS 1214.
aed85224-e952-5d86-a6e7-950b57c02e93 | note | ○ All galvanised coatings shall be smooth, adherent, and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Appearance is of prime importance and colour shall be uniform.
8b89236b-3652-523a-8dc4-956fe8894a3e | note | ○ Where curved W-beam of less than 45 m curve radius is specified, the curving operation shall be carried out off site in a manner that will not result in damage to the galvanising.
0246f86f-62b2-52a6-9b1f-acf2ad360abb | note | Freq - Prior to start of works
a55ce9e9-a9a7-5b9d-9c4f-0ef0e6b6f89a | note | Key - H
e9580467-d297-549b-8658-da0f85a8680e | note | Resp - SE
3135cc49-cbe1-5859-9a75-d668901ec702 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
ef1f3f0c-5719-5bf5-acd1-c633ece9f7ee | tickbox | Galvanisation Compliance/test certificates
| checkpoint | 1.9 - Protective Treatment - repair
3ae6d8da-7f28-5b6d-a457-e9496f1d572f | note | Ref docs - DoT Clause 708.05 (d)
6dd2df67-26b3-5d0d-acfb-df9fb0321826 | note | Acceptance criteria - Repairs to a damaged galvanised coating to be done with zinc-rich inorganic Paint with a minimum of 2 coats in accordance with AS 3750.9 and one coat of aluminium paint.
6af3765c-cdd0-59ff-a999-174fa39b4d02 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a977cd58-c635-5103-bfd2-993882a2e976 | button | Photo Evidence | Yes,No,N/A
| checkpoint | 1.10 - Material Compliance – Breakaway Cable Terminal
7aaeb42b-ddb9-5519-a5a6-dab94e347964 | note | Ref docs - DoT Clause 708.05 (f)
e1a9d132-b2ad-5253-8e81-6e1868da0907 | note | Acceptance criteria - The wire rope shall comply with the requirements of AS3569 and the details shown on Drawings.
727d1394-a87a-5a94-8b17-a805b9579b09 | note | ○ Wire ropes used in proprietary devices must comply with the manufacturer’s recommendations.
90c91ca0-26e0-5284-ac63-5528bf570235 | note | Freq - Prior to start of works
0ff273e7-159c-52ad-974c-2a5772ffbb84 | note | Key - H
3e92312d-43c8-5f3e-a095-d531790dcac2 | note | Resp - SE
88c0889f-56dc-54ea-9733-9f28016443fb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
54dfb0a0-6917-5262-ab29-88aa638af8f6 | tickbox | Compliance test certificates
| checkpoint | 1.11 - Material Inspection, Handling and Storage
3389ee76-eacd-5aad-b943-3602eac78131 | note | Ref docs - DoT Clause 708.06, 708.11, 708.13 IFC Drawings
d3a7b62d-643c-508d-8e00-4aa976be4230 | note | Acceptance criteria - Items are loaded, transported, unloaded, stacked, and handled in such a way to protect items from distortion and that galvanised surfaces are protected from damage.
820d3886-bef8-5169-a39b-e858f00b7f1d | note | ○ All materials stored to prevent damage and corrosion at least 200 mm above the ground on platforms, slabs, or other supports.
51694b40-dd40-555a-9ff1-686273d61baf | note | ○ Rusted, bent, or damaged steel shall be rejected.
30a8b8dd-9072-51ff-919b-f14b57061f70 | note | ○ If stacks located behind a serviceable road safety barrier system, the clear space must allow for dynamic deflection and proper functioning of the end treatments.
a67a0a75-a540-5193-ac82-996e47a7c98f | note | ○ Ensure that materials are in compliance with VicRoads specifications and IFC Drawings.
c0415847-ad4f-5b12-888f-35d98ef19957 | note | ○ Ensure there are no hard objects within the deflection zone of the barrier.
5558f5ae-fa02-50dc-8c1d-3604a690314b | note | Freq - Prior to start of works & Throughout construction process
fd0aec59-c682-5dba-9f9a-fec233456e8c | note | Key - R I
96c3a07c-8779-5c4d-9b9a-35ee9016f0a8 | note | Resp - SE
216174ae-46bc-56f1-bb91-977969de1640 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Incoming Material Checklist
| checkpoint | 1.12 - Pre-Construction Planning
53aa9b99-38ff-58f2-abdf-f147c48a2555 | note | Ref docs - DoT Clause 708.07 (a), (c) & (d)
db1e075b-9323-5e27-a2d3-2db666357bfe | note | Acceptance criteria - Plan and execute the work in a manner that prevents damage to underground and above ground facilities. Construct a guard fence to form a smooth line vertically and horizontally, when viewed along the line of the installation, free of humps, sags, or other irregularities, within tolerances.
2f408089-9ec3-5658-9274-8581dec6af31 | note | ○ Any component of a guard fence must not be welded, or flame cut in the field under any circumstances. Welding and flame cutting may only be conducted when shown on drawings in accordance with the manufacturer’s recommendations.
3e62a077-b6ee-5a54-bba2-590399dca194 | note | ○ End treatments and transitions commissioned at the earliest practicable time where the guard fence is being constructed on a road open to traffic. Temporary end treatments to the satisfaction of the Superintendent to be provided until the permanent treatments are complete.
f685f37a-d600-57a2-921b-2eb7bf8cd6ae | note | Removal of an existing installed safety barrier system includes:
5bc9ff55-3d73-5d30-95c5-a23c00cb7e6e | note | ○ Dismantling or demolition of safety barriers, transitions, and end treatments
b50b4d36-39ad-5ab2-a110-6c303a88ce42 | note | ○ Extracting all posts, anchors and other in-ground components and materials
d6897bed-b74b-52ba-a986-ed3681da48f2 | note | ○ Removing all components and waste materials from the site
c74c0aec-3165-5c95-9f1c-0e2311bb0efb | note | ○ Cleaning, backfilling and mechanically compacting all excavations and holes in 150 mm layers to not less than the density of the surrounding layers.
b6f2c501-c3dc-521d-874a-264e4220616f | note | ○ Stacking or disposing of components and waste materials
e4b85dc2-258d-5fb5-98e9-1148b3df309a | note | Freq - Prior to start of works
750283fb-7ae2-5137-9533-0d0e21112da2 | note | Key - I
2aa7c789-e15c-5f25-8836-bd66be9f1bd2 | note | Resp - SE
| checkpoint | 1.13 - Associated Pavement Shoulder widening
79b8eced-7c11-5f33-8ea5-7b3442116193 | note | Ref docs - VR 708.15, VR AGRD 06
ef751bbd-3ab6-519a-8542-823929c45c29 | note | Acceptance criteria - Where required, widening of the existing shoulder on the median or outer verge applications adjacent to locations where guard fence is to be installed, shall be completed.
050935ee-23c9-5239-8a27-1e2613ae599d | note | ○ The edge of shoulder shall be saw-cut to provide a neat straight edge against which the additional pavement can be placed.
ade2353a-ee6f-53ea-ab28-08b997729663 | note | ○ Pavement layers shall be stepped a minimum 150 mm horizontally to enable new widening to be keyed into the existing pavement.
5a206a14-c20e-5b0a-a778-e2134b5ad1b1 | button | Has the above been completed? | Yes,No,N/A
16f2f65d-487f-5044-9080-6465fc2815fe | note | Freq - Prior to start post install
3b3f9bd8-3bbd-5f67-aec7-ac540c439b43 | note | Key - H
28fee737-69f7-53fd-8338-73322beb68b1 | note | Resp - SE
569033c4-0bbd-5b88-b7fd-b6a3b98e234c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| section | 2.0 Post Installation
| checkpoint | 2.1 - Set Out
871b6392-ec0c-5930-8a59-0499001c81db | note | Ref docs - DoT Clause 708.08
a85e36e1-2ba2-5f66-9a2d-768f116295b3 | note | Acceptance criteria - Prior to installation, the required location and length of all barrier alignments are to be confirmed with the Superintendent.
a817ba2d-af17-5db5-8d9d-c5cae24ed1e8 | note | Freq - Each lot & Each possession
59c9626e-d88d-554c-bc62-a1ad5f004246 | note | Key - H
134e4889-ebad-596a-894c-32246ce149f8 | note | Resp - SE
b4d9ace9-7dfd-5a90-9cc5-199faeddada3 | note | SI Key - H
f8648611-5fc6-514a-8414-be42cdaae230 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Posts – Installation (Guardrail)
0be5b7ef-c449-52b6-a4a3-87709b14e847 | note | Ref docs - DoT Clause 708.08 (a), 708.08 (e), VicRoads AGRD
fae2942c-80a9-5377-990d-35f158891448 | note | Acceptance criteria - Installed to a depth not less than shown on IFC drawings/manufactures
96216321-8e00-55d9-8b20-526f6d6f9742 | note | ○ Posts orientated to the direction of traffic as shown on drawings.
39c058c5-a0a9-50e9-85b3-9854c898c1ad | note | ○ Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness.
4d0528f1-a171-521d-93f2-ca4b5a95aea4 | note | ○ If site conditions dictate that the posts cannot be driven, then the posts shall be installed in holes. The bottom of the holes shall be adequately compacted to achieve the same density as the surrounding soil.
6aa56b20-8bf7-58a2-a587-ca250b7316e9 | note | ○ Posts in rock – 75 mm clearance from back of post to face of the hole.
4e19b36d-cd18-5149-b2b8-8c69fc4c8e96 | note | ○ Posts shall be installed such that the back of post is not less than 500 mm from hinge point.
d614d932-78b1-5da7-99fe-3a85db4ac066 | note | ○ Refer to figure 1 at the back of this document for post offsets requirements.
eaa48549-38ef-5c8b-99e7-759248900cd9 | note | Freq - Each lot & Each possession
b5c3245d-ca21-5cad-9e51-f6c9a97d5bad | note | Key - I
f38b45c4-6b3f-5d6f-97f7-7aee9964c3ee | note | Resp - SE
c6f826f9-6c36-5c11-b3db-bda2924cf004 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| checkpoint | 2.3 - Posts – Installation (WRSB)
6cf59ae7-880e-522e-b95e-b5bbf27dea1f | note | Ref docs - DoT Clause 711.07 (c)
a9e01f99-2fec-5294-9200-a313c8555421 | note | Acceptance criteria - The Contractor shall install the wire rope and posts to the line, level and height as shown on the drawings, the specification, manufacturer’s specification and to the tolerances specified in clause 711.08.
f91f4145-dde7-5ffe-ab37-1d08bb452e40 | note | ○ Posts shall be spaced in accordance with the manufacturer’s specification unless otherwise required by the design requirements of VicRoads Road Design Note RDN 06-02. Posts shall be installed with their correct profile in the direction of travel.
52c9baed-2ef9-5ef4-a802-571f573c2b67 | note | ○ The vertical alignment of the wire ropes shall be smooth and uniform, without sudden changes in gradient and generally consistent with the vertical alignment of the edge of the traffic lanes. The length of the post socket or overall length of the post may be adjusted in accordance with the tolerances specified by the manufacturer to achieve the specified vertical alignment. Any such adjustment shall be as per the manufacturer’s specification and obtained written statement of advice, which shall be submitted by the Contractor for review by the Superintendent.
3b6deebe-f0c2-5eda-8f51-5b54569e98c1 | note | ○ The WRSB shall not be installed until the set out alignment of the posts has been reviewed and accepted by the Superintendent.
bacb8e29-1dc9-5d05-9da7-d7f81339bd66 | note | Freq - Each lot & Each possession
3ab35f8b-e598-55c7-aa4e-cc4956a31b30 | note | Key - H
d61a821d-20a5-5054-b42b-6283a2efd3bc | note | Resp - SE
9665a323-fe83-5dc8-8dae-0dedb6e6c316 | note | SI Key - H
ef3e9306-c34d-5e23-93a6-a82768444670 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Posts – Backfilling
d74654a4-bf9c-512c-819e-b11ac2d3e95b | note | Ref docs - DoT Clause 708.08 (a)
81771165-2438-5d25-ad3a-d74e2248a8d0 | note | Acceptance criteria - Posts in rock – Except for anchorage posts, post holes backfilled with a granular material.
402192cc-9c03-5c59-bae9-c3f8c94ad932 | note | ○ Other post holes backfilled with selected earth, free of rock.
c1c7380e-3109-51c9-8757-bf7d5cb4a8a0 | note | ○ Backfill shall be firmly compacted not exceeding 100 mm compacted layers.
bc4807ea-b482-5e9e-9bd2-d51e8ebf1b53 | note | ○ Posts in paved areas shall be backfilled 50 mm below underside of such paving and remaining depth filled with paving material.
eea17ced-d858-583d-896b-c34a113524e7 | note | Freq - Each lot & Each possession
4b9b5274-5870-5894-a370-0dfba958209b | note | Key - I
2d0f01d8-bc69-57b7-b853-288cbf2d2951 | note | Resp - SE
e467981c-54f1-5fef-99b2-7efb7be420c3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| checkpoint | 2.5 - Post – Foundation (Displacement Test)
37f1335b-36f6-57ad-b350-973216007601 | note | Ref docs - DoT Clause 708.08 (a)
b6b990f2-1600-5784-a395-58b6ceb1f0c5 | note | Acceptance criteria - Foundation displacement at ground level not to exceed 3 mm when a 1 kN. force is applied 200 mm below the top of the post in any direction.
3ed2f395-e697-554f-8e9d-50561991e156 | note | ○ Any failing post shall be rectified and retested plus one similar post within 5 m.
e64f80af-a20c-5fed-8a10-3d52b5f2e0d1 | note | ○ Rectification to be completed via re-compaction of material surrounding the post and/or removal and replacement of the post.
2017d560-40f0-5c58-841d-2613b7af6db4 | note | Freq - Each lot & Each possession
6273f132-ad47-5d41-a059-fdf5c80b6e43 | note | Key - R
f0cc14b4-960f-57fc-9477-31bd44c6f0da | note | Resp - SE
47db4e83-abc8-5b62-809c-95bcf8c05665 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Records
| checkpoint | 2.6 - Non-Standard Post Lengths
983c873e-73f3-5650-aa8a-73d343e22e72 | note | Ref docs - DoT Clause 708.08 (a)
0c47bc19-0a4f-5faa-9828-9bb10c73eae6 | note | Acceptance criteria - Where non-standard post lengths or other special measures are required (e.g., Shallow Concrete Foundations), details to be provided to the Superintendent.
276ab8d3-41c2-571b-8631-2a2446084958 | note | ○ Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre- qualified consultant.
1d09d70a-f063-580f-ad5e-a979721b202d | note | Freq - Each lot & Each possession
1583ec16-79df-53bc-a8c0-79576d21ae2f | note | Key - H
a6ddae76-9bc3-5a99-8745-f3889de5b3d3 | note | Resp - SE
e0f13893-2fcb-5493-ad91-72e0c89ac619 | note | SI Key - H
0a927d6e-06d1-5732-ab8e-3b93d127c043 | button | Remarks/record (eg. Test frequency reports, certificates, checklist etc) | Yes,No,N/A
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Bolted Connection In reinforced concrete beam
d27df47b-5ab5-5ab0-9270-c3590e86e258 | note | Ref docs - IFC Drawings VR 670, VR 708
ff8b5a1b-f1c4-5616-a83c-dcbcac214b4f | note | Acceptance criteria - Where posts are not required and guard rail is installed directly onto reinforced concrete:
2d55439b-d9e3-5aba-a744-3daee671341b | note | ○ Confirm bolt size and grade are as per IFC drawings.
3764a933-f2a9-557e-8e15-0dd89d51841b | note | ○ After the barrier has been installed and all connections made, the gap between the base plate and the top of concrete footing shall be completely filled with a flowable dual shrinkage compensating proprietary cementitious grout.
13476774-0353-5361-b701-72087de44f04 | note | ○ HP - Railing posts shall not be grouted until the Contractor provides a Survey Certificate verifying compliance with the specified tolerances on lines and levels.
8ebaaac3-34c6-53b3-b273-4eee2b6de4c6 | note | ○ Where Welding is required, welds shall be completed in accordance with “RAIL SPLICE DETAIL” as per 1630-P200-SYM- SBR-DRG-0461.
238f89c7-304c-566c-81ad-2fbb6697548c | note | ○ Where required, all damaged galvanised coatings to be repaired.
372cf115-d66a-588e-9ba5-00debae456c6 | note | Freq - Each lot & Each possession
2fa2dc5e-1d60-5cb1-937f-8f3353c52878 | note | Key - H
4c84e448-f18f-5f21-a619-b35d17e36702 | note | Resp - SE
8d9ec5c5-ff9f-5e91-960a-ba97ee15b7f5 | note | SI Key - H
1e88fdcb-38a5-5a20-a6cd-59d0418b33eb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Survey Conformance Check □
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Guard Fence and WRSB Installation
| checkpoint | 3.1 - Guard Fence/Rail - Installation
c96fbdbe-cbc3-503c-8d11-0e6e041f542b | note | Ref docs - PS3060.06 (X) DoT Clause 708.05 (d), 708.08 (b), 708.08 (e)
3447a693-1794-5b3c-914b-e47f732118dd | note | Acceptance criteria - Guard fence shall be installed at the offsets shown on Standard Drawing SD 3502 or as directed as per the IFC drawings
37dd420a-505b-5451-ad91-92bdee40c302 | note | ○ Guard Fence/Rail sections lapped so that the exposed ends face away from near sided approaching traffic.
57b22ca6-0dce-5351-b890-0afa504e78f1 | note | ○ Edges of guardrail fixed in contact with post or post blocks.
c46d1007-5e08-5ee6-b2ed-fc87edb4ed6d | note | ○ All bolts fully tightened.
0d7e056d-4537-55ac-a657-58aa09026ec9 | note | ○ All bolts on the traffic side of w-beam installations shall be flush with the w-beam.
897fe2f8-9427-5870-8925-a23bb3822449 | note | ○ Posts attached to bridges or culverts shall be bolted to supporting members as shown on drawings.
3af7b429-4a51-56ee-aea8-02e7345a8f9f | note | ○ Where radius of curvature is 45m or less, guardrail sections shall be curved to shape prior to delivery to site.
81867584-8c63-5644-a7f9-5ccf0cff2879 | note | ○ End treatments constructed in accordance with the drawings.
8ac5c623-34c5-54b4-86d8-0916b58f5008 | note | Freq - Each lot & Each possession
941e30a5-6883-5286-adcd-08ddcca6cab0 | note | Key - H
eec9b14d-a671-556f-97e5-d6b8967908c2 | note | Resp - SE NA
19fc00ed-c0ce-5391-9a0c-c15ff4d99e56 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Subcontractor Records
| checkpoint | 3.2 - End Treatments
24e3b36d-558b-5e52-88f4-2001b2c55d5d | note | Ref docs - DoT Clause 708.08 (c)
f7235130-4c65-58e1-b825-13ef44b7b38b | note | Acceptance criteria - During installation of wire ropes in the end treatments of W-beam, ensure that no twisting of the rope occurs.
8aa6fa8f-bfcb-5a00-a24c-55a79531c9f8 | note | ○ The anchorage cable shall be tightened sufficiently to remove slack.
86242746-0772-58f8-b320-6e2fc12ca3f2 | note | ○ When rope assemblies are used, the nuts at each end of the rope shall be tightened to a minimum torque of 50 Nm on the assemblies or as per the manufacturer’s requirements.
5ec59fa2-b3d8-582e-9a18-015ca87562e5 | note | Freq - Each lot & Each possession
7769bb1d-cc16-5a16-be87-bad6d351d527 | note | Key - R
26d49f72-f4ec-501c-8ae2-d24c87ca0dfa | note | Resp - SE
a6e54b21-9b16-5ab3-bfa3-9c45c75ca84d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Subcontractor Records
| checkpoint | 3.3 - Concrete Anchor Blocks (WRSB)
e584ea16-6116-55b8-9544-96f96d4e9166 | note | Ref docs - DoT Clause 711.07 (b) (ii) (iii)
a7898ba6-cfc2-59b5-b87d-094ab5de6e6e | note | Acceptance criteria - Anchor blocks and post foundations shall not be constructed until the design and manufacturer’s acceptance has been reviewed by the Superintendent.
04ec84d5-463c-5f28-95bb-aa2f55998d3b | note | ○ Anchor block foundation and post foundation holes shall be free of loose material, debris and water prior to the placement of concrete.
3b6490d6-756a-5e74-af3f-f6f64c4c81b4 | note | ○ Further to any installation guidelines for construction of anchor blocks for a proprietary WRSB system, the Contractor shall form anchor block holes by excavating the hole to the correct dimension, shape, level and alignment specified by the proprietary system.
79ea2f51-365a-5a6f-a876-bf66e05ff336 | note | ○ Over-excavation of the anchor block excavation shall not be reformed with form work or soil, but shall be cleaned out and filled with concrete forming the concrete anchor block.
e2ed4fdd-1b46-51bb-8bb1-062ced10d3f3 | note | ○ In situ concrete post foundations shall be constructed using N25 strength grade concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 711.04(c).
8f6f636b-6bea-59e0-8085-73eff0ef094d | note | ○ Notwithstanding the specific proprietary WRSB system requirements, the anchor blocks shall be constructed using N32 strength grade concrete or 32 MPa geopolymer binder-based concrete conforming to the requirements of clause 711.04(c).
adad5ddf-5f12-551e-a4e6-d213edb09c65 | note | ○ All anchor frames, posts, sockets and reinforcing rings shall be positioned to the line and levels as specified in the drawings and shall be secured against displacement during placing of the concrete.
5faaa980-5218-57ab-8dfa-8480c5be4490 | note | ○ No construction joints shall be provided within the anchor block.
8fa6f7c2-2422-523b-a76c-d7f908433ab5 | note | ○ The finished surface of all anchor blocks and footings shall be shaped such that water cannot pool on the surface.
24b427d5-2ed2-58c5-a661-cdb08394debe | note | ○ Anchor blocks and post foundation shall not be cast until inspected by the Superintendent.
951de37d-39bc-52a2-822e-5c62fad11034 | note | Freq - Each lot & Each possession
e9bf20bc-7d9f-54be-ac74-8fa5011a69bc | note | Key - H
5ce443ab-03ea-5e93-9ffc-a18180498949 | note | Resp - SE
68acb83d-9673-571c-a047-dfe818cb1435 | note | SI Key - H
28d0b242-c4df-514f-ab04-b22ddc65b6e6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Concrete dockets Pre-pour inspection, Subcontractor Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - WRSB Tolerances
b51cbd73-6f45-5333-88eb-f1f9f1e3f55f | note | Ref docs - DoT Clause 711.08 (a) (b) (c)
bc50bed2-88f2-58bf-b08f-ff210d260e1e | note | Acceptance criteria - Tolerances for construction of the WRSB system shall be in accordance with the lesser of the manufacturer’s specification or as follows:
aa179f09-d62c-5715-8a24-929a50db4dac | note | (a) vertical tolerance on the height of the WRSB shall be ± 20 mm from the design line
97cbb610-537f-55e3-84f2-d8ddc77f1f40 | note | (b) longitudinal line tolerance for the WRSB system shall be ± 20 mm in plan view
b1e4a9b2-a592-5282-a4d1-d87361e26667 | note | (c) tolerance on post spacing shall be ± 25 mm.
af5257e4-549d-5119-91f4-36475f3f8303 | note | ○ WRSB height shall be measured from the road pavement when it is located within 1.5 m of the edge of pavement. For distances beyond 1.5 m, the WRSB height shall be measured from the ground surface at its location.
989edb61-dcf0-58a0-bfa7-bc9d1150ec1c | note | Freq - Each lot & Each possession
c48a5a68-13c8-590a-b771-ae212452e9ee | note | Key - I
1ec0980d-f939-5a62-8efe-ce0e193347b8 | note | Resp - SE
415a94e0-0d54-5803-93f6-8323f839b469 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| checkpoint | 3.5 - Height of guard fence/rail
e9fce4c1-ce38-5edd-8b50-eba6078451df | note | Ref docs - DoT Clause 708.08 (d), 708.08 (f)
0cd6d697-9bcb-50b1-a838-a6400374e6dc | note | Acceptance criteria - Top of Rail shall be within 25 mm of the specified level.
64ce80ae-bdc9-530c-9eaa-fbad07a0af27 | note | ○ Rail shall be within 50 mm of the specified line.
116b2422-2bb3-51ae-b657-f0fb0dff5bb8 | note | ○ Variations in line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
63855a71-37c7-5d33-b869-68808fb92473 | note | ○ Top of bolt head relative to w-beam -0 mm, +5 mm
b247ad24-99d8-5c56-a143-1ad062293f5f | note | Notwithstanding the above, the line and level shall be adjusted to provide a smooth and even vertical and horizontal alignment.
19c9197f-0f15-56e7-8ba8-c397a380d5f2 | note | Guard rail install location:
7e6d7a8a-3af4-5cb5-b113-a2608254689f | tickbox | within 0 to 1 m behind the back of kerb:
26efce85-123c-55b1-a0cd-89f89b2f5e6d | note | mounting height (vertical dimension from ground surface to centre of w beam) shall be measured from the lip of kerb.
cfb81738-a23d-5433-b94c-6956a18075a6 | tickbox | within 1.5 m from edge of carriageway without kerb:
f08b218b-e1ba-50dd-b6d6-2d9f3e915ea8 | note | mounting height (vertical dimension from ground surface to centre of w beam) shall be measured from the lip of kerb.
ddb0ba6c-d03e-5049-baeb-64a554520047 | tickbox | Distances beyond 1.5m
d84a268b-36b3-58da-9402-42a8ffae72b8 | note | the mounting height shall be measured from the nominal ground surface at the guard fence location.
01c3a5de-42ad-515b-91a9-0901cbae4ab9 | note | Freq - Each lot & Each possession
6fdb1605-5a50-562f-9007-d7bd8f6f43b1 | note | Key - H
05558d81-3b1e-58f4-9ce5-acbe10cca922 | note | Resp - SE
0cf544fe-832a-5fa4-ab1d-f285f22ad2b7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c32a2e63-1263-5a0f-b63b-405bfc091984 | tickbox | As-built survey and tabulations verifying compliance (Survey Conformance Report)
| checkpoint | 3.6 - Motorcyclist Safety
8e1fdac4-fe7d-5f25-83f5-ba6ca0eec506 | note | Ref docs - DoT Clause 708.09 IFC Drawing
342696eb-6af8-5c12-9845-c16e8890d755 | note | Acceptance criteria - Where specified, steel rub rail or other proprietary under-run systems, as listed in RDN 06-04 to be at attached to Guard Fence on nominated sections of barrier as shown on the drawings only.
36360c8c-84bf-509f-9224-dae243de3b13 | note | ○ A 50 mm gap shall be provided between the rub rail and the ground to allow for passage of water.
7b7a6fee-8a80-5751-a23e-c5b6c5f3515c | note | Freq - Each lot & Each possession
0fb72d1a-9fb1-5cf8-aa52-7fe50c3d468a | note | Key - R I
b0bca89a-2053-5ade-a7ea-e061c25b6293 | note | Resp - SE
93221024-44d2-5273-a541-1ba2af88272b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| checkpoint | 3.7 - Installation of Delineators
498090b8-de5e-5267-9496-8f8ef86b2193 | note | Ref docs - DoT Clause 708.11
84a58a4b-fe98-5713-85db-7ef848e41092 | note | Acceptance criteria - Delineators to be as per VicRoads Supplement to AS 1742.2 Clause 4.2.5.4(b).
be3852d0-8d55-5c40-ba2b-d3b1533cf6ee | note | ○ Contractor to supply and fasten flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2.
a86e36a4-3e21-5c27-82a0-3bbb7d57d402 | note | ○ Red delineators on the left side of one-way and two-way roadways.
5e0f24c2-87d6-5d6a-8376-5a6c9e5a2710 | note | ○ White delineators on the right side of two-way roadways; and
39c0b09b-16e4-518e-b657-b8e243548cdd | note | ○ Yellow delineators on the right side of one-way roadways
098c4cfe-14cb-507f-bf7b-f2016dcbe4f6 | note | ○ Delineators not required where Guard Fence offset is greater than 4 m from the traffic lane.
b3cbca41-3fa3-58ca-8af2-2ef797c23e5f | note | White guideposts with delineators shall be installed in accordance with VicRoads Supplement to AS 1742.2 Clause 4.2.4 – Guideposts.
e9d31acf-a89e-554c-b373-410562b4bdb0 | note | Freq - Each lot & Each possession
af638b52-67fa-5db0-976b-9c3930d0f0fb | note | Key - R I
557d185d-47cb-5a93-937f-3596be646517 | note | Resp - SE
19e04af3-7607-5230-9351-0d9cec6a3db0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Subcontractor Records
| checkpoint | 3.8 - Concrete maintenance strips
5ca549a4-79d0-5f36-8d63-49ed07ef47cf | note | Ref docs - DoT Clause 708.12
267ada97-a47d-5b3f-a4e5-54119e14acc7 | note | Acceptance criteria - Concrete used for guard fence maintenance strips shall comply with AS1379 and VR 703.
2098ae2e-8250-5283-8d99-6b418da0ef74 | note | Concrete maintenance strips beneath all steel beam guard fence railing shall meet the following requirements:
e5bcd673-2dd4-53bb-bea1-25d0abad5757 | note | ○ 300 mm clear of the rear of the post and 300 mm clear from the face of w-beam
5dcb6f54-f5d1-599e-8251-dca25b77b7d8 | note | ○ Bedding to be 75mm thick of class 3 crushed rock
40d1e2fe-5b47-577f-9680-43b56124d2a7 | note | ○ Concrete shall be 75mm thick and 20MPa Strength.
62f3f1e1-5e1a-5ad2-8b96-25b4fa612d97 | note | ○ Edges of infill boarded up prior to pour.
0637f527-b39c-5367-af6f-14f77efbb2a7 | note | ○ Edge board shall be parallel with steel beam guard rail fencing.
b3696962-5563-5fde-9a14-739bb8284e9d | note | ○ Surface finished with a wooden float to produce a lightly textured finish.
ffa55a8e-f77e-5780-a347-3735c47dc016 | note | ○ Shall be constructed with a minimum 2% cross fall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
138b886d-47a3-5d7d-b13d-7b6fc4039d71 | note | Where maintenance strip is adjacent to kerb or pavement, cork expansion joint or approved alternative shall be placed in between kerb / pavement and infill area.
f877f554-db92-5c1f-b8ea-eab151e49583 | note | Where crushed rock is used, provide Incoming material testing requirements for Class 3 material.
d48992a1-5e62-5cf5-91b0-91269c91fb86 | note | Where concrete is to be used, testing of concrete shall be conducted as per 703.11.
8a325997-2627-51ad-be83-74daa1dbc28c | note | Frequency of testing:
2815119e-9283-55b4-9357-8672acf8871b | note | ○ 1 test per lot; or
ebeddd0d-2040-55fc-afbe-5f0e0f7a0b87 | note | ○ 1 test for every 50m3 of concrete.
982e4c4d-3d50-5e20-903e-e5f2c92dc7cb | note | Freq - Each lot & Each possession
d99e9848-6ade-51f1-b337-828e61e3aa7d | note | Key - R I
99dc6cc1-1f41-5690-893d-9a4d6cc152f4 | note | Resp - SE
55c52541-b665-545b-8c9a-86e95aaf0c96 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bb24c59a-cdee-5244-8d0e-963f952ba4a5 | note | Material Delivery Dockets:
9a64f52f-1e15-5dba-b5b5-b429a73d3c00 | tickbox | Concrete
13974f5a-27d2-5084-88dd-55e5e86232a9 | tickbox | Crushed Rock
c801dbf2-af36-530f-9cde-b9669cba84d9 | note | Subcontractor Records:
4ea87004-5b66-5750-b6e6-5f8d788611cd | tickbox | Concrete test results (if required)
537e679b-a44e-578f-9bf5-f2833e50c53a | tickbox | Class 3 Crushed Rock Material Certification (if required)
| checkpoint | 3.9 - Expansion Joints perpendicular to the line of Guard Fence
6e94c23c-809a-562f-a99d-fac57f8ca86a | note | Ref docs - DoT Clause 708.12, SD 3503, 1120-SYM- RFI-0074
3fe509f6-eb66-5607-9fdf-50dd40c35e2c | note | Acceptance criteria - Full depth expansion joints (cork or approved equivalent) shall be provided, perpendicular to the line of the steel beam guard fence, 200mm each side of every post. alternatively, the following 2 options could also be considered:
4206d219-667f-5bf8-aeac-92d6cbd95dc7 | note | (i) a 75% depth (56mm) saw cut (200mm each side of every post) for the full width of the maintenance strip;
d6663f61-3ab8-5d26-9a3b-5d42aa05a1dd | note | (ii) a leave-out area around the post filled with 75mm thick low strength concrete mix (less than 0.85mpa)
0f9b0298-45f5-5db0-ac91-690082485fdf | note | Additional option approved as per 1120-SYM-RFI- 0074:
e8975599-dc48-533a-9aa8-39b4a75c4512 | note | – Similar to the method used for Kerb, a guillotine cut between 40-70% to be completed during concreting works
b759ee33-2a07-5a70-98db-898c550b7e53 | note | – Following this a tooled edging to a depth of 20mm to produce a neat groove not less than 5mm wide on the exposed surface as seen on kerb profiles
f061c59a-70f8-5cec-aa38-a7a529a290f9 | note | Freq - Each lot & Each possession
2b6259c9-72cb-5831-b9cb-d71d4240c872 | note | Key - R I
284c67f8-8b2a-5564-ac34-72dedac4e8eb | note | Resp - SE
0e7849ee-c41d-59a2-9973-cc8a972fcae2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| checkpoint | 3.10 - Delineators
0e763483-bb09-5c28-8d93-ea81d2417e6f | note | Ref docs - DoT Clause 708.11
3871ef77-008a-5549-98f4-ad64deca0ec1 | note | Acceptance criteria -  Delineators to be as per VicRoads Supplement to AS 1742.2 Clause 4.2.5.4(b).
05569f87-f739-582a-9b6d-43e4250f928c | note | ○ Contractor to supply and fasten flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2.
9e2e8c0c-fd54-5e4d-ae85-ba7330581af0 | note | Freq - Prior to start of works
4bd5a5db-a8b9-59c7-8a82-5adc7949d058 | note | Key - R
9a36afbc-599d-5d7b-ae68-6c981fcc83e2 | note | Resp - SE
5e8ec8d4-64b1-5755-a081-3099a8faa313 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
81a989dd-b1f9-5005-96e3-bd4f3c9b72d6 | tickbox | Delineators Compliance test certificates
| checkpoint | 3.11 - WRSB Tensioning
3dfe5e7d-8dab-5fef-8dd0-b282c4567946 | note | Ref docs - VR711.07 (e)
4afad0ea-ef08-54b1-bc75-10b5e08a44ae | note | Acceptance criteria - Each wire rope shall be tensioned in accordance with the relationship between rope tension and ambient temperature, applicable to the proprietary WRSB system as per the manufacturer’s specification.
f8198ec0-0724-595b-80d0-7a3fc1f80271 | note | ○ A tensioning report for shall be submitted to the Superintendent for review within seven days of the tensioning works being carried out.
abe0eaa3-ed0d-54fd-bc96-316a36b4e08a | note | Freq - Each Lot
892b0054-730a-50ea-8fdc-33309fe40e98 | note | Key - R
67686436-4557-5387-9167-e62573e8366e | note | Resp - SE
cd12422c-64a3-55da-b835-2c0b01e73fcd | note | SI Key - R
18d666a0-7ded-5ef8-b0b0-71d425bfc08d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Tensioning report/subcontractor documentation
| checkpoint | 3.12 - WRSB Tensioning and Testing
d82c16a9-ae45-5963-b5c9-80ad1b2617e4 | note | Ref docs - VR711.07 (f)
fd5d878d-bda4-5425-9858-a6f356f50cae | note | Acceptance criteria - Side load testing of posts shall be undertaken at locations nominated by the Superintendent prior to the installation of the wire rope.
eae3f022-59c0-52d5-8862-69535e6b8627 | note | ○ Side load testing of posts shall be carried out by applying a force of 10 kN (approximately 1 tonne) to the post 600 mm above ground level at an angle of 45 degrees to the WRSB. The top of the footing shall not move more than 3 mm. If the footing withstands the force with a movement of less than 3 mm at ground level then the footing shall be considered acceptable.
733838ac-edea-554e-9d44-be455fa83e74 | note | Freq - Each Lot
ebc4c789-b0f9-5dab-828c-2d042a87c3f2 | note | Key - R
6baf4d30-998c-531d-a9a0-e1374c1cc54a | note | Resp - SE
0e572187-af92-5146-9d88-7500ac88529f | note | SI Key - H
e80c48a0-b782-51d5-b098-d4a33ec7aa37 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| signoff | AUTHORITY HOLDPOINT
| section | 4.0 Completion of Steel Beam Guard Fence
| checkpoint | 4.1 - Guard Fence Tolerances
cc1844e0-20ec-563c-ad07-34e5b9d066f7 | note | Ref docs - DoT Clause 708.08 (d)
5cb26424-b7b3-5e67-9954-f5ec7dd4c4a5 | note | Acceptance criteria - The guard fence shall be installed at the positions so confirmed and shall be constructed true to line and level and to the following tolerances:
df311e81-e85b-5440-8ae9-8eec780ef526 | note | i. Variation from true plan position of posts ±20 mm
4e0a9e92-aa1c-5aa0-9a08-dd13856d8b0e | note | ii. Variation of line of w-beams from specified vertical profile ± 10 mm.
ce02c2b7-aebc-5fef-827d-2edeb6187f24 | note | iii. Variation of w-beams from specified horizontal alignment ± 20 mm.
bbc75f64-3b02-5ad0-b3da-c0651fdb9fff | note | iv. Variation of posts from vertical (measured at top of the post) ± 15 mm.
0287a197-4343-5227-be70-9f20926b7e86 | note | v. Orientation of block and/or post to w-beam +0 mm, -15 mm measured at the point of greatest offset between the block or post to the w-beam)
a693246c-65f1-5a15-97a3-174966d2aa1d | note | vi. Dimension of holes -0 mm, +50 mm
0941ff52-3959-5ec4-81a1-ebb0bd2ee397 | note | Top of bolt head relative to w-beam -0 mm, +5 mm.
a2380672-49c1-587f-af50-fd6a2c12d1db | note | Freq - Each lot & Each possession
b7b5baec-ab8c-5c2e-93cc-8d8228c36d49 | note | Key - R I
0df26bbd-3556-5e18-936b-48a9615b01ce | note | Resp - SE
c9a559ee-2f2d-5378-a4a6-8b4a7bab379f | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
614b91a6-b480-5984-9cac-b340d59e2471 | tickbox | Survey Conformance Report
| checkpoint | 4.2 - Safety Barrier Compliance Audit
3f04d5bc-ed4b-571c-b1b6-5154f36881a5 | note | Ref docs - Table PS3090.021, VR 708.10, VR 711.09
9f830bb0-5298-5f5f-aa8e-2faa828998bd | note | Acceptance criteria - After Completion, arrange for a safety barrier compliance audit on all proprietary guard fence, end treatments and WRSB constructed under the Contract. The audit shall be undertaken, and a report prepared by the Australian Licensed Supplier of the safety barrier system.
87c5e846-8cbd-5b11-af96-65bcfea79275 | note | ○ In addition, complete and submit to the Superintendent, compliance certificates for review.
1be6ae85-1c47-593d-9286-361ada27c347 | note | ○ The CoC need to be signed by both Symal representative and the Supplier.
5ed8a98d-a601-5415-a04a-3aaf2c746dc0 | note | Freq - Each lot & Each possession
26346d23-fac4-5efe-91b1-c1d4cc78cf00 | note | Key - H
ab020342-636b-55ae-8582-795876ecb4d0 | note | Resp - SE
93cb0790-3bee-52af-ab1c-3d4649ea9ea1 | note | SI Key - H
40b20006-8bc0-5f4b-bc61-0356ea94a0a9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
31ff38c5-5a61-5db7-bcf1-0c4eaa7ce532 | tickbox | Compliance Audit and Certificate of Compliance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Reinstated Works
d28c4886-5204-57a8-8e6e-7fb6a96cd26e | note | Ref docs - DoT Clause 708.17, 708.18, 708.19, 708.20
c9d2b439-5d08-53ea-8ee7-6d3eda003c4f | note | Acceptance criteria - All existing signs and markings, median crossings and existing vegetation removed due to Guard Fence installation shall be reinstated.
8a6162bf-853c-536e-a0f1-03b34df2c0d9 | note | ○ Any damage to existing vegetation shall be rectified immediately to the satisfaction of the Superintendent.
eb2f0953-ef63-5bce-ba75-2670887e3e76 | note | ○ Reinstatement inspection not applicable for areas where guard rail is installed prior to landscaping works being completed – landscaping to be completed in accordance with the IFC Drawings and inspection to be covered in landscaping ITP.
dade2c08-5900-546f-a2bc-ac58145460d1 | note | Freq - Each lot & Each possession
e4887822-2f2e-5576-addb-83e40a12f7b9 | note | Key - H
06bac1c4-3e5a-5489-ac6d-c94ca4b16919 | note | Resp - SE
76ae7905-41a8-511d-9bfd-98455c13c0b7 | note | SI Key - H
13c49df7-590c-5022-a467-a2852d158b31 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
| signoff | AUTHORITY HOLDPOINT
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Test Reports
ec3c8fce-ff1e-54c7-8630-131b232e8b73 | note | Ref docs - VIC Roads Specification s
5eb07778-ed08-5530-ae9d-77d941c454f2 | note | Acceptance criteria - All Test reports received and Reviewed
9f67a983-7db1-5191-857f-c189bb788eaa | note | Freq - Each lot
6e901635-c356-5414-a16e-f9700a9d5231 | note | Key - R
d9cc66d9-010d-5c40-9447-bcd3f54facc1 | note | Resp - SE
96aca0f1-ef39-5231-a39c-10b68eaeee3d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
ec22e326-5eef-5f23-a613-fde558667da7 | tickbox | NATA Endorsed Test Reports
| checkpoint | 5.2 - Product Non-Conformance
1d648b1d-2609-52ba-a07b-389b840e8c05 | note | Ref docs - QMP
b1174fdb-e2dd-5f78-a949-981f20ccd764 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
255af716-647e-540e-8c0b-8c0283dc6c99 | note | Freq - Each lot
e9b7d273-0c5e-52a3-bd5e-b94152f9a5f0 | note | Key - R
bbe0d29a-c4e3-50e5-9595-88f2f96ab3b9 | note | Resp - SE
4888c87e-3f0e-5702-95ad-e922633c9f2a | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - NCR reports
| checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm
b5a6782f-7bf2-569e-91f8-faf828cacc0f | note | Ref docs - CQMP Lot Records
e61eb352-2d03-5c50-b5b9-1974fe22d98e | note | Acceptance criteria - All above criteria met, and records identified attached.
a339bad6-880e-54a6-96b9-d575a3bff30f | note | Freq - Each lot
2fc29405-db6a-5c67-bf74-6cbd9505b1b7 | note | Key - R
119efc14-7703-5668-a9e9-4052c217d433 | note | Resp - SE
5e29633f-8911-5f27-937d-c05b5a6e0241 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0033 Traffic Signal Installation | itp | 1630-P200-SYM-QAC-ITP-0033 Traffic Signal Installation |  |  | 1e625bb2-6947-4789-a64c-0480c4b02c75
| section | ITP Details
| checkpoint | ITP Details
95958e62-2d77-5443-ad5b-1fa756a2b7d0 | note | ITP No. - 0033
a39afecb-8d5a-5ec6-868c-e63f296ffe3d | note | Rev No. - 00
17886231-7cc4-5f13-90cd-9b9ab334c4ca | note | Date of Issue - 24/01/2024
6a4ead7c-5fac-5afb-95ad-ebc8ec3c0c19 | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Pre-Installation Meeting
0a28a48e-0e08-59a4-9e9e-6e9216b30f2f | note | Ref docs - VR Clause 730.08(c)
1c5104f5-4ec9-5ce7-b835-268c1e856491 | note | Acceptance criteria - The Contractor shall not commence installation of the traffic signal pedestals, poles, controller bases or pits until the Pre-Installation Report has been approved.
7151862a-51e5-5c18-afb7-9c328fa20bfe | button | Approval to Proceed? | Yes,No
b63153d6-80a5-583c-adc3-68910fd09840 | note | Freq - Each lot
e17cf055-5e38-5a3e-8fdf-1c025d594038 | note | Key - H, S
ad21fc11-1416-5e23-a547-a210bac8ca1f | note | Resp - SE
9377d072-5396-5002-81b0-7a3fcf46aac9 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Conduit Cover
| checkpoint | 2.1 - Excavation and Cover Requirements
3761995f-4964-5f27-a758-a537c11a534f | note | Ref docs - VR Clause 733.05 Table 733.051
eb96ebbe-ea80-51cf-8534-945ef88d3dff | note | Acceptance criteria - Cover requirements for both electrical and communications conduits shall be:
438fca31-df7f-5882-8a97-9798ea12ae5e | note | ○ Pavement surface to top of conduit minimum 1200 mm.
e4c2b28e-0091-56bd-8626-e4e79ba630f0 | note | ○ Invert of open drain to top of conduit minimum 750 mm.
dc679116-a267-53a2-b209-86ea5a13a632 | note | ○ Unpaved areas to top of conduit minimum 600 mm.
6fa4f4bf-df4e-52a7-8fd5-69742fde004c | note | ○ Or else as specified on design drawings.
653c668f-5401-5adc-906c-743321011498 | button | Has all the above been completed and approved? | Yes,No
5a300a53-be68-5919-baad-e54b8cc06218 | note | Freq - Each Lot & Each possession
7c044d3b-7d09-5c4a-8b3b-b146754ebdd2 | note | Key - S
e8f28cf2-60ff-59fe-954c-c1ed4ac47c0d | note | Resp - SE/SS
| section | 3.0 Conduits Installation
| checkpoint | 3.1 - General
d0988810-497c-5c75-98b1-33f9a129826a | note | Ref docs - VR Clause 730.09
5ed46064-fab3-53af-b5a2-6e708c7766ee | note | Acceptance criteria - The Contractor shall install all conduits in accordance with Section 733 and Technical Note TCN 010.
6c0842e6-94b0-59ff-bb97-95cf5a5a1e85 | note | ○ All electrical conduit installation works for traffic signals must be carried out by, or under the direct supervision of, a VicRoads prequalified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria.
f1320740-96c2-5ff2-ac3d-7a249409010c | note | ○ All communication conduit installation works are to be carried out under the ‘on site’ supervision of a licensed cabler.
e2d44cce-aafa-5738-8e4a-d851913efdf9 | button | Has all of the above been completed? | Yes,No
8e221690-5aea-5438-9a16-401e43795a90 | note | Freq - Each Lot & Each possession
87a701bb-29d1-5f21-8050-443fe61556a9 | note | Key - R
9f5d1ee0-3576-5681-8dc5-c7a14eb6c458 | note | Resp - SE/SS
| checkpoint | 3.2 - General
fc84c63b-5b3a-5eba-bba9-1882759c7cf0 | note | Ref docs - VR Clause 733.06 Table 733.061 AS/NZS 3000, AS/ACIF S009
c4615cf2-d998-51a6-87e3-30887721e8a6 | note | Acceptance criteria - All conduits shall be installed as shown on the VicRoads Standard Drawings and Contract specific drawings, or as otherwise specified.
bb4d574d-700e-5e92-9470-890cdfe5c35e | note | All conduits for electrical and communications cabling shall be installed to conform to the relevant requirements of controlling legislation, regulations, industry codes and standards, including:
c3d52a3f-f6bb-57e0-91cf-6472fd77d98a | note | ○ AS/NZS 3000 Electrical installations (Australian/New Zealand Wiring Rules)
b3e0305a-9831-50aa-855d-cc97336714f2 | note | ○ AS/ACIF S009 Installation requirements for customer cabling (Wiring Rules), and any other relevant requirements of the Australian Communications and Media Authority (ACMA) for connections to telecommunication carriers’ network.
a8b6550c-4139-54a4-85bd-9a25fafdb5dd | note | Installation of conduits shall be carried out in accordance with the following:
0af198ea-1387-543f-821f-2d3b683e2583 | tickbox | HD UPVC Plain to be Thrust bore or Open Trench.
dbf179a7-fcd9-5261-a20f-a90541d8fb12 | tickbox | HDPE continuous (must have ID not less than that of 100 mm HD UPVC for electrical and 90 mm HD UPVC for communications) to be Directional Bore.
db7152c9-8ed5-5a0f-9948-cf54799c13df | button | Has all of the above been completed? | Yes,No
cebc30c5-78eb-581a-b271-515266efd320 | note | Freq - Each Lot
323f1bef-d637-59c1-903f-6b21c74ae2c0 | note | Key - I
2ed7f2dc-e505-5851-bcc3-6848f27135db | note | Resp - SE/SS
| checkpoint | 3.3 - Bedding Material/Placement
1c1cb96d-7772-5736-87ca-f2162c05943f | note | Ref docs - VR Clause 733.08
0945eb4b-c097-5cc6-b5d6-872393e40dc2 | note | Acceptance criteria - Bedding material does comply with the requirements of Table 733.081.
1250f069-7432-5863-8a05-94399977f4aa | note | ○ Minimum 80 mm bedding below conduits on earth foundation.
0e1e8a65-32f6-5d4f-a70a-397c90b12638 | note | ○ Minimum 200 mm bedding below conduits on rock foundation.
9da12495-6d66-5857-bb3c-3887afae9b90 | note | ○ Bedding placed to full width of trench, and between conduits as shown on trench details on latest revision IFC drawings.
8915c8a5-2ed9-50cb-a014-449933a2daec | note | ○ Shaped sufficiently to maintain the conduit in line as the sections are placed.
f650fcdf-ea2a-5d73-aa5e-a197b17adba8 | button | Has all the above been completed? | Yes,No
4e973922-aa44-560a-8437-74b035ed6c83 | note | Freq - Each Lot
5a6f8e7b-fda5-5ef4-8f7d-9eff1f39ff54 | note | Key - I
99c104fa-82fd-5f6d-90cb-9401aa96e95c | note | Resp - SE/SS
1d1cb5a8-b43b-5c08-9225-803335c5c89b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
340c4aa0-d067-5189-89e4-41ac53ced5da | button | Material Compliance for Bedding/NATA Test Report | Yes,No
| checkpoint | 3.4 - Bedding Material/Placement
5436842a-0527-544e-b5a6-d7ecef540268 | note | Ref docs - VR Clause 733.08
dd4f6f4a-dd57-57c8-9d3d-6c9d563039d9 | note | Acceptance criteria - Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by Superintendent.
93d1e1f0-6ff7-5a2b-9e85-e39dbf80c444 | button | Approval to proceed? | Yes,No
2c15fb9c-0442-59c4-accf-2fe817ab06c3 | note | Freq - Each Lot
0716417b-984c-5548-b18a-39cba0d1be1a | note | Key - H, I
13aabc61-6654-5b37-a235-79b252f011c9 | note | Resp - SE/SS
d41e0a03-3139-5533-a998-065f0f27ef33 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Bedding Material/Placement
50e57d33-4dd2-516f-b36f-ac9a0ce894e4 | note | Ref docs - VR Clause 733.08
63f780fa-73d4-5791-935a-93c0f09a877a | note | Acceptance criteria - When conduit sections are in position, additional layers of bedding material shall be placed and compacted to a height 150 mm above the bedding previously placed.
fe55e86b-f9f1-51f7-81f1-904d26bc8acb | note | ○ Bedding material must not be the same material excavated for the trench, it shall be clearly identifiable as introduced material.
a9e677e6-6c48-58d0-9dc2-f6d1ec607fe1 | button | Has all the above been completed? | Yes,No
6c703dd7-9a11-5316-ab3b-bf00a56a85c7 | note | Freq - Each Lot
202a4e4c-0c81-5035-937b-57c3d03d5bef | note | Key - I
3d6ca88c-29b0-5409-94fd-f6f6ac34e0a3 | note | Resp - SE/SS
| checkpoint | 3.6 - Conduits for Traffic Signals/ITS/Public Lighting
5ba729d9-b6bc-5f0f-9579-df5199f31d74 | note | Ref docs - VR Clause 733.06
04530553-01ee-56b0-9f2d-6206704d797c | note | Acceptance criteria - a) All conduits shall terminate in a pit in accordance with VicRoads Standard Drawing TC 1207, TC-1230 and TC-2200 – TC223.
d4b196b5-27e7-53c9-a87c-652eb012b4ea | note | b) Only one size conduit shall be used for a complete run between pits; unequal size conduits shall not be joined in the ground.
5464f425-099a-5f5b-928b-56cb9268777b | note | c) All conduits shall be temporarily sealed prior to cabling to avoid blockage.
5297a071-2579-572a-9eb3-8b0c19dddb50 | note | d) Changes in conduit direction or depth shall be made by natural set or in the case of bottom entry, by means of a swept bend; elbows or tees shall not be used.
360b972a-0a90-5ed2-908a-01d0c4e6e88c | note | e) All conduit joints shall be correctly prepared and sealed with approved solvent cement.
0a81f823-3183-51e6-b6b6-0346d12ef54b | note | f) Conduits for detector cables shall be installed as shown in VicRoads Standard Drawings TC 1207 and TC 1320; and
836e2b23-a3dd-5adb-9567-4b773c093fdf | note | A 50 mm electrical (orange) conduit shall be used to convey the detector feeder cable from the detector pit to the cable pit, as shown in VicRoads Standard Drawing TC 1207.
eb1a4dc1-aaa5-5619-93f0-65c7aa2e8cb8 | button | Has all the above been completed correctly and to a high standard? | Yes,No
e0140f6b-d704-5843-8a9c-45433745103d | note | Freq - Each Lot
19c99c86-4af5-5e21-9bd9-27dc7a036bbb | note | Key - S, I
9248beab-d8b9-5ae4-ad0e-40a90eae862d | note | Resp - SE/SS
95bee509-bcfd-555e-968b-64276d9a4191 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9c3d248a-6045-5073-92bb-2cf4ceeba4cb | button | Installation Records from Subcontractor | Yes,No
| checkpoint | 3.7 - Draw Cords
b348ecea-9a00-57bc-a256-a4414260d2fe | note | Ref docs - VR Clause 733.07
29fbb3b5-9161-54d7-a912-2e2a3f06f419 | note | Acceptance criteria - Draw Cords to be 3 mm diameter and with a minimum breaking strain of 1.6 kN.
aed772c4-2116-5c97-a8f2-c5dbd932970a | note | Where the conduit terminates in a pit
9fd20d1b-dfb6-53c8-87a3-763faf6b4b72 | note | ○ Have no less than 500 mm of the draw cord tied to a marker peg 25 mm x 25 mm, no less than 300 mm long, left coiled in the pit for future use.
88dfe05b-5444-521b-92c1-5741c7dbd405 | note | Where conduits do not terminate into a pit.
e826e2e8-1577-5350-acf2-22304cefb801 | note | ○ Be tied to a marker peg 100 mm x 100 mm, not less than 400 mm long, driven firmly into the ground with the top 50 mm projecting above finished surface and painted yellow.
a4da669f-5e60-584c-be73-7ad44faadf7d | button | Has all the above been completed correctly and to VicRoads standard? | Yes,No,N/A
328dc11b-5fef-51b7-a64f-c17447a329da | note | Freq - Each Lot
c28b9c55-e622-5cb0-b083-1a58a8c64350 | note | Key - I
1acc0363-bfee-5c44-8f16-96d9cb03a599 | note | Resp - SE/SS
9559c946-b22f-58ce-bb18-b294d9d7ce76 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9a3f4a28-4784-5c55-af95-5c2278ac476b | button | Installation Records from Subcontractor | Yes,No
b40371ba-662b-575d-9a1a-7f4dbeee21a7 | button | Material Conformance Certificate | Yes,No
| section | 4.0 Backfill
| checkpoint | 4.1 - Material Properties
5d49307b-d42f-5ef9-b1b4-6fd019e0f22b | note | Ref docs - VR Clause Table 733.081
59d335cb-d820-5711-8085-981d4abda12c | note | Acceptance criteria - Backfill material properties to be as per Table 733.081.
ad5219ef-ce1a-5534-aefd-78e2ab36e88c | note | Freq - Each Lot
c95cc15d-db28-50e1-adc1-fa4d019433be | note | Key - R
2fe6fb9f-0282-545c-b461-1a7d98e0b401 | note | Resp - SE/SS
c6521d9c-44ca-58b2-994a-5cda47cd31e7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
eacf4f03-c0cc-5dd4-876c-f9c47ab07894 | button | NATA Test Report (if applicable) | Yes,No
| checkpoint | 4.2 - Filling
b00c4080-0b4e-5917-a826-2f3e189a08bd | note | Ref docs - VR Clause 733.08
4e9f925c-4df7-5b63-84e3-cd93c4ab4923 | note | Acceptance criteria - Unless otherwise specified or shown on the drawings, selected and common backfill shall be placed and compacted as follows under, around, and above the conduit after the sections are bedded:
c489c762-30f6-5304-ab25-0b96776e2a28 | note | ○ Place and compact selected backfill 400 mm above bedding (in non-trafficable areas) remaining fill to be common backfill.
5880df52-2b33-5b93-a359-86dfc8a72793 | note | ○ Place and compact selected backfill to subgrade level (in area’s to be paved)
c3deffcd-fe3c-5f94-bfc2-1aedd7944963 | button | Has all the above been completed? | Yes,No
86c87c5f-9c7a-52ca-bca0-a4bcdb5b01c0 | note | Freq - Each Lot
f78c7866-13af-53ac-be04-e0ff49c5ca2c | note | Key - R
c4bcbe31-622c-50f0-8d85-5a9346e982ca | note | Resp - SE/SS
| checkpoint | 4.3 - Compaction - Areas not to be paved and below pavement
d25baeb0-340d-5a6e-a424-c6af24d21f1a | note | Ref docs - VR Clause 733.08
1aeebcb1-8b7e-5abe-817e-8c67c4fabdab | note | Acceptance criteria - All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
17887f98-f87a-595e-9f04-825d52c0b469 | note | ○ Compacted to refusal using handheld mechanical equipment.
a9ec1ae8-13ad-5975-b67b-3044d11f9e80 | button | Has all the above been completed? | Yes,No
c92aa470-7db9-5521-a589-aaffc5d4c5b7 | note | Freq - Each Lot
f36609a2-6bac-5433-b269-6cc6427b2c3f | note | Key - R
93434535-05d8-53ba-907a-26a5a4b2f5e6 | note | Resp - SE/SS
| checkpoint | 4.4 - Compaction – Area’s pavement layer
39a082cb-66c7-5871-bcc9-a4977b803cd6 | note | Ref docs - VR Clause 733.08
b8de3f98-91e0-5937-a05f-6fc46bf2b5a2 | note | Acceptance criteria - Where specified, pavement material shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three. All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test. All pavement layers shall be placed and compacted in layers to a density ratio of not less than 98%. The calculation of density ratio shall be based on Modified compactive effort.
d1e3cb39-0b94-522b-b934-cd130ec6f4e1 | note | ○ Compacted to refusal using handheld mechanical equipment.
52b36b1f-d0db-5318-842d-5f79448c5968 | button | Has all the above been completed? | Yes,No
289652f7-669a-5cce-ac5a-1e08e72ce515 | note | Freq - Each Lot
d6cbe0a0-66aa-5e1c-ae3b-33ed9f1c2092 | note | Key - R
d8553df4-f58b-545b-9f1d-b1bcc836c70d | note | Resp - SE/SS
8eb96d17-6104-579f-84b5-c38cd23b974e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9e1c9eb6-13df-5040-ad90-28ee34b845d6 | button | NATA Test Report (if applicable) | Yes,No
| checkpoint | 4.5 - Warning Tape
81f5d3d0-b07f-5fb9-932d-3a1efbfd9574 | note | Ref docs - AS/NZS2648.1
fe5576ae-31be-503c-b68b-efe2054f673e | note | Acceptance criteria - Where marker tapes overlap electrical tape to overlay communications tape:
9779c15e-e655-5148-837c-d629f9906acd | note | ○ Marker tape 100 mm wide complying with AS/NZS2648.1 coloured orange with black lettering “DANGER BURIED ELECTRIC CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits in all trenches where electrical conduits are provided.
14508bf2-9150-541d-8319-d2b8656fc167 | note | ○ Marker tape 100 mm wide with two stainless steel tracer wires coloured white with black lettering “DANGER BURIED COMMUNICATION CABLE BELOW” inscribed at regular intervals installed 300 mm above the conduits. In all trenches where communication conduits are provided at least two meters of each tracer wire shall be anchored to and neatly coiled in each communication pit.
87f88bd3-6ecf-5099-8d99-b96bfef2c3d0 | note | ○ Where both electrical and communication conduits are provided in a trench two marker tapes shall be provided one for electrical and the other for communication conduits.
0a1cbf20-2fb4-53e8-902d-271745a7f149 | button | Has all of the above been completed? | Yes,No
0ecbc8ae-e522-50e6-89c6-0205753bb865 | note | Freq - Each Lot
d24bb72e-3525-5fea-b715-4dd7aa01b799 | note | Key - S
c25b2411-4b84-5a80-8e5d-84d12d90c902 | note | Resp - SE/SS
| section | 8.0 Completion
| checkpoint | 8.1 - As-built Information
3201bcf7-a2d7-5326-826b-c040938be83d | note | Ref docs - VR Clause 733.12
f69583d3-6401-58c3-9227-3bbb2ef78de1 | note | Acceptance criteria - Identification and recording as follows:
c14639b8-0f6b-521e-9a81-d8be4c112c35 | note | ○ All conduit locations not identified by pits immediately installed at the ends shall be marked with pegs 75 x 38 mm stakes projecting 0.4 m above the ground, with the top 150 mm painted yellow, or as otherwise agreed by the Superintendent.
210b6c47-4234-5d62-be75-3d52bfc2114c | note | ○ Conduits under road pavement shall be marked with stakes clear of the road pavement.
18a70d10-52c9-5a51-88a5-227b728c5088 | note | ○ Conduits not under road pavement shall be marked with stakes at the ends, at changes of direction, and at intervals of not more than 30 m.
119c4ea5-4d4b-58a8-999d-93f9e07c3aad | note | The actual installed location and depth of conduits on the as-built drawings.
5ca1069a-9535-5111-bf03-6ff53c198547 | button | Has all the above been completed correctly and to a high standard? | Yes,No,N/A
3bedce5f-81d3-520f-9bb0-c40c4b5c583a | note | Freq - Each Lot
2ef9d240-cd8c-5c59-9829-167f486f5196 | note | Key - R
20f0caf1-25af-5648-957d-ee80946a81fb | note | Resp - SE/SS
bcba6a8e-a574-5b96-ab9e-956ac4599bfb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
86f52337-e73f-53ec-88f9-ec41a669df58 | button | Survey Conformance Report | Yes,No
| section | 9.0 Work Lot Close Out
| checkpoint | 9.1 - Test Reports
a2f3deea-3c51-5636-80ed-2eb236ba5549 | note | Ref docs - VIC Roads Specifications
bcae1252-7737-5007-9789-b36f94e64f6f | note | Acceptance criteria - All Test reports received and reviewed.
063535b2-ede4-5369-9710-73f4c5cefffc | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
dfe8f87b-873d-515f-a4ac-26fe73be749b | note | Freq - Each Lot
4706cfe4-5c2d-51ae-a175-e0e087268dc3 | note | Key - R, I
6d05411b-4dcb-5a1d-9166-16bac01f59b6 | note | Resp - SE/SS
d15b8464-e1e6-5ee9-a0c5-a849995439cc | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7eb538e2-821e-5a05-b7cb-4c5991e27206 | button | NATA Endorsed Test Reports | Yes,No
| checkpoint | 9.2 - Product Non-Conformance
1b340429-7f25-549e-a373-684a5bb46c01 | note | Ref docs - CQMP
bbcedb07-fbea-56ea-9ed5-40c13c764784 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
d9710519-f580-5e62-93cd-725ea9ba7ece | button | Has all the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
29b3afae-27d2-54f9-84ee-9824bab80e12 | note | Freq - Each Lot
66646216-4455-587e-8030-4a5d0ae39ea5 | note | Key - R
45682104-c60f-5357-8cfd-8b6b93a4ace1 | note | Resp - SE/SS
859452d7-14cc-551e-b3e9-dfca29603251 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
46d50ac7-a582-560c-956a-8c8df3910bbc | button | NCR reports | Yes,No
| checklist | 1630-P200-SYM-QAC-ITP-0037 Rock Beaching Type 1, 2, 5. REV1 | itp | 1630-P200-SYM-QAC-ITP-0037 Rock Beaching Type 1, 2, 5. REV1 |  |  | 75ee6ce0-f337-49ab-a144-852c2b064490
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Conformity and Lot Maps
d8827dd7-8cc9-5c09-b0aa-84f05bc2ed9c | note | Ref docs - VR713.02 IFC Design
f3a01d19-67ef-5e56-aff5-b7f328e9a1fb | note | Acceptance criteria - Beaching finished surface shall conform to the levels, lines, and grades shown on the drawings or specified.
8f55e29e-9e07-562c-8eb5-3c760e8cf4c2 | note | Freq - Prior to start of works
819b33f3-f089-503a-92d5-79ad6def4897 | note | Key - I
f22ba963-505f-5473-ac60-288ea3d77b93 | note | Resp - SE
6e4da722-d0ec-5b9e-8680-45e462d3a321 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
2d9dbda5-e2c1-5d93-9f93-9736aa0c7a44 | button | Lot map | Yes,No,N/A
5d48cfb3-ed15-5dd8-9420-154711c8c470 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
fa809de4-1af3-5831-992e-15a3759df854 | button | Environmental permit | Yes,No,N/A
7149b9e8-ad38-5929-945a-2ccaadccc9bb | date | Inspection Date:
| checkpoint | 1.2 - Material Approval
d495145e-a16f-535c-8aef-fe249e06fb81 | note | Ref docs - VR713.03
4a3dc880-81db-5d42-a7f0-6c945977133e | note | Acceptance criteria - The contractor shall nominate material source, supply specified test results, and provide a representative sample for approval by the superintendent.
12b28385-f5f8-5fa4-a6ad-4e26ecc60faa | note | Freq - Prior to start of works
4c83fa21-a8d1-5ab1-81be-0e8d199b4a8f | note | Key - H
b2bd0119-17e8-5ceb-89f3-cb15b36c80ba | note | Resp - SE
e357fa46-33d8-5f83-8d37-5665f8d66a1c | note | SI Key - H
82d7eb46-3dae-59cf-afc6-e3eae8714f09 | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Beaching Material - Type 1 Ungrouted
9a65ee86-9680-56e2-a8dc-eb8b8d65910d | note | Ref docs - VR713.03
77fa900c-8744-511c-9b2d-04f2b3e43b9c | note | Acceptance criteria - Type 1 Beaching material shall be:
83a086ae-7c6f-5480-966e-4d1b69e8a6c2 | note | • Field or quarry rock >50mm diameter and of mass 20-70kg with at least 60% of Qty greater than 40kg.
d1310f17-a342-57ca-a7c4-80473bcbe982 | note | • Placed that the length of rock protection >100mm and the total layer thickness is >225mm.
36d92051-1942-5ec9-a8cb-603e57ee916c | note | Freq - Prior to start of works
6ce2860c-dc97-5553-9620-6852f01b8960 | note | Key - R
0a03d35e-335e-54b7-9f20-325e12fe2ead | note | Resp - SE
1271e4da-05ef-5c32-ab81-26752db5c118 | note | Remarks/record - Import Docket
209c5761-1af6-54e1-93b4-93a83085c654 | date | Inspection Date:
| checkpoint | 1.4 - Beaching Material - Type 2 Grouted
3ad06e16-d7b6-51a3-817f-e73fa3f462c9 | note | Ref docs - VR713.03
98703369-2c48-5393-8575-a161d93d2a65 | note | Acceptance criteria - Type 2 Beaching material shall be:
1ca21c86-ce12-5e13-9ce4-1322db7dde2c | note | • Field or quarry rock >50mm diameter and of mass 10-40kg with at least 60% of Qty greater than 25kg.
24214a73-babf-55a1-9e9e-cec7dbe4f1f6 | note | • Placed that the length of rock protection >100mm and the total layer thickness is >150mm.
0c283d85-7933-5719-b099-b51629034a58 | note | Freq - Prior to start of works
b42fdd54-dccc-5725-a52c-a853e8c95e69 | note | Key - R
51b1d970-669b-576b-9737-8d6d9880c704 | note | Resp - SE
0f33e219-7de4-5a6d-989b-6ed86299e69c | note | Remarks/record - Import Docket
ca4b6b72-e181-5554-a26d-29fecf53de87 | date | Inspection Date:
| checkpoint | 1.5 - Beaching Material - Type 5
977534b3-6976-5a7e-8816-282b455dc737 | note | Ref docs - VR713.03
0054d2ab-6ec6-5aba-8678-11ecb7861928 | note | Acceptance criteria - Type 5 Beaching material shall be:
c51a63ab-1ca9-561e-b147-ea268256ccde | note | • Design accepted by Melbourne Water and record of acceptance provided for superintendent approval.
bef9b4ec-941f-5610-956b-ad6e8c989b5d | note | • Field or quarry rock >50mm diameter, angular in shape, and 5% mass of rock fines for interlocking.
353fb197-a7c0-51a2-aaf1-9b26443bc9f2 | note | • Unless specified, the minimum d50 shall be 300mm rock sizing of depth 2 x d50 (600mm). the minimum d50 shall be 300mm rock sizing of depth 2 x d50 (600mm).
d7875e04-3c08-5581-bad6-1e4ece5ad490 | note | Freq - Prior to start of works
ea58b17a-f9a4-5c03-8eef-9cfad8c63b92 | note | Key - H
07190696-a400-51b1-b2b3-776b0de65117 | note | Resp - SE
e85f50f6-eccb-56a2-a291-55689efdf987 | note | SI Key - H
44945042-61c6-588d-9811-558f7b9c28d1 | note | Remarks/record - Import Docket
73d0e9d2-7492-59ce-8ea9-9caaf87e2edc | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Construction
| checkpoint | 2.1 - Geotextile Placement
821b169f-fc0b-52f2-9f55-ad4727cd845c | note | Ref docs - VR210.05(a)
b2c06d11-c1a5-50c4-82e6-d42d7bcd89e0 | note | Acceptance criteria - Geotextile is not to be placed without written superintendent approval.
1a1fbb23-9190-5dbe-96cd-b6aff43c67b3 | note | • Geotextile placed shall be without punctures or tears and rolls with imperfections shall not be used.
4d26693f-e9aa-58f6-b61a-f689ac9415aa | note | • Covered with fill material within 48Hr of placement.
98643285-87c0-5d71-9f93-1a60532eea58 | note | Freq - Each lot
4dc222fd-d03e-51e8-a718-9752f9dea5ea | note | Key - H
4ad173aa-864a-5076-9dc2-e1a1c6cd6a89 | note | Resp - SE
d626d43a-82f0-575b-ba34-e2a8c40341d2 | note | SI Key - H
ede85486-41e6-5fb1-a976-f1cee64838fd | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Bedding and Geotextiles - Type 1
c87e282d-196e-52e6-805f-1154235e53e1 | note | Ref docs - VR713.03(b) VR210
f7f97abe-07e4-5200-9775-c06cd8b09e62 | note | Acceptance criteria - Type 1 Beaching Material shall be placed on non-woven geotextile >250g/m2, laid with no kinks or folds.
34dba496-ca56-5733-b631-005d89f03433 | note | • Geotextile shall be buried 300mm below beaching edges and placed under and around excavation for toe wall and other perimeter walls.
061ddac6-569e-5c7d-aefc-725252c0caa5 | note | • Geotextiles are joined with 300-500mm overlap.
3f3639ad-54b1-585a-872e-cfdea05b3395 | note | Freq - Each lot
2cca31be-7cc6-5041-85de-b87a5733c3aa | note | Key - I
7031e2b3-069b-5e96-be5e-30c92b020bec | note | Resp - SE
29db4b7a-fddb-5259-b141-f5f06f560ed7 | date | Inspection Date:
| checkpoint | 2.3 - Bedding and Geotextiles - Type 2
47148f98-432c-58cf-8a61-5ae80bbfbbc9 | note | Ref docs - VR713.03(b)
2e0744a7-3fc4-5adc-992f-b1f7a703091f | note | Acceptance criteria - Type 2 Beaching material shall not require bedding unless specified or in design.
74eff602-79e1-5a9d-a0b9-f27f1fea84ca | note | Freq - Each Lot
04873f63-bc94-5b3f-a716-c1d26e8fc70d | note | Key - I
9427ad39-060f-560a-b7f4-8fee492a9f82 | note | Resp - SE
c697f3fd-5a44-5083-a612-7901aa2ff64d | date | Inspection Date:
| checkpoint | 2.4 - Bedding and Geotextiles - Type 5
f3f89a70-6a85-54c3-bd96-5387c5279151 | note | Ref docs - VR713.03(b) MWC 7251/08/103
cf8f008b-749e-57e8-980c-b1ae069ab2ab | note | Acceptance criteria - Type 5 Beaching Bedding shall be:
82d20837-1e8c-5cb7-a037-455a3871079e | note | • Developed in conjunction with Melbourne Water.
b064ba1b-0022-581d-be37-8bf438637d00 | note | • Well graded, and 0-100mm size for granular bedding.
60dc4058-e98a-54cb-bc18-042fa8b869e6 | note | • Granular filter thickness >100mm.
1f7c9bb2-5f96-54d4-bc83-74c254f3bb04 | note | Freq - Each lot
3d88c641-9885-58e4-9637-adf1585a0a01 | note | Key - I
4d4d895b-70bd-55db-9036-7083cbefbc65 | note | Resp - SE
0d40a188-550d-58dc-9fb5-615be9abfd6e | date | Inspection Date:
| checkpoint | 2.5 - Preparation of underlying surface
6d3d9582-f428-517f-a060-b7abf414b109 | note | Ref docs - VR713.04 VR210
a4d858a6-ba00-5391-b158-837b3e6cf36b | note | Acceptance criteria - Beaching placement surface shall be:
6dfa716d-1f71-54c1-adc1-133b25cef46b | note | • Excavated, compacted, and trimmed to provide a FSL of beaching in accordance with IFC design.
23364242-8ee9-50a3-b468-38c2b95b644a | note | • Any scours or hollows backfilled with class 4.
184f5bef-15fc-5e57-91bc-0d04acf5128e | note | Freq - Each lot
ac5d3f17-4d22-516b-a00e-069ae630fc73 | note | Key - I
e36f08df-3829-5e53-a449-0077c3eed66b | note | Resp - SE
63cc2de6-44fe-59d5-b467-56f71a02656a | date | Inspection Date:
| checkpoint | 2.6 - Placing Rock Beaching – All Types
a76b5294-0f53-56a2-9922-45ced3a70c77 | note | Ref docs - VR713.05
3dfbce8d-1fe2-53c6-b164-bd6bd916f280 | note | Acceptance criteria - All Beaching shall be placed such that:
51f35258-6a14-54a0-b256-0671c9338d4f | note | • There is no beaching protrusion >50mm above surrounding ground levels.
750c4374-a36f-578d-9a06-4e411e1a4a3e | note | Freq - Each lot
8a95ce89-2dc5-549e-ace2-b40861dfd6a7 | note | Key - I
8f1ffe0d-697e-5be1-afb0-58ce5718c754 | note | Resp - SE
f7a0932d-f596-5853-9929-17ec3f9ba894 | date | Inspection Date:
| checkpoint | 2.7 - Placing Rock Beaching – Type 1
5f91c845-b50a-5815-9ee3-dc38e8609d78 | note | Ref docs - VR713.05
3ec9e814-073f-5456-a702-6887828771c6 | note | Acceptance criteria - Type 1 Beaching shall be placed such that:
02558cbe-9e18-5553-bd67-52c4aae7a13c | note | • A tight ‘interlocking grid’ is formed to retain each rock with gaps <60mm on average.
c62d1b7f-3373-5b88-bf6e-4ce7091de04d | note | • There is not >100mm height variation along a 3m straight line along the finish surface.
d387b37b-2cf9-5a56-99c9-5c73f1db16e8 | note | • Voids filled mid-height of rock with topsoil.
0c8a4f71-a1a2-556c-abe0-5b9fb2db8e92 | note | Freq - Each lot
dbf4eba2-5431-5359-85ee-385ed03eab37 | note | Key - I
46921a60-507b-561e-b878-87ca1638d73c | note | Resp - SE
da47f7d0-968f-5f86-a871-be304575d922 | date | Inspection Date:
| checkpoint | 2.8 - Placing Rock Beaching – Type 2
df90921d-e018-5878-9946-3cb11b65c500 | note | Ref docs - VR713.05 VR13.06
61504b1f-9727-5690-bb0a-170145054b64 | note | Acceptance criteria - Type 2 Beaching shall be placed such that:
9f06263a-c12f-5402-9257-3102ae781751 | note | • An initial bed of mortar infiltrates the joints VR13.06.
4027ec98-fcb2-54a0-bc8c-e02f573eb95b | note | • Width of joints vary are between 10-60mm, and not exceeding 40mm on average.
8c77d6f9-e978-5502-9cfb-93b61c0ab921 | note | • There is not >75mm height variation along a 3m straight line along the finish surface.
7f07dbf8-d06b-501a-9ee1-5bae46e0117d | note | • Joints are free from debris before grouting.
42a5428a-b11c-5153-aa11-6bf71eca5cbf | note | Freq - Each lot
2c8ce4b2-e440-50bb-8faf-09604ce6ec2f | note | Key - I
d02ab3a3-83cc-5bbb-97f7-fd1aa305fc0c | note | Resp - SE
2f7dd1d8-eb5f-5f61-8b48-0db7bd7bc70c | date | Inspection Date:
| checkpoint | 2.9 - Placing Rock Beaching – Type 5
a0e19b2a-a566-5ffa-8f83-c06fd21bf848 | note | Ref docs - VR713.05
c3076fe2-5da5-5911-8a48-0fa9b2892ac2 | note | Acceptance criteria - Type 5 Beaching shall be placed such that:
01e0fdf3-2481-54b6-88e7-d8c6803cf6d5 | note | • There is not >75mm height variation along a 3m straight line along the finish surface.
61db753c-1c3c-5353-a4b8-0df44d6cb7bf | note | • Rocks are tightly interlocked, and voids are sealed with smaller rock for stability and sufficient water flow.
d7abf4c0-b2e9-5ef1-8ce6-a2e588865c29 | note | Freq - Each lot
84973cb3-8140-58dc-ab8a-84af882ff56a | note | Key - I
b6c22d95-85c1-5421-8de9-87250f5f051c | note | Resp - SE
83ace9d6-4beb-5fb3-bcc2-deab354f29ff | date | Inspection Date:
| checkpoint | 2.10 - Grouting – Type 2
83ba6197-09a2-54ad-a674-3de775bbc3c8 | note | Ref docs - VR713.06
b941d789-500b-54b9-bf62-02e0f982b339 | note | Acceptance criteria - Type 2 Beaching grouting shall be:
dc7a2054-541e-5864-ac43-85dcf157b396 | note | • With mortar one part Portland and 3 parts Sand by volume and thoroughly mixed with water.
952fedf9-fade-5075-a772-c10d953898f3 | note | • When air temperature >5°C and kept moist for 3 days.
88131b10-ca86-5a68-920a-9dd8f3b44b2b | note | • Such that joints are neatly finished and final mortar shall not be within 10mm of finished rock surface.
b3df3d8a-c63d-525d-ae73-012078b3592e | note | • Final grouting ensures mortar is firmly tamped into joints to fill the joints 20mm below general top of beaching.
c02592fb-888c-5c5a-a164-4f014892e473 | note | Freq - Each lot
02e9723b-d01e-5b33-b397-24b3a3c47e14 | note | Key - I
ab132ac7-e1a9-51cd-8425-592d9628ddf8 | note | Resp - SE
9474709c-1b28-5b6f-990c-4951e07ed150 | note | Remarks/record - Mortar Mix Product Detail
73b03536-0b22-5906-988b-8967144a02a4 | note | • Grout Product Detail
6ce7c686-bf17-576b-8950-18516222e2db | date | Inspection Date:
| checkpoint | 2.11 - Toe Walls – Type 1
b2c2887d-ca95-5ab1-bc5d-356f9b8ffeef | note | Ref docs - VR713.07 IFC design
43bab7bf-23e0-5368-9bc1-3da81ad8a75e | note | Acceptance criteria - Type 1 Beaching Toe Walls shall be:
d4cd56f8-660f-58f2-990a-ee51c663ddd4 | note | • Constructed where rock beaching slope >1:5 and be 600mm wide x 600mm deep.
09a89515-9172-5744-8654-2c201c141d30 | note | • Constructed 300mm wide x 400mm deep at front face and reinforced with L8TM trench mesh top and bottom.
b806c852-ed03-58bc-bb3b-a78e291aa0f9 | note | • Lined with geotextiles and filled with hand packed rock with larger voids filled with smaller stones.
c2557b70-5b43-548d-a729-826e2d4b2e2d | note | Freq - Each lot
20b1ce25-be90-5757-aa9b-f2b686e8d9c3 | note | Key - I
ee2e3e0e-f541-54bd-946f-4d63b005b59e | note | Resp - SE
a8225b38-3e3c-54f8-8850-b3cb4f80911d | note | Remarks/record - Dockets
6779d3ca-46ab-5dc1-9d1f-6aa1ca0b10fa | date | Inspection Date:
| checkpoint | 2.12 - Perimeter Walls – Type 2
86bd5a03-061e-5d8b-bb10-b96b181711a2 | note | Ref docs - VR713.07 VR703.11
815e3f12-96f7-5867-9680-07a5d5b35592 | note | Acceptance criteria - Type 2 Beaching Concrete Perimeter Walls shall be:
45943265-d13d-5c8c-a013-9c5fbc312152 | note | • Constructed around exposed edges of beaching.
54d39f27-e8a4-5811-b4e4-b9c1a1622c58 | note | • N20 strength grade.
71ec2964-1a8f-5bfe-a00b-7b01cbc41032 | note | Freq - Each lot
0f28ba94-b3ea-5bff-a536-ad05c82b3fd8 | note | Key - I
81320b2d-a2fe-506e-96ba-7508edd86338 | note | Resp - SE
19244ce7-d9b0-5a39-9965-63a5441dd4ee | note | Remarks/record - Dockets
92404713-8a23-5a26-8601-fc0e18f74a75 | date | Inspection Date:
| checkpoint | 2.13 - Drainage
e5a291ea-12a3-5a9c-be4d-dfc6061c5add | note | Ref docs - VR713.08 IFC design
dbcdfb22-80d1-5133-9ece-b58b0616cfe3 | note | Acceptance criteria - Where specified or shown on the design shall be:
8f4e3b28-e591-592e-b259-a6a52add07df | note | • 100mm diameter PVC pipe laid down the batter in a trench beneath the bedding to discharge immediately above the top of the toe wall.
0215c77b-62f0-59d9-b8a1-5b6c995c56ee | note | • The pipe securely bedded within the backfilled compacted crushed rock or natural gravel trench.
aa9d2854-2c47-59b1-a279-1bfff0babbc7 | note | • Weepholes consisting of 75 mm diameter PVC pipes placed through the beaching at 2 m centres immediately above the top of the concrete toe wall and cut off flush with the face of beaching.
cf181490-3c83-5f7a-80f1-7cb5c41a9425 | note | Freq - Each lot
a8dc5346-36a3-5ec5-a71c-39506d9d2a05 | note | Key - I
5de7886c-7008-59a3-88e4-30c8670cd13b | note | Resp - SE
ae542ec1-d621-54cc-901c-615ce2b8585e | date | Inspection Date:
| section | 3.0 Completion
| checkpoint | 3.1 - Cleaning
5acbd415-7417-593e-a89e-f07902512163 | note | Ref docs - VR713.09
2bc6d489-692a-5c93-9f7c-675e4ec29a2f | note | Acceptance criteria - Post-completion, beaching shall be cleaned, and foreign material and discolouration removed from surface.
2d8980e8-7c3b-5d75-9b10-ec4b8f011973 | note | Freq - Each lot
934cbb18-47ae-5320-a290-5d6f4f7cee5a | note | Key - I
7357a87d-a9b1-5373-95a2-b099bdddc104 | note | Resp - SE
9fd521ee-4843-548b-8f06-3ed6a5870e4d | date | Inspection Date:
| checkpoint | 3.2 - Conformity with drawings
4ff32819-edf4-50d0-abf0-e9058fb07338 | note | Ref docs - VR713.02
47aee2c1-7a6b-5727-8606-0ee5f833025a | note | Acceptance criteria - Beaching finished surface conforms to the levels, lines, and grades as shown in IFC design or specified.
f4b65a0d-b2f0-5bc6-a221-e7ea16c321d3 | note | • As-built survey completed.
38c3f6f6-fbd1-50b6-b8ea-465ac4573bbd | note | Freq - Each lot
adf29bf0-7cca-56cf-93ab-3d1f8e7e4f7d | note | Key - R
70b8a114-ab28-5daa-bcf5-c51227c3b9bf | note | Resp - SE
97151bbe-abf6-5f34-99af-966da6c16563 | note | Remarks/record - As-built Survey
1419f1bb-a097-5c34-8da7-da6380f6160f | date | Inspection Date:
| section | 4.0 Work Lot Close out
| checkpoint | 4.1 - Product Non-Conformance
24c55196-1d09-5d11-a862-788b48746571 | note | Ref docs - CQMP
17118027-966c-598c-b4ba-db1b4ce2e62e | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
87f668f1-9b8e-5175-bce7-b226284b774e | note | Freq - Each lot
c451ad61-d0c4-59b0-b0b1-20956470f329 | note | Key - R
3874b381-66dd-597b-9e76-beb9af4b421d | note | Resp - SE
b3243a0f-34f7-581b-b9cc-233b4bd0f7bb | note | Remarks/record -
d7a7aa05-ddb6-5152-a98d-6e1f2447affe | textbox | • NCR No
b2bfce6f-06d1-58e1-9241-8569c8dde05a | date | Inspection Date:
| checkpoint | 4.2 - Quality Representative to check the above criteria and records to confirm
56ee4264-90d5-5fe3-8e99-e86433058665 | note | Ref docs - CQMP Lot Records
5e196f1a-a1a7-53a5-baee-3b42c1d8daba | note | Acceptance criteria - All above criteria met, and records identified attached.
9dc761f7-9253-5076-a5e3-b58313b5f097 | note | Freq - Each lot
1eb970ac-c92f-5d6d-a882-ee669d1c6fec | note | Key - R
e6e3e7c6-eae0-5d39-97a1-30a7515264e7 | note | Resp - SE
788e9860-796d-56fe-a6c2-696062e33bc4 | note | Remarks/record - Completed Checklist (if applicable) and reports and other compliance records attached.
f884d328-3aa1-5ce6-9806-a1fa6caa896e | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0040 Asphalt Primer/Spray Seal | itp | 1630-P200-SYM-QAC-ITP-0040 Asphalt Primer/Spray Seal |  |  | 98488353-23db-4d60-8e4f-f824bf1063d5
| section | ITP Details
| checkpoint | ITP Details
c90be9e3-89b1-5e7d-98ca-814ec8b52496 | note | ITP No. - 1630-P200-SYM-QAC-ITP-0040
a47e0d7a-b2ef-5955-9f4c-b101a99e3533 | note | Rev No. - 00
77b6a57f-6607-5207-a922-4698dc44093c | note | Date of Issue - 24/11/2023
295e9b27-62b1-534d-ad12-0310e950c5a2 | note | ITP Type - New
| section | 1.0 Preliminaries
| checkpoint | 1.1 - Commencement of works
ca94bacf-d149-568d-9cab-30b5694b0792 | note | Ref docs - Sec 408.04 (b), Sec 408.09 (d), Sec 173.02 1130.03d
0bd0f3e1-e40a-5ec9-b42a-811517157dd3 | note | Acceptance criteria - Prior to the works being carried out, the Contractor shall provide written confirmation of the works that will be undertaken the following day and obtain agreement from Superintendent to any variation in the design rates of application to those provided under Cl. 408.13(a)
e3f456ef-be76-5ec6-9f4b-c61f095a9429 | note | ○ Works shall not commence until the Contractor & Superintendent have agreed that the road or pavement surface is fit & ready for surfacing no more than 24 hours prior to works occurring
5b85f18d-b81d-53ea-860c-7c3333f117db | note | ○ V/R 310 shall be satisfied for initial seals
c25c0238-edee-5b57-8389-a5aff16e9a22 | note | ○ Priming and initial sealing shall only be undertaken when the prevailing weather conditions, when assessed in accordance with AAPA HSE Guide No.8 – Environmental management when spraying bituminous materials, have a risk rating of ‘low’ or less and appropriate work practices to minimise risks are in place
936dc8b6-9543-54b3-b45a-a75f9b88923a | note | ○ Unless otherwise specified, the extent of each lot shall not exceed one day's production
a905857e-bec7-5e9b-870c-261c97dea534 | note | ○ Priming must not be carried out within 24 hours of forecast rain. (PS 3040.06h(viii)
ad25e884-02d4-5242-b583-ef0f5e60999b | note | A pre-sealing workshop is undertaken to present the below including the sealing subcontractor, the Superintendent and technical representatives from DTP prior to the preparation and sealing of any base course pavement layer.
e4f703a4-5a87-5aec-aff7-1e9eb3af6b10 | note | (A) pavement surface preparation;
5a2249ff-05b9-5352-9509-cc56b924adf5 | note | (B) assessment of priming and sealing application rates;
36adb031-f5ee-5281-b16c-18139f3afe3d | note | (C) the application of traffic on the sealed surface;
85ffe769-8aa1-5e71-9e0f-fb70ce57aac8 | note | (D) proposed periods for sealing;
59d30b79-3b35-5b2b-ab5c-ccb74ad4c97b | note | (E) protection of completed seals against rain or drop in temperature;
705983dd-e6ab-5d85-8d01-12f4dd12203a | note | (F) removal of aggregate;
55c5b9a2-8bf6-5940-9c1b-7856c3236327 | note | (G) Pavement Marking; and
ba7c94cf-d3f7-5d97-a503-a13c8c574520 | note | (H) general maintenance of the newly sealed surface. (Table 1067.11, PS 3040.06)
38861f44-c232-5c8e-bf00-3d9538cba5b0 | note | i) Construction program includes details of the sealing works.
73ac26bf-ea02-5339-b306-e8f10b7d7e25 | note | ii) a detailed program of planned sealing jobs on each day of the following week has been submitted on each preceding Thursday for Superintendent's review during the period of the contract. (VR 408.04b)
e5be32ef-3c28-5b9a-85d8-7a185279eef1 | note | Key - H
92205cef-b231-5bbb-baa0-fc10b854ee1c | note | VicRoads Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Aggregate Spreading (Forward facing)
ce04140a-e651-5176-8607-272f98396290 | note | Ref docs - Sec 408.13 (f), Sec 408.13 (d)
a186945f-c88f-5eae-8655-a6c4bcd4f701 | note | Acceptance criteria - Prior to commencing works - All aggregate spreading or discharge shall be undertaken using forward aggregate spreading & discharge plant.
c72d9b94-8fe1-51d9-be97-8edbff166b87 | note | ○ Minimum Temperature to meet criteria as set out in Table 408.131
8547a7d3-c20f-5b6e-adac-46757eb27d3b | note | ○ Minimum Temperature shall not apply to Strain Alleviating Membrane
9d3d4069-cc7d-50ac-8b83-9e7c87a64ab9 | note | ○ Forward aggregate spreading plants have been endorsed by the DTP - Chief Engineer (Roads). (408.13f)
2390f361-d19d-5a21-a786-0f1b63ff0d7a | note | ○ Aggregate stored at stacksites are managed to avoid contamination from other materials on the stacksite or from other sources such as vegetation, debris etc. (VR 408.12a)
787aef92-66bd-5ede-853d-21eadaddaa7e | note | For pre-coating material -
c298e817-2c70-5839-9711-3647e4e54ffa | note | i) Pre-coating material is conforming to VR 831.07 requirements.
40207d30-e98e-5b90-9820-bd6d5e1814a9 | note | ii) Proposal to use alternative pre-coating material to the requirements of 831.07 are submitted for Superintendent's review minimum 10 days prior to use.
f66c5fe0-ceea-5990-94e7-024f5a11290b | note | iii) Min. 3 years field performance has been submitted prior to using any proprietary material.
d9c31418-109c-55c9-893e-d8f98c6d33d0 | note | iv) Untried material has not been used without Superintendent's approval. (VR 408.09b, 831.07)
bcb89ba2-d727-5aac-a5f0-46c723de2a01 | note | Key - S, I
| checkpoint | 1.3 - Design Rates
331ed6ae-f086-5de8-b23c-341d5b853006 | note | Ref docs - Sec 408.13 (a), Sec 408.07, Sec 408.15
c79a5550-4510-5afa-938a-79a7c569cb2c | note | Acceptance criteria - The Contractor shall determine the design rates of application in accordance with the procedures set out in the Guide to Pavement Technology: Part 4K.
09d81e00-ef20-5dab-8cc0-3814b8fde9bc | note | ○ Rates shall be expressed in L/m2 and residual binder at 15°C.
aad0776f-ee56-5777-b726-ae309cfcf2e8 | note | ○ At least 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
0db7b2e9-6666-5fac-8af9-8431ecad6976 | note | ○ Prior to commencing works Calibration Certificate to be provided.
9c139c44-1d82-59b4-85c4-8a8b746a2211 | note | ○ Detail design calculations are shown in design. (VR 408.13a)
cf155230-f19a-56d0-8162-c146118e61a6 | note | ○ Variation in binder and aggregate application rate is calculated and submitted for acceptance of the work. VR 408.15
ac0d1c06-b71d-5fb6-a4c7-b0e7dc56f21a | textbox | Acceptance: |  |  |  | litres/m2 at 15°C
3cd2a89b-80f0-53ae-9530-3eb0b86c8a35 | button | Acceptance | Yes,No,N/A
09a6d85b-4a97-5d70-8de3-1b8abc6e3d18 | note | Key - H
7c6431d4-e19a-5576-813e-80c8156deb9c | note | VicRoads Key - H
70711518-f7d0-589b-a0f2-6013e68bdc45 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
fa4a4b27-fb4b-5d8a-8f5c-c9c3e5f848ea | tickbox | Desing Rates received and attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Air temperature
356af355-a047-50d8-bcc9-14c95f7ca1b1 | note | Ref docs - Sec 408
91a490ef-c9f1-5071-a143-bb0aeee94a04 | note | Acceptance criteria - Is the air temperature suitable for the application?
7d942766-cbd8-5088-bf31-d062cf76f9dc | note | Initial treatment:
df9b4155-9eb3-503d-b0f0-008707974921 | note | Primes - 10
7df84e66-f5df-558b-8c1e-bedcf491bcd2 | note | Primerseals (single/single) - 15
c5869ec6-670d-59f4-b59a-8d6d1bd056ee | note | Primerseals (double/double) - 10
eb0f288c-f133-58a5-852b-168c2c455261 | note | Reseal treatments:
a8c6774f-ca05-5190-a80e-adbe712df522 | note | C170 and crumb rubber modified PMBs - 15
e80227b9-e30e-5bed-8b70-fbe6af17ab7b | note | Other PMBs - 20
9793e475-6811-5e03-a5dd-7b5d448aefb8 | note | Geotextile reinforced seals - 20
3ab1f9e8-fb4f-5986-90a4-5c914712af02 | note | Recommendation - No rain forecast within 48 hours of sealing specially in routes of heavy traffic. (Pavement worktips-18)
40f1565b-d5d7-5ff7-b3af-f70516722937 | note | Acceptance -
6e92dcb2-e1ae-5250-943a-f391cd69788f | textbox | Air |  |  |  | °C
d965fa59-3840-5867-9d9e-530a47115b6f | textbox | Pavement |  |  |  | °C
11d7bbd0-c056-5199-bad8-3885002cf050 | note | Key - H
1d7b6d35-7cb0-5415-813a-df13bdb07a6f | note | VicRoads Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Written confirmation
f8c1b1ee-0464-5f2d-893c-06f8de871983 | note | Ref docs - Sec 408.03
327f7311-7c40-5b41-9b7c-8c63d002186f | note | Acceptance criteria - Has written confirmation of the works been sent to the Superintendent with confirmation received the day prior to application?
3f410091-8ceb-59a4-8c65-01d17d3060c4 | button | Acceptance | Yes,No,N/A
891ca765-e754-5f44-b068-0723ce7d0978 | note | Key - R
16d14633-e612-5a47-8a59-a7626dd4becb | note | VicRoads Key - R
| checkpoint | 1.6 - Bitumen
5d3e593d-caf3-5782-9611-cb56f03f7e0f | note | Ref docs - Sec 408.08 (a), Sec 480.08 (b)
10432aa7-0fab-5500-a5a2-57f84cd6349c | note | Acceptance criteria - Bitumen shall be Class 170 complying with the requirements of AS 2008
9a879cea-0b48-5d77-905e-029ee04cacf8 | note | ○ C170 incorporating ≤ 5 Pts CR is considered to be an unmodified bituminous binder.
b04587de-923b-5678-9f53-3dbeb1656066 | note | ○ Bitumen emulsion shall comply with the requirements of AS 1160
c2eb3e9b-4113-5347-9f44-3e04cf13cd46 | button | Acceptance | Yes,No,N/A
bb26c212-740f-53ef-96a2-689998d10bf2 | note | Key - R
f5a2e4d3-9370-55be-98a2-c5a81b7a73ef | note | VicRoads Key - R
a987a0d6-c1c0-56fb-9416-e57dcd147354 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bece7d71-51f2-5d77-bb9f-386884a76414 | tickbox | Compliance Certificate received and attached
| checkpoint | 1.7 - Seal preparation
46cf5c33-d37f-576e-80ab-da286b5921b1 | note | Ref docs - Sec 408.03
e57edccc-a7a3-5142-984c-86feb445c353 | note | Acceptance criteria - Has area been inspected by Contractor and Superintendent and are both in agreement that road is fit to surface?
416d417f-cf5f-51e2-a3e5-9e4e87323a15 | note | ○ Edge lines/lane lines are correctly marked prior to priming. (VR 310.02)
9fd98a06-73be-539e-8a5a-e64b0acc5b89 | button | Acceptance | Yes,No,N/A
b35885b9-e1bf-5e08-b5be-b7b8a0c2e644 | note | Key - H
4b608426-4944-5bcd-9b58-5e01a45ea445 | note | VicRoads Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Materials supplied
4ad0df5d-929d-55f2-a570-233786c484f3 | note | Ref docs - VicRoads Sec408 Supplier Information, Sec 408 (c), Sec 408 (e), Sec 480.09 (a), Sec 408.09 (e)
06ad4626-b119-5a6d-b7c6-cfde73e95b09 | note | Acceptance criteria - The bituminous material, crumb rubber, and aggregate supplied all conform to VicRoads as per supplier delivery?
1f53c75c-dccc-53cb-92a6-5b3bd297175d | note | ○ Cutback Bitumen - Cutback bitumen shall comply with the requirements of AS 2157
fb79fbf8-3825-5ac9-90c2-bbb519b5f03c | note | ○ Primer - Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
4debe1b5-e6a7-50ac-91f4-228ca13a1d00 | note | ○ Adhesion Agent - Satisfactory field performance. When adhesion agent is added to the binder, the total volume of adhesion agent ≤1% of the binder.
3e98439c-287b-5044-ba7c-ca8e5390f0d4 | note | ○ Geotextile Fabric - Non-woven needle punched fabric - min weight 135 g/m2 for seals of nominal size of 14mm and under, and 175 g/m2 for seals of nominal maximum size of larger than 14mm, melting point > 10 C above max binder spraying temp.
091f40d5-01a0-50d8-828f-66a458ebb999 | note | For sealing aggregate -
0107d9ee-b927-5ce8-8a25-2f7759bcbc10 | note | i) Each lot at the quarry has unique lot identification number and is mentioned on the delivery docket.
6912bea6-40cb-576f-9e31-ef903fc6382d | note | ii) Aggregate testing is done not more than 90 days prior to delivery. (VR 831.05b)
fe631eab-e9c9-5176-b2c6-4a4a866aca66 | note | i) Cutter is conforming to testing requirements in Table 408.091.
e30db467-c26a-5b5c-ae16-92e7ea6c74ea | note | ii) Min. 3 years field performance has been submitted prior to using any material non-conforming to Table 408.091.
a43a2271-7495-5f56-89f9-3a9556c30cdd | note | iii) Untried material has not been used without Superintendent's approval. (VR 408.09d)
e4670f94-3056-5c66-b7fe-23231ba43d77 | button | Acceptance | Yes,No,N/A
e831a87c-b01b-5ecb-abba-c21c01465aae | note | Key - R
c685b0ff-27f3-56c2-8f74-5ca06c6303f1 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
cc991f15-1dd8-5f72-a932-2415593b6775 | tickbox | Material documentation received and attached
| checkpoint | 1.9 - Binders for treatment types
fcb121c0-47ad-528b-9fb4-598d6c15b734 | note | Ref docs - Sec 408.10 (a), (b)
c802f0bb-fd7f-5d04-8699-50d0ec093d27 | note | Acceptance criteria - Initial Seal Binder - the binder to be used in Initial Seals shall be a suitable cutback bitumen, bitumen emulsion or a 9% (10 parts) crumb rubber modified binder. Other modified binders may be used subject to approval of the Superintendent.
c46b9474-f3c9-5138-8439-52c980dbbaf0 | note | ○ The Initial Seal shall be waterproof and capable of adhering to the pavement surface while retaining sufficient binder on the surface to hold the aggregate in place. Final Seal and Reseal Binders - Unless otherwise specified in Table 408.191, one of the following binder classes and seal sizes outlined in Table 408.101 shall be used.
236a482c-f71f-5576-b1b4-8291f5314046 | note | ○ Pavement temperature is adopted instead of air temperature to decide the percentage of cutter to be added. Variation in cutter among shaded areas and unshaded areas are carefully considered.
d40c3f6f-8275-5a61-b9c0-fd0c077c0d91 | note | ○ Prime is cured for at least 72 hours prior to sealing.
69e9e2e3-a845-5008-be5d-2137e3ac3509 | note | ○ Aggregate pre-coat should be dry. If the pre-coat is wet, amount of cutter is carefully reduced
b33fc9bf-abea-5486-8951-d0eb7217892b | button | Acceptance | Yes,No,N/A
cc72ed4b-8bd5-5aeb-aae9-7caf415e9434 | note | Key - W, R
| checkpoint | 1.10 - Aggregate
dbef9aa4-c7aa-5f38-bf4b-33f1dbb0413c | note | Ref docs - 408.09 (b) 408.11 (a), (b)
09e2fdca-61e5-57e8-a2de-ddc90a3f3baa | note | Acceptance criteria - Aggregate shall comply with the following Standard Specification Sections:
05ebaea5-5185-5479-8e7c-ab2bdaf106da | note | ○ 801 – Source Rock;
182494ea-342a-5b3f-93aa-f7ad5b6ab8c9 | note | ○ 831 – Aggregate; and
8ad54dbb-fefc-59da-ac39-9c6d156c30d3 | note | ○ 832 – Sands
e9e8acf8-1948-5889-8a02-bd64671ccf68 | note | Maximum lot size 350t of same class and size
a10e7ea6-831c-5a94-84e5-cb84c483ea2f | note | Acceptance of Aggregate - If all of the specified test results comply with the relevant requirements of Clauses 831.04(d), (e) and (f) the aggregate represented by the lot will be accepted
96cd8e3c-1605-5296-81ec-be056665bb53 | note | ○ Aggregate which does not meet the above acceptance criteria shall not be supplied or delivered.
ed69c269-dc5f-5f2c-8555-8d4bc7dd7ae1 | note | Aggregate Pre-coating Materials - Distillate based product, cutback bitumen, emulsion based product or proprietary product.
f6e946f0-732a-5ee3-a172-d865ef5250ba | note | Supply plant pre-coated aggregate from supplier or field pre-coated aggregate from stack site
78833202-5f32-5112-9044-278105125b6f | button | Acceptance | Yes,No,N/A
33958b4f-28f2-5ad4-bd56-93b1db2799eb | note | Key - H
becbec33-0e4a-58a1-ac7a-212e917fb23a | note | VicRoads Key - H
48a69154-06da-58e3-a961-42b672fa9dc2 | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
a496c30f-8fc5-5f08-bb02-c27fa7c54707 | tickbox | Test Certificate received and attached
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.11 - Conformance of previous layer
29e9e484-4eed-5e05-b9a8-3e9385df4180 | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
0f51448f-a90a-5c1a-9250-a42323a5c5cf | button | Acceptance | Yes,No,N/A
2b9067d1-f41a-593a-a44b-d34de436a417 | note | Key - S
| section | 3.0 Application of spray seal
| checkpoint | 3.1 - Surface Pre-treatment
cfe966a2-3cff-50c6-9d7a-5db982f737fc | note | Ref docs - Sec 408.13 (b)
383e95a2-64c2-5b33-b531-342c6dfa64f2 | note | Acceptance criteria - Correct variable surface texture shall be allowed for by contractor and carried out as part of the works to meet the requirements of Surface Texture and Aggregate Retention. Refer Tables 408.191, 408.152, 408.153
8f542386-7cf3-588e-b4ba-917feefa12e7 | button | Acceptance | Yes,No,N/A
256c944b-de44-54b0-9c2f-b6439f3aa738 | note | Key - S, I
| checkpoint | 3.2 - Rolling of Aggregate
ccceeb42-212e-565f-8920-bdf60460963e | note | Ref docs - Sec 408.13 (g)
54736086-ea8a-5e99-9b34-15be60831ad0 | note | Acceptance criteria - Rolling of aggregate shall:
dc0cf305-979b-57a5-8ac0-2ce03fb17c9a | button | Acceptance: be undertaken over the full width of the pavement being sealed including any untrafficked areas | Yes,No,N/A
405bde5a-14cc-5dea-b06a-28ec66d9482c | button | Acceptance: be undertaken by static rubber tyred rollers unless otherwise specified or approved by the Superintendent | Yes,No,N/A
8c7e3d3e-3dc4-5861-ac61-7bbde226172c | note | Key - S, I
| checkpoint | 3.3 - Sweeping of Road Surface
b9f3de7f-8898-53ee-86e8-a5c92dca0cc4 | note | Ref docs - Sec 408.13 (h)
69753ff1-2ad3-5d3f-8f06-29bdca7488b1 | note | Acceptance criteria - All surfaces shall be inspected prior to the application of a sprayed seal treatment to ensure that a clean surface is available for sealing works that is free from dirt, loose aggregate and other detritus
bbc36179-8f10-508f-9f28-3dabe031336a | note | ○ For multiple application treatments, intermediate sprayed seal layers shall be thoroughly swept to ensure that loose aggregate particles are removed prior to the application of the subsequent sprayed seal layers. This includes areas where an overlap of aggregate has occurred during the spreading operation
a1f0051d-8be4-57f0-93c5-227c0d076fa8 | note | ○ Traffic speed is controlled as per VR 166 as long the sealed surface is not swept. (VR 408.14)
64c0a68c-d113-5d77-b270-eb503013420b | button | Acceptance | Yes,No,N/A
f5e94cdd-2c69-5eb0-b19f-2711fad700cc | note | Key - H
dc9be46b-6b0c-5e62-8b59-f199f4d57561 | note | VicRoads Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Geotextiles
532baf10-f89b-51b1-a248-8b30f8faba03 | note | Ref docs - Sec 408.13 (c)
a14ae42a-ce72-59d3-8c77-4c0134cfce97 | note | Acceptance criteria - Geotextile fabric shall be fixed to the pavement surface free of wrinkles and/or folds.
0a27a048-2739-5f48-8932-7785ab62545e | note | ○ Transverse joins shall be butt jointed.
09344ec3-1949-5ce2-84a9-f84851cd08d7 | note | ○ Longitudinal joins shall be overlapped approximately 150mm and be located along lane lines.
ee47a943-a876-50fe-b7c5-2e99e8fb57e5 | note | ○ During placement of geotextile -
a1fdc1f9-8ee7-594c-94e6-d5f6006a1bdc | note | i) Additional binder as per seal design is added at the joints.
ef7a5b58-a3ef-5bf5-8d79-5c802178f570 | note | ii) Bond coat is applied as per seal design extending approximately 100mm beyond the geotextile.
f7f89d93-a9b7-5a1f-8d8b-60361f17a932 | note | ○ Recommendation - Geotextile Reinforced Seal is not programmed after 2nd week of March, when there is a rain forecast within 2 weeks and temperature is below 20°C. Coarse surface texture>2mm is corrected before applying Geotextile Reinforced Seal.
95835e58-92a1-5d09-9967-95b82836a0fb | button | Acceptance | Yes,No,N/A
b09846f7-d119-5c5c-96ad-e0395e7de2a9 | note | Key - I
| checkpoint | 3.5 - Removal of loose aggregate
803fb9dc-925b-55e8-a802-8842c71e2e83 | note | Ref docs - Sec 408.14
d2a279b5-09df-589b-8090-669e6d772b2e | note | Acceptance criteria - All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
2ea5d115-d1cd-5377-8bac-9cb6b4d3ed28 | note | NB: For seal of nominal size ≥ 10mm, < 40 loose stones/m2 to remain after removal of loose aggregate. For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
7c883cb5-2208-5667-b078-eafad2db5a70 | button | Acceptance | Yes,No,N/A
522c1603-6179-51ed-9633-2b03abc41397 | note | Key - I
| checkpoint | 3.6 - Acceptance of work - Aggregate retention
d18899c6-14b9-575e-b0ef-fd4bb58fc6a6 | note | Ref docs - Sec 408.15 (c)
625334ac-beb0-5acc-992b-e2dd5763616c | note | Acceptance criteria - Does the seal meet the visual inspection for aggregate retention as per Table 408.151
a10bf15e-c4eb-532d-9958-2fffb26801f1 | button | Acceptance | Yes,No,N/A
002f0f9a-e769-58af-8a89-b338feb6404b | note | Key - I
| checkpoint | 3.7 - Acceptance of work - Visual uniformity
68a09b3b-c189-500d-a2fd-16c197882a84 | note | Ref docs - Sec408.15 (d)
1ba0b71e-58dc-5f33-8924-f874fbdceacb | note | Acceptance criteria - Is the seal uniform in colour and texture?
afbe439b-1943-535d-abcc-b328e939fe43 | button | Acceptance | Yes,No,N/A
6b194fa8-3d45-5876-a326-baca7fb0f7fa | note | Key - I
| checkpoint | 3.8 - Job completion report
7de8d855-1685-5812-93e8-c38bb3eb65d5 | note | Ref docs - Sec408.17
a830711e-9ae9-5e48-bb8c-b37855fd86bb | note | Acceptance criteria - Job completion report (Spray Sheets) to be submitted within seven days of completion of sealing works.
5013d4ea-47dd-5c30-822c-10ab80a61144 | button | Acceptance | Yes,No,N/A
39434ffe-467f-52ec-971e-9e94d5639ba0 | note | Key - R
3947d683-7c5d-507b-8d6b-1668e854ab1f | note | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
a10da649-6f6b-57ff-b888-99e1814f5db4 | tickbox | Attach job completion
| checkpoint | 3.9 - Maintenance of seals
18b9500d-c431-59ca-b4b9-3a60dae1f410 | note | Ref docs - Sec408.16
3350931f-1ae0-5950-95e8-53e4bbe6fbba | note | Acceptance criteria - The contractor shall be responsible for the monitoring & maintenance of seals from the time of application until the end of the defects liability period.
20a66e39-42af-5857-b7ca-5136d9d459d8 | note | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work
1b969ca0-8e04-58e3-9924-3b49e1c78a86 | note | ○ The Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work.
a7e60433-3b56-5230-95cd-51cee9147afb | button | Acceptance | Yes,No,N/A
f4ca1e45-b1d3-51f3-88d2-a251b17a91cf | note | Key - S
bc29b029-a9a0-520a-bf62-2fcc73cb9d5d | note | VicRoads Key - S
| checklist | 1630-P200-SYM-QAC-ITP-0044 Permanent Sign Install | itp | 1630-P200-SYM-QAC-ITP-0044 Permanent Sign Install |  |  | bf96ff7f-1c53-45e7-9e1b-b6fd3d14850e
| section | ITP Details
| checkpoint | ITP Details
2a5c6007-2b32-5b4d-b377-dba1daa33b2a | note | ITP No. - 0044
b987dc5e-4111-50d1-a78d-a59b46618012 | note | Rev No. - 00
1c7683f4-f4b0-5606-904a-552bf93da580 | note | Date of Issue - 15/12/23
b92e1e29-457d-5b59-acf7-9d0113e4fafd | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Safety
c27f5a30-c610-5e71-8ff9-d5580b01899d | note | Ensure that the following items have been actioned:
513be4b3-aad4-5876-92f5-63635a6e0cb8 | note | – SWMS if applicable
55a884d6-0843-5b28-bfcf-f3d37a342a0c | note | – Plant Pre-start Inspection
ba5885ef-bbb5-58c8-ad3e-196c56143ba4 | note | – Service locations identified
b7018383-3611-5668-a468-82eb73c9cd5a | note | – Traffic Management Plans (if required)
b7903a5c-d3a7-5498-b870-aef0d6c19ada | note | – All staff inducted
749b820a-8879-5451-8bcb-13c4c490fc33 | note | Ref docs - SMP
2df3e7e5-7ea0-5f4f-a2b8-6d32ecab62b6 | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
20a5201c-fb39-5ef2-aed4-12e325de41da | note | ○ Plant inspections completed and entered.
44e7d64e-d7a9-5ed2-bc2b-d737743a2bf2 | note | ○ TSA training completed. Pre-work briefings completed.
fc6b8ea6-9062-54b2-99f1-aa3e2f41eab5 | note | ○ Service Diagrams available and services located.
8feda44c-bb49-57a0-9bda-027514f027d4 | button | Has all of the above been completed? | Yes,No
d48804cd-9a48-5c35-b6e0-b62d6012f043 | note | Freq - Once (Pre-Start)
e3bb6001-137f-50c6-a792-3f7f46e0e643 | note | Key - H
d209310e-df91-5f72-94b5-fca585bebb92 | note | Resp - SE
| checkpoint | 1.2 - Relevant Permits Acquired
8c30b39c-4f1c-5b10-8aeb-9e93c8d0073e | note | Ref docs - SMP
834c702b-ae56-5d6b-a0a5-47e110b889fa | note | Acceptance criteria - BYDA / Excavation permit
27c460b4-886e-5045-b2cc-97c2fb1f21a6 | note | – Penetration Permit
6e045453-b540-5717-8ba0-e2598de4c687 | note | – Working at Heights
68a73ff1-4ef4-5f2b-a669-312194215446 | note | – Lifting Permit
ef6c76ba-af20-5105-b4ee-fba22a59492a | note | – Hot works Permit
b6d572d8-8bf1-5671-a588-40b96e0382aa | button | Has all of the above been completed? | Yes,No
5c854b3f-3e24-55d7-b095-45b1de655e1d | note | Freq - Prior to start of works
f4cbab01-df3d-5372-846b-b12e8db43bac | note | Key - H
5c68f9ad-6465-5c27-9c0b-03636fa00792 | note | Resp - SE
| checkpoint | 1.3 - Check Survey Set-out
cf0e5fdd-44e7-57e5-ba13-2fc0f1394f7f | note | Ref docs - IFC Drawings
59469cb3-577f-548e-ba8a-2571b7f5366c | note | Acceptance criteria - Check survey set out is in line with IFC drawings.
e2b01e15-f368-5a27-b7b6-691829e473ea | button | Has all of the above been completed? | Yes,No
cea1585a-6347-5654-a4a8-3a585113fc0d | note | Freq - Prior to start of works
a6d571d0-a258-5746-8809-1190d3a606da | note | Key - H
962ab403-c36c-5d04-9c61-c03391b9ebfc | note | Resp - SE
| checkpoint | 1.4 - Sign Face Manufacture
f5319f4a-0202-5d43-9414-e1e97da09b75 | note | Ref docs - VicRoads Clause 860.02 DoT
ba9bd1fe-abda-5fd3-bca0-5e6ca8260c73 | note | Acceptance criteria - Sign Face manufactured in accordance with VicRoads Standard Specifications for Roadworks Section 860 – Manufacture of Road Signs
7f3ae6ca-df11-57b4-924a-70661b76e911 | button | Does the sign designed meet minimum specifications set out by VicRoads? | Yes,No
0f6f56bc-2b2c-5266-a271-b78ce8844f65 | note | Freq - Prior to starting works
9a8f3086-e41e-537d-8f14-82f9f8f79c5d | note | Key - H
8fd9305d-8500-5837-b2f6-2d2a15b23a62 | note | Resp - SE
68325c6a-7db8-5632-9fd4-4b724ca279d3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
64742fe0-88b7-5092-ab72-ab5d118dcf81 | button | Certificate of compliance from Manufacturer | Yes,No
240d81e6-c055-5449-8f27-94912d42cd88 | button | VicRoads Pre-qualification | Yes,No
| checkpoint | 1.5 - Supply and Storage of signs
ab8734d8-8523-5e95-9d43-1191d62c14a1 | note | Ref docs - VicRoads Clause 714.03, 860.06 DoT
5b4d9e27-c6a4-5b98-a769-9ba8d4b2ffbf | note | Acceptance criteria - Packaging and Storage of Sign to be in accordance with Specification 860.06.
7036e8bb-334f-52d6-9aae-f4abdf87e642 | note | ○ Sign and sign components to be collected from the specified storage location and prevented from damage and deterioration during transportation.
4539c903-32df-5208-afdb-477834dab6ba | note | ○ Signs shall be handled and transported so as to prevent damage to the sign face or other components.
dfce06ae-2203-5a47-a1d0-0902cc506860 | note | ○ Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges, or components, taking into account any recommendations of the sheeting manufacturer.
cbb47576-70bf-5b64-9390-327abeaa40c8 | button | Has all of the above been completed correctly? | Yes,No
d4e42064-3974-5459-a115-8b4626bb3acd | note | Freq - Prior to works start & each lot
9aad939f-535a-5c30-849d-b63b53d82909 | note | Key - W
d3b473a2-8894-5cb7-b3e7-31b1d82f5cb0 | note | Resp - SE
| checkpoint | 1.6 - Post Details
0e596daa-80bd-55fc-b41b-4866440d1b9d | note | Ref docs - VicRoads Clause 714.06 IFC Drawings, Sign and Post Schedule RDN 06-09 TEM Vol 2.02
8927384a-bafa-5e1d-88e6-689b5ef12a07 | note | Acceptance criteria - Post details shall be as shown on the Sign and Post Schedule from IFC Drawings and be in accordance with the VicRoads Traffic Engineering Manual Volume 2.
43ae39d0-b113-5d1f-b76f-be71cd683e18 | note | ○ Refer to VicRoads Road Design Note RDN 06 09 for a list of VicRoads accepted frangible post systems. (If applicable)
b529cd1a-3ccb-512c-886a-ffaa00b822ca | button | Does the post meet minimum structural design requirements? | Yes,No
5a331f37-31a6-5e4d-b3f8-ae9ec779f794 | note | Freq - Prior to works start & each lot
4f1adace-93e1-57f3-96c7-8a5dfb88fae9 | note | Key - H
ad412016-a18a-5c1f-9834-0c92e5a73bad | note | Resp - SE
| checkpoint | 1.7 - Alternative method of installation (If applicable or necessary)
9632876b-a92c-55ce-8f0e-54942d6182c3 | note | Ref docs - VicRoads Clause 714.04
47a3c944-1678-5b22-99e2-a9f5b4d37cca | note | Acceptance criteria - If the Contractor proposes to use an alternative method of installation, the Contractor shall submit full details to the Superintendent for approval not later than four weeks before the commencement of sign installation.
a7ea9048-411c-57c2-a681-a5e47f9048e4 | note | Freq - Each relevant lot
a2b4c36d-62c2-51da-9c06-048ad94f991e | note | Key - R
5b5dbdfd-1283-5364-8f64-442364d06cd5 | note | Resp - SE
696e8d07-3c2a-5bd3-9a6b-7ce05d83bbe7 | note | SI Key - H
a6bff18b-b33d-523f-9195-f0218e49f256 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
f7695f53-9a87-55be-a41b-2dcbb7057bf1 | button | Alternative method approved | Yes,No
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Posts and Foundations
| checkpoint | 2.1 - Location of posts
d6bb4996-73fb-58f0-845a-f7e0607e3ad2 | note | Ref docs - VicRoads Clause 714.06
d14b891d-81e8-54eb-9106-b44d221dd47a | note | Acceptance criteria - The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
ec9cabd9-1e24-5164-9d0a-6c861ae929f5 | button | Has all of the above been completed? | Yes,No
0e3b9431-8d25-5053-b4de-8638b9d6d819 | note | Freq - Each Post
2af6fc3b-8dfb-504a-a332-ff80e7f7f44a | note | Key - H
18ce0211-73ab-5676-8e55-163146a23399 | note | Resp - SE
bb1572c5-0ba6-570a-9e04-f20d547b92d1 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Post Foundations – Hole diameter
fffd12c6-1bca-5121-8020-92d7aa2d979d | note | Ref docs - VR Clause 714.06 (c) Signfix specs
b1b65227-94ca-5c21-8bc3-63155a692069 | note | Acceptance criteria - Refer table below for minimum diameter of foundation holes:
22e5ae09-cc27-55df-9a87-9531f5bf2fef | note | – – – – – – – – – – – – – –
17b8821c-7766-509e-abe3-d9a18f2512c9 | note | Post size and type (mm) ¦¦ Diameter (mm)
e1ad9f6a-a36d-5c76-b275-d1ca12d4f875 | note | – – – – – – – – – – – – – –
47ab5a31-88fb-5a95-bdb2-50c58c675791 | note | 32 mm and 50 mm nominal bore steel ¦¦ 225
ce2f3791-1df2-54a7-8f30-1079d1de502f | note | 80 mm to 150 mm nominal bore steel ¦¦ 300
ba2592a8-6813-50d6-9dd6-aed882cefb93 | note | All Signfix frangible posts– MASH approved ¦¦ 400
77e4d9c7-f39c-5fd6-979f-9e6776634b72 | note | – – – – – – – – – – – – – –
8a4024a0-70da-5227-8579-a7102d568d04 | button | Does the foundation hole meet minimum requirements? | Yes,No
bc2294c4-d48d-5707-bd55-8bcb21a8a9a6 | note | Freq - Each lot
23a6f3aa-3556-5736-bcfb-4592198b7750 | note | Key - H
9f16b142-b407-58c6-a7a8-cc3f98bb63a9 | note | Resp - SE
| checkpoint | 2.3 - Post Foundations - Dimensions
a00e70da-027d-56ec-a6aa-9de5078547a5 | note | Ref docs - IFC Drawings DoT 714.06(c)
0279067b-d0df-5a81-a0bc-af6b805f519f | note | Acceptance criteria - Concrete footings depth and dimensions to be as per IFC Drawings. Refer following drawings for post and footing schedule:
06be359b-11c1-511e-bf37-a9e25ca8f8f0 | note | ○ 1630-P200-SYM-CVR-DRG-2001
0e3b2f92-8ce9-5b90-9c29-c60843960ca3 | note | ○ 1630-P200-SYM-CVR-DRG-2002
f8351866-24ec-5e81-be12-de839cf26de1 | note | ○ 1630-P200-SYM-CVR-DRG-2003
10b63793-fb27-5072-be76-0aa438aac79b | note | ○ 1630-P200-SYM-CVR-DRG-2004
478efa1e-99af-5e7f-a046-d475308701c8 | note | Freq - Each Lot
65697fae-a18a-5572-bd42-97853a0c0bc9 | note | Key - R
b8fedf52-aabf-50da-8e89-68f3d97aa02f | note | Resp - SE
| checkpoint | 2.4 - Post Foundation – Concrete Supply
91541f2e-0bcf-5e67-a658-b6bbafd32aab | note | Ref docs - VicRoads document 703, VicRoads Clause 714.06 (c), VicRoads Document 610 IFC Drawings
a1fcce0c-bfd3-5c87-8b50-5ac0f4ebd110 | note | Acceptance criteria - Concrete used in foundations shall be 20 MPa, 20mm aggregate, 80mm slump complying with the requirements of Section 703.
1db4d3ce-2040-5823-980a-0e9ec2516f82 | note | Freq - Each Lot
f2724afb-2ec2-5dc7-925b-f15cb6eecdb4 | note | Key - R
795de6d4-51eb-5669-a2ac-4057cc205553 | note | Resp - SE
47e76268-217a-5d45-a0b4-c43cc27a2ea2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9502f974-5ba2-5f78-9c9b-e02ab1521357 | button | Delivery Dockets | Yes,No
| checkpoint | 2.5 - Post Foundations - Concrete Testing (If Applicable)
1060a2d6-1a56-5b4f-b09b-9dca59304ee0 | note | Ref docs - VicRoads document 703, VicRoads Clause 714.06 (c) IFC Drawings
84e4c0f7-080d-5bbd-a80c-625e6e0d8b3d | note | Acceptance criteria - Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
c529f6d5-2181-50a1-9976-151746507d91 | note | Frequency of testing:
f47df586-a5ef-50d6-b5ec-cd242afd0c8b | note | – At least one sample per day/lot;
dc56e7de-ec42-533a-be7e-e2a7d2603db2 | note | – Every 50m3 thereafter.
d46f0a22-35b1-5dc6-b994-8f58e98070ac | note | ○ Compressive strength testing and slump testing shall not be required for concrete used in extruded kerbs and channels and other edgings.
8c3831ed-3a20-52c1-b44f-477df74730f6 | button | Has concrete testing been completed? | Yes,No,N/A
1b7b8cbf-7f10-5b44-ac25-0647bc3f7e64 | note | Freq - Each lot, Every 50m3 of concrete
dcf94424-3ed8-5341-ba25-9f6344a4d726 | note | Key - R
ac404c7f-e1c5-5796-b79e-19d3cdfb51b9 | note | Resp - SE
06ea26c3-752c-5a67-87af-fc841352dfc7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
92327122-777e-55f2-abf0-2dd49cb269fb | button | Concrete Test Report: Compressive strength test results | Yes,No,N/A
| checkpoint | 2.6 - Post Foundations – Concrete foundation Tolerances
9232b008-f767-5124-aa54-3353d38c6d9c | note | Ref docs - VicRoads Clause 714.05 (a)
93590da2-4c11-5337-a19e-93a13e7883b4 | note | Acceptance criteria - The finished surface of concrete foundations shall be between 50 mm and 100 mm above the finished surface at the base of the sign and shall be shaped to ensure free drainage of water away from the base of the post.
cb2ef8a1-ac8e-5505-a4f4-ed9135e7c516 | note | Freq - Each Post
0b8b9c96-e933-527c-8a78-ec706406134e | note | Key - R
02474df0-cff1-5674-9987-50db3078c9d1 | note | Resp - SE
| checkpoint | 2.7 - Install of steel posts
4648f6c4-dcf0-5ad6-b575-4157347f07b0 | note | Ref docs - VicRoads Clause 714.06 (a)
83077502-bd8b-5a35-8311-4c40b1ca9bc2 | note | Acceptance criteria - Installation as per post schedule and IFC drawings.
f4d2ca1b-710a-55a8-b451-186b07d3a6ce | note | – Sockets –
4cedc2ac-37e9-5ce3-bdfa-3c28be98cdfc | note | ○ Where posts are to be mounted in sockets, the post shall be securely fixed into the socket by an approved vandal-proof method.
51bff268-0573-5e2c-b82b-4c5a62f45f0a | note | – Two or more posts –
8986a813-362a-563d-b0be-201b13558fa4 | note | ○ Signs to be mounted on two or more posts shall have posts positioned such that the sign face is rotated away from the approaching traffic to avoid direct reflection. Posts shall be positioned such that the sign is rotated away from the cross section by an amount equal to one tenth of the width of the sign (approximately 5º).
dae740b3-7ffa-5a5f-93f9-17d7d4605cf8 | note | Freq - Each Lot
cd991385-2f2f-5244-ae3f-a6eb1c6ff35d | note | Key - R
842afc2c-4af2-5ec1-9310-6474f49b987d | note | Resp - SE
| checkpoint | 2.8 - Posts in sockets
d3cdcc9b-d1d5-50eb-a63c-d718e2385c71 | note | Ref docs - VicRoads Clause 714.06 (d)
f0b7b68a-9a79-5de9-8aae-6582868bca78 | note | Acceptance criteria - If a sign is located in a paved area or in a location where the sign may be struck by a vehicle, e.g. at the end of an urban median or where it may be necessary to remove the sign to accommodate the swept path of over-dimensional vehicles, the post should be inserted into a socket cast into concrete foundation.
1af8b0a1-23c6-50d2-aba0-1785027ce58b | note | Suitable socket sizes for posts are as follows:
a6c7cdb9-be68-522d-af18-583f4dd94ae3 | note | – – – – – – – – – – – – – –
01e867e4-9843-5176-b184-2601fad575a0 | note | Post Size (mm) ¦¦ Socket Size (mm)
c1ce5669-3f9a-5c2d-9a3b-97cc5c17f65a | note | – – – – – – – – – – – – – –
a347d404-0b05-54ec-89ad-2854225cdad9 | note | 32mm Nominal Bore tube ¦¦ 50 mm nominal bore tube
bc972115-a7c6-5fa8-ad85-161ccfd2722a | note | 50mm Nominal Bore tube ¦¦ 65 mm nominal bore tube
f77aa34b-ed1e-519b-838c-3d3ce64a6b4f | note | – – – – – – – – – – – – – –
ac9914b3-52bb-57ec-b28d-a2da2cc894f5 | note | The socket install shall adhere to the following:
387b924e-e60f-5742-84c1-9bc518c18df4 | note | ○ The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface.
a7b03042-be3d-54cd-b06b-ee6829c7e041 | note | ○ The sign post must penetrate a minimum 450 mm into the socket.
08abbd1e-67c6-5293-b586-758c1e20a431 | note | ○ The sign post should be securely fixed into the socket by an approved vandal-proof method.
48c12786-1ed7-53fa-971c-145551489d5b | note | Freq - Each lot
9898d991-e274-5ca8-bf4d-5bf9029f9e3c | note | Key - R
10a233c1-aa0e-5b23-b25b-617090ef7555 | note | Resp - SE
| checkpoint | 2.9 - Steel Sign Supports - Coatings
528a54f2-3bd6-5f7e-ac71-8061a4d1b980 | note | Ref docs - VicRoads Clause 714.06 (b)
a1fe37e8-bb86-52df-9bce-1f60cea76938 | note | Acceptance criteria - Steel posts shall be either:
25f8ded8-1054-5c7d-abbf-fb5d60838429 | note | o Hot dipped galvanised in accordance with AS/NZS 4680;
4b1939a3-b6ec-5f58-bc9b-24cc966d99d1 | note | or
ad46d12f-eb73-5ccf-b0a0-f9943ca1cec0 | note | o Pre-galvanised prior to forming in accordance with Z275 coating class to AS 1397 (total minimum coating mass on both surfaces of 275 g/m2). The finished tube must be equivalent to AS/NZS 4792 ZB135/135. The weld seam made during forming of pre-galvanised steel post sections shall be repaired in accordance with AS/NZS 4792, Section 3, by applying a coating using a metal spraying system employing a suitable zinc or zinc-alloy wire/powder.
85fcf8e9-4f17-5eec-8ae1-9d6d942f7fc1 | note | Freq - Each lot
55d58bb1-054e-5274-a637-8f19d69e4cb8 | note | Key - R
aa53fd63-3051-507c-bc79-77972e797043 | note | Resp - SE
| checkpoint | 2.10 - Other support systems - VicRoads Approved Sign Support Systems
50177b46-4797-5912-bc27-17d24793f4c7 | note | Ref docs - VicRoads Clause 714.06 (f)
a6f4106c-1636-5354-8836-33c8a464c5e9 | note | Acceptance criteria - Other VicRoads approved proprietary supports systems may be used and shall be installed in accordance with the manufacturer’s specifications.
b0d42f53-3948-52d4-b261-238f94988f9d | button | Proprietary support system is VicRoads approved? | Yes,No,N/A
343894ad-2a19-5429-bf31-393546517226 | button | Manufacturers Specifications available? | Yes,No,N/A
1920703b-c787-5a10-a23f-8ee044324f3e | note | Freq - Each lot
6f99c158-901e-5328-a54c-0b81d0e437d3 | note | Key - R
f373fbc6-8d41-5716-ad1a-250a87f03350 | note | Resp - SE
c3f1235d-3940-5172-96f5-a43cc18338e4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
527af2fe-9c2a-5490-ba92-67d67cb99cac | button | Manufacturers Specifications | Yes,No
| checkpoint | 2.11 - Backfilling of post holes
b984d36d-c9e1-59d3-82d9-fadcaff17ff3 | note | Ref docs - VicRoads Clause 714.06 (e)
6fe88380-9953-5699-b788-0c8c4dff0bd6 | note | Acceptance criteria - 32mm and 50mm Nominal Bore Steel Posts
642d9765-ee20-5ff6-ac31-dc250d81e5d5 | note | ○ Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa, where ground sleeve is used.
362da7ad-b057-5b9c-b8cd-06daf0440a8d | note | Freq - Each lot
5924d3b5-a0b6-54d6-a8a4-6671cdb0c3e9 | note | Key - R
a77fb659-3d7b-590d-8d98-22743fdd62bb | note | Resp - SE
| section | 3.0 Install of Signs
| checkpoint | 3.1 - Fixings and Fittings
7aa21605-6659-586b-bbac-3db8492fe971 | note | Ref docs - VicRoads Clause 714.07 (a)
a98e1166-9b7e-5bbe-856f-98957370b397 | note | Acceptance criteria - Install of signs to be as per sign and post schedule in IFC Drawings.
a903623e-a6f8-5a76-b2ab-cb59bd3e5f0c | note | ○ Signs shall be attached to the posts or structures using the type and number of fittings specified in the schedule in the IFC drawings;
875fd012-10cc-5e96-9273-9fcd7701f8e7 | note | Or
6ec882c8-7f2d-58b5-88e3-31bc791fb843 | note | ○ As per following table:
8cdd428c-3325-5e59-a942-ff65cd15ca55 | note | – – – – – – – – – – – – – –
940c22f3-3939-5e04-92fe-6ebe9e5e1ea1 | note | Size of Sign ¦¦ Number of Fittings per Post
a3a648b4-0818-53e2-b06f-40c8ec1c6e6c | note | – – – – – – – – – – – – – –
9cc41265-c684-5f32-a568-bbd1180fce82 | note | Up to 200 mm in depth ¦¦ One
3c0d0552-d977-5790-99a7-04389516614a | note | 201 to 900 mm in depth ¦¦ Two
ad35d471-2c0f-570a-85e1-30827829718e | note | =901 to 1200 mm in depth ¦¦ Three
4e4ead4c-d67d-5839-b716-30fd00262833 | note | – – – – – – – – – – – – – –
00c086a4-99f5-5f64-aa48-21e6fbb6de04 | note | One extra fitting shall be provided per post for each 400 mm increment or part thereof above 1200 mm.
78b62c5e-0aad-5b45-b4af-b5d3b672b175 | note | – – – – – – – – – – – – – –
6d401463-b202-5bc6-abdf-321252296cb3 | note | Freq - Each lot
dedeb707-3b6f-5ebb-8809-4e399b15c351 | note | Key - W
8b1579fb-784f-5444-9de1-0d8b1c2f53d3 | note | Resp - SE
| checkpoint | 3.2 - Braced Signs
9bfcd099-f7cc-5789-8994-1eab46f1a6ad | note | Ref docs - VicRoads Clause 714.07 (b)
483c7e8c-35c6-587b-8aef-b85b26ff9df4 | note | Acceptance criteria - Braced signs For braced signs, the sign shall be attached to the post at every intersection point between the sign bracing member and the post.
d406a3c8-41c6-5d5b-af1e-46a079922eae | note | Freq - Each lot
6d7c1ef2-d16d-5799-a87b-49a56c6f9928 | note | Key - W
9896fcca-da06-5d3a-9419-7880e3ba308f | note | Resp - SE
| checkpoint | 3.3 - Sign assembly – two or more signs
abb99bee-c112-5ed0-b2c9-6b240a455f82 | note | Ref docs - VicRoads Clause 714.07 (c)
571af740-0cf9-5358-b0e9-936a0bec8395 | note | Acceptance criteria - Where a sign assembly consists of two or more signs, the signs shall be mounted in accordance with the sign assembly drawings.
c59db9a2-6f4b-5881-9842-c59b2fc04519 | note | Freq - Each lot
3ebc7bc7-1cc2-5133-a191-20349972d005 | note | Key - W
5ffdfa44-9f94-5bb0-ad44-924e318a6e0d | note | Resp - SE
| checkpoint | 3.4 - Signs Mounted on fragile posts
147c787d-2cf5-5560-96de-009d3f5e5fd5 | note | Ref docs - VicRoads Clause 714.07 (e)
d64631c0-c1e4-57f3-9890-d01db271258d | note | Acceptance criteria - When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that:
4d93a92a-31dc-5eb8-9c87-d16c1caa0e88 | note | ○ the uphill corner of the sign is a minimum of 800 mm above the ground;
065e0196-3347-5493-aa35-b0a6059625eb | note | ○ the sign at the longer post is 2200 mm minimum above the ground.
7cc22b9f-bf60-5342-96d7-45be09b211d8 | note | Freq - Each lot
b48ee74a-e22a-5587-856a-3560f44bdc80 | note | Key - W
469625d8-49f5-5472-ae9e-89e1ac1caf98 | note | Resp - SE
| checkpoint | 3.5 - Signs Mounted on existing poles – Proposal (If Applicable)
3ef9f6ed-8452-5cff-9cb1-b32076011086 | note | Ref docs - VicRoads Clause 714.07 (f)
01e250c1-af15-5eec-8b90-031ca427068a | note | Acceptance criteria - When proposing to mount a sign to an existing pole:
c15cbfd3-1d1e-5624-ad44-adb1dd14e3b6 | button | Obtain permission shall for use of structures which are not VicRoads property? | Yes,No,N/A
6c11ab62-1bd9-5481-bd66-b23503ddef90 | button | Strength of the pole and any other effects of mounting the sign in this way such as fatigue and durability checked by an experienced structural engineer? | Yes,No,N/A
c9afe2b5-a519-5434-9323-e37e680f40f1 | button | Evidence of the structural checking shall be submitted to the Superintendent for review? | Yes,No,N/A
f44462d5-2a4e-55a2-9077-57a5063a68d4 | note | Freq - Each lot
7aa82038-23ee-5005-b512-4bb8d8bb0ff9 | note | Key - H
a3560c44-fa4c-505c-8a55-84c960d073cb | note | Resp - SE
ad32fbd2-9560-5dcf-88a9-d1a6a8ff6d78 | note | SI Key - H
37f3d17e-f587-5624-b315-e70fed7e88a8 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
42c5b70d-9dc2-5f28-a495-c2107527dc7d | button | Structural Engineer report | Yes,No
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Signs Mounted on existing poles – Install (If Applicable)
296fca8a-6bc8-5fd1-80d0-a36311dc8fb2 | note | Ref docs - VicRoads Clause 714.07 (f)
043fe7da-60e6-5058-977a-bcf1b09d4544 | note | Acceptance criteria -
b31ad715-db43-59bd-aae0-b5cc6a5b7533 | button | Has section 3.5 been completed? | Yes,No,N/A
fe0db3d4-f154-5805-ad22-6813b2544e45 | note | ○ Signs to be installed on existing poles as per the IFC drawings.
1a0f1e91-0813-5e83-a19d-687b7cb91f6c | note | – Mounted with stainless steel strap –
495a1f92-7089-5447-8beb-892b5dab71a0 | note | ○ the brackets shall be attached to the pole using stainless steel straps of 12 mm minimum width and a minimum tensile strength 6.5 kN.
37f7cfce-1d02-5c55-8f46-f27329b22f6e | note | – Small signs (area NOT exceeding 0.3 m2) –
23ea8379-def3-58e5-95ae-9abf66083ba6 | note | ○ shall be attached to steel or concrete electricity distribution poles, tramway poles, lighting columns and signal pedestals or mast arms by banding or other proprietary fittings.
1d745998-dbf3-5cb8-bfbb-552949873cfd | note | – Large signs (area exceeding 0.3 m2) –
b7654606-695d-53ba-bc36-3a790a534c26 | note | ○ attached to existing poles (other than electricity distribution poles) provided that the pole has sufficient strength to support the additional loading due to the sign and that special joint-use supports are used.
c67a8c43-9dda-5a47-9ba8-ebae01f14865 | note | Freq - Each lot
6ad68be4-e4be-5fb8-bec0-37b83f7fdb52 | note | Key - W
3e88e954-8872-5cc4-b016-85df912628b9 | note | Resp - SE
| checkpoint | 3.7 - Signs facing oncoming traffic
d4001e1f-dfbc-5041-ae4f-239fa82b0831 | note | Ref docs - VicRoads Clause 714.07 (g)
a0b51748-bcb1-53b3-9246-66d5cd3fb814 | note | Acceptance criteria - Where the drawings indicate that a sign is to face oncoming traffic, it shall be mounted on posts which have been rotated in accordance with the requirements of clause 714.06(a), with the exception of signs mounted on structures over traffic lanes.
eb69455f-2d75-59d2-a6a4-e6fddce799a5 | note | Freq - Each lot
6ae53381-70e2-5f9a-a383-dc141d21be27 | note | Key - W
cbae445c-64ac-54b0-b745-f40ab9ca7495 | note | Resp - SE
| checkpoint | 3.8 - Relocation of signs (If applicable)
d6a12c8c-957f-5711-93e3-f4d5bcc853fa | note | Ref docs - VicRoads Clause 714.07 (h)
ee66a149-e78c-538d-8bac-fc4150ff3cb1 | note | Acceptance criteria - Where signs are to be removed or relocated:
fd80382f-5409-5f43-a282-3c31a04c3b0e | note | ○ dismantle and transport the signs, posts and fittings to the specified new location or as directed by the Superintendent;
4405a175-122a-55c9-a9ff-6b7a2db80514 | note | ○ Post holes shall be backfilled and compacted to the finished surface;
397b8943-7760-5b51-95cd-c2b5df97d139 | note | ○ Relocated signs shall be erected in their new position as specified.
| checkpoint | 3.9 - Stiffening Bars
e4fbf391-2bd3-5e3d-bce5-07509b4060d2 | note | Ref docs - VicRoads Clause 714.07 (i)
c502b7a2-0968-525a-8dbc-a75e76d9872a | note | Acceptance criteria - Stiffening bars to be removed after erection of signs.
fe6d43bb-779b-5d37-bb9e-fa51f47dfd61 | note | Freq - Each lot
beeebd29-4da8-5f25-8fa4-1633beb8ef67 | note | Key - W
04da7e41-78d2-5c8d-976c-7fb23de48555 | note | Resp - SE
| checkpoint | 3.10 - Single post mounting
f3dd6f7b-af38-5b95-b72e-3a6d4d1d42b3 | note | Ref docs - VicRoads Clause 714.07 (j)
c5e2d13b-83c6-554e-adfe-b65e48c1fac8 | note | Acceptance criteria - Single post mounting for large signs shall be provided if required on the drawings and the schedule. Single post mountings shall be designed in accordance with the VicRoads Traffic Engineering Manual Volume 2.
2d1c34f1-698b-5540-a794-973a1804fb6c | note | Freq - Each lot
26c18a8f-9c37-526f-bf23-06eb8928d21e | note | Key - W
dbd3fbad-71ea-5792-a249-a5e370b2259e | note | Resp - SE
| checkpoint | 3.11 - Proprietary sign install (If Applicable)
4278e891-8f20-57db-ab81-6da5d8e2bc0b | note | Ref docs - VicRoads Clause 714.07 (k)
0aa98ae0-0deb-5640-b869-c9657521e20d | note | Acceptance criteria - Installation of proprietary signs approved by VicRoads shall be in accordance with the supplier’s recommendations as modified by VicRoads conditions of approval.
706aadbb-bc47-56c6-af2f-9fbf8eca0b89 | button | Suppliers recommendations available? | Yes,No,N/A
d2f554fa-c20e-5a19-8d11-b9442987b20b | note | Freq - Each lot
1fbe207e-4fa7-5a31-9279-3e7058d8f73d | note | Key - R
7c20dcca-a064-52e3-8552-ad7d568027d3 | note | Resp - SE
cfefd0ea-4381-5854-8103-5f1527405fd8 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
34d49289-9117-5fd2-8695-0c161d5f21f0 | button | Supplier Recommendation | Yes,No
| section | 4.0 Completion
| checkpoint | 4.1 - Tolerances
dc24df44-f631-5434-9ef7-27a4a3b21089 | note | Ref docs - VicRoads Clause 714.05 (b)
12958842-1afc-569b-b20d-92a373d264cf | note | Acceptance criteria - Posts are positioned in accordance with the following tolerances:
687a0d2a-7e86-5b42-9d6b-97f309530d25 | note | ○ Posts are straight.
0eb75f3e-cd4c-562e-8858-8b0271277c24 | note | ○ Posts are vertical with a maximum deviation of 1 in 100.
bdc1ffa6-cdec-5456-bb8b-02622ac1b8da | note | ○ Post tops are 50 mm ± 10 below the top edge of the sign
9507c55a-b5ad-5703-9768-bc3046f5029a | note | Signs are positioned in accordance with the following tolerances:
4377d9ff-88c1-5df7-a7f9-a0e961b0ebc3 | note | ○ ± 40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign;
c85f1c6a-5b34-5966-8418-437a74719beb | note | ○ ± 100 mm of the pegged sign location or specified location.
2e1a9f15-9439-5e77-a146-c7f8d345f7df | note | ○ Signs are mounted level with a maximum deviation of 1 in 100.
f04370c0-df01-5ec1-9e7e-95f17b76347b | button | Tolerances checked? | Yes,No,N/A
5a1ec631-da52-5a34-9ce1-6b7fcd74c618 | note | Freq - Each lot
92dccb3b-2e1e-55dc-b396-72a0a718e5e9 | note | Key - R
f2877300-0997-5ad5-800c-db9e8760e70d | note | Resp - SE
| checkpoint | 4.2 - Conformance to Drawings
c17d73f6-9801-57b4-bf93-40047e178353 | note | Ref docs - IFC Drawings
6b889147-0394-5e18-9949-b86e3c83b08d | note | Acceptance criteria -
007549ba-8cd1-567b-873f-05dd93ce4ebd | button | Installed signs are installed correctly and checked against IFC documentation. | Yes,No,N/A
edbf4f0d-f3dc-5094-be36-ee76d94fe175 | note | Freq - Each lot
70836e9e-6e23-5462-a3f4-b95b004d8661 | note | Key - R
2b73f605-af79-5b3c-84ca-2770cb06a208 | note | Resp - SE
| checkpoint | 4.3 - Supply of signs – Warranty
83e1f653-b2ed-538e-a934-bfda3e52dbd2 | note | Ref docs - VicRoads 860.07
ae5ea683-e7fc-5123-85a4-4cf051112d75 | note | Acceptance criteria - Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty, and warranty Claims to be in accordance with Specification 860.07.
422ad9e3-cf5f-560c-a39c-4970e3380274 | note | ○ Provide Warranties in accordance with Table 860.071. See Page 8 Fig #1
4d46214e-5d21-53a8-ae3a-d3ef55a775a1 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9b37c56e-c22c-5439-86cd-34667ec0c2ab | button | Warranties for signboard and components (e.g., Retro-reflective, florescent, and non -reflective materials) | Yes,No
| section | 5.0 Work Lot Close out
| checkpoint | 5.1 - Product Non-Conformance
97c11008-c6ae-5f7c-9a97-f70240759801 | note | Ref docs - CQMP
cbfef01e-877f-5862-9307-940de2dec353 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
7d087942-c2a4-5686-9fbe-ff7e14f5a080 | note | Freq - Each lot
3447c8ff-d8c6-5255-a761-92b9f389896f | note | Key - R
b0ab8877-a803-51da-9a00-951af6bd5300 | note | Resp - SE
ffed6e96-6828-5a1a-8dae-0514c20fefb0 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bc0ce991-7924-542f-9221-986cc4d56f8d | textbox | NCR No
| checkpoint | 5.2 - Quality Representative to check the above criteria and records to confirm
a2b176ed-a522-53f5-b5d2-33fa2fd6dcd2 | note | Ref docs - CQMP Lot Records
559b4cd2-29af-57c4-ae86-ce0d69024ea4 | note | Acceptance criteria - All above criteria met, and records identified attached.
8d948fbf-b82c-5c9a-9676-88e132dccdd1 | note | Freq - Each lot
8e299e17-7047-5134-810b-2fe06ab22e2e | note | Key - R
19e4612e-6a66-5c46-9f30-031a80d6750f | note | Resp - SE
3aa036b9-58d0-586d-9c4b-86950d6cde94 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0045 Gas Relocation | itp | 1630-P200-SYM-QAC-ITP-0045 Gas Relocation |  |  | 7f38e928-2519-4e69-82bd-2c09f7bc9e54
| section | ITP Details
| checkpoint | ITP Details
b61e26e7-5621-53d4-8403-add888f918ef | note | ITP No. - 1630-SYM-QAC-ITP-0045
af3ecdd3-6ff6-5616-9888-09ec6b6a6269 | note | Rev No. - 00
c4c5e92f-f4ba-59c7-9f60-2276a277c821 | note | Date of Issue - 08/11/2023
2dfd3157-899c-5e0f-b8d8-33bd5f9244f7 | note | ITP Type - New/Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out
2aae07da-1b47-5e13-962e-9afb8fc7c8ba | note | Ref docs - IFC Drawings
2500728f-08fc-537e-a251-db5a150cc6d0 | note | Acceptance criteria - Ensure alignment setout has been completed and pegged.
0a8aa80d-8f5d-550c-bfa5-6327a480b8a4 | button | Has all of the above been completed? | Yes,No
2528bb84-e61a-5eb0-a828-e82a861a3c38 | note | Freq - Prior to start of works
70a2d473-9a15-5297-b4b3-3fc82a5842bd | note | Key - H
88344a54-4fba-5fe3-9870-75c6a272c065 | note | Resp - SE/SS
| section | 2.0 Conduit Covers
| checkpoint | 2.1 - Excavation and Cover Requirements
aba09ee2-d653-576a-a3a8-f88c0f3923b9 | note | Ref docs - VR Clause 706.03
9e54c4e9-0221-559d-9a35-1b69b77a410e | note | Acceptance criteria - Cover requirements for gas assets shall be:
7a6257d7-b6b7-5d70-9a23-c6179a13015d | note | ○ Pavement surface to top of conduit minimum 1200 mm.
1b941a59-2b0f-5b62-ad05-00ebda2e5b9b | note | ○ Invert of open drain to top of conduit minimum 750 mm.
5eb2dbad-f564-50da-a256-680c1c06db0e | note | ○ Unpaved areas to top of conduit minimum 600 mm.
e4732c2c-a330-5b7c-846d-3dfdbe238aff | note | ○ As per asset authority requirement for cover to other assets
baefeb3f-4f92-5720-8716-f364d6fd1594 | note | Or else as specified on design drawings in accordance with asset owner requirements
3a3c4399-63a4-5b6a-ab55-40352ec50ef4 | button | Has all of the above been completed and approved? | Yes,No,N/A
97b66a1a-969e-5b88-a57b-c437fc846e9c | note | Freq - Each Lot & Each possession
e1b7d413-2a12-5535-8fec-8a286e7c86ae | note | Key - S
b5e2e2d2-5436-535c-8ef7-d948a4af49ba | note | Resp - SE/SS
| section | 3.0 Backfill and Compaction
| checkpoint | 3.1 - Backfilling/Compaction (Areas not being paved)
9cede3c4-4b93-5e91-89f9-9213b9f17e4c | note | Ref docs - VR Spec 706.08, 706.09
7c8559a5-e867-52bd-9376-ab4625b8bb0d | note | Acceptance criteria - Unless backfilling requirements are specified by the Asset Owner Authority, backfill material properties and placement to be as per table VR706.061:
01ced2df-75e6-580b-b0e7-b1b43c2c29a9 | note | ○ The opening shall be backfilled with common backfill placed and compacted as specified in layers not exceeding 200 mm loose thickness.
0d29b16b-99c1-5d16-8376-6d6c5a41b818 | note | ○ Moisture Content between 85-115%
e6285a73-982d-57df-bdc9-fdd5183bd64a | note | ○ Compacted to refusal using handheld mechanical equipment with consideration to utility owner vibration requirements.
2c7a32e2-3a6f-52a5-a836-9558ef50a832 | button | Has all of the above been completed and approved by the relevant authority? | Yes,No,N/A
9deb6965-277c-543c-9995-0e7d28d8b296 | note | Freq - Each Lot
0ad9a5e5-c332-50da-b00a-49a71b2ffcb9 | note | Key - R
0bf1b0e3-f6bf-5da6-9bf4-555ec59da4ba | note | Resp - SE/SS
cf7fd9cf-2fca-58d2-9f3b-791465481427 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
fc87fd3f-8fec-50cd-a9b9-786492110f1d | button | NATA Test Report (if applicable) | Yes,No,N/A
| checkpoint | 3.2 - Backfilling/Compaction (Under areas to be paved)
571df67c-9be0-5f5d-90c3-25c4495e6847 | note | Ref docs - VR Clause 706.08, 706.09
cbadd1de-8b11-5502-8ee5-699f04cace02 | note | Acceptance criteria - Unless backfilling requirements are specified by the Asset Owner Authority, backfill material properties as per VR706.061:
88143a6b-2126-57fc-9600-0f5009800c2b | note | ○ Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness, and above that level with common backfill material.
44295bae-a498-51dc-8ab0-4d5ac0480571 | note | ○ The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97% based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
db21dc0f-c705-5660-a944-3c75ed0d0237 | note | ○ Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
b38b512f-8645-50fe-b7bd-092a480e1f8a | button | Has all of the above been completed and approved by the relevant authority? | Yes,No,N/A
2a3b5834-339c-5e47-9b7d-dc971dc16f89 | note | Freq - Each Lot
3206c7bf-c893-5728-a93e-1afb11c82de2 | note | Key - R
7fc83c6b-ce44-5551-93ea-61a875454e9c | note | Resp - SE/SS
052b1d60-6842-516a-be6d-b1663f05e0e8 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
e210945b-40b5-550e-9037-4ff647e88dcb | button | NATA Test Report (if applicable) | Yes,No,N/A
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Test Reports
0c5ba719-97df-51f5-babb-4023aa0a95d0 | note | Ref docs - VR706
7206dc57-b201-5738-9e41-5dd3d4929609 | note | Acceptance criteria - All Test reports received and reviewed.
f4371d4c-227f-5b68-824f-cdcb7745a7e7 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No,N/A
f1b88036-b202-52d1-85cf-cb0590a7f4b9 | note | Freq - Each Lot
72f647ad-b11d-5816-8d9b-7bbf2929fa90 | note | Key - R, I
8e1aa338-0b54-5e2e-819e-3ef0f45fc7c8 | note | Resp - SE
| checkpoint | 4.2 - As-built Information
99ae8833-2daf-57c7-9a1f-6169b9ef52f0 | note | Acceptance criteria - Where applicable, asbuilt pickup or as constructed drawing been provided by authority.
ca617c32-697c-5031-b103-0f3c3b4248c7 | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
6bc56ae2-6d86-5f52-bd55-fce835f85a61 | note | Freq - Each Lot
912ab512-bb07-5a9a-ad1d-012cabcfbee8 | note | Key - R
2f4d988b-1f0d-572f-a9dd-5fec3acf36a8 | note | Resp - SE
| checkpoint | 4.3 - Product Non-Conformance
efe9ec3d-175a-591c-a8ae-ba1f8a1e0e47 | note | Ref docs - CQMP
6128317f-bb0c-520b-891d-013fedefcd3a | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
3739600e-febd-5a55-b1fe-bed9bdb91cf5 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
aaa80cf4-b73c-52ea-ae8f-eb2c3f513693 | note | Freq - Each Lot
bcb34ebd-716e-5451-a003-453db14964f7 | note | Key - R
e1c1ded1-fc57-5491-94f6-3e47c87fd73f | note | Resp - SE
a7108966-2a02-52e2-9517-2810fa70e8a9 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
f6f27b2d-6b10-5059-9240-9d9a08b7254d | button | NCR reports | Yes,No,N/A
| checklist | 1630-P200-SYM-QAC-ITP-0048 Dense Graded Asphalt REV01 | itp | 1630-P200-SYM-QAC-ITP-0048 Dense Graded Asphalt REV01 |  |  | b11c9d8a-2426-40f3-a87a-2d6eba8e2a6c
| section | ITP Details
| checkpoint | ITP Details
bd6d53d1-2395-55c3-bb14-960070c92f38 | note | ITP No. - 1630-P200-SYM-QAC-ITP-0048
13612449-dd2e-5dfa-8111-fb0f4eb58b7d | note | Rev No. - 01
b52c00d8-cda4-5fba-8986-1ce41e15b4b9 | note | Date of Issue - 20/12/2023
92b1b675-f6e2-58cb-bee5-1feeacb69d33 | note | ITP Type - Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Asphalt Quality Plan
5c2aa563-6c38-5f86-b18c-941123a6ccee | note | Ref docs - VR407.04, VR407.11, VR407.27, VR407.29
7b191ff4-4727-5fa7-9710-54625671def5 | note | Acceptance criteria - The Contractor shall provide an Asphalt Quality Plan that addresses the following requirements:
9bbcce0c-caa9-564a-99d2-12c7d396a888 | note | (APPROVAL AND OTHER PRELIM REQUIREMENTS) Underlying layer conformance: Survey levels have been taken on the underlying layer. Test samples have been collected for the underlying layer. For core sample tests, the layer thickness is the mean thickness of the core samples and for nuclear gauge tests, the layer thickness is the nominated layer thickness.
1cd706bf-94f7-5d73-b79f-bf12dd7019ee | note | Min. thickness of cores extracted from pavement are not less than values given in Table 407.27
ec1600ed-2886-581e-bba9-b5e104089e2c | note | Test roll has been completed for the underlying layer. CCTV inspection of drainage and sub-surface drainage lots has been completed. NCR (s) has been raised for any non-conformances in underlying layer and no rework required.
dc60fd2b-84df-50a0-bb59-3c90c477da78 | note | ○ sourcing, handling, and storage of constituent materials
03d5ec14-9a8e-5b85-be29-2438a2de387f | note | ○ RAP Management plan
d1e5fbed-901a-53d1-adc5-9572521faae8 | note | ○ asphalt production and process control
3ae12a4e-a1f1-51ab-8245-02f298206bf5 | note | ○ asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
1d8d7b56-721c-5538-8f80-d44c21772de2 | note | ○ measuring and recording of pavement temperature, wind speed and weather conditions
4ecee9d9-3d19-5a8b-9084-3d95eed4bdca | note | ○ achieving a uniform application of tack coat
a2e288dc-51e3-5fdc-8aac-a48ae17d719e | note | ○ achieving uniform asphalt placement including determination of paving speed and paving plans
25bef73b-9ca1-5af8-9798-d7398d820a9b | note | ○ determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
33719cd0-5227-50da-8326-c8416f1fe36f | note | ○ procedures to maximise density at joints.
dfdc62c2-f8aa-5d1b-8425-48382974aabf | note | No Reclaimed Asphalt Pavement (RAP) is added to SMA.
d158e6d8-c992-5639-b6a7-14fc1e3977ee | note | Reclaimed Asphalt Pavement (RAP) is limited to Maximum 10% for RGG (Regulation Gap Graded) asphalt. (VR 404.03, 417.03 and 405.02)
7d904e0d-090e-5747-abed-8840708cb374 | note | Hot storage of mixed asphalt:
1eca39a1-08e6-5fd4-82ca-98dd1aa1d670 | note | i) Asphalt with PMB and C600 has not been stored in hot bins for more than 8 hours prior to use.
0ddf47e0-5aa8-5669-b846-7be491aec0ce | note | ii) Any other asphalt types have not been stored in hot bins for more than 18 hours prior to use.
6ba17e3e-0b81-5751-84f6-aa8dee4c9e86 | note | iii) DTP approval has been taken to store hot asphalt more than this time in hot bins.
908f0967-c2dd-5da7-9ca4-e8cfe7ab802a | button | Has all of the above been completed? | Yes,No,N/A
7b9a3b90-171c-5499-9b41-16cfb2412eaf | note | Freq - Prior to start of works
c5e2acb0-53fa-5bce-923d-33a06bca2065 | note | Key - R, H
496a64a6-f553-54ea-8d36-866716bcc2a5 | note | Resp - SE/PE
75b72c27-1b63-57ea-a758-7bc8e48acebb | note | SI Key - H
789b7cb3-9e43-5b05-98a7-eeb1078d2de3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - HP released – see AP 1630-SYM-AP-0052
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Check Survey Set-out
0d6fd0d0-e668-5e35-8f20-c1ab8632c70a | note | Ref docs - VR407.27, VR407.29, VR407.30
56a240c5-1914-5dd2-896f-4de207a19969 | note | Acceptance criteria - Record survey set out including frame, benchmark, and recovery points in place.
63604e1b-a508-5871-b654-f566a6702a0a | note | ○ 1.2. Identification of lots: Lot has been created for one shift's work for homogeneous placement method, material and appearance not exceeding 4,000 Sqm.
7736aa5a-8ed8-569f-872c-88ee05ee5378 | button | Has all of the above been completed? | Yes,No,N/A
dae61109-a233-589c-8379-7dda4acfcebb | note | Freq - Prior to start of works
83cd684f-6590-5fdb-8aff-bcb52c9aaac2 | note | Key - H, I
1e05035f-a63d-52c6-bd7a-2eb87076614b | note | Resp - SE/PE
a4bca026-c176-5245-8ed8-c4af4f9fa6a3 | note | SI Key - I
| checkpoint | 1.3 - Asphalt Mix Designs Approval and Compliance
f8f2fb7e-aed0-5582-915f-b96763930042 | note | Ref docs - VR404.05, VR405.04, VR407.06, VR407.09, VR407.10, PS3040.06 (g)
93c7c68e-7fab-5795-8032-f46314cf2494 | note | Acceptance criteria - The mix to be used shall be a VicRoads registered mix and shall comply with the requirements of clause 407.06. The Indirect Tensile Modulus of the mix is not required to be submitted.
18c11b12-490b-53d2-a295-005bfd2fd0f5 | note | All Asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport.
0d9d2ff0-8b62-5e7a-a520-c96a3af7ff68 | note | The registration for all mixes incorporated into the works shall be current at the time of their use. Mix is registered by VicRoads as ‘General’ mix at the time of placement, unless otherwise approved by the Superintendent and submitted for Superintendent's review.
442bcb94-1774-5f3c-af75-2f32447602cc | note | ○ For SMA (if requested); the following additional documents are submitted with mix design for SMA:
931440f0-80a6-5400-9747-80c4fe5023f2 | note | i) Marshall Stability to meet the requirements of clause 404.06(d);
fd5c8c83-6202-5c6e-bb46-87866e846eca | note | ii) the results of the Binder Drain Off tests meeting the requirements of clause 404.06(e) and the selected maximum mixing temperature to avoid excess binder drain off;
0cb8bc2e-c291-5643-914d-47a614b31443 | note | iii) the Indirect Tensile Modulus of the mix for a sample prepared at 5 ± 0.5% air voids.
00c2225d-f4e6-5ebd-a8ed-fbad36e7d0c0 | note | The Contractor shall submit documentation to the Superintendent nominating the asphalt mixes to be supplied no less than 7 days prior to their use.
a5224760-7877-53ab-b093-ebf1188ee42a | note | The contractor shall ensure to only use asphalt mixes that are registered by the State Road Authority as ‘General’ mixes at the time of placing the asphalt.
98f2ec31-f1ac-5065-86fb-044445843af7 | note | Where the Pavement Design allows the use of asphalt, the asphalt treatments must be applied in accordance with this Section PS3040.06 and the Technical References including section 407 of the VicRoads Standard Specification Sections for Roadworks.
0a5391c8-aa3a-548f-9c27-e531dba30dfa | note | Roller routine for compaction at procedural basis: Placement and rolling procedure validated against density test for individual mix including best practices in AS 2150 has been submitted for Superintendent's approval if total asphalt quantity of that mix type and/or size in the project is less than 300 tonnes and/or lot size is less than 50 Sqm. VR 407.27 (SMA: Placement and rolling procedure including best practices in AS 2150 has been submitted for Superintendent's approval for SMA thickness less than 25mm.) VR404.15
c2eac318-c980-5d54-acb8-348953a8e897 | note | Incoming material: Incoming material test reports have been collected from the supplier.
3cf2a917-307e-55b8-88bc-06848ff17da4 | note | ○ Material Change:
21c34096-2657-558f-931b-02830c8e43bc | note | i) The Superintendent and/or Designer have reviewed and agreed to any material change request.
8fd774f2-2ab7-5fc8-9e5e-93eadb3f463e | note | ii) Design Change Request (DCR) has been raised (if applicable) (1170.12)
fc6bb779-3f65-564c-9052-f807df7c164c | button | Has all of the above been completed? | Yes,No,N/A
81c33d6c-abd0-50d3-982a-06ececd44b83 | note | Freq - Each Possession
2d7d1d14-0f88-526d-a521-d3c4a4d60d94 | note | Key - H
48c8330f-1b82-561b-a840-2208b5c0066e | note | Resp - SE/PE
74140687-3ced-5cc1-ad6e-af110a5c2a27 | note | SI Key - H
0f7e51e4-2924-5eff-a922-9ef1b5fdcae6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - VicRoads Approval Certificate, Incoming Material testing (sieve analysis)
d37add0b-f7e9-597a-8920-7798d169b6db | textbox | Team Binder Reference No
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Asphalt Placement Plan
9bb39e3a-701a-5783-b1c8-6debfacb08e1 | note | Ref docs - VR407.04, VR407.13, VR407.17
6eb06f38-adac-52ad-a6d8-df7ba2f3d0c3 | note | Acceptance criteria - Subcontractor submission of placement and Lot Plan. Review of proposed layers, depths, paver runs, Surface Preparation, Joints and spreading.
edf913b6-0fb1-5036-8ef1-ce73dfaddbda | textbox | Lot Size
90e18975-6e2e-509c-862f-69380ef60390 | button | Has all of the above been completed? | Yes,No,N/A
d9cd4a51-838e-5798-a1b0-c11c542eab0a | note | Freq - Each possession
27b9e1ba-4075-532d-95f8-084d1385249d | note | Key - H
1e21a43a-3a56-5658-8dc1-75e7e56b7a05 | note | Resp - SE/PE
52c5ff43-85ed-5b87-ac15-ac595419fd0d | note | SI Key - H
b7367d9d-7af0-54d4-8a83-b48c26650c12 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
42f05195-6862-52b0-9e2c-e4dfad649b3d | textbox | Approval Correspondence if applicable
c60533b2-f858-5ad0-83a6-2427723edcc0 | note | Check placement adheres to Compliance with IFC drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Cold Weather placement
8385ef7d-0035-5eea-82ee-adc9b10e8002 | note | Ref docs - VR407.13
7757e0fc-5895-5d47-88c8-9831d97808d4 | note | Acceptance criteria - Prior to commencing cold weather placement of asphalt, the contractor shall submit a job specific cold weather placement management plan to the Superintendent for review
5272cd55-031f-5225-b7bd-3d71a4ac208c | button | Has all of the above been completed? | Yes,No,N/A
bc9af528-8fe7-5e98-941c-b02757e1cf06 | note | Freq - Each possession
d3112710-e1b0-5ee4-bf22-4d2a3ab360a1 | note | Key - H
fa259280-0d7d-50e4-9b55-fd4d77ae6b83 | note | Resp - SE/PE
b80d84a9-ab3c-5ed4-ab30-b90e5490e41a | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Asphalt type
ff5fc386-a31e-50fa-9b0d-85be94344287 | note | Ref docs - Table 407.21 VR407.24 IFC Drawing
9e1779d1-b38b-5e6b-8063-90159608add6 | note | Acceptance criteria - Asphalt Type:
e3048c29-6e81-55dd-b693-c4dbf0d91588 | tickbox | Base Course
b19dc940-2fc9-599e-a200-27022c226cb7 | note | Type SF, SI, SP, SG and SS
d52f2df9-2bcb-52ff-a65d-dfe7d62e0a4a | tickbox | Intermediate Course
397778b5-8b45-521b-b52b-2ec9f5c0a9f1 | note | SF, SI, SS
a8c144ce-a810-570c-9d1e-0616282ab666 | tickbox | Wearing
e979caa3-dfb1-5a4e-90bd-a106d6574a97 | note | L, N, V, H, SMAH
c97f141d-8993-5856-b14a-6fc0fa6040d7 | tickbox | Regulation Courses
b5fb5e3b-8245-5036-892a-a41e9cb9db5f | note | Existing pavement has been regulated to correct the shape to make it parallel to the finished surface.
4d4f227b-d64f-53f9-a745-9c3143d4eeea | note | L, N, V and H
17fc87a7-8b0c-540e-a90e-ceb8717cc7da | textbox | Layer Thickness as per IFC
7f9d3a37-9f2f-56a3-905d-9b6f74f30d7d | button | Has all of the above been completed? | Yes,No,N/A
2e4aadae-0219-5cfb-a41d-57b22bdc2b12 | note | Freq - Each possession
f1861ce1-9f5e-5cc5-a7d0-73390566dff9 | note | Key - R, I
24b3431e-a0f2-5abd-93db-bd9e79f45c5c | note | Resp - SE/PE
98bac0c4-58bb-5732-81e2-ef44cbc43b0c | note | SI Key - I
| checkpoint | 1.7 - Conformance of underlying lot/ Layer
8a1f488d-71a7-599c-a8cd-3900cb741a80 | note | Acceptance criteria - Has the previous layer passed acceptance criteria?
95440612-004b-5e0c-809d-9dbb4c2b15a9 | button | Has all of the above been completed? | Yes,No,N/A
c41c2bea-01d5-5fc6-b6e8-de760cd452a6 | note | Freq - Each lot
6f4db35b-18de-588f-bd95-6c112fe3b644 | note | Key - H
dbeac044-7020-515c-9c5e-3c2ae5c0a150 | note | Resp - SE/PE
693ffd4e-8828-5834-80af-3e1c0f831955 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
95517914-6076-5aec-a7a6-a1fdf2c4cfdf | textbox | Lot no (if applicable)
| section | 2.0 Hot Mix Asphalt Placement
| checkpoint | 2.1 - Profiling (Cold Planning) and preparatory works
30e80748-940e-55e4-b357-e557da717283 | note | Ref docs - VR402.02, VR402.03, VR 407.21 (F) (iii)
59a0d8d3-92db-5463-8f74-4f8dbdad6ec1 | note | Acceptance criteria - Cold planning shall be carried out in a manner as to leave a uniform surface on a plane parallel with the ultimate finished surface of the pavement as shown on the drawings.
4f877622-0725-5841-b0ba-21bdb9f86e10 | note | The nominal depth and width of pavement to be removed shall be as specified in Clause 402.06. After planning, no point on the planed surface shall lie more than 15 mm below a 3 m straightedge placed on the planed surface in any direction.
a75395c0-ad55-53bd-80aa-bf4e2b37295e | note | In locations where removal and replacement of asphalt or pavement is required on the same day, the rate of cold planning including clean up shall be at a rate consistent with the asphalt replacement process to minimise the pavement area closed to traffic
20d616c7-191e-54da-aff0-ce91c4be2ee6 | note | Removal of Temporary Ramping
a43b1beb-2a00-53f2-b6f3-908efcac1c06 | note | Prior to commencing each day’s work, temporary ramping shall be removed via means of cutting back along a straight line to expose a vertical face of fully compacted asphalt at specified depth.
4e120a26-aa02-52c4-946c-bee8c0aaac27 | note | All plants have a current certificate of calibration (if requested). Cutting machines have the following characteristics:
eef27930-e758-555e-be15-c3734c76ec82 | note | i) standard cutting drum with cutting tool spacing of 15 mm horizontally; and
1161b17a-d0ed-5c7b-836d-7539e739da9f | note | ii) fine tooth drum with a cutting tool spacing of 8 mm (or less) horizontally.
da61591c-7205-5ea5-91a5-cca6e8ad33cb | button | Has all of the above been completed? | Yes,No,N/A
5984240b-e9b0-5f14-9f7d-49a4417b78cc | note | Freq - Each lot
cae0430a-ae8d-5f7e-baeb-c9814beba33c | note | Key - R, I
5f3a7e9c-fd2e-5976-bd66-418201337040 | note | Resp - SE/PE
00ba4eb5-e367-5f27-a27f-51cc7138ee46 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
13cc9cdb-035c-5a88-b0ff-07d787ac0fc2 | button | Field Sheet | Yes,No,N/A
| checkpoint | 2.2 - Commencement of Placing
5196cd22-c113-5ddc-90f5-9648a4e088dd | note | Ref docs - VR402.04, VR404.14, VR407.23, VR407.26, VR408.08, VR407.22, VR407.30
edb79061-1e04-5cac-af4c-34736b83b4ba | note | Acceptance criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
97962a18-0e7f-5918-b41c-40c5245b2ff5 | note | Binder: A product quality certificate and test report from the manufacturer is obtained for each delivery of material or shift (if requested). Binder sample is collected from the supplier and supplied to MRPV (if requested). Unmodified bitumen is conforming to AS 2008. Modified bitumen (PMB) is conforming to ATS 3110.
c43e30b3-e268-54ab-b82c-a1b56d926b88 | note | Asphalt placement trial (if requested) to trial the mix, plants, procedures and personnel has been completed for each nominated mix and the completed ITP as well as test reports have been submitted for Superintendent's review.
688df790-b0a0-56c9-a84a-44706b216156 | note | All manhole and valve covers are to be raised or lowered to the new surface level and temporarily ramped where required.
e6ba202c-b3e8-5745-a4a6-70f44a793d1c | note | Preparation of exposed granular pavement: For smaller areas as required, exposed granular pavement material is watered, re compacted and primed or heavily tack coated prior to asphalting.
2165c5b8-0e89-54c0-9698-e4bd5b0a4bbe | note | ii) For larger areas, a bitumen emulsion primerseal is applied prior to placing asphalt.
8d943c28-1310-5f28-ab9f-acfa19ccc233 | note | Rolling: Vibratory rollers are not used to compact asphalt on bridge decks.
4077835d-1ddf-5c7e-be51-4397cbd38f26 | note | i) Pneumatic tyred rollers are not used for SMA.
0c699035-d18c-5559-b2cf-a2e2c42a1f94 | note | ii) Vibratory rollers are not used for more than 2 passes and immediately ceased if any breakdown of SMA aggregates are occurred.
e70de662-bec9-5e64-8f2a-7b18d4fc1be3 | button | Approval to proceed? | Yes,No,N/A
f9a785e0-e15f-54e8-8748-3edaef6ec456 | note | Freq - Each lot
8ca91606-df66-5b3b-b9a6-58dff3a82682 | note | Key - H, R, I
cced64c7-c78d-5449-91b8-a8b1b37730e2 | note | Resp - SE/PE
c7f373e1-2488-582f-a05d-0fee213ac1f3 | note | SI Key - H, I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Ambient conditions for Placing
fcaa8301-d48f-519c-82a7-1a975d53f2d6 | note | Ref docs - VR407.06, VR407.07, VR407.17, VR407.18, Table 407.171
26ea0cd8-ae8c-536c-8209-709c2b54af36 | note | Acceptance criteria - Intermediate and Base Course Asphalt not to be placed with surface temperature < 5˚C.
2e6d0253-01ec-5924-ba8f-b0dadee89122 | note | Asphalt mixes with PMB and Class 600 binder in intermediate or base course layers shall not be placed when the majority of area to be paved has a surface temperature < 10°C.
2c47672b-e907-5c33-87df-7dc70df12858 | note | Wearing Course Asphalt not to be placed with surface temperature < 10˚C,
f10c3d38-69a6-5385-8a64-42842ca4ccfb | note | Ambient condition for asphalt placement:
ac595a1f-a293-5452-9ec8-4bcc676e28b4 | note | i) Surface is dry and free from surface water;
322e257f-c41d-5ee3-bd38-44c3c7a8c865 | note | ii) Rain is not imminent;
893ee33f-f5d3-5bb9-bc83-bdc6662a4c68 | note | iii) Majority of the area to be asphalted have minimum pavement temperature as per Table 407.171
a676b13e-bd24-5484-8bb1-5ff26fb28f78 | note | Aggregates: Aggregates are conforming to asphalt type specific requirements.
f5ffc741-0035-585d-9e5c-5ed63f592ead | button | Approval to proceed? | Yes,No,N/A
8fa05e10-6414-5ad7-80f9-58b684c134bf | note | Freq - Each Possession
167a2280-dd73-5e1f-9535-0a8cd4d1e352 | note | Key - R, I, W
0d6e12c8-8d33-5afd-9895-bcd9c11d490d | note | Resp - SE/PE
a8a37bc3-bb62-5616-922b-428fd9619a45 | note | SI Key - I
| checkpoint | 2.4 - Approval of Tack Coat Used
fd96b0da-269b-5ee6-8563-3886899db50a | note | Ref docs - VR407.08
5f88c7ab-db71-5927-8ec3-7d34441e8529 | note | Acceptance criteria - The Contractor shall submit (if requested) the details of the trackless tack coat proposed to be used in the works.
f6b738fc-626b-569e-b253-b46c1389a3b6 | button | Approval to proceed? | Yes,No,N/A
03085cb8-5dfa-5b0f-8ccc-a505898a97e6 | note | Key - R, H, I
0387cc3e-004c-5b48-8b58-dd0cd1a9d871 | note | Resp - SE/PE
0a22b44c-8370-5da9-9de0-84894d2cbfaf | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Application of Cationic Bitumen Emulsion ‘Tack Coat’
0af6e980-afea-52a9-83f5-71469176797d | note | Ref docs - VR407.08, VR407.11, VR407.18, VR407.19, VR407.21, AS1160
b651878d-392a-5f1d-99d2-99a2fc0b0f9f | note | Acceptance criteria - Before tack coating and asphalt placement, contractor shall remove dangerous and loose material from site and sweep the area clean.
1fd14dc1-b372-5d08-ad9a-e4e739423c02 | note | Bitumen emulsion used for tack coating shall be a cationic rapid setting type complying with AS 1160. Emulsion diluted with water shall have a bitumen content of not less than 30%.
50a9644f-7c3b-56de-b482-541faafee758 | note | ii) Emulsion diluted with water have a bitumen content of not less than 30%.
36315975-a2fe-50ed-b064-68457f186612 | note | iii) if requested, demonstration will be provided prior to using proprietary grades of bituminous tack coat for it's superiority over CRS60 emulsion tack coat.
f37b2ede-66c4-50d0-98c2-fa389d36827e | note | iv) Tack coating material contain no more than two parts of cutter or other hydrocarbon solvent
ea85224f-54b5-5e63-97fb-c2989ce84b04 | note | Proprietary grades of bituminous tack may also be used where it can be demonstrated they will provide an equivalent or better bond between pavement layers compared to an emulsion tack and can be applied in a uniform distribution at the residual rates specified in Clause 407.19.
a1f53242-6602-559e-871e-97d9bbea1dde | note | Bituminous tack shall contain no more than two parts of cutter or other hydrocarbon solvent.
26972722-0ec2-590e-8175-7526fa4d5a4c | note | From 1 July 2022 only trackless tack coat will be permitted.
3eb6bfce-a62a-5302-8ad6-b2a5feaee8e6 | note | The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen (except for joints and chases where rates shall be doubled).
827ba026-3349-55fd-be07-d132c9af484d | note | i) A tack coat has been applied to all asphalt (where applicable), concrete or sprayed seals on which asphalt is to be placed except where asphalt is to be spread over a clean, un-trafficked, freshly laid asphalt, or over a clean primed surface, or on a granular material where the overall asphalt depth is 150mm or greater;
bf13d762-a948-567a-a277-67b2d09cc70a | note | ii) The application rate for the tack coat is 0.15 to 0.30 L/m2 of residual bitumen (except for joints and chases where rates are doubled);
340702f2-de72-5ea4-95db-0de30e48c515 | note | iii) Tack coat is uniform over the entire surface and intact during asphalt placement;
a67f18da-6830-5d64-8632-1587d2d99c8d | note | iv) Photographic evidence that includes an identifiable landmark relevant to the lot, has been supplied to show that tack has been applied uniformly over the lot.
d77ead07-f02a-5df7-b162-b3b68dec4753 | note | v) Before asphalt is placed, sufficient time has been allowed for emulsion based tack coats to break.
970fdd37-f85f-507a-9faa-c6b04a5c1207 | note | vi) All cold joints, abutting concrete edges and vertical joints with granular pavement are heavily tack coated.
a361267b-23ae-5ad9-9974-6a3f4d6323f4 | note | Degree of particle coating: Min. 95% of the coarse aggregate particles are fully coated with binder. (VR 407.11b)
96661450-a75b-51c7-b42a-5307b55df69d | button | Has all of the above been completed? | Yes,No,N/A
ba1efa20-985a-500e-ac8a-0580685d2784 | note | Key - R, H, I
ff16cb1b-67ba-5266-856f-f772236d2e56 | note | Resp - SE/PE
10d59d5a-d1d1-5335-b5b3-455dda1af961 | note | SI Key - I
| checkpoint | 2.6 - Verification of Delivery Dockets
ec3df3b3-7a26-5099-9fd3-f21334a86df1 | note | Ref docs - VR407.20
e2e1ce3b-eb4f-55ab-943a-037215e1a242 | note | Acceptance criteria - Asphalt deliveries to be made only during hours listed for possession of site.
97211bd2-0f9a-5a25-86b8-4c644b4a0826 | note | Check asphalt upon delivery for specification, segregation, separated binder, evidence of exposure to temperatures which are too hot or too cold to retain adequate workability and strength, and uncoated particles. Reject all non-compliant asphalt.
5dfb678b-532b-5555-b286-135beb59fab0 | note | At point of delivery, delivery dockets must be sighted to conform with the requirements of VR Section 407.20(b). Reject unconforming loads.
af1a23c2-f233-5331-be82-ee6380ac3510 | button | Has all of the above been completed? | Yes,No,N/A
c95ee7a8-c926-5c15-a359-d17e338a3899 | note | Key - I
837dcfbf-a79e-5f87-8898-2c5dfba094b8 | note | Resp - SE/PE
73c47e0a-abf8-5bc5-bacf-4af01b0881cd | note | SI Key - I
9bb5ff51-cb0e-5f2a-8325-6dbaad0c75ba | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bb6dd1e5-776b-5999-8864-c8ce4915f63f | tickbox | Delivery docket
a0d1de77-eece-573a-99a3-e969e160072c | tickbox | Tonnage report if applicable
| checkpoint | 2.7 - Construction - Jointing
cd55865a-c9a0-5384-8aee-f4d4fb330a6d | note | Ref docs - VR407.17, VR407.21
984e6805-b012-5e5f-a6dd-2bbe56ee6555 | note | Acceptance criteria - All transverse joints shall be offset from layer to layer by at least 2 m.
484ef692-1abc-5188-8edc-508af0a6f138 | note | Location of all joints shall be planned before work commences and provided to the Superintendent.
41e611dc-da69-568c-85a2-dcd768255d59 | note | Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
e2d41111-b11a-585a-a10d-88fd22392ddf | note | Longitudinal joints shall be parallel to the traffic lanes.
56906c9e-86ba-5fe3-b665-90b04c31b757 | note | Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
1018dfe0-e29b-5901-9ece-bf86de03c825 | note | Cold joints shall be avoided
792a6cff-d49d-5b5b-9248-c6e0d4f14d38 | note | Upon completion of each work day, and prior to opening to traffic, the following shall be adopted for treatment of exposed asphalt edges:
460c1d7c-f463-542d-bf64-ea2d5991ca6f | note | (i) Longitudinal edges
5b7fa951-8feb-5b47-81c3-8b9c25766524 | note | All longitudinal joints within the trafficked area shall be matched up between paver runs, except for a short section required to achieve minimum offset between transverse joints, unless otherwise approved by Superintendent. Exposed longitudinal edges within trafficked area are to be ramped down at a slope of not steeper than 5 horizontal to 1 vertical, by means of constructing a temporary wedge of dense graded or cold mixed asphalt.
bea0b5b6-b2a7-56a1-9161-51c7db17dba5 | note | (ii) Transverse edges
0ccb4bb6-d7c8-54a7-9e06-03cd3e5ac540 | note | At the end of paving run in the transverse directions, new asphalt mat shall be squared up to a straight line and ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Ramping shall not be exceed grade indicated in VR407.21
40aee243-d503-5b4d-9711-f966283da312 | button | Has all of the above been completed? | Yes,No,N/A
e2f3f3ba-5586-5457-af84-fa9c8aa8446e | note | Freq - Each lot
008ce14c-9485-5b97-b4f3-1fd58ad2f3e5 | note | Key - R, I
12e0815f-e693-53de-ae8b-7bd35d601d66 | note | Resp - SE/PE
9e476a40-639b-5f55-8e2a-ef7a75219813 | note | SI Key - I
| checkpoint | 2.8 - Matching Existing Pavement Surface at Junctions
6ff76016-ef83-5a8d-9032-60218be850f2 | note | Ref docs - VR407.21 (e)
ad667487-8c8f-5fea-ac8a-8e2367d42563 | note | Acceptance criteria - New Asphalt Layer to match the existing pavement surface.
c65a22be-428a-5cc7-9ac6-6e8cb117201e | note | A chase shall be cut from existing pavement by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times.
54d2779d-32d4-5a24-85c8-b38292f8a68a | note | The width of the chase shall be as follows.
73ef5a13-2205-5d03-8bb1-21d0f5647fac | note | (iii) at side streets and median openings – 600 mm
b0be736d-5eda-5a4b-89bd-bb605dea9b1d | note | (iv) on through carriageways with a speed limit of 80 km/h or less – 3 m
d0ecb67b-c1c8-52ed-8ca7-f55a78902acc | note | On through carriageways with a speed limit of more than 80 km/h – 6 m.
e8d59e19-b132-556e-a702-6f82366c2df9 | button | Has all of the above been completed? | Yes,No,N/A
4f62b2c1-652f-5fc6-bfda-257d7969cff2 | note | Freq - Each lot
b1babab4-d8ed-57d4-878a-f5399005884f | note | Key - R, I
6373cde8-591e-5bbe-be22-8ff60f9a8c26 | note | Resp - SE/PE
| checkpoint | 2.9 - Spreading
5239d3fa-a574-5245-9def-bc7a9c761675 | note | Ref docs - VR407.25, VR407.30
f2eef05c-a6b0-5b6d-a932-04a9164dbbbd | note | Acceptance criteria - Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified. All asphalt shall be spread with an asphalt paver except for small areas where use of a paver is not practicable.
586550a1-c7de-51bf-b9a9-c20872899cbe | note | All asphalt shall be spread with a purpose designed asphalt paving machine to form a uniformly smooth asphalt mat complying with the requirements of Clause 407.29 without segregation, tearing or gouging. In areas that are not accessible by a paver placement of asphalt by other means is permitted.
2a37c42b-b3c6-548b-8a53-84be4f97ca35 | note | Paving of asphalt:
ee92a371-feec-5fb3-b7ab-86c8a1c751aa | note | i) The width of a single paving run is not exceeding 6 metres unless paving in echelon is proposed in 407.30g or procedures are in place to ensure that a uniform asphalt layer free of segregation can be achieved;
c21841e0-6586-5d64-83f6-5e99f4b9fdc3 | note | ii) A transverse joint is constructed if the temperature of the asphalt in front of the paver has cooled down below 120°C due to any delay or stopping;
4cee6679-2a13-55af-9bb5-c78a80220904 | note | iii) Hand spreading is only used for areas where paver can not be used;
842f13bb-0d41-5082-8641-9f09c3ef0a1d | note | Hand spreading shall only be used for small areas where it is not practical to use a paver.
0dbf451b-8755-5a86-8784-ecc63ab596c3 | button | Has all of the above been completed? | Yes,No,N/A
7d80a4d0-9f43-569d-9846-531b503fcce3 | note | Freq - Each lot
74e13142-47ab-5375-a1f2-06d59f40b7d9 | note | Key - R, I
0421d8a1-4ea8-5581-a195-33c2ca8932b2 | note | Resp - SE/PE
b4a3b802-7be0-5562-bc29-de1c85559d6e | note | SI Key - I
| checkpoint | 2.10 - Trafficking or placement of asphalt over Type SF asphalt (If applicable)
34b02f7a-cc7a-55b3-83a3-ef8a49c7ae13 | note | Ref docs - VR407.28
129c1ebd-f927-52c9-b616-a10d5eada282 | note | Acceptance criteria - Trafficking or placement of asphalt over Type SF asphalt is not permitted unless the majority of the Type SF asphalt has a surface temperature of 50˚C or less and falling. (Table 407.281)
50085015-f878-540c-be29-1e8fd5dde6a5 | note | Trafficking:
9abdd785-f060-5d8f-aa6c-87d9e738d453 | note | i) No traffic is placed on SF asphalt until the Superintendent has agreed that the temperature of the asphalt is less than 50ºC and is trafficable.
b146cb20-cbae-5d81-a5c7-c4d302d23656 | note | ii) Traffic (including construction traffic) is ceased immediately if SF asphalt deformed/damaged after trafficking. No traffic is placed on SMA until the Superintendent has agreed that the temperature of the asphalt is less than 40ºC and is trafficable.
603583bd-d06c-5a5f-ba15-ce81a997da26 | button | Has all of the above been completed? | Yes,No,N/A
add2cdf4-add8-57ea-adad-d231d1bc6cfd | note | Freq - Each lot
2d14769b-9bba-56b7-a9a2-5c5603402f09 | note | Key - R, I
225f122c-3f58-5641-a191-ed34361e1b09 | note | Resp - SE/PE
20bd7986-cba9-582d-a046-3d6a069fc603 | note | SI Key - I
| section | 3.0 Performance Testing
| checkpoint | 3.1 - Compaction Testing
b4c5b789-87b4-5479-ada8-d5d83e49a3ef | note | Ref docs - VR407.27 Table 404.141, Table 407.271
5ff9c5f0-8ac2-521e-afbd-a3b3ef57e074 | note | Acceptance criteria -
8d41d2c6-0bf8-5830-941e-21845ea56e52 | tickbox | The minimum number of tests to be conducted for each lot should be six.
14709416-c8d5-5f11-85b0-0faa230d5e73 | note | Acceptance criteria:
71af61cb-396b-5f36-8b22-1cbaaee8c311 | tickbox | Thickness < 50 mm: CDR 95.0%
6f547dfb-c614-5441-811d-e2be9fba822e | tickbox | Thickness > 50 mm: CDR 96.0%
a90ffc5a-391e-5219-86d7-13637d11e4fb | button | Is this CDR Achieved? | Yes,No,N/A
d6f0f7db-542a-5b43-b3d7-5c34249c28d9 | note | Freq - Each lot
11b93614-c526-56b2-bb0f-929e4c55b3fa | note | Key - R
447010bc-2ca5-521d-a35b-1193da7153f8 | note | Resp - SE/PE
bc4ca0de-dfb0-5468-baa4-08bc71d32b1d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
3d4a1908-32f4-5869-bc4f-bb888710a1ea | button | NATA Test Report: Compaction Tests | Yes,No
0a00818d-0356-562e-b42d-1ab55b04164d | textbox | NCR No
| checkpoint | 3.2 - Compaction Testing – (Less than Six Test)
b4342159-41a1-5b5c-9da6-89ae884e61bb | note | Ref docs - VR404.14 Table 407.273
78cbf7f6-62a6-59bb-b419-837534f3ea48 | note | Acceptance criteria -
dcebc7fa-5425-578b-826b-38a34cf51488 | tickbox | Thickness < 50 mm: MDR 96.5%
97a2e884-1a1e-59e2-93eb-97c82a13e4f1 | tickbox | Thickness > 50 mm: MDR 97.0%
965d8bb9-a7b9-5008-ad67-2f742f1bd44a | button | Is this MDR Achieved? | Yes,No,N/A
f2e7ee13-1a55-5dab-8f79-b2d92afbc9e0 | note | Freq - Each lot
49f0d871-fa8e-50ed-a889-5e1e18e1fb80 | note | Key - R
813d0368-eb60-5171-8883-39557564225f | note | Resp - SE/PE
2fbd9f75-859c-5340-9b88-59da03f43c5e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
1ed38527-15e5-5a25-9d29-bd138a9cb158 | button | NATA Test Report: Compaction Tests | Yes,No
eb79bdf6-73df-524b-8615-aff1d19c4562 | textbox | NCR No
| section | 4.0 Completion and Compliance
| checkpoint | 4.1 - Finished Surface Levels
4f258aae-d5ee-5ef3-b176-b2e0ccdf77d6 | note | Ref docs - VR407.29 Table, VR407.292 Table, VR407.293, VR402.03, PS3040.023
c91ada9f-18fd-5fe0-9269-928b8ea37798 | note | Acceptance criteria - Refer table at the end of the ITP for reference.
6ca07d11-6a30-5660-a2be-93992c687b95 | note | The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements of Table 407.292 and 407.293
4f8a33c1-53f4-5baf-a7ec-20a0ef2a3db4 | note | Asphalt Layers:
f777ca9f-f957-5c0c-879e-ecc8c0805a2e | tickbox | Scale A: ± 5 Max. S 8mm (80 points min.)
980901b1-9d76-5689-810e-113316944079 | tickbox | Scale B: ± 8 Max. S 8mm (40 points min.)
2acf1040-d859-5054-ac72-e37ab8f25156 | note | Where min. average or nominal thickness of overlay specified, average thickness to be calculated as per VR 407.23 (c).
63f74451-71e2-5cda-9729-325924dab0f9 | note | Cleaning and disposal of material: The planed surface is swept clean prior to either diverting traffic onto the planed surface or placing asphalt.
38cecbd8-9120-51ea-8231-0582ee510be1 | button | Has all of the above been completed? | Yes,No,N/A
cef189b4-575e-50d6-a631-72088d6fa22d | note | Key - R, I, H
264c959c-b5df-52c6-ae33-3d609103577e | note | Resp - SV, SE/PE
5338d770-c37c-5c3b-8a4e-f5f96e61a5b1 | note | SI Key - I
3d8dc16c-a649-5bfe-9c46-8dac61452580 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c9078818-6e10-5ae1-bae7-5ae43d2fa8d3 | button | Conformance Report (Finished surface level and thickness) | Yes,No
| checkpoint | 4.2 - Rectification of surface levels
843384e4-b3cd-5a82-827d-145011f39419 | note | Ref docs - VR407.29
91c1cbf4-66fc-59dd-ad76-54d176424806 | note | Acceptance criteria - Rectification of surface levels shall not commence until approval to proceed is obtained from the Superintendent.
4d953503-7069-504e-a50e-c307ca5efc1d | button | Has all of the above been completed? | Yes,No,N/A
93cf5387-3d95-5e11-a809-39250aef21fb | note | Freq - Each lot
698dffa8-0c0d-5b1d-a780-e6600ed010fe | note | Key - R, H
54ebd489-1353-557e-95d1-4790eabe0830 | note | Resp - SE/PE
00da5965-b823-5717-9047-d685b28611ee | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Finish Surface/Shape
ffb36873-5beb-570d-b82a-9b1bc37c1715 | note | Ref docs - VR407.29 (a), VR407.29 (a) (iv), VR407.29 (a) (v)
9552175c-bfa5-53e2-8b55-966da57b3cfb | note | Acceptance criteria - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
384ccfc9-8865-543a-8f55-abcaf91eb4d4 | note | ○ Flush or not more than 5mm above lip of channel
976e84aa-7138-542f-9931-ce790b300bf5 | note | ○ No point on the finished surface of wearing course to be greater than 4 mm below a 3 m straight edge.
36ef32eb-c6ac-52f9-bc78-c73e9c15a895 | note | ○ Where asphalt pavement is not placed against a concrete edging, the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside.
357762c2-05e6-595f-baa8-22924dd4393e | note | ○ Where asphalt pavement is not placed against a concrete edging, the width of asphalt layers shall not be less than the design or specified width of layer by more than 50 mm or greater than the design or specified width by more than 100 mm.
3a99dfc5-9a82-5037-a79e-15abb7401b6c | note | ○ The average width over any 300 m shall not be less than the design or specified width.
11b6c79c-d131-5d3b-b86a-7315109d78aa | note | For intermediate and base course layers, the distance below the straight edge shall not exceed 6 mm and 10 mm, respectively.
a7b50426-4412-5d9d-8bce-e9f8205e217b | button | Has all of the above been completed? | Yes,No,N/A
9420a1a3-c9ad-5181-af51-2b35970a5498 | note | Freq - Each lot
122d3e64-2f2e-5603-abf2-43a929537c5b | note | Key - R
8caf703f-0c89-58fd-8829-eeb00d9e1dd7 | note | Resp - SE/PE, SV
b6e147ce-0126-597b-a2f0-22307c3d4330 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d2340160-7f9e-5a08-9880-318eb2140c74 | button | Straight edge checks involved. | Yes,No,N/A
e9451040-02fb-5151-9a31-5c6a465015df | button | Conformance report on finish surface/shape | Yes,No
| checklist | 1630-P200-SYM-QAC-ITP-0049 Fill Earthworks Type C | itp | 1630-P200-SYM-QAC-ITP-0049 Fill Earthworks Type C |  |  | 3af0804c-9944-481b-97b3-f90f1a23c33d
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Define Work Lot
9ea0de6d-4329-5898-bef1-3cb608f5a825 | note | Ref docs - 173.02 204.03 (h) Table 204.142 Lot Diagram
5e71ebe4-a0e1-507e-ad19-c8d5276603ef | note | Acceptance criteria - Survey boundaries clearly define the Earthworks Type C Construction works.
2608235d-67ce-51f4-82be-9c352636ba8c | note | • Lot diagram to be provided clearly marking up extents of lot area.
99890e8a-9e2f-5899-8e2a-7a77ac73668a | note | • Work Lot open on TeamBinder.
b95a3501-0e24-5ffa-9987-8dc0b59ddfb8 | note | • Lot size with no more than one day’s production
97047556-7670-5eb9-9871-e5ef0c4dff30 | note | Freq - Prior to start of works
890ed55e-dd6b-570e-b472-a7675f2ce41e | note | Key - R
23016b80-c867-5a91-9ef7-1e5f7cc8bc3b | note | Resp - SE
d39ab405-c7e9-51e5-aea9-72b9d1701615 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
e76c933a-14e7-5cad-89fa-2e8c42aab422 | button | Lot map | Yes,No,N/A
161f33d0-d921-5f4c-8364-e2004960580b | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
cbe8de43-c9fc-57f3-a518-7fb17cb7b5d1 | button | Environmental permit | Yes,No,N/A
069dd909-e654-5889-a4bc-147802ef693c | date | Inspection Date:
| section | 2.0 Set Out
| checkpoint | 2.1 - Set Out Survey Completed
599dfdff-bb73-5d2b-be42-a6bd057e3c9e | note | Ref docs - VR Clause 204.03 (a) IFC Drawings
b09c2e59-5a1f-513e-b3be-ad10ad9795e8 | note | Acceptance criteria - Set out pegs in place and clearly mark out limits of works as per IFC drawings.
0f5e11f3-0a7c-58f3-95b1-b916251c9eec | note | Freq - Each Lot
7c7c87fa-edaa-542f-880b-3ca1e926fdb5 | note | Key - R
e8946709-143d-5bd4-9a89-559eadcde98e | note | Resp - SE
691b5323-4497-5638-8756-c6fe889fb152 | date | Inspection Date:
| section | 3.0 Placement of Type C Material
| checkpoint | 3.1 - Underlying Layer Conformance
370562c2-4067-578a-bcd1-f0ae2f5801f5 | note | Ref docs - VR Clause 204.10(b) Construction Document
758b07ba-001d-5125-99c5-8183d9dc458b | note | Acceptance criteria - No fill to be placed until the area has been reviewed by the Superintendent.
9859684b-8e5c-5730-aa71-127675da9b3c | button | Approval to proceed granted? | Yes,No
d7e777ce-a2d5-540c-8c08-99532aa17511 | note | Freq - Each Lot
199714c2-6e04-592b-87be-1333aa7e6957 | note | Key - H W
39a17aa7-db57-5c6e-aed6-5011a9203feb | note | Resp - SE
09346a5c-a712-56c6-89ff-9c7dcfa56d8e | note | SI Key - H
fe2f799e-60e2-5d16-9262-0586bbbbed5b | date | Inspection Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Placing of Fill
4e9e6798-528d-5ac5-8aac-5035662b4a8d | note | Ref docs - VR Clause 204.10(d)
af04d73a-c485-5a40-a3e3-f486868d3a48 | note | Acceptance criteria - Spread and compact in layers not exceeding a compacted thickness of 300 mm.
5cd428f3-42ae-55b1-803a-ea72afbdeaf8 | note | • Where Type C material contains 25% or more of rock by volume, which will not break down during compaction to meet the maximum particle dimension required for a 300 mm thick layer, the loose thickness of each layer may equal the maximum particle dimension of the rock up to a maximum layer thickness of 500 mm.
31326611-5d09-5b27-ad0b-a297c7a76ac9 | note | • Rocks with a maximum particle dimension of less than 800 mm may be placed in Type C material zones as specified, with sufficient spacing between larger rocks to enable full compaction of the Type C material.
a88bf83c-0310-50e4-82b6-f17cd7d88388 | note | • The material shall be placed and compacted such that voids are completely filled with fine material.
4f0f774e-e762-5ad1-9948-1c20747e52c0 | note | • Material shall be compacted at minimum moisture ratio of 80%
6cbdfc03-7a42-52b9-bc95-1812e4ccee84 | note | Freq - Once Each Lot
db30b875-bce9-5e9b-ba7b-89e6808990da | note | Key - W
c9fcb384-2738-562c-8e14-268cfc10ec25 | note | Resp - SE
d33065bc-aa54-5e92-b592-9c529d595b53 | note | Remarks/record -
775b0939-a4d1-58ab-9c29-f6ea8b5b614b | button | • Verification Records: | Yes,No
4fd115d7-7692-5dd3-8661-7ac7df7900bf | button | • Material Compliance Certificates & Material Approval Register | Yes,No
07232ce7-20c3-5749-a8d1-a813f4df4169 | button | • VicRoads registration of recycled material blend (if applicable) | Yes,No
c6b64e7a-af36-5b6f-a82f-e5a836c40510 | date | Inspection Date:
| checkpoint | 3.3 - Keyed Fill Layers
88bb3b40-fcf3-5d9a-a3bd-935348e21d39 | note | Ref docs - VR Clause 204.10(c) 204.10(d) Construction Document
72f6b21f-4ae9-5766-8761-2e6a0552959e | note | Acceptance criteria - Placement surface textured to ensure layers keyed into each other.
a7509ddf-f963-59d0-bcdf-f1d962db6a09 | note | • Where a fill is to be constructed on steep sideling ground or against an existing embankment with side slope steeper than 4 horizontally to 1 vertically, benches shall be progressively cut over the full area to be covered by new fill.
f152b137-533d-546a-b215-7086d192969f | note | • The width of each bench shall be such as to permit safe and effective operation of plant but shall be not less than 1 m.
f91298c2-8b3c-52b0-9c4b-80388a4f10a6 | note | Freq - Once Each Lot
b7244457-a102-54c2-9a13-231df961e46d | note | Key - W
03d265ae-5919-5ffb-a6bf-27ed08b97208 | note | Resp - SE
211d0220-f9ac-5ec1-b16b-313d6e83aa6f | date | Inspection Date:
| section | 4.0 Geotechnical Analysis
| checkpoint | 4.1 - Compaction Testing / Moisture Testing
e215b2b0-60c4-565e-8156-074fb18b33e3 | note | Ref docs - VR Clause Table 204.131 Table 204.141 Table 204.142 173.04(d) Table PS3020.072
74495c2c-25c0-5627-8bf3-77ec81944ee7 | note | Acceptance criteria - All areas of the job will be considered as scale A.
ec0fccae-401d-5881-8952-467395fb3527 | note | ○ Scale A Testing: HWKR Rd, Princes Freeway, All Freeway Interchange Ramps, All other arterial roads.
03df5a87-37ae-5d8b-9c31-7daa48844e1e | note | ○ Scale B Testing: All other local roads, SUP.
8c1c3a68-91ff-5600-b691-0d933394bb79 | note | ○ Type C Material should meet the following compaction:
ed432d75-a0ef-5746-89cc-5122e4cac911 | note | • 95% for Scale A
7af71f92-5c09-5043-bb3d-972c661610ee | note | • 93% for Scale B
5981b486-c823-5c20-85b8-12d7e872616c | note | • 92% for Scale C
44722f09-42b1-5456-a444-8427abfb6f47 | note | ○ Type C material is to be tested as per table 201.141 and table 201.142. And should meet the moisture content requirements as per VR204.
ae24813c-afed-52b3-aec5-ee61fa3fa532 | note | ○ >70% for any material within 150mm of subgrade.
d992b7ea-404e-59e3-bebf-ae9850107d43 | note | ○ >80% for all material below cut floor level.
a0a7497a-7485-5066-8e9d-50818ccb1dcd | button | Have the results been achieved? | Yes,No
53d35691-a1d9-5f4f-abca-56068c70050b | note | Freq - Each Lot
9cf3d127-9c90-5da4-8c3a-a1cce9c98b11 | note | Key - R
f10d9286-6bcd-5bfb-937a-845edb0c16fa | note | Resp - SE
617b9cf2-df5c-5c18-9b60-97e9304bb552 | note | Remarks/record -
8d22e582-601e-539e-819d-65c6a2298ef8 | button | • NATA Test Report: Compaction | Yes,No
838fe65f-2163-59ef-afa9-585b8af5b32e | date | Inspection Date:
| checkpoint | 4.2 - Material Requirements
ba4d7880-adb4-5ff9-9624-6578515c8e3b | note | Ref docs - VR Clause Table 204.041
81a350fd-63be-5fc4-9c13-c8a2e34ba7f6 | note | Acceptance criteria - Type C material shall be capable of being spread in layers of not more than 500 mm and compacted as specified to achieve a stable condition.
f85dae6a-8cc3-5fd1-9530-6cec444b31d8 | button | Have the results been achieved? | Yes,No
04dda004-2c4a-50cd-a1b1-d56b37b20550 | note | Freq - Each Lot
82ff42af-1ba6-565d-a9fd-922fada03c00 | note | Key - R
91cba9c0-88bb-532f-81ae-b90eeb357f1d | note | Resp - SE
86895e5e-b873-52a1-92a9-05834d36b44f | date | Inspection Date:
| checkpoint | 4.3 - Reduced Frequency Post compaction testing of initial lots.
2e8fe6f2-ca02-5827-afda-d4a8906adab4 | note | Ref docs - VR Clause 204.14 Table 204.142 PS3020.07 (f)
eb9680f6-9fa0-5562-bd79-28d2310036d2 | note | Acceptance criteria - Testing of compaction for each lot as per Table 204.142
139adbdc-45b6-5395-93da-48835d6b0fb3 | note | • If Reduced frequency has been granted, the testing can be conducted at the following frequency:
106c2e65-07ac-580b-a0c3-87d00d3d6ae7 | note | • Compaction will only be required for every 6th lot.
59dfce6b-76ef-590d-9543-477ad6f279f1 | button | Has the criteria been achieved? | Yes,No
961e43eb-5a14-5144-8970-5cbba5e279e0 | note | Freq - Each Lot
f29511d9-1eba-567e-9d95-ee90791184a1 | note | Key - R
7f127af3-6d8a-55e6-b3b1-cae23168d49d | note | Resp - SE
62d0c62e-7e2a-5587-bb04-47f25058a140 | note | SI Key - R
a002b335-771b-587a-aff7-4f79a7700a94 | date | Inspection Date:
| section | 5.0 Completion
| checkpoint | 5.1 - Conformity with IFC Drawings and Construction Tolerances
04885355-8de2-506a-83aa-f0965214fcaa | note | Ref docs - VR Clause 204.03 Table 204.031
aaba57cd-c283-5d98-a8f0-0c116e5cc6eb | note | Acceptance criteria - Earthworks shall be finished to conform to the levels, lines, grades and cross-sectional specified or shown on the drawings.
96f5daa6-d08e-52d3-8422-4c9f46dbde67 | button | Does the final product conform to the above criterial? | Yes,No
2bac1c75-7281-5237-84b8-1f7a1187f87b | note | Freq - Each Lot
80078f6a-110d-58e8-9417-670e55dd1db6 | note | Key - R
0329ad64-bdfe-5b4a-b28c-7e079a9991bf | note | Resp - SE
3861828f-659c-5e3c-8738-3537b842e4f0 | date | Inspection Date:
| checkpoint | 5.2 - Preparation of Final Surface. (For Underside of Pavement Layers and the surface of the Cut Floor).
16ea9dae-b1c3-595d-829c-8fdc9660e620 | note | Ref docs - VR Clause 204.15
46ef3385-d75e-568a-9e51-f0481fa74144 | note | Acceptance criteria - Surface is Smooth, Hard, Tightly Bound and Free from Depressions Capable of Holding Water.
36631b3d-ed40-5508-9f54-3c33843f4949 | note | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of OMC prior to the placement of any pavement layers.
e4ec87d4-f0fd-5ed1-9060-3842a929f734 | button | Does the final product conform to the above criterial? | Yes,No
45231f03-a2ca-5c20-b6fd-f633775f13d7 | note | Freq - Each Lot
13f59b89-5767-5fdd-9d23-dcf1896a0ab5 | note | Key - R
6c9bf42f-0e91-5a2a-ad4b-975025fca5b6 | note | Resp - SE
3f1d190d-2597-51af-819c-5fa5f64d4048 | date | Inspection Date:
| section | 6.0 Work Lot Close Out
| checkpoint | 6.1 - Test Reports
c577dc1a-546f-5b7f-9c32-6456e799eb1c | note | Ref docs - DoT Specs
c489df70-a3ba-5d05-b01d-3db2179f67a5 | note | Acceptance criteria - All Test reports received and reviewed
6ae75d0a-9b33-5f2e-b656-333f613d39d6 | note | Freq - Each Lot
4b045265-05e8-5a60-a370-b848c0cb837d | note | Key - R
db706eef-ad12-5897-a4dc-d7293f46384c | note | Resp - SE
82de72b2-7d51-55e6-ac97-416cbd0b1600 | note | Remarks/record - NATA Endorsed Test Reports
2eeaab85-e6aa-5df9-a598-20ca5b9124e9 | date | Inspection Date:
| checkpoint | 6.2 - Product Non-Conformance
5dfba075-1951-5a7b-8871-a9f0b59a2b9b | note | Ref docs - QMP
a4e7c1f1-49a9-5a97-bd19-9b7b42b48ba1 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
a6df7b39-b31a-50cd-a410-bf9568f014ee | note | Freq - Each Lot
790fc848-a2ca-516d-bbf8-bed916593076 | note | Key - R
47134d44-f6d8-541a-9213-080d64db2aff | note | Resp - SE
f195881f-a884-5d6d-8e41-1e6ba7ebe697 | note | Remarks/record - NCR reports
aa296e1a-5e1d-5598-9ef8-33339649f8b8 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0052 Telstra Relocation | itp | 1630-P200-SYM-QAC-ITP-0052 Telstra Relocation |  |  | 9bd3b981-3211-4760-993c-356ca5ae4a6a
| section | ITP Details
| checkpoint | ITP Details
9717b8a3-a147-50a6-afa7-7719add4c2be | note | ITP No. - 1630-SYM-QAC-ITP-0052
fdc1ac1f-d2d4-5636-ada9-a72439990534 | note | Rev No. - 00
b7d05879-d1f6-5430-85e5-2d09314c4902 | note | Date of Issue - 24/08/2023
74f6a118-ffde-56fc-9fc9-e5ba6a6d2387 | note | ITP Type - New/Revised
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out
2d76476b-6eb4-5918-98ea-962d33623fb0 | note | Ref docs - IFC Drawings
8e86e164-caba-501f-b9d4-242038c3e4f7 | note | Acceptance criteria - Ensure alignment setout has been completed and pegged.
74a89bcf-03fa-56ef-aa63-a6218f121f7e | button | Has all of the above been completed? | Yes,No
d6775f3d-6da4-59cf-8ca0-2d543e7a3c0b | note | Freq - Prior to start of works
257ac27d-7676-547a-a769-872ccee2bcbd | note | Key - H
c5925389-68b7-5d6f-b286-49e76baa410f | note | Resp - SE/SS
| checkpoint | 1.2 - Boring under Carriageways
eb467532-4bdc-5f7a-abbb-687bab5f7dbe | note | Ref docs - VR Clause 706.04
82881a08-38cd-5bbe-b336-e63b4687af0f | note | Acceptance criteria - Boring by water jet not permitted. Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
9d08e7be-2add-5507-9569-5500e13da46a | button | Approval to proceed? | Yes,No,N/A
8eb34248-179d-5036-9da7-cd14630a197b | note | Freq - Prior to start of works
ae354d6a-2d2b-5d93-96bc-b8ac035b9312 | note | Key - H
909db19a-7781-5371-bbfc-5e5ae59c3f59 | note | Resp - SE
9901fff1-d51d-5762-9d23-6e08634e9ac8 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Conduit Covers
| checkpoint | 2.1 - Excavation and Cover Requirements
e348f0d5-ba0a-5465-845c-aa70afbcc986 | note | Ref docs - VR Clause 706.03
dc672c47-1ed5-5264-b43b-599b6e8fd388 | note | Acceptance criteria - Cover requirements for telecommunications assets shall be:
3a5f91e6-b443-593d-b368-adb99cda94ec | note | ○ Pavement surface to top of conduit minimum 1200 mm.
2d638516-38f7-5cb3-992b-e219d8a046dd | note | ○ Invert of open drain to top of conduit minimum 750 mm.
6e0f8e81-e6cf-584e-bf05-e3a402020a34 | note | ○ Unpaved areas to top of conduit minimum 600 mm.
ef188f67-d8e8-580d-b2d7-97e1d163a6ab | note | ○ As per asset authority requirement for cover to other assets
b8bbbbbc-003b-5e6c-861b-de33f84d6326 | note | Or else as specified on design drawings in accordance with asset owner requirements
f9c5888d-21d2-5fd0-8036-b30f67419b6b | button | Has all of the above been completed and approved? | Yes,No,N/A
a26e66fa-393f-5470-98ce-0a530530fdd4 | note | Freq - Each Lot & Each possession
a97052bc-6ebe-5cc0-b14e-ac3046209747 | note | Key - S
3cfe11cc-1f23-5cf6-bbb9-adb8e37e85b2 | note | Resp - SE/SS
| section | 3.0 Backfill and Compaction
| checkpoint | 3.1 - Backfilling/Compaction (Areas not being paved)
b12d68d3-8e35-5799-835a-7bc1157a1ce8 | note | Ref docs - VR Spec 706.08, 706.09
2b5d44b1-83bc-5629-a9f7-a3a9ad5eff04 | note | Acceptance criteria - Unless backfilling requirements are specified by the Asset Owner Authority, backfill material properties and placement to be as per table VR706.061:
360b8eb9-267a-5a21-9653-5e2da091ae94 | note | ○ The opening shall be backfilled with common backfill placed and compacted as specified in layers not exceeding 200 mm loose thickness.
cc1d4932-bb01-5426-ac84-8b1abf24d121 | note | ○ Moisture Content between 85-115%
20f8e05b-ba23-5037-9e2c-25e3608662b5 | note | ○ Compacted to refusal using handheld mechanical equipment with consideration to utility owner vibration requirements.
d3283d7b-8504-5a61-9d88-56c268edf254 | button | Has all of the above been completed and approved by the relevant authority? | Yes,No,N/A
df65679c-5710-57a1-a1b4-d672c4b117ca | note | Freq - Each Lot
58f104d2-e30c-5b66-915b-1de93a8fe095 | note | Key - R
99bec211-534d-568b-a694-4026dc8f1965 | note | Resp - SE/SS
9a6c4596-d8d4-5a71-8768-1bbeff12fc5e | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
b2d90803-a80b-5333-89fc-7e1264ff2e88 | button | NATA Test Report (if applicable) | Yes,No,N/A
| checkpoint | 3.2 - Backfilling/Compaction (Under areas to be paved)
6dda89a7-57a4-5a88-8e24-f6f4019cabf1 | note | Ref docs - VR Clause 706.08, 706.09
b4daa167-ef6f-5951-9c4b-0331d11f3b0a | note | Acceptance criteria - Unless backfilling requirements are specified by the Asset Owner Authority, backfill material properties as per VR706.061:
6081d3f0-9b30-5ea3-b8aa-43f6a805113b | note | ○ Trench shall be backfilled up to the nominated or designed subgrade level with selected backfill material placed and compacted in layers not exceeding 150 mm loose thickness, and above that level with common backfill material.
a449c105-a117-5c29-a57a-8977ce917030 | note | ○ The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97% based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
8feda12b-b67d-5d21-b265-5f0688891771 | note | ○ Considerations to be made to allow for Asset Owner Authority working restrictions, including vibratory restrictions.
c81955c1-753c-5f23-8990-44865f9e90a0 | button | Has all of the above been completed and approved by the relevant authority? | Yes,No,N/A
f626a958-813c-5af4-aaf7-40b6a07f03aa | note | Freq - Each Lot
17724898-b798-56f5-8243-c89150ca45ee | note | Key - R
5d805100-a8d6-52be-9ced-510225a14fc3 | note | Resp - SE/SS
c95d5456-00b0-5117-ae73-0f6f5ac6fc31 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
411dfa2c-cc84-5606-9699-a4bef16213bb | button | NATA Test Report (if applicable) | Yes,No,N/A
| section | 4.0 Work Lot Close Out
| checkpoint | 4.1 - Test Reports
77c6c77f-70f4-5abd-977b-3287b443fc9c | note | Ref docs - VIC Roads Specifications
cefc7097-5dac-510d-a737-cceed8e2e845 | note | Acceptance criteria - All Test reports received and reviewed.
3ba8d233-e1e0-543c-beea-ab5636aa86a1 | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
8f86a83f-fd7c-570f-8ac0-da73fdd39002 | note | Freq - Each Lot
9636c44e-9d07-570b-98db-35730d4634c8 | note | Key - R, I
6717c290-602f-5f09-8aef-5df0d31de0ab | note | Resp - SE
| checkpoint | 4.2 - As-built Information
429c409a-0847-576c-ad9a-71b255b62cd3 | note | Acceptance criteria - Where applicable, asbuilt pickup or as constructed drawing been provided by authority.
715593ef-96e2-5563-9062-19d85aa9833f | button | Has all of the above been completed correctly and to a high standard? | Yes,No,N/A
1236a693-5b76-593b-8b65-3efb6c5d3692 | note | Freq - Each Lot
c483f21d-4da7-5ef8-8d4f-fc047556ca7c | note | Key - R
f51550dc-867a-5852-af53-101677ef838f | note | Resp - SE
| checkpoint | 4.3 - Product Non-Conformance
8fc5053c-3e47-598e-a5d6-437ccec56788 | note | Ref docs - CQMP
41ba6b22-4447-5ac4-a0f8-e2fac9d90336 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
b551e2bb-2812-5005-8fdd-9f2514eea1dd | button | Has all of the above been proven to meet and/or exceed minimum tested requirements? | Yes,No
4bc16332-8500-5488-96a0-48bde6260b5d | note | Freq - Each Lot
c49eca69-ee64-5ae4-926d-ac74ba49008f | note | Key - R
a8f2096b-9273-5e8c-ace3-2ceab2149239 | note | Resp - SE
4402e6a6-a821-5451-94d5-c11add1d7bd2 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a61ad8bd-5dbc-54c1-bbc2-7aa8eb1595ff | button | NCR reports | Yes,No,N/A
| checklist | 1630-P200-SYM-QAC-ITP-0055 Public Lighting Electrical Installation REV 01 | itp | 1630-P200-SYM-QAC-ITP-0055 Public Lighting Electrical Installation REV 01 |  |  | cf0c9986-7e55-4ad9-9e37-e8c540dd8a8f
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Services
346bdec9-b869-5249-9651-7e7035f96cec | note | Ref docs - VR Clause 731.05
be5d996b-716d-5d06-b2e8-46c19135373b | note | Acceptance criteria - The location of all existing underground and above ground services has been proven and confirmed on site by the Contractor before commencement of any works.
2159a3be-2487-5cec-bb41-45af65c1a95a | note | Freq - Prior to start of works
ce955b9e-7a0f-5524-bd90-cece81b3975c | note | Key - H
f9e300e0-6e9c-5896-b6cb-cd133236ec59 | note | Resp - SE/SS
73498b28-da19-56f4-8886-9d54d7b1ceb5 | note | Remarks/record - Lot Map
b196b724-6c50-5a73-86c6-fa64690664d9 | date | Inspection Date:
| checkpoint-no-value | 1.1.1 - Lot Map
cd41955f-348e-5426-8d23-af5b5b4a5087 | button | Lot map | Yes,No,N/A
36d89477-569d-5f4a-90a1-0006d9765171 | date | Inspection Date:
| checkpoint-no-value | 1.1.2 - Environmental Permit
3ee00e3a-4085-5a03-bd07-be5233b290ec | button | Environmental permit | Yes,No,N/A
a29eedc4-6c37-5544-b288-958bde33e778 | date | Inspection Date:
| checkpoint | 1.2 - Check Survey Set-out
0aab3828-052c-51cd-8d55-11dcb8bd3cf0 | note | Ref docs - IFC Drawings
e00ddd32-37db-569f-bf9c-176c07a559da | note | Acceptance criteria - Survey set out including frame, benchmark, and recovery points in place.
d87feff1-ba18-5e20-89b0-26282f0580c1 | note | ○ Set-out to include height of finished surface and checks to be completed to ensure pole is clear of any obstructions (such as future guardrail).
5cd014b9-4023-5f0c-b583-a6ca78a19ba3 | note | Freq - Prior to start of works
2373b6d7-cb97-5cfb-8f21-c89b660563c8 | note | Key - H
8cd1ad52-659b-50b6-8d7b-43f319569808 | note | Resp - SE/SS
ff6fec29-9d2f-5960-91b5-a2ba2f44d349 | date | Inspection Date:
| section | 2.0 Poles and Outreach Brackets
| checkpoint | 2.1 - Installation of Frangible, Impact Absorbing (IA) and Slip Base (SB) Poles
f9f07576-ed3f-54cc-bfb0-9a093d0169e4 | note | Ref docs - VR Clause 731.06 (b) AS/NZS 3000 IFC Drawings Pole Manufacturer Specifications
457b4a82-784a-5853-b44c-452f5c6ca4ed | note | Acceptance criteria - Frangible poles are VicRoads type approved, and conform to VicRoads Specification TCS 014 Supply of Frangible Street Lighting Poles and to drawings TC 1064 and TC 1065. These poles were transported to the site of the works in one piece with the base section securely bolted to the upper section.
b75b45c6-5259-5372-9873-f4fd2bf33ac2 | note | ○ Pole foundations were constructed in accordance with manufacturers requirements.
388e0097-0e5a-5044-a52e-13f2e5c2f03a | note | ○ All frangible poles are installed in a vertical position +/- 2 degrees and in accordance with AS/NZS 3000.
d772a32b-a8c6-55b0-a44a-e5f35d423a99 | note | ○ All absorbing poles are installed so that the joint between pole and base is located at 75 mm ±25 mm above the finished ground surface level.
022d2600-c733-576c-87c4-e105f27176a4 | note | ○ All slip planes for slip base poles are located 75 mm ±25 mm above the finished ground surface level to allow proper movement of the pole if involved in a vehicle impact.
b6183a69-c47f-55b7-8461-1b870e46e589 | note | ○ The Contractor backfilled around the pole and reinstated the ground around the pit and pole. Where a concrete mowing pad has been formed around the pole at ground level, the Contractor ensured that the bolt heads are kept clear of the concrete.
f852f769-2013-5b3b-b7dc-51ff85c93118 | note | Freq - Each Lot
34b353a9-37fb-5d20-90cd-bf4ac2eb9ac2 | note | Key - I
ed8127f1-f6a9-5d10-ba5b-2de0b6c82aef | note | Resp - SE/SS
5fa0c79b-9946-5c31-968f-1dcb2b1fddba | tickbox | Remarks/record - Installation Records from Subcontractors
cf2fc465-02be-54de-abf7-930ca2078553 | date | Inspection Date:
| checkpoint | 2.2 - Installation of Outreach Brackets
b233b3ec-3631-53a8-9e05-cf5f60f7c8dd | note | Ref docs - VR Clause 731.06 (a) Table 731.061
647ee612-bca3-54d4-8c79-af45f8f81a75 | note | Acceptance criteria - All outreach brackets are firmly attached to the pole spigot using the clamping bolt assembly which is supplied with the outreach bracket (refer TCS 050, TC 1060, TC 1061). The bracket and luminaires are aligned as shown in the road lighting design at right angles to the vehicle path on the road, and installed and plumbed the pole and luminaire(s) to within the tolerances specified in Table 731.061
eeedd2da-04be-59ed-84e0-94dff4d9d2b1 | note | – – – – – – – – – – – – – – – – – – – – – –
7640acfe-c543-5ca5-a9c0-a409625979af | note | Table 731.061 Pole and Luminaire Orientation Details
1c893e66-effb-5915-98e2-c970ddeead3d | note | – – – – – – – – – – – – – – – – – – – – – –
db9cfd16-614f-534f-9de9-cd885f9c3e0b | note | Pole Height SB/IA Metres ¦¦ Lantern Mounting Height Metres ¦¦ Lantern Type (LED) ¦¦ Max Bracket Length Metres ¦¦ Lantern Angle to Road Degrees ¦¦ Lantern Upcast Angle Degrees ¦¦ Lantern Spin Angle Degrees
6e66ffbb-4de3-5ced-823c-a5301264e750 | note | – – – – – – – – – – – – – – – – – – – – – –
0e4f57eb-09e3-524d-a2d2-5224e9243ca3 | note | 8.5 ¦¦ 10.0 ¦¦ L1 ¦¦ 3.0 ¦¦ 90 ± 5 ¦¦ 5 ± 1 ¦¦ 0 ± 1
3e99205b-c1e1-5117-8979-562c81f83d4d | note | 11.0 ¦¦ 12.5 ¦¦ L2 ¦¦ 5.0 ¦¦ 90 ± 5 ¦¦ 5 ± 1 ¦¦ 0 ± 1
3459d971-1815-5b93-9595-c80527ea51a6 | note | 13.5* ¦¦ 15.0 ¦¦ L4 ¦¦ 5.0 ¦¦ 90 ± 5 ¦¦ 5 ± 1 ¦¦ 0 ± 1
59072747-7cdf-55c6-b5b8-5fa54bd1d1e7 | note | – – – – – – – – – – – – – – – – – – – – – –
1ecf5306-4668-5e8c-ba18-df3cc1ba1e1a | note | Freq - Each Lot
496a48f2-e79c-5f1c-8170-70fdf60e7be3 | note | Key - I
b6a5f524-dee5-500c-b805-5a66e2915586 | note | Resp - SE/SS
785d74aa-64b4-50dd-98c4-cb8ecc7ff620 | tickbox | Remarks/record - Installation Records from Subcontractor
c8c4f175-1544-59f1-8919-6fcb425d992d | date | Inspection Date:
| checkpoint | 2.3 - Torque
f8cd5ed4-3f28-5bba-9661-5779695b0439 | note | Ref docs - VR Clause 731.06 (d) TCN 006
9e2a2870-c8c8-50a0-8567-22d937cbc516 | note | Acceptance criteria - Slip base poles are installed in accordance with the following requirements:
2e9b964a-e442-546c-bf45-88450774e61a | note | (i) The pole bolt and nut assembly were installed such that the nuts are placed in the upper position to enable ease of access for correct torque installation and for subsequent 30 day cycle torque maintenance checking for slip base poles only as per Work Instruction TCN 006 - Work Instruction Retighten Slip Base Pole Flange Bolts
f9faf6a4-1695-5e38-9f67-49c7293685b5 | note | (ii) The bolts and nuts have been re run after galvanising and are free of excess galvanising in the threads
e5c86bcc-c23a-520b-a8c0-885161f87d02 | note | (iii) The thin slip plane washer has been supplied flat and free of kinks, bends, deformation and warping - a damaged slip plane washer can result in incorrect torque and eventual pole failure and shall not be used
41d81f79-f695-5bb6-be5d-edfe1d5f8c46 | note | (iv) The slip-plane flange nuts have been slackened off ONE AT A TIME and re-tightened as specified in TCN 006 Work Instruction Retighten Slip Base Pole Bolts.
1f44b6e6-a101-5a1e-8242-a5645a95e16c | note | The torque wrench used to tighten the bolts and nuts shall have a current calibration certificate (i.e. not more than 12 months old). The Contractor shall provide a copy of the calibration test report upon request by the Superintendent.
042cf498-6c08-5441-ba72-ef7916ace18c | note | Freq - Each Lot
8ccd91f1-d685-5109-91bd-328d830c4dc2 | note | Key - I
5a7de021-ad3b-5f7d-86c2-84d9af5d7af1 | note | Resp - SE/SS
cbedcfe7-d85d-5ab8-a18b-52f91f7c50cb | note | SI Key -
b67e6023-15f2-5ce9-9c96-f3ee5385f906 | tickbox | Remarks/record - Installation Records from Subcontractor
64244d2b-66da-5d09-9238-95d0fbe3a08b | tickbox | Remarks/record - Calibration Certificate for Torque Wrench
da3b4341-844e-53bc-9851-076b1fe0643c | date | Inspection Date:
| section | 3.0 Luminaire Orientation
| checkpoint | 3.1 - Luminaire orientation
6ac8bc1b-0d7b-5084-a86c-3d72ac10c97f | note | Ref docs - VR Clause 731.07 Table 731.061
74cb4c0a-87a9-5ce5-94d6-f06e6ee76ff1 | note | Acceptance criteria - The Contractor installed luminaires such that they meet the mounting and orientation requirements of Table 731.061.
34af7e8e-29b1-5318-8b3e-3ca9aea7ca66 | note | Freq - Each Lot
ca17b86e-2c59-59ba-b75f-12d9dda5b659 | note | Key - I
54513b59-32e8-598b-8455-d40e7651dd27 | note | Resp - SE/SS
695b4b5f-943c-51dd-81df-a1bfadf6a6f0 | tickbox | Remarks/record - Installation Records from Subcontractor
6345c3c7-60bc-5424-b37b-e702fe078fe2 | date | Inspection Date:
| section | 4.0 Conduits and Pits
| checkpoint | 4.1 - Conduits and Pits
d92b01dc-e4c4-5220-92cf-deacc9f0dcde | note | Ref docs - VR Clause 731.08
b0b7f008-c561-5cc2-8d70-da2810680764 | note | Acceptance criteria - Pits are generally located 1 metre in advance of, and 1 metre off the line of, each pole. A two metre spare length of each cable has been left coiled in each pit.
c6643b1f-e3f3-509f-ba13-28ac47242ea8 | note | Freq - Each Lot
ef6e8d46-855a-530a-8cd5-83a7c9268eb3 | note | Key - I
47535069-d00f-5226-96b6-869b4e622200 | note | Resp - SE/SS
de61ad37-c9c0-505a-b36c-120509a4650b | date | Inspection Date:
| section | 5.0 Electrical
| checkpoint | 5.1 - Wiring Rules
d865fd9b-676b-5d5f-b367-119348b1b74a | note | Ref docs - VR Clause 731.11 (a) AS/NZS 3000
0085f133-12a0-51d0-872c-160c8af17a6e | note | Acceptance criteria - All electrical works, electrical fittings, materials and installations fully conform to the requirements of the latest edition of AS/NZS 3000.
fb6b5d1a-ee2d-5bff-9101-eaf995f9c0b0 | note | ○ Where AS/NZS 3000 did not cover a specific aspect of the electrical works (e.g. such as pits) all works were undertaken in conformance to the requirements of the Energy Safe Victoria.
6c98a3a9-38e8-5d2b-b651-a7a7965308c9 | note | Freq - Each Lot
c980aee0-81f1-5522-ae97-80bb95691fe2 | note | Key - R
1b489711-a377-51e8-b802-171b77a17df7 | note | Resp - SE/SS
0c6d70fb-1fa1-509f-8e8a-9775a5d84333 | tickbox | Remarks/record - Installation Records from Subcontractor
fe6358ea-7621-5338-bef9-32d240b5eafb | date | Inspection Date:
| checkpoint | 5.2 - Registered Electrical Contractor
c559a99a-985f-58e6-bc24-517db635d8a2 | note | Ref docs - VR Clause 731.11 (b)
ecb79759-a5a0-5d20-a0e1-0a47e224f955 | note | Acceptance criteria - The electrical contractor engaged to carry out electrical works on any VicRoads road lighting installation (Public Lighting Site) were a Registered Electrical Contractor, being registered in accordance with:
a4ad32c1-a350-5fc1-80b7-7f99affc61fa | note | (i) Part 3 of the Electricity Safety Act 1998; and
150d9b44-b128-5280-abf9-6502b05bbc05 | note | (ii) Electricity Safety (Installations) Regulations 2009.
dd87d51a-7c17-522b-9a99-ffe154ccb1b0 | note | The electrical contractor was also prequalified within the VicRoads prequalification scheme at the level of ‘Traffic Control System Installation and Maintenance; Traffic Control Equipment (STCE)’.
8d99a209-cdc9-5cd5-8766-5fab5402ac02 | note | Freq - Each Lot
308877d1-9119-5989-a7d3-70bcf4905a05 | note | Key - R
5e1962f6-11d6-5e56-8822-1b13c7b94863 | note | Resp - SE/SS
f675f223-aad1-5615-baf3-fa468e44b251 | tickbox | Remarks/record - Compliance Certificate of Electrical contractor
d30b63cb-3581-5692-951a-e93c91cc5fd7 | date | Inspection Date:
| checkpoint | 5.3 - Electrical Design
ed096afe-274f-549a-a836-74929626d90e | note | Ref docs - VR Clause 731.11 (c)
5c6f14bc-5f9a-50b3-8c14-16626e80b325 | note | Acceptance criteria - Where practicable, all above ground electrical installations and works, such as point of power supply and the distribution cabinet, have been located a minimum of 5 m from any carriageway.
058265eb-a7e8-59f2-a2c2-ad30321e347e | note | Freq - Each Lot
ac81ca6b-a22f-549e-a4b4-0b7fefc0ee14 | note | Key - R
e43a441f-6762-5384-a720-024aaa2f6967 | note | Resp - SE/SS
94f53ec7-8af3-5fa2-96df-25040b54d7c5 | date | Inspection Date:
| checkpoint | 5.4 - Power Supply
4c9669ae-e338-5c64-91df-042b3ac0349e | note | Ref docs - VR Clause 731.11 (d)
6aa478e5-a548-59a3-a2bd-5281c6c131d5 | note | Acceptance criteria - The supply of electricity is in accordance with the following:
05e3d31d-d878-5339-9991-dfb2151cdf8d | note | (i) The ‘Point of Supply’ has been determined in conjunction with the relevant power distribution company. The supply of electrical power from the point of supply to the meter in the distribution cabinet has been in accordance with the requirements of the relevant power distribution company.
3e5255c3-8bb5-56ff-999d-fbf085a3e039 | note | (ii) The electricity supply has been a 415 volt 3 phase AC supply. Single phase power may only be supplied with the prior written approval of the Superintendent. The low voltage power supplies has been strategically placed to minimise the maximum load on each lighting circuit and to limit the extent of voltage drop.
61c18044-68a8-5002-9401-4b3140ff1415 | note | (iii) In accordance with the wiring design, copper consumer mains cable have been provided in underground conduit to the base of each LV supply point pole mechanically protected to 2.4 metres above ground level (on the pole) with 6 metre tail to power distribution company requirements for final termination by the power distribution company into a 3 phase, 100 amp, Fused Mains Box, 4 metres above ground in accordance with the Victorian Service and Installation Rules (SIRs). The cable for trunk electricity supply from the ‘point of supply’ to the road lighting distribution board or the appropriate road lighting power supply pit (where no distribution board is installed) as appropriate, is not less than 16 mm square 4 core, 3 phase plus earth, copper XLPE cable.
83c43b93-60ae-581f-883f-8ae9b5bec06c | note | Freq - Each Lot
1f8e65db-16b8-5cfe-879a-8a5626cb6c08 | note | Key - I
3dc48f1e-29c1-5b8a-af86-e1bbcdfa4c5f | note | Resp - SE/SS
1021aa0b-5e07-55d0-a4ad-79ef086a7f5e | tickbox | Remarks/record - Installation Records from Subcontractor
22ad9b13-7e6e-5574-83dc-366751ebbfbd | date | Inspection Date:
| checkpoint | 5.5 - Electrical Distribution Cabinet
a3eff2c9-a147-5752-885e-7be23030ae32 | note | Ref docs - VR Clause 731.11 (e) TCS 043
8c035f20-6e7a-5c33-9ae2-05db4fd2c060 | note | Acceptance criteria - (i) The distribution cabinet is in accordance with VicRoads Specification TCS 043.
db2330ce-7159-50ec-852a-cbe1c65162c9 | note | (ii) A distribution cabinet may be used to supply electricity to road lighting assets only or it may be used to supply a combination of road lighting assets and other ITS assets.
2450eff9-fa2e-5546-ab35-9a36105da2d1 | note | (iii) Unless specifically approved by the Superintendent, each site or installation shall include one only distribution cabinet.
2c2c9f64-f61d-5b19-8da6-e0a246f43d1e | note | (iv) Where an existing distribution cabinet does not have sufficient spare capacity for additional assets, a new distribution cabinet with sufficient capacity has replaced the existing distribution cabinet.
d7774609-91c0-550d-b014-21885b3cf8da | note | (v) Two or more distribution cabinets at the same location are not installed.
3805126f-38f8-53fb-9857-f9af71294ef7 | note | (vi) The cabinet is located not less than 5 metres from any carriageway, and where possible, beyond the clear zone. For any distribution cabinet located within the clear zone, the Contractor has provided traffic barriers to protect the cabinet.
39a488a1-4796-53a3-a540-3c7f849ba212 | note | (vii) The PE cell has been located so as to not be affected by light spillage at night.
b8e377b6-34fd-52fa-9d30-935dd7a20dbf | note | Freq - Each Lot
bd0ff36a-5c77-5053-9698-f1cc96a0b82a | note | Key - R
c3fe155a-f611-5cca-b42d-50baac235319 | note | Resp - SE/SS
8f9193ad-1b89-5e04-aa80-1b6657f119d1 | tickbox | Remarks/record - Installation Records from Subcontractor
a1fe6fba-2813-5d41-bb0d-7ff22c38a1cd | date | Inspection Date:
| checkpoint | 5.6 - Earthing Requirements
2f196ccd-87b1-5cee-9c6f-d266d673c299 | note | Ref docs - VR Clause 731.11 (g) AS/NZS 3000
a249a326-78cf-5f19-bda2-c57a5ab670e5 | note | Acceptance criteria - An earth rod has been installed in the earth rod inspection pit in the concrete base of the distribution cabinet as shown on VicRoads Standard Drawing TC 1062.
314da189-96d4-5cf6-870b-d27ced5faf96 | note | ○ An earth cable attached to the earth rod has been provided and installed in all VicRoads lighting circuits from the distribution cabinet. All earths have been terminated within the lighting distribution cabinet in accordance with Wiring Rules AS/NZS 3000 for the M.E.N. (multiple earthed neutral) system of earthing.
fb44a443-8600-5bc2-89b2-497d800750e2 | note | ○ Where necessary, and in accordance with the wiring design, a separate PVC insulated and sheathed earth cable has been provided to ensure compliance with AS/NZS 3000.
59838d71-6d0e-5292-8d47-c1811a988985 | note | ○ All poles have been individually earthed to the earth cable in the pit in the case of frangible poles and to the earth cable in the pole in the case of rigid poles.
aa4abbc8-d4c2-58f0-8d7c-ca77aeedc319 | note | ○ All luminaires have been individually earthed.
ea96d7ee-0fb4-58c3-a5ad-599793e8decd | note | ○ The size of earth cable is to be designed to ensure a Fault Loop Impedance ‘low enough to allow sufficient current to flow in the fault loop to cause the protective device to operate within the disconnection time’ in accordance with AS/NZS 3000.
49abf547-54d8-55e2-ada3-430f738ae099 | note | Freq - Each Lot
ab1c7232-3af8-5641-b2ab-91187d0cd844 | note | Key - I
a5084c9f-3de8-5ab9-ac16-bafb037c9413 | note | Resp - SE/SS
19703fe0-e4a6-555e-a805-309d42e80655 | tickbox | Remarks/record - Installation Records from Subcontractor
c1a02d3e-5c10-5b03-a619-d6979c763c8d | date | Inspection Date:
| checkpoint | 5.7 - Trunk Cabling
db1fd457-9e1f-58f1-909a-fedbcc822d79 | note | Ref docs - VR Clause 731.11 (h)
9f37023e-b79d-5bb4-97b9-760a583462c3 | note | Acceptance criteria - The cable used to connect the distribution cabinet to the first lighting pole and between lighting poles is one of the following methods:
b843e4a4-31ea-53d5-a9ac-a6d5cb245751 | note | (i) Orange circular, 4 core and earth
9d37a217-4979-5229-a604-5fc5bb6e3be3 | note | (ii) XLPE, 4 core and earth.
bf1dd18d-77c0-5f3d-944f-033aaa8cc5d2 | note | For each trunk cable entering a cable pit, a minimum of 2 m of spare cable has been coiled and left in each cable pit. This is to provide spare cable length for maintenance purposes.
f067b8bc-c96e-575e-ae48-0d15082a754c | note | Freq - Each Lot
fc87f4ef-6d6d-5e29-a6d8-fe580d4a31f2 | note | Key - I
3439e6d2-6d6d-56e5-8f1f-148001f9c10b | note | Resp - SE/SS
a2a886d0-e290-555e-b421-4782765080cb | tickbox | Remarks/record - Installation Records from Subcontractor
fab57f9f-2c51-5d8c-bcd5-1122995ae7ac | date | Inspection Date:
| checkpoint | 5.8 - Jointing
046e6e07-acc8-5a54-b31c-3fae4eb56012 | note | Ref docs - VR Clause 731.11 (i)
d23b1e28-6a5b-5e88-b213-f6ae6cc581f7 | note | Acceptance criteria - All electrical cable joints in pits are waterproof.
6479f3d0-cec7-53c9-9b04-0a65d0ab52ae | note | ○ Jointing is only allowed when connecting the pole wiring to the trunk cable as detailed in (i) and (ii) below.
ad2c58b1-9625-5fcb-9b29-5aeca913f367 | note | ○ Joints in the trunk cable for any other purpose (e.g. to extend a cable length) are not allowed without approval from the Superintendant.
ae10ad14-dcb9-5c30-b69e-f5fc7ad32fe6 | note | ○ Connection of the ‘trunk’ wiring to the ‘pole’ wiring in the cable pit has been achieved in one of the following manners:
efa99aa7-60ef-5e8a-afbd-a481a5d0e5ad | note | (i) Bell Style Enclosure
4c883116-2e6a-50ef-96cd-80fbb41f464c | note | An appropriate sized, VicRoads approved, ‘bell style’ enclosure with an ingress rating of not less than IP68. The cables to be fitted into the enclosure and sealed with heat-shrink or similar in accordance with the enclosure manufacturer’s directions. The enclosure is to include:
2f9a0615-fc1a-5636-9ef5-6657733b2761 | note | (i) Active connector
b5ee3245-569a-5b49-80c4-ee14646e4b15 | note | (ii) Neutral connector
b4cf14b4-0643-5081-890c-f7cb1c204a01 | note | (iii) Earth connector
720b8839-2ff3-5263-84cb-01f6e3af1cae | note | (iv) In-line, 8 amp, waterproof fuse to enable complete isolation of pole for maintenance purposes to enable complete isolation of pole for maintenance purposes.
4b0ed9fe-f20a-5d37-8b00-44970fd3a1ce | note | All connectors are further protected from water ingress by use of a water-displacing gel filled cap.
a3a1e355-4be4-542f-bd8b-2647f5447124 | note | The enclosure is designed to be held in place on the side of the pit, just under the pit lid, using a suitable mounting bracket. See Standard Drawings TC 1071 and TC 1072.
173922af-1405-5e4c-a652-e955163dc8c6 | note | (i) Underground Insulation Piercing Connectors
542b2747-d2fd-58b3-9cb1-e6e3b4ff1e88 | note | Suitable sized, insulation piercing, low voltage, waterproof connector. Such connectors are the type that use torque controlled, shearing type bolts. This type of connection also uses an ‘in line’ submersible 8 amp fuse to enable complete isolation of pole for maintenance purposes.
3586bd0b-4ea3-5f9a-8d0d-45e5fd0a868b | note | Freq - Each Lot
9e26412c-fc9a-520b-bb9d-f312f09127ab | note | Key - I
387fb727-148e-502f-bb44-3dce59762bb3 | note | Resp - SE/SS
866d4aee-7d60-5e86-81d6-10ad6928e6ed | tickbox | Remarks/record - Installation Records from Subcontractor
94f83def-d8ab-5723-af64-48d40979b63c | date | Inspection Date:
| checkpoint | 5.9 - Pole Cabling
818adcaa-77c8-5003-920d-70eae1fdf844 | note | Ref docs - VR Clause 731.11 (i)
c8eda293-19eb-56ff-ae91-b9fef2cc0544 | note | Acceptance criteria - Each pole has been cabled from the cable joint in the adjacent pit to the luminaire located at the limit of the bracket arm using one of the following methods:
86f1479d-8d74-5dba-98c1-9c375dd43b09 | note | (i) 2 m2 core, power industry cable with separate earth cable
4f103154-e0bd-5e3e-8206-602088b579b2 | note | (ii) 2.5 mm2, 2 core and earth, TPS (between luminaires on a double outreach only)
f0b69b9b-d4c4-5171-8a1a-08b5ba19dc7d | note | Note: The use of 2.52 TPS within the pole is no longer an approved wiring method.
01251473-a949-5948-816a-d30533b6548f | note | In an impact absorbing pole the cable has been supplied through the flexible conduit fitted inside the pole from the cable termination access door to the pole spigot, as shown in Standard Drawing TC 1064. Where a double bracket arm is used, 1.5 m of cable has been looped between the luminaires.
a330c534-2453-562c-ba6f-91eeae1cf423 | note | Freq - Each Lot
d1a411bf-c5f7-55df-bc7f-e71b944d2476 | note | Key - I
31020e61-d5d6-5ce6-b3cb-a8928b096b1e | note | Resp - SE/SS
e75014cc-8da9-5c76-9e07-eab8f2bc4400 | tickbox | Remarks/record - Installation Records from Subcontractor
3817a121-40b5-5429-a032-798ec13fb335 | date | Inspection Date:
| section | 6.0 Labelling of Installed Assets
| checkpoint | 6.1 - Distribution Cabinet Labeling
46d7a501-1fd5-5abb-abb6-d336e989a360 | note | Ref docs - VR Clause 731.12 (a)
a392423d-a60c-5e4c-9e32-79c37be76400 | note | Acceptance criteria - A cabinet identification label conforming to VicRoads Standard Drawing TC 2100 has been affixed to the distribution cabinet. The Superintendent will advise of the site number. The Contractor has maintained the cabinet label(s) to be clean, free of graffiti and clearly legible. The label has been located such that is can be viewed from the roadway.
cca87296-5c6f-57d8-a988-1b4a179856d6 | note | Freq - Each Lot
f63530e1-2942-514a-9518-8613667a1754 | note | Key - I
4590b21a-6216-5534-963a-e93c27adb839 | note | Resp - SE/SS
b0277041-87f8-53e4-8364-f1b438cb4f22 | tickbox | Remarks/record - Installation Records from Subcontractor
fcc63ed9-dd2d-5e16-b435-1fee51055327 | date | Inspection Date:
| checkpoint | 6.2 - Pole Labelling
7d51996c-036f-5c9a-9829-5a2ef431df8d | note | Ref docs - VR Clause 731.12 (b)
ee31aac7-835c-56b2-a7d8-f13cd643aa0a | note | Acceptance criteria - Each lighting pole has a label affixed to it in accordance with drawing number TC 2106. A VicRoads full asset number consists of a 5 digit site asset number followed by a 3 digit pole number. The string of 8 numbers is considered the full pole number. The pole location identifier provides for additional information to be coded. See standard drawings TC 1076 and TC 1077.
1e3a70c4-d3e5-5ce2-a3a0-e05896e5e4a3 | note | ○ Each label installed has the correct number overlays stuck on - matching the pole identification as per plans and inventory information provided by the Superintendent. There has been no blank squares/boxes on a pole identification label and each square contains a number from 0 to 9.
2b413832-bb52-50a9-bbda-145677b8d92d | note | ○ The pole label directly faces oncoming traffic at approximately a 45 degree angle between 2.5 m to 3 m above the surrounding ground level. For any lighting pole with a single outreach, one label has been installed. For any lighting pole with a double outreach and/or lighting up multiple passageways, two labels have been installed so that they are facing oncoming traffic, allowing it to be readable from either direction. See standard drawing TC 1078.
2679c94f-cbce-5737-a517-94899e7457ac | note | Freq - Each Lot
8a9befb0-0c5f-5542-93d1-84dedaa801e9 | note | Key - I
41e74fbf-05a7-5d92-8f4c-229cfcb86cd2 | note | Resp - SE/SS
ed5dc787-0fd1-52bd-a1db-6cd78bf6fb81 | tickbox | Remarks/record - Installation Records from Subcontractor
2ab4535a-06c7-5a14-81c6-2fa7885e3202 | date | Inspection Date:
| section | 7.0 Completion
| checkpoint | 7.1 - Backfilling, Re-Instatement and Clean-Up Works
139e4a7b-b114-589a-9f94-ca9f2a7265eb | note | Ref docs - VR Clause 731.15
8573cda5-2e84-5c8e-bbd5-674d606feb50 | note | Acceptance criteria - The Contractor has undertaken backfilling in accordance with Section 733 Conduits and Pits for Underground Wiring and Cabling, clause 733.06 Backfilling.
1eb00f15-44f7-5298-9018-bd98c16f5a03 | note | ○ On completion of all excavation and reinstatement works, the Contractor has ensured that all rubble, surplus crushed rock, surplus pavement materials, surplus concrete and all other surplus materials are removed from the site. The Contractor has left the work site in a clean and safe condition.
9d2ff5b5-c3ec-532e-adb8-b390ceccf6c1 | note | Freq - Each Lot
31a16953-be16-585d-a3b4-de925f7cba68 | note | Key - I
c84447ad-1105-544c-8c45-f3aa66d733b2 | note | Resp - SE/SS
3c1f0e07-4629-5372-80b6-66eb7db8470e | date | Inspection Date:
| checkpoint | 7.2 - Compliance
c08fa630-3a0f-5ea3-aeae-e17a08c118df | note | Ref docs - VR Clause 731.16 AS/NZS 3000
7a04bfde-8af4-5a13-a0be-d7e67830792d | note | Acceptance criteria - Following implementation of the installation phase of a stand-alone VicRoads lighting installation under this standard section, the Contractor has:
a49c5676-084e-5db9-b437-b8dbde33f262 | note | (i) Checked and adjusted luminaire orientation as required
df818fe4-d7e4-56b5-9fe2-e409f43e7a9a | note | (ii) Replaced all luminaires containing PE cells, or with the approval of the Superintendent, bypassed the PE cells in the luminaires
dfdd53e9-d262-513e-9051-5e651644cd52 | note | (iii) Replaced all damaged or non-functional luminaires, ballasts, and external igniters
d1d85c16-be17-52ee-8c6e-610921a68ffa | note | (iv) Checked all brackets for type, size, shape and tolerance and replace any not in conformance with the VicRoads standard drawings and within the specified tolerance limits
a0097c8b-4c78-585b-8848-8bb9523f4f08 | note | (v) Checked and adjusted all brackets for fixing and for orientation
bd4107e6-193e-5d0a-8a5e-f3d29aa45a79 | note | (vi) Inspected all joint use poles and joint use mast arms for proper installation and functioning, and rectified all faults
fcac683d-a3d7-5131-a056-46f4d29daca5 | note | (vii) Checked all lighting poles for type, size, location, orientation, bolt washers, bolt torque, slip plane washer, verticality, and ground clearance, and where not in compliance replaced, adjusted or reinstalled as appropriate
f877d1e9-58ad-5d40-832a-d9803f86329c | note | (viii) Inspected all pits, conduits, cables, and all other components, and where faulty repaired or replaced as necessary
043a1826-dc5c-57c2-a4b6-f27f83d3987d | note | (ix) Checked all electrical circuitry, materials, components, and equipment for conformance with AS/NZS 3000, and rectifed where full compliance has not been achieved
ebe1c018-8d3e-5df7-8188-6e682745ff03 | note | (x) Checked and confirmed that the distribution cabinet has been properly installed and sealed from pests and moisture and rectifed as necessary
e9af99e5-3fd9-5b05-94ca-d80a58efa2e7 | note | (xi) Inspected and tested the distribution cabinet for faults and non-complying components
fe45cb26-f57a-5f76-a360-a27234769222 | note | (xii) Tested the PE Cell and switching gear and replaced if found to be faulty or performing unsatisfactorily
d9096f99-0709-5bfd-bd62-c5f69b79604b | note | (xiii) Checked circuit diagrams for accuracy of each respective circuit
bfdb3e94-1443-5cb0-99df-d0b2d1ef87de | note | (xiv) Placed a copy of circuit diagrams in the distribution cabinet.
9d9a98b1-57ac-57f0-8cb1-ddd7ccef076b | note | Freq - Each Lot
80f3c063-7c26-50ad-ac3f-e3f6fce5fefb | note | Key - I
bb74758a-9d34-584d-9cd5-e20cfd307e90 | note | Resp - SE/SS
6af6afaa-e528-58e4-9d7d-1e52a0aebe54 | tickbox | Remarks/record - Installation Records from Subcontractor
0b2a4133-586d-5229-a6da-50fc6aba95e4 | date | Inspection Date:
| checkpoint | 7.3 - Testing and Certificate of Electrical Safety
56463a92-a662-5bc8-bed7-efc83856768b | note | Ref docs - VR Clause 731.16 (b)
82e1b884-3243-5584-87a9-724e2a35eb53 | note | Acceptance criteria - Prior to final acceptance, the Contractor has tested all distribution cabinets, circuits, switches, PE cells, luminaires, and all other electrical and electronic components for correct installation and operation.
92b4b043-5c52-5248-9205-351496536945 | note | ○ The Contractor has been responsible for arranging for the issuing of a Certificate of Electrical Safety for the electrical installation. The Superintendent will not accept the lighting installation as complete until such time as the Certificate of Electrical Safety has been issued.
0d263555-c3b1-5280-a453-d7ed977df502 | note | Freq - Each Lot
98171afc-0725-533a-bcbe-0e12bfbd356e | note | Key - R
ef30ed09-a357-588b-910d-309992d47996 | note | Resp - SE/SS
b65ab7a6-5a53-5d44-bd3e-c7278ecd386a | note | SI Key - W
b06bcb48-dd96-5a95-a39d-273350379826 | tickbox | Remarks/record - Certificate of Electrical Safety
4289c36a-b3d8-5675-8134-48ab064c7312 | date | Inspection Date:
| checkpoint | 7.4 - Commissioning
e34204a1-e0b5-5378-ac02-1b8af3fa4d18 | note | Ref docs - VR Clause 731.16 (c)
2847bbb3-dd81-518d-a19b-484c43770a39 | note | Acceptance criteria - Upon final acceptance, the Contractor has switched on the lighting installation at the distribution cabinet in automatic mode, and recorded the time, date and meter reading for contractual, warranty and power supply purposes and supplied this record to the Superintendent within 48 hours.
1d473a99-6575-5a0c-8fe0-120bcce894ba | note | Freq - Each Lot
a78e69f7-1339-5f80-a55c-66e01bb7e67f | note | Key - R
b614357c-af88-5406-9d29-def3623c67bb | note | Resp - SE/SS
ec2c7ef4-5068-5e97-8ab4-962b153cefd9 | note | SI Key - W
9d86e954-d6e1-51bc-b15c-0faafa2be962 | tickbox | Remarks/record - Installation Records from Subcontractor
865b8888-7ab0-5580-870b-8d0a099b7037 | date | Inspection Date:
| checkpoint | 7.5 - As-Built Information
0c874654-c2fb-5fe8-aaf4-447f3a7fd74d | note | Ref docs - VR Clause 731.16 (d)
d084b6a4-fbef-5c1b-9378-1273c50965ad | note | Acceptance criteria - The Contractor has supplied to the Superintendent a copy of ‘As Constructed’ plans
6d1612ff-1de3-5b24-9520-542c454af400 | note | Freq - Each Lot
6fc744ad-d446-53ef-bd4d-8409827cddc5 | note | Key - R
5da57530-4d3c-5a66-a942-26c35bf82129 | note | Resp - SE/SS
65b0d542-4dcd-5641-ba32-3a0108a0b522 | tickbox | Remarks/record - Survey Report
23101e78-1f12-5ee4-b042-4732bbfdf262 | date | Inspection Date:
| section | 8.0 Work Lot Close Out
| checkpoint | 8.1 - Test Reports
e36400ea-74c5-5fa7-bf18-ca6efc6fdaa5 | note | Ref docs - VIC Roads Specifications
c68ad0e0-3b1b-50b0-9361-dc59ab8ba60a | note | Acceptance criteria - All Test reports received and reviewed.
78f239ec-38a4-5428-a03d-368e8643c001 | note | Freq - Each Lot
74c79cb2-71e8-5dc5-8f2a-b6c76fa2815c | note | Key - R
29f6e316-e07e-5163-8f92-009f25323f7a | note | Resp - SE/SS
5a22966e-f2b0-50da-b935-1c3315a8b2bb | tickbox | Remarks/record - NATA Endorsed Test Reports
3842a632-a7bf-5d54-9b66-6f8c0cda85c4 | date | Inspection Date:
| checkpoint | 8.2 - Product Non-Conformance
09e981c6-9b49-5ab4-ab94-98fecb314239 | note | Ref docs - CQMP
e2702454-b7c4-5efc-93c0-f514b5f9120d | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
09af3c4e-b3d8-540a-83b4-51b9181f1dd6 | note | Freq - Each Lot
f03cb2ac-b12c-5c96-b349-74999c68bebe | note | Key - R
da04126a-1d6d-5311-8037-54f5397a5954 | note | Resp - SE/SS
251725a1-e041-57da-b150-0cf6307d5d5f | tickbox | Remarks/record - NCR reports
0c1fe23b-7353-563c-bac9-6bcf6b380451 | date | Inspection Date:
| checklist | 1630-P200-SYM-QAC-ITP-0056 Pavement Base Course (Crushed Rock) | itp | 1630-P200-SYM-QAC-ITP-0056 Pavement Base Course (Crushed Rock) |  |  | 3bce9b18-d7e2-4f3f-a7b4-96c0d123f565
| section | ITP Details
| checkpoint | ITP Details
0129137b-b6f3-5a21-a703-32e980121237 | note | ITP No. - 1630-P200-SYM-QAC-ITP-0056
dc178235-035f-54e2-9c89-0473f36a2eec | note | Rev No. - 00
e59afa3b-f66d-5a41-9666-08715293d303 | note | Date of Issue - 09/01/2024
a281e63b-f0e1-563a-934a-18a920839e16 | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out and TCM’s
9646783b-7ce6-5d48-ae0f-98cc511b3385 | note | Acceptance criteria - Record existing TCM’s on TCM offset sheet. Survey set out including frame, benchmark, and recovery points in place.
2e10fd8a-aaee-52a9-8c22-81091715aeee | note | Freq - Prior to start of Works
3ac1eddb-073e-5ebc-8a07-cd9dc2a0f967 | note | Key - H
36dad40b-b4f4-5861-9eec-c4848c592e9e | note | Resp - SE
| checkpoint | 1.2 - Crushed Rock Mix Registration
e1caa521-284d-5be1-a696-8a76fdcf90ab | note | Ref docs - DoT812.04, DoT304.03
c9b2302d-2937-5f4f-88cc-5931bf8cf71f | note | Acceptance criteria - HP: Crushed rock proposed is a current registered mix in accordance with VR500.02 and conforms to the specified requirements for that class.
a46026ab-c4e7-5b40-8a04-667ac76d2680 | note | ○ Mix is registered by VicRoads as ‘General’.
ce838188-1b69-53b1-8473-3fd3989d170c | note | Freq - Prior to start of works
359dbc3d-6fdf-52bb-b24d-65d84cd38250 | note | Key - H
adc5b1b6-ec98-5439-a494-56e59ab443cf | note | Resp - SE
8b5870fe-701d-5fd7-a99b-98c8e2635cb8 | note | SI Key - H
ac066f22-39ac-5a63-a81b-460781aba3bd | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7a935ea4-b55c-520a-9b84-8145c7e66710 | button | Crushed Rock Mix Registration | Yes,No
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Addition of Water
3e3993f4-3199-5021-bb72-66946652c81e | note | Ref docs - DoT304.03
dd240b8d-1a57-5ded-9788-568f457e6a70 | note | Acceptance criteria - Water added to the pavement will be clean and suitable for construction and substantially free from detrimental impurities such as oils, salts, acids, alkalis, and vegetable substances, and have no more 1000 mg/L of suspended solids.
e0a9d90a-550e-5768-bdd0-dba37f796df5 | note | Freq - Each Lot
f5b57589-2018-5237-8492-e2413ab40f23 | note | Key - I
97db09fa-7366-58b4-a910-d84f7e65767a | note | Resp - SE
| section | 2.0 Installation of Layer
| checkpoint | 2.1 - Maximum allowable lot size for a single layer of work.
0317172f-4590-5b17-a305-2bca046330b1 | note | Ref docs - DoT304.06(b) T.304.111
d9bc07da-62dd-58c3-b91f-e0305a5aead4 | note | Acceptance criteria - Each lot is a single layer of work, and its size is lesser of 4000m2 or one day’s production.
6c1c9aeb-fc2f-5fcd-ab73-d3796a0b7401 | note | Freq - Each Lot
350bb026-4f8f-5cd2-8ddc-fcba5e8edfc3 | note | Key - I
14dab2fd-cd91-57bf-aae0-1ec5f72a386b | note | Resp - SE
| checkpoint | 2.2 - Delivery Dockets
f1612860-7a1e-50c5-843c-fb31d9a53750 | note | Ref docs - DoT304.05
812751dd-5024-5da3-b551-cb198d394620 | note | Acceptance criteria - Delivery dockets of the material supplier conform to the requirements outlined in specification VR304.05: Name of supplier, docket number, project name, nature and source of material, and supplier’s stockpile identification number.
962469c8-bcfc-5b8a-af55-bf52898e9180 | note | Freq - Each Lot
88e16959-4d3b-5722-9fa7-cfce1c090e88 | note | Key - I
93ed6ace-41a3-5e49-89eb-94808add1f3f | note | Resp - SE
82f4b370-3248-5843-971b-583c1d1cfd83 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
b9a37e0b-896c-541c-8271-e5a5f7a46a1c | button | Delivery Dockets | Yes,No
| checkpoint | 2.3 - Conformity with Drawings
29a88b85-e57c-5cda-a093-72921f2466b9 | note | Ref docs - DoT304.06
073529ea-3555-56ad-9b0c-92ebcd4f027d | note | Acceptance criteria - Pavement course after compaction is smooth and uniform, and free of segregated areas and any water ponding.
ef2139f6-fb83-59f2-be75-7827addcfeda | note | Width
32916316-062b-5e68-9642-9a4b196e7c54 | note | ○ Width of each side of pavement is not less than specified offset width or more than 50mm outside specified offset width when measured at right angles from centre line or design line.
f37709fb-1ee3-58a1-a6cb-5cc3936766e2 | note | Surface Level
00a395b1-7198-5721-b415-06d77bc35767 | note | ○ Pavement constructed to the lip level of kerb and channel is flush with the lip of the channel or not more than 5mm above.
369d3a7d-7c20-58b5-849b-f71d6b7f24a9 | note | Shape
6f70ec63-f614-55c7-8667-1ca441c9864c | note | ○ No point on the layer is >8mm from a 3m straight edge or >10mm from a 6m straight edge. Placed in any direction.
cfb3a392-30e2-5c21-9ada-1f21a14bf8e6 | note | Freq - Each Lot
21cb616c-df86-5560-9638-cfc2470d7cce | note | Key - W
382f5964-a6ed-50e8-8bd2-daa8c3f74862 | note | Resp - SE
| checkpoint | 2.4 - Conformity with Drawings
d416cd1d-db60-5878-a7e1-dce391cb817a | note | Ref docs - DoT304.06
d9bb41d3-a1e6-57d9-be0c-728f0b795ff5 | note | Acceptance criteria - W: Any material compacted and then trimmed from the compacted surface to conform to the correct level or thickness as shown on the drawings shall not be re-used in the pavement construction without Superintendent approval.
418ff97a-6964-55eb-8ba6-872d4d6b0d75 | note | Freq - Each Lot
34fb1872-c5bb-552c-88ea-729965bdbbad | note | Key - R
160154ca-0344-5d88-8ff2-d39cde3056db | note | Resp - SE
4f6e29de-f6e3-57ac-9f33-3f4865d7ecaa | note | SI Key - W
| checkpoint | 2.5 - Construction - Jointing
087d0aea-6851-5dc7-87e0-62808f6020be | note | Ref docs - DoT304.07
95344195-9824-5045-ae74-1ff7953089b1 | note | Acceptance criteria - Material has been spread to minimise joints.
8bfc3855-9143-5466-9fdf-89a7acfa70dd | note | ○ Transverse joints are offset from one layer to the next by not less than 2m.
a73c9fa5-c236-559b-b645-f2002a3db6f2 | note | ○ Longitudinal joints are offset from one layer to the next by not less than 150mm and located within 300mm of planned position of traffic lines or within 300mm of centre of traffic lane.
2ce727ba-3c30-51fa-aedb-2cea111c755b | note | ○ Exposed lot and edge each lot of any part of jointing is kept moist until spreading and compaction is complete over entire layer.
6ba718c5-e678-55ad-8673-9f997e7c173c | note | Freq - Each Lot
af7fae2d-43f8-55f6-a57c-86999c865237 | note | Key - I
01c364d8-f4f0-57b8-b7de-f26814674bcc | note | Resp - SE
| checkpoint | 2.6 - Protection of compacted layer
81fd438b-8934-5817-bca5-34d80805dbf8 | note | Ref docs - DoT304.09
16d1e084-e561-5c6e-a32f-209123326809 | note | Acceptance criteria - Surface of each compacted layer is in good order/condition & free from contamination until the subsequent pavement work is to commence.
82d7619d-9f6e-5303-8161-6204669fc204 | note | Freq - Each Lot
4a23b4a2-0eac-56a5-9fd5-98a7cf0b36d0 | note | Key - I
358f7fc7-4fbe-5d9a-8c09-e2614e1604a4 | note | Resp - SE
| section | 3.0 Testing
| checkpoint | 3.1 - Testing – Stability (Proof Roll)
24b8ebe9-32b9-5ece-8e3a-e15d77ff4f73 | note | Ref docs - DoT304.08(b), DoT173.03(ii), DoT173.03(b)
c5ab3aeb-0ad5-5fe3-8471-1b9195750a69 | note | Acceptance criteria - HP: The contractor has provided for the Superintendent to attend all test rolling.
6687a990-1b21-5953-a59d-70fe16121fe1 | note | ○ Contact pressure of test vehicle is min. 450kPa/tyre during test over an area of min. 0.035m2/tyre. The layer doesn’t show visible deformation or springing.
740dfd2d-1062-57cb-b801-f690f43e0484 | note | Freq - Each Lot
3fbd9e38-4438-5767-a970-f2ff3973b418 | note | Key - H
18b9b926-baec-551f-8613-bef0ed55fdf7 | note | Resp - SE
c816e2cb-b8c3-5c50-a242-c43e7a362378 | note | SI Key - H
4b31a0fe-404d-5617-89c0-f8b381e600d7 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bf1dacbf-7a23-52a3-a14d-7fbde41613f9 | button | Proof Roll Checklist | Yes,No
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Unstable Area Rectification
8a069681-1fc6-5dc9-97fd-675af709e0ed | note | Ref docs - DoT304.08(b), DoT173.03(b)
fcdf14de-ac9d-5e1a-8d4c-6b93d37cfb3a | note | Acceptance criteria - Unstable areas identified during the proof roll have been rectified. Prior to any successive layer, the superintendent has required further test rolling to confirm the layer is sound.
8ec88877-f0f4-506c-96c5-fa9386c2667c | note | ○ Contact pressure of test vehicle is min. 450kPa/tyre during test over an area of min. 0.035m2/tyre. Layer doesn’t show visible deformation or springing.
cdcbf7cf-e38a-5b5d-b196-6591fbefba99 | note | Freq - Each Lot
bbe06247-41eb-5519-aa9f-6f5e240e4f3f | note | Key - I
9901b2d7-df0a-58a2-a42b-a4529a5c5c40 | note | Resp - SE
42a4fee9-89be-5929-9f30-de421c344319 | note | SI Key - R
55716257-cdce-5aeb-996a-d76edf9aae10 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
6b59ded3-5518-55c8-ad56-2192468c8d82 | button | Proof Roll Checklist (Post Rectification) | Yes,No
| checkpoint | 3.3 - Testing – Compaction
e22be5cd-1823-58ec-81d3-71ef6c98849e | note | Ref docs - DoT304 T.304.081, DoT173.04(d)
c89f9878-48b5-5743-9793-e97c0f3369be | note | Acceptance criteria - Scale A
63496c1b-dd06-5ab8-a20f-77612f3f6da6 | note | ○ Characteristic Density Ratio % (six tests):
90ad79fa-ce11-5694-97a8-7e3d25ccfa3c | note | ○ Greater than 100.0% Modified Compaction.
6d886c65-259c-5487-93fd-02b616ba5df5 | note | ○ Moisture content is at least 85% of optimum until test request is completed.
11a160aa-d7f3-5053-a259-8e5aafa49b78 | note | ○ Initial testing frequency: 1 test per lot.
ccecabb1-bcea-59d9-a79e-a3688334d4ae | note | ○ Reduced Testing: Once 3 consecutive lots of like material and/or work is passing, test 1 per 2 lots. If one lot fails, resume 1 test per lot.
e1fb43e5-ec13-5d79-a018-4e76e7d0167a | note | ○ Small Lot: Lots <500m2 can be CDR 3-Lot and accepted if 3-lot mean value is at least 102.0%. Small lots can’t qualify for reduced testing.
64857458-298a-5239-b0e2-6848beb59b82 | note | Freq - Each Lot
f393ff36-1de9-5529-9d94-33a4e67d8e62 | note | Key - R
b87c539b-ae70-5b6e-90cf-830eddfc77ea | note | Resp - SE
d1592471-0ca2-5414-a6e8-18ed70e6d3b2 | note | SI Key - R
4036df7e-e85d-5a98-bf17-c35f2a8851cc | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
7ed93d56-5d20-5633-8cde-be210d16efd7 | button | NATA Test Report: Compaction | Yes,No
28be91ce-680a-56c3-b746-736a8ccb3a50 | textbox | Prev. Tested Lot No. (If reduced frequency)
| checkpoint | 3.4 - Post Compaction Grading (Nominal Size = 20mm)
20cadd04-4468-549c-88df-a08ee92a8947 | note | Ref docs - DoT304.10(a) T.304.101 T.304.111
5ce7d16f-ab0c-5d42-91eb-28cbbf3ce3dd | note | Acceptance criteria - Sieve Size ¦ % Passing by Mass
e133fef0-5b01-5c08-a5dd-258ac7ad0dcd | note | 26.5 mm – 100%
7a2bb045-b35f-58e7-9758-aef01512d9d3 | note | 19.0 mm – 95 - 100%
c7265e23-eefd-5158-bb0b-c5ee8ca2e68b | note | 13.2 mm – 78 – 92%
bf1597b7-31a5-5cb1-86ef-9c3c52a77676 | note | 9.5 mm – 63 - 83%
184be879-0918-5477-8ed1-145635bfd89a | note | 4.75 mm – 44 - 64%
7e45fe42-74b5-56ce-a003-b4a9613d6216 | note | 2.36 mm – 30 - 49%
846f3ff8-333a-5e1b-943a-168297b9a846 | note | 0.425 mm – 14 - 23%
78c69d24-fc33-5213-bfd5-0e2276a4341b | note | 0.075 mm – 6 - 12%
a147aaf3-7278-5419-9868-a2ac9de5e7e8 | note | Minimum testing frequency: 1 test per 2 lots.
520ae919-e40d-566a-82f2-df97dbe297d1 | note | Freq - Each Lot
d46c858e-d82b-5dcb-9d53-2b02a25f4928 | note | Key - R
43cbcec0-172c-51a0-8416-37fa22cb158c | note | Resp - SE
01681724-d78e-55f2-b3d6-7ce7f3481fe4 | note | SI Key - R
ccaeeab1-f38f-53cb-8a47-baf1c6ea02be | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
6dc3e3e7-d719-5b27-89e3-db0397e04e06 | button | NATA Test Report: Grading | Yes,No
| checkpoint | 3.5 - Post Compaction - Plasticity Index
9c09ccaf-77f3-5e30-a093-0e2255cdbede | note | Ref docs - DoT304.10(b) T.304.111, T.304.103
661c92cb-3b74-5f93-89d6-0212d90e62cc | note | Acceptance criteria - PI: 2 – 6 (Class 1) Minimum testing frequency: 1 test per 4 lots.
5f9a1d26-222a-5e5d-879b-34188b637a1c | note | Freq - Each Lot
f53aaedf-cc00-5ad5-a7a4-6d5d0774d2d0 | note | Key - R
f0f4ef54-17b5-5ebc-a79a-d90eb5ec8b8a | note | Resp - SE
0270fc3c-6f88-5b17-88c4-fa216539e5e9 | note | SI Key - R
2106a455-49ee-5dd3-a5a9-538f463ac84d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
9030cd72-b77c-5b0f-bd24-522c01c0435a | button | NATA Test Report: Atterberg Limits | Yes,No
| checkpoint | 3.6 - Scale A Requirements for Post Compaction Grading and PI Testing
ce93e0d1-d6c0-5e89-a117-35302e6e0e4e | note | Ref docs - DoT304.11(c)(i)
b1aa54e7-4bdb-55c2-9aa5-abb5810fffe8 | note | Acceptance criteria - The first lot of each pavement layer shall be tested for post- compaction grading and PI.
11d266d3-ce50-52f7-854f-30189cd7c8cb | note | ○ Any reworked lot is re-tested for compliance.
eb0489b8-4faf-5294-bead-bfff7b84bf10 | note | Freq - Each Lot
fb27c9d4-289d-57a4-8f91-abacd4d747cd | note | Key - H
00f7c837-6f6f-5f02-aeb4-e89d6294d4f3 | note | Resp - SE
e33e6647-cfb8-5326-ad71-80f79f91afd4 | note | SI Key - R
| section | 4.0 Completion
| checkpoint | 4.1 - Survey as built
5d4e1914-a0d2-5878-a088-a661652ad267 | note | Ref docs - DoT304.06 T. 304.061, T. 304.062
965e0793-ea2c-51c1-8bd2-a6d5a3e872f1 | note | Acceptance criteria - Surface is smooth, uniform, free of segregation, conforming to grade, thickness, and drawing section. Each measurement is taken at random locations in accordance with the VicRoads Test Method.
90a8b779-b048-5f96-8b9e-4ff287e35590 | note | ○ Scale A: 80 measurements per lot are taken.
93c6855a-f9ff-5c6e-9578-a26a221a1980 | note | ○ Mean Range: +5mm to -5mm.
8b566038-0b2c-57e5-bd67-4ca4ff21962a | note | ○ Max Stnd. Deviation: 8mm.
b4570a97-5ec8-5a1e-85ba-c07667c2389a | note | Surface out of tolerance is rectified and re-surveyed.
96f2ddf7-c80a-5e16-8e9b-e3f549346dc1 | note | Freq - Each Lot
043df9d2-f7b9-592f-bb03-a353270f84cc | note | Key - R
0797d556-e2bf-5bb0-8a30-4ff0e7e4e8a2 | note | Resp - SE
2adf9c28-dc05-512c-b9da-c807a7ddf554 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
1f2d4b11-4cf5-5b70-a62d-d7b38e955d68 | button | Survey Conformance Certificate | Yes,No
| checkpoint | 4.2 - Thickness of Pavement Layers
c8614ce8-16ca-51b2-a7e9-2a28ee9a4cd1 | note | Ref docs - DoT304.06 (c) DoT304.08(v)
1fa2da55-0bc8-5b49-8c9d-d4ce21bc222e | note | Acceptance criteria - Base course is not less than specified thickness by more than 10mm and average thickness of base over every 100m section over full carriageway width is not less than specified thickness.
bb14a30d-3481-5a76-a987-ae8d84fbf7c0 | note | ○ Combined thickness of subbase and base courses is not less than specified thickness by more than 15mm.
9945e16f-a106-5716-878b-0ad7c236db4d | note | ○ Maximum base layer thickness is 150mm.
acd94a14-0158-5431-92d3-82579970469d | note | Freq - Each Lot
8c886b65-066a-5aa3-aacf-3ed2d9e52289 | note | Key - R
688bf32a-082a-56dd-9a1b-60df8b193d63 | note | Resp - SE
ba0de752-30f9-544b-b3e2-8b28e5e21365 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
a6da9678-7c34-58e8-84f9-9e7d05dd7f3f | button | Survey Conformance Certificate | Yes,No
| section | 5.0 Work Lot Close Out
| checkpoint | 5.1 - Test Reports
57b93e11-24bb-5193-8407-941eeec25b12 | note | Ref docs - VIC Roads Specifications
9b732ba3-cd20-5127-9701-f94c3286ed88 | note | Acceptance criteria - All Test reports received and reviewed.
b3b79876-0527-5abd-8098-f9ec36e5780b | note | Freq - Each Lot
d89ba20e-a0fa-5339-8b34-7a765b258b3f | note | Key - R
d134efdd-4b50-5c3c-b88c-97800f682af2 | note | Resp - SE
6649bad2-69be-5183-9a78-9d976c5bac22 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c12d4356-8803-50b9-8f67-8be84cf31b51 | button | NATA Endorsed Tests | Yes,No
| checkpoint | 5.2 - Product Non-Conformance
e24e9c19-54ef-5ad2-aa29-1fe3f6e79842 | note | Ref docs - CQMP
a00cef3e-8578-5a2a-8ead-f85012824c28 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
e974c792-990b-5db3-a0f3-3ddec8f350cf | note | Freq - Each Lot
e1c649e7-bf65-5bba-aae5-b50be2450813 | note | Key - R
633ec81d-9a4e-501f-9e0c-1339829afb37 | note | Resp - SE
42a4d801-bda1-5bef-9bce-139037850ce8 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
2856bd3f-63a6-53f0-ab06-b54b92121626 | button | NCR reports | Yes,No
| checkpoint | 5.3 - Quality Representative to check the above criteria and records to confirm.
56067714-d88b-5e4a-8892-2f174cf593e1 | note | Ref docs - CQMP Lot Records
2eac0369-5c5e-557c-8da4-3ccc541ffc95 | note | Acceptance criteria - All above criteria met, and records identified attached.
f80e68db-fcb2-5a60-a052-1cbc87d448c3 | note | Freq - Each Lot
5b763e62-71a0-5095-936b-88376603a34e | note | Key - R
6c12c50d-c784-5f45-9c84-712269f8827f | note | Resp - SE
f0246fc3-76b8-532d-a40a-b22c5a32627d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
809dfdb8-cc7c-549b-9d34-a38abdc8a487 | button | Completed Checklist (if applicable). reports and other compliance records attached. | Yes,No
| checklist | 1630-P200-SYM-QAC-ITP-0059 Landscape Works | itp | 1630-P200-SYM-QAC-ITP-0059 Landscape Works |  |  | 43494500-259e-468d-bb32-22c8b514bbfa
| section | ITP Details
| checkpoint | ITP Details
fceb55f0-1702-562e-aaec-76ec6613c312 | note | ITP No. - 0059
1d12c879-0446-5f0b-aae7-d6b60f2e1c33 | note | Rev No. - 00
d421d1bf-dcfa-513f-888e-eb3d76ee0167 | note | Date of Issue - 1/02/2024
07780657-b661-50d5-8371-492749401617 | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Check Survey Set-out and TCM’s
325aea80-16f5-5623-8b4e-4cfc52c6a426 | note | Ref docs - 720.06
b962b106-c4a5-561d-af0c-42a20ccc5fa6 | note | Acceptance criteria - Record existing TCM’s on TCM offset sheet.
f0c8d874-0d86-5dc4-a541-da15149306bf | note | ○ Survey set out including frame, benchmark, and recovery points in place.
d4a6342b-fc7c-5cf7-9611-910133ba3428 | note | ○ The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
3756610b-d84e-547c-8a64-a286237258cb | button | Has all of the above been completed? | Yes,No,N/A
86cdea6a-f861-58aa-822f-360e540da10f | note | Freq - Prior to start of works
d6e0c957-2e69-56fe-8123-850681da467d | note | Key - H
226958f4-91ca-50c2-a7d4-3b0354f9f99c | note | Resp - SE/PE
| checkpoint | 1.2 - Submission and Records
18135d70-7f9d-55c8-838f-001d899f4aca | note | Ref docs - 720.03, 720.044, 720.045
ee3f88f1-6770-5293-af0e-01e30a03b54b | note | Acceptance criteria - The following items shall be provided before commencement of the relevant landscape work (if requested):
ff295973-6fa7-5ea8-a84c-499140242333 | note | Inspections:
6729f9d9-d0c0-5cb1-9954-fbe89492e9c1 | note | ○ plant stock for all plant species
6d0c3e00-f87f-5298-baef-119e4c8cbbba | note | Samples
14cce942-8be6-53bf-8e42-ec6f509b42fa | note | ○ mulch
4a803b6b-a5ef-51eb-bca0-e938e4b0dcf6 | note | ○ imported topsoil
83313afe-e596-5daf-966e-3d9761b6e684 | note | Records
56982778-18a1-5768-97f1-24a1eb933e91 | note | ○ evidence of origin of indigenous provenance plant material
22c243bc-20c0-5022-ae04-3eaa750b05c6 | note | ○ analysis certificates for grass seed
6f2df652-d61b-5821-bd5f-67e893fe9884 | note | ○ details of suppliers
1e7287a1-1d06-5b76-8019-38a60695d9ea | note | ○ soil tests on topsoil
43f6297d-406c-5611-8111-46ef8a33d00a | note | ○ copies of fertiliser labels
ad871e5c-301b-58f6-bd71-afd5861fc169 | note | Have any/all of the above material records been acquired/completed and signed off?
b639e620-1617-527c-994d-35c77e023581 | button | Has all of the above been completed? | Yes,No,N/A
840bccf6-b550-5a30-a3da-579b405e515e | note | Freq - Prior to start of works
e8ed8a1e-5e51-5cde-bd4c-2a662de41a92 | note | Key - R
7a8a71dd-91bb-55b9-b75a-3a483536c0b0 | note | Resp - SE/PE
9ba466f3-fe75-5a3c-841c-e804656cb479 | note | SI Key - R
| section | 2.0 Site Preparation
| checkpoint | 2.1 - Setting Out of Landscape Softworks
d9d21a1e-d60d-539a-be19-aea34f1d7fbb | note | Ref docs - 720.06
02f1afeb-8eb2-5dba-b039-ca471c7e31af | note | Acceptance criteria - Set out the location and shape of planting areas in accordance with IFC Landscape Drawings.
0cdd25eb-a86a-5049-b154-b7b5dbfd2fdb | note | ○ Plant density requirements and planting offsets comply as shown in the plant schedules.
1383afa2-ff6c-50c8-a5d3-568daad88d32 | note | ○ Individual plants shall be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
45ae3304-76cc-5836-b04e-1c18731cf09d | button | Has all of the above been completed? | Yes,No,N/A
b81b4009-4aaa-5078-a44c-bdbbb6fcd4f7 | note | Freq - Prior to start of works, Each lot
bd563ed5-aea3-540a-b825-b45732ff800b | note | Key - S
a17a1e20-2617-5a21-8b6d-004661ad5c97 | note | Resp - SE/PE
| checkpoint | 2.2 - Site Preparation
4b0ce930-f8fc-5a2a-bc9e-774a944cb5d5 | note | Ref docs - 720.07
6621ddc1-d84d-5db3-952c-a64b67a0e64f | note | Acceptance criteria - Soil preparation shall be as described in Table 720.071 (Refer to page 8 Fig #1).
bc6a5eb3-2c0d-51ee-b580-417f28ee52de | note | Freq - Prior to start of works, Each lot
cbb8f47e-d9b7-5e1c-bc8f-846680192d6d | note | Key - S
33abe834-1a3a-5975-80ed-c757b9049de3 | note | Resp - SE/PE
| checkpoint | 2.3 - Soil Additives including Gypsum, lime. (If applicable)
55353ae9-d693-5a82-83ae-0083e44aa9d9 | note | Ref docs - 720.07(a) AS 4419 5.11
3b1b01cf-e7ba-5f6e-bc97-94e483aa4926 | note | Acceptance criteria - Soil additives, including any material used to modify the chemical properties of the soil, prior the physical ripping and cultivation and in accordance with results and recommendations from site topsoil analysis tests.
3904dcaf-aadb-541b-a0c0-55a65ce1b6b0 | note | ○ Apply sufficient gypsum to ensure soils are not dispersive, incorporating gypsum during ripping to a minimum depth of 300 mm.
4191636d-c082-5811-aa6c-3c439ccd99c6 | note | ○ Adjust soil pH if soil including subsoil, to a depth of 300 mm is not in the range of 5-8.
b86129fe-208e-5bef-a215-4a98fb7d26f7 | note | ○ Where salinity requirements for existing (unmoved) site subsoil or topsoil do not meet the acceptable range in AS 4419 5.6, shall notify the Superintendent.
bfe67538-bca6-5d81-b381-21001638fe9a | button | Has all of the above been completed? | Yes,No,N/A
96464e7c-0c70-546b-a377-36fd41d0c5c3 | note | Freq - Each lot
142b327c-d498-5cc2-a395-f556e894e77f | note | Key - I
d07465fb-4ce4-585e-b7e2-b691338b5ccc | note | Resp - SE/PE
2aa2d651-05b1-51db-b86f-c4d30704762c | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
d3844f5c-10e9-5906-82a4-26131495da93 | button | Site Topsoil Analysis Tests (If applicable) | Yes,No
| checkpoint | 2.4 - Ripping
be4d810a-abeb-564e-b861-6d6127a16f50 | note | Ref docs - 720.07 (b), 720.071
c2076f5c-c537-52d3-a905-237101f3cc45 | note | Acceptance criteria - Each ripped planting area, individual tree planting and grassing area prior to mulching, planting, or grassing are is to be made available.
b172b475-fe25-52d0-9278-a7da7372849b | note | ○ Rock and rubbish brought to the surface shall be removed and disposed.
a5e71b22-3da4-5b8a-afef-8caaaeca4f0b | note | ○ Ripping shall be postponed when the soil is at or wetter than field capacity.
ff63156b-d9ea-56ae-a29d-1beb4cab3e18 | note | ○ Do not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, submit alternative methods to achieve an equivalent result to the Superintendent for review.
efc23d4c-724d-5d6e-879c-823f7ab7e2be | button | Has all of the above been completed? | Yes,No,N/A
42f4392f-47fd-5f6d-9324-32645d972a00 | note | Freq - Each lot
2e61fd3d-26a2-5b22-985f-aaa3f9d0d3e0 | note | Key - H, I
91b7982c-b2f2-59f2-bca2-e47a12094e4b | note | Resp - SE/PE
768b8398-ec88-58f5-a4ba-830c91239a91 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Topsoil Application
e857f6c0-f82a-576c-b1e9-edafafa8aa0f | note | Ref docs - 720.07 (c)
44952bc7-7b11-5a5c-9589-172357e4ffff | note | Acceptance criteria - Topsoil shall be spread on planting areas and grassed areas. Topsoil is not compacted.
2e56736b-cc27-52d5-af0d-220cba2937cf | note | ○ Weedy site topsoil shall not be spread to other locations on the site. Weedy topsoil shall be handled in accordance with weed management procedures.
1991224b-76e3-5901-9660-5f99e6d011c9 | button | Has all of the above been completed? | Yes,No,N/A
68889277-605c-58e8-8526-4fa366f695b0 | note | Freq - Each lot
52645b55-d9e3-587a-a582-bd935341421d | note | Key - S
08ebb436-5dc5-5c18-b485-1dc95330bd4f | note | Resp - SE/PE
| checkpoint | 2.6 - Cultivation
134aa199-2711-51f5-b492-6444f7c416a6 | note | Ref docs - 720.07 (d)
a0133ace-215b-5541-88dc-fda244934210 | note | Acceptance criteria - Cultivation shall be undertaken to break soil down to the tilth with 80% of the volume composed of clods less than 50 mm in diameter.
815c703c-7c74-5f59-9acc-64ea7f1e35ba | note | ○ Rotary hoes and other powered cultivators that might create a hard pan beneath the depth of cultivation shall not be used for cultivations.
4aa2cff2-5126-5be5-ad28-6264f0eb9eb4 | note | ○ Cultivations shall not occur within the extent of existing vegetation areas marked for protection or the dripline of existing woody plants. Hand cultivation shall be used within root zones of trees to be retained.
58d1fc4a-1b27-5a24-a621-d365f13cf506 | button | Has all of the above been completed? | Yes,No,N/A
0ac13f67-151a-58e9-b8f9-bba864ad498b | note | Freq - Each lot
6dbb9fd4-a098-5b15-940d-7e57df3c6996 | note | Key - S
b5ff91e1-ddeb-5d82-907b-aac54d756c52 | note | Resp - SE/PE
| checkpoint | 2.7 - Topsoil Finished Surface Levels
40aea7f1-87f2-5909-9b57-09948c15602b | note | Ref docs - 720.07 (e)
054af221-9107-5e73-a463-0b1c508d99e4 | note | Acceptance criteria - The finished level of grassed areas shall be:
0f1a4564-440a-5b4c-a2a8-ccd68db3e77e | note | ○ not higher than 125 mm below weep holes or damp-proof courses in adjacent walls
48abbf5b-8a9b-51cf-8cff-e15871e0edb8 | note | ○ level with the bottom of fence plinths
2a1eac9a-571d-515c-9277-cf5b55bd57df | note | ○ level with adjacent pavements, kerbs, pits, and other structures.
266b6256-a80a-5af8-b854-acf301563d76 | note | The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
ae211587-b715-58c4-bc9f-b12f2d3adb6a | button | Has all of the above been completed? | Yes,No,N/A
02e093c4-ba32-52e2-b7c5-d21d76861eb0 | note | Freq - Each lot
357c2f9f-796b-5cfc-9d5e-21606d5cf8fa | note | Key - H, I
7d07b5e6-5120-5937-ad34-202cbaca1a46 | note | Resp - SE/PE
| checkpoint | 2.8 - Topsoil Finished Surface Levels
a3a08e1f-594d-58e4-af39-4be91d4e6578 | note | Ref docs - 720.07 (e)
66914962-6be9-5118-ba6d-418a6b7abb51 | note | Acceptance criteria - After cultivation and trimming, topsoil for stability on slopes may be lightly compressed. Vibrating plate is not used. Dry bulk density does not exceed the following:
9f42c3b3-c838-577f-915f-a3b2e0c869ed | note | – – – – – – – – – – – – – –
3aeec672-4b83-50fa-8fb5-a792bd6c7789 | note | Soil Texture (AS 4419) ¦¦ Max. Dry Bulk Density of Topsoils
fd88183a-ce49-5749-b29d-0aa2c5f317b8 | note | – – – – – – – – – – – – – –
09e35f11-9c9c-5951-a25f-d6567a925876 | note | Clay Soils ¦¦ 1.3g/cm3 (1.4g/cm3 on slopes steeper than 3:1)
4e87df52-3ca4-5323-8e8f-0477690f1220 | note | Loams ¦¦ 1.5 g/cm3
c12d42c3-5deb-5972-9df9-eb5851f7bb39 | note | Sandy Soils ¦¦ 1.7g/cm3
66ba1108-b97f-5fa3-aadb-93ba8ecb8168 | note | – – – – – – – – – – – – – –
dc1346d1-06d4-5c77-b9c1-1510ae1718bf | note | Freq - Each Lot
d511a4a0-0b90-5182-9fd1-2e7a22e4ae2f | note | Key - S
0576d35f-dd34-5489-b0f2-d95c0b2656a6 | note | Resp - SE/PE
| checkpoint | 2.9 - Acceptance of Topsoil Placement
2d80fecc-8a2e-56f0-83bf-a5d21bf0081a | note | Ref docs - 720.07 (e)
67b82669-777b-5c50-95ec-2df338f83dd6 | note | Acceptance criteria - Each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area shall be made available for review by the Superintended prior to mulching, planting or grassing.
84b59a32-fa3f-5bb5-b7d5-a805e507defa | note | ○ In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
ca8ec62c-2bc8-5042-a66e-55f93eed31e4 | button | Has all of the above been completed? | Yes,No,N/A
2cc845cb-7cdf-5e78-8f0c-95e5ce5388c9 | note | Freq - Each lot
87210c4b-257c-5a0f-95a4-3138f663821c | note | Key - H, I
6f1ef6e1-166e-53cd-966d-eecce0fa1ac6 | note | Resp - SE/PE
5d149b1b-3750-5136-bec7-9f82be676c9e | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.10 - Removal of Unwanted Matter
a034fb38-044d-5a77-aae4-13dc1370694a | note | Ref docs - 720.07 (f) Table 720.073
75f8b8a0-d0b0-5a84-b6d9-e5df8534570e | note | Acceptance criteria - All unwanted mater shall be removed from landscape areas.
df9abcb2-c56c-5419-b045-6851ce668fed | note | Mown Grass Areas:
41605760-55cc-5065-8f9e-c63ce75735f3 | note | ○ Any weeds, plastic, metal, glass, or material toxic to plants.
1a20b9dd-fde4-502b-a896-285cc4fd4ee6 | note | ○ Surface stone, rock, building rubble greater than 25 mm in diameter
5b457283-451a-5b0a-a0e3-831de19848a7 | note | ○ Clay lumps, sticks and exposed tree roots greater than 50 mm diameter
1d9919f7-584c-5e7e-b736-0325b1ca26fa | note | Planting Areas:
6824ca11-0fc9-5bc0-bc13-dfc698f5f64e | note | ○ Any weeds, plastic, metal, glass, or material toxic to plants
37c9abf7-2c66-50ca-9403-1f88787efa3e | note | ○ Any visible surface stone, rock building rubble greater than 75 mm in diameter
82a7fc43-6758-5895-97b8-8092a2c1f6ad | note | ○ Clay lumps, sticks, and expose tree roots greater than 100 mm diameter.
73693bd6-b0aa-56d2-9f6c-f07bbb4d7167 | button | Has all of the above been completed? | Yes,No,N/A
fbafdc5c-17ab-592f-9cc4-54f7e9fc1453 | note | Freq - Each lot
143eb20d-3aa5-5409-93e1-eb88648e014e | note | Key - S
e115d578-f949-563f-8d50-86e3adabfdb8 | note | Resp - SE/PE
| checkpoint | 2.11 - Existing Planting Areas
777d0859-7d0d-5727-a337-53401152f3fb | note | Ref docs - 720.07 (g)
1ed5fd7a-f15b-5bff-9afb-e683930a4935 | note | Acceptance criteria - Obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
4cb4bd15-f16b-5ba8-b833-0f7cdbc13b6b | button | Has all of the above been completed? | Yes,No,N/A
71e137f9-1b86-53cf-af62-edda49a200ff | note | Freq - Each lot
2301388f-ac05-5d91-945e-ea6a63863005 | note | Key - H, I
ce6955dc-e05e-5437-aecd-a4df2406d499 | note | Resp - SE/PE
4c82cdf6-46a9-5e40-b6fd-1728292630ba | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 3.0 Mulching
| checkpoint | 3.1 - Wood Mulch (Shredded or Chipped)
4811a634-9020-5caf-bef9-58a1c6daa82a | note | Ref docs - 720.08 (a)
961a3ed4-9723-5e0a-a9be-007cf2507e68 | note | Acceptance criteria - Install wood mulch to all Planting Areas unless otherwise specified. Mulch shall extend at least 1 m beyond plant centres at the outer edges of all Planting Areas.
a2f89359-b440-5cb8-8781-bea15afe7741 | note | ○ Install 2 m diameter mulch rings around all Individual Tree Plantings.
0dedecf6-888c-559d-b7ee-352b76ee897b | note | ○ Mulch Depth in all situations shall be a minimum 75 mm and maximum 125 mm.
64d40f38-53b8-5cbd-873c-65c55c3c8900 | note | Freq - Each lot
02d57f84-9cde-5820-a3fd-f977a28f6a8d | note | Key - S
1c34b483-48a9-5af6-9c3c-52fc4b2c67b9 | note | Resp - SE/PE
| checkpoint | 3.2 - Weed Control Mat and Erosion Control Mat
c877ea6d-8ece-5a5e-8b08-8efdf110f29a | note | Ref docs - 720.08 (b)
2bca10a8-f964-5cec-9c0d-58209e4363ab | note | Acceptance criteria - Install weed control mat for planting areas steeper than 2:1 and in planting areas prone to flooding or within 2 m of waterways, swales, wetlands, and sedimentation ponds or elsewhere as specified.
080a86cc-f092-5fac-845c-1f89f39c97e5 | note | ○ Weed control and erosion mat shall be laid and anchored in accordance with the manufacturer’s instruction.
683398da-a07d-51f7-b56a-747778ab90f5 | button | Has all of the above been completed? | Yes,No,N/A
9f8f8e7f-6b83-53b2-9bda-3421fb3cb23a | note | Freq - Each lot
72c136f0-538e-56d6-9e01-871a610275d1 | note | Key - S
279900ec-74a8-5c95-a24b-3344ae47109c | note | Resp - SE/PE
| section | 4.0 Planting
| checkpoint | 4.1 - Planting
cfddfe5f-062b-5772-b9b3-b097f23d9523 | note | Ref docs - 720.09 (a)
7886caf8-831f-5f60-be32-4de0befeb735 | note | Acceptance criteria - Carry out planting to ensure healthy, vigorous growth of plants.
c97d7fc8-4731-5f2a-9aee-bc1e087bc5ac | note | ○ Holes in heavy soils or on batters shall be prepared and to ensure adequate drainage.
bd68d097-e713-56c1-8e9d-5aaf280e6a07 | note | ○ Holes shall not be left smooth sided in basalt or plastic soils. Drill or auger hole diggers only be used where soil has been cultivated.
a8433885-5169-5bf3-9747-c00de33054cc | note | ○ Planting holes shall be backfilled with friable topsoil free of debris, rocks, and clods greater than 50mm in diameter.
ec0ed5d6-7057-552d-bec5-a43f777d544e | note | ○ In the event the specified plant is unlikely to be suited to the as constructed growing conditions, the Superintendent shall be notified.
38867ce7-9148-5538-997c-009cf8ed823e | button | Has all of the above been completed? | Yes,No,N/A
8796e34a-45fb-5a17-a80d-2c0b4cc6a009 | note | Freq - Each lot
79c4b16f-b568-534d-8cfb-d41d7fab3f64 | note | Key - S
8fd6a679-d5f1-5e5e-a63e-ea3d8d3bac18 | note | Resp - SE/PE
| checkpoint | 4.2 - Fertilising
7e7b90e8-7aa6-5456-96ff-f0326bf3785c | note | Ref docs - 720.09 (b)
975b5e33-7985-5686-b9f0-b5de9da78881 | note | Acceptance criteria - Fertilise advance trees and where specified and/or identified by the soil analysis, other planting areas with fertiliser in accordance with the manufacturer’s recommendations.
8dce2025-c323-5cb7-bdb2-89fcf532bb47 | button | Has all of the above been completed? | Yes,No,N/A
9b3329be-2e57-5139-915b-eedbaade9793 | note | Freq - Each lot
a0097668-8d5f-586e-abc4-4ac0d06755b9 | note | Key - S
94eabe94-5490-58f3-bc81-22c863fc3ab8 | note | Resp - SE/PE
| checkpoint | 4.3 - Initial Watering
412cde36-46b6-5a8a-a4c9-716c90ed7d3f | note | Ref docs - 720.09 (c)
42b634bc-07cc-5abf-a3b5-4f354668c3d7 | note | Acceptance criteria - Saturate each plant within 8 hours after planting. Cells and tubes shall be irrigated with a minimum 3L of water per plant.
0da2a0a3-d554-5e14-bea8-7eaa989bcd80 | note | ○ Under no circumstance shall any plant be planted into a dry planting hole (soil moisture at wilting prior or drier). If the soil is dry, the planting hole shall be saturated with water prior to planting.
86c9e868-97ce-5507-96a7-436a66ddc21b | button | Has all of the above been completed? | Yes,No,N/A
d2a8aec2-96cf-5a6d-82c0-e060355079da | note | Freq - Each lot
3a1e57e8-ae4a-53e8-a69b-7250a4ffe7a0 | note | Key - S
64e831b3-8e2b-564e-9780-e871a8c0123e | note | Resp - SE/PE
| section | 5.0 Grassing
| checkpoint | 5.1 - Seeded Grassing
5fea3d2a-f32d-5eaa-81ec-2c72a0659b41 | note | Ref docs - 720.10 (a)
9731326d-566a-5a5d-af72-41d9cac6e1d5 | note | Acceptance criteria - All areas indicated to be grassed on the IFC drawings.
6b0e984f-9f21-5fd5-ae11-5ad5ac3232be | note | ○ Seeding mix: 25% perennial rye, 35% annual rye, 15% cocksfoot, and 25% clover at 200kg/ha.
dd7bfb14-bca6-5de4-b5f8-bca128bba9b4 | note | ○ All areas disturbed will not be a planting area or managed as remnant indigenous vegetation.
da138cbf-2756-5290-a4ac-7998878c03e4 | note | ○ Grass seed shall be sown at minimum 100 kg/HA (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover.
2b2c7f1d-d8ca-56d7-921a-9b5a6a7c062f | note | ○ Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
f2eeba07-1476-550b-b2f6-69f0be67da8d | button | Has all of the above been completed? | Yes,No,N/A
7c2fbe7b-24fa-578d-a0da-41deab331916 | note | Freq - Each lot
78bf632a-4ae9-5fd8-bd6e-e500b16af748 | note | Key - S
4dbbd86b-2a13-5d61-92ff-e4f547a4626a | note | Resp - SE/PE
| checkpoint | 5.2 - Hydromulch & Seed Layer
cbb5042b-3079-5856-b5e8-a3e1070fd1d6 | note | Ref docs - IFC Landscaping and Urban Design
28e1fce4-4410-55e9-9f8b-768aba8ec52b | note | Acceptance criteria - Hydromulch Treatment:
afce8a51-a41e-5c5e-81ab-321a2a8207e4 | note | ○ min. 100mm cross-ripped subgrade
ee10a7c4-e891-5937-894b-5ae2c59037e7 | note | ○ min. 75mm ameliorated site top soil, over
83dc0297-e805-512c-a386-00a7ba0a4952 | note | ○ hydro-mulch & seed layer, over
5e472a16-08a6-53a3-9e17-3ddd2d078234 | note | Note: for hydromulch planting within swales refer to detail 01 / DRG 3001
853ce7c1-f3c9-5262-8131-f873167e2bd5 | button | Has all of the above been completed? | Yes,No,N/A
aa66a26f-bf52-5722-b99a-f50e419fa089 | note | Freq - Each lot
faff7703-a15d-5c21-a593-a46f22480af7 | note | Key - I
a79431b1-fa7b-5627-899f-1ecaece249d9 | note | Resp - SE/PE
| checkpoint | 5.3 - Fertilising
43137d34-135a-5318-a102-471e20c6cc43 | note | Ref docs - 720.10 (b)
e6c8dbbd-fc85-5cf5-a225-8d2277b119fd | note | Acceptance criteria - Fertiliser shall be placed evenly over the prepared surface in accordance with the manufacturer’s recommendations.
4ba57465-c2c4-5ab4-8094-6e125fd80a70 | note | Freq - Each lot
5a49e49d-0b03-507a-a4de-c17f6f15c8a0 | note | Key - S
da0fdbf3-2e2c-5dbe-a879-a2b3f8da4acb | note | Resp - SE/PE
| checkpoint | 5.4 - First Mow
c57e0762-8119-5e55-9130-874cbd2d2dce | note | Ref docs - 720.10 (c)
2bada41d-a604-5173-9c5d-db41e14a7930 | note | Acceptance criteria - First cut when at least 50% of the grassing area to be cut has grown to a minimum 75 mm and maximum 150 mm height. Mow to a minimum height of 75 mm. Less than 1/3 the height of the grass shall be removed in the first cut.
6a1c11f5-7cc9-542e-adbd-98608857e5c5 | button | Has all of the above been completed? | Yes,No,N/A
c86d04e1-614b-5877-9b33-bb6a428bb38e | note | Freq - Each lot
af74a5af-e970-5e8f-9ed9-ca637d4a2972 | note | Key - S
0555d4e0-cfd9-5995-b62c-654557e64660 | note | Resp - SE/PE
| section | 6.0 Completion
| checkpoint | 6.1 - As Built Survey
d7b6009b-6c83-59a8-9d33-6c02b2d15738 | note | Ref docs - VR Clause 720
6684de5c-a804-523b-8271-74808211e6d0 | note | Acceptance criteria - Finished level of grassed areas shall be no higher than 125 mm below weep-holes or damp-proof courses in adjacent walls and level with bottoms of fence plinths, kerbs, pavements and pits. Mulch shall extend at least 1m beyond plant centres at the outer edges of all
c4502c92-0e73-5bdf-a316-f065064c0174 | note | ○ Planting Areas with 2m diameter mulch rings around all Individual Tree Plantings.
c32da28b-66aa-5b0c-ae66-0ea05049ae21 | note | ○ Mulch Depth in all situations shall be a minimum 75 mm and maximum 125 mm.
41a7f5df-8116-587f-9534-67d8fee9e950 | button | Has all of the above been completed? | Yes,No,N/A
370be2f9-a35e-5116-b214-ab30b43d93d7 | note | Freq - Each lot
0e97e9ea-f119-5d60-95f7-6bc30127cb05 | note | Key - S
307737a8-194f-5ec6-95ec-7eb68baa9b29 | note | Resp - SE/PE, SV
f14da36e-d93a-508b-a1c9-712744f22d06 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
680ab0bd-33fb-5dec-b060-7fdab0abdbc1 | button | Survey conformance report | Yes,No
| section | 7.0 Work Lot Closeout
| checkpoint | 7.1 - Test Reports
e48346ca-4ea2-5dd1-b4f9-98006a88e481 | note | Ref docs - VIC Roads Specifications
b1d58b6c-e79a-5f39-9594-d34b842a7068 | note | Acceptance criteria -
d7ec03af-eea1-5a48-acb0-291c5ff62a96 | button | All Test reports received and Reviewed. | Yes,No
552d0c23-f4b0-5339-a0bb-26cfd0f8c5b0 | note | Freq - Each lot
ee8ae287-6430-5dab-ab41-40e6ab47aa84 | note | Key - R
62780a0a-bc3d-5149-ae5b-3e675d6789ef | note | Resp - SE/PE
2563fdc0-79fc-5ed0-a287-e1e3fd7ae556 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
eda7d386-d74a-5772-957f-bdccce41c8b9 | button | NATA Endorsed Test Reports | Yes,No
| checkpoint | 7.2 - Product Non-Conformance
8a3e22a7-24d8-58da-ae1b-6787c930831d | note | Ref docs - CQMP
d6a26ce6-e24b-5487-ae15-fd6db2ece3ef | note | Acceptance criteria -
2992e098-7a17-5f44-8c1e-1dc84f394506 | button | All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No
f56f1346-39fd-592e-83f0-5aa9123dad2d | note | Freq - Each lot
d90f69a8-4bf8-53a2-9c2e-22df3b256e8b | note | Key - R
e511a6d4-e1d7-57ac-8c0d-ccd148e43891 | note | Resp - SE/PE
a2e6a1a6-f644-5307-884c-2c151d05e6c5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
1c78103c-3cfb-5aa0-bbc3-5eca5b721a46 | textbox | NCR No:
8b4615a2-818f-51c5-be2c-5bb912e3b17c | button | NCR reports | Yes,No
| checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
32d03dea-ce46-508a-9912-29ec219b5962 | note | Ref docs - CQMP Lot Records
5e3109b8-5a3d-5478-b247-95b76f112829 | note | Acceptance criteria -
eae6fdb5-bbd8-5941-b71f-e2a18ef727b4 | button | All above criteria met, and records identified attached. | Yes,No
12444277-3d0f-59da-b2a5-c7fbbe803848 | note | Freq - Each lot
9a69483f-c3a7-5492-8e35-c824a66a5691 | note | Key - R
adb114b1-85ba-5788-971a-43a61bdd664b | note | Resp - SE/PE
285ad8d1-54e7-5e7f-9d9c-90d70184ef49 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.
| checklist | 1630-P200-SYM-QAC-ITP-0067 Painting & Anti Carbonation Coating | itp | 1630-P200-SYM-QAC-ITP-0067 Painting & Anti Carbonation Coating |  |  | b870f628-4212-40fc-93d0-1d8ffbfdc9eb
| section | ITP Details
| checkpoint | ITP Details
c8ec0d67-35f9-56e0-87a2-6cba022e496c | note | ITP No. - 0067
3c09a0b0-0c6c-5256-a54b-d846ad85996e | note | Rev No. - 00
da7a4439-fd1e-5652-be15-d567b2b793d1 | note | Date of Issue - 5/08/2024
3a7c7448-ac63-5c30-8333-0fccd16a7795 | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Safety
9570520f-b04e-5339-b4c1-c316bb54f57d | note | Ensure that the following items have been actioned:
f78b23f0-2c0a-5a36-a05d-21827c38b470 | note | – SWMS if applicable
ad108777-c9b5-5037-8bec-a1c7af0383e3 | note | – Plant Pre-start Inspection
18a454b2-dddb-52ed-888f-fcee597d9a10 | note | – Service locations identified
43f9d4f4-b65b-512c-9e82-58407b8ba9d0 | note | – Traffic Management Plans (if required)
81b9b475-8f79-5773-a922-81dd064c4100 | note | – All staff inducted
f6dee479-3996-5ea1-84cc-71edacfa443d | note | Ref docs - SMP
dc0ba3c9-3edd-5116-9f1a-b326a40de992 | note | Acceptance criteria - SWMS/WMS submitted reviewed and accepted if required.
bdcd1886-b097-54af-a2dd-40eb65c3dc5e | note | ○ Plant inspections completed and entered.
f38a1f78-468d-542f-a59d-95d799425b72 | note | ○ TSA training completed. Pre-work briefings completed.
5513d292-f79c-58be-a9af-c1b6acb39d69 | note | ○ Service Diagrams available and services located.
45a7f3ab-5722-5bc4-a060-95adc08b06cc | note | Freq - Once (Pre-Start)
5001a8f7-1823-53ae-94ec-987fa7593a14 | note | Key - H
1146b872-a525-51eb-9261-9be4418b367c | note | Resp - SE
| checkpoint | 1.2 - Relevant Permits Required
3669ccfc-3565-5a64-9b71-53d9cd3c1e30 | note | Ref docs - SMP
63a7ca99-14aa-550c-afca-0c5c74fe218d | note | Acceptance criteria -
1e774718-4e65-599f-aaec-b17f0e823b47 | tickbox | Permit to Work.
7612c616-2e18-510d-9713-3ed6f155ba10 | tickbox | WFH Permit
89ab76b1-1faf-5554-87f1-5aaace6f4438 | note | Freq - Prior to start of works
957f3ff8-783b-5db6-bbff-69b8247e2d5d | note | Key - H
6b616096-d37a-5e13-aff2-4b1a4c2085f0 | note | Resp - SE
| checkpoint | 1.3 - Define lot
a14198c4-cc63-55fc-81c5-2a7484f94619 | note | Ref docs - VR 686
ea79e3c4-c8e1-56d0-bae7-4c0f22ad99b6 | note | Acceptance criteria - Location & Application of Coating
5964ca7b-e509-5cf4-931f-cb925979c81b | note | Freq - Prior to start of works
f91f24f4-bf2d-5c5d-86bf-121622df94e2 | note | Resp - SE
94def1e7-76a3-5b81-aa96-59edf0461948 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Per Element
| checkpoint | 1.4 - Approval of process
c208fc98-f5dd-58d4-ba93-8315cfa070d2 | note | Ref docs - 686.04
2ae4e04d-d3a6-5329-a372-bb4953db299a | note | Acceptance criteria - The Contractor shall submit for review by the Superintendent not less than twenty-one (21) days prior to the commencement of the coating works, details of the concrete coating operations including information on the proposed coatings and primers, surface treatments, decorative/anti-carbonation coatings, substrate preparation, method of application, equipment, and operators, demonstrating compliance with the requirements of this specification.
4c5ab5f4-8f43-5964-9f88-d205bdef0fcf | note | Freq - Prior to start of works
5e7243b6-f086-5704-84dd-1394e7fec213 | note | Key - H
e44674d7-5ac1-5e85-903f-fd4979376f39 | note | Resp - SE
f81f5264-420d-54dd-8a39-fe55c67286f7 | note | SI Key - H
ab4e447f-af39-5175-893a-7bb2aa8fe0a4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c4634adb-47ec-5c56-8748-b6f013a9bd65 | tickbox | Material Data Sheet
b6ff8571-2ebc-575c-9fd2-2709f93d3ba8 | tickbox | Previous product test results/ Performance
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Material Approval
80feca48-57d5-5b90-8cd4-411814c0d46e | note | Ref docs - 686.04
2eb0320d-6e54-5d86-92a5-a5fa140b6123 | note | Acceptance criteria - Concrete coating works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with Clause 686.06 have been reviewed and accepted by the Superintendent.
b796a308-1460-521f-9519-47d787b2a226 | note | Freq - Prior to start of works
fd796ea5-c0f6-5f85-899c-d1855a0560d3 | note | Key - H
3e12d4a9-0244-569f-a94d-dec88a42c48c | note | Resp - SE
35a06c80-c02a-5294-b85f-f0946ddc458b | note | SI Key - H
45a769e7-4d80-5478-8307-46019815d5a6 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
497ffc8b-371f-5bb4-9313-5ef1d0f99baf | textbox | AP
| signoff | AUTHORITY HOLDPOINT
| section | 2.0 Protective and Decorative coating systems
| checkpoint | 2.1 - General requirements
cd154ab3-1d3d-5ec3-84af-35ba86d6b76a | note | Ref docs - 686.05
f556ca4e-862a-5071-9738-625e8c65b480 | note | Acceptance criteria - The protective or decorative coating system shall be water or acrylic based and solvent free./The protective or decorative coating system shall be clear or pigmented coating to a VicRoads Grey colour, or a combination of these. All coats in the system or separate coatings/treatments making up the system shall be physically and chemically compatible with each other.
a4b1131b-6c90-5b96-8a8e-d0bd6ca295e1 | note | Freq - Each lot
bd690637-3532-5a30-8226-03571b31d3cf | note | Key - S
77ad4aa7-5ec6-5f36-9113-146402ef8bb2 | note | Resp - SE
af25a835-0a60-533e-bf87-274ebed4f8d5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
e4122d48-c722-5356-be31-9f1275a25dff | tickbox | Vic roads Grey
| checkpoint | 2.2 - Guaranteed Outdoor exposure
2f2bc33c-7e6f-5336-b4c1-d8ce00c93ffe | note | Ref docs - 686.05
f741c37c-8cf5-5c9c-a2af-9de46e01e6e9 | note | Acceptance criteria - The Contractor shall supply the Superintendent with a certificate from the manufacturer in the form of a guarantee confirming that the coating system and materials comply with the requirements of this section, including a guaranteed outdoor exposure life of not less than ten (10) years prior to the need for re-coating.
a3983f5a-1ec4-5d67-b422-0dde6d3de43b | note | Freq - Each lot
1f4950f6-0586-530b-b169-e9b29b4f1406 | note | Key - H
73c3f57c-0232-513f-a592-df79e07915f7 | note | Resp - SE
609d2211-7489-5934-96d1-bc9d5ae97edb | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
762ba0bb-b78e-5930-bac9-023e374db6d0 | tickbox | COC 10 Years Warranty
| checkpoint | 2.3 - Coating system Requirements
c5a92af9-8744-5c23-b344-19c7e3d977bf | note | Ref docs - 686.05(a)
de399219-e48c-558a-94da-1ad8bd5f91b9 | note | Acceptance criteria - The coating system shall be capable of withstanding cleaning with hot water, in the range of 40°C to 50°C, detergent and scrubbing action without loss of adhesion, softening, or changing in colour or gloss.
e150b5f2-7b45-5398-9403-78e6a6289457 | note | ○ Coating systems applied to highly porous and/or relatively soft concrete substrates shall include a high-quality pore-filling primer coat or sealer to be applied prior to the application of at least two coats of the protective or decorative part of the overall coating system. The primer and/or the coating system as a whole shall also offer surface binding and toughening effect.
6e493cb9-3df9-53a8-b17b-4e3719a2b93c | note | ○ The Contractor shall provide evidence as to the compatibility of the proposed coating system to the nominated substrate. Such evidence shall include but not be limited to test certificates from a AS ISO/IEC 17025 accredited testing laboratory.
7f35cbc2-3c01-5752-b625-3e976ef143f5 | note | ○ Where a primer, undercoat or sealer is required as an integral part of the coating the primer, undercoat or sealer shall be a different colour to that of the final nominated colour and shall be in accordance with AS 2700.
bfca4e42-afb1-52f9-8751-a3298486e5bc | note | Freq - Each lot
83fdfeae-507a-5024-964b-919c104a1cc9 | note | Key - S
f41b40d1-e754-5366-903c-8f1b5a13ae3e | note | Resp - SE
dbf4ef28-caed-556d-8933-174f853ba137 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
c7badd20-adb1-5d96-8a55-c0061e759c56 | tickbox | Test certificates.
785c3efc-80d5-50fa-8ec8-87adaf177709 | tickbox | MDS
| checkpoint | 2.4 - Applied Coating system requirements.
293e031b-28bb-55a2-bb9b-df9e7484fd97 | note | Ref docs - 686.05
cf31e774-bb4c-5d11-99ec-7def3fc5e4cc | note | ○ AS 1580.408.5
c25318cb-d5ee-5792-9011-882cba17f08e | note | ○ ASTM D 4262-83:2005.
6cd3d7d5-1455-53fe-b09b-75e4c413891d | note | Acceptance criteria - The applied coating system shall also satisfy the following requirements:
94084d9c-d81f-5523-a345-6f34e18a30a1 | note | (i) bond strength greater than 0.75 MPa when tested fourteen (14) days after application in accordance with AS 1580.408.5;
29ffae22-7913-5464-acbe-aa7783b51ade | note | (ii) ability to bridge cracks up to 0.3 mm wide;
233bced5-1aac-5a99-8871-8110992f70d4 | note | (iii) ability to be recoated within 24 hours;
76012d08-7015-5678-a3a7-31b2849e17fb | note | (iv) have minimum pot life of 1 hour;
a08c70a1-e3e1-50a9-95ae-b3a06dd24e16 | note | (v) not to sag or run when applied correctly to vertical surfaces;
46f10854-bdab-542a-b4de-a9a7430844d2 | note | (vi) compatibility to an alkaline surface in accordance with ASTM D 4262-83:2005.
ee53f9da-34ad-5001-ba4f-35fcf5b90f51 | note | Freq - Each lot
f6a3e3ce-79ae-5feb-94bf-50899494aaa9 | note | Key - S
ebe5da2f-fbf5-5752-a272-b32f0e889da7 | note | Resp - SE
906f8456-6069-5578-9b81-942fa309dae5 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
4663c432-0129-53b8-9faa-f3c6b84f27de | tickbox | Test Certificates
| checkpoint | 2.5 - Performance Requirements for Decorative/Anti-Carbonation Coatings
5c34939b-3bde-557e-94bd-f1993d025500 | note | Ref docs - 686.05 AS/NZS 2311
83f7cf8f-5e12-525b-a37f-f7d3535dcd69 | note | ○ Clause 686.05(a)
15e6f024-d7cb-5a15-8fef-24d6a6a77510 | note | ○ Table 686.051
4640a0d3-c278-5930-8ae1-0837c233c2f6 | note | ○ AS/NZS 4548.5 and AS 1580.108.2
9525193e-46f7-528a-8c86-0c0f8ca39e2d | note | Acceptance criteria - Where required, concrete surfaces shall be painted with at least two coats of an approved decorative/anti-carbonation coating system (VicRoads Grey or approved alternative colour) in accordance with AS/NZS 2311 and the manufacturer’s specification to achieve a uniform colour and texture. The primer which forms an integral part of the coating system shall be applied onto the concrete substrate prior to the application of subsequent coats of the approved decorative/anti-carbonation coating. If a uniform colour and texture is not achieved the
34b5865f-a00e-5db1-83b2-919fd04bbe26 | note | ○ Contractor shall take remedial measures at his own expense to produce the required surface finish.
74e49d2b-39a1-5ea4-b588-4540c16cca4c | note | ○ In addition to the general requirements of Clause 686.05(a), approved coatings shall also satisfy the minimum performance criteria shown in Table 686.051, as determined by testing in accordance with the requirements of AS/NZS 4548.5 and AS 1580.108.2.
c5990b40-464a-59f0-8847-7587961991c3 | note | Freq - Each lot
187f5b26-073d-5289-8169-08b538f6ce3f | note | Key - S
b1b42927-6c9e-596c-a616-dbfb1f7c9305 | note | Resp - SE
a187084b-d473-5bf0-8d28-2934e5e62588 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
2526e5b2-cdd4-5511-868a-c74e578d6f9d | tickbox | Test Certificates
| section | 3.0 Trial application
| checkpoint | 3.1 - General
e6e0868c-0335-5550-8760-c5746c0b7538 | note | Ref docs - 686.06, 686.07, 686.11, 686.14, and 686.15
c6f2718c-0d1b-5c80-8001-8e8a90ff344f | note | Acceptance criteria - A trial application of the coating system, including any primers and undercoats shall be conducted on a test area of the actual substrate of not less than 10 m² or a test panel made from the same substrate, fourteen (14) days prior to the commencement of coating work. The test area or test panel shall be prepared and coated by the Contractor to satisfy the requirements of Clauses 686.06, 686.07, 686.11, 686.14, and 686.15, and in accordance with the material manufacturer’s recommendations.
85955f7e-81fb-5cfe-9101-75633759098e | note | Freq - Each lot
d6e5c301-b877-5fd2-8f30-87f89d2326df | note | Key - W
17056e7c-6a3a-5177-962e-7fe68b58bdf7 | note | Resp - SE
| checkpoint | 3.1 - Review of trial
ae5f48bb-75b0-5f93-a70a-cdb88550078a | note | Ref docs - 686.13
94fbf9c6-3237-52c7-bd48-515558e2e74e | note | Acceptance criteria - The Contractor shall not proceed with the full-scale coating works until the trial coating application has been carried out and the outcomes reviewed and approved by the Superintendent.
d27aabba-3094-54f6-8334-4ab7f22a228e | note | Freq - Each lot
2f0c32f4-2bbc-5f97-b8f9-2a5428f33f4e | note | Key - H
914cebf4-af5c-5ac2-b435-c9974fce62ee | note | Resp - SE
54bf55b2-a28a-5e3f-9b95-f2b20f1b6d69 | note | SI Key - H
559766e5-459c-5dab-91da-f7428b58522b | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
6f4a574b-0ed1-5b81-a46c-64d1e56c5853 | tickbox | Record of testing Sample
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Event of trial failure
7a5926f7-707d-5756-b297-3800b09b0c85 | note | Acceptance criteria - In the event that the trial application is rejected, the Contractor shall remove and dispose of any work deemed as unacceptable by the Superintendent, submit a new proposal to rectify the deficiencies (including prequalification testing of any new materials/methods) and repeat the trial application as described above. Any delays caused through rejection shall not constitute justification for extension of time.
43e6e568-9818-5e36-83bc-e421e91ea471 | note | Freq - Only in event of failure
bde250e3-07b7-5bb8-975c-2ddb926ae206 | note | Key - W
1254b910-6c1f-5bb9-8a70-b6f6f82c10b3 | note | Resp - SE
| section | 4.0 Surface preparation
| checkpoint | 4.1 - General
8bcb4a41-ed76-5958-bed7-6acbe5cba709 | note | Ref docs - VR 686(a)
af722227-274e-56be-8caf-f1867da64dbc | note | Acceptance criteria - The surface preparation shall be in accordance with the manufacturer’s recommendations for the coating system to be applied and as specified in this section.
95e5f083-e46e-59da-9fad-a5d89ade76f9 | note | Freq - Each lot
d7e948f4-adc6-5098-82aa-af259828d678 | note | Key - S
290903e2-9afc-5e80-852d-d7da868edf5b | note | Resp - SE
| checkpoint | 4.2 - Uncoated concrete preparation
461fae81-2f6d-5fd8-9cd2-fbf11d361728 | note | Ref docs - VR 686(b) AS 1627.1
18373743-3e71-5d7f-a9f0-605f610f9cbc | note | ○ AS 1627 VR 689
8210d8da-2e3c-5b1d-bd64-d3a63c99107f | note | Acceptance criteria - Concrete surfaces shall be dry unless otherwise approved by the Superintendent, and shall be free from oil (e.g. from release oils), grease, laitance and loose particles, remnants of curing compounds and organic contaminants (i.e. moss, algae etc). The concrete surface shall be prepared by high pressure jetting with potable water, either with or without added abrasive (i.e. up to 3000 psi or 20.7 MPa), steam cleaning, wire brushing, abrasion with angle grinder, or by other means to provide a strong, hard surface. Areas of persistent contamination shall be removed from the surface by the use of appropriate solvents or detergents followed by washing with potable water in accordance with AS 1627.1. Any abrasive blast cleaning shall be carried out in accordance with AS 1627.4 and other AS 1627. Any other OH&S and Environmental regulations imposed by the local government authority and the EPA.
fe6aeb21-7fab-55b7-8db7-590d8ba1cb77 | note | Freq - Each lot
f89e9d17-e438-5d9a-a43a-0cc9beb2859d | note | Key - S
8a54af8b-3315-5cba-98c5-729e22b91e2f | note | Resp - SE
| checkpoint | 4.3 - Uncoated concrete with defects Preparation
7e5620e9-8aa9-577e-bb26-e6b0dbd17fc9 | note | Ref docs - VR 686, VR 689
260a9cee-1ca4-532b-8f63-5b83cf7f0e7e | note | Acceptance criteria - Any blow holes, areas of honeycombing, loose surface layers and weak concrete, shrinkage cracks of width less than 0.2 mm or other defects, either revealed by a grinding process or exposed by other surface preparation methods, shall be filled with a suitable fairing coat cementitious repair material in accordance with the requirements of Section 689. If the surface of the concrete is weak, more material shall be removed and repaired in accordance with the requirements of Section 689. Such repairs shall be sufficient to result in a strong, sound substrate suitable for the intended protective or decorative coating system.
dec94409-a251-5453-a280-06dd0da20068 | note | ○ Projecting fins, rough spots and sudden steps shall be removed by light abrasion with an angle grinder to provide a surface which can be easily coated.
42e20203-99dc-5b80-94a0-8353c36063c3 | note | ○ Inactive cracks of width equal to or greater than 0.20 mm shall be sealed by resin injection in accordance with Section 687. Active cracks equal to or greater than 0.20 mm shall be treated by methods approved by the Superintendent and in accordance with Section 687.
14fd474f-0c5e-5daa-8b95-0ccf556b2036 | note | Freq - Each lot
b54489bd-1883-51ab-9b92-a6b6eb8f3323 | note | Key - W
838cb5a6-9f3c-52d8-afab-ebf8b5448539 | note | Resp - SE
| section | 5.0 Method of application
| checkpoint | 5.1 - Dry concrete surfaces
12eec110-1bae-5d26-8e78-6b4f1ed1e2ef | note | Ref docs - 686.07(a)(i)
4c906ad5-6076-5d2d-9864-689297883fed | note | Acceptance criteria - All concrete surfaces to receive a coating shall be dry at the time of application. Sufficient drying time shall be allowed after wet preparation methods to satisfy the requirements of Clause 686.14.
15771a8c-c2c7-597a-a3b6-c9e44cf6b5da | note | ○ The coating shall be applied following the manufacturer’s recommended application methods, overcoating times and coverage rates, mixing requirements, current materials safety data sheets and as specified in this section. The coating may be applied by brush, spray, roller, hand/glove or other technique to achieve the desired surface finish. Coverage rates shall be checked for compliance with the manufacturer’s requirements. The surface area of the concrete structure subject to application.
a0e331cb-8b40-59ad-ac2b-3d3502a16103 | note | ○ The coating system shall be applied as soon as possible (i.e. within 24 hours unless otherwise expressed in writing by the manufacturer) after the preparation of the concrete surface. The prepared surface shall be protected against contamination if it is left uncoated for more than 24 hours.
82bb399c-33a2-5b6f-82e1-773ba629df92 | note | ○ For multiple coat applications, the manufacturer’s stated minimum and maximum overcoating times for the prevailing weather conditions shall be satisfied, and successive coats shall have slightly different colour shades to assist in achieving uniform coverage. The difference in colour shall be such that a coat when either wet or dry shall be clearly distinguishable by means of colour difference, from the preceding coat.
dda49259-3d41-5404-94f2-da6609d5176c | note | Freq - Each lot
9db0137a-dd4c-51e4-a211-6c8d20cd8588 | note | Key - S
9181cecc-44d2-57e4-8533-a1bdb21fd591 | note | Resp - SE
| checkpoint | 5.2 - Specific requirements
b0b6d5a2-8a2f-512d-84f6-9ff9e408c235 | note | Ref docs - 686.07
49089476-0fbd-59c0-a723-fd5aa5a30bf2 | note | Acceptance criteria - All multi-part coating materials shall be mixed according to the coating material manufacturer’s instructions. The components shall be mixed in the specified proportions. The specified reaction period shall be allowed from the time the components are mixed until the application begins. No coating material shall be excessively thinned and any thinners used shall be the correct type as specified by the material manufacturer. The coating material shall be strained as specified by the material manufacturer.
fed663e0-a059-5810-bf87-f431df82027e | note | ○ No coating material shall be applied after its pot life has expired.
3434b32d-c4c1-5165-9354-7cbbf5f668f7 | note | ○ Where quantities of coating material are being applied by spraying successive batches of premixed multi-part material, the equipment shall be flushed and purged with clean solvent after 2/3 of the pot life of the material has expired from either the mixing of the first batch or since the last purge and cleaning of the equipment. Coating material ingredients shall be kept properly mixed in the spray pots or container during the application of the material whether by continuous mechanical agitation or intermittent manual agitation as required.
e7a9e8f1-620d-5fb2-bbcb-e302d5fdbfff | note | ○ Where brush or roller techniques are used, the brushes or roller heads shall be used for the day only and then discarded. The equipment shall not be cleaned for re-use.
2736a3d1-940e-5c35-bd78-f1b079b287c5 | note | ○ All coating operations shall be performed in a neat and workmanlike manner by personnel with experience in the use of protective coatings and application methods.
f92159fa-258e-5835-a5e1-842d13039661 | note | ○ Each coat shall have the required colour, gloss and opacity.
7c0b4a9b-b04e-5404-b766-6561dfdeb700 | note | ○ Each coat shall have the specified DFT. This film thickness shall be applied to all edges and corners. Coats which, in the opinion of the Superintendent, show excessive film builds shall be removed.
a931f0bd-4344-536f-9a50-1c3e9ff5a101 | note | ○ Each coat shall be smooth, uniform and free from sags, runs, mud cracking, wrinkling, fat edges, blisters, pinholes, holidays, dry spray, entrapped foreign bodies and heavy brush marks.
c51e81ee-3a46-5139-abe8-60fcbf0d08f3 | note | Freq - Each lot
c4689922-09bf-5f46-a0fb-f8a7fc61ba62 | note | Key - S
3d47690f-c0ba-550b-ad84-76b7c386f21d | note | Resp - SE
| checkpoint | 5.3 - Damp concrete surfaces
96335bea-accf-574a-be2e-8d46e5545493 | note | Ref docs - 686.07(b)
b40c3866-01fa-562c-9285-023e19f0582d | note | Acceptance criteria - Coatings for application on damp concrete substrates shall be specifically formulated for tolerance to moisture during application, curing and subsequent service.
d713aeec-460a-5868-9337-728ddf305464 | note | ○ All concrete surfaces to receive coating shall be surface-dry at the time of application. Where this requirement is not satisfied, temporary protection shall be provided to encase the concrete and coating applicator and prevent moisture penetration, ensuring adequate ventilation is provided.
374f5342-695c-54b7-a6bc-188bceb1622f | note | ○ Deposits of salt crystals which collect on coated surfaces shall be washed off with potable water and the surface allowed to dry, prior to further coating application.
b40d23cc-b64e-527f-8e5d-3ec3991702f6 | note | ○ With the exception of the surface moisture condition of concrete the coating shall be applied in accordance with Clause 686.07(a).
ead034be-2262-5d96-94c0-775ed93fdb22 | note | Freq - Each lot
3fed2114-1d43-5afa-aa79-4fa5eb8be5d7 | note | Key - S
103a7860-af49-5c96-8053-5641aad8ab57 | note | Resp - SE
| section | 6.0 Spray equipment
| checkpoint | 6.1 - General requirements
a84a8525-444f-586d-8f45-ed5439aca159 | note | Ref docs - 686.08
5d923211-57e7-5dc7-b502-ee31ce42460c | note | Acceptance criteria - The spray equipment shall be suitable for the work intended. It shall be capable of properly atomising the coating material to be applied and shall be equipped with accurate pressure regulators and gauges. The spray gun, nozzles and needles shall conform to the coating material manufacturer’s recommendations for the coating to be applied. The spray equipment shall be kept in such condition to permit efficient and effective coating material application. An efficient airline filter shall be fitted as close as possible to the pressure pot to eliminate line condensate and oil in the air supply to the spray gun.
74640642-a7e9-5b25-84a8-1ed451285b27 | note | Freq - Each lot
aa90dcd7-f468-501f-b177-75adb173b833 | note | Key - W
88ce1fbe-f4d2-5ac8-a5b8-2c5774e3e0e9 | note | Resp - SE
9096e8c3-85ae-53c4-be2a-106b0c44f360 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
035c423b-fe43-5492-b813-00d6ee3e0ff8 | tickbox | Photos
| section | 7.0 Drying and curing
| checkpoint | 7.1 - General requirements
e6a858e1-e9a1-5fc0-81fd-757e123af764 | note | Ref docs - 686.08
f820774c-3b2e-5e45-9170-dedbfc9c6751 | note | Acceptance criteria - The Contractor shall adhere to the manufacturer’s instructions regarding drying and curing requirements, and overcoating time intervals, for the prevailing weather conditions.
16fbab38-8a9c-5dc3-bd55-cf9feb25d140 | note | Freq - Each lot
ce18e5c3-d534-550f-8f54-6341da264abe | note | Key - WP
ba219eda-7687-5125-aeab-9830d73ceb20 | note | Resp - SE
| section | 8.0 Clean up and protection of works and property
| checkpoint | 8.1 - Preparations protocols
6a2406d5-b632-5685-a52c-87832cfe0840 | note | Ref docs - Clauses 686.11(b) and 686.11(c)
83d443b1-0ba5-5304-ba70-e5bc081a001a | note | ○ Clause 686.11
e7e6ac2c-7854-5fe4-9881-7f58e8a0851f | note | Acceptance criteria - The Contractor shall protect already painted or galvanized surfaces, services, bearings, joints, painted signs and nameplates during abrasive blasting operations or any other surface preparation process and during coating application processes.
c53365ea-9ae5-5345-aa82-0d7d0799b362 | note | ○ The Contractor shall remove all coating drips and droppings, smudges and over spray from all surfaces, including surfaces not being treated. The Contractor shall remove from the site all spent abrasive and all other rubbish accumulated during the work. The Contractor shall dispose of such wastes to the satisfaction of the Superintendent and by a means which conforms to Clauses 686.11(b) and 686.11(c).
fc532a31-65aa-5aee-b8b9-aec10bd0d29b | note | ○ The Contractor shall ensure that the coated works are protected from adverse conditions, dust and debris during the curing period of the coating system in accordance with the requirements of Clause 686.11.
f80c85f0-4799-545b-847b-13c0663fa65a | note | Freq - Each lot
b24d595e-298b-5398-bef2-0f996c152a4e | note | Key - W
272e129b-71cf-5ce9-a88f-4f06becf929c | note | Resp - SE
| checkpoint | 8.2 - Protection of property
764ebde3-a4a9-5023-88e6-083557568776 | note | Ref docs - 686.10
0e0717fa-3656-5005-b77a-595f6f359549 | note | Acceptance criteria - No spray painting shall be carried out within ten (10) metres of buildings, footpaths, roadways, pedestrians or vehicles without protective measures or methods being used which shall be submitted to the Superintendent for approval, a minimum of two working days in advance of the proposed works.
52933ede-07ea-54f5-a113-5e2757a986a3 | note | Freq - Each lot
3aab3579-53e9-5f20-867f-b07449ec5ec6 | note | Key - H
c10eb3b7-62ca-53ab-8521-3577210fd93b | note | Resp - SE
69f2ad64-dcb3-5600-9ec8-427de16e43c5 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| section | 9.0 Environmental conditions
| checkpoint | 9.1 - General
029b1922-1491-5da8-91f5-af49ac3b409d | note | Ref docs - 686.11 (a)
64a7da29-6d7f-5477-9545-af19c3738b7c | note | Acceptance criteria - Coating systems shall not be applied under any of the following conditions:
b2cba2c8-a140-5ad6-b4bc-a935e317e827 | note | (i) windy conditions where over spray and/or spatter may be generated;
2600c59f-1d98-54d4-93ba-b76f5d994997 | note | (ii) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied coating;
1cc720ab-a628-53ad-86d5-cb826506169d | note | (iii) when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer;
4f18070e-279c-555b-9deb-7a062beccbb3 | note | (iv) when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period;
eca54785-c366-509e-9355-d69a4382ee1c | note | (v) when rain spatter or run-off, including leakage through deck joints, contaminating the surface and adversely affecting the adhesion to the substrate, may occur;
b16312ef-ebb8-5ff2-9d1f-12baaf68ff09 | note | (vi) when the substrate surface is wet or damp, unless the coating is specifically required to be applied on a damp concrete surface in accordance with the requirements of Clause 686.07(b);
16ebc6b6-2100-5c65-89e2-bcd389df20f7 | note | (vii) the surface temperature of the substrate is less than 3°C above the dew point calculated in accordance with AS/NZS 2312 (Fig. 8.1) or exceeds 40°C.
e83ce192-e347-5c91-b770-d36f041083ee | note | Freq - Each lot
a806a102-1c1f-566a-976f-13431efd165b | note | Key - S
6095181b-d81e-5502-966c-2d158b0c40ad | note | Resp - SE
| checkpoint | 9.2 - Measurement of conditions
7f60be93-fa8a-596d-b4b7-18a67af1874d | note | Ref docs - 686.11 (a)
43462d42-5d8b-50c0-8949-2ba1929c87a2 | note | Acceptance criteria - The environmental conditions shall be measured, recorded and assessed against the requirements above once every four hours of each shift. A calibrated commercially available hygrometer (psychrometer) or electronic climatic measuring gauge shall be used to determine the parameters which require readings (i.e. items (i), (iii), (iv), (vi) and (vii)).
395161cc-5f12-55f8-bf7e-0bb3e25ccefb | note | Freq - Each lot
4ab00fbc-448d-5621-8c23-986882adacbd | note | Key - S
8df55d40-38f6-5197-9665-763de506d044 | note | Resp - SE
| section | 10.0 Handling and storage
| checkpoint | 10.1 - General Contractor handling
29342d04-c45c-570f-9ff3-e006daeb6545 | note | Ref docs - 686.12
12409026-da9a-517c-85cf-fffbb7442c44 | note | Acceptance criteria - All material shall be brought to site in the original unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers.
33af52d3-9907-52f0-8220-3edff8d75b03 | note | ○ The Contractor shall provide a certificate from the manufacturer for each batch of coating and primer material confirming:
fa701ddf-fe71-5d9a-b6b0-b3d077b6673c | note | (a) manufacturer’s name and address;
257c893d-620f-5e55-a6b0-701e453f5db3 | note | (b) product reference;
c66c0fd7-5aa1-5442-b183-0fa9984290ad | note | (c) batch number of identification;
7b5659d9-de74-5cfb-bdec-818eec4a6a14 | note | (d) quantity manufactured in the batch; and
2ef8ad4f-47c9-50b1-a4b2-f63f9fdccadc | note | (e) date of manufacture.
2667b7a1-506d-538b-a029-42b5aab3643a | note | ○ The Contractor shall maintain records showing which elements were treated with each coating batch. These records shall be handed over to the Superintendent before the Date of Practical Completion.
4e137749-751c-5d51-be8a-d1c9222dd841 | note | Freq - Each lot
ac31b21f-a7f6-553b-83ba-df88c379be60 | note | Key - W
7988fe8c-9921-51ce-9230-5bad9068a582 | note | Resp - SE
a46581d7-c4a3-5b49-9eb4-179a416fde7d | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
0b31bb92-36b2-567b-9141-52f2d7a3d502 | tickbox | Incoming Material Checklist
8c93e51c-6e09-5616-af88-4664ebd74e59 | tickbox | Certificate of batch information
| section | 11.0 Testing before and after application
| checkpoint | 11.1 - Testing before application
8b73cdd7-dcb8-5ef1-ae9d-b3e79401a4f2 | note | Ref docs - 686.14(a)
511d288a-0147-5deb-93a7-a48d359cffd0 | note | Acceptance criteria - All concrete surfaces prepared for coating shall be sampled and tested in accordance with the requirements of this section. Each sample of prepared concrete surface shall be tested as required for surface moisture condition, moisture content of concrete, environmental conditions and cross-cut adhesion of previously painted surfaces as specified in this section.
d261eb9c-bb0e-580d-85a0-b01e316ed7bb | note | ○ At least one test per sample shall be carried out immediately prior to the commencement of each day’s coating application to ensure that:
ccfd3371-4491-58cb-b4ee-a25002fa6c2c | note | (i) surface moisture conditions of concrete or other substrates satisfy the manufacturer’s recommendations.
161c700c-600e-507e-9b3e-3030f91b53f3 | note | (ii) moisture content of concrete and other substrates is free of water back pressure to satisfy the manufacturer’s recommendations, in accordance with ASTM D4263-83:2012;
83c9d67b-9aa9-511b-9b4b-34b5ac9102aa | note | (iii) the environmental conditions, as specified in Clause 686.11, are satisfied.
816f4df0-77c0-5b7f-92c3-70115b996972 | note | Freq - Each lot
1b7d5349-c0aa-5552-aaed-595b6a6bf825 | note | Key - W
02c4748f-7b6d-52c3-8d20-fdf6bf1bba96 | note | Resp - SE
| checkpoint | Testing after application
9cd36eb3-a2d6-51c6-b982-b369b4b1967b | note | Ref docs - VRS 686.14(b)
30788666-427f-5b81-82de-a4817f823c47 | note | Acceptance criteria - All applied coating shall be sampled and tested with calibrated equipment in accordance with the requirements of this section. Each sample of applied coating shall be tested as required for bond strength, WFT and DFT, amount of penetration of pore-lining penetrant and water absorption, as specified in this section.
1ff2f600-a146-5acd-bc09-8f0b5860cd1d | note | ○ At least three measurements per sample of each of the following tests shall be carried out after the application of materials to demonstrate compliance with this section.
529cd2be-b4d6-5cf0-b3f1-8502061a5dbe | note | ○ Sections Listed in VR 686.14
2bd72325-eb0b-5c98-a0e2-ef9297d27f07 | note | Freq - Each lot
e8e27307-2961-5586-bf79-a945ce4670f6 | note | Key - W
052e3d5d-e02d-58e1-a0dc-fab2001d8107 | note | Resp - SE
06727b73-6b8e-5eb6-b3ff-d62947acdaf3 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
54d662d1-b6df-5cb9-8d68-1e5366427c04 | tickbox | Record of Testing per Bridge Element
| section | 12.0 Testing before and after application
| checkpoint | 12.1 - Requirements for future maintenance of coatings
77413775-4ff7-5059-b02a-5f5d7c10878e | note | Ref docs - 686.18
d5360131-59bb-5dc2-9e89-c2af129a9fec | note | Acceptance criteria - The Contractor shall provide the manufacturer’s recommendations as follows:
cd6a443e-45a4-5f23-bad4-e98c00aad124 | note | (a) The methods of preparation to be used in the event that re-coating of the coated surface is required.
7b644f79-3915-5842-86aa-31ce38bb03b0 | note | (b) Which types of coating, other than the original product, are compatible with the finish coat for re-coating purposes.
31681a23-63d5-5356-a94e-08145958ca8f | note | (c) The technique which can be used to repair local damage to the coating, with particular reference to colour and gloss matching of finish coats applied after a time lapse of 5 years.
00cb1456-52e1-5225-9da4-721ef5c38e6c | note | Freq - For all works
37b059b0-488f-5658-9116-ac662f310dd0 | note | Key - R
cd82c855-aadc-5df5-8b2e-62bf5b47e9d6 | note | Resp - SE
| section | 13.0 Coating repairs
| checkpoint | 13.1 - Coating repairs if required
4f9d3683-a285-5ff5-bcd2-eed9d070467c | note | Ref docs - 686.17
4a550489-e3e1-54b1-ae37-23120d9c0b3f | note | Acceptance criteria - Should any of the coating application work not comply with the provisions of this specification then the areas concerned shall be repaired to the satisfaction of the Superintendent. Such repair work may include removal of the coating, followed by surface preparation and application of a new coating. The procedure for any repair work shall be reviewed by the Superintendent.
3ddf84c3-9a6c-5edf-b15d-9ea5cc238e46 | note | ○ For the purpose of this clause, non-complying work shall include coating failure due to yellowing, loss of adhesion, and colour change during the contract liability period.
7d55716c-d5e4-57ed-b44a-44e00bbfd26f | note | Freq - Only if Repairs are required
91777cc6-eb78-531d-9d73-0160a89fb6d2 | note | Key - S
296e6c46-5850-526d-9fc5-0cfde8e5a871 | note | Resp - PE
| section | 14.0 Work lot close out
| checkpoint | 14.1 - Test Reports
6462cc81-99a6-5f83-9128-6f65fc22d231 | note | Ref docs - DoT Specs
44460213-9f29-58a4-92e1-1b0759bb4190 | note | Acceptance criteria - All tests received and passed
58398f63-db50-50e7-a5da-dfdc01291307 | note | Freq - Each lot
42d59622-5e47-528a-bfba-2715fff4908b | note | Key - S
ec62685f-04e7-5a7e-be63-a5948cf0ec36 | note | Resp - SE
| checkpoint | 14.2 - Product Non-Conformance
781052f9-e11f-5fd7-bf8a-e676bb6c6b78 | note | Ref docs - QMP
7246d296-42c3-579b-80e4-300817e88397 | note | Acceptance criteria - All product non-conformance(s) recorded closed (if applicable)
02b1cdcd-5682-5b57-a338-a1f1dccc49db | note | Freq - Each lot
74b81d91-73b7-562b-a351-6101815005f6 | note | Key - S
d5a0c208-8275-5f49-9933-012fe49d4bd8 | note | Resp - SE
| checklist | 1630-P200-SYM-QAC-ITP-0069 Tactile Ground Surface Indicator (TGSI) Installation | itp | 1630-P200-SYM-QAC-ITP-0069 Tactile Ground Surface Indicator (TGSI) Installation |  |  | e042df08-f208-42aa-85ca-564be20028d9
| section | ITP Details
| checkpoint | ITP Details
d68249bc-4f28-513f-9829-3ef5cc1ec5e5 | note | ITP No. - 0069
818a5d7b-2017-50ac-b20c-fceaad0f4324 | note | Rev No. - 00
44627a89-c1e8-5f94-bd98-8358f95c9a85 | note | Date of Issue - 18/10/2024
2448ed0c-765f-5171-bb68-bc139a072721 | note | ITP Type - New
| section | 1.0 Pre-start activities
| checkpoint | 1.1 - Material Conformance
7f91a428-eb0b-5dad-9005-9f1b8de8eb83 | note | Ref docs - AS1428.4.1 Fig 2.1, Fig 3.1 RDN 06-05
cff0ed0b-d619-5e6a-ab8d-da7ed1072238 | note | Acceptance criteria - Tactile indicators shall conform to the requirements of AS1428.4.1.
9d2643d1-8d1f-5a80-85e4-6887640d07f2 | note | ○ Tactiles shall be chosen from the DTP approved list per RDN 06-05
7d7f93c5-63f1-5b01-8383-cccfe1a62a8f | note | ○ Tactiles shall be approved by council representative where (if applicable).
359d6c80-e730-50c5-8828-daf86848bdf7 | note | Freq - Prior to start of works
61441b8a-abdc-593e-960a-1d8b9d796ec3 | note | Key - H
71ad2a0e-dead-5f62-ae6c-cf037aee1ffe | note | Resp - SE
5fe4dafe-8745-50f0-95d8-c81daaa9f3a9 | note | SI Key - H
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Luminance-contrast testing
133a5e6b-0516-5f8c-b2c1-7941e587ff85 | note | Ref docs - AS 1428.4.1 Cl 2.2
714e5420-911e-552a-bd58-a34de83e1f16 | note | Acceptance criteria - Luminance-contrast testing shall be completed as per AS 1428.4.1 to confirm the selected TGSIs have a luminance-contrast to the base surface of not less than 30%
fd8f2bde-2773-54f7-a565-a7dd8eaa1eaa | note | Freq - Prior to start of works
5daf1cd7-e37c-5b2a-bc45-3b8473ddd921 | note | Key - H
30080bab-4578-5dca-8ff5-17359bcf3ec1 | note | Resp - SE
4f2a001d-0a9e-583e-a20a-b0b548f1d9e4 | note | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
020703ea-95a3-5621-99e9-3674221c32cc | tickbox | Test Report
| section | 2.0 Installation
| checkpoint | 2.1 - Set out
0b2d17d7-97c9-5c18-9fb5-eab2ad9d3d98 | note | Ref docs - AS 1428.4.1 Cl 2.2, Cl 3.2
734bad44-fef8-5919-8ef2-f932afa83d5c | note | Acceptance criteria - TGSI’s shall be inspected prior to fixing to confirm the below tolerances are met:
98e807ed-dbb9-5f3a-9e78-32396bcb90a2 | note | – TGSI’s shall be inspected prior to fixing to confirm the below tolerances are met:
ec695923-aa9e-54cf-9db8-2e9481577d53 | note | – 300mm from face of kerb ± 10mm
de34d2a9-d8b0-5842-a0a9-22e810c991ae | note | – TGSI base is a maximum 3mm above the ground surface.
68143418-7cea-5bf5-98ff-fd9e05ea1f90 | note | – Within 300mm of traffic signal push-buttons (where applicable).
f9e768d4-aec9-54cb-a01d-bd1ab8b03ee1 | note | Freq - Each Lot
979dc973-a961-5c74-a13c-4227c6495fc2 | note | Key - H
0c6e6638-425e-57a6-bb02-794cd21fd174 | note | Resp - SE
| checkpoint | 2.2 - Tactile Install - Warning
cddd3bf5-944f-520d-ada7-e5d3322eaec7 | note | Ref docs - AS1428.4.1 Cl 2.2
9966e90f-2247-5848-a26c-209d93a8187c | note | Acceptance criteria - Tactiles shall be installed:
d22beb61-ea1b-5875-b29f-8fecf5735e20 | note | – Perpendicular to the carriageway
898035ed-ed16-5809-8ac9-e1012e19d11e | note | – To the full width of the path of travel
3a7be27f-fedc-5612-9de5-d00504c7b687 | note | – So that there is no likelihood of the edges lifting
f5516bb2-74cd-5415-993c-2bcf4d7a52ab | note | – In accordance with AS1428.4.1 and the IFC drawings
e53e85c4-775a-5464-9fed-b8e782754fcc | note | Freq - Each Lot
f90993b3-aff1-5826-a8bb-64bc70844830 | note | Key - H
d369b1f2-2c24-511a-9a1f-9a8c5c99c799 | note | Resp - SE
| checkpoint | 2.3 - Tactile Install - Directional
b859b6d7-c53b-5477-b899-041dd59ef29d | note | Ref docs - AS1428.4.1 Cl 3.2
9be33abd-f7e3-526b-8f7c-950546058bb6 | note | Acceptance criteria - Tactiles shall be installed:
a988d4e5-8625-52f9-9bf6-15cbf3f451b8 | note | – Parallel to the required direction of travel
c0c93fe6-9a4d-5e3e-9d77-ce0ed46fd4e3 | note | – Along the centreline of the required direction of travel
adbf7f38-132a-5575-835d-dd60c92c2f49 | note | – So that there is no likelihood of the edges lifting
99142681-3a87-5182-8e1e-9a30dda06d87 | note | – In accordance with AS1428.4.1 and the IFC drawings
86148bee-85a7-577a-892b-66692ceb7c79 | note | Freq - Each Lot
4ffd4d2e-0906-521e-b29a-84d05966af59 | note | Key - H
9773e28f-876f-5d4b-b334-4afbfa8aa67a | note | Resp - SE
| section | 3.0 Work Lot Close Out
| checkpoint | 3.1 - Product Non-Conformance
647c832b-a1b2-5e30-a4a0-acc267ec3c6b | note | Ref docs - CQMP
cf8386ca-2963-5c01-9eb0-d976d4822b48 | note | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
9b63d275-ed0f-5258-a062-f10d3f8da264 | note | Freq - Each lot
7d63e801-8b9a-5d4f-b22b-d51a2e17add1 | note | Key - R
b7782c58-a1d4-5404-82f4-69e0d48f879c | note | Resp - SE
| checkpoint | 3.2 - Quality Representative to check the above criteria and records to confirm
e3833244-8195-56c1-8e69-763e910b70af | note | Ref docs - CQMP, Lot Records
69237d93-ad5a-503c-b62c-547735ccecb7 | note | Acceptance criteria - All above criteria met, and records identified attached.
8640b94a-fb4e-5d1c-8bed-ec58292f4a32 | note | Freq - Each lot
05c58114-fbb5-5ecc-8583-2c10c8282f07 | note | Key - R
244327d8-8a4e-5c2b-8146-6b289c968a7b | note | Resp - SE