## Table 1
|  |  |  | ASM-FRM- A3541693 | [5 empty] | Version: 3.0
Civil ITR 7. Road Gravels
Project Details
Contractor |  |  | Consolidated Power Projects |  |  |  |  | Structure/Lot Identifier |  |  | Road Gravels - Lot 1
Project Title and Number: |  |  | PP230174 13297 Ulinda BESS GC |  |  |  |  | Drawing Reference |  |  | H-138263-510, 511, 512, 513
Instruction to Contractor seeking hold point release and/or approval to proceed with work
Contractors shall have all relevant supporting evidence on file with all ITR check items verified and completed where required, prior to site inspection by a Powerlink Representative and/or request of hold point release. All activities listed are to be undertaken in accordance with the relevant specifications/design where applicable.
Item |  | Work activity/item to be validated or verified |  |  |  | Evidence | Acceptance Criteria |  | Contractor Rep |  |  | Powerlink Rep
[9 empty] | Initial |  | Date | Initial | Date
1 |  | Material submission approved (Circle layer type) Sub-Base / Base / Capping layer |  |  |  | Email / Report | SSC413 Cl 2.2 SSC420 Cl 2.8
2 |  | Set out of road/pavement confirmed |  |  |  | Survey / Visual | IFC
3 |  | Check of existing underground services |  |  |  | Permit # | Excavation Permit
4 |  | Confirmation of required design thickness for this compacted layer (Record layer thickness) |  |  |  | Visual / Photo | IFC
5 |  | Finished levels confirmed for this layer |  |  |  | Visual / Photo | IFC
6 |  | Approval to place over underlying layers |  |  |  | Visual / Report | SSC413 Cl 2.3
|  | Hold Point Release Required |  |  |  |  | PLQ Representative
7 |  | Existing surface lightly scarified and moisture corrected prior to placement of next layer |  |  |  | Visual / Photo | SSC413 Cl 2.3
8 |  | Record required compaction test value and type |  |  |  | Test Report | SSC413 Cl 2.3
9 |  | List any re-work or replacement of this layer (i.e.: Soft spot removal) |  |  |  | Visual / Photo | SSC413 Cl 2.3
10 |  | Check line/level of completed layer prior to testing |  |  |  | Survey / Visual | SSC413 Cl 2.3
11 |  | Test results forwarded to PLQ |  |  |  | Email / Report | SSC413 Cl 2.3
|  | Hold Point Release Required |  |  |  |  | PLQ Representative
12 |  | Test rolling undertaken |  |  |  | Visual / Photo | SSC413 Cl 2.4
|  | Final Hold Point Release |  |  |  |  | PLQ Representative
| Current version: 23/04/2021 | [8 empty] | Page 10 of 20
[5 empty] | HARDCOPY IS UNCONTROLLED |  |  |  |  | © Powerlink Queensland
Created from ASM-FRM-A3541693 v1.1 effective date: 23/04/2021