## Table 1
|  | ASM-FRM- A3541693 |  |  |  |  | Version: 3.0
Civil ITR 14. Earthworks
Instruction to Contractor seeking hold point release and/or approval to proceed with work
Contractors shall have all relevant supporting evidence on file with all ITR check items verified and completed where required, prior to site inspection by a Powerlink Representative and/or request of hold point release. All activities listed are to be undertaken in accordance with the relevant specifications/design where applicable.
Item | Work activity/item to be validated or verified |  |  | Evidence | Acceptance Criteria | Contractor Rep |  |  | Powerlink Rep
[6 empty] | Initial |  | Date | Initial | Date
1 | GTIA RPEQ’s details responsible for the all Earthworks activities, submitted to PLQ |  |  | Email | SSC-420 Cl. 2.2
2 | Certification of all imported materials submitted for approval |  |  | Email/Report | SSC-420 Cl. 2.8.1
3 | Stockpile areas not shown on AFC drawings have been agreed by PLQ |  |  | Visual/Photo | SSC-420 Cl. 2.16
| Hold Point Release Required |  |  |  | PLQ Representative
4 | Permanent and temporary survey control shown on AFC drawings has been installed with details submitted to PLQ |  |  | Email/Visual | SSC-420 Cl. 2.3.2, SSC-426 Cl. 2.8.8
5 | Prior to any clearing the limits of work have been clearly marked out |  |  | Visual/Photo | SSC-414 Cl. 2.2.1
| Witness Point required |  |  |  | PLQ Representative
6 | Existing topsoil has been treated prior to removal |  |  | Visual/Photo | SSC-420 Cl. 2.16
7 | After the removal of topsoil inspections will be carried out |  |  | Visual/Photo | SSC-420 Cl. 2.5
| Hold Point Release Required |  |  |  | PLQ Representative
8 | Areas of rock have been over excavated |  |  | Visual/Photo | SSC-420 Cl. 2.11
9 | Insitu material treated and compacted prior to filling |  |  | Visual/Photo | SSC-420 Cl. 2.6.3
| Hold Point Release Required |  |  |  | PLQ Representative
10 | All fill layers to be tested and inspected by PLQ |  |  | Visual/Photo/Report | SSC-420 Cl. 2.9
| Witness Point required |  |  |  | PLQ Representative
11 | Each layer lightly scarified before placement of next layer |  |  | Visual/Photo | SSC-420 Cl. 2.9
12 | Final layer inspected by PLQ: prior to inspection all test results to be submitted to PLQ |  |  | Visual/Photo/Report | SSC-420 Cl. 2.9
| Final Hold Point Release |  |  |  | PLQ Representative
Current version: 23/04/2021 | [6 empty] | Page 17 of 20
|  |  | HARDCOPY IS UNCONTROLLED |  |  |  | © Powerlink Queensland
|  | ASM-FRM- A3541693 |  |  |  |  | Version: 3.0
Civil ITR 14. Earthworks