## Table 1
Inspection and Test Plan
Contract: | [6 empty] | 3200-0706
Customer: | [6 empty] | Neoen / Tesla
ITP Title: | [6 empty] | Earthworks Select Fill
ITP Number: | [6 empty] | 3200-0706-ITP-CE-001
Current Revision: | [6 empty] | A
Current Revision Date: | [6 empty] | 2024-11-11
Status: | [6 empty] | Draft
Lot Number / Area
Lot Description
ITP Approval
Workflow |  |  |  | Name | [6 empty] | Title / Position | [9 empty] | Signature | [5 empty] | Date
Prepared by: |  |  |  | Edwin Mendoza | [6 empty] | Senior Civil Project Engineer | [15 empty] | 2024-11-11
Reviewed by: |  |  |  | Edwin Mendoza | [6 empty] | Senior Civil Project Engineer | [15 empty] | 2024-11-11
Reviewed by: |  |  |  | Mehdi Farahmand | [6 empty] | QA/QS Lead | [15 empty] | 2024-11-11
Approved by: |  |  |  | Matthew Sultana | [6 empty] | Construction Manager | [15 empty] | 2024-11-11
Revision History
Date | [5 empty] | Revision Number | [5 empty] | Revision Details
2024-11-11 | [5 empty] | A | [5 empty] | First draft issued for review / comment
Title: Inspection and Test Plan- Earthworks Select Fill ID: UGLMS-4-987 Version: 8.0 Date Published: 13/06/2024 UGL Governance System - Uncontrolled Document when Printed
ITP Number: |  |  |  |  | 3200-0706-ITP-CE-001 | [17 empty] | ITP Title: | [5 empty] | Earthworks Select Fill
Contact Details | [9 empty] | Summary of Requirements | [12 empty] | Principal Codes / Standards | [7 empty] | Records
Customer: |  |  |  |  | Neoen/ Tesla |  |  |  |  | Process Qualifications: Level 1 Supervision at all times for bulk earthworks; from subgrade to pavement. | [12 empty] |  AS1289 - Methods of testing soils for engineering purposes  AS3798 - Guidelines on earthworks for commercial and residential developments  MRTS04 General Earthworks  MRTS05 Unbound Pavements | [7 empty] | (MDR Insert as marked )
Operations Mgr: |  |  |  |  | Mark Groth | [25 empty] | Inspect Release Cert
Project Engineer: |  |  |  |  | Edwin Mendoza | [25 empty] | Deviations/Concessions
Quality Rep: |  |  |  |  | Mehdi Farahmand | [25 empty] | Material Certificates
Subcontractors | [9 empty] | Traceability: | [20 empty] | Conformance Certificate
Design: |  |  |  |  | UGL Engineering |  |  |  |  | Material | [5 empty] | Alloy Verification: | [14 empty] | Welding Records
Drafting: |  |  |  |  | UGL Engineering |  |  |  |  | Heat Treatment | [5 empty] | Pressure Testing: | [14 empty] | Welder Qual. Register
Subcontractor: |  |  |  |  | Western Down Civil (WDC) |  |  |  |  | Consumable: | [5 empty] | NDT | [14 empty] | NDT Reports
[10 empty] | Welder ID: | [5 empty] | WPS | [6 empty] | Client Specifications | [7 empty] | Report on Repairs
[10 empty] | Electrical: | [5 empty] | Instrumentation | [6 empty] | N/A | [7 empty] | Heat Treatment Records
Dimensional Records
Surveillance / Inspection Key | [9 empty] | Heat Treatment: | [12 empty] | UGL Procedures/ WI’s | [7 empty] | Non-Conformance Rpts
HOLD POINT (H): Nominated point beyond which work shall not proceed without verified acceptance by nominee | [22 empty] |  3200-0706-PLN-001- QMP  3200-0706-PLN-004 -ERP  3200-0706-PLN-005- CEMP  0706-C-DRG-0001 Cover Sheet and Drawing List  0706-C-DRG-0002 General Notes  0706-C-DRG-0003 General Arrangement and Set Out Plan  0706-C-DRG-0004 Bulk Earthworks Plan  0706-C-DRG-0006 Earthworks Sections Sheet 1 of 2  0706-C-DRG-0007 Earthworks Sections Sheet 2 of 2  0706-C-DRG-0008 Finished Grading Sheet 1 and 2  0706-C-DRG-0009 Pavement Plan  0706-C-DRG-0010 Drainage Civil  0706-C-DRG-0011 Earthworks Sections and Details  0706-C-DRG-0012 Erosion and Sedimentation Control Plan Construction Stage  0706-C-DRG-0013 Erosion and Sedimentation Control Plan Completion Stage  0706-C-DRG-0014 Erosion and Sediment Control Details  0706-C-DRG-0015 Drainage Details Sheet 1 and Sheet | [7 empty] | Pressure Test Records
[10 empty] | Dimensional Control: | [20 empty] | Drawing & Data Sheets
Misc Verification Records
WITNESS POINT (W): Points at which the nominee shall be notified and invited to witness an activity but further work may proceed without the presence of the nominee. | [9 empty] | Testing (NDT): | [20 empty] | Electrical Test Sheets
Position
[10 empty] | Acceptance Specification: | [20 empty] | Operations Manager |  |  | OM
REVIEW (R): Verify by examination of documentary evidence that inspection / tests have been satisfactorily conducted. | [30 empty] | Project Engineer |  |  | PE
[10 empty] | Pressure Testing: | [20 empty] | Quality Representative |  |  | QR
[31 empty] | Pre-Processing |  |  | PP
SURVEILLANCE (S): Continuing evaluation of the status of methods, analysis of records and monitoring of activities on a random basis to ensure quality of requirements will be met. | [9 empty] | Elect. / Instrumentation: | [20 empty] | Technician |  |  | T
[31 empty] | Welding Supervisor |  |  | WS
[10 empty] | Notes: All sampling and testing for earthworks and concrete shall be taken by a NATA accredited laboratory. | [20 empty] | Workshop Foreman |  |  | WF
VISUAL (V): 100% Visual inspection of work / item to ensure compliance with code / spec | [30 empty] | Document Controller |  |  | DC
[31 empty] | Store Person |  |  | SP
DIMENSIONAL (D): Measurement of critical dimensions to ensure work/item is within tolerance | [30 empty] | Subcontractor |  |  | SC
[31 empty] | Elect. / Instrumentation |  |  | E/I
ITP Number: |  |  |  |  | 3200-0706-ITP-CE-001 | [19 empty] | ITP Title: |  |  |  |  | Earthworks Select Fill
ITEM NO.: | PROCESS ACTIVITY |  |  |  |  | PROCEDURE / INSTRUCTION | [6 empty] | ACCEPTANCE CRITERIA |  |  |  |  | RELEVANT SECTION | [6 empty] | VERIFYING DOCUMENT |  |  |  | VERIFICATION (SIGN & DATE) |  |  |  | REMARKS
[29 empty] | S/C | UGL |  | Client
STAGE 1: PREPARATION WORKS
1.1 | Permits and Approvals |  |  |  |  | Ensure Permits are in place including, but not limited to:  Excavation Permits | [6 empty] | Excavation Permit |  |  |  |  | UGL Safety Critical Risk Control – Excavation and Trenching | [6 empty] |  Approved Permits in place and stored on project drive.  Working Party to have access and sign onto permits where required. |  |  |  | H | H |  | S
1.2 | CEMP and Emergency Response Plans |  |  |  |  | Controls established within CEMP and ERP shall be adhered to throughout works. | [6 empty] | 3200-0706-PLN-005 – CEMP 3200-0706-PLN-004 - ERP |  |  |  |  | 0706-C-DRG-0012 0706-C-DRG-0014 Erosion and Sedimentation Control Plan | [6 empty] | Site Audits as works progress |  |  |  | R | R |  | S
1.3 | Identification of underground services |  |  |  |  | Use of DBYD and pothole to positively identify underground services. | [6 empty] | N/A |  |  |  |  | UGL Safety Critical Risk Control – Excavation and Trenching | [6 empty] | DBYD / Excavation Permit Survey (if required) |  |  |  | H | H |  | S
1.4 | Approval of Subcontractor SWMS and Construction Methodologies |  |  |  |  | Submission, review, and approval of all subcontractor SWMS and construction methodologies for the works. | [6 empty] |  SWMS Approved  Construction Methodologies Approved |  |  |  |  |  UGL-Contractor HSEQ Requirements  Scope Of Work Cl2.1 item m. | [6 empty] |  UGL SWMS Review Forms and approved SWMS  UGL SWMS Register |  |  |  | H | H |  | S
1.5 | Conformance of Materials |  |  |  |  | All delivered materials and procured items conforms to project specification and AFC drawings. | [6 empty] | As per Drawings and Specifications |  |  |  |  | MRTS04 Table A.1 No. 1.1 Earth Fill Material and Table 14.2.2. | [6 empty] |  Material Certificates  Test Reports |  |  |  | H | H |  | S
1.6 | Inspection Measuring and Test Equipment (IMTE) Registers |  |  |  |  | Supply of all calibration certificates to the Engineer including but not limited to: Survey equipment | [6 empty] | Visual |  |  |  |  | UGL 3200-0706- PLN-001 QMP Section 9.8 | [6 empty] |  Calibration Certificates  UGL IMTE Register |  |  |  | R | R |  | S
STAGE 2: CONSTRUCTION WORKS
2.1 | Setout of pad |  |  |  |  |  Registered Surveyor to set out pad with pegs and markers.  Check surveyor marks against known structures, such as boundaries, fences , and more or control points. | [6 empty] |  Drawing provided showing marked out areas and exclusion zones.  Drawing Number: 0706-C-DRG-0003 |  |  |  |  |  Drawing Number: 0706-C-DRG- 0002 General Notes G8.  Drawing Number: 0706-C-DRG- 0003 | [6 empty] |  Survey complies with checks and AFC drawings.  AFC Drawings |  |  |  | H | H |  | S
2.2 | Subgrade: In location of existing surface- hardstand material: Tyne existing surface |  |  |  |  |  Tyne surface and remove any unsuitable material i.e., construction debris, vegetation etc.  Moisture conditioned as required and compact to 98% SMDD.  Proof Roll using either 7,000 litre single rear axle or 10,000 litre double rear axle water tanker. | [6 empty] |  Pad free of all unwanted materials  Soil compacted 98% SMDD.  Stockpile is not to exceed 2m and a slope of 1V:3H. |  |  |  |  | Drawing Number: 0706-C-DRG-0011 Notes Item 2, 3 & 5. | [6 empty] |  3200-0706-ITC-CE-001 Earthworks Select Fill  SMDD Test Report (NATA Accredited Laboratory) |  |  |  | H | H |  | S
2.3 | Subgrade: In location where NO existing hardstand material – strip surface |  |  |  |  |  Strip surface to 150mm depth and remove any unsuitable material i.e., construction debris, vegetation etc.  Moisture conditioned as required and compact 200mm minimum depth to 98% SMDD to achieve minimum CBR 5%.  Proof Roll using either 7,000 litre single rear axle or 10,000 litre double rear axle water tanker. | [6 empty] |  Pad free of all unwanted materials.  Soil compacted to 98% SMDD, No perceptible deformation. |  |  |  |  | Drawing Number: 0706-C-DRG-0011 Notes Item 2, 3 & 5. | [6 empty] |  3200-0706-ITC-CE-001 Earthworks Select Fill  SMDD Test Report (NATA Accredited Laboratory) |  |  |  | H | H |  | S
2.4 | Presence of contaminated soil or heritage items |  |  |  |  | If contaminated soil or heritage items are found during excavation, works are to stop immediately. | [6 empty] | Visual inspection |  |  |  |  | 3200-0706-PLN-005 – CEMP | [6 empty] | UGL team to document as per 3200-0706-PLN-005 CEMP |  |  |  | H | H |  | S
2.5 | Finish Subgrade |  |  |  |  | Survey finish surface of subgrade. | [6 empty] |  Survey Conformance Report for finish surface uniformity.  Tolerances average ±10mm Vertical  Maximum ±20mm in 3m straight edge at any direction.  Minimum CBR 5%. |  |  |  |  | Drawing Number: 0706-C-DRG-0011 Notes Item 2, 3 & 5. Drawing 0706-C- DRG-0002 Gen. Notes E5 & P1. MRTS04 Cl 6.3.1 Table 6.3.1 | [6 empty] |  3200-0706-ITC-CE-001 Earthworks Select Fill  Survey Conformance Report for finish surface uniformity |  |  |  | H | H |  | S
2.6 | Select Fill tie-in |  |  |  |  | Tie-in new select fill material to existing pad through series of benching. | [6 empty] |  Platform bench dimension 200mm vertical steps and 600mm wide. |  |  |  |  | Drawing number 0706-C-DRG-0011 Typical Platform Tie-In detail | [6 empty] |  Visual  Dimensional check |  |  |  | H | H |  | S
2.7 | Select Fill Class A1 Select Fill Material CBR 15% |  |  |  |  |  Place maximum 200mm thick loose material and compact in layers.  Compact to 98% SMDD.  Trim final surface level for uniformity. | [6 empty] |  Fill compacted to 98% SMDD.  Surface Tolerance ±5mm V/H  Maximum ±10mm in 3m straight edge at any direction.  OMC ±4.  Minimum 4 test per lot. |  |  |  |  | Drawing TC18368- C-DRG-0001 Earthworks Notes E9. | [6 empty] |  Survey Conformance Report for finish surface uniformity.  NATA test report for Density and OMC  3200-0706-ITC-CE-001 Earthworks Select Fill |  |  |  | H | H |  | S
2.8 | Proof Roll |  |  |  |  |  Proof roll using either 7,000 litre single rear axle or 10,000 litre tandem rear axle water tanker | [6 empty] |  No perceptible surface deformation |  |  |  |  |  MRTS05 Cl 9.4.7  Testing Method Q723 | [6 empty] |  Visual |  |  |  | H | H |  | S
STAGE 3: ITP CLOSE-OUT
3.1 | Compilation of survey records |  |  |  |  | Sub-contractor to provide survey records to Engineer for review and acceptance. Deviations or changes to AFC Design shall be highlighted to Engineer. | [6 empty] | Provision of CAD file of Works. |  |  |  |  | UGL 3200-0706- PLN-001 QMP Section 11.1.1 | [6 empty] |  As-Constructed drawing |  |  |  | R | R |  | S
3.2 | Develop Punchlist |  |  |  |  | Walkdown and inspection of works and development of punch list with Engineer and or Supervisor. | [6 empty] | Punchlist closed in a timely manner. |  |  |  |  | UGL 3200-0706- PLN-001 QMP Section 9.7 | [6 empty] |  Master Punchlist Register |  |  |  | R | R |  | S
3.3 | Closeout of NCRs |  |  |  |  | Any NCRs that have been raised during the progress of the works have been formally closed out and lessons have been captured. Refer to UGL Quality Management Plan. | [6 empty] | NCRs close out in a timely manner. |  |  |  |  | UGL 3200-0706- PLN-001 QMP Section 9.5 | [6 empty] |  NCR Closed, signed off. |  |  |  | R | R |  | S
3.4 | Changes captured and agreed within RFIs |  |  |  |  | Any deviations to AFC Design or Contract Specifications are to be captured, recorded, and agreed via the Formal RFI process. | [6 empty] | All RFI’s to be agreed or accepted in a timely manner. |  |  |  |  | UGL 3200-0706- PLN-001 QMP Section 11.1.1 | [6 empty] |  Site RFI Register |  |  |  | R | R |  | S
3.5 | As Constructed records – Red Line Mark-Up (RLMU) Drawings. |  |  |  |  | Sub-contractor to compile and record changes on AFC Drawings, to be issued to UGL Engineering via Teambinder. | [6 empty] | AFC drawing stamped with As-Constructed Drawing, date and signed by Subcontractor/ Surveyor. |  |  |  |  | UGL 3200-0706- PLN-001 QMP Section 11.1.1 | [6 empty] |  As-Constructed Drawing / RLMU drawing |  |  |  | R | R |  | S
COMMENTS AND NOTES
ITP COMPLETION AND SIGN-OFF
S/C Representative | [12 empty] | UGL Representative | [14 empty] | Client Representative
Name: | [12 empty] | Name: | [14 empty] | Name:
Signature: | [12 empty] | Signature: | [14 empty] | Signature:
Date: | [12 empty] | Date: | [14 empty] | Date:
ITP Number: |  |  | 3200-0706-ITP-CE-001 | [11 empty] | ITP Title: |  |  |  | Earthworks Select Fill
Attachment A - Inspection and Test Plan Notes
Document Rev | [7 empty] | Activity Ref | [5 empty] | Change | [7 empty] | Reason for Change
Earthworks Select Fill INSPECTION & TEST CHECKLIST (ITC) Checklist No: 3200-0706-ITC-CE-001
Project No: |  |  |  | 3200-0706 | [5 empty] | Title: |  |  | WD BESS |  |  |  | Client: |  |  | NEOEN TESLA
Description: |  |  |  | CE – Earthworks Select Fill
Lot No: | [9 empty] | Drawing / Area Ref:
Work Pack No: |  |  |  | 3200-0706-WP-002: General Civil Works | [5 empty] | ITP Ref: | [6 empty] | 3200-0706-ITP-CE-001
NOTE: Strike through sections that are not applicable.
Item |  | Description | [17 empty] | Yes |  |  |  | No |  | N/A
1 |  | Prior Works
1.1 |  | Materials are compliant to design
1.2 |  | Surveyor pad layout
1.3 |  | Installation of Erosion and Sediment Controls installed
2 |  | Earthworks – Subgrade
2.1 |  | Existing surface – with existing hardstand material
2.1.1 |  | Surface tyned and free of unsuitable material i.e., construction debris, vegetation, etc.
2.1.2 |  | Compacted to 98% prior to fill Actual SMDD value: Test Report number:
2.1.3 |  | Surface has been proof rolled. No perceptible movement observed.
2.2 |  | Existing surface – without existing hardstand material
2.2.1 |  | Surface stripped to 150mm depth and free of unsuitable material i.e., construction debris, vegetation etc.
2.2.2 |  | Compact subgrade to a minimum depth of 200mm to 98% SMDD to achieve CBR 5% Actual SMDD value: Test Report number:
2.3 |  | Finish subgrade surface level Survey pick-up (As-Constructed) prior to select fill Tolerances: ± 10 V/H
2.4 |  | Cultural heritage artefacts – Visual only
2.5 |  | Contaminated soil – Visual only
2.6 |  | Earthworks : Select Fill Type A1 with CBR 15%
2.6.1 |  | Platform Tie In 200mm vertical steps and 600mm wide
2.6.2 |  | Spread fill and compact maximum layer of 150mm
2.6.3 |  | Compacted to 98% SMDD Actual SMDD value: Test Report number:
2.6.4 |  | Finish fills surface level Survey pick-up (As-Constructed) Tolerances: ± 10 V/H
3 |  | Post Works
3.1 |  | Final sweep to remove loose and unwanted materials prior to next layer
3.2 |  | Clean-up of Site
Comments
Checked – Subcontractor
Name: | [8 empty] | Signed: | [8 empty] | Date:
Verified – UGL Project Engineer
Name: | [8 empty] | Signed: | [8 empty] | Date: