## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC - Earthworks Select Fill | [5 empty] | ITC - Earthworks Select Fill
section | 1 - Prior Works
checkpoint | 1.1 - Materials are compliant to design
checkpoint | 1.2 - Surveyor pad layout
checkpoint | 1.3 - Installation of Erosion and Sediment Controls installed
section | 2 - Earthworks – Subgrade
checkpoint | 2.1 - Existing surface – with existing hardstand material
checkpoint | 2.1.1 - Surface tyned and free of unsuitable material i.e., construction debris, vegetation, etc.
checkpoint | 2.1.2 - Compacted to 98% prior to fill
textbox | Actual SMDD value:
textbox | Test Report number:
checkpoint | 2.1.3 - Surface has been proof rolled. No perceptible movement observed.
checkpoint | 2.2 - Existing surface – without existing hardstand material
checkpoint | 2.2.1 - Surface stripped to 150mm depth and free of unsuitable material i.e., construction debris, vegetation etc.
checkpoint | 2.2.2 - Compact subgrade to a minimum depth of 200mm to 98% SMDD to achieve CBR 5%
textbox | Actual SMDD value:
textbox | Test Report number:
checkpoint | 2.3 - Finish subgrade surface level Survey pick-up (As-Constructed) prior to select fill Tolerances: ± 10 V/H
checkpoint | 2.4 - Cultural heritage artefacts – Visual only
checkpoint | 2.5 - Contaminated soil – Visual only
section | 2.6 - Earthworks : Select Fill Type A1 with CBR 15%
checkpoint | 2.6.1 - Platform Tie In 200mm vertical steps and 600mm wide
checkpoint | 2.6.2 - Spread fill and compact maximum layer of 150mm
checkpoint | 2.6.3 - Compacted to 98% SMDD
textbox | Actual SMDD value:
textbox | Test Report number:
checkpoint | 2.6.4 - Finish fills surface level Survey pick-up (As-Constructed) Tolerances: ± 10 V/H
section | 3 - Post Works
checkpoint | 3.1 - Final sweep to remove loose and unwanted materials prior to next layer
checkpoint | 3.2 - Clean-up of Site
checkpoint | Checked – Subcontractor / Verified – UGL Project Engineer
holdpoint | Add Signatures