## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 3200-0706-ITP-CE-001 Earthworks Select Fill | itp |  |  |  |  | 3200-0706-ITP-CE-001 Earthworks Select Fill
section | STAGE 1: PREPARATION WORKS
checkpoint | 1.1 - Permits and Approvals
label | PROCEDURE / INSTRUCTION - Ensure Permits are in place including, but not limited to:
label | ○ Excavation Permits
label | ACCEPTANCE CRITERIA - Excavation Permit
label | RELEVANT SECTION - UGL Safety Critical Risk Control – Excavation and Trenching
label | VERIFYING DOCUMENT - Approved Permits in place and stored on project drive.
label | ○ Working Party to have access and sign onto permits where required.
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 1.2 - CEMP and Emergency Response Plans
label | PROCEDURE / INSTRUCTION - Controls established within CEMP and ERP shall be adhered to throughout works.
label | ACCEPTANCE CRITERIA - 3200-0706-PLN-005 – CEMP
label | ○ 3200-0706-PLN-004 - ERP
label | RELEVANT SECTION - 0706-C-DRG-0012
label | ○ 0706-C-DRG-0014
label | ○ Erosion and Sedimentation Control Plan
label | VERIFYING DOCUMENT - Site Audits as works progress
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 1.3 - Identification of underground services
label | PROCEDURE / INSTRUCTION - Use of DBYD and pothole to positively identify underground services.
label | ACCEPTANCE CRITERIA - N/A
label | RELEVANT SECTION - UGL Safety Critical Risk Control – Excavation and Trenching
label | VERIFYING DOCUMENT - DBYD / Excavation Permit Survey (if required)
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 1.4 - Approval of Subcontractor SWMS and Construction Methodologies
label | PROCEDURE / INSTRUCTION - Submission, review, and approval of all subcontractor SWMS and construction methodologies for the works.
label | ACCEPTANCE CRITERIA - SWMS Approved
label | ○ Construction Methodologies Approved
label | RELEVANT SECTION - UGL-Contractor HSEQ Requirements
label | ○ Scope Of Work Cl2.1 item m.
label | VERIFYING DOCUMENT - UGL SWMS Review Forms and approved SWMS
label | ○ UGL SWMS Register
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 1.5 - Conformance of Materials
label | PROCEDURE / INSTRUCTION - All delivered materials and procured items conforms to project specification and AFC drawings.
label | ACCEPTANCE CRITERIA - As per Drawings and Specifications
label | RELEVANT SECTION - MRTS04 Table A.1, No. 1.1 Earth Fill Material and Table 14.2.2.
label | VERIFYING DOCUMENT - Material Certificates
label | ○ Test Reports
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 1.6 - Inspection Measuring and Test Equipment (IMTE) Registers
label | PROCEDURE / INSTRUCTION - Supply of all calibration certificates to the Engineer including but not limited to: Survey equipment
label | ACCEPTANCE CRITERIA - Visual
label | RELEVANT SECTION - UGL 3200-0706- PLN-001 QMP Section 9.8
label | VERIFYING DOCUMENT - Calibration Certificates
label | ○ UGL IMTE Register
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
section | STAGE 2: CONSTRUCTION WORKS
checkpoint | 2.1 - Setout of pad
label | PROCEDURE / INSTRUCTION - Registered Surveyor to set out pad with pegs and markers.
label | ○ Check surveyor marks against known structures, such as boundaries, fences , and more or control points.
label | ACCEPTANCE CRITERIA - Drawing provided showing marked out areas and exclusion zones.
label | ○ Drawing Number: 0706-C-DRG-0003
label | RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0002 General Notes G8.
label | ○ Drawing Number: 0706-C-DRG-0003
label | VERIFYING DOCUMENT - Survey complies with checks and AFC drawings.
label | ○ AFC Drawings
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.2 - Subgrade: In location of existing surface- hardstand material: Tyne existing surface
label | PROCEDURE / INSTRUCTION - Tyne surface and remove any unsuitable material i.e., construction debris, vegetation etc.
label | ○ Moisture conditioned as required and compact to 98% SMDD.
label | ○ Proof Roll using either 7,000 litre single rear axle or 10,000 litre double rear axle water tanker.
label | ACCEPTANCE CRITERIA - Pad free of all unwanted materials
label | ○ Soil compacted 98% SMDD.
label | ○ Stockpile is not to exceed 2m and a slope of 1V:3H.
label | RELEVANT SECTION - Drawing Number: 0706-C-DRG-0011 Notes Item 2, 3 & 5.
label | VERIFYING DOCUMENT - 3200-0706-ITC-CE-001 Earthworks Select Fill
label | ○ SMDD Test Report (NATA Accredited Laboratory)
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.3 - Subgrade: In location where NO existing hardstand material – strip surface
label | PROCEDURE / INSTRUCTION - Strip surface to 150mm depth and remove any unsuitable material i.e., construction debris, vegetation etc.
label | ○ Moisture conditioned as required and compact 200mm minimum depth to 98% SMDD to achieve minimum CBR 5%.
label | ○ Proof Roll using either 7,000 litre single rear axle or 10,000 litre double rear axle water tanker.
label | ACCEPTANCE CRITERIA - Pad free of all unwanted materials.
label | ○ Soil compacted to 98% SMDD, No perceptible deformation.
label | RELEVANT SECTION - Drawing Number: 0706-C-DRG-0011 Notes Item 2, 3 & 5.
label | VERIFYING DOCUMENT - 3200-0706-ITC-CE-001 Earthworks Select Fill
label | ○ SMDD Test Report (NATA Accredited Laboratory)
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.4 - Presence of contaminated soil or heritage items
label | PROCEDURE / INSTRUCTION - If contaminated soil or heritage items are found during excavation, works are to stop immediately.
label | ACCEPTANCE CRITERIA - Visual inspection
label | RELEVANT SECTION - 3200-0706-PLN-005 – CEMP
label | VERIFYING DOCUMENT - UGL team to document as per 3200-0706-PLN-005 CEMP
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.5 - Finish Subgrade
label | PROCEDURE / INSTRUCTION - Survey finish surface of subgrade.
label | ACCEPTANCE CRITERIA - Survey Conformance Report for finish surface uniformity.
label | ○ Tolerances average ±10mm Vertical
label | ○ Maximum ±20mm in 3m straight edge at any direction.
label | ○ Minimum CBR 5%.
label | RELEVANT SECTION - Drawing Number: 0706-C-DRG-0011 Notes Item 2, 3 & 5.
label | ○ Drawing 0706-C- DRG-0002 Gen. Notes E5 & P1.
label | ○ MRTS04 Cl 6.3.1 Table 6.3.1
label | VERIFYING DOCUMENT - 3200-0706-ITC-CE-001 Earthworks Select Fill
label | ○ Survey Conformance Report for finish surface uniformity
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.6 - Select Fill tie-in
label | PROCEDURE / INSTRUCTION - Tie-in new select fill material to existing pad through series of benching.
label | ACCEPTANCE CRITERIA - Platform bench dimension 200mm vertical steps and 600mm wide.
label | RELEVANT SECTION - Drawing number 0706-C-DRG-0011 Typical Platform Tie-In detail
label | VERIFYING DOCUMENT - Visual
label | ○ Dimensional check
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.7 - Select Fill Class A1 Select Fill Material CBR 15%
label | PROCEDURE / INSTRUCTION - Place maximum 200mm thick loose material and compact in layers.
label | ○ Compact to 98% SMDD.
label | ○ Trim final surface level for uniformity.
label | ACCEPTANCE CRITERIA - Fill compacted to 98% SMDD.
label | ○ Surface Tolerance ±5mm V/H
label | ○ Maximum ±10mm in 3m straight edge at any direction.
label | ○ OMC ±4.
label | ○ Minimum 4 test per lot.
label | RELEVANT SECTION - Drawing TC18368- C-DRG-0001 Earthworks Notes E9.
label | VERIFYING DOCUMENT - Survey Conformance Report for finish surface uniformity.
label | ○ NATA test report for Density and OMC
label | ○ 3200-0706-ITC-CE-001 Earthworks Select Fill
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.8 - Proof Roll
label | PROCEDURE / INSTRUCTION - Proof roll using either 7,000 litre single rear axle or 10,000 litre tandem rear axle water tanker
label | ACCEPTANCE CRITERIA - No perceptible surface deformation
label | RELEVANT SECTION - MRTS05 Cl 9.4.7
label | ○ Testing Method Q723
label | VERIFYING DOCUMENT -  Visual
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
section | STAGE 3: ITP CLOSE-OUT
checkpoint | 3.1 - Compilation of survey records
label | PROCEDURE / INSTRUCTION - Sub-contractor to provide survey records to Engineer for review and acceptance. Deviations or changes to AFC Design shall be highlighted to Engineer.
label | ACCEPTANCE CRITERIA - Provision of CAD file of Works.
label | RELEVANT SECTION - UGL 3200-0706- PLN-001 QMP Section 11.1.1
label | VERIFYING DOCUMENT -  As-Constructed drawing
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.2 - Develop Punchlist
label | PROCEDURE / INSTRUCTION - Walkdown and inspection of works and development of punch list with Engineer and or Supervisor.
label | ACCEPTANCE CRITERIA - Punchlist closed in a timely manner.
label | RELEVANT SECTION - UGL 3200-0706- PLN-001 QMP Section 9.7
label | VERIFYING DOCUMENT -  Master Punchlist Register
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.3 - Closeout of NCRs
label | PROCEDURE / INSTRUCTION - Any NCRs that have been raised during the progress of the works have been formally closed out and lessons have been captured.
label | ○ Refer to UGL Quality Management Plan.
label | ACCEPTANCE CRITERIA - NCRs close out in a timely manner.
label | RELEVANT SECTION - UGL 3200-0706- PLN-001 QMP Section 9.5
label | VERIFYING DOCUMENT -  NCR Closed, signed off.
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.4 - Changes captured and agreed within RFIs
label | PROCEDURE / INSTRUCTION - Any deviations to AFC Design or Contract Specifications are to be captured, recorded, and agreed via the Formal RFI process.
label | ACCEPTANCE CRITERIA - All RFI’s to be agreed or accepted in a timely manner.
label | RELEVANT SECTION - UGL 3200-0706- PLN-001 QMP Section 11.1.1
label | VERIFYING DOCUMENT -  Site RFI Register
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.5 - As Constructed records – Red Line Mark-Up (RLMU) Drawings.
label | PROCEDURE / INSTRUCTION - Sub-contractor to compile and record changes on AFC Drawings, to be issued to UGL Engineering via Teambinder.
label | ACCEPTANCE CRITERIA - AFC drawing stamped with As-Constructed Drawing, date and signed by Subcontractor/ Surveyor.
label | RELEVANT SECTION - UGL 3200-0706- PLN-001 QMP Section 11.1.1
label | VERIFYING DOCUMENT -  As-Constructed Drawing / RLMU drawing
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
section | ITP COMPLETION AND SIGN-OFF
checkpoint | ITP COMPLETION AND SIGN-OFF
textbox | S/C Representative
textbox | UGL Representative
textbox | Client Representative
holdpoint | Add Signatures
checklist | 3200-0706-ITP-CE-003 Pavement Base Layer | itp |  |  |  |  | 3200-0706-ITP-CE-003 Pavement Base Layer
section | STAGE 1: PREPARATION WORKS
checkpoint | 1.1 - Permits and Approvals
label | PROCEDURE / INSTRUCTION - Ensure Permits are in place including, but not limited to:
label | ○ Excavation Permits
label | ACCEPTANCE CRITERIA - NA
label | RELEVANT SECTION - NA
label | VERIFYING DOCUMENT - NA
label | VERIFICATION (SIGN AND DATE): S/C -
label | VERIFICATION (SIGN AND DATE): UGL -
label | VERIFICATION (SIGN AND DATE): Client -
checkpoint | 1.2 - CEMP and Emergency Response Plans
label | PROCEDURE / INSTRUCTION - Controls established within CEMP and ERP shall be adhered to throughout works.
label | ACCEPTANCE CRITERIA - 3200-0706-PLN-005 – CEMP
label | ○ 3200-0706-PLN-010 - ERP
label | RELEVANT SECTION - 0706-C-DRG-0012
label | ○ 0706-C-DRG-0013
label | ○ Erosion and Sedimentation Control Plan
label | VERIFYING DOCUMENT - Site Audits as works progress.
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 1.3 - Identification of underground services
label | PROCEDURE / INSTRUCTION - Use of DBYD and pothole to positively identify underground services.
label | ○ Use progress As-Constructed drawings for installed buried cables
label | ACCEPTANCE CRITERIA - NA
label | RELEVANT SECTION - UGL Safety Critical Risk Control – Excavation and Trenching
label | VERIFYING DOCUMENT - DBYD / Excavation Permit Survey (if required).
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 1.4 - Approval of Subcontractor SWMS
label | PROCEDURE / INSTRUCTION - Submission, review, and approval of all subcontractor SWMS for the works
label | ACCEPTANCE CRITERIA - SWMS Approved
label | RELEVANT SECTION - UGL-Contractor HSEQ Requirements
label | VERIFYING DOCUMENT - UGL SWMS Review Forms and approved SWMS.
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 1.5 - Conformance of Materials
label | PROCEDURE / INSTRUCTION - All delivered materials and procured items conform to project specification and AFC drawings.
label | ACCEPTANCE CRITERIA - As per Drawings and Specifications
label | RELEVANT SECTION - MRTS05 Type 2.1
label | VERIFYING DOCUMENT - Material Certificate
label | ○ Test Reports complying to Type 2.1 material by NATA accredited laboratory.
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 1.6 - Inspection Measuring and Test Equipment (IMTE) Registers
label | PROCEDURE / INSTRUCTION - Supply of all calibration certificates to the Engineer including but not limited to: Survey equipment
label | ACCEPTANCE CRITERIA - Visual
label | RELEVANT SECTION - UGL 3200-0706-PLN-001 QMP Section 9.8
label | VERIFYING DOCUMENT - Calibration Certificates.
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
section | STAGE 2: CONSTRUCTION WORKS
checkpoint | 2.1 - Setout of pad
label | PROCEDURE / INSTRUCTION - Registered Surveyor to set out pad with pegs and markers.
label | ○ Check surveyor marks against known structures, such as boundaries, fences
label | ACCEPTANCE CRITERIA - Drawing provided showing marked out areas and exclusion zones.
label | RELEVANT SECTION - Drawing Number: 0706-C-DRG-0003
label | ○ Drawing Number: 0706-C-DRG-0002 General Notes G8.
label | VERIFYING DOCUMENT - Survey complies with checks and contract drawings.
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.2 - Underlying ITP/ITC closed and signed off.
label | PROCEDURE / INSTRUCTION -  Verify ITC if closed and signed off.
label | ACCEPTANCE CRITERIA -  Signed off ITC document 3200- 0706-ITC-CE-002 Pavement Subbase Layer
label | RELEVANT SECTION - NA
label | VERIFYING DOCUMENT - Survey Conformance Report for finish surface uniformity
label | ○ 3200-0706-ITC-CE-002 Pavement Subbase Layer
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.3 - Base Layer (Class 2.1)
label | PROCEDURE / INSTRUCTION - Spread material and compact to maximum:
label | – 150mm Typical Battery Storage Platform
label | – 150mm Typical Sealed Road Pavement
label | – 150mm Typical Substation Platform
label | ○ Compact material to 100% SMDD.
label | ○ Minimum CBR 80%.
label | ○ Trim final surface level for uniformity within tolerance.
label | ACCEPTANCE CRITERIA - Material compacted to 100% at specified maximum thickness layer.
label | ○ CBR 80%
label | ○ Tolerances ±5mm
label | ○ Maximum ±5mm in 3m straight edge at any direction.
label | ○ Minimum 4 test per lot
label | RELEVANT SECTION - Drawing Number: 0706-C-DRG-0011
label | ○ MRTS05 Type 2.1 (Class 2.1)
label | VERIFYING DOCUMENT - Survey Conformance Report for finish surface uniformity
label | ○ SMDD material test report
label | ○ 3200-0706-ITC-CE-003 Pavement Base Layer
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.4 - Proof Rolling
label | PROCEDURE / INSTRUCTION - Proof roll using either 7,000 litre single rear axle or 10,000 litre tandem near axle water tanker
label | ACCEPTANCE CRITERIA - No perceptible surface deformation
label | RELEVANT SECTION - MRTS05 Cl 9.4.7
label | ○ Testing Method Q723
label | VERIFYING DOCUMENT -  Visual
label | VERIFICATION (SIGN AND DATE): S/C - H
label | VERIFICATION (SIGN AND DATE): UGL - H
label | VERIFICATION (SIGN AND DATE): Client - S
holdpoint | HOLD POINT
checkpoint | 2.5 - Finish Platform - Single size dressing layer
label | PROCEDURE / INSTRUCTION - Spread single gravel dressing layer minimum 100mm thick.
label | ○ Single size clean gravel and free of unwanted materials
label | ACCEPTANCE CRITERIA - Final surface free of loose material and properly clean.
label | ○ Visual and spread evenly.
label | RELEVANT SECTION - Drawing Number: 0706-C-DRG-0011 under Typical substation platform detail with gravel layer.
label | VERIFYING DOCUMENT - Visual and at random checking.
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
section | STAGE 3: ITP CLOSE-OUT
checkpoint | 3.1 - Compilation of survey records
label | PROCEDURE / INSTRUCTION - Sub-contractor to provide survey records to Engineer for review and acceptance. Deviations or changes to AFC Design shall be highlighted to Engineer.
label | ACCEPTANCE CRITERIA - Provision of CAD file of Works.
label | RELEVANT SECTION - UGL 3200-0706-PLN-001 QMP Section 11.1.1
label | VERIFYING DOCUMENT - As-Constructed drawing
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.2 - Develop Punchlist
label | PROCEDURE / INSTRUCTION - Walkdown and inspection of works and development of punch list with Engineer and or Supervisor.
label | ACCEPTANCE CRITERIA - Punchlist closed in a timely manner.
label | RELEVANT SECTION - UGL 3200-0706-PLN-001 QMP Section 9.7
label | VERIFYING DOCUMENT - Master Punchlist Register
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.3 - Closeout of NCRs
label | PROCEDURE / INSTRUCTION - Any NCRs that have been raised during the progress of the works have been formally closed out and lessons have been captured.
label | ○ Refer to UGL Quality Management Plan.
label | ACCEPTANCE CRITERIA - NCRs close out in a timely manner.
label | RELEVANT SECTION - UGL 3200-0706-PLN-001 QMP Section 9.5
label | VERIFYING DOCUMENT - NCR Closed, signed off.
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.4 - Changes captured and agreed within RFIs
label | PROCEDURE / INSTRUCTION - Any deviations to AFC Design or Contract Specifications are to be captured, recorded, and agreed via the Formal RFI process.
label | ACCEPTANCE CRITERIA - All RFI’s to be agreed or accepted in a timely manner.
label | RELEVANT SECTION - UGL 3200-0706-PLN-001 QMP Section 11.1.1
label | VERIFYING DOCUMENT - RFI Register
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
checkpoint | 3.5 - As Constructed records – Red Line Mark-Up (RLMU) Drawings.
label | PROCEDURE / INSTRUCTION - Sub-contractor to compile and record changes on AFC Drawings, to be issued to UGL Engineering via Teambinder.
label | ACCEPTANCE CRITERIA - NA
label | RELEVANT SECTION - UGL 3200-0706-PLN-001 QMP Section 11.1.1
label | VERIFYING DOCUMENT - As-Constructed Drawing / RLMU drawing
label | VERIFICATION (SIGN AND DATE): S/C - R
label | VERIFICATION (SIGN AND DATE): UGL - R
label | VERIFICATION (SIGN AND DATE): Client - S
section | ITP COMPLETION AND SIGN-OFF
checkpoint | ITP COMPLETION AND SIGN-OFF
textbox | S/C Representative
textbox | UGL Representative
textbox | Client Representative
holdpoint | Add Signatures
checklist | 13297-PLQ-CI-ITR02 BLD | itp |  |  |  |  | 13297-PLQ-CI-ITR02 BLD
section | Details
checkpoint | 1 - Concrete mix design submitted
label | Evidence or Record - Mix Design Code
label | Acceptance Criteria - GSC-010.1 Cl. 4.3
checkpoint | 2 - Placement method submitted
label | Evidence or Record - Email Reference
label | Acceptance Criteria - GSC-010.1 Section 9.2
checkpoint | 3 - Curing methods submitted
label | Evidence or Record - Email Reference
label | Acceptance Criteria - GSC-010.1 Section 12.1
checkpoint | 4 - Approval for earlier stripping or loading
label | Evidence or Record -
label | Acceptance Criteria - GSC-010.1 Section 11.2
checkpoint | 5 - Spare Compaction equipment on site suitable for the proposed task.
label | Evidence or Record - Visual
label | Acceptance Criteria - GSC-010.1 Section 9.3
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 6 - Details of supplied concrete (Actual)
textbox | ○ Batched time
textbox | ○ Arrival time on site
textbox | ○ Slump
textbox | ○ Concrete temp
textbox | ○ Ambient temp
textbox | Evidence or Record - Load No
textbox | Acceptance Criteria - Docket No
checkpoint | 7 - Time of last load placed
textbox | Acceptance Criteria - Docket No
checkpoint | Test cylinders taken, placed and protected on site by testing authority
textbox | Print Name and Company:
holdpoint | Sign:
checkpoint | 8 - Final check of formwork and cast in items, such as hold down bolts.
label | Evidence or Record - Visual
label | Acceptance Criteria - GSC-010.1 Section 7.1
checkpoint | 9 - Approved curing agents applied
label | Evidence or Record - Visual
label | Acceptance Criteria - GSC-010.1 Section 12.2
checkpoint | 10 - New concrete protected from inclement weather
label | Evidence or Record - Visual / Photo
label | Acceptance Criteria - GSC-010.1 Section 9.4
checkpoint | 11 - Level checks undertaken prior to concrete set stage
label | Evidence or Record - Visual
label | Acceptance Criteria - AFC Drawing
holdpoint | Final Hold Point Release (PLQ Representative)
checklist | 13297-PLQ-CI-ITR06 Subgrade - Lot 1 | itp |  |  |  |  | 13297-PLQ-CI-ITR06 Subgrade - Lot 1
section | Details
checkpoint | 1 - Set out of Road/Structure confirmed
label | Evidence or Record - Survey
label | Acceptance Criteria - SSC-413/414/420 Cl 2.3
checkpoint | 2 - Sub-grade levels confirmed
label | Evidence or Record - Visual
label | Acceptance Criteria - SSC-413/414/420 Cl 2.3
checkpoint | 3 - Compaction requirements confirmed
label | Evidence or Record - Test Results
label | Acceptance Criteria - SSC-413/414/420 Cl 2.3
checkpoint | 4 - Check of existing underground services undertaken
label | Evidence or Record - Visual/Wanding
label | Acceptance Criteria - SSC-414 Cl 2.2
checkpoint | 5 - Ground surface treatment undertaken and completed as per specification
label | Evidence or Record - Visual/Test Results
label | Acceptance Criteria - SSC-420 Cl 2.6
checkpoint | 6 - Insitu material has been scarified, moisture corrected and compacted to a depth of 200mm
label | Evidence or Record - Visual
label | Acceptance Criteria - SSC-413 Cl 2.3, SSC-420 Cl 2.6
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 7 - Any replacement sub-grade material used has been approved for use
label | Evidence or Record - Report/Email
label | Acceptance Criteria - SSC-420 Cl 2.8
checkpoint | 8 - Geometric checks undertaken prior to required testing
label | Evidence or Record - Visual/Survey
label | Acceptance Criteria - SSC-420 Cl 2.3
checkpoint | 9 - List the required type of testing and the number of tests that have been undertaken
label | Evidence or Record - Visual/Report
label | Acceptance Criteria - SSC-413 Cl 2.3
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 10 - Test rolling undertaken
label | Evidence or Record - Visual
label | Acceptance Criteria - SSC-413 Cl 2.3
holdpoint | Final Hold Point Release (PLQ Representative)
checklist | 13297-PLQ-CI-ITR07 Road Gravels - Lot 1 | itp |  |  |  |  | 13297-PLQ-CI-ITR07 Road Gravels - Lot 1
section | Details
checkpoint | 1 - Material submission approved
dropdown | (Select layer type) | Sub-Base,Base,Capping layer
label | Evidence or Record - Email / Report
label | Acceptance Criteria - SSC413 Cl 2.2, SSC420 Cl 2.8
checkpoint | 2 - Set out of road/pavement confirmed
label | Evidence or Record - Survey / Visual
label | Acceptance Criteria - IFC
checkpoint | 3 - Check of existing underground services
label | Evidence or Record - Permit #
label | Acceptance Criteria - Excavation Permit
checkpoint | 4 - Confirmation of required design thickness for this compacted layer
textbox | (Record layer thickness)
label | Evidence or Record - Visual / Photo
label | Acceptance Criteria - IFC
checkpoint | 5 - Finished levels confirmed for this layer
label | Evidence or Record - Visual / Photo
label | Acceptance Criteria - IFC
checkpoint | 6 - Approval to place over underlying layers
label | Evidence or Record - Visual / Report
label | Acceptance Criteria - SSC413 Cl 2.3
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 7 - Existing surface lightly scarified and moisture corrected prior to placement of next layer
label | Evidence or Record - Visual / Photo
label | Acceptance Criteria - SSC413 Cl 2.3
checkpoint | 8 - Record required compaction test value and type
label | Evidence or Record - Test Report
label | Acceptance Criteria - SSC413 Cl 2.3
checkpoint | 9 - List any re-work or replacement of this layer (i.e.: Soft spot removal)
label | Evidence or Record - Visual / Photo
label | Acceptance Criteria - SSC413 Cl 2.3
checkpoint | 10 - Check line/level of completed layer prior to testing
label | Evidence or Record - Survey / Visual
label | Acceptance Criteria - SSC413 Cl 2.3
checkpoint | 11 - Test results forwarded to PLQ
label | Evidence or Record - Email / Report
label | Acceptance Criteria - SSC413 Cl 2.3
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 12 - Test rolling undertaken
label | Evidence or Record - Visual / Photo
label | Acceptance Criteria - SSC413 Cl 2.4
holdpoint | Final Hold Point Release (PLQ Representative)
checklist | 13297-PLQ-CI-ITR14 Bulk Earthworks - Lot 1 | itp |  |  |  |  | 13297-PLQ-CI-ITR14 Bulk Earthworks - Lot 1
section | Details
checkpoint | 1 - GTIA RPEQ’s details responsible for the all Earthworks activities, submitted to PLQ
label | Evidence or Record - Email
label | Acceptance Criteria - SSC-420 Cl. 2.2
checkpoint | 2 - Certification of all imported materials submitted for approval
label | Evidence or Record - Email/Report
label | Acceptance Criteria - SSC-420 Cl. 2.8.1
checkpoint | 3 - Stockpile areas not shown on AFC drawings have been agreed by PLQ
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-420 Cl. 2.16
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 4 - Permanent and temporary survey control shown on AFC drawings has been installed with details submitted to PLQ
label | Evidence or Record - Email/Visual
label | Acceptance Criteria - SSC-420 Cl. 2.3.2, SSC-426 Cl. 2.8.8
checkpoint | 5 - Prior to any clearing the limits of work have been clearly marked out
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-414 Cl. 2.2.1
holdpoint | Witness Point Required (PLQ Representative)
checkpoint | 6 - Existing topsoil has been treated prior to removal
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-420 Cl. 2.16
checkpoint | 7 - After the removal of topsoil inspections will be carried out
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-420 Cl. 2.5
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 8 - Areas of rock have been over excavated
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-420 Cl. 2.11
checkpoint | 9 - Insitu material treated and compacted prior to filling
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-420 Cl. 2.6.3
holdpoint | Hold Point Release Required (PLQ Representative)
checkpoint | 10 - All fill layers to be tested and inspected by PLQ
label | Evidence or Record - Visual/Photo/Report
label | Acceptance Criteria - SSC-420 Cl. 2.9
holdpoint | Witness Point Required (PLQ Representative)
checkpoint | 11 - Each layer lightly scarified before placement of next layer
label | Evidence or Record - Visual/Photo
label | Acceptance Criteria - SSC-420 Cl. 2.9
checkpoint | 12 - Final layer inspected by PLQ: prior to inspection all test results to be submitted to PLQ
label | Evidence or Record - Visual/Photo/Report
label | Acceptance Criteria - SSC-420 Cl. 2.9
holdpoint | Final Hold Point Release (PLQ Representative)