## Sheet1
1.1 | Permits and Approvals | Ensure Permits are in place including, but not limited to:  Excavation Permits | NA | NA | NA |  |  |  | 1.1 - Permits and Approvals | PROCEDURE / INSTRUCTION - Ensure Permits are in place including, but not limited to:  Excavation Permits | ACCEPTANCE CRITERIA - NA | RELEVANT SECTION - NA | VERIFYING DOCUMENT - NA | VERIFICATION (SIGN AND DATE): S/C - | VERIFICATION (SIGN AND DATE): UGL - | VERIFICATION (SIGN AND DATE): Client - | 1.1 - Permits and Approvals
1.2 | CEMP and Emergency Response Plans | Controls established within CEMP and ERP shall be adhered to throughout works. | 3200-0706-PLN-005 – CEMP 3200-0706-PLN-010 - ERP | 0706-C-DRG-0012 0706-C-DRG-0013 Erosion and Sedimentation Control Plan | Site Audits as works progress. | R | R | S | 1.2 - CEMP and Emergency Response Plans | PROCEDURE / INSTRUCTION - Controls established within CEMP and ERP shall be adhered to throughout works. | ACCEPTANCE CRITERIA - 3200-0706-PLN-005 – CEMP 3200-0706-PLN-010 - ERP | RELEVANT SECTION - 0706-C-DRG-0012 0706-C-DRG-0013 Erosion and Sedimentation Control Plan | VERIFYING DOCUMENT - Site Audits as works progress. | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | PROCEDURE / INSTRUCTION - Ensure Permits are in place including, but not limited to:  Excavation Permits
1.3 | Identification of underground services | Use of DBYD and pothole to positively identify underground services. Use progress As-Constructed drawings for installed buried cables | NA | UGL Safety Critical Risk Control – Excavation and Trenching | DBYD / Excavation Permit Survey (if required). | H | H | S | 1.3 - Identification of underground services | PROCEDURE / INSTRUCTION - Use of DBYD and pothole to positively identify underground services. Use progress As-Constructed drawings for installed buried cables | ACCEPTANCE CRITERIA - NA | RELEVANT SECTION - UGL Safety Critical Risk Control – Excavation and Trenching | VERIFYING DOCUMENT - DBYD / Excavation Permit Survey (if required). | VERIFICATION (SIGN AND DATE): S/C - H | VERIFICATION (SIGN AND DATE): UGL - H | VERIFICATION (SIGN AND DATE): Client - S | ACCEPTANCE CRITERIA - NA
1.4 | Approval of Subcontractor SWMS | Submission, review, and approval of all subcontractor SWMS for the works | SWMS Approved | UGL-Contractor HSEQ Requirements | UGL SWMS Review Forms and approved SWMS. | H | H | S | 1.4 - Approval of Subcontractor SWMS | PROCEDURE / INSTRUCTION - Submission, review, and approval of all subcontractor SWMS for the works | ACCEPTANCE CRITERIA - SWMS Approved | RELEVANT SECTION - UGL-Contractor HSEQ Requirements | VERIFYING DOCUMENT - UGL SWMS Review Forms and approved SWMS. | VERIFICATION (SIGN AND DATE): S/C - H | VERIFICATION (SIGN AND DATE): UGL - H | VERIFICATION (SIGN AND DATE): Client - S | RELEVANT SECTION - NA
1.5 | Conformance of Materials | All delivered materials and procured items conform to project specification and AFC drawings. | As per Drawings and Specifications |  MRTS05 Type 2.1 |  Material Certificate  Test Reports complying to Type 2.1 material by NATA accredited laboratory. | R | R | S | 1.5 - Conformance of Materials | PROCEDURE / INSTRUCTION - All delivered materials and procured items conform to project specification and AFC drawings. | ACCEPTANCE CRITERIA - As per Drawings and Specifications | RELEVANT SECTION -  MRTS05 Type 2.1 | VERIFYING DOCUMENT -  Material Certificate  Test Reports complying to Type 2.1 material by NATA accredited laboratory. | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | VERIFYING DOCUMENT - NA
1.6 | Inspection Measuring and Test Equipment (IMTE) Registers | Supply of all calibration certificates to the Engineer including but not limited to: Survey equipment | Visual | UGL 3200-0706-PLN- 001 QMP Section 9.8 | Calibration Certificates. | R | R | S | 1.6 - Inspection Measuring and Test Equipment (IMTE) Registers | PROCEDURE / INSTRUCTION - Supply of all calibration certificates to the Engineer including but not limited to: Survey equipment | ACCEPTANCE CRITERIA - Visual | RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 9.8 | VERIFYING DOCUMENT - Calibration Certificates. | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | VERIFICATION (SIGN AND DATE): S/C -
2.1 | Setout of pad |  Registered Surveyor to set out pad with pegs and markers.  Check surveyor marks against known structures, such as boundaries, fences | Drawing provided showing marked out areas and exclusion zones. |  Drawing Number: 0706-C-DRG-0003  Drawing Number: 0706-C-DRG-0002 General Notes G8. | Survey complies with checks and contract drawings. | H | H | S | 2.1 - Setout of pad | PROCEDURE / INSTRUCTION -  Registered Surveyor to set out pad with pegs and markers.  Check surveyor marks against known structures, such as boundaries, fences | ACCEPTANCE CRITERIA - Drawing provided showing marked out areas and exclusion zones. | RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0003  Drawing Number: 0706-C-DRG-0002 General Notes G8. | VERIFYING DOCUMENT - Survey complies with checks and contract drawings. | VERIFICATION (SIGN AND DATE): S/C - H | VERIFICATION (SIGN AND DATE): UGL - H | VERIFICATION (SIGN AND DATE): Client - S | VERIFICATION (SIGN AND DATE): UGL -
2.2 | Underlying ITP/ITC closed and signed off. |  Verify ITC if closed and signed off. |  Signed off ITC document 3200- 0706-ITC-CE-002 Pavement Subbase Layer | NA |  Survey Conformance Report for finish surface uniformity  3200-0706-ITC-CE-002 Pavement Subbase Layer | H | H | S | 2.2 - Underlying ITP/ITC closed and signed off. | PROCEDURE / INSTRUCTION -  Verify ITC if closed and signed off. | ACCEPTANCE CRITERIA -  Signed off ITC document 3200- 0706-ITC-CE-002 Pavement Subbase Layer | RELEVANT SECTION - NA | VERIFYING DOCUMENT -  Survey Conformance Report for finish surface uniformity  3200-0706-ITC-CE-002 Pavement Subbase Layer | VERIFICATION (SIGN AND DATE): S/C - H | VERIFICATION (SIGN AND DATE): UGL - H | VERIFICATION (SIGN AND DATE): Client - S | VERIFICATION (SIGN AND DATE): Client -
2.3 | Base Layer (Class 2.1) |  Spread material and compact to maximum: - 150mm Typical Battery Storage Platform - 150mm Typical Sealed Road Pavement - 150mm Typical Substation Platform  Compact material to 100% SMDD.  Minimum CBR 80%.  Trim final surface level for uniformity within tolerance. |  Material compacted to 100% at specified maximum thickness layer.  CBR 80%  Tolerances ±5mm  Maximum ±5mm in 3m straight edge at any direction.  Minimum 4 test per lot |  Drawing Number: 0706-C-DRG-0011  MRTS05 Type 2.1 (Class 2.1) |  Survey Conformance Report for finish surface uniformity  SMDD material test report  3200-0706-ITC-CE-003 Pavement Base Layer | H | H | S | 2.3 - Base Layer (Class 2.1) | PROCEDURE / INSTRUCTION -  Spread material and compact to maximum: - 150mm Typical Battery Storage Platform - 150mm Typical Sealed Road Pavement - 150mm Typical Substation Platform  Compact material to 100% SMDD.  Minimum CBR 80%.  Trim final surface level for uniformity within tolerance. | ACCEPTANCE CRITERIA -  Material compacted to 100% at specified maximum thickness layer.  CBR 80%  Tolerances ±5mm  Maximum ±5mm in 3m straight edge at any direction.  Minimum 4 test per lot | RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0011  MRTS05 Type 2.1 (Class 2.1) | VERIFYING DOCUMENT -  Survey Conformance Report for finish surface uniformity  SMDD material test report  3200-0706-ITC-CE-003 Pavement Base Layer | VERIFICATION (SIGN AND DATE): S/C - H | VERIFICATION (SIGN AND DATE): UGL - H | VERIFICATION (SIGN AND DATE): Client - S | 1.2 - CEMP and Emergency Response Plans
2.4 | Proof Rolling |  Proof roll using either 7,000 litre single rear axle or 10,000 litre tandem near axle water tanker |  No perceptible surface deformation |  MRTS05 Cl 9.4.7  Testing Method Q723 |  Visual | H | H | S | 2.4 - Proof Rolling | PROCEDURE / INSTRUCTION -  Proof roll using either 7,000 litre single rear axle or 10,000 litre tandem near axle water tanker | ACCEPTANCE CRITERIA -  No perceptible surface deformation | RELEVANT SECTION -  MRTS05 Cl 9.4.7  Testing Method Q723 | VERIFYING DOCUMENT -  Visual | VERIFICATION (SIGN AND DATE): S/C - H | VERIFICATION (SIGN AND DATE): UGL - H | VERIFICATION (SIGN AND DATE): Client - S | PROCEDURE / INSTRUCTION - Controls established within CEMP and ERP shall be adhered to throughout works.
2.5 | Finish Platform -Single size dressing layer |  Spread single gravel dressing layer minimum 100mm thick.  Single size clean gravel and free of unwanted materials |  Final surface free of loose material and properly clean.  Visual and spread evenly. |  Drawing Number: 0706-C-DRG-0011 under Typical substation platform detail with gravel layer. |  Visual and at random checking. | R | R | S | 2.5 - Finish Platform -Single size dressing layer | PROCEDURE / INSTRUCTION -  Spread single gravel dressing layer minimum 100mm thick.  Single size clean gravel and free of unwanted materials | ACCEPTANCE CRITERIA -  Final surface free of loose material and properly clean.  Visual and spread evenly. | RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0011 under Typical substation platform detail with gravel layer. | VERIFYING DOCUMENT -  Visual and at random checking. | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | ACCEPTANCE CRITERIA - 3200-0706-PLN-005 – CEMP 3200-0706-PLN-010 - ERP
3.1 | Compilation of survey records | Sub-contractor to provide survey records to Engineer for review and acceptance. Deviations or changes to AFC Design shall be highlighted to Engineer. | Provision of CAD file of Works. | UGL 3200-0706-PLN- 001 QMP Section 11.1.1 | As-Constructed drawing | R | R | S | 3.1 - Compilation of survey records | PROCEDURE / INSTRUCTION - Sub-contractor to provide survey records to Engineer for review and acceptance. Deviations or changes to AFC Design shall be highlighted to Engineer. | ACCEPTANCE CRITERIA - Provision of CAD file of Works. | RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 11.1.1 | VERIFYING DOCUMENT - As-Constructed drawing | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | RELEVANT SECTION - 0706-C-DRG-0012 0706-C-DRG-0013 Erosion and Sedimentation Control Plan
3.2 | Develop Punchlist | Walkdown and inspection of works and development of punch list with Engineer and or Supervisor. | Punchlist closed in a timely manner. | UGL 3200-0706-PLN- 001 QMP Section 9.7 | Master Punchlist Register | R | R | S | 3.2 - Develop Punchlist | PROCEDURE / INSTRUCTION - Walkdown and inspection of works and development of punch list with Engineer and or Supervisor. | ACCEPTANCE CRITERIA - Punchlist closed in a timely manner. | RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 9.7 | VERIFYING DOCUMENT - Master Punchlist Register | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | VERIFYING DOCUMENT - Site Audits as works progress.
3.3 | Closeout of NCRs | Any NCRs that have been raised during the progress of the works have been formally closed out and lessons have been captured. Refer to UGL Quality Management Plan. | NCRs close out in a timely manner. | UGL 3200-0706-PLN- 001 QMP Section 9.5 | NCR Closed, signed off. | R | R | S | 3.3 - Closeout of NCRs | PROCEDURE / INSTRUCTION - Any NCRs that have been raised during the progress of the works have been formally closed out and lessons have been captured. Refer to UGL Quality Management Plan. | ACCEPTANCE CRITERIA - NCRs close out in a timely manner. | RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 9.5 | VERIFYING DOCUMENT - NCR Closed, signed off. | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | VERIFICATION (SIGN AND DATE): S/C - R
3.4 | Changes captured and agreed within RFIs | Any deviations to AFC Design or Contract Specifications are to be captured, recorded, and agreed via the Formal RFI process. | All RFI’s to be agreed or accepted in a timely manner. | UGL 3200-0706-PLN- 001 QMP Section 11.1.1 | RFI Register | R | R | S | 3.4 - Changes captured and agreed within RFIs | PROCEDURE / INSTRUCTION - Any deviations to AFC Design or Contract Specifications are to be captured, recorded, and agreed via the Formal RFI process. | ACCEPTANCE CRITERIA - All RFI’s to be agreed or accepted in a timely manner. | RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 11.1.1 | VERIFYING DOCUMENT - RFI Register | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | VERIFICATION (SIGN AND DATE): UGL - R
3.5 | As Constructed records – Red Line Mark-Up (RLMU) Drawings. | Sub-contractor to compile and record changes on AFC Drawings, to be issued to UGL Engineering via Teambinder. | NA | UGL 3200-0706-PLN- 001 QMP Section 11.1.1 | As-Constructed Drawing / RLMU drawing | R | R | S | 3.5 - As Constructed records – Red Line Mark-Up (RLMU) Drawings. | PROCEDURE / INSTRUCTION - Sub-contractor to compile and record changes on AFC Drawings, to be issued to UGL Engineering via Teambinder. | ACCEPTANCE CRITERIA - NA | RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 11.1.1 | VERIFYING DOCUMENT - As-Constructed Drawing / RLMU drawing | VERIFICATION (SIGN AND DATE): S/C - R | VERIFICATION (SIGN AND DATE): UGL - R | VERIFICATION (SIGN AND DATE): Client - S | VERIFICATION (SIGN AND DATE): Client - S
1.3 - Identification of underground services
PROCEDURE / INSTRUCTION - Use of DBYD and pothole to positively identify underground services. Use progress As-Constructed drawings for installed buried cables
ACCEPTANCE CRITERIA - NA
RELEVANT SECTION - UGL Safety Critical Risk Control – Excavation and Trenching
VERIFYING DOCUMENT - DBYD / Excavation Permit Survey (if required).
VERIFICATION (SIGN AND DATE): S/C - H
VERIFICATION (SIGN AND DATE): UGL - H
VERIFICATION (SIGN AND DATE): Client - S
1.4 - Approval of Subcontractor SWMS
PROCEDURE / INSTRUCTION - Submission, review, and approval of all subcontractor SWMS for the works
ACCEPTANCE CRITERIA - SWMS Approved
RELEVANT SECTION - UGL-Contractor HSEQ Requirements
VERIFYING DOCUMENT - UGL SWMS Review Forms and approved SWMS.
VERIFICATION (SIGN AND DATE): S/C - H
VERIFICATION (SIGN AND DATE): UGL - H
VERIFICATION (SIGN AND DATE): Client - S
1.5 - Conformance of Materials
PROCEDURE / INSTRUCTION - All delivered materials and procured items conform to project specification and AFC drawings.
ACCEPTANCE CRITERIA - As per Drawings and Specifications
RELEVANT SECTION -  MRTS05 Type 2.1
VERIFYING DOCUMENT -  Material Certificate  Test Reports complying to Type 2.1 material by NATA accredited laboratory.
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
1.6 - Inspection Measuring and Test Equipment (IMTE) Registers
PROCEDURE / INSTRUCTION - Supply of all calibration certificates to the Engineer including but not limited to: Survey equipment
ACCEPTANCE CRITERIA - Visual
RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 9.8
VERIFYING DOCUMENT - Calibration Certificates.
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
2.1 - Setout of pad
PROCEDURE / INSTRUCTION -  Registered Surveyor to set out pad with pegs and markers.  Check surveyor marks against known structures, such as boundaries, fences
ACCEPTANCE CRITERIA - Drawing provided showing marked out areas and exclusion zones.
RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0003  Drawing Number: 0706-C-DRG-0002 General Notes G8.
VERIFYING DOCUMENT - Survey complies with checks and contract drawings.
VERIFICATION (SIGN AND DATE): S/C - H
VERIFICATION (SIGN AND DATE): UGL - H
VERIFICATION (SIGN AND DATE): Client - S
2.2 - Underlying ITP/ITC closed and signed off.
PROCEDURE / INSTRUCTION -  Verify ITC if closed and signed off.
ACCEPTANCE CRITERIA -  Signed off ITC document 3200- 0706-ITC-CE-002 Pavement Subbase Layer
RELEVANT SECTION - NA
VERIFYING DOCUMENT -  Survey Conformance Report for finish surface uniformity  3200-0706-ITC-CE-002 Pavement Subbase Layer
VERIFICATION (SIGN AND DATE): S/C - H
VERIFICATION (SIGN AND DATE): UGL - H
VERIFICATION (SIGN AND DATE): Client - S
2.3 - Base Layer (Class 2.1)
PROCEDURE / INSTRUCTION -  Spread material and compact to maximum: - 150mm Typical Battery Storage Platform - 150mm Typical Sealed Road Pavement - 150mm Typical Substation Platform  Compact material to 100% SMDD.  Minimum CBR 80%.  Trim final surface level for uniformity within tolerance.
ACCEPTANCE CRITERIA -  Material compacted to 100% at specified maximum thickness layer.  CBR 80%  Tolerances ±5mm  Maximum ±5mm in 3m straight edge at any direction.  Minimum 4 test per lot
RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0011  MRTS05 Type 2.1 (Class 2.1)
VERIFYING DOCUMENT -  Survey Conformance Report for finish surface uniformity  SMDD material test report  3200-0706-ITC-CE-003 Pavement Base Layer
VERIFICATION (SIGN AND DATE): S/C - H
VERIFICATION (SIGN AND DATE): UGL - H
VERIFICATION (SIGN AND DATE): Client - S
2.4 - Proof Rolling
PROCEDURE / INSTRUCTION -  Proof roll using either 7,000 litre single rear axle or 10,000 litre tandem near axle water tanker
ACCEPTANCE CRITERIA -  No perceptible surface deformation
RELEVANT SECTION -  MRTS05 Cl 9.4.7  Testing Method Q723
VERIFYING DOCUMENT -  Visual
VERIFICATION (SIGN AND DATE): S/C - H
VERIFICATION (SIGN AND DATE): UGL - H
VERIFICATION (SIGN AND DATE): Client - S
2.5 - Finish Platform -Single size dressing layer
PROCEDURE / INSTRUCTION -  Spread single gravel dressing layer minimum 100mm thick.  Single size clean gravel and free of unwanted materials
ACCEPTANCE CRITERIA -  Final surface free of loose material and properly clean.  Visual and spread evenly.
RELEVANT SECTION -  Drawing Number: 0706-C-DRG-0011 under Typical substation platform detail with gravel layer.
VERIFYING DOCUMENT -  Visual and at random checking.
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
3.1 - Compilation of survey records
PROCEDURE / INSTRUCTION - Sub-contractor to provide survey records to Engineer for review and acceptance. Deviations or changes to AFC Design shall be highlighted to Engineer.
ACCEPTANCE CRITERIA - Provision of CAD file of Works.
RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 11.1.1
VERIFYING DOCUMENT - As-Constructed drawing
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
3.2 - Develop Punchlist
PROCEDURE / INSTRUCTION - Walkdown and inspection of works and development of punch list with Engineer and or Supervisor.
ACCEPTANCE CRITERIA - Punchlist closed in a timely manner.
RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 9.7
VERIFYING DOCUMENT - Master Punchlist Register
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
3.3 - Closeout of NCRs
PROCEDURE / INSTRUCTION - Any NCRs that have been raised during the progress of the works have been formally closed out and lessons have been captured. Refer to UGL Quality Management Plan.
ACCEPTANCE CRITERIA - NCRs close out in a timely manner.
RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 9.5
VERIFYING DOCUMENT - NCR Closed, signed off.
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
3.4 - Changes captured and agreed within RFIs
PROCEDURE / INSTRUCTION - Any deviations to AFC Design or Contract Specifications are to be captured, recorded, and agreed via the Formal RFI process.
ACCEPTANCE CRITERIA - All RFI’s to be agreed or accepted in a timely manner.
RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 11.1.1
VERIFYING DOCUMENT - RFI Register
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S
3.5 - As Constructed records – Red Line Mark-Up (RLMU) Drawings.
PROCEDURE / INSTRUCTION - Sub-contractor to compile and record changes on AFC Drawings, to be issued to UGL Engineering via Teambinder.
ACCEPTANCE CRITERIA - NA
RELEVANT SECTION - UGL 3200-0706-PLN- 001 QMP Section 11.1.1
VERIFYING DOCUMENT - As-Constructed Drawing / RLMU drawing
VERIFICATION (SIGN AND DATE): S/C - R
VERIFICATION (SIGN AND DATE): UGL - R
VERIFICATION (SIGN AND DATE): Client - S