## Sheet1
1 | GTIA RPEQ’s details responsible for the all Earthworks activities, submitted to PLQ | Email | SSC-420 Cl. 2.2 | 1 - GTIA RPEQ’s details responsible for the all Earthworks activities, submitted to PLQ | Evidence or Record - Email | Acceptance Criteria - SSC-420 Cl. 2.2 | 1 - GTIA RPEQ’s details responsible for the all Earthworks activities, submitted to PLQ
2 | Certification of all imported materials submitted for approval | Email/Report | SSC-420 Cl. 2.8.1 | 2 - Certification of all imported materials submitted for approval | Evidence or Record - Email/Report | Acceptance Criteria - SSC-420 Cl. 2.8.1 | Evidence or Record - Email
3 | Stockpile areas not shown on AFC drawings have been agreed by PLQ | Visual/Photo | SSC-420 Cl. 2.16 | 3 - Stockpile areas not shown on AFC drawings have been agreed by PLQ | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-420 Cl. 2.16 | Acceptance Criteria - SSC-420 Cl. 2.2
4 | Permanent and temporary survey control shown on AFC drawings has been installed with details submitted to PLQ | Email/Visual | SSC-420 Cl. 2.3.2, SSC-426 Cl. 2.8.8 | 4 - Permanent and temporary survey control shown on AFC drawings has been installed with details submitted to PLQ | Evidence or Record - Email/Visual | Acceptance Criteria - SSC-420 Cl. 2.3.2, SSC-426 Cl. 2.8.8 | 2 - Certification of all imported materials submitted for approval
5 | Prior to any clearing the limits of work have been clearly marked out | Visual/Photo | SSC-414 Cl. 2.2.1 | 5 - Prior to any clearing the limits of work have been clearly marked out | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-414 Cl. 2.2.1 | Evidence or Record - Email/Report
6 | Existing topsoil has been treated prior to removal | Visual/Photo | SSC-420 Cl. 2.16 | 6 - Existing topsoil has been treated prior to removal | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-420 Cl. 2.16 | Acceptance Criteria - SSC-420 Cl. 2.8.1
7 | After the removal of topsoil inspections will be carried out | Visual/Photo | SSC-420 Cl. 2.5 | 7 - After the removal of topsoil inspections will be carried out | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-420 Cl. 2.5 | 3 - Stockpile areas not shown on AFC drawings have been agreed by PLQ
8 | Areas of rock have been over excavated | Visual/Photo | SSC-420 Cl. 2.11 | 8 - Areas of rock have been over excavated | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-420 Cl. 2.11 | Evidence or Record - Visual/Photo
9 | Insitu material treated and compacted prior to filling | Visual/Photo | SSC-420 Cl. 2.6.3 | 9 - Insitu material treated and compacted prior to filling | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-420 Cl. 2.6.3 | Acceptance Criteria - SSC-420 Cl. 2.16
10 | All fill layers to be tested and inspected by PLQ | Visual/Photo/Report | SSC-420 Cl. 2.9 | 10 - All fill layers to be tested and inspected by PLQ | Evidence or Record - Visual/Photo/Report | Acceptance Criteria - SSC-420 Cl. 2.9 | 4 - Permanent and temporary survey control shown on AFC drawings has been installed with details submitted to PLQ
11 | Each layer lightly scarified before placement of next layer | Visual/Photo | SSC-420 Cl. 2.9 | 11 - Each layer lightly scarified before placement of next layer | Evidence or Record - Visual/Photo | Acceptance Criteria - SSC-420 Cl. 2.9 | Evidence or Record - Email/Visual
12 | Final layer inspected by PLQ: prior to inspection all test results to be submitted to PLQ | Visual/Photo/Report | SSC-420 Cl. 2.9 | 12 - Final layer inspected by PLQ: prior to inspection all test results to be submitted to PLQ | Evidence or Record - Visual/Photo/Report | Acceptance Criteria - SSC-420 Cl. 2.9 | Acceptance Criteria - SSC-420 Cl. 2.3.2, SSC-426 Cl. 2.8.8
5 - Prior to any clearing the limits of work have been clearly marked out
Evidence or Record - Visual/Photo
Acceptance Criteria - SSC-414 Cl. 2.2.1
6 - Existing topsoil has been treated prior to removal
Evidence or Record - Visual/Photo
Acceptance Criteria - SSC-420 Cl. 2.16
7 - After the removal of topsoil inspections will be carried out
Evidence or Record - Visual/Photo
Acceptance Criteria - SSC-420 Cl. 2.5
8 - Areas of rock have been over excavated
Evidence or Record - Visual/Photo
Acceptance Criteria - SSC-420 Cl. 2.11
9 - Insitu material treated and compacted prior to filling
Evidence or Record - Visual/Photo
Acceptance Criteria - SSC-420 Cl. 2.6.3
10 - All fill layers to be tested and inspected by PLQ
Evidence or Record - Visual/Photo/Report
Acceptance Criteria - SSC-420 Cl. 2.9
11 - Each layer lightly scarified before placement of next layer
Evidence or Record - Visual/Photo
Acceptance Criteria - SSC-420 Cl. 2.9
12 - Final layer inspected by PLQ: prior to inspection all test results to be submitted to PLQ
Evidence or Record - Visual/Photo/Report
Acceptance Criteria - SSC-420 Cl. 2.9