## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 966bc36c-30c4-4479-951d-4aa845e89d05 |  | checklist | Completion Documentation |  |  |  |  | Yes | Add Completion Documentation | 00a7f8ff-b5ca-46b5-b39d-b43ae6798119
checkpoint-status | 828d96d0-42f5-40ee-9656-dd905b00ff67 |  | checkpoint | Producer Statements (PS3) - Doors, Finishing Lines and Hardware Installation - attached
checkpoint-status | a122fb0e-17d5-448b-833a-e4e11f805246 |  | checkpoint | Product warranty attached
checkpoint-status | 6ad5095f-9375-4f70-a378-83d6238daeaa |  | checkpoint | Additional documents attached (if required)
checklist-sectioned | 76bb7e56-360c-4e84-8369-1eb06aad91f7 |  | checklist | ST - S - Insitu Stitch Joints |  |  |  |  | Yes | B07 - ST - S - Insitu Stitch Joints | 027cc7cb-0443-4e40-b837-eaabbd9c569b
checkpoint-group | 3d9dd0d2-b9eb-4c4e-b1b5-7a402620845e |  | section | Pour Details
checkpoint-status | 60cb0dbe-6d0b-49f9-8726-9df78eaa9481 |  | checkpoint | Pour Details:
text | e9de8479-7495-5801-82d1-265526fa9cd3 |  | textbox | Area to be poured:
text | c10dbd85-cebe-5925-9334-0fcb1d4448f5 |  | textbox | Date of pour:
checkpoint-status | f3718ed3-0623-460e-ace8-4d473d3bbfc8 |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group | 6b49bd5d-b7c0-4ce2-96ce-e0eb4ed9d0d0 |  | section | Formwork
checkpoint-status | 2aa6f0d1-284b-465d-9e9c-8a71faf769b3 |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status | 57b9eec7-b7f9-4d8b-a2b9-0e1a13e5ed27 |  | checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
checkpoint-group | 8d51dd27-0272-4bcc-92ec-2a4ac2aa9764 |  | section | Reinforcing
checkpoint-status | e9e69456-fbb7-4740-9640-acced5496f57 |  | checkpoint | Size and type correct to specification
checkpoint-group | b5be4148-ee66-47ff-81e6-b58473b673b8 |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status | 894c0285-f8f1-46a3-9659-4279f254fb41 |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint | 835d1669-dfec-4260-bfe2-18d84e7dfc31 |  | signoff | Raise remedial / Request Signoff
checkpoint-status | f6aca6a4-d6a8-472c-99bd-9c79111cc19a |  | checkpoint | All relevant inspections completed and attached
checkpoint-status | db52de0d-fe1e-4295-9078-624d61bd057c |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group | 73e09ca0-7e96-46d6-a12c-be680d16a778 |  | section | Concrete Supplier Specifics
checkpoint-status | 598550d4-0567-45cb-bf28-dd40895b4e51 |  | checkpoint | Test blocks booked
checkpoint-status | 39d02ac2-1301-4193-8f1f-8ae085d7de0c |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group | 7dc0bfcf-0f26-4de2-940c-08235aa8c623 |  | section | Post Pour Checks/Sign Off
checkpoint-status | c6df533e-906b-4c97-93e9-22a1b98ceadc |  | checkpoint | Any remedial work completed
holdpoint | 5c3dfb2a-1ff8-43c4-a498-6c412c764845 |  | signoff | Raise remedial / Request Signoff
checkpoint-status | 750a4b34-de68-4879-9bef-d462a9636f24 |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status | 4dbcd4e1-654f-4bdd-aa88-5967b60614cb |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | ba41903e-65db-4d45-9d21-277f243a1566 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 8f0cf9e5-c71b-4df2-a8fd-e99d1d049ec6 |  | checklist | FC - S - Air conditioning Pre-Installation Works |  |  |  |  | Yes | FC - S - Air conditioning Pre-Installation Works | 05de00d6-f862-4e3b-ba93-8a5ad376124f
checkpoint-status | 48cc16af-6862-47fe-a075-ff44b4984047 |  | checkpoint | Aircon channel installed
checkpoint-status | 04221896-7041-4c71-9599-6e538639cad4 |  | checkpoint | Aircon brackets installed
checkpoint-status | e1d66748-4e55-4f6e-bf80-71ffb69b5616 |  | checkpoint | Threaded rod installed
checkpoint-status | 719fdda3-6baa-423a-968b-1eb40ac1e71c |  | checkpoint | Flashing covers installed
checkpoint-status | a6d53684-a563-46a8-bed4-c370d614b876 |  | checkpoint | Trade seal installed
checklist-flat | b981f3fe-6e05-4c5b-8125-4179f7a2f258 |  | checklist | FC - S - Gutters |  |  |  |  | Yes | FC - S - Gutters | 0fb88b71-1727-49ab-91db-c329aae98fac
checkpoint-status | 44b42e82-0fad-484f-8329-91c7e45dd3b8 |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 2d13d3dc-1b80-404b-b2d6-19cd2a461a4a |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | f63cd17b-b839-4555-b48e-14e816575b0c |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | fc9d1b2a-901e-4362-824c-cbd366cc0672 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 4061986c-fb62-4430-96b1-9ef03d0f5e1a |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 044097e2-94bc-409d-9a80-0531476fac42 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | c38c7237-4b20-4285-b20a-2f7d9ea4e425 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-sectioned | 39db5a91-5ac8-4462-808c-6d53bf731824 |  | checklist | ST - S - Concrete Pour |  |  |  |  | Yes | ST - S - Concrete Pour | 13796a75-db13-4352-a135-4f27a72d6ea5
checkpoint-group | 44a6aaca-73cd-47e1-8b3d-b45a951653c3 |  | section | Pour Details
checkpoint-status | ef3ec0ce-affa-400d-9651-31c1f64aff17 |  | checkpoint | Pour details entered
text | 25674297-f2c6-5bb7-ad92-0648a519efca |  | textbox | Area to be poured:
text | 0bc9827e-c47a-5c9f-9d21-985718081821 |  | textbox | Date of pour:
checkpoint-status | c367d739-c731-4e36-a9b2-8742d2de67b6 |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group | 02fcb529-302f-4c04-b0d3-b45d9378d08d |  | section | Formwork and Embedded Items
checkpoint-status | 4c5a8e23-96d8-4f52-b3eb-2f92d6b63028 |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status | 8985e314-f972-46ea-8ffa-3e1b3415b1e2 |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | 8b31908b-c688-4ad2-ab5b-777e5371d403 |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status | b05be524-7289-4733-a12b-763f85e4160f |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group | e54b3eb2-d62c-44f3-83f8-33aa4c2b30ca |  | section | Reinforcing
checkpoint-status | a7f6adff-ecbd-4dc4-87ff-0d8b534f90ca |  | checkpoint | Size and type correct to specification
checkpoint-status | 19eb82e1-ff2a-49e4-a14e-bd8a3e913405 |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status | bc813038-a546-42ad-80b9-7519215e74a1 |  | checkpoint | Specified covers checked/correct
checkpoint-status | 8f499669-5f47-455d-8b58-5934e59ab895 |  | checkpoint | Splice laps checked/correct
checkpoint-status | 04ea87db-7480-4f9c-8012-4cb022f81a40 |  | checkpoint | All couplers installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
boolean | 417435b9-5af3-5c7d-a2a7-2f80f4bd6051 |  | tickbox | Appointment with the engineers confirmed (Enter date & time of the appointment)
boolean | 128d0fad-97d7-5dd3-bf3f-3a401543049d |  | tickbox | Reidbar – coupler and flange nut installations are inspected by the MV Engineer
checkpoint-status | ed61e214-c9f7-4d23-aeb7-acf80af13481 |  | checkpoint | IMBMS couplers testing carried out for Village Podiums in the form of tensile testing in accordance with NZS3101.1.2006 and results acceptable
checkpoint-status | 2f3d3b41-a9f4-4a37-aaa2-34bf3e85491e |  | checkpoint | All starter bars are installed correctly (location, size and spacing )
checkpoint-status | 226eeaf1-7846-41b4-b7ae-8bab75494195 |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status | a20329b4-bb95-4cc4-9092-e5f3a3aa86ef |  | checkpoint | Welding certificates sited and attached
checkpoint-status | 78f9dfc9-6343-4f63-9b33-0cec93ffecc0 |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status | a5177a15-3fda-4985-800c-60556ef7af08 |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
checkpoint-group | da166797-e603-4bab-8ffc-39ade7cde657 |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status | 0fd1a1b0-0342-4277-bec0-bdcdc28b3415 |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status | 96716a24-811b-4e67-9374-3061673080ed |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status | 831b10f3-8c3f-4270-9337-eed11cce0687 |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status | 17e054f1-31c4-4484-a0cb-ae40b3b04ac2 |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group | b7074fde-8221-4edc-ae9e-2aa9765e4627 |  | section | Concrete Supplier Specifics
checkpoint-status | 554baba8-5f66-4b41-ac87-f0aa411e3dda |  | checkpoint | Concrete Supplier details entered
text | a004eb29-1890-5904-ad7a-c46ce0ce4a2e |  | textbox | Supplier Name:
text | 0dfc3299-1c45-5410-ad6c-5edd421e0f13 |  | textbox | Specified concrete strength:
text | d80b9634-f637-513f-8185-8faf3b86f59f |  | textbox | Concrete strength ordered:
text | 788feda3-6e7c-5316-ae46-446ef89cbeae |  | textbox | Concrete quantity ordered:
button | af22f67c-e95e-5749-bbed-47a30b912633 | DataPoint is missing 'button' values | button | Test blocks booked
checkpoint-status | 787579b7-f93c-48ac-bcc8-16b0bd79b788 |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status | 7c4ab76c-f5c2-4018-b3f4-d68cfd826710 |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group | 7c5dfdc3-5e30-40fa-9317-dc593c88c8f2 |  | section | Placement Method
checkpoint-status | b56976f2-72dc-46de-bfc2-c3ad750287e4 |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status | 6397f949-c4b5-442a-a107-d38b398bb2c4 |  | checkpoint | Heights and falls checked/confirmed before placement
button | 7e76c38a-f183-54b7-ace8-05aeadf8b727 | DataPoint is missing 'button' values | button | Is the cover correct to specification
checkpoint-status | d1caa945-8e62-4e39-a04d-b06211ff0de1 |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status | 390c276a-cccb-47c2-a7f4-a5a8ee0e96cd |  | checkpoint | Any curing compound applied correctly
checkpoint-status | 8552b779-4c70-44cb-977f-f215cbafc095 |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group | 3137a681-2f89-4e89-9c1f-4c69cc138d16 |  | section | Post Pour Checks/Sign Off
checkpoint-status | 94e4d535-2f75-4433-8c51-c4daa54eabcf |  | checkpoint | Any remedial work completed
holdpoint | 3150fa84-f5e0-446c-b56d-999815b46b5c |  | signoff | Raise remedial/ Request Sign Off
checkpoint-status | c4fb18bd-c26e-4ee4-8611-ddfbe50ea6e9 |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-sectioned | 68c96541-5b6d-4439-9f5b-eb65584db480 |  | checklist | FC - S - Louvres Pre-Installation & Bracket Installation |  |  |  |  | Yes | FC - S - Louvres Pre-Installation & Bracket Installation | 16027974-a351-42a4-8061-245735afb3a1
checkpoint-group | 6623888c-8f27-465f-a7f1-335fece94326 |  | section | Pre-Installation Checks
checkpoint-status | 78b8e7e1-4a5c-4ecc-85ed-fc4158c33998 |  | checkpoint | Pre Fit - Studding completed & setout checked
checkpoint-status | 644ab244-cb14-421f-83f0-1168d0289b93 |  | checkpoint | Waterproofing to pre-fit studs completed and acceptable
checkpoint-group | 8e577ea9-9da3-4b8f-9a13-a7eed3af4944 |  | section | Installation Checks
checkpoint-status | c45e22e3-16e2-4c7b-8bb3-2b5dd0e45abe |  | checkpoint | Louvres height is compliant
checkpoint-status | 4bffcc1a-a1a7-4acd-8068-4d05c4be53e5 |  | checkpoint | No Gaps Larger than 75 mm
checkpoint-status | 6bd49eb3-9d13-4554-b8d5-ada8099076ea |  | checkpoint | Louvre brackets installed
checkpoint-status | 95ff71fe-af7d-4573-af8f-60dcb58421ab |  | checkpoint | All bolts installed done up correctly
checkpoint-status | c5ce9cf1-39e5-48b7-b331-20ca8ac773b8 |  | checkpoint | Endcaps in place and acceptable
checkpoint-status | 40886240-a494-44b0-b331-d3c148b74160 |  | checkpoint | Any paint touch ups completed
checkpoint-status | e3913ded-6748-429b-9129-6781cbc3bec2 |  | checkpoint | All louvre bracket installation works completed, reviewed and approved and protection installed
checklist-flat | b9be09bc-6fbb-4379-8978-719bcd8a2a62 |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | B07 - ST - S - Precast Wall Panel Installation | 16084553-27bf-46fa-8cb7-4e20ebb26546
checkpoint-status | effce33f-4112-4356-8a1c-6c9e17ea7dbd |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | 5fedfc67-6498-439a-91b5-762dce063812 |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status | 00d89f56-01ff-40cc-bb40-d1d2b5083c10 |  | checkpoint | Installed in correct location
checkpoint-status | 02e2aaf4-839f-4a3c-9149-329cddd88585 |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status | 81047c2c-07d3-4787-b7f6-4d4835be0178 |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status | 5bb7f475-ee48-4271-9d40-31e827babe32 |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
checkpoint-status | 96e96d4b-1e43-4c58-b0a3-f7e3eacc77f3 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 345c0926-ceaf-4d81-a969-e036f4bf17fc |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 39601e9e-08dc-4bdd-9e83-cad47ddcc4f0 |  | checklist | FC - S - Air conditioning |  |  |  |  | Yes | FC - S - Air conditioning | 188fadc2-168f-4b03-b2cd-16dbf619b3f2
checkpoint-status | 8d8a359a-6e99-487d-b54d-c4bcd29d0264 |  | checkpoint | Aircon channel installed
checkpoint-status | be68f1ed-7122-45d8-a40f-0c336da81704 |  | checkpoint | Aircon brackets installed
checkpoint-status | 9b998fcc-f00e-4d46-b591-62da7292f2db |  | checkpoint | Threaded rod installed
checkpoint-status | 58e65258-ef44-4978-afc0-fc76edeccfc8 |  | checkpoint | Flashing covers installed
checkpoint-status | 063afbb4-552a-4157-ade2-5a8844320151 |  | checkpoint | Trade seal installed
checkpoint-status | b4a1d919-ea40-492e-b03d-630fdcb27da0 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | a3df539d-8f85-4bba-8903-fb26cf2634f8 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | b1379a3f-1682-4b81-a84e-da16eb40ffa4 |  | checklist | FC - S - Roofing - Timber Framing, Hatches, Gutters |  |  |  |  | Yes | FC - S - Roofing - Timber Framing, Hatches, Gutters | 1d564d94-80ed-40dc-b6a1-998310e28128
checkpoint-group | e660132a-ef61-4951-8ea8-08ff90f99c78 |  | section | Hatches
checkpoint-status | 1f2a2dd1-487a-4e8a-b49e-8ec8d388e3ee |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 3bac3d59-0a2d-494e-bf3d-7bc3a04b9bc4 |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 1829e2cf-2520-4a67-8753-4efb458f5a62 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 12659b13-3a4e-4a16-9bf5-02f9f44181f2 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 15dd51c5-e8cc-4eca-9f15-2721bfe802f8 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 793121d8-2be3-46e6-82a9-23a32060ecbb |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 2e22c92a-74da-48b4-99d3-9698d4598250 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-group | 027cf500-d460-40fd-bebf-c8be44fd7b53 |  | section | Gutters
checkpoint-status | 79a9ebad-f24d-4465-b60f-2a542f7cd01d |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 3a7e17f6-9a53-4c01-9756-e1572f5fc628 |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 56728047-a53e-476f-8257-5a6ce68a181b |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 8a198ef3-1352-40bb-9fd0-c3fac54d9993 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | dd8bf7bb-859c-44fb-8810-415fa83107ac |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 305ac004-969b-42be-abb9-f0c3284c832c |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 5e75be59-1076-4bf6-90ec-096f64d97169 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-flat | 291a6f2d-c29d-4895-ae41-6948760fdcdb |  | checklist | ST - S - Casting Plate Installation |  |  |  |  | Yes | ST - S - Casting Plate Installation | 2163dcf4-ce34-455c-ba2b-5a9cacf4c621
checkpoint-status | e3bfe372-7433-4d0b-b25a-d75a76692f9e |  | checkpoint | Plate correct size as per drawing
checkpoint-status | a1a9a8c7-d440-4c13-a692-fb8d3ae4a901 |  | checkpoint | Cast in weld plate in correct position
checkpoint-status | a0d7eb19-5a2d-4dca-8580-fb0df1ca8795 |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status | 15c9b39b-ef0f-4d0c-b142-879617dd275c |  | checkpoint | Plate installed in correct position, plumb and level
checkpoint-status | 347b4c7b-06d0-4733-84d1-98f48e8d51b1 |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status | fe8ebd66-246c-4062-96a2-f1d5f89468ee |  | checkpoint | Paint repair completed
checkpoint-status | 1fb0d981-ef32-4856-87bb-5a70f56aa600 |  | checkpoint | Plate installation completed correctly (checked location & level)
checklist-flat | e62e4f6f-7b50-4302-a126-b0e43ac31815 |  | checklist | Fire Door |  |  |  |  | Yes | QA - Fire Door Checklist | 256a3cfb-207d-47ac-bb79-afd418efdd0f
checkpoint-status | a7497ff2-2abf-4874-b5b0-fa597a7d4d03 |  | checkpoint | Door details
text | 11d5aa62-df8c-46a5-84a3-e10c1ecdaf54 |  | textbox | Door #:
text | 4a7f7768-d9a1-4277-be86-685d3e710b21 |  | textbox | Fire rating
text | a324f537-ea1e-49ef-9272-4af3d92c37da |  | textbox | Hanging
text | a5ad5062-99ad-4f6d-9bcc-c60956c89f92 |  | textbox | If other - specify here
checkpoint-status | 17d5bddc-b6ab-477e-aa3f-2c631fd6eec9 |  | checkpoint | Screw fixing completed, checked, correct and acceptable (photos attached)
checkpoint-status | 65c20301-a0e7-49e8-9210-bcf74f22976c |  | checkpoint | Jamb size checked
checkpoint-status | d21de7f5-9269-4056-8b2b-7abf64271b7a |  | checkpoint | Frame Perimeter gap max 10mm
checkpoint-status | e83fddff-5d97-4896-8ec2-bed81edf518d |  | checkpoint | Door stop smoke seal installed and checked
checkpoint-status | 82518e31-0390-4277-9291-084a7ec69ed8 |  | checkpoint | Correct hardware installed and operating to spec
checkpoint-status | d563ec47-5e12-46af-af5a-b113445bffc4 |  | checkpoint | Maximum 10mm floor clearance after the finished surface
checkpoint-status | 77bd46b2-117d-4105-8c1f-82ef7ed69fa4 |  | checkpoint | All door hardware installed and checked
checklist-sectioned | c07864fb-3129-41e3-8272-c3f270cb5e59 |  | checklist | ST - S - Concrete Pour - Without Reo |  |  |  |  | Yes | ST - S - Concrete Pour - Without Reo | 25bf008b-09b3-4764-86f7-ae0b439912bd
checkpoint-group | 73090e0f-a006-4d8d-bc56-1a4f32bac32a |  | section | Pour Details
checkpoint-status | aec9283c-1181-47ac-890a-f3b393152374 |  | checkpoint | Pour Details
text | 00b8150e-dac4-58b6-8e63-c6bf0db59ae1 |  | textbox | Area to be poured:
text | 48508789-f393-5b28-be36-870a075d7f65 |  | textbox | Date of pour:
checkpoint-status | 6469a795-5676-47cf-b6fe-ee2775b986cc |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group | 2fa7c124-0b83-430b-b450-d90092c50020 |  | section | Formwork and Embedded Items
checkpoint-status | 2a1237a2-7f6a-4baf-a0d2-7419f54c4b08 |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status | 090969de-9709-43ae-8b00-a3cd406ecf8e |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | 88234a99-5dde-4ba3-9156-b3000527c132 |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status | d602466a-9180-45fa-b621-a0caba5a36c9 |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group | cf7e0b83-941a-44c3-bd25-126be0b26705 |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status | 3ed2d380-6d16-4c55-84f7-4f795fbbb9f5 |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status | 9341fc97-fbf2-47a1-b253-463a06cc8936 |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status | 5e77352c-9364-441c-a03a-37dd77902230 |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status | 9614d750-836f-4488-86db-7edc01b1fb8a |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group | 6e83ee1c-c20e-47be-81b7-fab04b6ae4e5 |  | section | Concrete Supplier Specifics
checkpoint-status | 33591a90-1c6f-474a-993c-c552a25e3241 |  | checkpoint | Concrete Supplier Specifics
text | 58d47fee-d553-53e5-9296-2bea8e54bcf7 |  | textbox | Supplier Name:
text | c23987e3-a03a-58cc-aa95-44215a097b12 |  | textbox | Specified concrete strength:
text | 1a07081b-b1c0-51de-8047-e6f6219b35f3 |  | textbox | Concrete strength ordered:
text | ba2e0fb1-97d9-57cb-9487-a071e383b88b |  | textbox | Concrete quantity ordered:
button | 6a572364-4951-5ca3-ad46-deb5b34097ec | DataPoint is missing 'button' values | button | Test blocks booked
checkpoint-status | 676352d8-7929-485d-8e35-b8e0cfa2f7e0 |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status | 7444986b-e12b-4958-93dd-7fbb54ee8d7d |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group | 5dd253b9-7ba1-480a-9ec8-f06395955822 |  | section | Placement Method
checkpoint-status | 224525dc-6c9a-4d09-8181-1a4b5dd8aecd |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status | bf872764-0fa8-42b5-9c36-27276b1e1c11 |  | checkpoint | Heights and falls checked/confirmed before placement
button | 28e7fe75-efd1-5aff-828e-9e5fe0260dbf | DataPoint is missing 'button' values | button | Is the cover correct to specification
checkpoint-status | 0021cdcd-7346-48d3-bca7-ae2df8b4d5b2 |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status | 028c9f9a-d328-41c9-823f-b161e0dd8e95 |  | checkpoint | Any curing compound applied correctly
checkpoint-status | 146f9875-4647-4164-a8f5-2dd4d7fda69d |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group | 720b8f3f-b8a7-4fc8-8942-65e66efbaf3d |  | section | Post Pour Checks/Sign Off
checkpoint-status | 6cf6c60a-1c3e-4108-8f5c-8b43ac6651cf |  | checkpoint | Any remedial work completed
holdpoint | 2f912dcc-b14a-4e1f-b862-4d574ad1f190 |  | signoff | Raise remedial/ Request Sign Off
checkpoint-status | 23eead23-5323-4c8e-b333-cc5ba20ed9b6 |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat | 021a1189-fb37-4c73-977e-475de677c18c |  | checklist | FC - S - Hatches |  |  |  |  | Yes | FC - S - Hatches | 2b3ef62e-02f7-42bd-a190-84332aed5470
checkpoint-status | 1e666248-4429-4254-acc2-bf43d80554d5 |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 9e6911f4-c3ab-44e8-ade1-0ce3e31715fa |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 65cca8dc-2b58-4f00-ac4d-e9ccea13cd19 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | e1a1620c-6212-40e4-8ad1-fa13b73bc140 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 0c71ed47-8270-42fe-beea-af6665ede109 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 1b90b4db-e5ee-4186-aafa-e2bf52d203b3 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | e60d2afc-aa3a-4142-8db4-13a6d61c1bfd |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-flat | 90181196-90f3-410c-a697-9f8147fd3cac |  | checklist | F - S - Shell Beam Installation |  |  |  |  | Yes | F - S - Shell Beam Installation | 2bfb8466-c9ca-4d0d-b9f4-e379856f8e87
checkpoint-status | daeb1005-d921-4d00-bd8a-4b97d17d250a |  | checkpoint | Shell beams inspected for damage
checkpoint-status | 1ef257db-67bd-4839-9599-40c3c5f91aff |  | checkpoint | Shell beams installed in correct locations
checklist-flat | ace095f4-f491-4022-97c1-f84692eab2b0 |  | checklist | FC - S - Air conditioning Pre-Installation Works |  |  |  |  | Yes | FC - S - Air conditioning Pre-Installation Works | 327f7cb6-31b6-4b11-ab45-dfd0dd40b1bf
checkpoint-status | 390e4bae-db50-4854-a42a-5d194ef2a9da |  | checkpoint | Aircon channel installed
checkpoint-status | 59b77244-2676-4957-b641-b5cdddc7fdaf |  | checkpoint | Aircon brackets installed
checkpoint-status | e1b98c0e-f0c1-4afd-8add-dc2e1df1f5c8 |  | checkpoint | Threaded rod installed
checkpoint-status | 61bb384a-ebbe-40db-af26-dcc1582337f5 |  | checkpoint | Flashing covers installed
checkpoint-status | 653b9bcd-a9d2-46f5-8345-7b21f81568d4 |  | checkpoint | Trade seal installed
checklist-flat | 60297c1b-e521-4708-a100-15b78c4eb7f7 |  | checklist | FC - S - Exterior Timber Framing |  |  |  |  | Yes | FC - S - Exterior Timber Framing | 376a3b82-2031-4502-8c26-d5430f13e903
checkpoint-status | 4eb784bc-baf8-42e7-bed2-a124b1c6880f |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 7a5f6d1e-5069-44e5-8113-80835014765c |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 1b792fdf-427c-4c27-9a88-44c8edade002 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 7a94460e-0395-4bdd-aa80-0d936b4b72de |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 097bd9a0-d6f1-4270-b9ce-2f68b9d9fda5 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 03ad5d74-254c-485b-a18d-d95cd34c8e77 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 127d5d37-9f41-4df1-b197-ca6e19712787 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-sectioned | 98ac9c41-57ff-42bc-b13d-b47df63b30bf |  | checklist | ST - S - Insitu Stitch Joints |  |  |  |  | Yes | ST - S - Insitu Stitch Joints | 37be9b65-d619-468a-98fa-4e317693251e
checkpoint-group | 46cb3a01-c14d-4f08-bde0-b3d4c99158d3 |  | section | Pour Details
checkpoint-status | d4974499-b487-4d50-a81c-4dd14ba2d78d |  | checkpoint | Pour Details:
text | efadad84-e5ff-5af8-b26d-66c04d149aab |  | textbox | Area to be poured:
text | a4fdbc51-5027-5117-8029-5728e6b87f0e |  | textbox | Date of pour:
checkpoint-status | f83b9ec2-01ff-4047-85d7-410d5d3a2fba |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group | d7292d77-b7e6-434b-ae63-033291bde1a1 |  | section | Formwork
checkpoint-status | 788a2925-a7a5-4cd1-a0c6-a3c29c8f67d1 |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status | 09d8e7f1-23ae-4033-9cdd-bf0c7c7eda13 |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-group | 7a725e16-d48d-4846-a511-d80f7e2d1f57 |  | section | Reinforcing
checkpoint-status | dfa6821a-724a-48e8-81f7-09a8bdcb3331 |  | checkpoint | Size and type correct to specification
checkpoint-group | 136d5db5-0f7b-47cc-8b78-aab68ec51222 |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status | c2467b7b-e75d-433f-8f67-fc20aca7a68f |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint | 090b88a9-4d19-4279-86c9-6b089dd4aaa4 |  | signoff | Raise remedial / Request Sign Off
checkpoint-status | 2970f2c7-8f60-4d1a-9e82-b0ecde1e55e6 |  | checkpoint | All relevant inspections completed and attached
checkpoint-status | b6a32fbb-370a-4ffd-9393-dff3340fe28e |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group | e4d8ad59-ee8d-4362-a625-3d5a92964c06 |  | section | Concrete Supplier Specifics
checkpoint-status | 14e3e9a2-ff85-40ba-8e0b-41dacf9a3613 |  | checkpoint | Concrete Supplier Specifics
button | eee4ad42-9033-5e4a-aa21-1efbd2545728 | DataPoint is missing 'button' values | button | Test blocks booked
checkpoint-status | 651eacbd-0de0-4eac-97b1-1fd6c2a9812e |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-group | af31ca40-b3f6-43d4-9294-f230c887f1ac |  | section | Post Pour Checks/Sign Off
checkpoint-status | 7b054e35-229e-4d75-b4a7-09bfb6ace105 |  | checkpoint | Any remedial work completed
holdpoint | 3acc2c65-275e-4414-a3cb-a1f8eac08c47 |  | signoff | Raise remedial / Request Sign Off
checkpoint-status | 17c7176f-bb5a-48be-a4b6-7836fd8db909 |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checklist-flat | 996b5110-b987-4796-afce-7b3616c60541 |  | checklist | ST - S - Precast Wall Bracket Installation |  |  |  |  | Yes | B07 - ST - S - Precast Wall Bracket Installation | 392bdf3c-420a-43a4-8704-3868dc0a6eda
checkpoint-status | 22a97285-738e-45a3-9371-9346a030afe0 |  | checkpoint | Bracket correct size as per drawing
checkpoint-status | e6ed0445-4a1e-4be7-a20d-81af58f1f71e |  | checkpoint | Cast in weld plate in correct position
checkpoint-status | 75137da0-3313-4ee5-91b3-caf98c476393 |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status | 9ea4a8a2-3e8a-4f43-9639-bc3aa1f2cdda |  | checkpoint | Bracket installed in correct position, plumb and level
checkpoint-status | 7d92e7ba-735b-4f3e-a82f-cecb602b1c57 |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status | 3f54e6e3-1af5-466a-bb6d-6a0f52e9a8b1 |  | checkpoint | Paint repair completed
checkpoint-status | 25ffe743-66aa-483d-9aea-2bf6b823c345 |  | checkpoint | Bracket installation completed correctly (checked location & level)
checkpoint-status | 152b663a-2039-4373-9176-8f71c41af3f4 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | e6dec60e-8991-479d-be1e-a5ca391bb685 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 3370c346-fc33-44d2-bac4-3c36024412e9 |  | checklist | ST - S - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - S - Precast Spandrel Panel Installation | 3d5081ef-8d65-4f67-92fc-a135f4fe86df
checkpoint-status | 5329ce0f-9f8d-4657-9d9b-9c00ea70ce04 |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | 42ba28e9-7364-4004-994b-2432b505f1aa |  | checkpoint | Installed in correct location
checkpoint-status | 02f5fb65-94e4-4a8c-b6ef-afa59ccb446d |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status | b1ad79fb-239e-4af0-8bcc-8cd0e3287830 |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
checklist-sectioned | 51188ffb-3aed-4a09-a0e3-eecbb88a19a4 |  | checklist | ST - S - Rib & Infill Installation |  |  |  |  | Yes | ST - S - Rib & Infill Installation | 4593f626-944b-42d9-a585-ce6c4fbd35b6
checkpoint-group | f79af459-e7ec-4bc3-b6ee-c26aa15327c8 |  | section | Pre-commencement
checkpoint-status | f9250ec6-a349-49a4-ac06-500376568a28 |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status | 380f1cd9-f5f3-4f8d-9fa9-dc1bc32fec6a |  | checkpoint | Grid set-out offset and level correct
checkpoint-status | 1b3945e6-b1ad-4f80-8bfe-7a81e222adcf |  | checkpoint | Props tagged and fixings as per approved temp works design and temp work approval report attached
checkpoint-status | 22c39bc3-be4b-4924-b83c-028c34a7fb08 |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-status | 4168e869-507a-489b-a540-4ca964634404 |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group | d27571c4-80d6-430f-bae6-2e37baebb4b6 |  | section | Installation
checkpoint-status | 2be5ea72-f3fc-42f3-bdb2-b52a2244b9d2 |  | checkpoint | All grids ready for rib installation
checkpoint-status | 8f40721f-168d-4cbc-9a82-4dcd2771dd8d |  | checkpoint | All Ribs placed, locations, heights and orientation approved. No damage during install and approval given to install planks
checkpoint-status | a3bf4569-aae0-4d80-80a3-da6d6c34c7b2 |  | checkpoint | All planks installed correctly (adequate seating etc)
checkpoint-status | 9666b7f0-807b-4164-ace3-aaaeb5f5e9dd |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (NO GAPS)
checkpoint-status | be330a8c-a73d-4606-8a40-926edfb7e89a |  | checkpoint | Rib & Infill Installation completed correctly (checked location & level) and damage free
checklist-flat | bebdf746-3222-4537-ba53-e7fc53a94c5a |  | checklist | ST - S - Stair Installation |  |  |  |  | Yes | ST - S - Stair Installation | 54565f6a-3c77-4a7c-a460-9dc755e4af93
checkpoint-status | 558e1bda-0035-4f24-9834-3083c5532fff |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status | c2496cad-a063-46b6-ae41-2e1cb0792019 |  | checkpoint | Grid Set-out offset and level correct
checkpoint-status | a2776dba-ddb4-4141-80a3-113833de2027 |  | checkpoint | Joints scabbled and acceptable
checkpoint-status | ff502b79-d1cb-449d-859e-1fcafb9e6874 |  | checkpoint | All setout completed correctly and approved
checkpoint-status | 209a220c-7fce-4fe8-b6a5-cdfc045ce0b4 |  | checkpoint | Temporary support installed and approved
checkpoint-status | 1b29569f-85cc-44c7-a462-cf2cb74b4ea6 |  | checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
checklist-flat | f91ce056-891f-4b4d-bce0-288bcb4ac606 |  | checklist | Internal Doors |  |  |  |  | Yes | QA - Internal Doors Checklist | 59ee8019-34ff-4346-998a-f6b31b208f4c
checkpoint-status | 00ede113-03c7-4952-916c-bb16e0de8c2c |  | checkpoint | Area & substrate acceptable
checkpoint-status | 34089f28-f51d-4f48-be24-1927e67338a9 |  | checkpoint | Door fitted correctly as per specification (product, size, location, level, swing, fixings, etc)
checkpoint-status | 1eb419e4-388d-4cdc-8767-48cde9ecc040 |  | checkpoint | Door install completed, checked, correct and acceptable (photos attached)
checkpoint-status | f54104de-face-4275-9ef7-3912b5feeaa2 |  | checkpoint | All internal doors completed correctly within tolerance in respective area (photos attached)
checklist-flat | 8397d39f-195d-4f55-80cd-3f007f9cef28 |  | checklist | FC - S - RAB |  |  |  |  | Yes | FC - S - RAB | 5e5c1ec0-4b13-49d1-af4b-e5086a48884a
checkpoint-status | bdfa8f5d-cd0f-4af5-bebd-3522c77f67b9 |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status | d1c36c25-e144-4a69-b98d-9a553171b9ba |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status | 8983f131-ede0-46da-852b-17d92f090e43 |  | checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint-status | d744028c-53b7-4c45-9309-e32cd1b6c839 |  | checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint-status | 4bb0c05b-76ca-41d4-8f1c-2fc2fc6e6489 |  | checkpoint | Bracing checked and accurate
checkpoint-status | 50f6808b-29c4-45e8-8479-1ebf20012809 |  | checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint-status | be4e6b65-08da-4392-b15e-9c59f55daf08 |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status | c333be2a-0790-4780-a728-fce2424ec579 |  | checkpoint | Batten on RAB Board for cladding fixings
checkpoint-status | c558e554-a795-4948-abce-e52dac130658 |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checkpoint-status | 9454dc77-042f-480c-962c-198e355bb480 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 0d086467-9143-44b3-a1ae-15263c49c70a |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | b26887d4-0ab8-4ba6-b197-7503565d7202 |  | checklist | FC - S - Brick Works |  |  |  |  | Yes | FC - S - Brick Works | 6373e692-d514-4ddf-a8fe-1e0f4547a834
checkpoint-group | a77f2f0a-3817-4e4c-8b39-6640fd57ae47 |  | section | Preinstall checks
checkpoint-status | 2d573ee6-2de1-4002-be4e-61f3763c6a3b |  | checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint-status | d9e95341-3f9c-46ee-8d98-4d22291d344c |  | checkpoint | Ground clearance correct to specification
checkpoint-status | 4ee9fe29-f162-4afb-ab21-24494044cbd8 |  | checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
checkpoint-group | 7c5acab9-08ac-484a-90d0-7fba3e264a62 |  | section | Brick installation
checkpoint-status | 21b900b6-ca67-46c8-9586-e52d7068ea46 |  | checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint-status | 3c8721b3-c558-494a-8f22-9d09820e9604 |  | checkpoint | Control joints installed correctly
checkpoint-status | 76917571-ff7e-42ec-97b2-a6d5abfb1881 |  | checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint-status | f6168c61-e43c-4ec9-8e96-a7f732cd8790 |  | checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint-status | c14bdc64-8f65-41f8-84bb-245ca52c6c77 |  | checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint-status | 5b9a143a-1d7e-4801-9a0c-76509c810cd0 |  | checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint-status | 2ef86fe8-20a5-4b6a-b445-acf03f8aa4e9 |  | checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint-status | 92a102e6-8799-484b-b940-c1b509a3f9c2 |  | checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint-status | fcacdfe3-2e48-4c50-8e00-e51c2cf2dcb4 |  | checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint-status | f23ac3c9-2db0-44f7-9eae-a52713811322 |  | checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
checklist-sectioned | 093e4680-ef04-4585-bdcc-c4c21c295557 |  | checklist | ST - S - Concrete Pour - Without Reo |  |  |  |  | Yes | B07 - ST - S - Concrete Pour - Without Reo | 68772d80-f3b0-4771-bba6-dc5e643d5869
checkpoint-group | 79db47c7-1bd1-4100-86c4-1880c0ad5adc |  | section | Pour Details
checkpoint-status | 9dbf23fd-8bfb-4795-bc41-d6bdde8bc6ca |  | checkpoint | Pour details entered
text | 7566a217-ac39-5f64-aafa-7acf18a93440 |  | textbox | Area to be poured:
text | d8041b1f-0097-5cbb-aab6-c5cafa7f2786 |  | textbox | Date of pour:
checkpoint-status | 21ff5b16-8171-4d4d-87a2-0c3a90f6aabb |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group | 7d4867a7-043f-49e2-be3a-ca88bad6fb36 |  | section | Formwork and Embedded Items
checkpoint-status | cc746dfc-c826-41ec-9858-5cdf367f5438 |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status | 8a9e9091-e580-433d-ad7c-255cf0ea7add |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | 483be9c9-8596-4a9f-b75c-ea6ebd1b48ef |  | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint-status | 822a87c9-f9c4-4779-8d13-9c68df29f0ef |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-group | 760a8758-76b8-4c2e-ad0d-5344ca4d3779 |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status | 701fed32-7fd1-4640-879c-4b0bef700164 |  | checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint-status | 3e00ba53-8d97-412a-a2f2-7345b7e0d1f2 |  | checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint-status | 0e9079f7-c459-4762-a2da-031ad6204328 |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint-status | 2b044d41-4de1-4650-b4a8-1b573dbdd52a |  | checkpoint | Ryman inspection completed - Approval given to pour concrete
checkpoint-group | 39b3f940-231c-402e-a7ce-de748559b3a8 |  | section | Concrete Supplier Specifics
checkpoint-status | f77e9b9f-500b-4fc7-90be-ff63332fa6e8 |  | checkpoint | Concrete Supplier details entered
text | 7c7ec040-fbf4-571d-9126-80de23d95687 |  | textbox | Supplier Name:
text | f08da116-7ddb-58c6-aefe-5d31cfef9024 |  | textbox | Specified concrete strength:
text | 8bbdd148-814d-5020-9918-1ef1adfdf900 |  | textbox | Concrete strength ordered:
text | 7174207c-5b8c-5546-a5df-e7b534a76b53 |  | textbox | Concrete quantity ordered:
button | b51289a9-7425-5d30-85ff-1d4afd744fd2 |  | button | Test blocks booked | Yes,No
checkpoint-status | 104778b3-53dc-4b8d-b805-e2c5744aefc9 |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status | 4b9f911f-d346-413d-915e-6c02378948b7 |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-group | ca311222-c7db-4c32-bcf3-6584a885e061 |  | section | Placement Method
checkpoint-status | 1363a92f-0134-4541-8fee-8d97d5e79a3e |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint-status | e3ba7a06-003c-4919-a5fe-fc68c8eb0cd6 |  | checkpoint | Heights and falls checked/confirmed before placement
button | c78b259f-a587-5c46-86f5-cca9f8dda42d |  | button | Is the cover correct to specification | Yes,No
checkpoint-status | 45e14ab4-d0e2-4548-9e0b-dd206d6211e3 |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status | e6df3bd1-78d3-4433-bf75-d1807ca83f5c |  | checkpoint | Any curing compound applied correctly
checkpoint-status | 9f499f1e-c114-41f9-909b-3e3abbd68d28 |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-group | da037f63-b6b9-4fb1-b471-8d7784e18d00 |  | section | Post Pour Checks/Sign Off
checkpoint-status | 81143d2a-b153-40d0-989e-5a5399222a27 |  | checkpoint | Any remedial work completed
holdpoint | d9a78611-4acc-46db-9fd5-32e149406a2c |  | signoff | Raise remedial/ Request Signoff
checkpoint-status | 26f39059-a378-4fa7-be7b-279ca6d4c599 |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint-status | 01f1263d-58b8-48fc-9d0e-6de75c585fe7 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | f7e076dc-b431-4593-9cb8-e35e64739178 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 2231b032-9e69-4284-91cb-9e698a165abb |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | ST - S - Precast Wall Panel Installation | 6c169cde-c636-4aca-a54a-62ddaf1b6cc4
checkpoint-status | fa54e028-0eb3-4326-a286-4c63d27462d8 |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | 9f81e7e3-fe06-4f6d-a0d5-bf6f7baeb33b |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status | 6ce8aa48-b953-4d50-bb46-2520c3ed1854 |  | checkpoint | Installed in correct location
checkpoint-status | f064e7f9-6e73-40fc-aa06-28fe04cc7f38 |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status | 5888bcbf-8aa7-4787-83b1-892550b46c09 |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status | 00361aeb-5062-4905-9eed-4c611eb699ef |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
checklist-sectioned | c89d8ec6-e4b0-4cac-b9dd-fa281d97d7b2 |  | checklist | FC - S - Louvre Installation |  |  |  |  | Yes | FC - S - Louvre Installation | 763f2257-afd9-4edc-8bf6-12dcdd952096
checkpoint-group | 01ecb36d-9991-4ff9-931f-3543aa74caf6 |  | section | Pre-Installation Checks
checkpoint-status | dac48cfd-30d6-4f98-b567-93b61f2d5896 |  | checkpoint | Pre Fit - Studding completed & setout checked
checkpoint-status | 4e1882b8-1471-4fb1-af34-c8cdb60fd078 |  | checkpoint | Waterproofing to pre-fit studs completed and acceptable
checkpoint-group | 586b69bb-4d6d-4736-a118-49a661685de6 |  | section | Installation Checks
checkpoint-status | 15b1dd52-a0a3-4b19-a875-792cc6879c46 |  | checkpoint | Louvres height is compliant
checkpoint-status | b966d988-e841-4add-88ea-479efc27ac6f |  | checkpoint | No Gaps Larger than 75 mm
checkpoint-status | b2f2d5a7-78fc-4ba5-8ed5-781ebd293524 |  | checkpoint | Louvre brackets installed
checkpoint-status | bfcd7120-9a7c-4b29-a133-4fc9d8d3548a |  | checkpoint | All bolts installed done up correctly
checkpoint-status | b9601d8b-6839-430b-b436-f84d06c345e7 |  | checkpoint | End Caps in place and acceptable
checkpoint-status | 673787ba-d959-4770-a5da-f0a1de82de9e |  | checkpoint | Any paint touch ups completed
checkpoint-status | fc717708-fbac-436d-b9b1-f750c3096222 |  | checkpoint | All louvre bracket installation works completed, reviewed and approved and protection installed
checkpoint-status | 0ca73c64-fc8f-4c72-ab50-5a7b6509cf68 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 35c4162a-e922-4d2b-98d5-26001907f85c |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | ac78e475-fa68-4f23-a16c-3c39a3067137 |  | checklist | Skirting and Architrave |  |  |  |  | Yes | QA - Skirting and Architrave Checklist | 79dfbb27-c970-4f55-875f-0d52f5967ea8
checkpoint-status | 66989f8c-4d49-4385-9d3e-028623867a36 |  | checkpoint | Area & substrate acceptable
checkpoint-status | d3386efb-4090-4aa1-b2e7-37bfacc4f6df |  | checkpoint | All skirting and architrave (trim) completed correctly within tolerance in respective area (photos attached)
holdpoint | 35990de9-0ca1-4c7b-9b70-d9f31e7d344a |  | signoff | QA has been reviewed and approved by the main contractor
checklist-flat | 44386b09-75f6-4fbc-a0c6-b41c28525170 |  | checklist | ST - S - Remedial Works Sign-Off |  |  |  |  | Yes | ST - S - Remedial Works Sign-Off | 7c631904-9ffa-45de-b5fa-c8eef15b3123
checkpoint-status | 76ec0b8a-fb1b-4efc-9963-5180e03ed46b |  | checkpoint | Any remedial work completed
holdpoint | a47f1ce9-e0a1-426c-b9e2-7d69cac845a8 |  | signoff | Raise remedial / Request Sign Off
checkpoint-status | 525e19e8-2a09-49a0-addf-b4cea8032793 |  | checkpoint | Remedial Works signed off - All final checks and documentation completed and attached
checklist-flat | 5ec40c03-2f00-4b11-a4b4-15e20163ac83 |  | checklist | FC - S - Flashing installation |  |  |  |  | Yes | FC - S - Flashing installation | 92f3552c-2942-43ff-9367-a53352c7046f
checkpoint-status | 97637918-56b0-4027-abc2-9db8c8b77e86 |  | checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint-status | 04a9d1eb-98b3-4f64-a129-fc1a0471a477 |  | checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint-status | a9a71502-5a5a-499a-8364-42136c8ea0d7 |  | checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint-status | 5af8b649-fd96-42a1-9383-8e1e271fd4da |  | checkpoint | Aluminium window jamb side flashings are installed
checkpoint-status | d5382550-1e5b-495f-8620-6b780497ef00 |  | checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checkpoint-status | 2cec90a5-b342-4b16-8fb7-3183e336430d |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 2663a8d4-0b98-4e4a-8e2a-63030eb02419 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 5651f710-f157-4812-9922-ab636b6d2fa1 |  | checklist | Fire door: |  |  |  |  | Yes | SYS - Fire Door Checklist | 95ecbd86-5f22-4303-bd16-cce7bc75c5e9
checkpoint-status | 628b23da-1fe0-4a1b-8479-ddafdbc569f3 |  | checkpoint | Door details
text | 23b2e1fe-741b-51ed-8734-797d4dfdd48c |  | textbox | Door #:
text | 6918f03f-be67-52c1-89ce-f6ed62122fa8 |  | textbox | Fire rating
text | 8b0476a2-18e4-53e9-a721-5d71c9e5f698 |  | textbox | Hanging
text | b2490db1-baaa-570a-acb3-6d9397d12e76 |  | textbox | If other - specify here
checkpoint-status | c922ba5d-20c6-4069-9ce7-e0fca447df98 |  | checkpoint | Screw fixing completed, checked, correct and acceptable (photos attached)
checkpoint-status | bc8e392d-7c27-4d69-bcf0-3a10fb631f6a |  | checkpoint | Jamb size checked
checkpoint-status | 44e0bca7-4868-40f5-8092-97995cb24391 |  | checkpoint | Frame Perimeter gap max 10mm
checkpoint-status | f6aa273a-a67a-42e5-af88-a624a346effc |  | checkpoint | Door stop smoke seal installed and checked
checkpoint-status | 82cc8c1c-af2e-44c4-9ed9-08420f23139d |  | checkpoint | Correct hardware installed and operating to spec
checkpoint-status | 46d90318-c37c-4d3f-9ef5-9a725e660902 |  | checkpoint | Maximum 10mm floor clearance after the finished surface
checkpoint-status | b00d191e-9f0f-49c6-9772-11ac0604957b |  | checkpoint | All door hardware installed and checked
checklist-flat | 2fbcc442-3cb2-4864-a4fa-d6ed5dc9b081 |  | checklist | ST - S - Precast Flat slab Installation |  |  |  |  | Yes | ST - S - Precast Flat slab Installation | 98e083be-e569-4f33-b551-e93740447cb5
checkpoint-status | 321f4017-badd-4db6-8e11-7f5c90c6999f |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | 57be0935-bbbf-4b74-86e7-2ede6a35f466 |  | checkpoint | Installed in correct location
checkpoint-status | 823c556e-fdcc-4c5b-832b-29e748bf3d18 |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status | 2b249873-be57-4280-af00-009ab11ebd73 |  | checkpoint | Precast Flat slab Installation completed (checked location & level) and no damages
checklist-flat | d624aedb-2fe4-418d-895b-e887bf1178a4 |  | checklist | ST - S - Stair Installation |  |  |  |  | Yes | B07 - ST - S - Stair Installation | 9adcd2d8-7eb8-49f9-868a-4e40ca2dfe64
checkpoint-status | 888cff40-6dce-41c9-b108-23da945062a4 |  | checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status | 854da099-1959-43a0-a097-bdb6e8af71bd |  | checkpoint | Grid Set-out offset and level correct
checkpoint-status | 2641e141-7e11-44ad-a506-5b36ecbe1c80 |  | checkpoint | Joints scabbled and acceptable
checkpoint-status | 208c188b-9186-4d9a-9d1f-5405260cb3f4 |  | checkpoint | All setout completed correctly and approved
checkpoint-status | aeb20543-0964-4069-92b2-81881070e737 |  | checkpoint | Temporary support installed and approved
checkpoint-status | 5a5b25af-4493-4251-a47f-295bb6d54481 |  | checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
checkpoint-status | 4025ac22-cbbc-4b9b-b5f3-7a15ef2caa0b |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 1e1c89b3-d7b3-4d7d-bbc1-67f370ed95b0 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | c179d632-c8d1-4ee0-9557-69b58d6a3d0d |  | checklist | ST - S - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - S - Precast Shell Beam Lintel Installation | 9aea6d6d-80e4-4ab7-9630-d3c6074cfc16
checkpoint-status | 9b201286-13ef-4446-8de7-181963526c87 |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | 26e0eaf2-cf06-4474-97c7-2ba485e471e4 |  | checkpoint | Installed in correct location
checkpoint-status | 43ad55c3-afdf-4cf8-b91b-b273707b363d |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status | 258ae9b5-5f5a-4fc1-86de-58bae1d24184 |  | checkpoint | Precast Shell Beam Lintel Installation completed (checked location & level) and no damages
checklist-flat | 38a7a9b5-31a6-4e35-bf74-9f04fa4dfffa |  | checklist | FC - S - Exterior Timber Framing |  |  |  |  | Yes | FC - S - Exterior Timber Framing | 9afc816a-20d1-4c26-8ae7-fd1404b8ef3e
checkpoint-status | da527405-52b5-4c33-bd62-f0f30b311a2e |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 3cd1ce48-c65a-41a4-b74b-1b4dd417252b |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | a4080d4b-488b-46d9-b42e-2c3668928511 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 5a1facc7-d7bf-4f8e-a256-9e4daad83e1a |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 28fba871-0a6c-4ece-957d-d13b707bd678 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 23da62a3-2b2d-4c27-83a8-ec1266667160 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | a42196b0-405b-47dd-8900-c5b43131244c |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status | ce4948fd-9d3a-4e61-b62a-fd0ef170bd91 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 8bbd8b0c-7574-42ef-be9d-20b0dba28659 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 11bc58e3-28b3-4f61-9e63-b2cf21eaccab |  | checklist | FC - S - RAB |  |  |  |  | Yes | FC - S - RAB | a423caa0-f00f-41ba-b37e-2c5ac8da76ad
checkpoint-status | c3760d54-3c22-4acd-bf8d-5e0667500887 |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status | 46552491-21a9-48d7-8103-0604e2d97d6f |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status | 9669695d-fc24-4af0-a72c-2ffd1b82992b |  | checkpoint | Wrapshield / Vaproshield to interfloor installed after vertical taping
checkpoint-status | e2b90627-be9b-4e1e-8507-0bbafc610d44 |  | checkpoint | Bracing checked and accurate
checkpoint-status | 3cfd6338-e5d3-48dc-8233-11d2979f5d4f |  | checkpoint | Penetrations and punctures sealed with flashing tape
checkpoint-status | 419e13e8-2fed-4776-95e7-ae017ec63137 |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status | 81e0fbdc-9694-4655-bcde-3c1e911f7065 |  | checkpoint | Batten on RAB Board for cladding fixings
checkpoint-status | 7a8f4578-6b30-4dbb-a665-b174a2940b27 |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checklist-flat | 74205f49-af65-448a-b5c1-f24393bdec04 |  | checklist | ST - S - Remedial Works |  |  |  |  | Yes | ST - S - Remedial Works | a5fe0a08-034a-437e-b353-e6d5ba35b8b2
checkpoint-status | b821e49e-a274-42cb-963b-b3c0f5d11d1f |  | checkpoint | Remedial works completed as per Engineers Report (Photo Required)
checklist-flat | b00fdfd6-0a37-4dd6-a190-8f11a400b22c |  | checklist | FC - S - Eyebrow - Canopy |  |  |  |  | Yes | FC - S - Eyebrow - Canopy | a9a9966a-ce27-4e8d-afca-6d0a50f3541d
checkpoint-status | fd13947e-f0e6-40b3-a61b-4c8e898ab7cd |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 889ece46-80e6-4b6f-b24b-f16e6adf35a9 |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 7fe2c8ef-2378-4433-add3-784ae069725e |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 87d9a5df-7787-4dac-9f69-db5ea7a320e2 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 53f5ab46-b47c-431e-a9b1-3c8532b93f5a |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 5196ccd1-84bf-4337-8b45-d050929ca104 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 111f7160-25cc-4000-a9c8-5fe848cf1ac6 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status | 1192594a-5359-4eb3-a3c4-7eb4b4bba53d |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 5218c7ed-383d-4a19-8626-978b17e8b768 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 5a11da41-4273-4201-bf20-e1ca969c300e |  | checklist | FC - S - Windows, Sliders and Sealants |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | ae61ada5-954a-48a6-b28f-f4cbb77748ba
checkpoint-status | df03fef3-1036-4c40-83c2-633ec40f05b6 |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status | 168ead9e-9f35-4687-9bb5-d732e95872c1 |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status | 42c7f2a0-76af-4885-8796-5963135bb7f3 |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status | e901de26-d6f6-4660-8009-9e3d9db2eee3 |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status | 549a2c51-51da-46f3-9a24-d2ae6df3c63e |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status | db512ce7-893e-41e5-9c85-7bc1eadac061 |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status | 91b36505-163a-4a1c-b846-14dc69ff5c93 |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status | eb55c204-3ea9-4d17-9f74-c0afb09094ac |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status | befbf57a-e278-4c92-b58e-c3027e46ff1e |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status | 6beeeb2c-8297-43ed-bb98-38adc2a51b6c |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint-status | 3deae055-8d46-4d5f-bbdc-2153dc2cf899 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | b031c5b8-2fd5-4b64-81b3-dffb6e0b9825 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | c7767ad7-7546-4d4f-804a-7af38ae48cb6 |  | checklist | FC - S - RAB |  |  |  |  | Yes | FC - S - RAB | ae64129b-be94-4919-9bb8-8dee408600d3
checkpoint-status | bc1566e5-c951-4f5f-a1b8-4d4eceecdd57 |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs
checkpoint-status | a29d9e59-f493-4675-8fcb-8cc6d080991c |  | checkpoint | White MS sealant for air seals between RAB board and concrete horizontal and vertical joints
checkpoint-status | a446cf42-b1b8-4842-89a9-cc052ef80ee3 |  | checkpoint | 3M taping around windows and external corners and vertical joints and horizontal flashing checked
checkpoint-status | 2b7ff5a9-f973-478f-80ca-05ddafd7704a |  | checkpoint | Vaproshield to interfloor installed after vertical taping
checkpoint-status | 2a510c85-b283-40a2-ab34-9df0012fe9bd |  | checkpoint | Bracing checked and accurate
checkpoint-status | bbafe584-2532-471f-a12b-7ae2160f9137 |  | checkpoint | Penetrations and punctures sealed with flashing tape, sealant, and trade seal
checkpoint-status | d9fefcee-d9df-4bb4-ae78-610981844564 |  | checkpoint | Sealing joints over internal and external joints
checkpoint-status | 3f97da71-578c-455b-91ed-52c8fcaab35b |  | checkpoint | Batten on RAB Board for cladding fixings
checkpoint-status | bd128f7d-70bc-4797-a503-78907768b326 |  | checkpoint | All RAB board installation completed to specification & within tolerance in respective area(s)
checklist-flat | e5732b35-92e7-44c1-b820-6b10d83c8766 |  | checklist | FC - S - Hatches |  |  |  |  | Yes | FC - S - Hatches | b47a5f91-ca66-4e46-aa1f-d39319280063
checkpoint-status | fea6b0ba-7384-4ebf-bdb6-c4fabf65c2e6 |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | 69fc4ad1-9b17-43cb-9ef3-7660507dc2c2 |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 90a53870-f43b-4d96-8b9d-9cafbb052277 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | 194690f8-b3ad-4e4d-808f-04b9179b1374 |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 4ed669da-871f-4e7e-9621-8baf604aea68 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | d522c58b-8b9f-4db1-9b79-c904329a132f |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 2b785561-eb4d-43eb-9539-eb31d74ee3a3 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status | c8c3b4cf-f144-42c2-a536-59fffd7aa0a6 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 48d32170-15c6-4121-89ff-4a1491d3587f |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | f5b87b06-f85d-4c08-aa1f-14bac293e3f1 |  | checklist | ST - S - Steel Deck Concrete Topping |  |  |  |  | Yes | B07 - ST - S - Steel Deck Concrete Topping | b7954d6a-309a-4921-b75b-35f39724b4c9
checkpoint-status | 00dc87cc-5e07-4cd9-a732-f048cb99af32 |  | checkpoint | Area clean and accessible
checkpoint-status | 046b8394-90c2-4917-9f38-a805ca45bdce |  | checkpoint | Material and size are correct
checkpoint-status | 938b73f5-ce6d-4787-b916-bfacf9f7b4a9 |  | checkpoint | Installed in the correct location and orientation
checkpoint-status | 8050d47e-2e2d-4b80-97ec-f4f3f828e64d |  | checkpoint | Firmly secured in the correct method
checkpoint-status | 0be2b35a-917d-4cae-a2b9-8173e716174c |  | checkpoint | Area left tidy and accessible, and work signed off
checkpoint-status | 3dc16450-5b3b-4ec8-b37c-c71ad8f4a838 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 5d935456-4c47-4d43-9856-b0d9b0bce8f9 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 0ab96bce-9f37-4372-921b-b0221c94a1f0 |  | checklist | FC - S - Brick Works |  |  |  |  | Yes | FC - S - Brick Works | bed30336-ca9f-47e0-b00a-f77a96e8df13
checkpoint-group | cf90496b-e897-420e-9eb4-f66fde18ffb8 |  | section | Preinstall checks
checkpoint-status | d578c89e-bff1-494f-b8d6-86e520af69ed |  | checkpoint | Area accessible, substrate acceptable & approval to start works - Consider services, cavity & waterproofing requirements prior to install
checkpoint-status | 9f4e0a9b-48b3-4cc9-b304-8d5be0ec83df |  | checkpoint | Ground clearance correct to specification
checkpoint-status | 88d922b0-24c8-4641-bf11-eaf96e598838 |  | checkpoint | Grids/Wall marked for reference. RL reference/TOW confirmed. Base/Concrete/footing clean, tidy and level ready for first coarse.
checkpoint-group | 3319d7a3-3615-46e4-8c35-ef13d8fad00f |  | section | Brick installation
checkpoint-status | a6033d09-0b15-457e-8b8e-a2b2b8f2ed9e |  | checkpoint | Base of wall starting correct location - Brick base overhang within tolerances (no more than 20mm)
checkpoint-status | 5369e46c-8ee0-4008-8bd5-838018fabc84 |  | checkpoint | Control joints installed correctly
checkpoint-status | d08c7aba-9086-4047-8b2f-e3b7f3b7ed8a |  | checkpoint | Weep holes installed correctly - Consider setout & size
checkpoint-status | 01660c5f-5775-4c76-ad73-43236e3e71f8 |  | checkpoint | Mortar Joints installed within tolerances (7-13mm)
checkpoint-status | e0da3854-800e-412d-a2de-62c2326afd36 |  | checkpoint | Wall ties installed and aligning with specification (spacing, spans, length etc)
checkpoint-status | cb3736d3-35cb-4a42-8caa-83b8f7b680b7 |  | checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checkpoint-status | da430463-357f-487a-859c-0754e0de974f |  | checkpoint | All relevant flashings and waterproofing/taping completed as required - If Applicable
checkpoint-status | d755d70f-0b2d-45fd-b6f0-7708095a41a6 |  | checkpoint | Caulking completed (correct colour) and satisfactory finish achieved
checkpoint-status | 73ac71c7-0539-4a36-814d-30194d1fbd5d |  | checkpoint | Brick cavity is correctly formed and free of obstructions
checkpoint-status | 86deaf5f-5a49-485c-90d1-624608cfcce4 |  | checkpoint | Brickwork completed to required specification. All brickwork washed/clean & area left clean & tidy - Wall built within tolerance - straight, level and to the correct height and colour
checkpoint-status | d3c0256b-e43c-4afb-a863-d87581d55ac1 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | fb051abc-3c0a-4cdc-a9c9-f1337c3a5126 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | 4c1616ca-98e2-45a2-8555-b61f37262388 |  | checklist | FC - S - Soffits |  |  |  |  | Yes | FC - S - Soffits | cccac0ed-21fd-40c0-b17b-60377b5a628c
checkpoint-group | 2fce50fb-61b3-4595-b776-d38dcfb9c5f8 |  | section | Pre-Installation Checks
checkpoint-status | 771ea1c0-eb51-4a3f-9aec-f335f1c19721 |  | checkpoint | Wiring in and anchored down for downlights, checked and accurate
checkpoint-status | e56ae000-d594-4a81-9e7b-28b2f6e85ed4 |  | checkpoint | Air Conditioning pre wire and pipe completed and acceptable
checkpoint-status | e6eed0ae-1324-4977-aeb0-0c5c75c40ca1 |  | checkpoint | Fire sprinklers droppers installed and acceptable
checkpoint-group | 27d5cbb0-4ff5-40d2-a03a-55b842f4ca2c |  | section | Soffits works checks
checkpoint-status | 7bffcb0d-cbd3-4e72-8759-20903c1d0e12 |  | checkpoint | Framing completed, checked and accurate including sheet joins/blocking
checkpoint-status | d9855894-afa4-4d71-8550-b9dee9bff12f |  | checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint-status | 8f33f084-06a0-420f-aae3-91661350b21f |  | checkpoint | Villaboard installed, stopped and painted, checked and acceptable
checkpoint-status | 17b6af09-ce4e-40e8-8037-c9a63dcfa8e4 |  | checkpoint | Plaster installed as per spec and painted and acceptable
checkpoint-status | 90d77508-7643-4d7e-aad7-34b4db62ab0c |  | checkpoint | All soffits completed and acceptable
checkpoint-status | df0b283a-da3a-4b99-a740-7a6135269bd7 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 79f776af-2f6d-4bb2-b301-977628ea8e6c |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | eed53c0b-9a3a-4ae2-8f40-03291b9be260 |  | checklist | FC - S - Louvres Pre-Installation & Bracket Installation |  |  |  |  | Yes | FC - S - Louvres Pre-Installation & Bracket Installation | d18b0035-4789-49f6-88b7-878a8b4a5989
checkpoint-group | 9113d7a6-652d-44b4-bfb6-cf3ba3605845 |  | section | Pre-Installation Checks
checkpoint-status | 781493b4-bad3-4e7c-bad1-f933e4750442 |  | checkpoint | Pre Fit - Studding completed & setout checked
checkpoint-status | 778a60da-bdbd-4b48-90ce-2a5c005e7c50 |  | checkpoint | Waterproofing to pre-fit studs completed and acceptable
checkpoint-group | 5be5550d-efec-4b81-a91e-3bde091fa45d |  | section | Installation Checks
checkpoint-status | d8aeb33d-0ffb-4f15-ac4a-1e9a502291df |  | checkpoint | Louvres height is compliant
checkpoint-status | 5cf5a6af-e989-438d-8af9-ad4e4e633d0e |  | checkpoint | No Gaps Larger than 75 mm
checkpoint-status | 3122360d-75fb-497d-b526-14f81d55c33e |  | checkpoint | Louvre brackets installed
checkpoint-status | 016d3bc5-8d3e-4a7b-aa1e-5b23cf790023 |  | checkpoint | All bolts installed done up correctly
checkpoint-status | 7e2f5b3f-34a3-43bd-bfb4-9799d3f67128 |  | checkpoint | Endcaps in place and acceptable
checkpoint-status | a144de80-c053-4a5f-a02b-bd01e3b9dd2b |  | checkpoint | Any paint touch ups completed
checkpoint-status | 6c5c63d4-993a-4f27-8db0-50a0f2dbdacd |  | checkpoint | All louvre bracket installation works completed, reviewed and approved and protection installed
checklist-flat | b158c866-af0a-42e4-98a0-722ce5f51ad8 |  | checklist | ST - S - Precast Spandrel Panel Installation |  |  |  |  | Yes | B07 - ST - S - Precast Spandrel Panel Installation | d2c8967d-48c8-443d-af4c-59a93e3bb223
checkpoint-status | 8aebadcc-6c7e-438c-a764-baa52b8b1266 |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | abe01e71-508f-4b13-a6a4-03658c568586 |  | checkpoint | Installed in correct location
checkpoint-status | 6798408b-7028-4dcf-a870-4f6f3c752668 |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status | 4940f15c-6014-48b7-bb3c-320422072112 |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
checkpoint-status | 49976092-6f5f-4d53-8abc-f1d4890c236d |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | f9af06d1-3421-4dc6-83c6-f46b96bc42ee |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | e99aea05-27f9-4fba-a89e-0b56611f8c7b |  | checklist | ST - S - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - S - Precast Wall Bracket Installation | d3323202-0ff3-4c89-a659-eef3b2a050af
checkpoint-status | cd57a19d-dc94-4718-b70e-72cbd6692dc0 |  | checkpoint | Bracket correct size as per drawing
checkpoint-status | 4aeb49ca-d8f0-43e1-9bb6-d730fc2c1353 |  | checkpoint | Cast in weld plate in correct position
checkpoint-status | 86908e31-0e03-417f-9fe6-48b790dea999 |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status | a142233b-b511-4b32-a881-1fb36ef64491 |  | checkpoint | Bracket installed in correct position, plumb and level
checkpoint-status | 3e771156-710f-4cf5-a525-cd59896c95cc |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status | 74461312-1f98-4a87-ada9-301fba18a820 |  | checkpoint | Paint repair completed
checkpoint-status | 559a869d-d51d-410f-8f21-f4e02c1b315f |  | checkpoint | Bracket installation completed correctly (checked location & level)
checklist-flat | 55a34102-fd70-4422-8a41-790aa16759a5 |  | checklist | FC - S - Brick Works - Angles & Lintels |  |  |  |  | Yes | FC - S - Brick Works - Angles & Lintels | d3beab8c-5cd2-4485-81a6-903e94c75969
checkpoint-status | 13032925-42d4-4643-9323-e5adb01c4be6 |  | checkpoint | Horizontal shelf angles & lintel bars installed and correctly fixed where required - Consider horizontal and vertical alignment
checklist-flat | d4c3e49c-a944-4c7a-8343-ece9e4c10883 |  | checklist | FC - S - Flashing installation |  |  |  |  | Yes | FC - S - Flashing installation | d7704889-1155-4a2c-9d39-a59fb209df68
checkpoint-status | 9a6636df-6bc4-4e00-b683-f20b395224fb |  | checkpoint | Head flashing installed with sealant at windows and doors (STO system)
checkpoint-status | 4f83a4dd-41dd-4e3c-82f9-d495e9cb6153 |  | checkpoint | Rainshield installed between joinery and lintel (brick)
checkpoint-status | 9ab808f8-f891-4c7a-b914-50c5a0203cd9 |  | checkpoint | DPC and WANZ bar installed at the bottom of the joinery (see fixing) as per manufacturer's spec
checkpoint-status | c727fe1a-3b10-489e-b570-606ae62be809 |  | checkpoint | Aluminium window jamb side flashings are installed
checkpoint-status | c7c9d778-184c-43ff-99b1-5c007acd6963 |  | checkpoint | All flashing installed at windows and doors to specification & within tolerance in respective area(s)
checklist-flat | 14fdcb4e-9203-47e3-9b42-9e4e08a550a3 |  | checklist | Hardware Install |  |  |  |  | Yes | QA - Hardware Install | d77af2ce-9186-4574-acb2-295ac35a4880
checkpoint-status | 2fcafb01-509a-46ce-aff7-8ca035ec1f17 |  | checkpoint | Vanity Unit Installed as per spec
checkpoint-status | ac479dfa-92e0-4b8c-80c9-482aa397459e |  | checkpoint | Bathroom Mirror Cabinets Installed as per spec
checkpoint-status | a3b11f6e-f440-42b4-9d5b-d13b8d740197 |  | checkpoint | Bathroom Grab Rails Installed as per spec
checkpoint-status | 839d737e-da0c-4546-802d-86b1e3c2c089 |  | checkpoint | Shower Grab Rail Installed as per spec
checkpoint-status | 96429b44-ae07-4660-a51a-0326303bdda6 |  | checkpoint | Heated Towel Rail Installed as per spec
checkpoint-status | 4db00bef-19a4-456d-a626-4db9710f03ae |  | checkpoint | Toilet Mirror Cabinets Installed as per spec
checkpoint-status | 4bec775e-29dc-442f-b365-2fe5246bc5a5 |  | checkpoint | Toilet Grab Rails Installed as per spec
checkpoint-status | 9193227e-6441-4c34-86ae-9d89658188dd |  | checkpoint | Toilet Hand Wash Basin Installed as per spec
checklist-flat | e0ba4b5c-b0e9-48af-9996-96443b062a19 |  | checklist | FC - S - Windows, Sliders and Sealants |  |  |  |  | Yes | FC - S - Windows, Sliders and Sealants | d94caa89-e2f7-4481-9065-b8807bfb220b
checkpoint-status | d43258af-2521-4bd9-8067-6ac0d1501016 |  | checkpoint | Fixings and clearance around opening min 6mm & max 18mm and PEF rod/air seal are within acceptable tolerance level
checkpoint-status | 1efd7003-38e6-4d17-9b76-82607434fb75 |  | checkpoint | Check taping around, before installing the windows and sliders
checkpoint-status | 4a94555d-0a32-49be-8f6a-03f78c98ab62 |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status | 9f58ce5d-2518-4099-85aa-9962c7087b82 |  | checkpoint | Jambs level and straight for finishing lines on the side
checkpoint-status | b1717735-c7e8-487a-945c-01f44df4faab |  | checkpoint | Door and window jambs flush to GIB Board
checkpoint-status | 0021b6eb-3ca0-4985-babe-2351e6588c77 |  | checkpoint | Check air seal is provided at the rear of the window reveal
checkpoint-status | bfe033c5-feb3-48b6-a878-4e77cffcdc06 |  | checkpoint | All joints detailed as per attached Detail Document
checkpoint-status | 60515f35-8fb1-4fc5-8ced-25a79d300002 |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status | c10bb994-72e7-4057-87db-fa192b82a78b |  | checkpoint | Sill support fixing bars installed for all joinery within acceptable tolerance level
checkpoint-status | a3ff85a4-ee23-466b-ab1f-3ed5b60a7ecb |  | checkpoint | All windows, sliders and sealant installation completed to specification & within tolerance in respective area(s)
checkpoint-status | cb8ad48f-3c4e-4a16-8941-f4eeac045514 |  | checkpoint | All door stoppers installation completed to specification & within tolerance in respective area(s)
checklist-flat | 47f15dc2-8ab2-483e-be5a-b67aa4af363c |  | checklist | ST - S - Flat Bar With Gusset Installation |  |  |  |  | Yes | ST - S - Flat Bar With Gusset Installation | dd09ec1d-2b03-4098-a7cd-82959a91c700
checkpoint-status | 11a8cfad-7efe-4ea8-afea-d9b397c02aea |  | checkpoint | Flat bar correct size as per drawing
checkpoint-status | cf7c628e-4c50-4eef-ac68-2ead3866dee1 |  | checkpoint | Cast in weld plate in correct position
checkpoint-status | a252401d-4f69-448d-848e-0c1f67ef8325 |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status | d1f30b8f-10a6-4fd4-b068-0ca78971540d |  | checkpoint | Flat bar installed in correct position, plumb and level
checkpoint-status | c60dcd1f-63d7-4f59-b1b6-41f3905e4e80 |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status | 244fe9bd-21dd-454d-86db-01772c01eecb |  | checkpoint | Paint repair completed
checkpoint-status | f3362eab-c966-4adc-aadc-1362b788c5a1 |  | checkpoint | Flat bar installation completed correctly (checked location & level)
checklist-flat | 58fec189-fe05-4f36-8529-00edaf7bd597 |  | checklist | FC - S - Tapes |  |  |  |  | Yes | FC - S - Tapes | ddd3b69c-806c-47ea-8f98-53fef2251dba
checkpoint-status | 119f6aa0-6aa5-41d0-b268-c4645fe58843 |  | checkpoint | 3m taping around windows and sliders around the exterior framings as per the manufacturer specifications
holdpoint | 2bdb0fcd-a947-4f0c-809b-3907d9c5eb94 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned | d2070d2d-3413-4f1d-98e3-2d0e150950af |  | checklist | PRE - S - Nogs |  |  |  |  | Yes | PRE - S - Nogs | de72ca95-f558-4cb0-8c84-6300752487f0
checkpoint-group | 45c1564b-f055-42af-bce9-8fbb828a8e82 |  | section | Service Nogs Toilet
checkpoint-status | d8a78259-c274-4505-bdc8-91ddc5dc93c0 |  | checkpoint | Wall Vanity nogs installed
checkpoint-status | 2acbb5d7-e0ee-4e66-9b5a-6dbb043ee9b9 |  | checkpoint | Handrail and Toilet roll holder Nogs installed
checkpoint-group | bf3e43c7-dab8-44c8-ba21-cf8a33645720 |  | section | Bathroom
checkpoint-status | a691e369-e57e-4c0d-a570-f97aca8e77ad |  | checkpoint | Mirror cabinet nogs installed
checkpoint-status | d1045dc2-5994-4f82-9226-dab49e99b370 |  | checkpoint | Wall Vanity nogs installed
checkpoint-status | 087f1c19-073f-4339-be4b-136f99bf5ca2 |  | checkpoint | Toilet: Handrail nogs Installed
checkpoint-status | 3fba1853-1f03-4a49-a7c4-34a297800ab5 |  | checkpoint | Shower: Handrails nogs (3 areas) installed
checkpoint-status | a55f78af-4835-44a1-ad99-c6a03d282147 |  | checkpoint | Wall Mounted Heater nog installed
checkpoint-status | 55714ca5-d8f0-4ea2-b430-8b1eee975e2a |  | checkpoint | Towel rail nogs installed
checkpoint-status | a17ddded-1241-4a88-88bd-c7319fb81bb0 |  | checkpoint | Shower head nog installed
checkpoint-status | 1e76c206-0418-4aaa-9d6b-bebb6a1ab266 |  | checkpoint | Shower mixer nog installed
checkpoint-group | c43fac99-5906-4cba-8065-759611320459 |  | section | Laundry
checkpoint-status | ced8dc2b-c48d-48ba-9c28-b57d660334ac |  | checkpoint | Dryer nogs installed
checkpoint-status | 09882ad9-d722-42e8-bef6-e61335d0a298 |  | checkpoint | Cupboard nogs installed
checkpoint-group | 91d388e4-7fa5-4a3b-99e6-4f8d654cde23 |  | section | Service Nogs General
checkpoint-status | 19a7b03c-83ae-4c4e-864e-695835b3527b |  | checkpoint | Nogs / Service Nogs installed correctly as per plan
checklist-sectioned | a7a1ebd8-f3b7-4ae0-994d-a709770784d5 |  | checklist | FC - S - Soffits |  |  |  |  | Yes | FC - S - Soffits | e60bbe77-5f4c-445d-ba7f-5412ecdbbd01
checkpoint-group | 345960a8-319e-4d25-9a73-0255073c97d5 |  | section | Pre-Installation Checks
checkpoint-status | 0e00c2bc-f034-4de2-b326-e2695214d940 |  | checkpoint | Wiring in and anchored down for downlights, checked and accurate
checkpoint-status | 4230a526-b1eb-4752-b33a-c1cee62fc94f |  | checkpoint | Air Conditioning pre wire and pipe completed and acceptable
checkpoint-status | ec90e6d0-275a-432e-9358-40041fecd5a0 |  | checkpoint | Fire sprinklers droppers installed and acceptable
checkpoint-group | 388c1231-5210-4e1c-85bf-a33d8c208cdc |  | section | Soffits works checks
checkpoint-status | 913db335-adc8-4ca9-9470-6ba4cc45ee4a |  | checkpoint | Framing completed, checked and accurate including sheet joins/blocking
checkpoint-status | 36cc2bcc-70f6-44c8-88e4-01fb5e6316a0 |  | checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint-status | 124d087e-4522-41d7-8c25-9e8ef7dffa69 |  | checkpoint | Villaboard installed, stopped and painted, checked and acceptable
checkpoint-status | 12c665fa-718e-4d10-8d88-99e28a16cb28 |  | checkpoint | Plaster installed as per spec and painted and acceptable
checkpoint-status | 1c94abb3-4d6d-415e-ad4c-0c13e367e559 |  | checkpoint | All soffits completed and acceptable
checklist-flat | 3f1ac6e1-7263-4120-8045-c905b5f6d5e7 |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | B07 - ST - S - Precast Flat Slab Installation | e6682b2e-1aee-4700-845e-696aa238e811
checkpoint-status | bd2d62b5-0b14-43ed-a573-74fbb2496712 |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | b5587508-1643-493e-bd4d-348d67b10698 |  | checkpoint | Installed in correct location
checkpoint-status | 55c4d59b-03a2-44dc-afa3-f787be083ba2 |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status | 6035af94-1e53-474b-a405-3433ebc8f135 |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
checkpoint-status | d467eda7-22d2-49aa-9be9-881b103d73f6 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 6e7bffbd-c75f-44cb-80b1-3b57d28b9c27 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | a1514171-abb7-4eb8-8784-1d459d512dc1 |  | checklist | FC - S - Eyebrow - Canopy |  |  |  |  | Yes | FC - S - Eyebrow - Canopy | eba305e9-9d92-46ac-8bf0-ae9e061566f6
checkpoint-status | 0119472c-22bc-4472-bf90-45f62b959926 |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | ae7b8a90-793f-4905-8778-6171adc7e44f |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | 6eb5fc09-8e72-43c9-a2c0-206767263743 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | edc3787b-8af5-4731-a065-f0dd22b0c5af |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | ddf5ce7a-3c78-4208-95e7-d5b67a9a6dc4 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | cdb24237-2e04-4825-9c19-0ca270bc2635 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | b75862d1-2331-4ca9-b8bc-4cd1c9c15013 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checklist-sectioned | b753bc6d-ca40-4847-94b3-1b044d9ac69b |  | checklist | FC - S - Soffit - Pre-Installation & Timber Framing |  |  |  |  | Yes | FC - S - Soffit - Pre-Installation & Timber Framing | efab1c39-bb84-45b3-8213-a7ff745aad00
checkpoint-group | df2b825e-f6f4-4821-afd5-36c1e107dbfc |  | section | Pre-Installation Checks
checkpoint-status | a080ca95-d001-4086-9079-86a546c802d8 |  | checkpoint | Wiring in and anchored down for downlights, checked and accurate
checkpoint-status | 8987678b-0e9e-41ff-90ff-819389c010dd |  | checkpoint | Air Conditioning pre wire and pipe completed and acceptable
checkpoint-status | b663eea2-d74e-4192-93cc-3e4e662b0290 |  | checkpoint | Fire sprinklers droppers installed and acceptable
checkpoint-group | 990af52e-12cd-4142-9ee7-4786d8fcc552 |  | section | Soffits Timber Framing Checks
checkpoint-status | 5d50bc19-db7c-41d4-bca4-90cac694e0a6 |  | checkpoint | Framing completed, checked and accurate including sheet joins/blocking
checkpoint-status | 72adc580-a24a-42d3-9a97-1f2704b6d8d5 |  | checkpoint | Framing centre correct at 600mm centres, including set out to allow all sheets joints to be fully supported
checkpoint-status | cc4a2d08-affa-46ac-8092-337e21686293 |  | checkpoint | All soffit timber framing completed and acceptable
checklist-flat | 2ae8bf4f-0b77-455d-9e1c-c8016e47a8ac |  | checklist | FC - S - Gutters |  |  |  |  | Yes | FC - S - Gutters | f0cc8b93-16dd-4d0d-87bf-bd678c08d490
checkpoint-status | 4a05d0e7-52f1-4335-9718-2903b695bf62 |  | checkpoint | Setout completed, checked & accurate (no clashes & wall locations clearly marked)
checkpoint-status | c40abcd3-959f-4f7e-92ed-45b98088406c |  | checkpoint | Framing Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status | d62358e0-452a-4e30-a29c-4243a2809665 |  | checkpoint | All frames have been installed square, straight and plumb
checkpoint-status | b72b7142-8256-41a7-a8f5-9ba2b0eec50f |  | checkpoint | DPC installed (if required) correctly
checkpoint-status | 0f4ad56f-6322-4689-8cc0-898380718855 |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements (attach relevant photos)
checkpoint-status | 4c049162-32c5-403c-bac4-0dcd59de7538 |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status | 16bc5414-3bb3-4100-9219-b2b110173293 |  | checkpoint | All timber framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status | 3593a64e-1e33-4ddd-9faa-00a5dee046e8 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | a665163b-df41-46ac-995b-e215db8011ff |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | dcbe7710-7ee9-4661-bae8-6630f498800d |  | checklist | ST - S - Precast Double TEE Beam Installation |  |  |  |  | Yes | ST - S - Precast Double TEE Beam Installation | f3fb58f7-7430-4f2c-bc6b-df9dac0e63af
checkpoint-status | 2843aa89-2523-438a-ac6d-e270ab2bc339 |  | checkpoint | Inspected on arrival and damage free
checkpoint-status | 21979516-5d7c-44d2-8ce9-58b41df3c810 |  | checkpoint | Installed in correct location
checkpoint-status | 942a23fa-878a-44dd-bb46-11147a302722 |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status | 3d5417c6-8092-4637-989a-95859faf5f2c |  | checkpoint | Double TEE installation completed (checked location & level) and no damages
checklist-flat | 73870799-d23f-41a0-a679-315e93942f21 |  | checklist | FC - S - Air conditioning |  |  |  |  | Yes | FC - S - Air conditioning | fa6b5f78-6241-40e1-91aa-8b87deb5372d
checkpoint-status | 4e78c9aa-7963-40f6-a581-ee9815cc8e9e |  | checkpoint | Aircon channel installed
checkpoint-status | 42df487a-ddea-4bae-95ba-a729bdfefa3b |  | checkpoint | Aircon brackets installed
checkpoint-status | d039f54d-8e78-4af2-962a-700616f18983 |  | checkpoint | Threaded rod installed
checkpoint-status | 7efdb59b-7f85-4cb8-af3d-86a949e3ed80 |  | checkpoint | Flashing covers installed
checkpoint-status | dba639af-e6f2-4256-8fd1-2bdf57b82217 |  | checkpoint | Trade seal installed
checklist-sectioned | c8d0130f-d95c-43ee-b9eb-b101876756d3 |  | checklist | FC - S - Louvre Installation |  |  |  |  | Yes | FC - S - Louvre Installation | fd3cd229-5e86-4db7-975f-5e66ae9e9492
checkpoint-group | 01caa26a-ea27-4e2e-b6cb-d2015aed4e08 |  | section | Pre-Installation Checks
checkpoint-status | 9ece4da0-7a83-42d8-a783-ffc73acb05e4 |  | checkpoint | Pre Fit - Studding completed & setout checked
checkpoint-status | 2269b69c-0664-4aed-bcc7-8e2181bec1a3 |  | checkpoint | Waterproofing to pre-fit studs completed and acceptable
checkpoint-group | c234d3d6-e2a6-4566-974b-ac6be23e13e3 |  | section | Installation Checks
checkpoint-status | 2460c851-7836-4e8a-ab3d-8efe9914e229 |  | checkpoint | Louvres height is compliant
checkpoint-status | 691a2b04-85e6-4d29-afd5-9a13656bbba7 |  | checkpoint | No Gaps Larger than 75 mm
checkpoint-status | 3bb5f899-91ad-4664-9342-c6833583d7da |  | checkpoint | Louvre brackets installed
checkpoint-status | 49e7702a-e6fb-4243-9554-d56c4ff73621 |  | checkpoint | All bolts installed done up correctly
checkpoint-status | d9052e9b-7e3b-4d89-94cd-a0516b51112a |  | checkpoint | Endcaps in place and acceptable
checkpoint-status | 8a245ad0-9315-423f-9446-0631ed385e9e |  | checkpoint | Any paint touch ups completed
checkpoint-status | b739cee2-689d-4b9d-90f0-b375b392fbf5 |  | checkpoint | All louvre bracket installation works completed, reviewed and approved and protection installed