## Breakdown
A.G.A(Keith Park)
QA
Civil Works
B05
Ramp
[5 empty] | Footing | pre-populate | ST - S - Concrete Pour - Without Reo
[5 empty] | Insitu Wall | pre-populate | ST - S - Concrete Pour - Without Reo
|  |  |  | Clark Road Capping Beam Pour - 06/11/22 |  | pre-populate | ST - S - Concrete Pour - Without Reo
|  |  |  | Cemetry Side Capping Beam Pour - 09/11/22 |  | pre-populate | ST - S - Concrete Pour - Without Reo

## Checklists
Type | Name
checklist | ST - S - Concrete Pour - Without Reo
section | Pour Details
checkpoint | Pour details entered
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Pre-Pour Completion (Approval to pour)
checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
checkpoint | Concrete Supplier details entered
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
button | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
holdpoint | Raise remedial/ Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS