## Breakdown
|  | PROJECT BREAKDOWN |  |  |  |  | CHECKLISTS
Accurate Ceilings - Riccarton Park
Project Build QA
Stage 3 - THB11, THB13
THB11 (TH33,34,35,36)
|  |  |  | TH 33 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
|  |  |  | TH 34 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
|  |  |  | TH 35 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
|  |  |  | TH 36 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
|  |  | THB13 (TH37, 38, 39) |  |  | prepopulate | PRE - S - Suspended ceiling grids
|  |  |  | TH 37 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
|  |  |  | TH 38 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
|  |  |  | TH 39 | Ceiling Install | prepopulate | PRE - S - Suspended ceiling grids
| Compliance Documentation |  |  |  | Completion Documents | prepopulate | CST - S - Completion Documents

## QA & Compliance checklist
checklist | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist | PRE - S - Townhouse Suspended Ceilings
section | Prestart
checkpoint | Latest drawings available checked and referenced and attached
text | Drawing number(s) & Revisions
checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
section | Ceiling Grid Install
checkpoint | Ceiling height confirmed
checkpoint | Correct product delivered, reviewed and approved as per specification
checkpoint | Gib standard plasterboard screw fixed to metal ceiling system as per manufacturer specification (2-3 photos attached)
checkpoint | Appropriate fixings used and installed as per specification (2-3 photos attached)
checkpoint | Appropriate spacings for respective grid elements
checkpoint | Battens level checked and accurate
Checkpoint | Perimeter channel/angle installed correctly (2-3 photos attached)
checkpoint | Clips installed to appropriate centres
checkpoint | All strong backs installed where required to meet specification
checkpoint | All ceiling grid completed in respective area to required specification (Attach photo of respective completed grid)
holdpoint | Request sign off
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS