## Breakdown
Townhouse
Façade
Block 1
|  |  | prepopulate | Townhosue Preclosure Inspections
RAB
Builidng Wrap & Flashing Tape Installed
Cavity Batten -Espan Area
Cavity Batten- Axon Areas
Cavity Flashings
Soffit Install - Level 1 & 2
Metal Roof underlay etc
Gutters Installed
|  |  | prepopulate | Townhouse Cladding Installs
metal roof
Gutters Installed
Downpipes
Membrane Installation ( mark NA where not present)
Aluminium Window
Cladding Axon Panel
Cladding Espan 340
Soffit Lining Install - Level 1 & 2
Soffit Painting
|  |  | prepopulate | Townhouse Exterior works
TH-Exterior Balconies Waterproofing
Fabworx Blaustrades
Deck framing
Intertenancy Screens
Timber decking
Block 2
as above

## Facade
type | name
checklist | Townhosue Preclosure Inspections
section | RAB
checkpoint | RAB board installed & complete ( pass once below all signed off)
bool | Correct fixings type & patterns/Spacing
bool | Flashings installed checked and correct
bool | All joints/penetrations/openings taped as per specs
bool | Services checked, type and location
checkpoint | RAB QA received, reviewed, attached and approved
holdpoint | RAB Request inspection by Façade Engineer/ Architect/Council
checkpoint | RAB inspections by Architect done & signed off
bool | RAB Façade engineers remedials done and signed off
bool | RAB Architects remedials done and signed off
bool | RAB Council inspections carried out any remedials done
section | Builidng Wrap & Flashing Tape Installed
checkpoint | RAB board installed and signed off
checkpoint | Builidng wrap and flashing tape installed
bool | Correct fixing types & Pattern/Spacing
Bool | Flashings installed checked and correct
bool | All joints/penetrations/openings taped as per specs
bool | Services checked, type and location
checkpoint | Builiding Wrap QA received, reviewed, attached and approved
holdpoint | Requst Inspection by façade enigneer /Council and Architec
checkpoint | Building Wrap Inspections
bool | Building Warp -Architect remedials completed and signed off
bool | Building Wrap -Façade engineers remedials done and signed off
bool | Building Wrap - Council inspection carried out and any remedials complete
section | Cavity Batten -Espan Area
checkpoint | Builidng wrap and flashing tape installed and signed off
checkpoint | Cavity batten correct type and fixings installation completed, checked and approval to clad
bool | Appropriate fixings for cavity (as per design)
bool | Service penetrations complete
checkpoint | Cavity Batten QA received, reviewed, attached and approved
holdpoint | Cavity Batten - Request inspection
checkpoint | Cavity Batten - Inspection architect done and signed off
bool | Cavity Batten - Façade remedials complete and signed off
bool | Cavity Batten -Architects remedials done and signed off
bool | Cavity Batten - council remedials complete and signed off
section | Cavity Batten- Axon Areas
checkpoint | Builidng wrap and flashing tape installed and signed off
checkpoint | Cavity batten correct type and fixings installation completed, checked and approval to clad
bool | Appropriate fixings for cavity (as per design)
bool | Service penetrations complete
checkpoint | Cavity Batten QA received, reviewed, attached and approved
holdpoint | Cavity Batten - Request inspection
checkpoint | Cavity Batten - Inspection completed and signed off
bool | Cavity Batten - Façade remedials complete and signed off
bool | Cavity Batten -Architects remedials done and signed off
bool | Cavity Batten - council remedials complete and signed off
section | Cavity Flashings
checkpoint | Cavity battens installed and signed off
bool | Correct material ordered
checkpoint | Flashings Critical Lines
text | Number,Location , elevation
checkpoint | Cavity flashings QA received, reviewed, attached and approved
checkpoinnt | Cavity flashings Ssot check with Subcontractor -Installed/fixed in correct place
holdpoint | Request Cavity flashings inspections -Architect /Façade engneer
checklist | Cavity Flashings Archtiect /Façade Engineer Sign off
bool | Façade engineers remedials done and signed off
bool | Architect remedials completed and signed off
section | Soffit Install - Level 1 & 2
checkpoinnt | Trades QA received, reviewed, attached and approved
bool | Soffit Framing completed, checked and accurate inclusing sheet joins/blocking
bool | Relevant services first fix and nogging completed
checkpoint | General photos, comments and observations during installation
holdpoint | Consultant/Council Inspections requested
checkpoint | Inspections completed
bool | Façade engineers remedials done and signed off
bool | Architect remedials completed and signed off
bool | Council inspections complete
bool | Steel studd engineer remedials completed and signed off
Section | Metal Roof underlay etc
checkpoint | Roof underlay installed -ply and confirmed ok to fix over
checkpoint | Correct wrap used and fixed as per specification
checkpoint | Cavity battens installed at correct spacings and fixings for Windloading
checkpoint | Product checked and correct as per specification including fixings for windloading
checkpoint | All prestart checks completed and approval given to install Veedek
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
holdpoint | Approved for roofing install Signoff
section | Gutters Install
bool | Support framing complete
bool | Spot checks done on falls
bool | Material order made
bool | Where required waterpoofing complete
checkpoint | General comments and photos of additional paint application
checklist | Townhouse Cladding Installs
Section | Metal Roof
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | All roofing elements completed, checked and approved as per specifications
holdpoint | Request inspections
checkpoint | Inspections complete
bool | Façade engineers remedials done and signed off
bool | Architect remedials completed and signed off
Bool | Council inpection complete
section | Downpipes
checkpoint | Downpipes installed & complete
bool | Spot checks done
bool | All inspection points installed
checkpoint | General comments and photos of additional paint application
checkpoint | Trades QA received, reviewed, attached and approved
checklist | Water testing done and past
checklist | Council inspections complete
section | Membrane Installation ( mark NA where not present)
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | Mat installed as per product specification
checkpoint | General photos, comments and observations during install
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | Tanking to area completed, checked and approved as per specifications
checkpoint | Initial testing complete
checklist | Any remedials completed
holdpoint | Request Inspections
checklist | Inspections complete
bool | Manufacturer review if needed
bool | Façade engineers remedials done and signed off
bool | Architect remedials completed and signed off
bool | TCC inspection complete
section | Aluminium Window
checkpoint | Opening approved (ready for install of seismic frames)
checkpoint | Joinery in correct location
checkpoint | Nebulite QA( frames) received, reviewed, attached and approved
checkpoint | Inspection completed and joinery install completed as per specification
checkpoint | Water testing done and past
holdpoint | Request inpsection windows
checkpoint | Window inspections complete
bool | Façade engineers remedials complete and signed off
bool | Architects remedials complete and singed off
bool | Council inspection complete
section | Cladding Axon Panel
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | General photos, comments and observations during install
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Fixing type and spacing checked and correct to specification
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | All roofing elements completed, checked and approved as per specifications
holdpoint | Request inspections
bool | Façade engineers remedials complete and signed off
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off
section | Cladding Espan 340
checkpoint | Product checked and correct as per specification
checkpoint | All prestart checks completed and approval given to install
checkpoint | General photos, comments and observations during install
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Relevant Services considered, checked and approved where applicable
checkpoint | All roofing elements completed, checked and approved as per specifications
holdpoint | Request Inspections
checklist | Inspections complete
bool | Façade engineers remedials complete and signed off
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off
section | Soffit Lining Install - Level 1 & 2
checkpoinnt | Trades QA received, reviewed, attached and approved
Checkpoint | Soffits complete, ( pass when all below ticked)
bool | Soffit Framing completed, checked and accurate inclusing sheet joins/blocking
bool | Relevant services first fix and nogging completed
bool | Lining product checked and correct, all pre checks completed & approval to line
bool | Joints all neat and correct
checkpoint | General photos, comments and observations during installation
holdpoint | Inspections requested
checkpoint | Inspections completed
bool | Steel studd engineer remedials completed and signed off
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off
section | Soffit Painting
checkpoint | First coat/ sealant coat completed
checkpoint | General comments and photos of additional paint application
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Design team inspections completed
bool | Architects remedials complete and singed off
checklist | Townhouse Exterior works
Section | TH-Exterior Balconies Waterproofing
checkpoint | Waterproofing completed and water tested
Holdpoint | Request inspections
checkpoint | Inspections complete
bool | Façade engineers remedials complete and signed off
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off
section | Fabworx Blaustrades
checkpoint | Waterproofing installed and signed off
checkpoint | Trades QA received, reviewed, attached and approved
Spot check with Subcontractor -Installed in correct place and correct fixings
checkpoint | Request Inspections
bool | Façade engineers remedials complete and signed off
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off
bool | Structural engineer remedials completed
Section | Deck Framing
checkpoint | Correct jacks being used as per specification
checkpoint | Correct size/treatment bearers and fixings to jacks used
bool | position checked
bool | reduced levels at top of bearers checked
bool | Approval given to install timber joists
Text: | Relevant Drawing Numbers & Revisions
checkpoint | Correct joist size /teatment installed
bool | Dimensions / locations checked and accurate
bool | All frames are square & Level
bool | Fixings are correct type and installed correctly
bool | Any bracing requirements installed
checkpoint | General additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
holdpoint | Request Inspections
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off
section | Intertenancy Screens
checkpoint | Waterproofing installed and signed off
checkpoint | Trades QA received, reviewed, attached and approved
Spot check with Subcontractor -Installed in correct place
section | Timber Decking
hold point | Review orentation of decking
Text: | Relevant Drawing Numbers & Revisions
checkpoint | Installation of timber decking
bool | Dimensions / locations checked and accurate
bool | All frames are square & Level
bool | Fixings are correct
checkpoint | Any additional photos, comments and observations
checkpoint | Trades QA received, attached, reviewed and approved
hold point | Raise Remedial / Request trades QA / Signoff
holdpoint | Request Inspections
bool | Architects remedials complete and singed off
bool | Council remedials complete and signed off