## Northwood
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Instruction to CONQA | Checklist Name
Stage 8 (TH08-09)
TH08 (TH11 & TH12)
RFL
Structure
Tier 6: Concrete Pour (Rib Raft System) | Prepopulate | ST - S - Concrete Pour
Aqua Pro Plumbing & Drainage
Foundation
Tier 6: Underslab Plumbing | Prepopulate | F - S - Underslab plumbing
Tier 5: Fitout; Tier 6: Plumbing - First fix | Prepopulate | PRE - S - First Fix - Plumbing
Tier 6: Plumbing - Second Fix | Prepopulate | POST - S - Plumbing Second Fix
Francis & Norton Construction Ltd
Tier 5: Structure; Tier 6: Roof structure - Timber Trusses | Prepopulate | ST - S - Roof structure - Timber Trusses
Tier 5: Façade; Tier 6: Timber Framing | Prepopulate | ST - S - Timber Framing
Tier 6: RAB / Ecoply | Prepopulate | FC - S - RAB
Tier 6: External Enveloping | Prepopulate | FC - S - External Envelope
Tier 6: Soffits | Prepopulate | FC - S - Soffits
Tier 5: Fitout; Tier 6: Windows, Sliders and Sealants | Prepopulate | FC - S - Windows, Sliders and Sealants
Tier 6: Nogs | Prepopulate | PRE - S - Nogs
Tier 6: Skirting/Architraves & Trims | Prepopulate | POST - S - Skirting/ Architraves & Trims
Tier 6: Internal Door Installation | Prepopulate | POST - S - Internal door installation
Richie's Brick & Block Limited
Tier 5: Façade | Prepopulate | FC - S - Brick Works
Tier 5: Individual letter boxes (Brick works) | Prepopulate | FC - S - Brick Works
Waterproofing Concept Ltd
Façade
Tier 6: Roof - Flat | Prepopulate | FC - S - Roofing
GG Don Plumbing, Roofing & Sheetmetal
Tier 5: Façade; Tier 6: Roof - Pitched | Prepopulate | FC - S - Roofing
Tier 6: Roof /Flashings (Ridge/Valley/Hips) | Prepopulate | FC - S - Roofing Iron/Flashings
Tier 6: Fascia/Gutter Installation | Prepopulate | FC - S - Fascia/Gutter
Tier 6: Down Pipes | Prepopulate | FC - S - Down Pipes
HPAC
Tier 5: Façade; Tier 6: Heatpump Installation | Prepopulate | S - S - Air conditioning
Premier Plastering Christchurch Limited
Tier 5: Façade; Tier 6: Nibs and beams | Prepopulate | FC - S - External Plaster - Nibs & Beams
Tier 6: STO Poly Plaster | Prepopulate | FC - S - STO Poly Plaster
Kings Electrical
Tier 5: Foundation; Tier 6: Undergound services (Electrical Conduit) | Prepopulate | F - S - Underground services
Tier 5: Fitout; Tier 6: Electrical - First Fix | Prepopulate | PRE - S - First Fix - Electrical
Tier 6: Electrical - Second Fix | Prepopulate | Post - S - Second Fix - Electrical
Tier 6: Underfloor heating | Prepopulate | POST - S - Underfloor heating
NCS
Tier 5: Foundation; Tier 6: Undergound services (Communication/Data Conduit) | Prepopulate | F - S - Underground services
Tier 5: Fitout; Tier 6: Nurse call, Data, Communication & Security - First fix | Prepopulate | PRE - S - First Fix - Nurse Call, Data & Communications & Security
GK Fyfe & Associates Limited
Tier 5: Façade; Tier 6: Soffits (painting of) | Prepopulate | FC - S - Soffits
Tier 5: Fitout; Tier 6: Internal Lining - Walls (incl.supply) | Prepopulate | POST - S - Internal Lining - Walls
Tier 6: Internal Lining - Ceilings (incl.supply) | Prepopulate | POST - S - Internal Lining - Ceilings
Tier 6: Stopping | Prepopulate | POST - S - Stopping
Tier 6: Painting | Prepopulate | POST - S - Painting
Hush Interiors
Tier 5: Fitout; Tier 6: Suspended Ceiling Grid | Prepopulate | PRE - S - Suspended ceiling grids
Aspire Joinery
Tier 5: Fitout; Tier 6: Kitchen - incl. sealant | Prepopulate | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes
Tier 6: Ensuite/Bathroom/Laundry/Wardrobe | Prepopulate | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes
Turtle Tiling
Tier 5: Fitout; Tier 6: Bathroom (Shower Floor) | Prepopulate | POST - S - Screeding
Tier 6: Bathroom/Ensuite/WC | Prepopulate | POST - S - Internal Waterproofing & Tiling - Bathrooms & WC
Tier 6: Laundry/Kitchen | Prepopulate | POST - S - Tiling
Carpet Court
Tier 5: Fitout; Tier 6: Carpet installation | Prepopulate | POST - S - Carpet Installation
Dyers Road Timber (T/A VIP Install)
Tier 5: Fitout; Tier 6: Insulation - Ceiling | Prepopulate | PRE - S - Insulation
Tier 6: Insulation - Wall | Prepopulate | PRE - S - Insulation
TH09 (TH13, TH14, TH15 & TH16)
RFL
Structure
Tier 6: Concrete Pour (Rib Raft System) | Prepopulate | ST - S - Concrete Pour
Aqua Pro Plumbing & Drainage
Foundation
Tier 6: Underslab Plumbing | Prepopulate | F - S - Underslab plumbing
Tier 5: Fitout; Tier 6: Plumbing - First fix | Prepopulate | PRE - S - First Fix - Plumbing
Tier 6: Plumbing - Second Fix | Prepopulate | POST - S - Plumbing Second Fix
Francis & Norton Construction Ltd
Tier 5: Structure; Tier 6: Roof structure - Timber Trusses | Prepopulate | ST - S - Roof structure - Timber Trusses
Tier 5: Façade; Tier 6: Timber Framing | Prepopulate | ST - S - Timber Framing
Tier 6: RAB / Ecoply | Prepopulate | FC - S - RAB
Tier 6: External Enveloping | Prepopulate | FC - S - External Envelope
Tier 6: Soffits | Prepopulate | FC - S - Soffits
Tier 5: Fitout; Tier 6: Windows, Sliders and Sealants | Prepopulate | FC - S - Windows, Sliders and Sealants
Tier 6: Nogs | Prepopulate | PRE - S - Nogs
Tier 6: Skirting/Architraves & Trims | Prepopulate | POST - S - Skirting/ Architraves & Trims
Tier 6: Internal Door Installation | Prepopulate | POST - S - Internal door installation
Richie's Brick & Block Limited
Tier 5: Façade | Prepopulate | FC - S - Brick Works
Tier 5: Individual letter boxes (Brick works) | Prepopulate | FC - S - Brick Works
Waterproofing Concept Ltd
Façade
Tier 6: Roof - Flat | Prepopulate | FC - S - Roofing
GG Don Plumbing, Roofing & Sheetmetal
Tier 5: Façade; Tier 6: Roof - Pitched | Prepopulate | FC - S - Roofing
Tier 6: Roof /Flashings (Ridge/Valley/Hips) | Prepopulate | FC - S - Roofing Iron/Flashings
Tier 6: Fascia/Gutter Installation | Prepopulate | FC - S - Fascia/Gutter
Tier 6: Down Pipes | Prepopulate | FC - S - Down Pipes
HPAC
Tier 5: Façade; Tier 6: Heatpump Installation | Prepopulate | S - S - Air conditioning
Premier Plastering Christchurch Limited
Tier 5: Façade; Tier 6: Nibs and beams | Prepopulate | FC - S - External Plaster - Nibs & Beams
Tier 6: STO Poly Plaster | Prepopulate | FC - S - STO Poly Plaster
Kings Electrical
Tier 5: Foundation; Tier 6: Undergound services (Electrical Conduit) | Prepopulate | F - S - Underground services
Tier 5: Fitout; Tier 6: Electrical - First Fix | Prepopulate | PRE - S - First Fix - Electrical
Tier 6: Electrical - Second Fix | Prepopulate | Post - S - Second Fix - Electrical
Tier 6: Underfloor heating | Prepopulate | POST - S - Underfloor heating
NCS
Tier 5: Foundation; Tier 6: Undergound services (Communication/Data Conduit) | Prepopulate | F - S - Underground services
Tier 5: Fitout; Tier 6: Nurse call, Data, Communication & Security - First fix | Prepopulate | PRE - S - First Fix - Nurse Call, Data & Communications & Security
GK Fyfe & Associates Limited
Tier 5: Façade; Tier 6: Soffits (painting of) | Prepopulate | FC - S - Soffits
Tier 5: Fitout; Tier 6: Internal Lining - Walls (incl.supply) | Prepopulate | POST - S - Internal Lining - Walls
Tier 6: Internal Lining - Ceilings (incl.supply) | Prepopulate | POST - S - Internal Lining - Ceilings
Tier 6: Stopping | Prepopulate | POST - S - Stopping
Tier 6: Painting | Prepopulate | POST - S - Painting
Hush Interiors
Tier 5: Fitout; Tier 6: Suspended Ceiling Grid | Prepopulate | PRE - S - Suspended ceiling grids
Aspire Joinery
Tier 5: Fitout; Tier 6: Kitchen - incl. sealant | Prepopulate | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes
Tier 6: Ensuite/Bathroom/Laundry/Wardrobe | Prepopulate | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes
Turtle Tiling
Tier 5: Fitout; Tier 6: Bathroom (Shower Floor) | Prepopulate | POST - S - Screeding
Tier 6: Bathroom/Ensuite/WC | Prepopulate | POST - S - Internal Waterproofing & Tiling - Bathrooms & WC
Tier 6: Laundry/Kitchen | Prepopulate | POST - S - Tiling
Carpet Court
Tier 5: Fitout; Tier 6: Carpet installation | Prepopulate | POST - S - Carpet Installation
Dyers Road Timber (T/A VIP Install)
Tier 5: Fitout; Tier 6: Insulation - Ceiling | Prepopulate | PRE - S - Insulation
Tier 6: Insulation - Wall | Prepopulate | PRE - S - Insulation