## Breakdown
Keith Park(Solid Masonry)
B06/ B07 Ramp
|  | Blockwall | Pre-populate | ST - S - Blockwork

## checklist
checklist-flat | ST - S - Blockwork
checkpoint | Grids available for reference and base of wall marked accurately, RL reference/top of wall (TOW) confirmed
checkpoint | Base of wall in correct location
checkpoint | Horizontal reinforcing installed correctly (centres/ size / splicing etc)
checkpoint | Ties / Control joints installed as required
checkpoint | Vertical reinforcing installed as required with appropriate splice
checkpoint | Openings checked and correct - location, height and width
checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
checkpoint | Concrete specifications checked and correct
checkpoint | All blocks filled to correct height
checkpoint | Starter bars in centre of block if applicable
checkpoint | Blockwork wall(s) complete to required specification
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS