## Sheet1
Miriam Corban - Aquaproofing
QA
B01
Area A
|  |  |  | Roof membrane | Prepopulate | FC - S - Roofing
Area B
|  |  |  | Roof membrane | Prepopulate | FC - S - Roofing
Area C
|  |  |  | Roof membrane | Prepopulate | FC - S - Roofing
Area D
|  |  |  | Roof membrane | Prepopulate | FC - S - Roofing
Area E
|  |  |  | Roof membrane | Prepopulate | FC - S - Roofing
|  | Completion Documents |  |  | Prepopulate | CST - S - Completion Documents

## Sheet2
checklist | FC - S - Roofing
section | Pre-installation checks
checkpoint | Scaffolding in place and tagged
checkpoint | Edge protection and safety nets installed
checkpoint | Correct Purlin / Steelwork heights
checkpoint | Correct Precast wall heights
checkpoint | Observations
section | Plywood Gutter Substrate
checkpoint | Plywood laid a minimum 0.5 degrees
checkpoint | Plywood surface smooth finish CD minimum 1.75mm H3 no knots
checkpoint | Plywood laid with 2mm gaps
checkpoint | Plywood fastened with stainless steel screws recessed 2mm
checkpoint | Outlets installed correctly 73-75mm above plywood
checkpoint | Observations
section | Steel Tray Substrate
checkpoint | Metal profile installed upside down with fastenings spaced correctly
checkpoint | Flashings installed on hips and valleys
checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint | Outlets framed and plywood routed out
checkpoint | Unused Roofing Iron Secured
checkpoint | Observations
section | Insulation panels
checkpoint | Sheets installed in brick-bond pattern
checkpoint | No gaps between sheets
checkpoint | Adhesive applied evenly and at correct amount
checkpoint | Sheets held down for correct length of time
checkpoint | Roof is confirmed uniform and flat
checkpoint | Observations
section | Membrane
checkpoint | Insulation panels are acceptable level of cleanliness
checkpoint | Membrane colour and thickness confirmed correct
checkpoint | Membrane penetrations have been sealed and are watertight
checkpoint | All welded seams and proprietary items to be seam probed
checkpoint | Observations
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS