## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | ITP - Type A Pavement |  |  |  |  | Yes | ITP - Type A Pavement | fb34c0f5-281f-4e52-be05-c8346d70ed7a
checkpoint-group | Pre-construction / Preliminary Compliance Requirements
checkpoint-status | 600.1 - Method Statement Development / Job Safety Analysis / Enviro Site Specific Plans
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority
label | Responsibility - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.2 - Drawings and Specification
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - DWG’s and Specifications are of For Construction and latest revision. Reviewed and approved by Designer and Client.
label | Responsibility - Downer
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.3 - Set out
label | H
label | Minimum Test Frequency - Prior to Construction
label | Acceptance Criteria - Set out as per latest Design Model / For Construction Drawings.
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.4 - Material Approvals
label | Detail of Activity - Submit testing data fir the following materials: - AP65 -GAP 40 -GAP 20 -Hardfill
label | H
label | Minimum Test Frequency - Prior to Construction
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Material approvals to be sent to the Engineer. Refer Project Specs and Drawings;
label | • Recycled Pavement/Subgrade Improvement Material:
label | • AP40:
label | ○ CBR >20%
label | ○ Sand Equivalent > 20
label | ○ Grading < 35% passing 75um sieve
label | • AP65:
label | ○ Crushing Resistance < 100kN
label | ○ Weathering Quality Index of A,AB, AC, BA, BB or CA
label | ○ Sand Equivalent ≥ 25 if > 4% passing 75um sieve
label | ○ CBR minimum 40 using heavy compaction
label | ○ Grading
label | Responsibility - Designer
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.5 - Materials Approvals
label | H
label | Minimum Test Frequency - Prior To Construction
label | Acceptance Criteria - Ensure underground services are positively identified and asbuilt. Where this interferes with design permanent works, Service provider and Designer to be notified immediately.
label | Record documents - InEight Records
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | Construction and Finishing
checkpoint-status | 600.6 - Existing Pavement Assessment
label | Detail of Activity - Confirm Pavement Depth
label | H
label | Minimum Test Frequency - 50m centres
label | Inspection / Test method - Test Pits / Visual Inspection
label | Acceptance Criteria - Mill 200mm. Dig/core test pits to confirm if existing pavement:
label | – If existing underlying pavement is of sufficient depth (i.e. ≥250mm below mill surface/≥450mm below finished level), continue with "Existing Pavement" steps below (light green rows).
label | – If insufficient depth or poor quality, advise WSP Engineer, mill/excavate to 450mm from FL, and complete "Full New Pavement" requirements below (light blue rows for Recycled or Mixed Materials, light yellow rows for Engineered Material only - i.e. AP65,).
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Existing pavement to measure 450mm from finished level (minimum). If not "Full New Pavement" requirements are to be followed.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.7 - Existing Pavement Assessment
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Beam Testing
label | Acceptance Criteria - Review beam test results to determine if undercuts are required.
label | <1mm:
label | – No Undercut
label | 1 - 2.5mm Beam Deflection:
label | – Undercut 50mm
label | – Backfill with 20/40 drainage aggregate
label | 2.5 - 5mm Beam Deflection:
label | – Undercut 100mm
label | – Backfill with AP65
label | 5+ mm Beam Deflection:
label | – Undercut 200mm
label | – Backfill with AP65
label | Record documents - QC Sheets / Lab Result Sheet
label | Responsibility - Contractor
checkpoint-status | 600.8 - Existing Pavement Assessment
label | Detail of Activity - Milled Surface Stringlines
label | M
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Finished Level – String Line, +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | Record documents - QC Sheets (String Sheet)
label | Responsibility - Contractor
checkpoint-status | 600.9 - Existing Pavement - Subbase Stabilising (During Construction)
label | Detail of Activity - Mat Samples (1m2 canvas)
label | W
label | Minimum Test Frequency - 1 mat weighed every 400m2
label | Inspection / Test method - Mat Samples
label | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.10 - Existing Pavement - Subbase Stabilising (During Construction)
label | Detail of Activity - Plateau Density Test
label | W
label | Minimum Test Frequency - 1 Plateau Density Test per lot
label | Inspection / Test method - NDM
label | Acceptance Criteria - Determine minimum number of roller passes required to reach peak compaction strength using both primary compaction and finishing compaction rollers.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.11 - Existing Pavement - Subbase Stabilising (During Construction)
label | Detail of Activity - Stabilisation Depth
label | M
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - Visual Inspection (with tape measure)
label | Acceptance Criteria - Stabilised to 200mm depth.
label | Record documents - QC Sheets (Photos)
label | Responsibility - Contractor
checkpoint-status | 600.12 - Existing Pavement - Subbase Stabilising (Post Construction)
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Benkleman Beam
label | Acceptance Criteria - ≤ 2mm deflection
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.13 - Existing Pavement - Subbase Stabilising (Post Construction)
label | Detail of Activity - Stabilised Depth
label | M
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Core Visual Inspection
label | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | • Grading of aggregate (i.e. good mix of different stone sizes)
label | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | Record documents - QC Sheets (Photos / Coring Report)
label | Responsibility - Contractor
checkpoint-status | 600.14 - Existing Pavement - Subbase Stabilising (Post Construction)
label | Detail of Activity - Stringlines
label | H
label | Minimum Test Frequency - Every 10m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | Tolerance: +10mm/-30mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.15 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | Detail of Activity - Subgrade Levels
label | H
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Cut subgrade to 450mm below finished level.
label | • String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.16 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | Detail of Activity - Scala Penetrometer
label | H
label | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | Inspection / Test method - Scala Penetrometer
label | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | • ≥ 3 blows per 100mm - No Undercut
label | • 2-3 blows per 100mm - 200mm Undercut
label | • 1-2 blows per 100mm - 300mm Undercut
label | • <1 blow per 100mm - 450mm Undercut
label | Record documents - QC Sheets (Scala Sheet)
label | Responsibility - Contractor
label | Comments - Scala results to meet or exceed per below:
label | • 0mm - 100mm - ≥ 3 blows per 100mm
label | • 100mm - 200mm - ≥ 2 blows per 100mm
label | • 200mm - 300mm - ≥ 2 blows per 100mm
label | • 300mm - 400mm - ≥ 1 blow per 100mm
label | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.17 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Layer
label | Detail of Activity - Proof Roll
label | H
label | Minimum Test Frequency - One per lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut
label | • 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
label | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.18 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | Detail of Activity - Undercut Measurements
label | M
label | Minimum Test Frequency - Every undercut section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Measure and record undercut area and depth
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
checkpoint-status | 600.19 - Full Depth New Pavement - Recycled/Mixed Material - Subgrade Improvement Layer
label | Detail of Activity - Backfill Layers
label | M
label | Minimum Test Frequency - Every 20m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Use recycled pavement (millings), Hardfill or AP65 if available.
label | • We propose to use proof roll instead of NDM testing because of the variablity of the recycled material and the bitumen content in it making it hard to test. This supersedes clause 22.2.1 in the project Specification.
checkpoint-status | 600.20 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Layer
label | Detail of Activity - Construct Subbase
label | M
label | Minimum Test Frequency - Per Lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Construct subbase with 200mm of millings and top up with AP65 if needed. (330mm below TOK)
label | • Add 50mm of 20-40 drainage material. (280mm below TOK)
label | • Ensure material is compacted and enough volume to be stabilised.
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Check each layer with strings
checkpoint-status | 600.21 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Mat Samples (1m2 canvas)
label | W
label | Minimum Test Frequency - 1 mat weighed every 400m2
label | Inspection / Test method - Mat Samples
label | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.22 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Plateau Density Test
label | W
label | Minimum Test Frequency - 1 Plateau Density Test per lot
label | Inspection / Test method - NDM
label | Acceptance Criteria - Determine minimum number of roller passes to achieve peak/maximum density using both primary compaction and finishing compaction rollers.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.23 - Full Depth New Pavement - Recycled/Mixed Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Stabilisation Depth
label | M
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - Visual Inspection (with tape measure)
label | Acceptance Criteria - Stabilised to 200mm depth.
label | Record documents - QC Sheets (Photos)
label | Responsibility - Contractor
checkpoint-status | 600.24 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Beam Test
label | H
label | Minimum Test Frequency - 20m centres, alternating wheel tracks where possible
label | Inspection / Test method - Benkleman Beam
label | Acceptance Criteria - ≤ 2mm deflection
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.25 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Depth
label | M
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Core Visual Inspection
label | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | • Grading of aggregate (i.e. good mix of different stone sizes)
label | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | Record documents - QC Sheets (Photos / Coring Report)
label | Responsibility - Contractor
checkpoint-status | 600.26 - Full Depth New Pavement - Recycled/Mixed Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stringlines
label | H
label | Minimum Test Frequency - Every 10m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Layer Finished Level – String Line, each lane. Tolerance: +10mm/-30mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.27 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | Detail of Activity - Subgrade Levels
label | H
label | Minimum Test Frequency - 20m centres
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Cut subgrade to 450mm below finished level.
label | • String line tolerance to be within +20mm/-50mm (i.e. 20mm high, 50mm deep)
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - Remove to waste and excavate 530mm from top of kerb / 450mm from finished surface level.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.28 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | Detail of Activity - Scala Penetrometer
label | H
label | Minimum Test Frequency - Inferred CBR, 5 tests per 500m2. 1 per 20lm
label | Inspection / Test method - Scala Penetrometer
label | Acceptance Criteria - Scala (bearing Strength on insitu subgrade) to depth 500mm, with the following requirement to be achieved;
label | • ≥ 3 blows per 100mm - No Undercut
label | • 2-3 blows per 100mm - 200mm Undercut
label | • 1-2 blows per 100mm - 300mm Undercut
label | • <1 blow per 100mm - 450mm Undercut
label | Record documents - QC Sheets (Scala Sheet)
label | Responsibility - Contractor
label | Comments - Scala results to meet or exceed per below:
label | • 0mm - 100mm - ≥ 3 blows per 100mm
label | • 100mm - 200mm - ≥ 2 blows per 100mm
label | • 200mm - 300mm - ≥ 2 blows per 100mm
label | • 300mm - 400mm - ≥ 1 blow per 100mm
label | • 400mm - 500mm - ≥ 1 blow per 100mm
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.29 - Full Depth New Pavement - Engineered Material - Subgrade Layer
label | Detail of Activity - Proof Roll
label | H
label | Minimum Test Frequency - One per lot
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Proof roll – Check for uniformity, soft areas to be undercut 200mm and backfilled with recycled pavement, AP40 Hardfill or AP65.
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
label | Comments - Backfilled with recycled pavement (millings), Hardfill or AP65.
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.30 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | Detail of Activity - Undercut Measurements
label | M
label | Minimum Test Frequency - Every undercut section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Measure and record undercut area and depth
label | Record documents - QC Sheets/Site records
label | Responsibility - Contractor
checkpoint-status | 600.31 - Full Depth New Pavement - Engineered/Quarry/AP65 Material - Subgrade Improvement Layer
label | Detail of Activity - Backfill Layers
label | M
label | Minimum Test Frequency - Every 20m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Backfill and compact in 160mm-200mm layers
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.32 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - MDD and OWC
label | M
label | Minimum Test Frequency - MDD and OWC 1 test per 5000m² laid
label | Inspection / Test method - Laboratory Test
label | Acceptance Criteria - Report value only
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
checkpoint-status | 600.33 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Mat Samples (1m2 canvas)
label | W
label | Minimum Test Frequency - 1 mat weighed every 400m2
label | Inspection / Test method - Mat Samples
label | Acceptance Criteria - Subbase to be stabalised with 3% cement.
label | • Keep record of tonnage of stabilisation agent (cement) used per area 14. kg/m2 +/- 0.5kg/m2.
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.34 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Plateau Density Test
label | W
label | Minimum Test Frequency - 1 Plateau Density Test per lot (take samples from behind stabiliser as required - min 3 - for lab testing to determine moisture correction)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Determine minimum number of roller passes required to meet 95% MDD using both primary compaction and finishing compaction rollers. Report values. Used for moisture contect correction
label | Record documents - QC Sheets
label | Responsibility - Contractor
checkpoint-status | 600.35 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Stabilisation Depth
label | M
label | Minimum Test Frequency - Once per lot
label | Inspection / Test method - Visual Inspection (with tape measure)
label | Acceptance Criteria - Stabilised to 200mm depth.
label | Record documents - QC Sheets (Photos)
label | Responsibility - Contractor
checkpoint-status | 600.36 - Full New Pavement - Engineered/Quarry/AP65 Material - Subbase Stabilising (During Construction)
label | Detail of Activity - Indirect Tensile Strength (ITS)
label | H
label | Minimum Test Frequency - Two (2) soaked & two (2) dry ITS - taken by IANZ accredited lab technician behind hoe
label | Inspection / Test method - Laboratory Test
label | Acceptance Criteria - Dry ITS > 500 Kpa
label | • Soaked ITS >450 Kpa
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.37 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Subbase Compaction
label | H
label | Minimum Test Frequency - Backscatter NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Mean ≥ 95% MDD, Min ≥ 92%
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.38 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Subbase Compaction
label | H
label | Minimum Test Frequency - Direct Transmission NDM (1 per 200m2)
label | Inspection / Test method - NDM
label | Acceptance Criteria - Tests to be completed at 100mm depth increments starting at 200mm depth. Check for consistency/uniformity in test results.
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.39 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stabilised Depth
label | M
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Core Visual Inspection
label | Acceptance Criteria - Cohesivity (cores hold together to be removed)
label | • Grading of aggregate (i.e. good mix of different stone sizes)
label | • Stabilised depth - Tolerance: 200mm +20mm / -60mm
label | Record documents - QC Sheets (Photos / Coring Report)
label | Responsibility - Contractor
checkpoint-status | 600.40 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Indirect Tensile Strength (ITS)
label | H
label | Minimum Test Frequency - Cores (1 per 2000m2, minimum 3 per lot)
label | Inspection / Test method - Laboratory Test
label | Acceptance Criteria - Target lab results.
label | Tolerance: Lab result +/- 25%
label | Record documents - IANZ Accredited Lab Results
label | Responsibility - WSP Laboratory
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.41 - Full New Pavement - Engineered/Quarry/AP65 Material - Stabilised Subbase (Post Construction)
label | Detail of Activity - Stringlines
label | H
label | Minimum Test Frequency - Every 10m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Layer Finished Level – String Line, each lane
label | Tolerance: +10mm/-30mm
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | Close Out
checkpoint-status | 600.27 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Record documents - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.28 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - As-built to be submitted at the completion of construction
label | Acceptance Criteria - As-built to be submitted at the completion of construction
label | Information to be captured: Maintain Redline drawings through works.
label | Record documents - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 600.29 - RAMM Data
label | H
label | Inspection / Test method - Info to be submitted by the completion of project construction
label | Acceptance Criteria - Information to be captured:
label | Record documents - N/A
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | Client Final Inspection - Contractor
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | Contractor's Rep Name:
holdpoint | Add Signature
checkpoint-status | Client Final Inspection - BBO Engineer
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | BBO Engineers Rep Name:
holdpoint | Add Signature