## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Data Plate & Access Point |  |  |  |  | Yes | Data Plate & Access Point (Anchor Points) | 0516253e-3154-4731-9497-98120a11e20b
checkpoint-status |  |  | checkpoint | Details of Data Plate
select | 403b708d-bbc6-5181-8eaa-94e7135a8653 |  | dropdown | Has the Data Plate been installed on site? | Yes,No
label | 25cdc082-83be-5a8b-af4e-f4494ab4327c |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Data Plate
checkpoint-status |  |  | checkpoint | Details of Access Point
select | 72bb6808-fd13-55c0-a64c-26196c3ab360 |  | dropdown | Has the Access Point been confirmed? | Yes, No
label | c72eca94-0dd4-55b1-b651-27609d1548c9 |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Access Area
checklist-flat |  |  | checklist | Practical Completion |  |  |  |  | Yes | Practical Completion | 14a01c40-5c5d-41ec-bb8f-0736b5fcb547
checkpoint-no-status |  |  | checkpoint | System installed and ready for review from Project Manager.
holdpoint |  |  | signoff | Request Review from PM
checkpoint-status |  |  | checkpoint | Project Manager has reviewed, checked and approved system.
checkpoint-status |  |  | checkpoint | PM to send to PBI admin to close out and archive
checklist-flat |  |  | checklist | Pre-Fit Off Checklist |  |  |  |  | Yes | Pre-Fit Off Checklist | 1ac1f32a-442d-48fb-83e0-86572827a43a
checkpoint-status |  |  | checkpoint | Confirm structure is in accordance to the details provided
label | f33b5857-8198-41c5-971a-8ab0ef42c8f7 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Plinths/ bases/post installed in accordance with details provided
checkpoint-status |  |  | checkpoint | Photos taken
checklist-flat |  |  | checklist | Rail Checklist |  |  |  |  | Yes | Rail Checklist | 1c3caaa1-aa4b-4570-9699-2bb9783cdbc7
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | e8290b74-d9f4-4fff-8ae6-12b9cea20415 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Description input of location / person Rail systems shuttle left with
text | ca58e151-497c-4575-8066-88012502f631 |  | textbox | Location / Person:
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Data Plate, Access Point & Carriages/Travellers |  |  |  |  | Yes | Data Plate, Access Point & Carriages/Travellers | 27a96e22-a043-4d60-bb39-da626c9398b0
checkpoint-no-status |  |  | checkpoint | Details of Data Plate
select | 63469906-f15a-5496-8221-9448894bafda |  | dropdown | Has the Data Plate been installed on site? | Yes,No
label | d20042fa-7b7b-59f5-810f-ad0743858b6a |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Data Plate
checkpoint-no-status |  |  | checkpoint | Details of Access Point
select | 0e6a920d-bef6-5104-bb3f-af69c22c9a99 |  | dropdown | Has the Access Point been confirmed? | Yes, No
label | d0ddc701-4f77-5d80-a6ea-7cf06d1fbdaf |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Access Area
checkpoint-no-status |  |  | checkpoint | Details of Rail Carriages/Cable Travellers
select | e64fb688-5f88-58ac-a761-ee142bdb13e1 |  | dropdown | Has the Rail Carriages/Cable Travellers been left on site | Yes, No
label | 09d4b280-ffd0-5382-8504-c7adb1ec24a9 |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of carriages/travellers
checklist-flat |  |  | checklist | Fit Off Checklist - Line (250m Plus and Joiner) |  |  |  |  | Yes | Fit Off Checklist - Line (250m Plus and Joiner) | 360c7e42-13a9-4737-9e76-16a2c4007f02
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 2591b6a8-a436-50d4-8af4-478f627bb0ac |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of line pull test - 4 photos required
checkpoint-status |  |  | checkpoint | Photo taken of Swages - 12 photos required
checkpoint-status |  |  | checkpoint | Photo taken of line pull test - 4 photos required of joiner
checkpoint-status |  |  | checkpoint | Photo taken of Swages - 12 photos required of joiner
checkpoint-status |  |  | checkpoint | Photo taken of Joiner - 1 photo required
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Fit Off Checklist - Line |  |  |  |  | Yes | Fit Off Checklist - Line | 5f80ab59-cb9b-44a1-b88e-0fa84d784bb9
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 6242ec89-db8b-4c92-ac8b-40331fb90cc3 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of line pull test and swages
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Variations |  |  |  |  | Yes | Add Variations | 88b511a0-85cf-43a1-adc3-957edd30b0f0
checkpoint-no-status |  |  | checkpoint | Photographic evidence added
checklist-flat |  |  | checklist | Data Plate, Access Point |  |  |  |  | Yes | Data Plate, Access Point (Rails and Line Systems) | 9f07b273-e76f-4962-894c-c2f37d7b1a31
checkpoint-status |  |  | checkpoint | Details of Data Plate
select | 03dbc1b0-6c85-5fd6-9c79-02119790a5a9 |  | dropdown | Has the Data Plate been installed on site? | Yes,No
label | e6f87b3b-155f-5f80-adb6-52ec0ea6aa75 |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Data Plate
checkpoint-status |  |  | checkpoint | Details of Access Point
select | 3595d2fb-d76d-5d6d-9507-7cfd76a66eec |  | dropdown | Has the Access Point been confirmed? | Yes, No
label | 1519de5b-6974-522a-90f4-a2e518b6206a |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Access Area
checkpoint-status |  |  | checkpoint | Details of Rail Carriages/Cable Travellers
select | cbbac47e-949a-5f10-808b-f06ea571d2bd |  | dropdown | Has the Rail Carriages/Cable Travellers been left on site | Yes, No
label | c5d0da41-9c6a-5274-9963-cc4aac0a9fb6 |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of carriages/travellers
checklist-flat |  |  | checklist | Fit Off Checklist - Line (250m or less) |  |  |  |  | Yes | Fit Off Checklist - Line (250m or less) | b3342702-df49-4f7d-9570-5b17f3cc00d2
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | c057f622-89f1-53fd-b96b-1987af5e38ee |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of line pull test - 4 photos required
checkpoint-status |  |  | checkpoint | Photo taken of Swages - 12 photos required
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Fit Off Checklist - Miscellaneous Item |  |  |  |  | Yes | Fit Off Checklist - Miscellaneous Item | b3ab64ac-66ef-4464-9d41-3a098cda6439
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 31d45639-4a4a-4893-9d3e-5407e3a8b1f5 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photos taken of installed item
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Practical Completion |  |  |  |  | Yes | SYS - PT - Practical Completion | c0b83ee7-b027-4bb5-bc37-1db12b31713e
checkpoint-no-status |  |  | checkpoint | System installed and ready for review from Project Manager.
holdpoint |  |  | signoff | Request Review to PM
checkpoint-status |  |  | checkpoint | Project Manager has reviewed, checked and approved system.
checkpoint-status |  |  | checkpoint | PM to send to PBI admin to close out and archive
holdpoint |  |  | signoff | Send to PBI Admin
checklist-flat |  |  | checklist | Fit Off Checklist - Ladder System |  |  |  |  | Yes | Fit Off Checklist - Ladder System | cc2fbefe-b390-481d-8dfd-50a5eb514969
checkpoint-status |  |  | checkpoint | Installed to manufacturer or PBI Installation instructions
checkpoint-status |  |  | checkpoint | Installed as per AS1657:2018
checkpoint-status |  |  | checkpoint | All fixings secure
checkpoint-status |  |  | checkpoint | Top step of ladder flush with either walk-off kit or building edge
checkpoint-status |  |  | checkpoint | No unsealed penetrations to the roof
select | e818fe12-6246-53f0-9a63-1f49e8cfaa6c | DataPoint is missing 'select' values | dropdown | If caged, cage start between 2m and 2.2m from ground level?
select | ad2e32ba-e540-5754-8d49-896e9a0dba32 | DataPoint is missing 'select' values | dropdown | If ladder is above 3.5m, does it contain a cage?
select | 9775424e-dddf-576c-9c8f-1181d0808835 | DataPoint is missing 'select' values | dropdown | If ladder is above 6m, does it have a mid-way platform?
checkpoint-status |  |  | checkpoint | Photo uploaded of clean work area
label | aa4e23aa-e2dc-5825-b468-4ee2d3107778 |  | note | 1 photo required
checkpoint-status |  |  | checkpoint | Video taken
label | bf9baba5-e020-5af6-8b81-282938aadd68 |  | note | 1 photo required
checklist-flat |  |  | checklist | Fit Off Checklist - Anchor |  |  |  |  | Yes | Fit Off Checklist - Anchor | e24aadf0-789c-4eca-a9cc-537016bae12c
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 10b13284-475d-4dd5-8ace-bbc47a64d07b |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Required number of photo(s) taken of installed anchor(s)
select | 075e8ef5-42fb-423c-9690-730db3d03787 |  | dropdown | Anchor Type | FROG 1 photo req,L4543 2 photos req,L4544 3 photos req,L4550 2 photos req,L4551 2 photos req,L4552 2 photos req,M16 Chemset 2 photos req,M16 Through BOLT 2 photos req,SAFETOR 3 photos req,Spiratech 1 photo req
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Roof Access Requirements |  |  |  |  | Yes | Roof Access Requirements | e577b931-5067-4dd7-88be-70a4a81714bf
checkpoint-status |  |  | checkpoint | Brief description of roof access requirements for Recert Team
text | 0334d05e-4855-5b04-b088-823ae99e302b |  | textbox | Description
checklist-flat |  |  | checklist | Overall Pre-start |  |  |  |  | Yes | SYS - PT - Overall Pre-start | f2c44c2a-44ca-40d1-8700-e071c83679ae
checkpoint-status |  |  | checkpoint | Overall Pre-start
text | c0560214-57ff-57e5-8e5d-48f63e9b2f7a |  | textbox | Job Number and Name
text | b188ff0e-b381-5769-a848-a9abfb95f7e2 |  | textbox | Site Address
text | 1232c5d6-997c-58cf-ade2-4e6d04e87430 |  | textbox | Main Contractor
text | 9447a2d5-f114-52c9-8a70-868bb5119862 |  | textbox | QS and Contact Info
text | 2726b989-21a3-5593-8dd3-763c9ac4f5d8 |  | textbox | Project Manager and Contact Info
text | 5ff884ed-c59b-5e36-9b5f-34d19074db4c |  | textbox | Site Manager and Contact Info
text | ae8032f3-b71a-5c05-9be3-35f75f681548 |  | textbox | PBI Installer and Contact Info
text | 4ee10446-19a4-5fc1-841e-a3b51a3df736 |  | textbox | PBI PM
checkpoint-no-status |  |  | checkpoint | System information:
checkpoint-no-status |  |  | checkpoint | SSP Attached
checkpoint-no-status |  |  | checkpoint | Task Analysis Attached
checkpoint-no-status |  |  | checkpoint | Relevant Drawings Attached
checkpoint-no-status |  |  | checkpoint | Pre-Start Photos