## QA Folder Structure
QA Folder Structure | Enviro Systems | Checklists
Enviro 700X - Balconies
REFER TO CONQA WEB APP - ALREADY SET UP |  |  | Enviro 700X - Balcony Set Downs & Window Reveals
Enviro 200P Ultra - Internal Wet Areas
Enviro 700X + 250NS

## ITPs Checklists
type | name | values
checklist-flat | Enviro HP1200 + 800 TC
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
holdpoint | Surface Preparation
label | Inspect and confirm surface preparation is suitable to commence works and conforms to project specification & AMS. Record & document.
checkpoint | Check and record concrete age and moisture content meet the requirements of the membrane system.
Label | Record and document
checkpoint | Substrate crack and falls inspection
Label | Prepare substrate to open concrete pores, remove contamination, laitance, raised areas of poured concrete, concrete slurry/residue, form work residue and form work marks. Expose substrate defects and achieve required surface profile.
checkpoint | Detail expansion & construction joints
label | Sealed joints are to be covered with self-adhesive bond breaker tape.
checkpoint | Detail Turn-Ups, penetrations, internal corners and rainwater drains
label | Apply fillets to all turn ups, penetrations, internal corners that are to receive membrane
holdpoint | Confirm the following parameters conform with AMS requirements: Concrete Moisture Content Concrete Temperature Air Temperature Relative Humidity Dew Point Approximate Air Speed Record & document. Check weather forecasts to ensure favorable conditions are expected to continue during the application period.
label | Relative Humidity = < 75% Substrate Temperature = 5°C to 60°C Air Temperature = 4°C to 45°C Relative Humidity = 75% maximum Dew Point = at least 3°C below substrate temperature Approximate Air Speed = less than 10 knots or such that overspray is minimal and wind-blown debris does not occur
checkpoint | Apply Primer
label | Attach photos
checkpoint | Apply membrane
label | Attach photos
chekpoint | Testing
label | Bond Strength = 1.5 MPa minimum One bond test per 50m². If membrane fails bond strength testing, membrane is to be rectified as detailed in AMS
checkpoint | Apply Non-Slip Top Coat to membrane where specified
label | Top Coat to be applied at a calculated average coverage as determined in the project AMS
checkpoint | Testing
label | DFT Testing Results
holdpoint | Final Sign Off
label | Final Sign Off by Site Manager / Foreman
checklist-flat | Enviro HP1200
Label | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint | Batch Number
Label | Record batch number
holdpoint | Surface Preparation
label | Inspect and confirm surface preparation is suitable to commence works and conforms to project specification & AMS. Record & document.
checkpoint | Check and record concrete age and moisture content meet the requirements of the membrane system.
Label | Record and document
checkpoint | Substrate crack and falls inspection
Label | Prepare substrate to open concrete pores, remove contamination, laitance, raised areas of poured concrete, concrete slurry/residue, form work residue and form work marks. Expose substrate defects and achieve required surface profile.
checkpoint | Detail expansion & construction joints
label | Sealed joints are to be covered with self-adhesive bond breaker tape.
checkpoint | Detail Turn-Ups, penetrations, internal corners and rainwater drains
label | Apply fillets to all turn ups, penetrations, internal corners that are to receive membrane
holdpoint | Confirm the following parameters conform with AMS requirements: Concrete Moisture Content Concrete Temperature Air Temperature Relative Humidity Dew Point Approximate Air Speed Record & document. Check weather forecasts to ensure favorable conditions are expected to continue during the application period.
label | Relative Humidity = < 75% Substrate Temperature = 5°C to 60°C Air Temperature = 4°C to 45°C Relative Humidity = 75% maximum Dew Point = at least 3°C below substrate temperature Approximate Air Speed = less than 10 knots or such that overspray is minimal and wind-blown debris does not occur
checkpoint | Apply Primer
label | Attach photos
checkpoint | Apply membrane
label | Attach photos
chekpoint | Testing
label | Bond Strength = 1.5 MPa minimum One bond test per 50m². If membrane fails bond strength testing, membrane is to be rectified as detailed in AMS
holdpoint | Final Sign Off
label | Final Sign Off by Site Manager / Foreman
checkpoint | Batch Number
Label | Record batch number
checkpoint | Substrate crack and falls inspection
Label | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2. Ensure all fixings and joints have been set and junction between wall and floor does not exceed more than 10mm. Ensure Puddle flanges reccessed in concrete.
checkpoint | Substrate crack and falls inspection
Label | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be reffered to engineers for treatment methodolgy. Builder to approve falls on substrate(Min 1:100 outside shower and 1:80 in showers ) prior to application of membrane.
checkpoint | Moisture Content
Label | Note. min. 3 tests per bathroom Enviro Epoxy B-LV up to 6.9% Enviro Prime WB up to 6.9%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
Label | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane. RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
Label | If applying Enviro Epoxy B-LV, thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform. If applying Enviro Prime WB, mix at low speed (400RPM) until thouroghly mixed.
checkpoint | Applying primer
Label | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Application range: 5-40 degrees celcius.
Seal/apply bondbreaker at junctions hob/floor | Apply Enviro Flex Pro to form smooth 12mm flexible cove to all internal corners, penetrations and joints.
Application of 200P ultra | Mix Bucket at low speed( 400RPM) unitl thouroghly mixed. Apply two coats of 200p Ultra to wet area in accordance with Australian Standards Application range 5-40*C
QA Testing | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT to manufacturers instructions. 0.6mm walls 1.0mm floors 3 tests on floor/ 3 tests on walls. 24 hour Flood testing.
holdpoint | Completion of Work Element
checklist-flat | Enviro Epoxy RC / Ultra Tuff
checkpoint | Relevant Australian Standards Checked
label | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Cutting - Make sure that adjoining ends of intersecting waterstop segments are cut extremely straight
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Epoxy Application (1st coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
label | (If no aggregate is required, 1st coat of epoxy can be dilluted with 10% xylene
label | If aggregate is required, broadcast at correct coverage while 1st coat has been applied and is in it's wet state prior to curing
checkpoint | Epoxy Application (2nd Coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured.
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF

## Sheet1 (hidden)
Enviro 700X application
Batch Number
Record batch number of product(s)
Yes | No | N/A
attach photo
Substrate Preparation
Obtain clearance for work to commence.
Yes | No | N/A
Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. Must achieve CSP-1 to CSP-2
Yes | No | N/A
Attach Photos reference of swatch next to substrate
Cracks in substrate
Fill all cracks in substrates wider than 1.0 mm (but not more than 1.6mm) with filler compatible (Enviro-Flex Pro) with the membrane system.
Live cracks or greater than 1.6mm to be referred to engineers for treatment methodology
Yes | No | N/A
Attach photos
Moisture content of susbtrate
3 tests per 15m2 Must be less than 4% and AS4654 (1 and 2). If greater refer to Mirvac for special instruction for change of primer to Hydro-epoxy
Yes | No | N/A
Attach photos of moisture readings( mark area and full shot of area
HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
Ambient temperature and RH (Reading twice a day - every 4 hours)
Mirvac to record temperature and provide reading. Temp must be applicable to membrane application
Yes | No | N/A
Notes of temperature day and time
Mirvac to confirm temperature suitable for application. Sign off
Application of Primer
If using epoxy, Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
yes | No | N/A
If using Enviro 789- Mix at low speed (400RPM) until thouroghly mixed
Yes | No | N/A
Using a brush and roller, apply primer.Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Prime 789 will take around 1-5 hrs @ 20 degrees C (but could be longer depending on ambient temp and RH). Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C (but could be longer depending on ambient temp and RH)
Yes | No | N/A
Attach Photos
Application of sealant to Australian Standard
Apply Enviro Flex Pro to form smooth 12mm flexible cove to all internal corners, penetrations and joints.
Yes | No | N/A
Attach Photos
first coat Application of Enviro-700X
Mix bucket at low speed ( 400RPM) until thouroghly mixed. Record ambient temperature, day and time using a brush for cutting and roller for surface, apply the first coat of 700x. Where membrane is terminated on a building element: Ensure that the termination height is 150mm of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice.
Yes | No | NA
attach photos
second coat application of Enviro- 700X
Allow first coat to fully cured prior to application. Mix bucket at low speed ( 400RPM) until thouroghly mixed. Record ambient temperature, day and time using a brush for cutting and roller for surface, apply the first coat of 700x. Where membrane is terminated on a building element: Ensure that the termination height is 150mm of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice.
Application of 250 N-S Top coat
Allow membrane to fully cured prior to application.Mix bucket at low speed ( 400RPM) until thouroghly mixed.If final coat has been exposed greater than 48 hours, refer to Mirvac for special instructions.Using a brush and roller apply 250 NS as final U.V protection coat. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice.
Yes | No | N/A
attach photos
Protection of Membrane edge
Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Esnure vertical membrane termination junctions are caulked with Enviro FC pro.
Yes | No | N/A
attach photos
QA Testing
Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required
Yes | No | N/A
attach photos
Thickness testing of application to the recommended dft of 1.5mm to manufacturers instructions. 5 tests per 15m2
Yes | No | N/A
Attach photos
24hours flood testing to mark out if applicable
Yes | No | N/A
Attach photos
Holiday/ spark testing of area if flood testing is not applicable
Yes | No | N/A
Attach photos
CLICK HERE TO REQUEST BUILDER SIGN OFF